## Sheet1
Transactions will post to the GC POS # | POS number (has both a GC and reg POS#) | 1556 (21556) | 1640 (21640) | 1641 (21641) | 1642 (21642) | 1643 (21643) | 1644 (21644) | ? | ? | ? | ?
POS # RESORT READINESS APPROVAL & SIGNOFF STATUS |  | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED
| DEPLOYMENT SCHEDULE | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED | NOT INSTALLED
IT Tech to image each POS | POS Imaged | Y | Y | Y | Y | Y | Y
| EMV Type (BlueTooth or hard wired enter model # for each) | Move 5000 | Move 5000 | Lane 7000 | Lane 7000 | n/a | Move 5000
For Guest Connect POS's only | Pass Printer (dedicated, shared, n/a) | Shared | Shared | Dedicated | Dedicated | Shared | n/a
| Close In Printers | n/a | n/a | 1 | 1 | n/a | n/a
| Kmv Enabled | n/a | n/a | n/a | n/a | KMV | n/a
Resort Readiness Testing - Each POS Terminal |  | - | - | - | - | - | - | - | - | - | -
1- Misc Validation |  | - | - | - | - | - | - | - | - | - | -
1a | Go into Intranet and verify that home page is PSS Sharepoint site - https://inside.vailresorts.com/sites/dept/PSS/default.aspx Ignore error message and click "Training Resources" on the leftside menu bar for more resources | [6 empty] | N/A | N/A | N/A | N/A
2 - Guest Connect - Open and Validate Guest Connect information |  | - | - | - | - | - | - | - | - | - | -
2a | Validate Guest Connect opens without errors | [6 empty] | N/A | N/A | N/A | N/A
2b | Ensure you restart the Credit Card Device Integration in Guest Connect thru the Hamburger menu Hamburger Menu > Device Management > Restart
2c | Validate product tiles appear on home screen | [6 empty] | N/A | N/A | N/A | N/A
2d | In "hamburger menu," select Settings and verify " File Image Capture" set to Y | [6 empty] | N/A | N/A | N/A | N/A
3 - Test Payment Options, Boca Printer, Receipt Printer and Cash Drawer |  | - | - | - | - | - | - | - | - | - | -
3a | Create or select a test customer profile. | [6 empty] | N/A | N/A | N/A | N/A
3b | Select a ticket product and do not attach to customer This is in order to generate paper ticket. If no Boca printer, select product PHC#164567 and attach customer. | [6 empty] | N/A | N/A | N/A | N/A
3c | Validate default payment method. | [6 empty] | N/A | N/A | N/A | N/A
3d | Test and validate all forms of credit card (Visa, Discover, Amex)
3e | Validate other payment methods are available. Sell ticket to cash. | [6 empty] | N/A | N/A | N/A | N/A
3f | Verify receipt prints and is accurate. (Only if receipt printer) and is accurate. Email receipt when no receipt printer | [6 empty] | N/A | N/A | N/A | N/A
3g | Validate cash drawer opens ONLY if connected to guest connect, otherwise not applicable. Resorts are cashless, so no cash drawes to be installed - validate with PC tech | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3h | Verify paper ticket prints and date on ticket is correct. (Keep ticket for step 8). ONLY when Boca Printer is available |  |  |  |  | N/A |  | N/A | N/A | N/A | N/A
4 - Test Loading of Ticket Media |  | - | - | - | - | - | - | - | - | - | -
4a | Add a new ticket product to test customer's transaction cart. | [6 empty] | N/A | N/A | N/A | N/A
4b | Scan unused ticket media and validate it loads to customer in cart. Sell to cash. (Keep media card for step 8). | [6 empty] | N/A | N/A | N/A | N/A
5 - Test Credit Card Swipe and EMV device |  | - | - | - | - | - | - | - | - | - | -
5a | Attach test customer to transaction cart. | [6 empty] | N/A | N/A | N/A | N/A
5b | Add "OptIn" $1 donation product to cart. | [6 empty] | N/A | N/A | N/A | N/A
5c | With INT credit card payment method selected, swipe credit card using card reader. | [6 empty] | N/A | N/A | N/A | N/A
5d | Delete payment, then select INT credit card again. Use EMV device tp process payment. | [6 empty] | N/A | N/A | N/A | N/A
5e | Validate transaction processes to credit card. | [6 empty] | N/A | N/A | N/A | N/A
6 - Test Season Pass Printer, Defer media print, and Camera |  | - | - | - | - | - | - | - | - | - | -
6a | Attach test customer to transaction cart. | [6 empty] | N/A | N/A | N/A | N/A
6b | Sell an Epic Pass product to cash. | [6 empty] | N/A | N/A | N/A | N/A
6c | During purchase process, validate defer media option is available. | [6 empty] | N/A | N/A | N/A | N/A
6d | Validate camera is working by taking pass photo. | [6 empty] | N/A | N/A | N/A | N/A
6e | Verify Season Pass Zebra printer prints media with photo. (Keep media card for step 8). | [6 empty] | N/A | N/A | N/A | N/A
7 - Test Barcodes that were printed, the Barcode reader and Scan Settings |  | - | - | - | - | - | - | - | - | - | -
7a | In Scan Tools setting in "hamburger menu", validate the default scan location is resort specific (TBD) | [6 empty] | N/A | N/A | N/A | N/A
7b | Validate all resort specific scan locations are available. | [6 empty] | N/A | N/A | N/A | N/A
7c | Scan test paper ticket, ticket media and season pass to test barcode reader and validate barcodes printed correctly. | [6 empty] | N/A | N/A | N/A | N/A
8 - Test the Zebra Label Printer (if applicable - ski school locations only) |  | - | - | - | - | - | - | - | - | - | -
8a | In "hamburger menu," select Print Academy Labels and enter test customer pass number. Are ALabels being implemented? Which POS locations sell SRS? | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8b | Verify that label prints with test customer information. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 - Refund Products |  | - | - | - | - | - | - | - | - | - | -
9a | Refund all transactions completed in testing. | [6 empty] | N/A | N/A | N/A | N/A
10 - Complete a POS Close |  | - | - | - | - | - | - | - | - | - | -
10a | In "hamburger menu," select POS Close. Run validation an ensure in Balance. If in Balance, complete a final close. If not in Balance, contact Integration BA | [6 empty] | N/A | N/A | N/A | N/A
10b | Once POS successfully closed, open Application Manager > Report Shell, select Location Close Reports > Closer Reorts run and print POS Close Combined Report. | [6 empty] | N/A | N/A | N/A | N/A
11 - Validate all Products |  | - | - | - | - | - |  |  |  | - | -
11a | Ensure all expected Products and Pricing (or Price Changeable is active) are active for Phase I (no inventory)
12 - self check-In tests |  | - | - | - | - | - | - | - | -
12a | TBD | N/A | N/A | N/A | N/A | N/A | N/A
| TBD | N/A | N/A | N/A | N/A | N/A | N/A
| Validate Contract Printed at expected area | N/A | N/A | N/A | N/A | N/A | N/A
| Validate Contract contains all expected data | N/A | N/A | N/A | N/A | N/A | N/A

## Sheet2
POSNumber | POSImaged | EMVType | PassPrinter | CloseInPrinter | KMVEnabled | 1a Go into Intranet and verify that home page is PSS Sharepoint site - https://inside.vailresorts.com/sites/dept/PSS/default.aspx Ignore error message and click "Training Resources" on the leftside menu bar for more resources | 2 - Guest Connect - Open and Validate Guest Connect information | 2a Validate Guest Connect opens without errors | 2b Validate Guest Connect opens without errors | 2c Validate product tiles appear on home screen | 2d In "hamburger menu," select Settings and verify " File Image Capture" set to Y | 3 - Test Payment Options, Boca Printer, Receipt Printer and Cash Drawer | __PowerAppsId__
1556 (21556) | Y | Move 5000 | Shared | n/a | n/a | Pass | Pass | WIP |  |  |  | N/A | UUtk1m-CeTA
1640 (21640) | Y | Move 5000 | Shared | n/a | n/a | [6 empty] | N/A | uxJzCnm_w_4
1641 (21641) | Y | Lane 7000 | Dedicated | 1 | n/a | [6 empty] | N/A | KuxXQW8ggiI
1642 (21642) | Y | Lane 7000 | Dedicated | 1 | n/a | Drop2 | Drop2 | Drop31 |  |  |  | N/A | OKpNel60lXo
1643 (21643) | Y | n/a | Shared | n/a | KMV | [6 empty] | N/A | t14kvwHzde0
1644 (21644) | Y | Move 5000 | n/a | n/a | n/a | [6 empty] | N/A | G1BehsjTzxc