## WBS DictionaryDeliverables
Deliverables/Work Packages in BOLD |  |  | Owner | Description/Activities/Notes | Due Date | Document 1 | Document 2 | Document 3 | Physical and HR resources | Assumptions/Constraints | Quality Requirements | Acceptance Criteria
1. Viz Upgrade |  |  |  | High Level Scope - MSE to 5.1.3 (Engines, Gatewways, Preview Engines) - Pilot v6 to 8.4 upgrade to VM (Pre build) Plug ins backwards compatible - OS to Win 10/Server 2016 - Domain Change to cbc-rc Enough to Upgrade to address Pilot Lag on Windows 10 and Migrate to CBC-RC Domain - stay aligned with SRC when they move to NMRC - RFP for replacement Graphic system expected 1-2 years |  | Version Control | English Diagram | Viz Overview
1.1 Preparation
|  | 1.1.1 Inventory of English devices |  |  |  | Version Control
|  | 1.1.2 Determine versions |  | - Windows 10 worktations - Windows 2016 Servers - MSE 5.1.3 - Pilot 8.4 - Viz Engine TBD - Trio - TBD - Graphic Hub WIndows 2016 (determine if version needs to be upgraded with OS, 3.4?)
|  | 1.1.3 Determine requirements for English Vizrt Updates |  | - Vizrt will not support 3.8 2016 on current hardware, only support 3.9+ on 2016 - There is an issue with the qualaified 3.9+ Video Driver. Woud require a replacement video card. - We will move forward with 3.8 2016 and Simon will negotiate support of this combination
|  | 1.1.4 Engine Preparation |  | - Image existing servers for Backup - BIOS - Firware Updates - Video card
1.1.5 Prepare French system for Domain Test
| 1.2 English Vizrt Updates |  |  | - MSE 5.1.3 - Prior to VCP, - Server 2016 - We have tested CR56 Windows Server 2016 with Viz Engine 3.8 on existing hardware. At this stage, we have one machine running in production as a test. Results still pending. - New Domain - Vizrt will not support 3.8 2016 on current hardware, only support 3.9 on 2016 - There is an issue with the qualaified 3.9 Video Driver. May require a replacement video card - Artists Windows 10
| 1.3 VCP/Content Pilot |  |  | - Application Server and Oracle DB - Stores Data Elements and Templates which are created from Scenes - Linux, no AD but DNS reliant - VCP Slow on Windows 10, VCP 8.4. will fix - Built Oracle lab on VM, great performance during stress testing - Requires MSE 5.1.3 - VM - Oracle Schema 8.3 - iNEWS plug in 8.5 - Build VM and test - Oracle cluster has been built
|  | 1.3.1 VCP DB server to 2016 VM |  | - VCP Slow on Windows 10, VCP 8.4. will fix, VM - DB v8.4 on Oracle Cluster, Remove from Domain - Viz doesn't suggest moving DB to VM for DR. Joanna/Anjana advise VM will provide true DR. Simon discussing with Viz |  | Version Control
|  | 1.3.2 VCP Application Server to 2016 VM |  | - Going to VM is particularly attractive to us as it will allow us to include Commvault and have our Disaster Recovery in the opposite city's data centre. - Remove from Domain |  | Version Control
|  | 1.3.3 Client Plug in |  | - Trio - Pushed out 2 weeks prior to upgrade to iNEWS workstations
| 1.4 VizOne to new Domain |  |  | - Media Database - English VizOne does not have any planned update or move to VM at this stage. Looking for recommendations from Viz - Formerly known as VME - Ron M to provide quote to Simon for professional services
| 1.5 Move Graphics Hub to 2016 Server |  |  | - Server 2016/version TBD - Stores Scenes - Cluster, Main/Backup - Populates templates, geometry. - Replicates to regions - Not urgent
| 1.6 Artists |  |  | - Create Scenes - Need to verify if Z420 will run Windows 10 - After Graphics hubs verified

## Activity List
Activity | Assigned to | Deadline | Start Date | End Date | Completed | Vimbiz SR | Notes | Documents | JIRA
1.1.1 Inventory of English devices
Populate the missing information in Version Control | Frank/Laura |  |  |  | yes |  |  | Version Control | 18
1.1.2 Determine versions
Test z420 Artists on Windows 10 | [8 empty] | 24
Prepare a Graphics Hub with 2016 for testing | Laura |  |  |  | wip |  | Our Dell R320 servers don't fully meet the minimum specs outlined by Viz in the 3.4.2 system requirements. Are we still planning to virtualize ETV Graphic Hubs ? - RAM and CPU minimum pasted above. - Our Dell R320 Hub hardware is currently at 1.8GHz Xeon E5-2403 with 4 cores. There is 8GB of 1333 DDR3 RAM. So # of cores and RAM type/speed is under spec'd on our current hardware. |  | 147
Test Latest Graphic Hub Version w/2016 | Simon | [5 empty] | Need Graphics designer to test |  | 25
Test 3.11.1 on ML350 with M2000 card | Laura |  |  |  | yes |  | Tested successfully. z840s have M2000 |  | 21
Test 3.11.1 on ML350 with K2000 card | Laura |  |  |  | yes |  |  |  | 22
Find P2000 card | Simon | [7 empty] | 41
Test 3.11.1 on ML350 with P2000 card | Laura | [7 empty] | 40
Schedule Control 56 3.11.1 install | Simon |  |  |  | yes |  |  |  | 148
Upgrade Control 56 with 3.11.1 w/K2000 2016 | Laura |  |  |  | yes |  |  |  | 148
Test Control 56 with 3.11.1 w/K2000 Windows 2016 | Laura |  | 2020-08-25 |  |  |  | Upgraded Aug 26 |  | 149
Upgrade Lab with 3.14. w/K2000 2016 | Laura |  |  |  | yes
Schedule Control 56 3.14.4 install | Simon |  |  |  | yes
Upgrade Control 56 with 3.14. w/K2000 2016 | Laura |  |  |  | yes |  | - upgrade was very finicky but working now. - Initially both machines would not detect the Matrox card after uninstalling reinstalling updated drivers and software despite doing it in the correct order. - I had to uninstall/reinstall both again. - then the trio channels did not sync with the rest of the control room |  | 150
Determine Engine Hardware/Version configuration | Simon |  |  |  | wip |  | - VizArtist Bundle 3.14.4 nVidia Quadro 442.19 Matrox 10.1.1 VCP 6.0.0.21291 Datapool 2.13.4 - Trio ad: TrioClient 3.2.3 MSE 5.1.3 Instead of VCP install Oracle bit runtime clien |  | 23
1.1.3 Determine requirements for English Vizrt Updates
Inventory Graphics cards in service | Frank |  |  |  | wip |  |  | Version Control | 19
Inventory available replacement cards | Frank |  |  |  | wip |  |  |  | 151
Determine required Hardware purchases | Simon
1.1.4 Engish Vizrt Updates - Preparation
Calgary | [8 empty] | 26
Charlotttetown | [8 empty] | 27
Edmonton | [8 empty] | 28
Fredericton | [8 empty] | 29
Halifax | [8 empty] | 30
Montreal | [8 empty] | 31
Ottawa | [8 empty] | 32
Regina | [8 empty] | 33
St. John's | [8 empty] | 34
Toronto | [8 empty] | 35
Vancouver | [8 empty] | 36
Windsor | [8 empty] | 37
Winnipeg | [8 empty] | 38
Yellowknife | [8 empty] | 39
1.2 English Vizrt Updates (Site) - Separate into items
Calgary
Charlotttetown
Edmonton
Fredericton
Halifax
Montreal
Ottawa
Regina
St. John's
Toronto
Vancouver
Windsor
Winnipeg
Yellowknife
1.3.1 VCP Oracle DB serer to 2016 VM
Build and prep DB on new VM | Joanne/Anjana
Schedule Test Copy |  |  |  |  | yes |  | Wed Sept 16th 02:30-04:00
Test Copy DB to VM |  |  | Wed Sept 16
Test
Sign off from Production
Migrate to new DB
1.3.2 VCP Application Server to 2016 VM
Build VM
Test VM
Sign off from Production
Mirate to new Server
1.3.3 VCP Client Plug in
Push update to iNEWS clients
1.4 VizOne to new Domain
1.5 Move Graphics Hub to 2016 Server | [6 empty] | Under Site in Jira
1.6.2 Move Artists to cbc-rc domain | [6 empty] | Under Site in Jira

## Issue Log
Issue | Description | Status | Reported By | Assigned to | Date Reported | Date Resolved
Viz 3.8 not supported on 2016 | Viz does not support Server 2016 w/3.8. Current Video Card driver not qualified on v3.9+, would require replacement video card. We will move forward with 2016/3.8. 56 has been running with this combination for several weeks. | Open | Viz | Simon | 2020-07-24
Vizrt does not recommend running VCP Oracle DB on VM | Concerns over Availability/DR. Anjana and Joanna advise that VM will provide true DR. CBC will move forward with the deployment in VM for the Oracle DB based on the specs provided prior to the call. To help VizRT support, CBC and VizRT will work together to document the move to VM including replication processes. Documentation will be kept in the confluence knowledge base at VizRT. Current support contract should cover this task. VizRT to send commands and process for export/import of the existing prod DB VizRT to return information on what impact there will be to modify the listener to use any other port than the default 1521. | Closed | Viz | Simon | 2020-07-24 | 2020-08-25

## Stakeholders
Name | Role | Contact
Simon | Lead Engineer/PM
Paul Stoikoff | Engineer/PM
Adam V | Engineer/PM
Patrick | English System Manager
Stanley | French System Manager
Denis B | French TMS Project Coord
JC | English TMS Project Coord
Khalid | French System Admin
Laura | System Admin
Frank | System Admin
Steve Papadakis | Viz Account Manager
Ron Miller | Viz Solutions Architect
Ata | Viz Support
Barry Henson | Viz PM
Cameron Villers | Viz System Engineer
Anders Levin | Viz BD Translation Expert

## Vizrt data Power BI
Date Week | Region | Deliverable | Total Activties Required "Total" | Total Activies Completed "Done" | Total Activties Remaining "To do" | Weight | Deliverable 70% - English Vizrt Updates - Engine Image (MSE, 2016, NEW Domain, BIOS and Firmware updates), MSE on Gateway, Artists 10% - VCP DB to VM -Move 2 Pilot DB and Application servers to VM 10% - VizONE Migrate to new Domain - Migrate the VizOne server to the cbc-rc domain 10% - Graphics Hub - Upgrade Graphics Hub servers to Windows 2016
2020-09-07 | Calgary | English Vizrt Updates | 1 | 1 | 0 | 70
2020-09-07 | Calgary | Graphics Hub | 1 | 1 | 0 | 10
2020-09-07 | Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
2020-09-07 | Charlottetown | Graphics Hub | 1 |  | 1 | 10
2020-09-07 | Edmonton | English Vizrt Updates | 1 |  | 1 | 70
2020-09-07 | Edmonton | Graphics Hub | 1 |  | 1 | 10
2020-09-07 | Fredericton | English Vizrt Updates | 1 |  | 1 | 70
2020-09-07 | Fredericton | Graphics Hub | 1 |  | 1 | 10
2020-09-07 | Halifax | English Vizrt Updates | 5 | 5 | 0 | 70
2020-09-07 | Halifax | Graphics Hub | 1 | 1 | 0 | 10
2020-09-07 | Montreal | English Vizrt Updates | 3 |  | 3 | 70
2020-09-07 | Montreal | Graphics Hub | 2 |  | 2 | 10
2020-09-07 | Ottawa | English Vizrt Updates | 7 |  | 7 | 70
2020-09-07 | Ottawa | Graphics Hub | 1 |  | 1 | 10
2020-09-07 | Regina | English Vizrt Updates | 1 |  | 1 | 70
2020-09-07 | Regina | Graphics Hub | 1 |  | 1 | 10
2020-09-07 | St. John's | English Vizrt Updates | 3 |  | 3 | 70
2020-09-07 | St. John's | Graphics Hub | 1 |  | 1 | 10
2020-09-07 | Toronto | English Vizrt Updates | 62 |  | 62 | 70
2020-09-07 | Toronto | VCP DB to VM | 2 | 1 | 1 | 10
2020-09-07 | Toronto | Graphics Hub | 5 |  | 5 | 10
2020-09-07 | Toronto | VizONE Migrate to new Domain | 1 | 1 | 0 | 10
2020-09-07 | Vancouver | English Vizrt Updates | 4 |  | 4 | 70
2020-09-07 | Vancouver | Graphics Hub | 1 |  | 1 | 10
2020-09-07 | Windsor | English Vizrt Updates | 1 |  | 1 | 70
2020-09-07 | Windsor | Graphics Hub | 1 |  | 1 | 10
2020-09-07 | Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
2020-09-07 | Winnipeg | Graphics Hub | 1 |  | 1 | 10
2020-09-07 | Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
2020-09-07 | Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10
| Calgary | English Vizrt Updates | 1 |  | 1 | 70
| Calgary | Graphics Hub | 1 |  | 1 | 10
| Charlottetown | English Vizrt Updates | 1 |  | 1 | 70
| Charlottetown | Graphics Hub | 1 |  | 1 | 10
| Edmonton | English Vizrt Updates | 1 |  | 1 | 70
| Edmonton | Graphics Hub | 1 |  | 1 | 10
| Fredericton | English Vizrt Updates | 1 |  | 1 | 70
| Fredericton | Graphics Hub | 1 |  | 1 | 10
| Halifax | English Vizrt Updates | 5 |  | 5 | 70
| Halifax | Graphics Hub | 1 |  | 1 | 10
| Montreal | English Vizrt Updates | 3 |  | 3 | 70
| Montreal | Graphics Hub | 2 |  | 2 | 10
| Ottawa | English Vizrt Updates | 7 |  | 7 | 70
| Ottawa | Graphics Hub | 1 |  | 1 | 10
| Regina | English Vizrt Updates | 1 |  | 1 | 70
| Regina | Graphics Hub | 1 |  | 1 | 10
| St. John's | English Vizrt Updates | 3 |  | 3 | 70
| St. John's | Graphics Hub | 1 |  | 1 | 10
| Toronto | English Vizrt Updates | 62 |  | 62 | 70
| Toronto | VCP DB to VM | 2 |  | 2 | 10
| Toronto | Graphics Hub | 5 |  | 5 | 10
| Toronto | VizONE Migrate to new Domain | 1 |  | 1 | 10
| Vancouver | English Vizrt Updates | 4 |  | 4 | 70
| Vancouver | Graphics Hub | 1 |  | 1 | 10
| Windsor | English Vizrt Updates | 1 |  | 1 | 70
| Windsor | Graphics Hub | 1 |  | 1 | 10
| Winnipeg | English Vizrt Updates | 1 |  | 1 | 70
| Winnipeg | Graphics Hub | 1 |  | 1 | 10
| Yellowknife | English Vizrt Updates | 3 |  | 3 | 70
| Yellowknife | Graphics Hub | 1 |  | 1 | 10

## Power BI option (hidden)
Deliverable/Region | Total Activties Required "Total" | Week 1 | Week 2 | Week 3 | Total Activies Completed "Done" | Total Activties Remaining "To do" | Weight | Deliverable 70% - English Vizrt Updates - Engine Image (MSE, 2016, NEW Domain, BIOS and Firmware updates), MSE on Gateway, Artists 10% - VCP DB to VM -Move 2 Pilot DB and Application servers to VM 10% - VizONE Migrate to new Domain - Migrate the VizOne server to the cbc-rc domain 10% - Graphics Hub - Upgrade Graphics Hub servers to Windows 2016
VCP DB to VM |  |  |  |  | 0 | 0
Toronto | 2 |  | 2 |  | 2 | 0
VizONE to New Domain |  |  |  |  | 0 | 0
Toronto | 1 |  |  | 1 | 1 | 0
English Vizrt Updates |  |  |  |  | 0 | 0
Calgary | 2 | 2 |  |  | 2 | 0 | 70
Charlottetown | 2 | 0 | 0 | 1 | 1 | 1 | 70
Edmonton | 2 |  |  |  | 0 | 2 | 70
Fredericton | 2 |  |  |  | 0 | 2 | 70
Halifax | 6 |  |  |  | 0 | 6 | 70
Montreal | 5 |  |  |  | 0 | 5 | 70
Ottawa | 8 |  |  |  | 0 | 8 | 70
Regina | 2 |  |  |  | 0 | 2 | 70
St. John's | 4 |  |  |  | 0 | 4 | 70
Toronto | 66 |  |  |  | 0 | 66 | 70
Vancouver | 5 |  |  |  | 0 | 5 | 70
Windsor | 2 |  |  |  | 0 | 2 | 70
Winnipeg | 2 |  |  |  | 0 | 2 | 70
Yellowknife | 4 |  |  |  | 0 | 4 | 70
Graphics Hubs |  |  |  |  | 0
Calgary |  |  |  |  | 0
Charlottetown |  |  |  |  | 0
Edmonton |  |  |  |  | 0
Fredericton |  |  |  |  | 0
Halifax |  |  |  |  | 0
Montreal |  |  |  |  | 0
Ottawa |  |  |  |  | 0
Regina |  |  |  |  | 0
St. John's |  |  |  |  | 0
Toronto |  |  |  |  | 0
Vancouver |  |  |  |  | 0
Windsor |  |  |  |  | 0
Winnipeg |  |  |  |  | 0
Yellowknife |  |  |  |  | 0
0

## Sheet10 (hidden)
Date | Site | Engine Updates Required | Engine Updates Completed | VCP Servers | VCP Complete | VizONE Domain | VizONE Domain Complete | Graphics Hubs Required | Graphics Hubs Complete | Total Activities Required | Total Activities Completed | % Complete
2 | Calgary | 2 | 0 | [6 empty] | 5 | 0 | 0%
3 | Charlotttetown | 2 | 0 | [6 empty] | 2 | 0 | 0%
4 | Edmonton | 2 | 0 | [6 empty] | 2 | 0 | 0%
5 | Fredericton | 2 | 0 | [6 empty] | 2 | 0 | 0%
6 | Halifax | 6 | 0 | [6 empty] | 6 | 0 | 0%
7 | Montreal | 5 | 0 | [6 empty] | 5 | 0 | 0%
8 | Ottawa | 8 | 0 | [6 empty] | 8 | 0 | 0%
9 | Regina | 2 | 0 | [6 empty] | 2 | 0 | 0%
10 | St. John's | 4 | 0 | [6 empty] | 4 | 0 | 0%
11 | Toronto | 66 | 0 | 2 | 0 | 1 | 0 |  |  | 69 | 0 | 0%
12 | Vancouver | 5 | 0 | [6 empty] | 5 | 0 | 0%
13 | Windsor | 2 | 0 | [6 empty] | 2 | 0 | 0%
14 | Winnipeg | 2 | 0 | [6 empty] | 2 | 0 | 0%
15

## Dashboard Data (hidden)
Site | English Vizrt Updates Required | English Vizrt Updates Completed | VCP Servers | VCP Complete | VizONE Domain | VizONE Domain Complete | Graphics Hubs Required | Graphics Hubs Complete | Total Activities Required | Total Activities Completed | % Complete
Calgary | 2 | 0 |  |  |  |  | 1 |  | 6 | 0 | 0%
Charlotttetown | 2 | 0 |  |  |  |  | 1 |  | 3 | 0 | 0%
Edmonton | 2 | 0 |  |  |  |  | 1 |  | 3 | 0 | 0%
Fredericton | 2 | 0 |  |  |  |  | 1 |  | 3 | 0 | 0%
Halifax | 6 | 0 |  |  |  |  | 2 |  | 8 | 0 | 0%
Montreal | 5 | 0 |  |  |  |  | 1 |  | 6 | 0 | 0%
Ottawa | 8 | 0 |  |  |  |  | 1 |  | 9 | 0 | 0%
Regina | 2 | 0 |  |  |  |  | 1 |  | 3 | 0 | 0%
St. John's | 4 | 0 |  |  |  |  | 1 |  | 5 | 0 | 0%
Toronto | 66 | 0 | 2 | 0 | 1 | 0 | 2 |  | 71 | 0 | 0%
Vancouver | 5 | 0 |  |  |  |  | 1 |  | 6 | 0 | 0%
Windsor | 2 | 0 |  |  |  |  | 1 |  | 3 | 0 | 0%
Winnipeg | 2 | 0 |  |  |  |  | 1 |  | 3 | 0 | 0%
Yellowknife | 4 | 0 |  |  |  |  | 1 |  | 5 | 0 | 0%
[9 empty] | 134 | 0 | 0%
Overal Project Completion
Item | Weight
English English Vizrt Updates | 70 | Engine Image (MSE, 2016, NEW Domain, BIOS and Firmware updates), MSE on Gateway, Artists
VCP DB to VM | 10
VizONE Migrate to new Domain | 10
Graphics Hub | 10