## Sheet 2
JOB NUMBER | Development | PROJECT | ADDRESS | Latitude | Longitude | PROJECT MANAGER | SUPERINTENDENT | Builders Risk Expires | Status | Entity Owning | Deal Structure | LOI / Lease Date | Close Date | Lender | Permit Submitted Date | Permit Approval Date | Permit Approval Time Frame | Construction Value | Start Date | Completion Date | Duration in Months | CO Date | Punchlist Complete | Lessons Learned
Peggy | Peggy | Peggy | Jenna |  |  | Brandon | Brandon | Peggy | Brandon | Jenna | Jenna | Jenna | Jenna | Jenna | Nolan | Nolan | Nolan | Trevor | Dion | Dion | Dion | Dion | Dion | Branonn
OK2019 | Santa Fe | Santa Fe Development | 100 Southwest 134th Street, OKC, OK 73170 |  |  | Adam England | Josh Williams |  | Construction | TBD | JV | N/A | 2020-10-11 |  | N/A | 2021-04-16 | N/A | 1000000 | 2021-05-03 | 2022-01-10 | 9
OK2025 | Santa Fe | Autism in Motion - Sante Fe Dev. | 112 Southwest 134th Street, OKC, OK 73170 | 35.3343 | -97.5144 | Adam England | Josh Williams |  | PreConstruction | AG AIM OK RE Holdings, LLC | JV | 2020-04-22 | Pending |  | 2021-01-05 | 2021-04-16 | 101 | 975000 | 2021-05-03 | 2021-12-29 19:12 | 8
OK2033-1 | Santa Fe | Santa Fe Shell - Santa Fe Dev. | 112 Southwest 134th Street, OKC, OK 73170 | 35.3343 | -97.5144 | Adam England | Josh Williams |  | PreConstruction | TBD | JV | N/A | Pending |  | 2021-03-29 | 2021-08-15 | 139 | 900 | 2021-07-05 | 2022-01-01 14:24 | 6
OK2033-2 | Santa Fe | Old School Bagel - Santa Fe Dev. | 112 Southwest 134th Street, OKC, OK 73170 | 35.3343 | -97.5144 | Adam England | Josh Williams |  | PreConstruction | TBD | JV | N/A | Pending |  | 2021-06-20 | 2021-08-15 | 10 | 175000 | 2021-09-14 | 2022-03-13 14:24 | 6
OK2016 | N/A | One Core Health | 100 NE 85th Street, OKC, OK 73114 | 35.5572 | -97.5107 | Bob Solomon | Dion Hall / Anthony Fox | 2021-10-30 | Construction | TAG OneCore RE Holdings, LLC | JV | 2020-02-24 | 2020-09-25 | Interbank | 2020-08-11 | 2020-11-12 | 93 | 13407911 | 2020-10-15 | 2021-12-01 | 13.6877
OK1936-TI | N/A | Dr. Fischer TI | 720 West 71St Street S, Tulsa, OK 74132 | 36.0606 | -96.0003 | Chris Goldsmith | Gary Clinton |  | Construction | AG Medical RE Holdings, LLC | GMP | 2019-08-02 | 2019-12-09 |  | 2021-03-24 | 2021-04-16 | 23 | 177819 | 2021-05-01 | 2021-09-07 | 4.2857
OK2008 | N/A | Dr. Mark Gaches, DDS - Owasso | 11492 N. 137th E. Ave., Owasso, OK | 36.2887 | -95.8221 | Chris Goldsmith | Gary Clinton | Processing | Construction | AG Hi Point RE Holdings, LLC | JV | 2019-09-23 | 2020-11-17 | First State Bank | 2020-08-28 | 2021-03-05 | 189 | 700000 | 2021-04-04 | 2021-09-27 | 3.4
OK2014 | N/A | Clark Shell | 7877 E 71st South., Tulsa, OK 74133 | 36.0609 | -95.7331 | Chris Goldsmith | Gary Clinton | 2021-11-23 | Construction | AG Clark RE Holdings, LLC | JV | N/A | 2020-11-25 | Oklahoma Fidelity Bank | 2020-10-16 | 2021-02-19 | 126 | 1375000 | 2021-03-01 | 2021-12-27 | 10
OK2014-1 | N/A | Clark Shell - Dr. Pfeffer | 7877 E 71st South Ste A, Tulsa, OK 74133 | 36.0609 | -95.7331 | Chris Goldsmith | Gary Clinton | 2021-11-23 | Construction | AG Clark RE Holdings, LLC | GMP | 2019-09-23 | 2020-11-25 | Oklahoma Fidelity Bank | 2020-12-03 | 2021-03-25 | 112 | 650000 | 2021-03-29 | 2021-11-24 19:12 | 8
OK2014-2 | N/A | Clark Shell - Enhance DDS | 7877 E 71st South Ste B., Tulsa, OK 74133 | 36.0609 | -95.7331 | Chris Goldsmith | Gary Clinton | 2021-11-23 | Construction | AG Clark RE Holdings, LLC | JV | N/A | 2020-11-25 | Oklahoma Fidelity Bank | 2020-12-03 | 2021-03-25 | 112 | 400000 | 2021-03-29 | 2021-11-24 19:12 | 8
OK2032-4 | N/A | Cross Roads - Old School Bagel-TI | 1171 N. 38th Street, Broken Arrow, OK 74014 | 36.0624 | -95.7424 | Chris Goldsmith | Gary Clinton |  | PreConstruction | Broken Arrow Retail, LLC | JV | N/A | 2021-04-13 |  | 2021-06-10 | 2021-06-29 | 19 | 300000 | 2021-07-29 | 2021-11-26 09:36 | 4
OK2011-2 | N/A | Mustang - Old School Bagel | 1709 S Mustang Rd., Mustang, OK 73064 Ste D | 35.4478 | -97.7251 | Wes Gaddy | Josh Williams | 2021-07-24 | Construction | TAG Mustang RE Holdings, LLC | JV | N/A | 2020-05-20 | Southwest National Bank of Weatherford |  | 2020-08-19 |  | 165000 | 2020-11-01 | 2021-03-31 | 4.9834
OK2038 | N/A | Dr. Farmer - Wonga Corner | 1152 W. Douglas Midwest City, OK | 35.4385 | -97.4063 | Wes Gaddy | Daniel Frary |  | Construction | Wonga Corner, LLC | JV | 2021-02-18 | Closed |  | 2021-02-26 | 2021-03-17 | 19 | 355000 | 2021-03-17 | 2021-07-29 | 3
TX1901 | N/A | Dr. Dyer - Sequoia Spur | 115 Shell Rd, Georgtown, TX 78633 | 30.6844 | -97.7174 | Wes Gaddy | James Stephenson | 2021-10-03 | Construction | Sequoia Spur RE Holdings, LLC | JV | N/A | 2019-05-17 | American Nation Bank |  | 2020-07-06 |  | 1750000 | 2020-11-01 | 2021-10-15 | 11.5615
TX1903 | N/A | Ramon Franklin Warehouse | 1308 Corporate Drive East, Arlinton, TX 76006 | 32.7702 | -97.0656 | Wes Gaddy | Roger Harris / James Stephenson |  | Construction | AG RF RE Holdings, LLC | JV | N/A | 2019-12-20 | American Nation Bank | 2020-12-09 | 2021-01-27 | 49 | 1125000 | 2021-02-01 | 2021-11-01 | 6.7
TX2001 | N/A | Dr. Lippian - Texarkana | 5220 Gibson Ln., Texarkana, TX 75501 | 33.4583 | -94.1107 | Wes Gaddy | Roger Harris | 2022-01-25 | Construction | King Fisher Holdings, LLC | GMP | 2020-09-21 | 2020-10-30 | Great Plains National Bank | 2020-09-30 | 2020-12-29 | 90 | 1650000 | 2021-01-28 | 2021-10-21 | 8
TX2005 | McKinney | McKinney Development | Virginia and Ridge Road, McKinney, TX |  |  | Wes Gaddy | TBD |  | PreConstruction | TBD | JV | 2020-08-04 | TBD |  | 2021-06-10 | 2021-10-01 | 113 | 600000 | 2022-02-01 | 2022-09-29 19:12 | 8
TX2008-1 | McKinney | Dr. Barabra Lee - McKinney Development | McKinney, TX |  |  | Wes Gaddy | TBD |  | PreConstruction | TBD | JV | 2020-08-04 |  |  | 2021-07-09 | 2021-10-01 | 84 | 750000 | 2022-02-01 | 2022-09-29 19:12 | 8
TX2006-1 | N/A | Sunnyvale Shell | Sunnyvale, TX |  |  | Kevin Trosper | TBD |  | PreConstruction | TBD | JV |  | 2021-04-12 | American Nation Bank | 2021-06-15 | 2021-07-30 | 45 | 1736318 | 2021-08-09 | 2022-04-06 19:12 | 8 |  |  |  | Need to be doing earthwork by 8-1-21
TX2006-2 | N/A | Sunnyvale Shell - Dr Luna | Lot 6 South of Hwy 80 and East of S. Collins RD, Sunnyvale, TX |  |  | Wes Gaddy | TBD |  | PreConstruction | TBD | JV | 2020-09-04 | 2021-04-12 | American Nation Bank | 2021-06-15 | 2021-08-09 | 55 | 376000 | 2021-08-09 | 2022-04-06 19:12 | 8
TX2006-3 | N/A | Sunnyvale Shell - Dr. Rohani | Lot 6 South of Hwy 80 and East of S. Collins RD, Sunnyvale, TX |  |  | Wes Gaddy | TBD |  | PreConstruction | TBD | JV | 2020-09-04 | 2021-04-12 | American Nation Bank | 2021-07-09 | 2021-08-23 | 45 | 376000 | 2021-08-09 | 2022-04-06 19:12 | 8
TX2007-1 | N/A | Carrollton Shell | Carrollton, TX |  |  | Wes Gaddy | TBD |  | PreConstruction | TBD | JV |  |  |  | 2021-06-15 | 2021-08-15 | 61 | 1700000 | 2021-09-14 | 2022-07-12 | 10
TX2007-2 | N/A | Carrollton Shell - Dr. Bui | Carrollton, TX |  |  | Wes Gaddy | TBD |  | PreConstruction | TBD | JV |  |  |  | 2021-07-09 | 2021-08-23 | 45 | 225 | 2021-09-22 | 2022-05-20 19:12 | 8
OK1924 | Yukon | Yukon Development | N Yukon Parkway and Main Street, Yukon, OK |  |  | TBD | TBD |  | PreConstruction | TBD | TBD | N/A | COMPLETE |  | HOLD | HOLD | HOLD | 2500000 | HOLD | HOLD | 12
OK2026 | Covel 35 | Covell I35 Edmond Dev. | TBD Covell Road, Edmond, OK |  |  | TBD | TBD |  | PreConstruction | TBD | JV | N/A | 2021-03-08 |  | 2021-04-21 | ?? | #VALUE! | 400000 | #VALUE! | #VALUE! | 2
OK2034 | Covel 35 | Dr. Rex Johnson, DVM - Covel I35 | TBD Covell Road, Edmond, OK |  |  | TBD | TBD |  | PreConstruction | TBD | JV | 2020-05-14 | 2021-03-08 |  | 2021-05-12 | ?? | #VALUE! | 1750000 | #VALUE! | #VALUE! | 10
OK2037 | N/A | Master Hand Milling | TBD, Edmond, OK |  |  | TBD | TBD |  | PreConstruction | TBD | JV | 2020-09-04 | Pending Land Selection |  | 2021-07-26 | 2021-08-28 | 33 | 4000000 | 2021-10-01 | 2022-09-27 04:48 | 12
OK2102 | N/A | Puppy Paws - East Edmond | East Edmond |  |  | TBD | TBD |  | PreConstruction |  | JV |  | Pending Land Selection |  | 2021-08-15 | 2021-10-17 | 63 | 3000000 | 2021-11-16 | 2022-09-13 | 10
OK2106-1 | N/A | Fox Lake Shell | Edmond, OK |  |  | TBD | TBD |  | PreConstruction |  | JV |  |  |  | 2021-06-21 | 2021-08-12 | 52 | 10000000
OK2107 | N/A | Jack Be Grocery |  |  |  | 2021-06-11 | 2021-08-04 |  | PreConstruction |  | JV |  |  |  | 2021-06-11 | 2021-08-04 | 54 | 5000000
OK2108 | N/A | Puppy Paws - Lone Oak |  |  |  | TBD | TBD |  | PreConstruction |  | JV |  |  |  | 2021-06-28 | 2021-09-17 | 81 | 1750000
OKxxxx | N/A | Dr. Brad Mitchell Development |  |  |  | TBD | TBD |  | PreConstruction |  | JV | [5 empty] | 0 | HOLD
OKxxxx | N/A | Coltrane South - Aya Rowe - Chiro |  |  |  | TBD | TBD |  | PreConstruction |  |  | 2021-02-12 |  |  |  |  | 0
TN2101 | N/A | AIM - Memphis TN |  |  |  | TBD | TBD |  | PreConstruction | AG AIM Memphis RE Holdings, LLC | JV |  |  |  | 2021-06-18 | 2021-08-09 | 52 | 1000000 | 2021-09-08 | 2022-05-06 19:12 | 8
TX2101 | N/A | Bob Mills - Fort Worth |  |  |  | Wes Gaddy | TBD |  | PreConstruction | [5 empty] | 2021-04-09 | 2021-06-10 | 62 | 2250000 | 2021-07-10 | 2021-11-18 05:40 | 4.36
TX2102-1 | N/A | San Antonio Shell - Dr. Abeskharon | San Antonio, TX |  |  | TBD | Roger Harris |  | PreConstruction |  | JV |  |  |  | 2021-07-06 | 2021-09-27 | 83 | 1750000
OKxxxx |  | 63rd and Grand Building | Classen Curve |  |  | TBD | TBD |  | PreConstruction | [8 empty] | 8000000
OK2110-1 |  | Shawnee Shell |  |  |  | TBD | TBD |  | PreConstruction | [5 empty] | 2021-07-14 | 2021-09-02 |  | 1750000 | 2021-09-15
OK2110-2 |  | Shawnee-OSB |  |  |  | TBD | TBD |  | PreConstruction | [5 empty] | 2021-07-14 | 2021-09-02 |  | 290000 | 2021-09-15
OK2111-1 | Santa Fe | Chamberlin Reality Shell | Southwest 134th Street, OKC, OK 73170 |  |  | TBD | TBD |  | PreConstruction | [5 empty] | 2021-07-27 | 2021-09-17 |  | 1750000 | [6 empty] | 60-75 days out
OK2111-2 | Santa Fe | Chamberlin Reality | Southwest 134th Street, OKC, OK 73170 |  |  | TBD | TBD |  | PreConstruction | [5 empty] | 2021-07-27 | 2021-09-17 |  | 1750000
OK???? |  | Peak View Brewery and Distillery | Reservoir by Costco | [16 empty] | 2022-08-01
OK???? |  | Regent Center (Fox Lake Similar) | Broken Arrow | [5 empty] | Design
OK2105-1 | N/A | Valencia Flex - Breakroom 405 | 2215 NW 178th Street Ste. A |  |  | Cory Muir | John Stroud |  | TI |  |  | 2021-01-23 |  |  | 2021-03-22 | 2021-04-09 | 18 | 150000 | 2021-06-03 | 2021-06-14 | 0.36545
OK2105-2 | N/A | Valencia Flex - Christ Fit Gym | 2213 NW 178th Street, Ste. C |  |  | Cory Muir | John Stroud |  | TI |  |  | 2021-02-02 |  |  | 2021-03-22 | 2021-04-06 | 15 | 100000 | 2021-05-24 | 2021-06-22 | 0.96346
OK1923-3 | N/A | Riverwest - Tropical Smoothie | Sandsprings |  |  | Chris Goldsmith | Gary Clinton |  | TI | [7 empty] | 0 | 90000 | 2021-05-28 | 2021-07-23 | 1.8605
OKxxxx |  | Valencia Custom Pools |  |  |  | Cory Muir | John Stroud |  | TI | [5 empty] | N/A | N/A |  |  |  |  | 0
|  | Valencia Prevail Fitness |  |  |  | Cory Muir | John Stroud |  | TI | [5 empty] | 2021-05-21 | 2021-06-04 |  |  |  |  | 0
|  | Yukon Salon-Yukon PPT | 901 E Main St, Yukon, OK |  |  | Cory Muir |  |  | TI | Blondette, LLC | [9 empty] | 2021-06-24 | 1474.1196
|  | Valencia Flex - Magnus Industries Batting Cages | 2215 NW 178th St., Suite D |  |  | Cory Muir |  |  | TI | Magnus Industries, LLC | [9 empty] | 2021-07-09 | 1474.6179
|  | Classy K9-Coletrane South | 241 S Coltrane Rd |  |  | Cory Muir |  |  | TI | The Classy K9, LLC | [9 empty] | 2021-06-25 | 1474.1528
|  | Nutrition Club Piedmont | 12000 NW Expressway |  |  | Cory Muir |  |  | TI | Surrey Nutrition Partners, LLC | [9 empty] | 2021-07-09 | 1474.6179
|  | Stanton Optical-Riverwest | 115 Alexander Blvd |  |  | Cory Muir |  |  | TI | Daniel & Max, LLC | [7 empty] | 50000 |  | 2021-07-23 | 1475.0831
|  | Regent Bank - Coltrane Corner |  |  |  | Cory Muir |  |  | TI | [5 empty] | 2021-05-24 | 2021-06-02 |  | 60000 |  |  | 0
OK1809 | N/A | Valencia Flex | 2215 NW 178th Street, Edmond, OK 73012 |  |  | Jason Nowell | Daniel Frary | Cancelled | Complete | AG Valencia RE Holdings, LLC | JV | N/A | N/A |  |  | N/A |  | N/A | N/A | Complete
OK1909-3 | N/A | Creekwood - All State TI - Mike Lackey |  |  |  | Brandon Cheney | Brandon Cheney |  | Complete |  |  |  | TI |  | 2021-04-13 | 2021-05-03 | 20 | 89724 | 2021-05-11 | 2021-06-01 | 0.69767
OK1912 | N/A | Dr. Shirley | 2441 SW 134th St. OKC 73170 |  |  | Jason Nowell | Adam England / Roger Harris | 2021-07-22 | Complete |  | GMP | N/A | N/A |  |  | N/A |  | 1219262 | 2020-02-28 | 2021-01-08 | 10.4651
OK1913 | N/A | Dr. Rudd/Western | 12208 S Western Ave., OKC73170 |  |  | Jason Nowell | Josh Williams | 2021-07-21 | Complete | AGTB RE Holdings, LLC | JV | N/A | N/A |  |  | N/A |  | N/A | N/A | Complete
OK1914 | N/A | Dr. Morey/Woodland Trails Vet. | 216 W Covell Rd., Edmond, OK 73003 |  |  | Jason Nowell | Adam England | Cancelled | Complete | Woodland RE Holdings, LLC | JV | N/A | N/A |  |  | N/A |  | N/A | N/A | Complete
OK1917 | N/A | Colonial Point - Shell | 12000 Northwest Expy, Yukon, OK 73099 |  |  | Wes Gaddy | Daniel Frary | Cancelled | Complete | Piedmont RE Holdings, LLC | JV | N/A | N/A |  |  | N/A |  | N/A | N/A | Complete | 11 | 2020-12-04
OK1917-2 | N/A | Colonial Point - Old School Bagel | 12000 Northwest Expy, Yukon, OK 73099 |  |  | Wes Gaddy | Daniel Frary | Cancelled | Complete | Piedmont RE Holdings, LLC | JV | N/A | N/A |  |  | N/A |  | N/A | N/A | Complete | 6 | 2020-12-04
OK1917-3 | N/A | Colonial Point - Enhance Dental | 12000 Northwest Expy, Yukon, OK 73099 |  |  | Wes Gaddy | Daniel Frary | Cancelled | Complete | Piedmont RE Holdings, LLC | JV | N/A | N/A |  |  | N/A |  | N/A | N/A | Complete | 6 | 2020-12-04
OK1918 | N/A | Glen Eagles | 916 NW 139th Street Parkway, Edmond, OK 73013 |  |  | Jason Nowell | Adam England / Roger Harris | Cancelled | Complete | Shrink Wrapped, LLC | GMP | N/A | N/A |  |  | N/A |  | N/A | N/A | Complete
OK1923-2 | N/A | Enhanced River West | 152 W Alexander Blvd., Sand Springs, OK 74063 |  |  | Chris Goldsmith | Gary Clinton | Cancelled | Complete | Riverwest RE Holdings, LLC | JV | N/A | N/A |  |  | Complete |  | N/A | N/A | 2020-11-19
OK2024 | N/A | Bodyworx | 9201 S. Sooner Rd., Suite E, OKC 73135 |  |  | Adam England | John Stroud | 2021-12-18 | Complete | King Fisher Holdings, LLC | GMP | N/A | 2020-10-24 | Cornerstone Bank | 2020-09-24 | 2020-12-01 | 68 | 984546 | 2021-02-14 | 2021-08-05 | 5.7143
OK1925 | N/A | Glenpool Small Retail | Glenpool, OK |  |  | Chris Goldsmith | Gary Clinton |  | Complete |  |  | N/A | N/A |  |  | Complete |  | N/A | N/A | Complete
OK1926 | N/A | Hunter's Pharmacy | 10120 Broadway Ext., OKC 73114 |  |  | Bob Solomon | Dale Smith / Dylan Ashley | 2021-04-02 | Complete | AG Kimbaco RE Holdings, LLC | JV | 2019-06-28 | 2020-04-07 | First Liberty Bank | 2020-05-14 | 2020-07-08 | 55 | 9534114 | 2020-07-21 | 2021-06-24 | 11.2292 |  | Closeout
OK1927 | N/A | Dr. Nellis | 9314 S Delaware Ave., Tulsa, OK 74137 |  |  | Chris Goldsmith | Gary Clinton | 2022-01-13 | Complete | AG Delaware RE Holdings, LLC | JV | 2019-06-24 | N/A |  | 2020-02-04 | 2020-04-23 | 79 | 890454 | 2020-04-30 | 2021-01-22 | 8.8704 | 2021-01-27 | 2021-02-05
OK1931 | N/A | Dr. Crowley | 15101 Crown at Lone Oak Rd, OKC 73013 |  |  | Jason Nowell | Adam England / Roger Harris | Cancelled | Complete | Lone Oak RE Holdings, LLC | JV | 2019-07-08 | N/A |  |  | N/A |  | 577676 | 2020-02-28 | 2020-12-22 | 9.9003
OK1935 | N/A | Murfield Dental | 16430 Murfield Place, Edmond, OK 73013 |  |  | Jason Nowell | Adam England / Roger Harris | Cancelled | Complete | King Fisher Holdings, LLC | GMP | N/A | N/A |  |  | N/A |  | N/A | N/A | Complete
OK1936 | N/A | Dr. Fischer | 720 West 71St Street S, Tulsa, OK 74132 |  |  | Chris Goldsmith | Gary Clinton | 2021-12-04 | Complete | AG Medical RE Holdings, LLC | GMP | 2019-08-02 | 2019-12-09 | First Oklahoma Bank | 2020-04-08 | 2020-06-22 | 75 | 2080665 | 2020-06-22 | 2021-04-15 | 9.8671
OK2001 | 61st | 61st Development | 9035 E. 61st Street, Tulsa, OK 74145 |  |  | Chris Goldsmith | Gary Clinton |  | Complete | King Fisher Holdings, LLC | JV | N/A | 2020-02-13 |  | 2020-09-24 | 2021-03-16 | 173 | 700000 | 2021-07-12 | 2021-11-09 09:36 | 4
OK2002 | N/A | Tulsa Hills - 71st Development | 708 W. 71st Street, Tulsa, OK 74132 |  |  | Chris Goldsmith | Gary Clinton |  | Complete | TBD | JV | N/A | Contingent on IDP |  |  | 2020-12-28 |  | 700000 | 2021-01-27 | 2021-07-26 14:24 | 6
OK2003 | N/A | Choctaw - Enhanced Dental | 2651 Market Blvd., Choctaw, OK 73020 |  |  | Wes Gaddy | Josh Williams | Cancelled | Complete | CDC Investment Properties, LLC | Cost+ | N/A | N/A |  |  | N/A |  | 660134 | 2020-06-01 | 2020-11-20 | 5 | 2020-12-04
OK2004 | 61st | Dr. LoScuito - 61st St. Dev. | 9068 E 61st Street, Tulsa, OK 74145 |  |  | Chris Goldsmith | Gary Clinton |  | Complete | Kickapoo RE Holdings, LLC | JV | 2019-10-08 |  |  | 2020-07-27 | 2021-04-07 | 254 | 469659 | 2021-07-12 | 2022-01-08 14:24 | 6
OK2005 | N/A | Quail Springs Shell | 14424 N May Ave., OKC 73134 |  |  | Adam England | Daniel Frary | 2021-07-20 | Complete | AG Quail Springs RE Holdings, LLC | JV | N/A | 2020-07-22 |  | 2020-05-22 | 2020-06-24 | 33 | 784985 | 2020-08-05 | 2021-02-10 | 6.2791
OK2005-1 | N/A | Quail Springs - Enhanced Dental | 14424 N May Ave., OKC 73134 Ste A |  |  | Adam England | Daniel Frary | 2021-07-20 | Complete | AG Quail Springs RE Holdings, LLC | JV | N/A | 2020-07-22 |  | 2020-07-29 | 2020-10-02 | 65 | 297313 | 2020-09-28 | 2021-02-14 | 4.6179
OK2005-2 | N/A | Quail Springs - Just Kids Ped's | 14424 N May Ave., OKC 73134 Ste B |  |  | Adam England | Daniel Frary | 2021-07-20 | Complete | AG Quail Springs RE Holdings, LLC | JV | N/A | 2020-07-22 |  | 2020-06-25 | 2020-07-17 | 22 | 222517 | 2020-09-28 | 2021-02-10 | 4.485
OK2006 | N/A | Enhanced Dental - El Reno | 1601 Investors Ave., El Reno, OK 73036 |  |  | Bob Solomon | John Stroud | 2021-07-13 | Complete | ERD Investment Properties, LLC | Cost+ | N/A | 2020-09-25 |  | 2020-06-16 | 2020-06-23 | 7 | 1208821 | 2020-10-20 | 2021-07-15 | 8.9037
OK2011-1 | N/A | Mustang Shell | 1709 S Mustang Rd., Mustang, OK 73064 |  |  | Wes Gaddy | Josh Williams | 2021-07-24 | Complete | TAG Mustang RE Holdings, LLC | JV | N/A | 2020-05-20 | Southwest National Bank of Weatherford |  | 2020-08-19 |  | 950000 | 2020-09-01 | 2021-03-31 | 7.01
OK2011-3 | N/A | Mustang - Enhanced Dental | 1709 S Mustang Rd., Mustang, OK 73064 Ste A |  |  | Wes Gaddy | Josh Williams | 2021-07-24 | Complete | TAG Mustang RE Holdings, LLC | JV | N/A | 2020-05-20 | Southwest National Bank of Weatherford |  | 2020-07-01 |  | 315000 | 2020-11-01 | 2021-03-31 | 4.9834
OK2018 | 61st | Dr. Sandra Mackey - 61st St. Dev. | 9050 E. 61st Street, Tulsa, OK 74145 |  |  | Chris Goldsmith | Gary Clinton |  | Complete | King Fisher Holdings, LLC | GMP | 2019-10-04 |  |  | 2020-10-03 | 2021-03-24 | 172 | 500000 | 2021-07-12 | 2022-01-08 14:24 | 6
OK2020-1 | N/A | Western Shell | 11521 South Western Ave., OKC, OK 73170 |  |  | Adam England | Daniel Frary | 2021-12-10 | Complete | AG Western RE Holdings, LLC | JV | N/A | 2020-09-25 | First Liberty Bank | 2020-08-03 | 2020-11-27 | 116 | 1207684 | 2020-11-09 | 2021-08-02 | 8.8372
OK2020-2 | N/A | Western - Scammahorn | 11521 South Western Ave., OKC, OK 73170 |  |  | Adam England | Daniel Frary | 2021-12-10 | Construction | AG Western RE Holdings, LLC | JV | 2020-04-20 | 2020-09-25 | First Liberty Bank | 2020-08-06 | 2020-11-28 | 114 | 267573 | 2020-11-09 | 2021-08-10 | 9.103 | 2021-08-10
OK2020-3 | N/A | Western - Dr. Olsen | 11521 South Western Ave., OKC, OK 73170 |  |  | Adam England | Daniel Frary | 2021-12-10 | Complete | AG Western RE Holdings, LLC | JV | N/A | 2020-09-25 | First Liberty Bank | 2020-08-11 | 2020-11-28 | 109 | 230170 | 2020-11-09 | 2021-08-02 | 8.8372
OK2020-4 | N/A | Western - PT Central | 11521 South Western Ave., OKC, OK 73170 |  |  | Jared Dalton | Daniel Frary | INACTIVE | Complete | PTC of Moore, LLC | Lease | 2020-07-22 | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OK2021 | N/A | Dr. Torabi, DDS - Tulsa Hills, 71st Development | 708 W. 71st Street, Tulsa, OK 74132 |  |  | TBD | TBD |  | Complete | AGTKA RE Holdings, LLC | JV | 2019-11-14 | Contingent on IDP |  | 2020-12-08 | 2020-12-22 |  | 725000 | 2021-01-21 | 2020-02-25 | 8
OK2022 | 61st | Just Kids - 61st St. Dev. | 9086 E 61st Street, Tulsa, OK 74145 |  |  | Chris Goldsmith | Gary Clinton |  | Complete | AG JKP RE Holdings, LLC | JV | N/A |  |  | 2020-11-03 | 2021-04-20 | 168 | 577801 | 2021-07-12 | 2022-01-08 14:24 | 6
OK2023 | N/A | Western Urgent Care | 12208 S Western, OKC 73170 |  |  | Bob Solomon | Dion Hall / Andy Carroll | 2021-08-18 | Complete | AG Slootheer RE Holdings, LLC | JV | 2020-06-17 | 2020-08-03 |  |  | 2020-08-04 |  | 415686 | 2020-08-07 | 2020-10-16 | 2.3256 | 2020-11-09
OK2027-1 | N/A | Tulsa Hills Shell - 71st Development | 708 W. 71st Street, Tulsa, OK 74132 |  |  | TBD | TBD |  | Complete | TBD | JV | N/A | Contingent on IDP |  | TBD | TBD |  |  | HOLD
OK2027-2 | N/A | Just for Kids - Tulsa Hills - 71st Development | 708 W. 71st Street, Tulsa, OK 74132 |  |  | TBD | TBD |  | Complete | TBD | JV | N/A | Contingent on IDP |  | TBD | TBD |  |  | HOLD
OK2028 | N/A | Dr. Blake Christensen | 13601 Memorial Park, OKC, OK |  |  | DEAD | DEAD |  | Complete | TBD | GMP | 2019-11-13 | COMPLETE |  | DEAD | No | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD
OK2030 | N/A | Positive Impact - Dr. Israelsen | 6872 Prosper Cir., Edmond, OK |  |  | Jared Dalton | Adam England | INACTIVE | Complete | AG Waterloo RE Holdings, LLC | JV | N/A | N/A |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OK2031 | N/A | T-Mobile - Guthrie | 1904 S Division Street, Guthrie, OK 73044 |  |  | Adam England | Josh Williams |  | Complete | Sigma PL RE Holdings, LLC | TBD | N/A | TBD |  | 2021-01-29 | 2021-03-05 | 35 | 723063 | 2021-03-01 | 2021-07-16 | 5
OK2032-1 | N/A | Cross Roads - Shell | 1168 N. 38th Street, Broken Arrow, OK 74014 |  |  | Chris Goldsmith | Gary Clinton |  | Complete | Broken Arrow Retail, LLC | JV | N/A | 2021-04-13 |  | 2021-06-10 | N/A | N/A | 0 | N/A | N/A | 0
OK2032-2 | N/A | Cross Roads - Dr. Angela Rhodes | 1169 N. 38th Street, Broken Arrow, OK 74014 |  |  | Chris Goldsmith | Gary Clinton |  | Complete | Broken Arrow Retail, LLC | JV | N/A | Pending Refinance |  | 2020-12-22 | 2021-01-25 | 34 | 200000 | 2021-02-24 | 2021-06-24 09:36 | 4
OK2032-3 | N/A | Cross Roads - State Farm Ins. | 1170 N. 38th Street, Broken Arrow, OK 74014 |  |  | Chris Goldsmith | Gary Clinton |  | Complete | Broken Arrow Retail, LLC | JV | N/A | Pending Refinance |  | 2020-12-22 | 2021-01-12 | 21 | 150000 | 2021-02-11 | 2021-06-11 09:36 | 4
OK2032-5 | N/A | Cross Roads - Dispensary | 1172 N. 38th Street, Broken Arrow, OK 74014 |  |  | Chris Goldsmith | Gary Clinton |  | Complete | Broken Arrow Retail, LLC | JV | N/A | 2021-04-13 |  |  | N/A |  | 0
OK2035 | N/A | Just Kids - Tulsa Hills, 71st Development | 708 W. 71st Street, Tulsa, OK 74132 |  |  | TBD | TBD |  | Complete | TBD | JV | N/A | Contingent on IDP |  | HOLD | HOLD |  | 200000 | HOLD |  | 6
OK2036 | N/A | Dr. Matt Cole, DDS | 4239 NW Expressway, OKC, OK |  |  | TBD | TBD |  | Complete | TBD | JV | 2020-05-15 |  |  | 2021-05-26 | 2021-07-13 | 48 | Dead | 2021-08-01 | 2022-03-29 19:12 | 8
OK2039 | N/A | Rockwell Daycare |  |  |  | Adam England | John Stroud |  | Complete | [5 empty] | 2020-12-01 | 2020-12-21 | 20 | 59405 | 2021-02-01 | 2021-03-31 | 1.9269
OK2101 | N/A | Christian Counseling | 12901 E Britton, Jones, OK |  |  | Brandon Cheney | John Stroud |  | Complete | Britton Holdings, LLC |  | 2021-01-13 |  |  | N/A | N/A | 0 | 53500 | 2021-04-01 | 2021-05-31 | 1.9934
OK2103 | Santa Fe | Bethesda - Santa Fe Dev. | 112 Southwest 134th Street, OKC, OK 73170 |  |  | TBD | Josh Williams |  | Complete | TBD | JV | N/A | Pending Land Selection |  | 2021-06-07 | 2021-07-25 | 48 | Dead | 2021-05-02
OK2104 | N/A | Wimberley Walker Remodel |  |  |  | TBD | TBD |  | Complete |  | JV | [6 empty] | 500577
Okxxxx | N/A | Glenpool - Midleton's | Glenpool |  |  | Chris Goldsmith | Gary Clinton |  | Complete | 2021-02-10 | [8 empty] | 2021-04-16
OKxxxx | N/A | Hyperbaric Theropy - Sears Shell |  |  |  | TBD | TBD |  | Complete | [7 empty] | HOLD
OKxxxx | N/A | AiM - Yukon |  |  |  | TBD | TBD |  | Complete | [7 empty] | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD
OKxxxx | N/A | Aim - Addition & OSB |  |  |  | TBD | TBD |  | Complete | [7 empty] | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD
TX1902 | N/A | Dr. Cairns -Toe-Tal | 6000 N Park Dr., Watagua, TX 76148 |  |  | Wes Gaddy | James Stephenson | 2021-10-02 | Complete | North Park Dr RE Holdings, LLC | JV | N/A | N/A |  |  | N/A |  | N/A | N/A | N/A | 10 | Complete
TX2004 | N/A | Marshall Ridge Development LOCATION | Hwy 377 and Marshall Ridge Parkway, Keller, TX |  |  | Wes Gaddy | TBD |  | Complete | TBD | JV | 2020-07-15 | 2021-01-18 |  | DEAD | DEAD | DEAD | 1500000 | DEAD | DEAD | 8
TX2009 | N/A | Alliance Pediatrics - Marshall Ridge Development | Hwy 377 and Marshall Ridge Parkway, Keller, TX |  |  | Wes Gaddy | TBD |  | Complete | TBD | JV | 2020-07-15 | 2021-01-18 |  | DEAD | DEAD | DEAD | 1500000 | DEAD | DEAD | 8
Formulas:
Completion Date = [Start Date]+(4*7*[Duration in Months])
Completion Date = [Start Date]+([Duration in Months]*7*4.3)
Start Date = [Permit Approval Date]+30
Permit Approval Date = [Permit Submitted Date]+23
SUPERINTENDENT = [PROJECT MANAGER]+54
Note on O6: Bob Snyder:
Note on Q7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Trevor has to resubmit new site plan for shell
Note on S15: Trevor Hayes: Updated value
Note on P21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Land Issue, will be pushed back. Date TBD
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Site approval is in City and preapproval is needed prior to building permit review
Note on P23: Trevor Hayes: Updated permit date
Note on C26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Going in for site approval
Note on P26: Trevor Hayes: Updated permit date
Note on P28: Bob Snyder: The City may not want this development
Note on P30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Site permit comment from City of Edmond Moved Date
Note on C31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Working through site issues
Note on C38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Finish out of existing building so may go faster Reply: General Contractor to submit for AGC
Note on S38: Trevor Hayes: Revised value
Note on C42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Peggy to set up project number
Note on C43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Peggy to set up project number
Note on C44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stand alone building on Santa Fe Developement Reply: Peggy to set up project number
Note on C45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stand alone building on Santa Fe Developement Reply: Peggy to set up project number
Note on C49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will have a pilon sign
Note on C76: Bob Snyder: Delayed due to Archaelogical Review
Note on Q76: Bob Snyder: Delayed due to Archaelogical Review
Note on C77: Bob Snyder: This deal is dead.
Note on N77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current Tenent has 30 Days to Vacate Upon Closing
Note on T77: Bob Snyder: After land closing there is a 30 period for the former occupant to vacate. Must have permit to close on the land.
Note on C79: Bob Snyder: Delayed due to Archaelogical Review
Note on Q79: Bob Snyder: Delayed due to Archaelogical Review
Note on U80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Has to complete prior to 2/1/2020. Just Kids lease is expiring and they will not be granted extensions.
Note on U81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Has to complete prior to 2/1/2020. Just Kids lease is expiring and they will not be granted extensions.
Note on U82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Has to complete prior to 2/1/2020. Just Kids lease is expiring and they will not be granted extensions.
Note on C86: Bob Snyder: Delayed due to Archaelogical Review
Note on Q86: Bob Snyder: Delayed due to Archaelogical Review
Note on C91: Bob Snyder: This deal is dead.
Note on C92: Trevor to get with Chris on turnover update to confirm he is good
Note on Q92: Bob Snyder: Delayed due to Archaelogical Review
Note on U93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure if this date has changed Reply: Testing to see what this does if I reply. Date will be 10/16
Note on C94: Bob Snyder: This deal is dead.
Note on N94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending Denver's approval to release CDs. CDs will take 4 weeks to develop from IDP approval.
Note on C95: Bob Snyder: This deal is dead.
Note on N95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending Denver's approval to release CDs. CDs will take 4 weeks to develop from IDP approval.
Note on Q99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Building is exsisting
Note on C100: Not Active
Note on C101: Not Active
Note on C103: Bob Snyder: This deal is dead.
Note on S104: Trevor Hayes: Dead
Note on C107: Bobby Snyder: May have died
Note on S107: Trevor Hayes: Dead
Note on A115: Dead

## 2021 Billing Projections
[14 empty] | 2020 | 2021 | [11 empty] | 2022 | 2023
|  | PM | SUP | Permit | Start Date | Comp Date | Duration | Spectrum Value | ProCore Value | Variance | Forecasted Value | Variance |  | Annual | January | February | March | April | May | June | July | August | September | October | November | December | Annual | Annual | TOTAL | DELTA
Adam English / Jared Dalton |  | AE
OK2005 | Quail Springs Shell | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 730841 | 54144 | [13 empty] | 784985 | #REF!
OK2005-1 | Quail Springs - Enhanced Dental | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 193860 | 56123 | 47330 | [12 empty] | 297313 | #REF!
OK2005-2 | Quail Springs - Just Kids Ped's | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 185068 | 37449 | [13 empty] | 222517 | #REF!
OK2019 | Santa Fe Development | AE | JW | No | #REF! | #REF! | #REF! | #REF! | [5 empty] | 0 |  |  | 75000 | 100000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 75000 |  |  |  | 1000000 | #REF!
OK2020-1 | Western Shell | AE | DF | Yes | 2021-03-17 | 2021-07-29 | 4.4518 | 355000 | [5 empty] | 341769 | 123702.1429 | 123702.1429 | 123702.1429 | 123702.1429 | 123702.1429 | 123702.1429 | 123702.1429 | [7 empty] | 1207684 | -852684
OK2020-2 | Western - Scammahorn | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 72229 |  |  |  | 48836 | 48836 | 48836 | 48836 | [7 empty] | 267573 | #REF!
OK2020-3 | Western - Dr. Olsen | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 45650 |  |  |  | 46130 | 46130 | 46130 | 46130 | [7 empty] | 230170 | #REF!
OK2024 | Bodyworx | AE | Stroud | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 280923 | 100518 | 100518 | 100518 | 100518 | 100518 | 100518 | 50515 | 50000 | [6 empty] | 984546 | #REF!
OK2025 | Autism in Motion - Sante Fe Dev. | AE | TBD | No | 2021-03-01 | 2021-12-27 | 10 | 1375000 | [8 empty] | 75000 | 100000 | 100000 | 125000 | 125000 | 125000 | 125000 | 125000 | 75000 |  |  |  | 975000 | 400000
OK2031 | T-Mobile - Guthrie | AE | JW | No | #REF! | #REF! | #REF! | #REF! | [5 empty] | 0 |  | 120510.5 | 120510.5 | 120510.5 | 120510.5 | 120510.5 | 120510.5 | [7 empty] | 723063 | #REF!
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | AE | TBD | No | #REF! | #REF! | #REF! | #REF! | [20 empty] | 0 | #REF!
OK2033-2 | Old School Bagel - Santa Fe Dev. | AE | TBD | No | #REF! | #REF! | #REF! | #REF! | [10 empty] | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 |  |  |  | 175000 | #REF!
OK2039 | Rockwell Daycare | AE | Stroud | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 0 |  | 30000 | 29405 | [11 empty] | 59405 | #REF!
[8 empty] | #REF! | [5 empty] | 1850340 | 371936.1429 | 422060.6429 | 524135.6429 | 639696.6429 | 689696.6429 | 714696.6429 | 664693.6429 | 325000 | 275000 | 275000 | 175000 | 0 | 0 | 0 | 6927256 | #REF!
Bob Solomon |  | BS
OK1926 | Hunter Pharmacy | BS | DS | Yes | 2021-03-29 | 2021-06-24 19:12 | 2.9169 | 650000 | 8913792 | -8263792 | 8917546 | -8267546 | 3754 | 4251267 | 829806 | 986301 | 1033536 | 1016301 | 817564 | 599339 |  | 0 | 0 | 0 | 0 | 0 |  |  | 9534114 | -8884114
OK2006 | El Reno Enhanced Dental | BS | Stroud | Yes | 2020-09-28 | 2021-04-21 | 6.8106 | #REF! | 1021270 | #REF! | 945919 | #REF! | #REF! | 687650 | 140000 | 180232 | 140523 | 60416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1208821 | #REF!
OK2016 | OneCore | BS | DH | Yes | 2021-01-27 | 2021-12-15 | 10.6977 | #REF! | 12555112 | #REF! | 12611053 | #REF! | #REF! | 735905 | 1015000 | 1200000 | 1300000 | 1274530 | 1379154 | 1414621 | 1379154 | 1274530 | 843964 | 843964 | 520154 | 226935 |  |  | 13407911 | #REF!
[8 empty] | #REF! | [5 empty] | 5674822 | 1984806 | 2366533 | 2474059 | 2351247 | 2196718 | 2013960 | 1379154 | 1274530 | 843964 | 843964 | 520154 | 226935 | 0 | 0 | 24150846 | #REF!
Christopher Goldsmith |  | CG
OK1927 | Dr. Nellis | CG | GC | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 890454 | [14 empty] | 890454 | #REF!
OK1936 | Dr. Fischer | CG | GC | Yes | 2020-10-15 | 2021-12-01 | 13.6877 | 13407911 | [5 empty] | 1881717 | 100000 | 10000 | 88948 | [11 empty] | 2080665 | 11327246
OK1936-TI | Dr. Fischer TI | CG | GC | No | #REF! | #REF! | #REF! | #REF! | [5 empty] | 0 |  |  | 50000 | 50000 | 50000 | 27819 | [8 empty] | 177819 | #REF!
OK2001 | 61st Development | CG | GC | No | #REF! | #REF! |  | #REF! | [8 empty] | 125000 | 150000 | 150000 | 150000 | 60000 | [7 empty] | 635000 | #REF!
OK2004 | Dr. Loscuito | CG | GC | No | 2020-11-01 | 2021-03-31 | 4.9834 | 165000 | [5 empty] | 32120 | [5 empty] | 50000 | 75000 | 125000 | 125000 | 125000 | 67880 |  |  |  | 600000 | -435000
OK2008 | Dr. Gaches | CG | GC | No | 2021-02-01 | 2021-11-01 | 9.0698 | 1125000 | [5 empty] | 65749 |  |  | 50000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 50000 | 24251 |  |  |  | 700000 | 425000
OK2014 | Clark Shell | CG | GC | No | 2021-01-28 | 2021-10-21 | 8.8372 | 1650000 | [5 empty] | 91138 |  |  | 100000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 133862 |  |  |  | 1375000 | 275000
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | GC | No | HOLD | HOLD | #VALUE! | 2500000 | [5 empty] | 124344 |  |  | 25000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 60000 | 50656 |  |  |  | 650000 | 1850000
OK2014-2 | Clark Shell - Enhance DDS | CG | GC | No | #REF! | #REF! | #REF! | #REF! | [5 empty] | 14681 |  |  | 25000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 10319 |  |  |  | 400000 | #REF!
OK2018 | Dr. Sandra Mackey - 61st St. Dev. | CG | GC | No | #REF! | #REF! | #REF! | #REF! | [5 empty] | 0 |  | 0 |  |  |  | 50000 | 100000 | 100000 | 100000 | 100000 | 50000 |  |  |  | 500000 | #REF!
OK2022 | Just Kids - 61st St. Dev. | CG | GC | No | 2020-11-01 | 2021-10-15 | 11.5615 | 1750000 | [5 empty] | 0 |  | 0 |  |  |  | 75000 | 100000 | 125000 | 125000 | 100000 | 50000 |  |  |  | 575000 | 1175000
OK2032-1 | Cross Roads - Shell | CG | GC | No | 2021-05-01 | 2021-09-07 | N/A | 0 | [5 empty] | 0 | [14 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | GC | No | #REF! | #REF! | #REF! | #REF! | [5 empty] | 0 |  |  |  | 25000 | 25000 | 50000 | 50000 | 25000 | [6 empty] | 175000 | #REF!
[8 empty] | #REF! | [5 empty] | 3100203 | 100000 | 10000 | 463948 | 575000 | 575000 | 752819 | 735000 | 725000 | 700000 | 635000 | 386968 | 0 | 0 | 0 | 8758938 | #REF!
Nolan Krampe |  | NK
OK2019 | Santa Fe Development | NK |  | Yes | 2021-05-03 | 2022-01-10 | 8.3721 | 1000000 | [5 empty] | 0 |  |  | 7500 | 7500 | 7500 | 7500 | [8 empty] | 30000 | 970000
[8 empty] | 1000000 | [5 empty] | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 970000
Wes Gaddy |  | WG
OK2011-1 | Mustang Shell | WG | JW | Yes | 2021-04-04 | 2021-09-27 | 5.8472 | 700000 | 819670 |  |  |  |  | 745760 | 105645 | 98595 | [12 empty] | 950000 | -250000
OK2011-2 | Mustang - Old School Bagel | WG | JW | Yes | 2021-05-03 | 2021-12-29 19:12 | 8 | 975000 | 142789 |  |  |  |  | 94173 | 50000 | 20827 | [12 empty] | 165000 | 810000
OK2011-3 | Mustang - Enhanced Dental | WG | JW | Yes | #VALUE! | #VALUE! | #VALUE! | 400000 | 272772 |  |  |  |  | 176191 | 75000 | 63809 | [12 empty] | 315000 | 85000
TX1901 | Dr. Dyer - Sequoia Spur | WG | JS | Yes | 2021-05-24 | 2021-06-22 | 0.96346 | 100000 | [5 empty] | 621560 | 110730 | 125000 | 150000 | 175000 | 175000 | 150000 | 150000 | 92710 | [6 empty] | 1750000 | -1650000
TX1903 | Ramon Franklin Warehouse | WG | TBD | Yes | 0 | 0 | 0 | 10000000 | [5 empty] | 131243 |  |  | 150000 | 200000 | 200000 | 250000 | 193757 | [7 empty] | 1125000 | 8875000
TX2001 | Dr. Lippian - Texarkana | WG | RH | Yes | 0 | 0 | 0 | 5000000 | 1339023 |  |  |  |  | 103605 |  | 100000 | 150000 | 150000 | 250000 | 250000 | 250000 | 250000 | 146395 | [5 empty] | 1650000 | 3350000
TX2004 | Marshall Ridge Development | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [11 empty] | 100000 | 187500 | 187500 | 187500 | 187500 | 187500 | 187500 | 275000 |  | 1500000 | #REF!
TX2005 | McKinney Development | WG | TBD | No | 0 | 0 | 0 | HOLD | [13 empty] | 100000 | 100000 | 125000 | 125000 | 100000 | 50000 |  | 600000 | #VALUE!
TX2006-1 | Sunnyvale Shell | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 100000 | 150000 | 200000 | 200000 | 200000 | 650000 |  | 1500000 | #REF!
TX2006-2 | Dr. Luna - Sunnyvale Shell | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 50000 | 65000 | 65000 | 65000 | 65000 | 440000 |  | 750000 | #REF!
TX2006-3 | Dr. Rohani - Sunnyvale Shell | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 50000 | 65000 | 65000 | 65000 | 65000 | 440000 |  | 750000 | #REF!
TX2007-1 | Carrollton Shell | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 187500 | 187500 | 187500 | 187500 | 187500 | 562500 |  | 1500000 | #REF!
TX2007-2 | Dr. Bui - Carrollton Shell | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 30000 | 30000 | 30000 | 30000 | 30000 | 350000 |  | 500000 | #REF!
TX2008 | Dr. Barabra Lee McKinney Development | WG | TBD | No | 0 | 0 | 0 | 0 | [13 empty] | 50000 | 100000 | 100000 | 100000 | 100000 | 300000 |  | 750000 | -750000
TX2009 | Alliance Pediatrics - Marshall Ridge Development | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [11 empty] | 200000 | 225000 | 225000 | 225000 | 225000 | 225000 | 100000 | 75000 |  | 1500000 | #REF!
[8 empty] | #REF! | [5 empty] | 1872532 | 341375 | 408231 | 450000 | 525000 | 625000 | 950000 | 1006257 | 1322710 | 1256395 | 1185000 | 1185000 | 1035000 | 3142500 | 0 | 15305000 | #REF!
PreConstruction |  | TBD
OK1924 | Yukon Development | TBD | TBD | No | #REF! | #REF! |  | #REF! | [18 empty] | 2500000 |  | 2500000 | #REF!
OK2026 | Covell I35 Edmond Dev. | TBD | TBD | No | #REF! | #REF! | #REF! | #REF! | [10 empty] | 125000 | 150000 | 125000 | [7 empty] | 400000 | #REF!
OK2028 | Dr. Blake Christensen | TBD | TBD | No | #REF! | #REF! | #REF! | #REF! | [9 empty] | 120554 | 640652 | 780589 | 1254600 | 1554600 | 1884600 | 1884600 | 1884600 | 1254600 | 740605 |  | 12000000 | #REF!
OK2034 | Dr. Rex Johnson, DVM - Covel I35 | TBD | TBD | No | #REF! | #REF! | #REF! | #REF! | [10 empty] | 100000 | 150000 | 150000 | 150000 | 150000 | 200000 | 200000 | 200000 | 450000 |  | 1750000 | #REF!
OK2036 | Dr. Matt Cole, DDS | TBD | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 125000 | 250000 | 350000 | 350000 | 350000 | 1075000 |  | 2500000 | #REF!
OK2037 | Master Hand Milling | TBD | TBD | No | 2021-05-28 | 2021-07-23 | 1.8605 | 90000 | [15 empty] | 800000 | 800000 | 800000 | 1600000 |  | 4000000 | -3910000
OK2038 | Dr. Farmer TI - Wonga Corner | TBD | TBD | No | 0 | 0 | 0 | 1750000 | [8 empty] | 88750 | 100000 | 110000 | 56250 | [8 empty] | 355000 | 1395000
OK2102 | Puppy Paws | TBD | TBD | No | 2021-09-08 | 2022-05-06 19:12 | 8 | 1000000 | [18 empty] | 3000000 |  | 3000000 | -2000000
TNxxxx | AIM - Memphis TN | TBD | TBD | No | 2021-08-09 | 2022-04-06 19:12 | 8 | 1736318 | [18 empty] | 1500000 |  | 1500000 | 236318
#REF! | #REF! | TBD | TBD | No | 2021-08-09 | 2022-04-06 19:12 |  | 376000 | [18 empty] | 2000000 |  | 2000000 | -1624000
[8 empty] | #REF! | [5 empty] | 0 | 0 | 0 | 88750 | 220554 | 975652 | 1136839 | 1529600 | 1829600 | 2284600 | 3234600 | 3234600 | 2604600 | 12865605 | 0 | 30005000 | #REF!
[29 empty] | 0 | 0
[29 empty] | 0 | 0
[7 empty] | TOTAL | #REF! | 25064428 | #REF! | 22474518 | #REF! | #REF! | 12497897 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 | 16008105 | 0 | 85177040 | #REF!
Note on B27: Bob Snyder: Delayed due to Archaelogical Review
Note on I35: Existing Building

## 01 2021
[14 empty] | 2020 | 2021 | [11 empty] | 2022 | 2023
|  | PM | SUP | Permit | Start Date | Comp Date | Duration | Spectrum Value | ProCore Value | Variance | Forecasted Value | Variance |  | Annual | January | February | March | April | May | June | July | August | September | October | November | December | Annual | Annual | TOTAL | DELTA
Adam English |  | AE
OK2005 | Quail Springs Shell | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 628337 | 137155 | 19493 | [12 empty] | 784985 | #REF!
OK2005-1 | Quail Springs - Enhanced Dental | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 162612 | 95646 | 39055 | [12 empty] | 297313 | #REF!
OK2005-2 | Quail Springs - Just Kids Ped's | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 131745 | 62828 | 27944 | [12 empty] | 222517 | #REF!
OK2019 | Santa Fe Development | AE | JW | No | #REF! | #REF! | #REF! | #REF! | [8 empty] | 75000 | 100000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 75000 |  |  |  | 1000000 | #REF!
OK2020-1 | Western Shell | AE | DF | Yes | 2021-03-17 | 2021-07-29 | 4.4518 | 355000 | [5 empty] | 244435 | 181308 | 150000 | 150000 | 150000 | 135000 | 135000 | 61941 | [7 empty] | 1207684 | -852684
OK2020-2 | Western - Scammahorn | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 46929 | 38525 |  |  | 48836 | 48836 | 48836 | 35611 | [7 empty] | 267573 | #REF!
OK2020-3 | Western - Dr. Olsen | AE | DF | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 34010 | 31345 |  |  | 46130 | 46130 | 46130 | 26425 | [7 empty] | 230170 | #REF!
OK2024 | Bodyworx | AE | STROUD | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 230830 | 155142 | 100518 | 100518 | 100518 | 100518 | 100518 | 50000 | 45984 | [6 empty] | 984546 | #REF!
OK2025 | Autism in Motion - Sante Fe Dev. | AE | TBD | No | 2021-03-01 | 2021-12-27 | 10 | 1375000 | [8 empty] | 75000 | 100000 | 100000 | 125000 | 125000 | 125000 | 125000 | 125000 | 75000 |  |  |  | 975000 | 400000
OK2031 | T-Mobile - Guthrie | AE | JW | No | #REF! | #REF! | #REF! | #REF! | [7 empty] | 120510.5 | 120510.5 | 120510.5 | 120510.5 | 120510.5 | 120510.5 | [7 empty] | 723063 | #REF!
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | AE | TBD | No | #REF! | #REF! | #REF! | #REF! | [20 empty] | 0 | #REF!
OK2033-2 | Old School Bagel - Santa Fe Dev. | AE | TBD | No | #REF! | #REF! | #REF! | #REF! | [10 empty] | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 |  |  |  | 175000 | #REF!
OK2039 | Rockwell Daycare | AE | STROUD | Yes | #REF! | #REF! | #REF! | #REF! | [7 empty] | 30000 | 29405 | [11 empty] | 59405 | #REF!
[8 empty] | #REF! | [5 empty] | 1478898 | 701949 | 487520.5 | 550433.5 | 665994.5 | 700994.5 | 725994.5 | 569487.5 | 320984 | 275000 | 275000 | 175000 | 0 | 0 | 0 | 6927256 | #REF!
Bob Solomon |  | BS | [27 empty] | 0
OK1926 | Hunter Pharmacy | BS | DS | Yes | 2021-03-29 | 2021-06-24 19:12 | 2.9169 | 650000 | 8913792 | -8263792 | 8917546 | -8267546 | 3754 | 4251267 | 974630 | 986301 | 1033536 | 1016301 | 817564 | 454515 |  | 0 | 0 | 0 | 0 | 0 |  |  | 9534114 | -8884114
OK2006 | El Reno Enhanced Dental | BS | STROUD | Yes | 2020-09-28 | 2021-04-21 | 6.8106 | #REF! | 1021270 | #REF! | 945919 | #REF! | #REF! | 501155 | 186495 | 180232 | 180232 | 160707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1208821 | #REF!
OK2016 | OneCore | BS | DH | Yes | 2021-01-27 | 2021-12-15 | 10.6977 | #REF! | 12555112 | #REF! | 12611053 | #REF! | #REF! | 802663 | 1051823 | 1200000 | 1300000 | 1274530 | 1379154 | 1414621 | 1379154 | 1274530 | 843964 | 843964 | 520154 | 123354 |  |  | 13407911 | #REF!
[8 empty] | #REF! | [5 empty] | 5555085 | 2212948 | 2366533 | 2513768 | 2451538 | 2196718 | 1869136 | 1379154 | 1274530 | 843964 | 843964 | 520154 | 123354 | 0 | 0 | 24150846 | #REF!
Christopher Goldsmith |  | CG | [27 empty] | 0
OK1927 | Dr. Nellis | CG | GC | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 890454 | [14 empty] | 890454 | #REF!
OK1936 | Dr. Fischer | CG | GC | Yes | 2020-10-15 | 2021-12-01 | 13.6877 | 13407911 | [5 empty] | 1788494 | 93223 | 100000 | 98948 | [11 empty] | 2080665 | 11327246
OK1936-TI | Dr. Fischer TI | CG | GC | No | #REF! | #REF! | #REF! | #REF! | [8 empty] | 50000 | 50000 | 50000 | 27819 | [8 empty] | 177819 | #REF!
OK2001 | 61st Development | CG | GC | No | #REF! | #REF! | #REF! | #REF! | [10 empty] | 150000 | 150000 | 150000 | 125000 | 60000 | [5 empty] | 635000 | #REF!
OK2004 | Dr. Loscuito | CG | GC | No | 2020-11-01 | 2021-03-31 | 4.9834 | 165000 | [5 empty] | 32120 | [5 empty] | 50000 | 75000 | 125000 | 125000 | 125000 | 67880 |  |  |  | 600000 | -435000
OK2008 | Dr. Gaches | CG | GC | No | 2021-02-01 | 2021-11-01 | 9.0698 | 1125000 | [5 empty] | 65749 |  |  | 50000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 50000 | 24251 |  |  |  | 700000 | 425000
OK2014 | Clark Shell | CG | GC | No | 2021-01-28 | 2021-10-21 | 8.8372 | 1650000 | [5 empty] | 91138 |  |  | 100000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 133862 |  |  |  | 1375000 | 275000
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | GC | No | HOLD | HOLD | #VALUE! | 2500000 | [5 empty] | 124344 |  |  | 25000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 60000 | 50656 |  |  |  | 650000 | 1850000
OK2014-2 | Clark Shell - Enhance DDS | CG | GC | No | #REF! | #REF! | #REF! | #REF! | [5 empty] | 14681 |  |  | 25000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 10319 |  |  |  | 400000 | #REF!
OK2018 | Dr. Sandra Mackey - 61st St. Dev. | CG | GC | No | #REF! | #REF! | #REF! | #REF! | [7 empty] | 0 |  |  |  | 50000 | 100000 | 100000 | 100000 | 100000 | 50000 |  |  |  | 500000 | #REF!
OK2022 | Just Kids - 61st St. Dev. | CG | GC | No | 2020-11-01 | 2021-10-15 | 11.5615 | 1750000 | [7 empty] | 0 |  |  |  | 75000 | 100000 | 125000 | 125000 | 100000 | 50000 |  |  |  | 575000 | 1175000
OK2032-1 | Cross Roads - Shell | CG | GC | No | 2021-05-01 | 2021-09-07 | N/A | 0 | [20 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | GC | No | #REF! | #REF! | #REF! | #REF! | [9 empty] | 25000 | 25000 | 50000 | 50000 | 25000 | [6 empty] | 175000 | #REF!
[8 empty] | #REF! | [5 empty] | 3006980 | 93223 | 100000 | 348948 | 425000 | 575000 | 752819 | 825000 | 850000 | 760000 | 635000 | 386968 | 0 | 0 | 0 | 8758938 | #REF!
Jason Nowell |  | NK | [27 empty] | 0
#REF! | #REF! | NK | AE | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 1206321 | 11381 | 1560 | [12 empty] | 1219262 | #REF!
#REF! | #REF! | NK | AE | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 570676 | 2335 | 4665 | [12 empty] | 577676 | #REF!
NK #REF! #REF!: #REF! | [5 empty] | 1776997 | 13716 | 6225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1796938 | #REF!
Jason Nowell #REF! #REF!: Nolan Krampe; NK NK NK: NK | [21 empty] | 0
OK2019 | Santa Fe Development | NK | NK | Yes | 2021-05-03 | 2022-01-10 | 8.3721 | 1000000 | [8 empty] | 7500 | 7500 | 7500 | 7500 | [8 empty] | 30000 | 970000
NK #REF! #REF!: 1000000 | [5 empty] | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 970000
Jason Nowell #REF! #REF!: Wes Gaddy; NK NK NK: WG | [21 empty] | 0
#REF! | #REF! | WG | WILLIAMS | Yes | #REF! | #REF! | #REF! | #REF! | [5 empty] | 568347 | 879 | 90908 | [12 empty] | 660134 | #REF!
OK2008 | Dr. Mark Gaches, DDS - Owasso | WG | WILLIAMS | Yes | 2021-04-04 | 2021-09-27 | 5.8472 | 700000 | 819670 |  |  |  |  | 720455 | 114649 | 89591 | 25305 | [11 empty] | 950000 | -250000
OK2025 | Autism in Motion - Sante Fe Dev. | WG | WILLIAMS | Yes | 2021-05-03 | 2021-12-29 19:12 | 8 | 975000 | 142789 |  |  |  |  | 64622 | 39561 | 50000 | 10817 | [11 empty] | 165000 | 810000
OK2026 | Covell I35 Edmond Dev. | WG | WILLIAMS | Yes | #VALUE! | #VALUE! | #VALUE! | 400000 | 272772 |  |  |  |  | 124791 | 64927 | 73882 | 51400 | [11 empty] | 315000 | 85000
OK2105-2 | Valencia Flex - Christ Fit Gym | WG | Stephensen | Yes | 2021-05-24 | 2021-06-22 | 0.96346 | 100000 | [5 empty] | 407476 | 214084 | 125000 | 175000 | 175000 | 175000 | 175000 | 160000 | 143440 | [6 empty] | 1750000 | -1650000
OK2106-1 | Fox Lake Shell | WG | TBD | Yes | 0 | 0 | 0 | 10000000 | [5 empty] | 131243 |  |  | 150000 | 200000 | 200000 | 250000 | 193757 | [7 empty] | 1125000 | 8875000
OK2107 | Jack Be Grocery | WG | RH | Yes | 0 | 0 | 0 | 5000000 | 1339023 |  |  |  |  | 103605 |  | 100000 | 150000 | 150000 | 250000 | 250000 | 250000 | 250000 | 146395 | [5 empty] | 1650000 | 3350000
#REF! | #REF! | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [11 empty] | 100000 | 187500 | 187500 | 187500 | 187500 | 187500 | 187500 | 275000 |  | 1500000 | #REF!
OKxxxx | Dr. Brad Mitchell Development | WG | TBD | No | 0 | 0 | 0 | HOLD | [13 empty] | 100000 | 100000 | 125000 | 125000 | 100000 | 50000 |  | 600000 | #VALUE!
#REF! | #REF! | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 100000 | 150000 | 200000 | 200000 | 200000 | 650000 |  | 1500000 | #REF!
#REF! | #REF! | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 50000 | 65000 | 65000 | 65000 | 65000 | 440000 |  | 750000 | #REF!
#REF! | #REF! | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 50000 | 65000 | 65000 | 65000 | 65000 | 440000 |  | 750000 | #REF!
#REF! | #REF! | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 187500 | 187500 | 187500 | 187500 | 187500 | 562500 |  | 1500000 | #REF!
#REF! | #REF! | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 30000 | 30000 | 30000 | 30000 | 30000 | 350000 |  | 500000 | #REF!
OKxxxx | Coltrane South - Aya Rowe - Chiro | WG | TBD | No | 0 | 0 | 0 | 0 | [13 empty] | 50000 | 100000 | 100000 | 100000 | 100000 | 300000 |  | 750000 | -750000
#REF! | #REF! | WG | TBD | No | #REF! | #REF! | #REF! | #REF! | [11 empty] | 200000 | 225000 | 225000 | 225000 | 225000 | 225000 | 100000 | 75000 |  | 1500000 | #REF!
#REF!: #REF! | [5 empty] | 1552192 | 433221 | 438473 | 562522 | 525000 | 625000 | 975000 | 1016257 | 1373440 | 1256395 | 1185000 | 1185000 | 1035000 | 3142500 | 0 | 15305000 | #REF!
#REF!: PreConstruction; WG: TBD | [21 empty] | 0
OK1924 | Yukon Development | TBD | TBD | No | #REF! | #REF! |  | #REF! | [18 empty] | 2500000 |  | 2500000 | #REF!
OK2026 | Covell I35 Edmond Dev. | TBD | TBD | No | #REF! | #REF! | #REF! | #REF! | [10 empty] | 125000 | 150000 | 125000 | [7 empty] | 400000 | #REF!
OK2028 | Dr. Blake Christensen | TBD | TBD | No | #REF! | #REF! | #REF! | #REF! | [9 empty] | 120554 | 640652 | 780589 | 1254600 | 1554600 | 1884600 | 1884600 | 1884600 | 1254600 | 740605 |  | 12000000 | #REF!
OK2034 | Dr. Rex Johnson, DVM - Covel I35 | TBD | TBD | No | #REF! | #REF! | #REF! | #REF! | [10 empty] | 100000 | 150000 | 150000 | 150000 | 150000 | 200000 | 200000 | 200000 | 450000 |  | 1750000 | #REF!
OK2036 | Dr. Matt Cole, DDS | TBD | TBD | No | #REF! | #REF! | #REF! | #REF! | [13 empty] | 125000 | 250000 | 350000 | 350000 | 350000 | 1075000 |  | 2500000 | #REF!
OK2037 | Master Hand Milling | TBD | TBD | No | 2021-05-28 | 2021-07-23 | 1.8605 | 90000 | [15 empty] | 800000 | 800000 | 800000 | 1600000 |  | 4000000 | -3910000
OK2038 | Dr. Farmer TI - Wonga Corner | TBD | TBD | No | 0 | 0 | 0 | 1750000 | [8 empty] | 88750 | 100000 | 110000 | 56250 | [8 empty] | 355000 | 1395000
OK2102 | Puppy Paws | TBD | TBD | No | 2021-09-08 | 2022-05-06 19:12 | 8 | 1000000 | [18 empty] | 3000000 |  | 3000000 | -2000000
TNxxxx | AIM - Memphis TN | TBD | TBD | No | 2021-08-09 | 2022-04-06 19:12 | 8 | 1736318 | [18 empty] | 1500000 |  | 1500000 | 236318
#REF! | #REF! | TBD | TBD | No | #REF! | #REF! | #REF! | 376000 | [18 empty] | 2000000 |  | 2000000 | -1624000
#REF!: #REF! | [5 empty] | 0 | 0 | 0 | 88750 | 220554 | 975652 | 1136839 | 1529600 | 1829600 | 2284600 | 3234600 | 3234600 | 2604600 | 12865605 | 0 | 30005000 | #REF!
[29 empty] | 0 | 0
#REF!: Billing Forecast Total; #REF!: #REF! | 25064428 | #REF! | 22474518 | #REF! | #REF! | 13938499 | 3455936 | 3489659.5 | 4071921.5 | 4295586.5 | 5080864.5 | 5467288.5 | 5319498.5 | 5648554 | 5419959 | 6173564 | 5501722 | 3762954 | 16008105 | 0 | 87634112 | #REF!
#REF!: Billing Goal | [5 empty] | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 | 16008105
#REF!: Difference | [5 empty] | -718546 | 657818.8571 | 282834.8571 | 63528.8571 | -23411.1429 | 11297.8571 | -108526.1429 | 4793.8571 | 171714 | 60000 | 0 | 0 | -103581
#REF!: Rev Actual | [6 empty] | 2897650
#REF!: Rev Goal | [6 empty] | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 | 12779270.2215
#REF!: Difference | [6 empty] | 663913.0849
#REF!: GP Actual | [6 empty] | 261214
#REF!: GP Goal | [6 empty] | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 | 1403910.8085
#REF!: Difference | [6 empty] | 15819.1266
#REF!: GP % Actual | [6 empty] | 9.01%
#REF!: GP % Goal | [6 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
#REF!: Difference | [6 empty] | -0.99%
#REF!: OH Actual | [6 empty] | 257087
#REF!: OH Goal | [6 empty] | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
#REF!: Difference | [6 empty] | 17913
#REF!: NP Actual | [6 empty] | 4127
#REF!: NP Goal | [6 empty] | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 | 500000.0033
#REF!: Difference | [6 empty] | -20412.4873
Note on B27: Bob Snyder: Delayed due to Archaelogical Review
Note on I35: Existing Building

## 02 2021
[14 empty] | 2020 | 2021 | [11 empty] | 2022 | 2023
|  | PM | SUP | Permit | Start Date | Comp Date | Duration | Spectrum Value | ProCore Value | Variance | Forecasted Value | Variance |  | Annual | January | February | March | April | May | June | July | August | September | October | November | December | Annual | Annual | TOTAL | DELTA
Adam English |  | AE
OK2005 | Quail Springs Shell | AE | DF | Yes | #REF! | #REF! | #REF! | 845876 | [5 empty] | 628337 | 137155 | 19492 | 60892 | [11 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | DF | Yes | #REF! | #REF! | #REF! | 297313 | [5 empty] | 162612 | 95646 | 33342 | 5713 | [11 empty] | 297313 | 0
OK2005-2 | Quail Springs - Just Kids Ped's | AE | DF | Yes | #REF! | #REF! | #REF! | 222517 | [5 empty] | 131745 | 62828 | 27944 | [12 empty] | 222517 | 0
OK2020-1 | Western Shell | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 1207684 | [5 empty] | 244435 | 181308 | 16313 | 150000 | 150000 | 160000 | 160000 | 145628 | [7 empty] | 1207684 | 0
OK2020-2 | Western - Scammahorn | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 267573 | [5 empty] | 46929 | 38525 |  | 38525 | 40000 | 40000 | 40000 | 23594 | [7 empty] | 267573 | 0
OK2020-3 | Western - Dr. Olsen | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 230170 | [5 empty] | 34010 | 31345 |  | 15000 | 45000 | 45000 | 40000 | 19815 | [7 empty] | 230170 | 0
OK2024 | Bodyworx | AE | STROUD | Yes | 2021-02-14 | 2021-08-31 | 6.5781 | 984546 | [5 empty] | 230830 | 155142 | 20934 | 100000 | 125000 | 125000 | 100518 | 81138 | 45984 | [6 empty] | 984546 | 0
OK2031 | T-Mobile - Guthrie | AE | JW | Yes | 2021-03-01 | 2021-07-29 | 4.9834 | 723063 | [8 empty] | 140000 | 140000 | 140000 | 163063 | 140000 | [7 empty] | 723063 | 0
OK2039 | Rockwell Daycare | AE | STROUD | Yes | 2021-02-01 | 2021-03-31 | 1.9269 | 81500 | [8 empty] | 30000 | 30000 | 21500 | [9 empty] | 81500 | 0
[8 empty] | 4860242 | [5 empty] | 1478898 | 701949 | 118025 | 540130 | 530000 | 531500 | 503581 | 410175 | 45984 | 0 | 0 | 0 | 0 | 0 | 0 | 4860242 | 0
Bob Solomon |  | BS | [27 empty] | 0
OK1926 | Hunter Pharmacy | BS | DS | Yes | 2020-07-21 | 2021-06-24 | 11.2292 | 9534114 | 8913792 | 620322 | 8917546 | 616568 | 3754 | 4251267 | 974630 | 965506 | 1033536 | 1016301 | 817564 | 475310 |  | 0 | 0 | 0 | 0 | 0 |  |  | 9534114 | 0
OK2006 | El Reno Enhanced Dental | BS | STROUD | Yes | 2020-10-20 | 2021-06-07 | 7.6412 | 1208821 | 1021270 | 187551 | 945919 | 262902 | -75351 | 501155 | 186495 | 202246 | 66601 | 160707 | 91617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1208821 | 0
OK2016 | OneCore | BS | DH | Yes | 2020-10-15 | 2021-12-16 | 14.186 | 13107911 | 12555112 | 552799 | 12611053 | 496858 | 55941 | 802663 | 1051823 | 822272 | 1300000 | 1300000 | 1400000 | 1450000 | 1379154 | 1270563 | 843964 | 843964 | 520154 | 123354 |  |  | 13107911 | 0
[8 empty] | 23850846 | [5 empty] | 5555085 | 2212948 | 1990024 | 2400137 | 2477008 | 2309181 | 1925310 | 1379154 | 1270563 | 843964 | 843964 | 520154 | 123354 | 0 | 0 | 23850846 | 0
Christopher Goldsmith |  | CG | [27 empty] | 0
OK1927 | Dr. Nellis | CG | GC | Yes | #REF! | #REF! | #REF! | 890454 | [5 empty] | 890454 | [14 empty] | 890454 | 0
OK1936 | Dr. Fischer | CG | GC | Yes | 2020-06-22 | 2021-04-15 | 9.8671 | 2499778 | [5 empty] | 1697608 | 93223 |  | 98948 | 609999 | [10 empty] | 2499778 | 0
OK1936-TI | Dr. Fischer TI | CG | GC | No | 2021-05-01 | 2021-07-30 | 2.99 | 177819 | [8 empty] | 50000 | 50000 | 50000 | 27819 | [8 empty] | 177819 | 0
OK2001 | 61st Development | CG | GC | No | 2021-05-01 | 2021-08-29 | 3.9867 | 700000 | [9 empty] | 65000 | 150000 | 150000 | 150000 | 125000 | 60000 | [5 empty] | 700000 | 0
OK2004 | Dr. Loscuito - 61st Dev. | CG | GC | No | 2021-06-01 | 2021-11-28 | 5.9801 | 469659 | [5 empty] | 32120 | [5 empty] | 50000 | 75000 | 80000 | 80000 | 75000 | 77539 |  |  |  | 469659 | 0
OK2018 | Dr. Sandra Mackey - 61st St. Dev. | CG | GC | Yes | 2021-05-01 | 2021-10-28 | 5.9801 | 446790 | [11 empty] | 25000 | 75000 | 100000 | 100000 | 100000 | 46790 |  |  |  | 446790 | 0
OK2022 | Just Kids - 61st St. Dev. | CG | GC | No | 2021-05-01 | 2021-10-28 | 5.9801 | 577801 | [11 empty] | 75000 | 100000 | 125000 | 125000 | 100000 | 52801 |  |  |  | 577801 | 0
OK2008 | Dr. Gaches | CG | GC | Yes | 2021-04-04 | 2021-07-15 | 3.3887 | 683158 | [5 empty] | 65749 |  |  | 50000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 50000 | 7409 |  |  |  | 683158 | 0
OK2014 | Clark Shell | CG | GC | Yes | 2021-03-01 | 2021-12-27 | 10 | 1436404 | [5 empty] | 91138 |  |  | 100000 | 150000 | 150000 | 150000 | 150000 | 150000 | 175000 | 175000 | 145266 |  |  |  | 1436404 | 0
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 648253 | [5 empty] | 124344 |  |  | 25000 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 60000 | 48909 |  |  |  | 648253 | 0
OK2014-2 | Clark Shell - Enhance DDS | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 400187 | [5 empty] | 14681 |  |  | 25000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 10506 |  |  |  | 400187 | 0
OK2032-1 | Cross Roads - Shell | CG | GC | No | N/A | N/A | N/A | 0 | [20 empty] | 0 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | CG | GC | No | DEAD | DEAD | N/A | 15360 | [7 empty] | 15360 | [12 empty] | 15360 | 0
OK2032-3 | Cross Roads - State Farm | CG | GC | No | DEAD | DEAD | N/A | 5720 | [7 empty] | 5720 | [12 empty] | 5720 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | GC | No | 2021-05-20 | 2021-09-17 | 3.9867 | 175000 | [9 empty] | 25000 | 25000 | 50000 | 50000 | 25000 | [6 empty] | 175000 | 0
OK2032-5 | Cross Roads - Dispensary | CG | GC | No | [24 empty] | 0 | 0
[8 empty] | 9126383 | [5 empty] | 2916094 | 93223 | 21080 | 348948 | 1099999 | 575000 | 727819 | 800000 | 805000 | 740000 | 610000 | 389220 | 0 | 0 | 0 | 9126383 | 0
Nolan Krampe |  | NK | [27 empty] | 0
OK2021 | Christian Counciling | NK | NK | Yes | 2021-03-01 | 2021-05-31 | 3.0233 | 52095 | [8 empty] | 7500 | 15000 | 20000 | 9595 | [8 empty] | 52095 | 0
[8 empty] | 52095 | [5 empty] | 0 | 0 | 0 | 7500 | 15000 | 20000 | 9595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | 0
Wes Gaddy |  | WG | [27 empty] | 0
OK2003 | Enhance Dental - Choctaw | WG | WILLIAMS | Yes |  |  | 0 | 604799 | [5 empty] | 568347 | 879 | 35573 | [12 empty] | 604799 | 0
OK2011-1 | Mustang Shell | WG | WILLIAMS | Yes | 2020-09-01 | 2021-03-31 | 7.01 | 940687 | [5 empty] | 720455 | 114649 |  | 105583 | [11 empty] | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 223564 | 819670 |  |  |  |  | 64622 | 39562 | 18328 | 101052 | [11 empty] | 223564 | 0
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 314022 | [5 empty] | 124791 | 64927 | 25844 | 98460 | [11 empty] | 314022 | 0
OK2038 | Dr. Farmer TI - Wonga Corner | WG | WILLIAMS | Yes | 2021-03-17 | 2021-06-15 | 2.99 | 383545 | 142789 | [7 empty] | 75000 | 175000 | 133545 | [9 empty] | 383545 | 0
TX1901 | Dr. Dyer - Sequoia Spur | WG | WILLIAMS | Yes | 2020-11-01 | 2021-07-31 | 9.0365 | 1809504 | 272772 |  |  |  |  | 407476 | 214131 | 74131 | 135000 | 200000 | 250000 | 275000 | 253766 | [7 empty] | 1809504 | 0
TX1903 | Ramon Franklin Warehouse | WG | Stephensen | Yes | 2021-02-01 | 2021-08-21 | 6.6777 | 1006579 | [5 empty] | 131243 |  |  | 150000 | 150000 | 150000 | 150000 | 150362 | 124974 | [6 empty] | 1006579 | 0
TX2001 | Dr. Lippian - Texarkana | WG | TBD | Yes | 2021-01-28 | 2021-09-25 | 7.9734 | 1639962 | [5 empty] | 103605 |  | 71204 | 150000 | 200000 | 250000 | 250000 | 250000 | 200000 | 165153 | [5 empty] | 1639962 | 0
TX2004 | Marshall Ridge Dev. | WG | TBD | No | DEAD | DEAD | N/A | 37392 | [7 empty] | 37392 | [12 empty] | 37392 | 0
TX2005 | McKinney Development | WG | RH | No | 2021-09-22 | 2022-05-20 | 7.9734 | 1550000 | 1339023 | [7 empty] | 150000 | 150000 | 250000 | 250000 | 250000 | 250000 | 146395 |  | 103605 |  |  |  | 1550000 | 0
TX2008-1 | Dr. Lee - McKinney Development | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 1500000 | [13 empty] | 187500 | 187500 | 187500 | 187500 | 187500 | 562500 |  | 1500000 | 0
TX2006-1 | Sunnyvale Shell | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 1500000 | [11 empty] | 100000 | 187500 | 187500 | 187500 | 187500 | 187500 | 187500 | 275000 |  | 1500000 | 0
TX2006-2 | Sunnyvale Shell - Dr. Luna | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 600000 | [13 empty] | 100000 | 100000 | 125000 | 125000 | 100000 | 50000 |  | 600000 | 0
TX2006-3 | Sunnyvale Shell - Dr. Rohani | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 1500000 | [13 empty] | 100000 | 150000 | 200000 | 200000 | 200000 | 650000 |  | 1500000 | 0
TX2007-1 | Carrllton Shell | WG | TBD | No | 2021-09-22 | 2022-07-20 | 10 | 750000 | [13 empty] | 50000 | 65000 | 65000 | 65000 | 65000 | 440000 |  | 750000 | 0
TX2007-2 | Carrolton Shell - Dr. Bui | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 750000 | [13 empty] | 50000 | 65000 | 65000 | 65000 | 65000 | 440000 |  | 750000 | 0
TX2009 | Alliance Pediatrics-Marsh | WG | TBD | No | DEAD | DEAD |  | 3575 | [7 empty] | 3575 | [12 empty] | 3575 | 0
[8 empty] | 13564568 | [5 empty] | 831737 | 318620 | 226899 | 859512 | 875000 | 1033545 | 1025000 | 1091628 | 1249974 | 1066548 | 830000 | 933605 | 805000 | 2417500 | 0 | 13564568 | 0
PreConstruction |  | TBD | [27 empty] | 0
FL2001 | Elysee Lot 6 | TBD | TBD | No |  |  |  | 61092 | [5 empty] | 61092 | [14 empty] | 61092 | 0
FL2002 | Elysee Lot 7 | TBD | TBD | No |  |  |  | 61092 | [5 empty] | 61092 | [14 empty] | 61092 | 0
OK1924 | Yukon Development | TBD | TBD | No | HOLD | HOLD | HOLD | 2500000 | [18 empty] | 2500000 |  | 2500000 | 0
OK2019 | Santa Fe Development | TBD | JW | No | #REF! | 2021-11-08 | #REF! | 1000000 | [8 empty] | 75000 | 100000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 75000 |  |  |  | 1000000 | 0
OK2025 | Autism in Motion - Sante Fe Dev. | TBD | JW | No | 2021-05-03 | 2021-12-29 | 7.9734 | 1051400 | [8 empty] | 75000 | 100000 | 100000 | 125000 | 125000 | 125000 | 125000 | 125000 | 75000 | 76400 |  |  | 1051400 | 0
OK2028P | Precon - Memorial Park | TBD | TBD | No | DEAD | DEAD |  | 461956 | [6 empty] | 353138 | 108818 | [12 empty] | 461956 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | TBD | JW | No | 2021-05-01 | 2021-10-28 | 5.9801 | [21 empty] | 0 | 0
OK2033-2 | Old School Bagel - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | 175000 | [10 empty] | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 |  |  |  | 175000 | 0
OK2103 | Bethesda - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | 1500000 | [16 empty] | 125000 | 150000 | 1225000 |  | 1500000 | 0
OK2026 | Covell I35 Edmond Dev. | TBD | TBD | No | 2021-06-24 | 2021-08-23 | 1.9934 | 400000 | [10 empty] | 125000 | 150000 | 125000 | [7 empty] | 400000 | 0
OK2034 | Dr. Rex Johnson, DVM - Covel I35 | TBD | TBD | No | 2021-06-25 | 2022-04-22 | 10 | 1750000 | [10 empty] | 100000 | 150000 | 150000 | 150000 | 150000 | 200000 | 200000 | 200000 | 450000 |  | 1750000 | 0
OK2036 | Dr. Matt Cole, DDS | TBD | TBD | No | 2021-08-01 | 2022-03-29 | 7.9734 | 2500000 | [13 empty] | 125000 | 250000 | 350000 | 350000 | 350000 | 1075000 |  | 2500000 | 0
OK2037 | Master Hand Milling | TBD | TBD | No | 2021-10-01 | 2022-09-27 | 11.9934 | 4000000 | [15 empty] | 800000 | 800000 | 800000 | 1600000 |  | 4000000 | 0
OK2102 | Puppy Paws | TBD | TBD | No | 2021-07-26 | 2022-05-23 | 10 | 3000000 | [18 empty] | 3000000 |  | 3000000 | 0
OK2104 | Wimberley Walker Remodel | TBD | TBD | No |  |  |  | 500577 | [7 empty] | 17615 | [10 empty] | 482962 |  | 500577 | 0
OK2105-1 | Valencial Lex - Breakroom 405 | TBD | TBD | No | 2021-08-09 | 2022-04-06 19:12 | 8 | 1500000 | [18 empty] | 1500000 |  | 1500000 | 0
OK2105-2 | Valencial Lex - Christ Fit Gym | TBD | TBD | No |  |  | 0 | 2000000 | [18 empty] | 2000000 |  | 2000000 | 0
OK2106-1 | Fox Lake Shell | TBD | TBD | No |  |  |  | 10000000 | [11 empty] | 125000 | 500000 |  |  |  | 1250000 | 2000000 | 6125000 |  | 10000000 | 0
OK2107 | Jack Be Grocery | TBD | TBD | No | [24 empty] | 0 | 0
OK2108 | Puppy Paws - West Edmond | TBD | TBD | No |  |  |  | 1750000 | [18 empty] | 1750000 |  | 1750000 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | [24 empty] | 0 | 0
OKxxxx | Sears Shell - Hyperbaric Theropy | TBD | TBD | No | [24 empty] | 0 | 0
OKxxxx | AIM - Yukon | TBD | TBD | No | [24 empty] | 0 | 0
OKxxxx | AIM - Additions & OSB | TBD | TBD | No | [24 empty] | 0 | 0
OK1909-3 | Creekwood - All State TI | TBD | TBD | No |  |  |  | 89724 | [18 empty] | 89724 |  | 89724 | 0
OKxxxx | Creekwood - Mike Lackey | TBD | TBD | No | [24 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | [24 empty] | 0 | 0
OKxxxx | Coltrane South - Aya Rowe - Chiro | TBD | TBD | No | [24 empty] | 0 | 0
OKxxxx | Glenpool - Midleton's | TBD | TBD | No | [24 empty] | 0 | 0
OKxxxx | Gleenpool Finance | TBD | TBD | No | [24 empty] | 0 | 0
OKxxxx | Riverwest - Midleton's | TBD | TBD | No | [24 empty] | 0 | 0
OKxxxx | Riverwest - Tropical Smoothie | TBD | TBD | No |  |  |  | 90000 | [18 empty] | 90000 |  | 90000 | 0
TNxxxx | AIM - Memphis TN | TBD | TBD | No | 2021-08-01 | 2022-03-29 |  | 1500000 | [18 empty] | 1500000 |  | 1500000 | 0
TX2101 | Bob Mills - Forth Worth | TBD | TBD | No | 2021-08-28 | 2022-02-24 |  | 200000 | [18 empty] | 200000 |  | 200000 | 0
TX2102-1 | Dr. Abeskharon - San Antonio | TBD | RH | No | [24 empty] | 0 | 0
[29 empty] | 0 | 0
[29 empty] | 0 | 0
[8 empty] | 36090841 | [5 empty] | 122184 | 353138 | 126433 | 150000 | 200000 | 475000 | 700000 | 1050000 | 550000 | 675000 | 1625000 | 2900000 | 3576400 | 23587686 | 0 | 36090841 | 0
0
[7 empty] | Billing Forecast Total | 89094036 | 25064428 | 1360672 | 22474518 | 1376328 | -15656 | 12192800 | 3795406 | 2521609 | 4411810 | 5197007 | 4944226 | 4891305 | 4730957 | 3921521 | 3325512 | 3908964 | 4742979 | 4504754 | 26005186 | 0 | 89094036 | 0
[7 empty] | Billing Goal | [6 empty] | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 | 16008105
[7 empty] | Difference | [6 empty] | -2464245 | 997288.8571 | -685215.6429 | 403417.3571 | 878009.3571 | -125340.6429 | -684509.6429 | -583747.6429 | -1555319 | -2034447 | -2264600 | -758743 | 638219
[7 empty] | Rev Actual | [7 empty] | 2897650
[7 empty] | Rev Goal | [7 empty] | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 | 12779270.2215
[7 empty] | Difference | [7 empty] | 663913.0849
[7 empty] | GP Actual | [7 empty] | 261214
[7 empty] | GP Goal | [7 empty] | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 | 1403910.8085
[7 empty] | Difference | [7 empty] | 15819.1266
[7 empty] | GP % Actual | [7 empty] | 9.01%
[7 empty] | GP % Goal | [7 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
[7 empty] | Difference | [7 empty] | -0.99%
[7 empty] | OH Actual | [7 empty] | 257087
[7 empty] | OH Goal | [7 empty] | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
[7 empty] | Difference | [7 empty] | 17913
[7 empty] | NP Actual | [7 empty] | 4127
[7 empty] | NP Goal | [7 empty] | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 | 500000.0033
[7 empty] | Difference | [7 empty] | -20412.4873
Note on B23: Bob Snyder: Delayed due to Archaelogical Review
Note on I31: Existing Building

## 03 2021
[14 empty] | 2020 | 2021 | [12 empty] | 2022 | 2023
|  | PM | SUP | Permit | Start Date | Comp Date | Duration | Spectrum Value | ProCore Value | Variance | Forecasted Value | Variance |  | Annual | January | February | March | April | May | June | July | August | September | October | November | December |  | Annual | Annual | TOTAL | DELTA
Adam English |  | AE
OK2005 | Quail Springs Shell | AE | DF | Yes | #REF! | #REF! | #REF! | 845876 | [5 empty] | 628337 | 137155 | 19492 | 60892 | [12 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | DF | Yes | #REF! | #REF! | #REF! | 297313 | [5 empty] | 162612 | 95646 | 33342 | 5713 | [12 empty] | 297313 | 0
OK2005-2 | Quail Springs - Just Kids Ped's | AE | DF | Yes | #REF! | #REF! | #REF! | 222517 | [5 empty] | 131745 | 62828 | 27944 | [13 empty] | 222517 | 0
OK2020-1 | Western Shell | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 1207684 | [5 empty] | 244435 | 181308 | 16313 | 286477 | 150000 | 160000 | 160000 | 9151 | [8 empty] | 1207684 | 0
OK2020-2 | Western - Scammahorn | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 267573 | [5 empty] | 46929 | 38525 |  | 45735 | 40000 | 40000 | 40000 | 16384 | [8 empty] | 267573 | 0
OK2020-3 | Western - Dr. Olsen | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 230170 | [5 empty] | 34010 | 31345 |  | 42608 | 40000 | 45000 | 35000 | 2207 | [8 empty] | 230170 | 0
OK2024 | Bodyworx | AE | STROUD | Yes | 2021-02-14 | 2021-08-31 | 6.5781 | 984546 | [5 empty] | 230830 | 155142 | 20934 | 247073 | 100000 | 100000 | 84583 | 0 | 45984 | [7 empty] | 984546 | 0
OK2031 | T-Mobile - Guthrie | AE | JW | Yes | 2021-03-01 | 2021-07-29 | 4.9834 | 723063 | [8 empty] | 79004 | 140000 | 140000 | 163063 | 200996 | [8 empty] | 723063 | 0
OK2039 | Rockwell Daycare | AE | STROUD | Yes | 2021-02-01 | 2021-03-31 | 1.9269 | 81500 | [8 empty] | 81500 | 0 | 0 | [10 empty] | 81500 | 0
[8 empty] | 4860242 | [5 empty] | 1478898 | 701949 | 118025 | 849002 | 470000 | 485000 | 482646 | 228738 | 45984 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4860242 | 0
Bob Solomon |  | BS | [17 empty] | 781920 | [10 empty] | 0
OK1926 | Hunter Pharmacy | BS | DS | Yes | 2020-07-21 | 2021-06-24 | 11.2292 | 9534114 | 8913792 | 620322 | 8917546 | 616568 | 3754 | 4251267 | 974630 | 965506 | 726926 | 1016301 | 817564 | 781920 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 9534114 | 0
OK2006 | El Reno Enhanced Dental | BS | STROUD | Yes | 2020-10-20 | 2021-06-07 | 7.6412 | 1208821 | 1021270 | 187551 | 945919 | 262902 | -75351 | 501155 | 186495 | 202246 | 66602 | 160707 | 91616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1208821 | 0
OK2016 | OneCore | BS | DH | Yes | 2020-10-15 | 2021-12-16 | 14.186 | 13107911 | 12555112 | 552799 | 12611053 | 496858 | 55941 | 802663 | 1051823 | 822272 | 1170091 | 1300000 | 1400000 | 1450000 | 1379154 | 1270563 | 843964 | 843964 | 520154 | 253263 |  |  |  | 13107911 | 0
[8 empty] | 23850846 | [5 empty] | 5555085 | 2212948 | 1990024 | 1963619 | 2477008 | 2309180 | 2231920 | 1379154 | 1270563 | 843964 | 843964 | 520154 | 253263 |  | 0 | 0 | 23850846 | 0
Christopher Goldsmith |  | CG | [5 empty] | Target | [22 empty] | 0
OK1927 | Dr. Nellis | CG | GC | Yes | #REF! | #REF! | #REF! | 890454 | [5 empty] | 890454 | [15 empty] | 890454 | 0
OK1936 | Dr. Fischer | CG | GC | Yes | 2020-06-22 | 2021-04-15 | 9.8671 | 2499778 | [5 empty] | 1697608 | 93223 |  | 247214 | 461733 | [11 empty] | 2499778 | 0
OK1936-TI | Dr. Fischer TI | CG | GC | No | 2021-05-01 | 2021-07-30 | 2.99 | 177819 | [8 empty] | 0 | 75000 | 75000 | 27819 | [9 empty] | 177819 | 0
OK2001 | 61st Development | CG | GC | No | 2021-05-01 | 2021-08-29 | 3.9867 | 700000 | [9 empty] | 65000 | 150000 | 150000 | 150000 | 125000 | 60000 | [6 empty] | 700000 | 0
OK2004 | Dr. Loscuito - 61st Dev. | CG | GC | No | 2021-06-01 | 2021-11-28 | 5.9801 | 469659 | [5 empty] | 32120 | [5 empty] | 50000 | 75000 | 80000 | 80000 | 75000 | 77539 |  |  |  |  | 469659 | 0
OK2018 | Dr. Sandra Mackey - 61st St. Dev. | CG | GC | Yes | 2021-05-01 | 2021-10-28 | 5.9801 | 446790 | [11 empty] | 25000 | 75000 | 100000 | 100000 | 100000 | 46790 |  |  |  |  | 446790 | 0
OK2022 | Just Kids - 61st St. Dev. | CG | GC | No | 2021-05-01 | 2021-10-28 | 5.9801 | 577801 | [11 empty] | 75000 | 100000 | 125000 | 125000 | 100000 | 52801 |  |  |  |  | 577801 | 0
OK2008 | Dr. Gaches | CG | GC | Yes | 2021-04-04 | 2021-07-15 | 3.3887 | 683158 | [5 empty] | 65749 |  |  | 72518 | 85000 | 85000 | 85000 | 69891 | 85000 | 85000 | 50000 | 0 |  |  |  |  | 683158 | 0
OK2014 | Clark Shell | CG | GC | Yes | 2021-03-01 | 2021-12-27 | 10 | 1436404 | [5 empty] | 91138 |  |  | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 175000 | 175000 | 245266 |  |  |  |  | 1436404 | 0
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 648253 | [5 empty] | 124344 |  |  | 0 | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | 60000 | 73909 |  |  |  |  | 648253 | 0
OK2014-2 | Clark Shell - Enhance DDS | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 400187 | [5 empty] | 14681 |  |  | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 35506 |  |  |  |  | 400187 | 0
OK2032-1 | Cross Roads - Shell | CG | GC | No | N/A | N/A | N/A | 0 | [21 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | GC | No | 2021-05-20 | 2021-09-17 | 3.9867 | 175000 | [9 empty] | 25000 | 25000 | 50000 | 50000 | 25000 | [7 empty] | 175000 | 0
OK2032-5 | Cross Roads - Dispensary | CG | GC | No |  |  |  | 0 | [21 empty] | 0 | 0
[8 empty] | 9105303 | [5 empty] | 2916094 | 93223 | 0 | 319732 | 976733 | 600000 | 727819 | 784891 | 805000 | 740000 | 610000 | 531811 | 0 |  | 0 | 0 | 9105303 | 0
Nolan Krampe |  | NK | [5 empty] | Target | [22 empty] | 0
OK2021 | Christian Counciling | NK | NK | Yes | 2021-03-01 | 2021-05-31 | 3.0233 | 52095 | [8 empty] | 0 | 15000 | 20000 | 17095 | [9 empty] | 52095 | 0
[8 empty] | 52095 | [5 empty] | 0 | 0 | 0 | 0 | 15000 | 20000 | 17095 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 52095 | 0
Wes Gaddy |  | WG | [5 empty] | Target | [22 empty] | 0
OK2003 | Enhance Dental - Choctaw | WG | WILLIAMS | Yes |  |  | 0 | 604799 | [5 empty] | 568347 | 879 | 35573 | 656 | -656 | [11 empty] | 604799 | 0
OK2011-1 | Mustang Shell | WG | WILLIAMS | Yes | 2020-09-01 | 2021-03-31 | 7.01 | 940687 | [5 empty] | 720455 | 114649 |  | 105583 | [12 empty] | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 223564 | 819670 |  |  |  |  | 64622 | 39562 | 18328 | 101052 | [12 empty] | 223564 | 0
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 314022 | [5 empty] | 124791 | 64927 | 25844 | 98461 | -1 | [11 empty] | 314022 | 0
OK2038 | Dr. Farmer TI - Wonga Corner | WG | WILLIAMS | Yes | 2021-03-17 | 2021-06-15 | 2.99 | 383545 | 142789 | [7 empty] | 0 | 175000 | 208545 | [10 empty] | 383545 | 0
TX1901 | Dr. Dyer - Sequoia Spur | WG | WILLIAMS | Yes | 2020-11-01 | 2021-07-31 | 9.0365 | 1809504 | 272772 |  |  |  |  | 407476 | 214131 | 74131 | 135778 | 200000 | 250000 | 275000 | 252988 | [8 empty] | 1809504 | 0
TX1903 | Ramon Franklin Warehouse | WG | Stephensen | Yes | 2021-02-01 | 2021-08-21 | 6.6777 | 1006579 | [5 empty] | 131243 |  |  | 0 | 200000 | 200000 | 200000 | 150362 | 124974 | [7 empty] | 1006579 | 0
TX2001 | Dr. Lippian - Texarkana | WG | TBD | Yes | 2021-01-28 | 2021-09-25 | 7.9734 | 1639962 | [5 empty] | 103605 |  | 71204 | 158532 | 200000 | 250000 | 250000 | 241468 | 200000 | 165153 | [6 empty] | 1639962 | 0
TX2005 | McKinney Development | WG | RH | No | 2021-09-22 | 2022-05-20 | 7.9734 | 600000 | 1339023 | [7 empty] | 0 |  |  |  |  | 150000 | 150000 | 150000 | 150000 |  |  |  |  | 600000 | 0
TX2008-1 | Dr. Lee - McKinney Development | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 750000 | [13 empty] | 150000 | 150000 | 150000 | 150000 | 150000 |  |  |  | 750000 | 0
TX2006-1 | Sunnyvale Shell | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 1736318 | [11 empty] | 100000 | 150000 | 175000 | 200000 | 200000 | 200000 | 200000 |  | 511318 |  | 1736318 | 0
TX2006-2 | Sunnyvale Shell - Dr. Luna | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 376000 | [13 empty] | 50000 | 75000 | 75000 | 75000 | 75000 | 0 | 26000 |  | 376000 | 0
TX2006-3 | Sunnyvale Shell - Dr. Rohani | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 376000 | [13 empty] | 50000 | 75000 | 75000 | 75000 | 75000 |  | 26000 |  | 376000 | 0
TX2007-1 | Carrllton Shell | WG | TBD | No | 2021-09-22 | 2022-07-20 | 10 | 1700000 | [13 empty] | 75000 | 125000 | 200000 | 200000 | 200000 |  | 900000 |  | 1700000 | 0
TX2007-2 | Carrolton Shell - Dr. Bui | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 225000 | [14 empty] | 50000 | 50000 | 50000 | 50000 |  | 25000 |  | 225000 | 0
[8 empty] | 12685980 | [5 empty] | 2120539 | 434148 | 225080 | 600062 | 774343 | 908545 | 825000 | 794818 | 974974 | 990153 | 900000 | 900000 | 750000 |  | 1488318 | 0 | 12685980 | 0
PreConstruction |  | TBD | [5 empty] | Target | [22 empty] | 0
FL2001 | Elysee Lot 6 | TBD | TBD | No |  |  |  | 61092 | [5 empty] | 61092 | [15 empty] | 61092 | 0
FL2002 | Elysee Lot 7 | TBD | TBD | No |  |  |  | 61092 | [5 empty] | 61092 | [15 empty] | 61092 | 0
OK1924 | Yukon Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [19 empty] | 2500000 |  | 2500000
OK2019 | Santa Fe Development | TBD | JW | No | #REF! | 2021-11-08 | #REF! | 1000000 | [8 empty] | 0 | 100000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 75000 | 75000 |  |  |  | 1000000 | 0
OK2025 | Autism in Motion - Sante Fe Dev. | TBD | JW | No | 2021-05-03 | 2021-12-29 | 7.9734 | 975000 | [8 empty] | 0 |  | 100000 | 125000 | 150000 | 150000 | 150000 | 150000 | 150000 |  |  |  |  | 975000 | 0
OK2028P | Precon - Memorial Park | TBD | TBD | No | DEAD | DEAD |  | 461956 | [6 empty] | 353138 | 108818 | [13 empty] | 461956 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | TBD | JW | No | 2021-05-01 | 2021-10-28 | 5.9801 | 900000 | [11 empty] | 75000 | 125000 | 125000 | 150000 | 150000 | 150000 | 125000 |  |  |  | 900000 | 0
OK2033-2 | Old School Bagel - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | 175000 | [10 empty] | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 |  |  |  |  | 175000 | 0
OK2103 | Bethesda - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | HOLD | [21 empty] | 0 | HOLD
OK2026 | Covell I35 Edmond Dev. | TBD | TBD | No | 2021-06-24 | 2021-08-23 | 1.9934 | 400000 | [10 empty] | 125000 | 150000 | 125000 | [8 empty] | 400000 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | CG | GC | No | DEAD | DEAD | DEAD | 15630 | [7 empty] | 15630 | [13 empty] | 15630 | 0
OK2032-3 | Cross Roads - State Farm | CG | GC | No | DEAD | DEAD | DEAD | 5720 | [7 empty] | 5720 | [13 empty] | 5720 | 0
OK2034 | Dr. Rex Johnson, DVM - Covel I35 | TBD | TBD | No | 2021-06-25 | 2022-04-22 | 10 | 1750000 | [10 empty] | 100000 | 150000 | 150000 | 150000 | 150000 | 200000 | 200000 | 200000 |  | 450000 |  | 1750000 | 0
OK2036 | Dr. Matt Cole, DDS | TBD | TBD | No | 2021-08-01 | 2022-03-29 | 7.9734 | 1500000 | [13 empty] | 125000 | 175000 | 200000 | 200000 | 200000 |  | 600000 |  | 1500000 | 0
OK2037 | Master Hand Milling | TBD | TBD | No | 2021-10-01 | 2022-09-27 | 11.9934 | 4000000 | [15 empty] | 800000 | 800000 | 800000 |  | 1600000 |  | 4000000 | 0
OK2102 | Puppy Paws | TBD | TBD | No | 2021-07-26 | 2022-05-23 | 10 | 3000000 | [19 empty] | 3000000 |  | 3000000 | 0
OK2104 | Wimberley Walker Remodel | TBD | TBD | No |  |  |  | 500577 | [7 empty] | 17615 | 71648 | [10 empty] | 411314 |  | 500577 | 0
OK2105-1 | Valencial Lex - Breakroom 405 | TBD | TBD | No | 2021-08-09 | 2022-04-06 19:12 | 8 | 150000 | [19 empty] | 150000 |  | 150000 | 0
OK2105-2 | Valencial Lex - Christ Fit Gym | TBD | TBD | Yes |  |  | 0 | 100000 | [10 empty] | 50000 | 50000 | [9 empty] | 100000 | 0
OK2106-1 | Fox Lake Shell | TBD | TBD | No |  |  |  | 10000000 | [12 empty] | 405000 | 780000 | 1100000 | 1300000 | 1400000 | 1400000 |  | 3615000 |  | 10000000 | 0
OK2107 | Jack Be Grocery | TBD | TBD | No |  |  |  | 5000000 | [19 empty] | 5000000 |  | 5000000 | 0
OK2108 | Puppy Paws - West Edmond | TBD | TBD | No |  |  |  | 1750000 | [19 empty] | 1750000 |  | 1750000 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [21 empty] | 0 | HOLD
OKxxxx | Sears Shell - Hyperbaric Theropy | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [21 empty] | 0 | HOLD
OKxxxx | AIM - Yukon | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [21 empty] | 0 | DEAD
OKxxxx | AIM - Additions & OSB | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [21 empty] | 0 | DEAD
OK1909-3 | Creekwood - All State TI | TBD | TBD | No |  |  |  | 89724 | [19 empty] | 89724 |  | 89724 | 0
OKxxxx | Creekwood - Mike Lackey | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Coltrane South - Aya Rowe - Chiro | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Glenpool - Midleton's | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Gleenpool Finance | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Riverwest - Midleton's | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Riverwest - Tropical Smoothie | TBD | TBD | No |  |  |  | 90000 | [19 empty] | 90000 |  | 90000 | 0
TNxxxx | AIM - Memphis TN | TBD | TBD | No | 2021-08-01 | 2022-03-29 |  | 1500000 | [19 empty] | 1500000 |  | 1500000 | 0
TX2004 | Marshall Ridge Dev. | WG | TBD | No | DEAD | DEAD | DEAD | 37392 | [7 empty] | 37392 | [13 empty] | 37392 | 0
TX2009 | Alliance Pediatrics-Marsh | WG | TBD | No | DEAD | DEAD | DEAD | 3575 | [7 empty] | 3575 | [13 empty] | 3575 | 0
TX2101 | Bob Mills - Forth Worth | TBD | TBD | No | 2021-08-28 | 2022-02-24 |  | 2000000 | [19 empty] | 2000000 |  | 2000000 | 0
TX2102-1 | Dr. Abeskharon - San Antonio | TBD | RH | No |  |  |  | 1750000 | [19 empty] | 1750000 |  | 1750000 | 0
[30 empty] | 0 | 0
[30 empty] | 0 | 0
[8 empty] | 37276758 | [5 empty] | 122184 | 353138 | 188750 | 71648 | 100000 | 525000 | 700000 | 1105000 | 1480000 | 1875000 | 2950000 | 3000000 | 2800000 |  | 24506038 | 0 | 39776758 | -2500000
0
[7 empty] | Billing Total | 87831224 | 0 | 0 | 0 | 0 | 0 | 12192800 | 3795406 | 2521879 | 3804063 | 4813084 | 4847725 | 4984480 | 4292601 | 4576521 | 4449117 | 5303964 | 4951965 | 3803263 |  | 25994356 | 0 | 90331224 | -2500000
[7 empty] | Billing Goal | [6 empty] | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 |  | 16008105
[7 empty] | Difference | [6 empty] | -2464245 | 997288.8571 | -684945.6429 | -204329.6429 | 494086.3571 | -221841.6429 | -591334.6429 | -1022103.6429 | -900319 | -910842 | -869600 | -549757 | -63272
[7 empty] | Rev Actual | [7 empty] | 2897650
[7 empty] | Rev Goal | [7 empty] | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 |  | 12779270.2215
[7 empty] | Difference | [7 empty] | 663913.0849
[7 empty] | GP Actual | [7 empty] | 261214
[7 empty] | GP Goal | [7 empty] | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 |  | 1403910.8085
[7 empty] | Difference | [7 empty] | 15819.1266
[7 empty] | GP % Actual | [7 empty] | 9.01%
[7 empty] | GP % Goal | [7 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |  | 10%
[7 empty] | Difference | [7 empty] | -0.99%
[7 empty] | OH Actual | [7 empty] | 257087
[7 empty] | OH Goal | [7 empty] | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 |  | 300000
[7 empty] | Difference | [7 empty] | 17913
[7 empty] | NP Actual | [7 empty] | 4127
[7 empty] | NP Goal | [7 empty] | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 |  | 500000.0033
[7 empty] | Difference | [7 empty] | -20412.4873
Note on B23: Bob Snyder: Delayed due to Archaelogical Review
Note on I31: Existing Building

## 04 2021
[14 empty] | 2020 | 2021 | [12 empty] | 2022 | 2023
|  | PM | SUP | Permit | Start Date | Comp Date | Duration | Spectrum Value | ProCore Value | Variance | Forecasted Value | Variance |  | Annual | January | February | March | April | May | June | July | August | September | October | November | December |  | Annual | Annual | TOTAL | DELTA
Adam English |  | AE
OK2005 | Quail Springs Shell | AE | DF | Yes | #REF! | #REF! | #REF! | 845876 | [5 empty] | 628337 | 137155 | 19492 | 60892 | 0 | 0 | [10 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | DF | Yes | #REF! | #REF! | #REF! | 303150 | [5 empty] | 162612 | 95646 | 33342 | 5713 | 5836.8 | 0 | [10 empty] | 303149.8 | 0.2
OK2005-2 | Quail Springs - Just Kids Ped's | AE | DF | Yes | #REF! | #REF! | #REF! | 222517 | [5 empty] | 131745 | 62828 | 27944 |  |  | 0 | [10 empty] | 222517 | 0
OK2020-1 | Western Shell | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 1207684 | [5 empty] | 244435 | 181308 | 16313 | 286477 | 175064.87 | 173559 | 134935 | 9151 | [8 empty] | 1221242.87 | -13558.87
OK2020-2 | Western - Scammahorn | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 267573 | [5 empty] | 46929 | 38525 |  | 45735 | 40858.44 | 33047 | 40000 | 16384 | [8 empty] | 261478.44 | 6094.56
OK2020-3 | Western - Dr. Olsen | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 230170 | [5 empty] | 34010 | 31345 |  | 42608 | 27036.87 | 28599 | 35000 | 2207 | [8 empty] | 200805.87 | 29364.13
OK2024 | Bodyworx | AE | STROUD | Yes | 2021-02-14 | 2021-08-31 | 6.5781 | 984546 | [5 empty] | 230830 | 155142 | 20934 | 247073 | 88548.33 | 113241 | 84583 | 0 | 45984 | [7 empty] | 986335.33 | -1789.33
OK2031 | T-Mobile - Guthrie | AE | JW | Yes | 2021-03-01 | 2021-07-29 | 4.9834 | 723063 | [8 empty] | 79004 | 201430.48 | 171286 | 163063 | 200996 | [8 empty] | 815779.48 | -92716.48
OK2039 | Rockwell Daycare | AE | STROUD | Yes | 2021-02-01 | 2021-03-31 | 1.9269 | 81500 | [8 empty] | 81500 |  | 0 | 0 | [9 empty] | 81500 | 0
[8 empty] | 4866079 | [5 empty] | 1478898 | 701949 | 118025 | 849002 | 538775.79 | 519732 | 457581 | 228738 | 45984 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4938684.79 | -72605.79
Bob Solomon |  | BS | [17 empty] | 781920 | [10 empty] | 0
OK1926 | Hunter Pharmacy | BS | DS | Yes | 2020-07-21 | 2021-06-24 | 11.2292 | 9534114 | 8913792 | 620322 | 8917546 | 616568 | 3754 | 4251267 | 974630 | 965506 | 726926 | 1007479.26 | 826386 | 781920 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 9534114.26 | -0.26
OK2006 | El Reno Enhanced Dental | BS | STROUD | Yes | 2020-10-20 | 2021-06-07 | 7.6412 | 1208821 | 1021270 | 187551 | 945919 | 262902 | -75351 | 501155 | 186495 | 202246 | 66602 | 48430.03 | 147754.5 | 56138.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1208821.03 | -0.03
OK2016 | OneCore | BS | DH | Yes | 2020-10-15 | 2021-12-16 | 14.186 | 13107911 | 12555112 | 552799 | 12611053 | 496858 | 55941 | 802663 | 1051823 | 822272 | 1170091 | 1068761.19 | 1515619.5 | 1565619.5 | 1379154 | 1270563 | 843964 | 843964 | 520154 | 253263 |  |  |  | 13107911.19 | -0.19
[8 empty] | 23850846 | [5 empty] | 5555085 | 2212948 | 1990024 | 1963619 | 2124670.48 | 2489760 | 2403678 | 1379154 | 1270563 | 843964 | 843964 | 520154 | 253263 |  | 0 | 0 | 23850846.48 | -0.48
Brandon Cheney |  | BS | [17 empty] | 781920 | [10 empty] | 0
OK2019 | Santa Fe Development | TBD | JW | No | #REF! | 2021-11-08 | #REF! | 1000000 | [8 empty] | 0 | 0 | 154842 | 125000 | 125000 | 125000 | 125000 | 125000 | 75000 | 75000 |  |  |  | 929842 | 70158
[8 empty] | 24850846 | [5 empty] | 5555085 | 2212948 | 1990024 | 1963619 | 2124670.48 | 2644602 | 3310598 | 1504154 | 1395563 | 968964 | 968964 | 595154 | 328263 |  | 0 | 0 | 25562608.48 | -711762.48
Christopher Goldsmith |  | CG | [5 empty] | Target | [22 empty] | #VALUE!
OK1927 | Dr. Nellis | CG | GC | Yes | #REF! | #REF! | #REF! | 890454 | [5 empty] | 890454 | [15 empty] | 890454 | 0
OK1936 | Dr. Fischer | CG | GC | Yes | 2020-06-22 | 2021-04-15 | 9.8671 | 2499778 | [5 empty] | 1697608 | 93223 |  | 247214 | 203015.61 | 258717 | [10 empty] | 2499777.61 | 0.39
OK1936-TI | Dr. Fischer TI | CG | GC | No | 2021-05-01 | 2021-07-30 | 2.99 | 177819 | [8 empty] | 0 |  | 112500 | 65319 | [9 empty] | 177819 | 0
OK2001 | 61st Development | CG | GC | No | 2021-05-01 | 2021-08-29 | 3.9867 | 700000 | [11 empty] | 257500 | 257500 | 125000 | 60000 | [6 empty] | 700000 | 0
OK2004 | Dr. Loscuito - 61st Dev. | CG | GC | No | 2021-06-01 | 2021-11-28 | 5.9801 | 469659 | [5 empty] | 32120 | [5 empty] | 50000 | 75000 | 80000 | 80000 | 75000 | 77539 |  |  |  |  | 469659 | 0
OK2018 | Dr. Sandra Mackey - 61st St. Dev. | CG | GC | Yes | 2021-05-01 | 2021-10-28 | 5.9801 | 446790 | [11 empty] | 25000 | 75000 | 100000 | 100000 | 100000 | 46790 |  |  |  |  | 446790 | 0
OK2022 | Just Kids - 61st St. Dev. | CG | GC | No | 2021-05-01 | 2021-10-28 | 5.9801 | 577801 | [11 empty] | 75000 | 100000 | 125000 | 125000 | 100000 | 52801 |  |  |  |  | 577801 | 0
OK2008 | Dr. Gaches | CG | GC | Yes | 2021-04-04 | 2021-07-15 | 3.3887 | 683158 | [5 empty] | 65749 |  |  | 72518 | 31181.82 | 111909 | 111909 | 69891 | 85000 | 85000 | 50000 | 0 |  |  |  |  | 683157.82 | 0.18
OK2014 | Clark Shell | CG | GC | Yes | 2021-03-01 | 2021-12-27 | 10 | 1436404 | [5 empty] | 91138 |  |  | 0 | 55754.38 | 197123 | 197123 | 150000 | 150000 | 175000 | 175000 | 245266 |  |  |  |  | 1436404.38 | -0.38
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 648253 | [5 empty] | 124344 |  |  | 0 |  | 97500 | 97500 | 65000 | 65000 | 65000 | 60000 | 73909 |  |  |  |  | 648253 | 0
OK2014-2 | Clark Shell - Enhance DDS | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 400187 | [5 empty] | 14681 |  |  | 0 |  | 75000 | 75000 | 50000 | 50000 | 50000 | 50000 | 35506 |  |  |  |  | 400187 | 0
OK2032-1 | Cross Roads - Shell | CG | GC | No | N/A | N/A | N/A | 0 | [21 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | GC | No | 2021-05-20 | 2021-09-17 | 3.9867 | 175000 | [10 empty] | 37500 | 62500 | 50000 | 25000 | [7 empty] | 175000 | 0
OK2032-5 | Cross Roads - Dispensary | CG | GC | No |  |  |  | 0 | [21 empty] | 0 | 0
[8 empty] | 9105303 | [5 empty] | 2916094 | 93223 | 0 | 319732 | 289951.81 | 890249 | 1016851 | 892391 | 805000 | 740000 | 610000 | 531811 | 0 |  | 0 | 0 | 9105302.81 | 0.19
Nolan Krampe |  | NK | [5 empty] | Target | [22 empty] | #VALUE!
OK2021 | Christian Counciling | NK | NK | Yes | 2021-03-01 | 2021-05-31 | 3.0233 | 52095 | [8 empty] | 0 | 15000 | 20000 | 17095 | [9 empty] | 52095 | 0
Breakroom 405
Creekwood Allstate
Empite Financial
Christfit Gym
[8 empty] | 52095 | [5 empty] | 0 | 0 | 0 | 0 | 15000 | 20000 | 17095 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 52095 | 0
Wes Gaddy |  | WG | [5 empty] | Target | [22 empty] | #VALUE!
OK2003 | Enhance Dental - Choctaw | WG | WILLIAMS | Yes |  |  | 0 | 604799 | [5 empty] | 568347 | 879 | 35573 | 656 | 0 | [11 empty] | 605455 | -656
OK2011-1 | Mustang Shell | WG | WILLIAMS | Yes | 2020-09-01 | 2021-03-31 | 7.01 | 940687 | [5 empty] | 720455 | 114649 |  | 105583 | [12 empty] | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 226188 | 819670 |  |  |  |  | 64622 | 39562 | 18328 | 101052 | 2623.99 | [11 empty] | 226187.99 | 0.01
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 314022 | [5 empty] | 124791 | 64927 | 25844 | 98461 | 1940 | [11 empty] | 315963 | -1941
OK2038 | Dr. Farmer TI - Wonga Corner | WG | WILLIAMS | Yes | 2021-03-17 | 2021-06-15 | 2.99 | 383545 | 142789 | [7 empty] | 0 | 118932.08 | 264613 | [10 empty] | 383545.08 | -0.08
TX1901 | Dr. Dyer - Sequoia Spur | WG | WILLIAMS | Yes | 2020-11-01 | 2021-07-31 | 9.0365 | 1809504 | 272772 |  |  |  |  | 407476 | 214131 | 74131 | 135778 | 437831.75 | 170722.67 | 195722.67 | 173710.67 | [8 empty] | 1809503.76 | 0.24
TX1903 | Ramon Franklin Warehouse | WG | Stephensen | Yes | 2021-02-01 | 2021-08-21 | 6.6777 | 1006579 | [5 empty] | 131243 |  |  | 0 |  | 300000 | 300000 | 150362 | 124974 | [7 empty] | 1006579 | 0
TX2001 | Dr. Lippian - Texarkana | WG | TBD | Yes | 2021-01-28 | 2021-09-25 | 7.9734 | 1639962 | [5 empty] | 103605 |  | 71204 | 158532 | 124183.45 | 287500 | 287500 | 242285 | 200000 | 165153 | [6 empty] | 1639962.45 | -0.45
TX2005 | McKinney Development | WG | RH | No | 2021-09-22 | 2022-05-20 | 7.9734 | 600000 | 1339023 | [7 empty] | 0 |  |  |  |  | 150000 | 150000 | 150000 | 150000 |  |  |  |  | 600000 | 0
TX2008-1 | Dr. Lee - McKinney Development | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 750000 | [13 empty] | 150000 | 150000 | 150000 | 150000 | 150000 |  |  |  | 750000 | 0
TX2006-1 | Sunnyvale Shell | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 1736318 | [11 empty] | 100000 | 150000 | 175000 | 200000 | 200000 | 200000 | 200000 |  | 511318 |  | 1736318 | 0
TX2006-2 | Sunnyvale Shell - Dr. Luna | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 376000 | [13 empty] | 50000 | 75000 | 75000 | 75000 | 75000 | 0 | 26000 |  | 376000 | 0
TX2006-3 | Sunnyvale Shell - Dr. Rohani | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 376000 | [13 empty] | 50000 | 75000 | 75000 | 75000 | 75000 |  | 26000 |  | 376000 | 0
TX2007-1 | Carrllton Shell | WG | TBD | No | 2021-09-22 | 2022-07-20 | 10 | 1700000 | [13 empty] | 75000 | 125000 | 200000 | 200000 | 200000 |  | 900000 |  | 1700000 | 0
TX2007-2 | Carrolton Shell - Dr. Bui | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 225000 | [14 empty] | 50000 | 50000 | 50000 | 50000 |  | 25000 |  | 225000 | 0
[8 empty] | 12688604 | 2574254 | 0 | 0 | 0 | 0 | 2120539 | 434148 | 225080 | 600062 | 685511.27 | 1022835.67 | 883222.67 | 716357.67 | 974974 | 990153 | 900000 | 900000 | 750000 |  | 1488318 | 0 | 12691201.28 | -2597.28
PreConstruction |  | TBD | [5 empty] | Target
FL2001 | Elysee Lot 6 | TBD | TBD | No |  |  |  | 61092 | [5 empty] | 61092 | [15 empty] | 61092 | 0
FL2002 | Elysee Lot 7 | TBD | TBD | No |  |  |  | 61092 | [5 empty] | 61092 | [15 empty] | 61092 | 0
OK1924 | Yukon Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [21 empty] | 0 | HOLD
OK2025 | Autism in Motion - Sante Fe Dev. | TBD | JW | No | 2021-05-03 | 2021-12-29 | 7.9734 | 975000 | [8 empty] | 0 |  | 100000 | 125000 | 150000 | 150000 | 150000 | 150000 | 150000 |  |  |  |  | 975000 | 0
OK2028P | Precon - Memorial Park | TBD | TBD | No | DEAD | DEAD |  | 461956 | [6 empty] | 353138 | 108818 | [13 empty] | 461956 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | TBD | JW | No | 2021-05-01 | 2021-10-28 | 5.9801 | 900000 | [11 empty] | 75000 | 125000 | 125000 | 150000 | 150000 | 150000 | 125000 |  |  |  | 900000 | 0
OK2033-2 | Old School Bagel - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | 175000 | [10 empty] | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 |  |  |  |  | 175000 | 0
OK2103 | Bethesda - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | HOLD | [21 empty] | 0 | HOLD
OK2026 | Covell I35 Edmond Dev. | TBD | TBD | No | 2021-06-24 | 2021-08-23 | 1.9934 | 400000 | [10 empty] | 125000 | 150000 | 125000 | [8 empty] | 400000 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | CG | GC | No | DEAD | DEAD | DEAD | 15630 | [7 empty] | 15630 | [13 empty] | 15630 | 0
OK2032-3 | Cross Roads - State Farm | CG | GC | No | DEAD | DEAD | DEAD | 5720 | [7 empty] | 5720 | [13 empty] | 5720 | 0
OK2034 | Dr. Rex Johnson, DVM - Covel I35 | TBD | TBD | No | 2021-06-25 | 2022-04-22 | 10 | 1750000 | [10 empty] | 100000 | 150000 | 150000 | 150000 | 150000 | 200000 | 200000 | 200000 |  | 450000 |  | 1750000 | 0
OK2036 | Dr. Matt Cole, DDS | TBD | TBD | No | 2021-08-01 | 2022-03-29 | 7.9734 | 1500000 | [13 empty] | 125000 | 175000 | 200000 | 200000 | 200000 |  | 600000 |  | 1500000 | 0
OK2037 | Master Hand Milling | TBD | TBD | No | 2021-10-01 | 2022-09-27 | 11.9934 | 4000000 | [15 empty] | 800000 | 800000 | 800000 |  | 1600000 |  | 4000000 | 0
OK2102 | Puppy Paws | TBD | TBD | No | 2021-07-26 | 2022-05-23 | 10 | 3000000 | [19 empty] | 3000000 |  | 3000000 | 0
OK2104 | Wimberley Walker Remodel | TBD | TBD | No |  |  |  | 500577 | [7 empty] | 17615 | 71648 | [10 empty] | 411314 |  | 500577 | 0
OK2105-1 | Valencial Lex - Breakroom 405 | TBD | TBD | No | 2021-08-09 | 2022-04-06 19:12 | 8 | 150000 | [19 empty] | 150000 |  | 150000 | 0
OK2105-2 | Valencial Lex - Christ Fit Gym | TBD | TBD | Yes |  |  | 0 | 100000 | [10 empty] | 50000 | 50000 | [9 empty] | 100000 | 0
OK2106-1 | Fox Lake Shell | TBD | TBD | No |  |  |  | 10000000 | [12 empty] | 405000 | 780000 | 1100000 | 1300000 | 1400000 | 1400000 |  | 3615000 |  | 10000000 | 0
OK2107 | Jack Be Grocery | TBD | TBD | No |  |  |  | 5000000 | [19 empty] | 5000000 |  | 5000000 | 0
OK2108 | Puppy Paws - West Edmond | TBD | TBD | No |  |  |  | 1750000 | [19 empty] | 1750000 |  | 1750000 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [21 empty] | 0 | HOLD
OKxxxx | Sears Shell - Hyperbaric Theropy | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [21 empty] | 0 | HOLD
OKxxxx | AIM - Yukon | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [21 empty] | 0 | DEAD
OKxxxx | AIM - Additions & OSB | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [21 empty] | 0 | DEAD
OK1909-3 | Creekwood - All State TI | TBD | TBD | No |  |  |  | 89724 | [19 empty] | 89724 |  | 89724 | 0
OKxxxx | Creekwood - Mike Lackey | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Coltrane South - Aya Rowe - Chiro | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Glenpool - Midleton's | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Gleenpool Finance | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Riverwest - Midleton's | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Riverwest - Tropical Smoothie | TBD | TBD | No |  |  |  | 90000 | [19 empty] | 90000 |  | 90000 | 0
TNxxxx | AIM - Memphis TN | TBD | TBD | No | 2021-08-01 | 2022-03-29 |  | 1500000 | [19 empty] | 1500000 |  | 1500000 | 0
TX2004 | Marshall Ridge Dev. | WG | TBD | No | DEAD | DEAD | DEAD | 37392 | [7 empty] | 37392 | [13 empty] | 37392 | 0
TX2009 | Alliance Pediatrics-Marsh | WG | TBD | No | DEAD | DEAD | DEAD | 3575 | [7 empty] | 3575 | [13 empty] | 3575 | 0
TX2101 | Bob Mills - Forth Worth | TBD | TBD | No | 2021-08-28 | 2022-02-24 |  | 2000000 | [19 empty] | 2000000 |  | 2000000 | 0
TX2102-1 | Dr. Abeskharon - San Antonio | TBD | RH | No |  |  |  | 1750000 | [19 empty] | 1750000 |  | 1750000 | 0
[30 empty] | 0 | 0
[30 empty] | 0 | 0
[8 empty] | 36276758 | [5 empty] | 122184 | 353138 | 188750 | 71648 | 0 | 400000 | 575000 | 980000 | 1355000 | 1750000 | 2825000 | 2925000 | 2725000 |  | 22006038 | 0 | 36276758 | 0
0
[7 empty] | Billing Total | 86839685 | 2574254 | 0 | 0 | 0 | 0 | 12192800 | 3795406 | 2521879 | 3804063 | 3653909.35 | 5342576.67 | 5353427.67 | 4196640.67 | 4451521 | 4324117 | 5178964 | 4876965 | 3728263 |  | 23494356 | 0 | 86914888.36 | -75203.36
[7 empty] | Billing Goal | [6 empty] | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 |  | 16008105
[7 empty] | Difference | [6 empty] | -2464245 | 997288.8571 | -684945.6429 | -204329.6429 | -665088.2929 | 273010.0271 | -222386.9729 | -1118063.9729 | -1025319 | -1035842 | -994600 | -624757 | -138272
[7 empty] | Rev Actual | [7 empty] | 2897650 | 3085444 | 3369732
[7 empty] | Rev Goal | [7 empty] | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 |  | 12779270.2215
[7 empty] | Difference | [7 empty] | 663913.0849 | 525435.8876 | 169832.1532
[7 empty] | GP Actual | [7 empty] | 261214 | 325090 | 157521
[7 empty] | GP Goal | [7 empty] | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 |  | 1403910.8085
[7 empty] | Difference | [7 empty] | 15819.1266 | 43851.4788 | -194015.0348
[7 empty] | GP % Actual | [7 empty] | 9.01% | 10.54% | 4.67%
[7 empty] | GP % Goal | [7 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |  | 10%
[7 empty] | Difference | [7 empty] | -0.99% | 0.54% | -5.33%
[7 empty] | OH Actual | [7 empty] | 256248 | 250107 | 305940
[7 empty] | OH Goal | [7 empty] | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 |  | 300000
[7 empty] | Difference | [7 empty] | 18752 | 24893 | -30940
[7 empty] | NP Actual | [7 empty] | 4126 | 74711 | -101036
[7 empty] | NP Goal | [7 empty] | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 |  | 500000.0033
[7 empty] | Difference | [7 empty] | -20413.4873 | 46587.1479 | -136189.6035
Note on B26: Bob Snyder: Delayed due to Archaelogical Review
Note on I34: Existing Building

## 05 2021
[14 empty] | 2020 | 2021 | [12 empty] | 2022 | 2023
|  | PM | SUP | Permit | Start Date | Comp Date | Duration | Spectrum Value | ProCore Value | Variance | Forecasted Value | Variance |  | Annual | January | February | March | April | May | June | July | August | September | October | November | December |  | Annual | Annual | TOTAL | DELTA
Adam English |  | AE
OK2005 | Quail Springs Shell | AE | DF | Yes | #REF! | #REF! | #REF! | 845876 | [5 empty] | 628337 | 137155 | 19492 | 60892 | 0 | 0 | [10 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | DF | Yes | #REF! | #REF! | #REF! | 303150 | [5 empty] | 162612 | 95646 | 33342 | 5713 | 5836.8 | 0 | [10 empty] | 303149.8 | 0.2
OK2005-2 | Quail Springs - Just Kids Ped's | AE | DF | Yes | #REF! | #REF! | #REF! | 222517 | [5 empty] | 131745 | 62828 | 27944 | 0 | 0 | 0 | [10 empty] | 222517 | 0
OK2020-1 | Western Shell | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 1207684 | [5 empty] | 244435 | 181308 | 16313 | 286477 | 175064.87 | 173559 | 134935 | 9151 | [8 empty] | 1221242.87 | -13558.87
OK2020-2 | Western - Scammahorn | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 267573 | [5 empty] | 46929 | 38525 | 0 | 45735 | 40858.44 | 33047 | 40000 | 16384 | [8 empty] | 261478.44 | 6094.56
OK2020-3 | Western - Dr. Olsen | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 230170 | [5 empty] | 34010 | 31345 | 0 | 42608 | 27036.87 | 28599 | 35000 | 2207 | [8 empty] | 200805.87 | 29364.13
OK2024 | Bodyworx | AE | STROUD | Yes | 2021-02-14 | 2021-08-31 | 6.5781 | 984546 | [5 empty] | 230830 | 155142 | 20934 | 247073 | 88548.33 | 113241 | 84583 | 0 | 45984 | [7 empty] | 986335.33 | -1789.33
OK2031 | T-Mobile - Guthrie | AE | JW | Yes | 2021-03-01 | 2021-07-29 | 4.9834 | 723063 | [5 empty] | 0 | 0 | 0 | 79004 | 201430.48 | 171286 | 163063 | 200996 | [8 empty] | 815779.48 | -92716.48
OK2039 | Rockwell Daycare | AE | STROUD | Yes | 2021-02-01 | 2021-03-31 | 1.9269 | 81500 | [5 empty] | 0 | 0 | 0 | 81500 | 0 | 0 | 0 | [9 empty] | 81500 | 0
[8 empty] | 4866079 | [5 empty] | 1478898 | 701949 | 118025 | 849002 | 538775.79 | 519732 | 457581 | 228738 | 45984 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4938684.79 | -72605.79
Bob Solomon |  | BS | [28 empty] | 0
OK1926 | Hunter Pharmacy | BS | DS | Yes | 2020-07-21 | 2021-06-24 | 11.2292 | 9534114 | 8913792 | 620322 | 8917546 | 616568 | 3754 | 4251267 | 974630 | 965506 | 726926 | 1007479.26 | 748387 | 781920 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 9456115.26 | 77998.74
OK2006 | El Reno Enhanced Dental | BS | STROUD | Yes | 2020-10-20 | 2021-06-07 | 7.6412 | 1208821 | 1021270 | 187551 | 945919 | 262902 | -75351 | 501155 | 186495 | 202246 | 66602 | 48430.03 | 7649 | 56138.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1068715.53 | 140105.47
OK2016 | OneCore | BS | DH | Yes | 2020-10-15 | 2021-12-16 | 14.186 | 13107911 | 12555112 | 552799 | 12611053 | 496858 | 55941 | 802663 | 1051823 | 822272 | 1170091 | 1068761.19 | 823660 | 1565619.5 | 1379154 | 1270563 | 843964 | 843964 | 520154 | 253263 |  |  |  | 12415951.69 | 691959.31
[8 empty] | 23850846 | [5 empty] | 5555085 | 2212948 | 1990024 | 1963619 | 2124670.48 | 1579696 | 2403678 | 1379154 | 1270563 | 843964 | 843964 | 520154 | 253263 |  | 0 | 0 | 22940782.48 | 910063.52
Brandon Cheney |  | BS
OK2019 | Santa Fe Development | TBD | JW | No | #REF! | 2021-11-08 | #REF! | 1000000 | [8 empty] | 0 | 0 | 154842 | 125000 | 125000 | 125000 | 125000 | 125000 | 75000 | 75000 |  |  |  | 929842 | 70158
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | TBD | JW | No | 2021-05-01 | 2021-10-28 | 5.9801 | 900000 | [9 empty] | 0 | 0 | 75000 | 125000 | 125000 | 150000 | 150000 | 150000 | 125000 |  |  |  | 900000 | 0
OK2033-2 | Old School Bagel - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | 175000 | [9 empty] | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 |  |  |  |  | 150000 | 25000
OK2103 | Bethesda - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | HOLD | [21 empty] | 0 | HOLD
OK2105-1 | Valencial Flex - Breakroom 405 | TBD | TBD | No | 2021-08-09 | 2022-04-06 19:12 | 8 | 150000 | [19 empty] | 150000 |  | 150000 | 0
OK2105-2 | Valencial Flex - Christ Fit Gym | TBD | TBD | Yes |  |  | 0 | 100000 | [10 empty] | 50000 | 50000 | [9 empty] | 100000 | 0
[8 empty] | 2325000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 204842 | 275000 | 275000 | 275000 | 300000 | 300000 | 250000 | 200000 |  | 150000 | 0 | 2229842 | 95158
Christopher Goldsmith |  | CG
OK1927 | Dr. Nellis | CG | GC | Yes | #REF! | #REF! | #REF! | 890454 | [5 empty] | 890454 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 890454 | 0
OK1936 | Dr. Fischer | CG | GC | Yes | 2020-06-22 | 2021-04-15 | 9.8671 | 2499778 | [5 empty] | 1697608 | 93223 | 0 | 247214 | 203016 | 0 | [10 empty] | 2241061 | 258717
OK1936-TI | Dr. Fischer TI | CG | GC | No | 2021-05-01 | 2021-07-30 | 2.99 | 177819 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 65319 | [9 empty] | 65319 | 112500
OK2001 | 61st Development | CG | GC | No | 2021-05-01 | 2021-08-29 | 3.9867 | 700000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 257500 | 257500 | 125000 | 60000 | [6 empty] | 700000 | 0
OK2004 | Dr. Loscuito - 61st Dev. | CG | GC | No | 2021-06-01 | 2021-11-28 | 5.9801 | 469659 | [5 empty] | 32120 | 0 | 0 | 0 | 0 | 0 | 50000 | 75000 | 80000 | 80000 | 75000 | 77539 |  |  |  |  | 469659 | 0
OK2018 | Dr. Sandra Mackey - 61st St. Dev. | CG | GC | Yes | 2021-05-01 | 2021-10-28 | 5.9801 | 446790 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 33274 | 25000 | 75000 | 100000 | 100000 | 100000 | 46790 |  |  |  |  | 480064 | -33274
OK2022 | Just Kids - 61st St. Dev. | CG | GC | No | 2021-05-01 | 2021-10-28 | 5.9801 | 577801 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 100000 | 125000 | 125000 | 100000 | 52801 |  |  |  |  | 577801 | 0
OK2008 | Dr. Gaches | CG | GC | Yes | 2021-04-04 | 2021-07-15 | 3.3887 | 683158 | [5 empty] | 65749 | 0 | 0 | 72518 | 31181.82 | 36101 | 111909 | 69891 | 85000 | 85000 | 50000 | 0 |  |  |  |  | 607349.82 | 75808.18
OK2014 | Clark Shell | CG | GC | Yes | 2021-03-01 | 2021-12-27 | 10 | 1436404 | [5 empty] | 91138 | 0 | 0 | 0 | 55754.38 | 185059 | 197123 | 150000 | 150000 | 175000 | 175000 | 245266 |  |  |  |  | 1424340.38 | 12063.62
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 648253 | [5 empty] | 124344 | 0 | 0 | 0 | 0 | 0 | 97500 | 65000 | 65000 | 65000 | 60000 | 73909 |  |  |  |  | 550753 | 97500
OK2014-2 | Clark Shell - Enhance DDS | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 400187 | [5 empty] | 14681 | 0 | 0 | 0 | 0 | 0 | 75000 | 50000 | 50000 | 50000 | 50000 | 35506 |  |  |  |  | 325187 | 75000
OK2032-1 | Cross Roads - Shell | CG | GC | No | N/A | N/A | N/A | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | GC | No | 2021-05-20 | 2021-09-17 | 3.9867 | 175000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 62500 | 50000 | 25000 | [7 empty] | 137500 | 37500
OK2032-5 | Cross Roads - Dispensary | CG | GC | No |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
[8 empty] | 9105303 | [5 empty] | 2916094 | 93223 | 0 | 319732 | 289952.2 | 254434 | 1016851 | 892391 | 805000 | 740000 | 610000 | 531811 | 0 |  | 0 | 0 | 8469488.2 | 635814.8
Kevin Trosper |  | BS
| Breakroom 405 | [29 empty] | 0
| Creekwood Allstate | [29 empty] | 0
| Empite Financial | [29 empty] | 0
| Christfit Gym | [29 empty] | 0
[30 empty] | 0 | 0
[30 empty] | 0 | 0
[8 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Nolan Krampe |  | NK
OK2021 | Christian Counciling | NK | NK | Yes | 2021-03-01 | 2021-05-31 | 3.0233 | 52095 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | [9 empty] | 52095 | 0
[8 empty] | 52095 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 52095 | 0
Wes Gaddy |  | WG | [5 empty] | Target
OK2003 | Enhance Dental - Choctaw | WG | WILLIAMS | Yes |  |  | 0 | 604799 | [5 empty] | 568347 | 879 | 35573 | 656 | 0 | [11 empty] | 605455 | -656
OK2011-1 | Mustang Shell | WG | WILLIAMS | Yes | 2020-09-01 | 2021-03-31 | 7.01 | 940687 | [5 empty] | 720455 | 114649 |  | 105583 | [12 empty] | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 226188 | 819670 |  |  |  |  | 64622 | 39562 | 18328 | 101052 | 2623.99 | [11 empty] | 226187.99 | 0.01
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 314022 | [5 empty] | 124791 | 64927 | 25844 | 98461 | 1940 | [11 empty] | 315963 | -1941
OK2038 | Dr. Farmer TI - Wonga Corner | WG | WILLIAMS | Yes | 2021-03-17 | 2021-06-15 | 2.99 | 383545 | 142789 | [7 empty] | 0 | 118932 | 110310 | [10 empty] | 229242 | 154303
TX1901 | Dr. Dyer - Sequoia Spur | WG | WILLIAMS | Yes | 2020-11-01 | 2021-07-31 | 9.0365 | 1809504 | 272772 |  |  |  |  | 407476 | 214131 | 74131 | 135778 | 437831.75 | 31174 | 195722.67 | 173710.67 | [8 empty] | 1669955.09 | 139548.91
TX1903 | Ramon Franklin Warehouse | WG | Stephensen | Yes | 2021-02-01 | 2021-08-21 | 6.6777 | 1006579 | [5 empty] | 131243 |  |  | 0 |  | 83010 | 300000 | 150362 | 124974 | [7 empty] | 789589 | 216990
TX2001 | Dr. Lippian - Texarkana | WG | TBD | Yes | 2021-01-28 | 2021-09-25 | 7.9734 | 1639962 | [5 empty] | 103605 |  | 71204 | 158532 | 124183.45 | 320119 | 287500 | 242285 | 200000 | 165153 | [6 empty] | 1672581.45 | -32619.45
TX2005 | McKinney Development | WG | RH | No | 2021-09-22 | 2022-05-20 | 7.9734 | 600000 | 1339023 | [7 empty] | 0 |  |  |  |  | 150000 | 150000 | 150000 | 150000 |  |  |  |  | 600000 | 0
TX2008-1 | Dr. Lee - McKinney Development | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 750000 | [13 empty] | 150000 | 150000 | 150000 | 150000 | 150000 |  |  |  | 750000 | 0
TX2006-1 | Sunnyvale Shell | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 1736318 | [11 empty] | 100000 | 150000 | 175000 | 200000 | 200000 | 200000 | 200000 |  | 511318 |  | 1736318 | 0
TX2006-2 | Sunnyvale Shell - Dr. Luna | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 376000 | [13 empty] | 50000 | 75000 | 75000 | 75000 | 75000 | 0 | 26000 |  | 376000 | 0
TX2006-3 | Sunnyvale Shell - Dr. Rohani | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 376000 | [13 empty] | 50000 | 75000 | 75000 | 75000 | 75000 |  | 26000 |  | 376000 | 0
TX2007-1 | Carrllton Shell | WG | TBD | No | 2021-09-22 | 2022-07-20 | 10 | 1700000 | [13 empty] | 75000 | 125000 | 200000 | 200000 | 200000 |  | 900000 |  | 1700000 | 0
TX2007-2 | Carrolton Shell - Dr. Bui | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 225000 | [14 empty] | 50000 | 50000 | 50000 | 50000 |  | 25000 |  | 225000 | 0
TX2101 | Bob Mills - Forth Worth | TBD | TBD | No | 2021-08-28 | 2022-02-24 |  | 2000000 | [10 empty] | 105517 | [8 empty] | 2000000 |  | 2105517 | -105517
[8 empty] | 14688604 | [5 empty] | 2120539 | 434148 | 225080 | 600062 | 685511.19 | 650130 | 883222.67 | 716357.67 | 974974 | 990153 | 900000 | 900000 | 750000 |  | 3488318 | 0 | 14318495.53 | 370108.47
PreConstruction |  | TBD
FL2001 | Elysee Lot 6 | TBD | TBD | No |  |  |  | 61092 | [5 empty] | 61092 |  |  |  | 73311 | 0 | [10 empty] | 134403 | -73311
FL2002 | Elysee Lot 7 | TBD | TBD | No |  |  |  | 61092 | [5 empty] | 61092 |  |  |  | 73311 | 0 | [10 empty] | 134403 | -73311
OK1924 | Yukon Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [9 empty] | 0 | 0 | [10 empty] | 0 | HOLD
OK2025 | Autism in Motion - Sante Fe Dev. | TBD | JW | No | 2021-05-03 | 2021-12-29 | 7.9734 | 975000 | [8 empty] | 0 | 0 | 0 | 125000 | 150000 | 150000 | 150000 | 150000 | 150000 |  |  |  |  | 875000 | 100000
OK2028P | Precon - Memorial Park | TBD | TBD | No | DEAD | DEAD |  | 461956 | [6 empty] | 353138 | 108818 |  | 0 | 0 | [10 empty] | 461956 | 0
OK2026 | Covell I35 Edmond Dev. | TBD | TBD | No | 2021-06-24 | 2021-08-23 | 1.9934 | 400000 | [9 empty] | 0 | 0 | 150000 | 125000 | [8 empty] | 275000 | 125000
OK2032-2 | Cross Roads - Dr. Rhodes | CG | GC | No | DEAD | DEAD | DEAD | 15630 | [7 empty] | 15630 |  | 0 | 0 | [10 empty] | 15630 | 0
OK2032-3 | Cross Roads - State Farm | CG | GC | No | DEAD | DEAD | DEAD | 5720 | [7 empty] | 5720 |  | 0 | 0 | [10 empty] | 5720 | 0
OK2034 | Dr. Rex Johnson, DVM - Covel I35 | TBD | TBD | No | 2021-06-25 | 2022-04-22 | 10 | 1750000 | [9 empty] | 233134 | 0 | 150000 | 150000 | 150000 | 150000 | 200000 | 200000 | 200000 |  | 450000 |  | 1883134 | -133134
OK2036 | Dr. Matt Cole, DDS | TBD | TBD | No | 2021-08-01 | 2022-03-29 | 7.9734 | 1500000 | [9 empty] | 0 | 41062 |  |  | 125000 | 175000 | 200000 | 200000 | 200000 |  | 600000 |  | 1541062 | -41062
OK2037 | Master Hand Milling | TBD | TBD | No | 2021-10-01 | 2022-09-27 | 11.9934 | 4000000 | [9 empty] | 0 | 0 |  |  |  |  | 800000 | 800000 | 800000 |  | 1600000 |  | 4000000 | 0
OK2102 | Puppy Paws | TBD | TBD | No | 2021-07-26 | 2022-05-23 | 10 | 3000000 | [9 empty] | 0 | 0 | [8 empty] | 3000000 |  | 3000000 | 0
OK2104 | Wimberley Walker Remodel | TBD | TBD | No |  |  |  | 500577 | [7 empty] | 17615 | 71648 | [10 empty] | 411314 |  | 500577 | 0
OK2106-1 | Fox Lake Shell | TBD | TBD | No |  |  |  | 10000000 | [12 empty] | 405000 | 780000 | 1100000 | 1300000 | 1400000 | 1400000 |  | 3615000 |  | 10000000 | 0
OK2107 | Jack Be Grocery | TBD | TBD | No |  |  |  | 5000000 | [19 empty] | 5000000 |  | 5000000 | 0
OK2108 | Puppy Paws - West Edmond | TBD | TBD | No |  |  |  | 1750000 | [19 empty] | 1750000 |  | 1750000 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [21 empty] | 0 | HOLD
OKxxxx | Sears Shell - Hyperbaric Theropy | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [21 empty] | 0 | HOLD
OKxxxx | AIM - Yukon | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [21 empty] | 0 | DEAD
OKxxxx | AIM - Additions & OSB | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [21 empty] | 0 | DEAD
OK1909-3 | Creekwood - All State TI | TBD | TBD | No |  |  |  | 89724 | [19 empty] | 89724 |  | 89724 | 0
OKxxxx | Creekwood - Mike Lackey | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Coltrane South - Aya Rowe - Chiro | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Glenpool - Midleton's | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Gleenpool Finance | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Riverwest - Midleton's | TBD | TBD | No | [25 empty] | 0 | 0
OKxxxx | Riverwest - Tropical Smoothie | TBD | TBD | No |  |  |  | 90000 | [19 empty] | 90000 |  | 90000 | 0
TNxxxx | AIM - Memphis TN | TBD | TBD | No | 2021-08-01 | 2022-03-29 |  | 1500000 | [19 empty] | 1500000 |  | 1500000 | 0
TX2004 | Marshall Ridge Dev. | WG | TBD | No | DEAD | DEAD | DEAD | 37392 | [7 empty] | 37392 |  | 0 | 0 | [10 empty] | 37392 | 0
TX2009 | Alliance Pediatrics-Marsh | WG | TBD | No | DEAD | DEAD | DEAD | 3575 | [7 empty] | 3575 |  | 0 | 0 | [10 empty] | 3575 | 0
TX2102-1 | Dr. Abeskharon - San Antonio | TBD | RH | No |  |  |  | 1750000 | [19 empty] | 1750000 |  | 1750000 | 0
[30 empty] | 0 | 0
[30 empty] | 0 | 0
[8 empty] | 32951758 | [5 empty] | 122184 | 353138 | 188750 | 71648 | 379756 | 41062 | 425000 | 830000 | 1205000 | 1575000 | 2650000 | 2750000 | 2600000 |  | 19856038 | 0 | 33047576 | -95818
0
[7 empty] | Billing Total | 87839685 | 0 | 0 | 0 | 0 | 0 | 12192800 | 3795406 | 2521879 | 3804063 | 4018665.66 | 3249896 | 5513427.67 | 4321640.67 | 4576521 | 4449117 | 5303964 | 4951965 | 3803263 |  | 23494356 | 0 | 85996964 | 1842721
[7 empty] | Billing Goal | [6 empty] | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 |  | 16008105
[7 empty] | Difference | [6 empty] | -2464245 | 997288.8571 | -684945.6429 | -204329.6429 | -300331.9829 | -1819670.6429 | -62386.9729 | -993063.9729 | -900319 | -910842 | -869600 | -549757 | -63272
[7 empty] | Rev Actual | [7 empty] | 2897650 | 3085444 | 3369732
[7 empty] | Rev Goal | [7 empty] | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 |  | 12779270.2215
[7 empty] | Difference | [7 empty] | 663913.0849 | 525435.8876 | 169832.1532
[7 empty] | GP Actual | [7 empty] | 261214 | 325090 | 157521
[7 empty] | GP Goal | [7 empty] | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 |  | 1403910.8085
[7 empty] | Difference | [7 empty] | 15819.1266 | 43851.4788 | -194015.0348
[7 empty] | GP % Actual | [7 empty] | 9.01% | 10.54% | 4.67%
[7 empty] | GP % Goal | [7 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |  | 10%
[7 empty] | Difference | [7 empty] | -0.99% | 0.54% | -5.33%
[7 empty] | OH Actual | [7 empty] | 256248 | 250107 | 305940
[7 empty] | OH Goal | [7 empty] | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 |  | 300000
[7 empty] | Difference | [7 empty] | 18752 | 24893 | -30940
[7 empty] | NP Actual | [7 empty] | 4126 | 74711 | -101036
[7 empty] | NP Goal | [7 empty] | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 |  | 500000.0033
[7 empty] | Difference | [7 empty] | -20413.4873 | 46587.1479 | -136189.6035
Note on B31: Bob Snyder: Delayed due to Archaelogical Review
Note on I39: Existing Building

## 06 2021
[14 empty] | 2020 | 2021 | [12 empty] | 2022 | 2023
|  | PM | SUP | Permit | Start Date | Comp Date | Duration | Spectrum Value | ProCore Value | Variance | Forecasted Value | Variance |  | Annual | January | February | March | April | May | June | July | August | September | October | November | December |  | Annual | Annual | TOTAL | DELTA
Adam English |  | AE
OK2005 | Quail Springs Shell | AE | DF | Yes | #REF! | #REF! | #REF! | 845876 | [5 empty] | 628337 | 137155 | 19492 | 60892 | 0 | 0 | 0 | 0 | [8 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | DF | Yes | #REF! | #REF! | #REF! | 303150 | [5 empty] | 162612 | 95646 | 33342 | 5713 | 5837 | 0 | 0 | [9 empty] | 303150 | 0
OK2005-2 | Quail Springs - Just Kids Ped's | AE | DF | Yes | #REF! | #REF! | #REF! | 222517 | [5 empty] | 131745 | 62828 | 27944 | 0 | 0 | 0 | 0 | [9 empty] | 222517 | 0
OK2019 | Santa Fe Development | TBD | JW | No | #REF! | 2021-11-08 | #REF! | 1181870 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 154842 | 139424 | 150000 | 150000 | 150000 | 150000 | 150000 | 137604 |  |  |  | 1181870 | 0
OK2020-1 | Western Shell | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 1307434 | [5 empty] | 244435 | 181308 | 16313 | 286477 | 175065 | 254689 | 149147 | [9 empty] | 1307434 | 0
OK2020-2 | Western - Scammahorn | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 267573 | [5 empty] | 46929 | 38525 | 0 | 45735 | 40858 | 33047 | 43566 | 18913 | [8 empty] | 267573 | 0
OK2020-3 | Western - Dr. Olsen | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 231276 | [5 empty] | 34010 | 31345 | 0 | 42608 | 27037 | 28599 | 46383 | 21294 | [8 empty] | 231276 | 0
OK2020-4 | Western - PT Central | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OK2024 | Bodyworx | AE | STROUD | Yes | 2021-02-14 | 2021-08-31 | 6.5781 | 984546 | [5 empty] | 230830 | 155142 | 20934 | 247073 | 88548 | 113241 | 61708 | 67070 | [8 empty] | 984546 | 0
OK2025 | Autism in Motion - Sante Fe Dev. | TBD | JW | No | 2021-05-03 | 2021-12-29 | 7.9734 | 1051400 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 111250 | 150000 | 175000 | 175000 | 200000 | 200000 | 40150 |  |  |  | 1051400 | 0
OK2031 | T-Mobile - Guthrie | AE | JW | Yes | 2021-03-01 | 2021-07-29 | 4.9834 | 723063 | [5 empty] | 0 | 0 | 0 | 79004 | 201430 | 171285 | 187324 | 84020 | [8 empty] | 723063 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | TBD | JW | No | 2021-05-01 | 2021-10-28 | 5.9801 | 1367414 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 150000 | 175000 | 175000 | 175000 | 175000 |  | 392414 |  | 1367414 | 0
OK2033-2 | Old School Bagel - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OK2039 | Rockwell Daycare | AE | STROUD | Yes | 2021-02-01 | 2021-03-31 | 1.9269 | 81500 | [5 empty] | 0 | 0 | 0 | 81500 | 0 | 0 | 0 | [9 empty] | 81500 | 0
OK2103 | Bethesda - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | HOLD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | HOLD
[8 empty] | 8567619 | [5 empty] | 1478898 | 701949 | 118025 | 849002 | 538775 | 755703 | 738802 | 616297 | 475000 | 500000 | 525000 | 525000 | 352754 |  | 392414 | 0 | 8567619 | 0
Cassidy Hedrick |  | BS | [28 empty] | 0
OK2028P | Precon - Memorial Park | [6 empty] | 461956 | [5 empty] | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | [9 empty] | 461956 | 0
OK2104 | Wimberley Walker Remodel | [6 empty] | 500577 | [5 empty] | 0 | 0 | 17615 | 71648 | 0 | 97695 | 103125 | 100000 | 100000 | 10494 | [6 empty] | 500577 | 0
[8 empty] | 962533 | [5 empty] | 0 | 353138 | 126433 | 71648 | 0 | 97695 | 103125 | 100000 | 100000 | 10494 | 0 | 0 | 0 |  | 0 | 0 | 962533 | 0
Christopher Goldsmith |  | CG
OK1936 | Dr Fischer | CG | GC | Yes | 2020-06-22 | 2021-04-15 | 9.8671 | 2419061 | [5 empty] | 1788494 | 93223 | -90886 | 247214 | 203016 | 0 | 88152 | 20348 | 69500 | [7 empty] | 2419061 | 0
OK2008 | Dr. Gaches | CG | GC | Yes | 2021-04-04 | 2021-07-15 | 3.3887 | 683158 | [5 empty] | 65749 | 0 | 0 | 72518 | 31182 | 36101 | 79510 | 53107 | 90000 | 90000 | 90000 | 74991 |  |  |  |  | 683158 | 0
OK2014 | Clark Shell | CG | GC | Yes | 2021-03-01 | 2021-12-27 | 10 | 1436404 | [5 empty] | 91138 | 0 | 0 | 0 | 55754 | 185059 | 486176 | 117904 | 150000 | 175000 | 150000 | 25373 |  |  |  |  | 1436404 | 0
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 648253 | [5 empty] | 124344 | 0 | 0 | 0 | 0 | 0 | 82390 | 65000 | 65000 | 65000 | 60000 | 73909 | 112610 |  |  |  | 648253 | 0
OK2014-2 | Clark Shell - Enhance DDS | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 400187 | [5 empty] | 14681 | 0 | 0 | 0 | 0 | 0 | 50940 | 50000 | 60000 | 60000 | 60000 | 60000 | 44566 |  |  |  | 400187 | 0
OK2018 | Dr. Mackey - 61st Street | [6 empty] | 33274 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 33274 | 0 | [9 empty] | 33274 | 0
OK2032-1 | Cross Roads - Shell | CG | GC | No | N/A | N/A | N/A | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | CG | GC | No | DEAD | DEAD | DEAD | 253822 | [5 empty] | 0 | 0 | 15630 | 0 | 0 | 0 | 0 | 238192 | [8 empty] | 253822 | 0
OK2032-3 | Cross Roads - State Farm | CG | GC | No | DEAD | DEAD | DEAD | 129826 | [5 empty] | 0 | 0 | 5720 | 0 | 9280 | 0 | 0 | 114826 | [8 empty] | 129826 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | GC | No | 2021-05-20 | 2021-09-17 | 3.9867 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OK2032-5 | Cross Roads - Dispensary | CG | GC | No |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
[8 empty] | 6003985 | [5 empty] | 2084406 | 93223 | -69536 | 319732 | 299232 | 254434 | 787168 | 659377 | 434500 | 390000 | 360000 | 234273 | 157176 |  | 0 | 0 | 6003985 | 0
Cory Muir |  | BS | [28 empty] | 0
OK2034 | Dr. Rex Johnson, DVM - Covel I35 | TBD | TBD | No | 2021-06-25 | 2022-04-22 | 10 | 1961016 | [5 empty] | 0 | 0 |  |  | 233134 | 0 | 0 | 72994 | 150000 | 150000 | 200000 | 200000 | 200000 |  | 754888 |  | 1961016 | 0
[15 empty] | 0 | [14 empty] | 0 | 0
[8 empty] | 1961016 | [5 empty] | 0 | 0 | 0 | 0 | 233134 | 0 | 0 | 72994 | 150000 | 150000 | 200000 | 200000 | 200000 |  | 754888 | 0 | 1961016 | 0
Jason Nowell |  | BS
OK1912 | Dr. Shirley | TBD | TBD | No | 2021-06-25 | 2022-04-22 | 10 | 1219262 | [5 empty] | 1206322 | 11381 | 0 | 0 | 0 | 0 | 0 | 1559 | [8 empty] | 1219262 | 0
OK1931 | Dr. Crowley | [6 empty] | 577676 | [5 empty] | 568341 | 2335 | 0 | 0 | 0 | 0 | 0 | 7000 | [8 empty] | 577676 | 0
[15 empty] | 0 | [15 empty] | 0
[8 empty] | 1796938 | [5 empty] | 1774663 | 13716 | 0 | 0 | 0 | 0 | 0 | 8559 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1796938 | 0
Bob Solomon |  | BS | [28 empty] | 0
OK1926 | Hunter Pharmacy | BS | DS | Yes | 2020-07-21 | 2021-06-24 | 11.2292 | 9534114 | 8913792 | 620322 | 8917546 | 616568 | 3754 | 4251267 | 974630 | 965506 | 726926 | 1007479 | 748387 | 599421 | 260498 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9534114 | 0
OK2006 | El Reno Enhanced Dental | BS | STROUD | Yes | 2020-10-20 | 2021-06-07 | 7.6412 | 1208821 | 1021270 | 187551 | 945919 | 262902 | -75351 | 501155 | 186495 | 202246 | 66602 | 48430 | 7649 | 118643 | 77601 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1208821 | 0
OK2016 | OneCore | BS | DH | Yes | 2020-10-15 | 2021-12-16 | 14.186 | 13107911 | 12555112 | 552799 | 12611053 | 496858 | 55941 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1379154 | 1270563 | 950000 | 950000 | 800000 | 350000 |  | 131996 |  | 13107911 | 0
[8 empty] | 23850846 | [5 empty] | 5555085 | 2212948 | 1990024 | 1963619 | 2124670 | 1579696 | 2254992 | 1717253 | 1270563 | 950000 | 950000 | 800000 | 350000 |  | 131996 | 0 | 23850846 | 0
Kevin Trosper |  | BS
OK1909-3 | Allstate Insurance | [6 empty] | 67027 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 67027 | [9 empty] | 67027 | 0
OK2101 | Christian Counciling | NK | NK | Yes | 2021-03-01 | 2021-05-31 | 3.0233 | 52095 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | [9 empty] | 52095 | 0
OK2105-1 | Breakroom 405 (VAL) | [6 empty] | 156692 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 156692 | [8 empty] | 156692 | 0
OK2105-2 | Christfit Gym | [6 empty] | 94557 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 94557 | [8 empty] | 94557 | 0
OK2105-4 | Prevail Fitness (VAL) | [6 empty] | 101240 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 101240 | [8 empty] | 101240 | 0
OK2105-5 | Magnus Batting Cage (VAL) | [6 empty] | 36900 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 36900 | [8 empty] | 36900 | 0
| Empite Financial | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
[8 empty] | 508511 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 119122 | 389389 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 508511 | 0
Wes Gaddy |  | WG | [5 empty] | Target
OK2003 | Enhance Dental - Choctaw | WG | WILLIAMS | Yes |  |  | 0 | 660134 | [5 empty] | 568347 | 879 | 35573 | 656 | 0 | 0 | 535 | 54144 | [8 empty] | 660134 | 0
OK2011-1 | Mustang Shell | WG | WILLIAMS | Yes | 2020-09-01 | 2021-03-31 | 7.01 | 940687 | [5 empty] | 720455 | 114649 | 0 | 105583 | 0 | 0 | 0 | [9 empty] | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 226188 | 819670 |  |  |  |  | 64622 | 39562 | 18328 | 101052 | 2624 | 0 | 0 | [9 empty] | 226188 | 0
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 315962 | [5 empty] | 124791 | 64927 | 25844 | 98461 | 1939 | 0 | 0 | [9 empty] | 315962 | 0
OK2038 | Dr. Farmer TI - Wonga Corner | WG | WILLIAMS | Yes | 2021-03-17 | 2021-06-15 | 2.99 | 383545 | 142789 |  |  |  |  | 0 | 0 | 0 | 0 | 118932 | 110310 | 66219 | 88084 | [8 empty] | 383545 | 0
TX1901 | Dr. Dyer - Sequoia Spur | WG | WILLIAMS | Yes | 2020-11-01 | 2021-07-31 | 9.0365 | 1809504 | 272772 |  |  |  |  | 407476 | 214131 | 74131 | 135778 | 437832 | 31174 | 82243 | 100000 | 100000 | 100000 | 100000 | 26739 |  |  |  |  | 1809504 | 0
TX1903 | Ramon Franklin Warehouse | WG | Stephensen | Yes | 2021-02-01 | 2021-08-21 | 6.6777 | 1006579 | [5 empty] | 131243 | 0 | 0 | 0 |  | 83010 | 67371 | 150362 | 124974 | 150000 | 150000 | 149619 |  |  |  |  | 1006579 | 0
TX2001 | Dr. Lippian - Texarkana | WG | TBD | Yes | 2021-01-28 | 2021-09-25 | 7.9734 | 1639962 | [5 empty] | 103605 | 0 | 71204 | 158532 | 124183 | 320119 | 192377 | 242285 | 200000 | 165153 | 62504 | [5 empty] | 1639962 | 0
TX2005 | McKinney Development | WG | RH | No | 2021-09-22 | 2022-05-20 | 7.9734 | 600000 | 1339023 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 150000 | 150000 | 150000 | 150000 |  |  |  |  | 600000 | 0
TX2006-1 | Sunnyvale Shell | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 1910050 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 119451 | 0 | 175000 | 200000 | 200000 | 200000 | 200000 |  | 815599 |  | 1910050 | 0
TX2006-2 | Sunnyvale Shell - Dr. Luna | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 288979 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7826 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | 31153 |  | 288979 | 0
TX2006-3 | Sunnyvale Shell - Dr. Rohani | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 366822 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 0 | 50000 | 75000 | 75000 | 75000 | 75000 |  | 9106 |  | 366822 | 0
TX2007-1 | Carrllton Shell | WG | TBD | No | 2021-09-22 | 2022-07-20 | 10 | 1700000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 75000 | 125000 | 200000 | 200000 | 200000 |  | 900000 |  | 1700000 | 0
TX2007-2 | Carrolton Shell - Dr. Bui | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 225000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 50000 | 50000 | 50000 |  | 25000 |  | 225000 | 0
TX2008-1 | Dr. Lee - McKinney Development | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 750000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 150000 | 150000 | 150000 | 150000 | 150000 |  |  |  | 750000 | 0
TX2101 | Bob Mills - Forth Worth | TBD | TBD | No | 2021-08-28 | 2022-02-24 |  | 2259828 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 105517 | 201248 | [7 empty] | 1953063 |  | 2259828 | 0
[8 empty] | 15083240 | [5 empty] | 2120539 | 434148 | 225080 | 600062 | 685510 | 650130 | 744986 | 634875 | 1074974 | 1215153 | 1187504 | 1051358 | 725000 |  | 3733921 | 0 | 15083240 | 0
PreConstruction |  | TBD
FL2001 | Elysee Lot 6 | TBD | TBD | No |  |  |  | 134403 | [5 empty] | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | [9 empty] | 134403 | 0
FL2002 | Elysee Lot 7 | TBD | TBD | No |  |  |  | 134403 | [5 empty] | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | [9 empty] | 134403 | 0
OK1924 | Yukon Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | HOLD
OK2026 | Covell I35 Edmond Dev. | TBD | TBD | No | 2021-06-24 | 2021-08-23 | 1.9934 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OK2028P | Precon - Memorial Park | TBD | TBD | No | DEAD | DEAD |  | 461956 | [6 empty] | 353138 | 108818 |  | 0 | 0 | 0 | [9 empty] | 461956 | 0
OK2036 | Dr. Matt Cole, DDS | TBD | TBD | No | 2021-08-01 | 2022-03-29 | 7.9734 | 1500000 | [6 empty] | 0 | 0 | 0 | 0 | 41062 | 0 |  | 125000 | 175000 | 200000 | 200000 | 200000 |  | 558938 |  | 1500000 | 0
OK2037 | Master Hand Milling | TBD | TBD | No | 2021-10-01 | 2022-09-27 | 11.9934 | 4000000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 800000 | 800000 | 800000 |  | 1600000 |  | 4000000 | 0
OK2102 | Puppy Paws | TBD | TBD | No | 2021-07-26 | 2022-05-23 | 10 | 3000000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 3000000 |  | 3000000 | 0
OK2104 | Wimberley Walker Remodel | TBD | TBD | No |  |  |  | 500577 | [6 empty] | 0 | 17615 | 71648 | 0 | 97695 | 103125 | [7 empty] | 210494 |  | 500577 | 0
OK2106-1 | Fox Lake Shell | TBD | TBD | No |  |  |  | 10000000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 405000 | 780000 | 1100000 | 1300000 | 1400000 | 1400000 |  | 3615000 |  | 10000000 | 0
OK2107 | Jack Be Grocery | TBD | TBD | No |  |  |  | 5000000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5000000 |  | 5000000 | 0
OK2108 | Puppy Paws - West Edmond | TBD | TBD | No |  |  |  | 1750000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1750000 |  | 1750000 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | HOLD
OKxxxx | Sears Shell - Hyperbaric Theropy | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | HOLD
OKxxxx | AIM - Yukon | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | DEAD
OKxxxx | AIM - Additions & OSB | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | DEAD
OK1909-3 | Creekwood - All State TI | TBD | TBD | No |  |  |  | 67027 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 67027 | [9 empty] | 67027 | 0
OKxxxx | Creekwood - Mike Lackey | TBD | TBD | No | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OKxxxx | Coltrane South - Aya Rowe - Chiro | TBD | TBD | No | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OKxxxx | Glenpool - Midleton's | TBD | TBD | No | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OKxxxx | Gleenpool Finance | TBD | TBD | No | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OKxxxx | Riverwest - Midleton's | TBD | TBD | No | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
OKxxxx | Riverwest - Tropical Smoothie | TBD | TBD | No |  |  |  | 90000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 90000 |  | 90000 | 0
TNxxxx | AIM - Memphis TN | TBD | TBD | No | 2021-08-01 | 2022-03-29 |  | 1500000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1500000 |  | 1500000 | 0
TX2004 | Marshall Ridge Dev. | WG | TBD | No | DEAD | DEAD | DEAD | 37392 | [6 empty] | 0 | 37392 | 0 | 0 | 0 | 0 | [9 empty] | 37392 | 0
TX2009 | Alliance Pediatrics-Marsh | WG | TBD | No | DEAD | DEAD | DEAD | 3575 | [6 empty] | 0 | 3575 | 0 | 0 | 0 | 0 | [9 empty] | 3575 | 0
TX2102-1 | Dr. Abeskharon - San Antonio | TBD | RH | No |  |  |  | 1750000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1750000 |  | 1750000 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0
[8 empty] | 29929333 | [5 empty] | 122184 | 353138 | 167400 | 71648 | 146622 | 138757 | 170152 | 405000 | 905000 | 1275000 | 2300000 | 2400000 | 2400000 |  | 19074432 | 0 | 29929333 | 0
0
[7 empty] | Billing Total | 88664021 | 0 | 0 | 0 | 0 | 0 | 13135775 | 4162260 | 2557426 | 3875711 | 4027943 | 3476415 | 4918347 | 4603744 | 4410037 | 4490647 | 5522504 | 5210631 | 4184930 |  | 24087651 | 0 | 88664021 | 0
[7 empty] | Billing Goal | [6 empty] | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 |  | 16008105
[7 empty] | Difference | [6 empty] | -1521270 | 1364142.8571 | -649398.6429 | -132681.6429 | -291054.6429 | -1593151.6429 | -657467.6429 | -710960.6429 | -1066803 | -869312 | -651060 | -291091 | 318395
[7 empty] | Rev Actual | [7 empty] | 2897650 | 3085444 | 3369732
[7 empty] | Rev Goal | [7 empty] | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 |  | 12779270.2215
[7 empty] | Difference | [7 empty] | 663913.0849 | 525435.8876 | 169832.1532
[7 empty] | GP Actual | [7 empty] | 261214 | 325090 | 157521
[7 empty] | GP Goal | [7 empty] | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 |  | 1403910.8085
[7 empty] | Difference | [7 empty] | 15819.1266 | 43851.4788 | -194015.0348
[7 empty] | GP % Actual | [7 empty] | 9.01% | 10.54% | 4.67%
[7 empty] | GP % Goal | [7 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |  | 10%
[7 empty] | Difference | [7 empty] | -0.99% | 0.54% | -5.33%
[7 empty] | OH Actual | [7 empty] | 256248 | 250107 | 305940
[7 empty] | OH Goal | [7 empty] | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 |  | 300000
[7 empty] | Difference | [7 empty] | 18752 | 24893 | -30940
[7 empty] | NP Actual | [7 empty] | 4126 | 74711 | -101036
[7 empty] | NP Goal | [7 empty] | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 |  | 500000.0033
[7 empty] | Difference | [7 empty] | -20413.4873 | 46587.1479 | -136189.6035
Note on I30: Bobby Snyder: Project on Hold
Note on I31: Existing Building

## 07 2021
[14 empty] | 2020 | 2021 | [12 empty] | 2022 | 2023
|  | PM | SUP | Permit | Start Date | Comp Date | Duration | Spectrum Value | ProCore Value | Variance | Forecasted Value | Variance |  | Annual | January | February | March | April | May | June | July | August | September | October | November | December |  | Annual | Annual | TOTAL | DELTA | COMMENTS
Adam England |  | AE
OK2005 | Quail Springs Shell | AE | DF | Yes | #REF! | #REF! | #REF! | 845876 | [5 empty] | 628337 | 137155 | 19492 | 60892 | 0 | 0 | 0 | 0 | [8 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | DF | Yes | #REF! | #REF! | #REF! | 303150 | [5 empty] | 162612 | 95646 | 33342 | 5713 | 5837 | 0 | 0 | 0 | [8 empty] | 303150 | 0
OK2005-2 | Quail Springs - Just Kids Ped's | AE | DF | Yes | #REF! | #REF! | #REF! | 222517 | [5 empty] | 131745 | 62828 | 27944 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 222517 | 0
OK2019 | Santa Fe Development | TBD | JW | No | #REF! | 2021-11-08 | #REF! | 1181870 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 154842 | 139424 | 0 | 300000 | 150000 | 150000 | 150000 | 137604 |  |  |  | 1181870 | 0 | No billing in July
OK2020-1 | Western Shell | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 1307434 | [5 empty] | 244435 | 181308 | 16313 | 286477 | 175065 | 254689 | 149147 | 0 | [8 empty] | 1307434 | 0
OK2020-2 | Western - Scammahorn | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 267573 | [5 empty] | 46929 | 38525 | 0 | 45735 | 40858 | 33047 | 43566 | 18912 | 1 | [7 empty] | 267573 | 0 | Do we need to bill or adjust the contract?
OK2020-3 | Western - Dr. Olsen | AE | DF | Yes | 2020-11-09 | 2021-07-09 | 8.0399 | 231276 | [5 empty] | 34010 | 31345 | 0 | 42608 | 27037 | 28599 | 46383 | 20189 | 1105 | [7 empty] | 231276 | 0 | Do we need to bill or adjust the contract?
OK2024 | Bodyworx | AE | STROUD | Yes | 2021-02-14 | 2021-08-31 | 6.5781 | 984546 | [5 empty] | 230830 | 155142 | 20934 | 247073 | 88548 | 113241 | 61708 | 67070 | [8 empty] | 984546 | 0
OK2025 | Autism in Motion - Sante Fe Dev. | TBD | JW | No | 2021-05-03 | 2021-12-29 | 7.9734 | 1051400 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 111250 | 14446 | 310554 | 175000 | 200000 | 200000 | 40150 |  |  |  | 1051400 | 0
OK2031 | T-Mobile - Guthrie | AE | JW | Yes | 2021-03-01 | 2021-07-29 | 4.9834 | 723063 | [5 empty] | 0 | 0 | 0 | 79004 | 201430 | 171285 | 187324 | 84019 | 1 | [7 empty] | 723063 | 0 | Do we need to bill or adjust the contract?
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | TBD | JW | No | 2021-05-01 | 2021-10-28 | 5.9801 | 1367414 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275000 | 175000 | 175000 | 175000 | 175000 |  | 392414 |  | 1367414 | 0 | No billing at all.
OK2039 | Rockwell Daycare | AE | STROUD | Yes | 2021-02-01 | 2021-03-31 | 1.9269 | 81500 | [5 empty] | 0 | 0 | 0 | 81500 | 0 | 0 | 0 | 0 | [8 empty] | 81500 | 0
[8 empty] | 8567619 | 0 | 0 | 0 | 0 | 0 | 1478898 | 701949 | 118025 | 849002 | 538775 | 755703 | 738802 | 204636 | 886661 | 500000 | 525000 | 525000 | 352754 |  | 392414 | 0 | 8567619 | 0
Wes Gaddy |  | WG | [5 empty] | Target
OK2003 | Enhance Dental - Choctaw | AE | WILLIAMS | Yes |  |  | 0 | 660134 | [5 empty] | 568347 | 879 | 35573 | 656 | 0 | 0 | 535 | 0 | 54144 | [7 empty] | 660134 | 0
OK2011-1 | Mustang Shell | WG | WILLIAMS | Yes | 2020-09-01 | 2021-03-31 | 7.01 | 940687 | [5 empty] | 720455 | 114649 | 0 | 105583 | 0 | 0 | 0 | 0 | [8 empty] | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 226188 | 819670 |  |  |  |  | 64622 | 39562 | 18328 | 101052 | 2624 | 0 | 0 | 0 | [8 empty] | 226188 | 0
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | Yes | 2020-11-01 | 2021-03-31 | 4.9834 | 315962 | [5 empty] | 124791 | 64927 | 25844 | 98461 | 1939 | 0 | 0 | 0 | [8 empty] | 315962 | 0
OK2038 | Dr. Farmer TI - Wonga Corner | KK | WILLIAMS | Yes | 2021-03-17 | 2021-06-15 | 2.99 | 383545 | 142789 |  |  |  |  | 0 | 0 | 0 | 0 | 118932 | 110310 | 66219 | 58693 | 29391 | [7 empty] | 383545 | 0
TX1901 | Dr. Dyer - Sequoia Spur | BS | WILLIAMS | Yes | 2020-11-01 | 2021-07-31 | 9.0365 | 1809504 | 272772 |  |  |  |  | 407476 | 214131 | 74131 | 135778 | 437832 | 31174 | 82243 | 45087 | 154913 | 100000 | 100000 | 26739 |  |  |  |  | 1809504 | 0
TX1903 | Ramon Franklin Warehouse | KK | MILLER | Yes | 2021-02-01 | 2021-08-21 | 6.6777 | 1006579 | [5 empty] | 131243 | 0 | 0 | 0 |  | 83010 | 67371 | 0 | 275336 | 150000 | 150000 | 149619 |  |  |  |  | 1006579 | 0 | Contract value needs to be increased.
TX2001 | Dr. Lippian - Texarkana | BS | HARRIS | Yes | 2021-01-28 | 2021-09-25 | 7.9734 | 1639962 | [5 empty] | 103605 | 0 | 71204 | 158532 | 124183 | 320119 | 192377 | 74223 | 368062 | 165153 | 62504 | [5 empty] | 1639962 | 0
TX2006-1 | Sunnyvale Shell | KT | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 1910050 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 119451 | 0 | 175000 | 200000 | 200000 | 200000 | 200000 |  | 815599 |  | 1910050 | 0
TX2006-2 | Sunnyvale Shell - Dr. Luna | KT | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 288979 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7826 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 0 | 31153 |  | 288979 | 0
TX2006-3 | Sunnyvale Shell - Dr. Rohani | KT | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 366822 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 0 | 50000 | 75000 | 75000 | 75000 | 75000 |  | 9106 |  | 366822 | 0
TX2101 | Bob Mills - Forth Worth | KK | JOHNSON | No | 2021-08-28 | 2022-02-24 |  | 2259828 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 105517 | 201248 | 0 | 250000 | 500000 | 500000 | 400000 | 303063 |  |  |  | 2259828 | 0
[8 empty] | 11808240 | [5 empty] | 2120539 | 434148 | 225080 | 600062 | 685510 | 650130 | 744986 | 178003 | 1406846 | 1240153 | 1137504 | 901358 | 628063 |  | 855858 | 0 | 11808240 | 0
Christopher Goldsmith |  | CG
OK1936 | Dr Fischer | CG | GC | Yes | 2020-06-22 | 2021-04-15 | 9.8671 | 2297711 | [5 empty] | 1788494 | 93223 | -90886 | 247214 | 203016 | 0 | 88152 | 152817 | -184319 | [7 empty] | 2297711 | 0 | Is this contract value correct?
OK2008 | Dr. Gaches | CG | GC | Yes | 2021-04-04 | 2021-07-15 | 3.3887 | 683158 | [5 empty] | 65749 | 0 | 0 | 72518 | 31182 | 36101 | 79510 | 164718 | 90000 | 90000 | 53380 | [5 empty] | 683158 | 0
OK2014 | Clark Plaza Shell | CG | GC | Yes | 2021-03-01 | 2021-12-27 | 10 | 1436404 | [5 empty] | 91138 | 0 | 0 | 0 | 55754 | 185059 | 486176 | 117904 | 150000 | 175000 | 150000 | 25373 |  |  |  |  | 1436404 | 0
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 648253 | [5 empty] | 124344 | 0 | 0 | 0 | 0 | 0 | 82390 | 0 | 130000 | 65000 | 60000 | 73909 | 112610 |  |  |  | 648253 | 0
OK2014-2 | Clark Shell - Enhance DDS | CG | GC | Yes | 2021-03-29 | 2021-11-24 | 7.9734 | 400187 | [5 empty] | 14681 | 0 | 0 | 0 | 0 | 0 | 50940 | 0 | 110000 | 60000 | 60000 | 60000 | 44566 |  |  |  | 400187 | 0
OK2018 | Dr. Mackey - 61st Street | [6 empty] | 446790 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 33274 | 0 | 0 | [6 empty] | 413516 |  | 446790 | 0
[8 empty] | 5912503 | [5 empty] | 2084406 | 93223 | -90886 | 319732 | 289952 | 254434 | 787168 | 435439 | 295681 | 390000 | 323380 | 159282 | 157176 |  | 413516 | 0 | 5912503 | 0
Cory Muir |  | BS | [28 empty] | 0
OK2034 | Dr. Rex Johnson, DVM - Covel I35 | TBD | TBD | No | 2021-06-25 | 2022-04-22 | 10 | 1961016 | [5 empty] | 0 | 0 |  |  | 233134 | 0 | 0 | 72994 | 150000 | 150000 | 200000 | 200000 | 200000 |  | 754888 |  | 1961016 | 0
[8 empty] | 1961016 | [5 empty] | 0 | 0 | 0 | 0 | 233134 | 0 | 0 | 72994 | 150000 | 150000 | 200000 | 200000 | 200000 |  | 754888 | 0 | 1961016 | 0
Jason Nowell |  | BS
OK1912 | Dr. Shirley | TBD | TBD | No | 2021-06-25 | 2022-04-22 | 10 | 1219262 | [5 empty] | 1206322 | 11381 | 0 | 0 | 0 | 0 | 0 | 0 | 1559 | [7 empty] | 1219262 | 0 | Do we need to bill or adjust the contract?
OK1931 | Dr. Crowley | [6 empty] | 577676 | [5 empty] | 568341 | 2335 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | [7 empty] | 577676 | 0 | Do we need to bill or adjust the contract?
[8 empty] | 1796938 | [5 empty] | 1774663 | 13716 | 0 | 0 | 0 | 0 | 0 | 0 | 8559 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1796938 | 0
Bob Solomon |  | BS | [28 empty] | 0
OK1926 | Hunter Pharmacy | BS | DS | Yes | 2020-07-21 | 2021-06-24 | 11.2292 | 9534114 | 8913792 | 620322 | 8917546 | 616568 | 3754 | 4251267 | 974630 | 965506 | 726926 | 1007479 | 748387 | 599421 | 93601 | 166897 | [7 empty] | 9534114 | 0
OK2006 | El Reno Enhanced Dental | BS | STROUD | Yes | 2020-10-20 | 2021-06-07 | 7.6412 | 1208821 | 1021270 | 187551 | 945919 | 262902 | -75351 | 501155 | 186495 | 202246 | 66602 | 48430 | 7649 | 118643 | 54525 | 23076 | [7 empty] | 1208821 | 0 | Do we need to bill or adjust the contract?
OK2016 | OneCore | BS | DH | Yes | 2020-10-15 | 2021-12-16 | 14.186 | 13107911 | 12555112 | 552799 | 12611053 | 496858 | 55941 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1270563 | 950000 | 950000 | 800000 | 303147 |  |  |  | 13107911 | 0
[8 empty] | 23850846 | [5 empty] | 5555085 | 2212948 | 1990024 | 1963619 | 2124670 | 1579696 | 2254992 | 1706129 | 1460536 | 950000 | 950000 | 800000 | 303147 |  | 0 | 0 | 23850846 | 0
Kevin Trosper |  | BS
OK1902-1 | Empite Financial | [6 empty] | 46806 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46806 | [7 empty] | 46806 | 0
OK1909-3 | Allstate Insurance | [6 empty] | 67027 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 67027 | 0 | [8 empty] | 67027 | 0
OK2101 | Christian Counciling | NK | NK | Yes | 2021-03-01 | 2021-05-31 | 3.0233 | 52095 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | 0 | [8 empty] | 52095 | 0
OK2105-1 | Breakroom 405 (VAL) | [6 empty] | 156692 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156692 | [8 empty] | 156692 | 0
OK2105-2 | Christfit Gym | [6 empty] | 94557 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94557 | [8 empty] | 94557 | 0
OK2105-3 | Custom Pools | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OK2105-4 | Prevail Fitness (VAL) | [6 empty] | 101240 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36103 | 65137 | [7 empty] | 101240 | 0
OK2105-5 | Magnus Batting Cage (VAL) | [6 empty] | 36900 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36900 | [8 empty] | 36900 | 0
[8 empty] | 555317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119122 | 324252 | 111943 | 0 | 0 | 0 | 0 |  | 0 | 0 | 555317 | 0
Cassidy Hedrick |  | BS | [28 empty] | 0
OK2028P | Precon - Memorial Park | [6 empty] | 461956 | [5 empty] | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 461956 | 0
OK2104 | Wimberley Walker Remodel | [6 empty] | 500577 | [5 empty] | 0 | 0 | 17615 | 71648 | 0 | 97695 | 103125 | 92500 | 100000 | 17994 | [6 empty] | 500577 | 0
[8 empty] | 962533 | [5 empty] | 0 | 353138 | 126433 | 71648 | 0 | 97695 | 103125 | 92500 | 100000 | 17994 | 0 | 0 | 0 |  | 0 | 0 | 962533 | 0
PreConstruction |  | TBD
FL2001 | Elysee Lot 6 | TBD | TBD | No |  |  |  | 3111793 | [5 empty] | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 3503 | [6 empty] | 2973887 |  | 3111793 | 0
FL2002 | Elysee Lot 7 | TBD | TBD | No |  |  |  | 3111793 | [5 empty] | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 2134 | [6 empty] | 2975256 |  | 3111793 | 0
OK1917-4 | Nutrition Club (COL P) | [6 empty] | 38040 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OK1922-1 | Aya Rowe (COLT) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OK1922-3 | Regent Bank (COLT) | [6 empty] | 74344 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OK1922-4 | Klassy K9 (COLT) | [6 empty] | 6336 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OK1923-3 | Tropical Smootie - RIVE | [6 empty] | 89125 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OK1923-4 | Stanton Optical - RIVE | [6 empty] | 75650 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OK1924 | Yukon Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | HOLD
OK2020-4 | Western - PT Central | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OK2026 | Covell I35 Edmond Dev. | TBD | TBD | No | 2021-06-24 | 2021-08-23 | 1.9934 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OK2028P | Precon - Memorial Park | TBD | TBD | No | DEAD | DEAD |  | 461956 | [5 empty] | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 461956 | 0
OK2032-1 | Cross Roads - Shell | CG | GC | No | N/A | N/A | N/A | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | CG | GC | No | DEAD | DEAD | DEAD | 253822 | [5 empty] | 0 | 0 | 15630 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 238192 |  | 253822 | 0
OK2032-3 | Cross Roads - State Farm | CG | GC | No | DEAD | DEAD | DEAD | 129826 | [5 empty] | 0 | 0 | 5720 | 0 | 9280 | 0 | 0 | 0 | [6 empty] | 114826 |  | 129826 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | GC | No | 2021-05-20 | 2021-09-17 | 3.9867 | HOLD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | HOLD
OK2032-5 | Cross Roads - Dispensary | CG | GC | No |  |  |  | HOLD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | HOLD
OK2033-2 | Old School Bagel - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OK2033-3 | Chamberlain Realty - Santa Fe Dev. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OK2036 | Dr. Matt Cole, DDS | TBD | TBD | No | 2021-08-01 | 2022-03-29 | 7.9734 | 1500000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 41062 | 0 | 0 | 125000 | 175000 | 200000 | 200000 | 200000 |  | 558938 |  | 1500000 | 0
OK2037 | Master Hand Milling | TBD | TBD | No | 2021-10-01 | 2022-09-27 | 11.9934 | 4000000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 800000 | 800000 | 800000 |  | 1600000 |  | 4000000 | 0
OK2102 | Puppy Paws | TBD | TBD | No | 2021-07-26 | 2022-05-23 | 10 | 3000000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3000000 |  | 3000000 | 0
OK2103 | Bethesda - Santa Fe Dev. | TBD | JW | No | 2021-05-15 | 2021-11-11 | 5.9801 | HOLD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | HOLD
OK2104 | Wimberley Walker Remodel | TBD | TBD | No |  |  |  | 500577 | [5 empty] | 0 | 0 | 17615 | 71648 | 0 | 97695 | 103125 | 0 | [6 empty] | 210494 |  | 500577 | 0
OK2106-1 | Fox Lake Shell | TBD | TBD | No |  |  |  | 10000000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780000 | 1100000 | 1300000 | 1400000 | 1400000 |  | 4020000 |  | 10000000 | 0
OK2107 | Jack Be Grocery | TBD | TBD | No |  |  |  | 5000000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000000 |  | 5000000 | 0
OK2108 | Puppy Paws - West Edmond | TBD | TBD | No |  |  |  | 1750000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1750000 |  | 1750000 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | HOLD
OKxxxx | Sears Shell - Hyperbaric Theropy | TBD | TBD | No | HOLD | HOLD | HOLD | HOLD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | HOLD
OKxxxx | AIM - Yukon | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | DEAD
OKxxxx | AIM - Additions & OSB | TBD | TBD | No | DEAD | DEAD | DEAD | DEAD | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | DEAD
OK1909-3 | Creekwood - All State TI | TBD | TBD | No |  |  |  | 67027 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 67027 | 0 | [8 empty] | 67027 | 0
OKxxxx | Creekwood - Mike Lackey | TBD | TBD | No | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | TBD | TBD | No | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OKxxxx | Coltrane South - Aya Rowe - Chiro | TBD | TBD | No | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OKxxxx | Glenpool - Midleton's | TBD | TBD | No | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OKxxxx | Gleenpool Finance | TBD | TBD | No | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OKxxxx | Riverwest - Midleton's | TBD | TBD | No | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
OKxxxx | Riverwest - Tropical Smoothie | TBD | TBD | No |  |  |  | 90000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 90000 |  | 90000 | 0
TNxxxx | AIM - Memphis TN | TBD | TBD | No | 2021-08-01 | 2022-03-29 |  | 1500000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1500000 |  | 1500000 | 0
TX2004 | Marshall Ridge Dev. | WG | TBD | No | DEAD | DEAD | DEAD | 37392 | [5 empty] | 0 | 0 | 37392 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 37392 | DEAD
TX2005 | McKinney Development | WG | RH | No | 2021-09-22 | 2022-05-20 | 7.9734 | 600000 | 1339023 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 |  |  |  |  | 600000 | 0
TX2007-1 | Carrllton Shell | WG | TBD | No | 2021-09-22 | 2022-07-20 | 10 | 1700000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 125000 | 200000 | 200000 | 200000 |  | 900000 |  | 1700000 | 0
TX2007-2 | Carrolton Shell - Dr. Bui | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 225000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 50000 | 50000 | 50000 |  | 25000 |  | 225000 | 0
TX2008-1 | Dr. Lee - McKinney Development | WG | TBD | No | 2021-09-22 | 2022-05-20 | 7.9734 | 750000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 |  |  |  | 750000 | 0
TX2009 | Alliance Pediatrics-Marsh | WG | TBD | No | DEAD | DEAD | DEAD | 3575 | [5 empty] | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 3575 | 0
TX2102-1 | Dr. Abeskharon - San Antonio | TBD | RH | No |  |  |  | 1750000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1750000 |  | 1750000 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
[8 empty] | 39826256 | [5 empty] | 122184 | 353138 | 188750 | 71648 | 155902 | 138757 | 170152 | 5637 | 1280000 | 1750000 | 2850000 | 2950000 | 2800000 |  | 26706593 | 0 | 39542761 | 283495
0
[7 empty] | Billing Total | 95241268 | 0 | 0 | 0 | 0 | 0 | 13135775 | 4162260 | 2557426 | 3875711 | 4027943 | 3476415 | 4918347 | 3019590 | 5700226 | 4998147 | 5985884 | 5535640 | 4441140 |  | 29123269 | 0 | 94957773 | 283495
[8 empty] | Billing Goal | [5 empty] | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 |  | 16008105
[8 empty] | Difference | [5 empty] | -1521270 | 1364142.8571 | -649398.6429 | -132681.6429 | -291054.6429 | -1593151.6429 | -657467.6429 | -2295114.6429 | 223386 | -361812 | -187680 | 33918 | 574605
[8 empty] | Rev Actual | [6 empty] | 2897650 | 3085444 | 3369732
[8 empty] | Rev Goal | [6 empty] | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 |  | 12779270.2215
[8 empty] | Difference | [6 empty] | 663913.0849 | 525435.8876 | 169832.1532
[8 empty] | GP Actual | [6 empty] | 261214 | 325090 | 157521
[8 empty] | GP Goal | [6 empty] | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 |  | 1403910.8085
[8 empty] | Difference | [6 empty] | 15819.1266 | 43851.4788 | -194015.0348
[8 empty] | GP % Actual | [6 empty] | 9.01% | 10.54% | 4.67%
[8 empty] | GP % Goal | [6 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |  | 10%
[8 empty] | Difference | [6 empty] | -0.99% | 0.54% | -5.33%
[8 empty] | OH Actual | [6 empty] | 256248 | 250107 | 305940
[8 empty] | OH Goal | [6 empty] | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 |  | 300000
[8 empty] | Difference | [6 empty] | 18752 | 24893 | -30940
[8 empty] | NP Actual | [6 empty] | 4126 | 74711 | -101036
[8 empty] | NP Goal | [6 empty] | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 |  | 500000.0033
[8 empty] | Difference | [6 empty] | -20413.4873 | 46587.1479 | -136189.6035
Note on I37: Bobby Snyder: Project on Hold
Note on I78: Existing Building
Note on I79: Bobby Snyder: On Hold
Note on I80: Bobby Snyder: On Hold
Note on I81: Bobby Snyder: On Hold
Note on I82: Bobby Snyder: On Hold
Note on I106: Bobby Snyder: DEAD

## 08 2021
[17 empty] | 2020 | 2021 | [11 empty] | 2022 | 2023
Job Number | Project | PM | SUP | Address | Status | Permit Submitted | Permit Received | Permit Approval Time | Permit Received | Start Date | Comp Date | Planned Comp Date | Duration | Punchlist Complete Date | Lessons Learned | Spectrum Value | Annual 2020 | January | February | March | April | May | June | July | August | September | October | November | December | Annual 2022 | Annual 2023 | TOTAL | DELTA | COMMENTS
Adam England |  | AE
OK2003 | Enhance Dental - Choctaw | AE | WILLIAMS | 2651 Market Blvd., Choctaw, OK 73020 | Complete | 2020-02-06 | 2020-05-01 | 85 | Yes | 2020-06-01 | 2020-11-20 |  | 5.7143 | Complete |  | 605990 | 568347 | 879 | 35573 | 656 | 0 | 0 | 535 | 0 | 0 | [6 empty] | 605990 | 0
OK2005 | Quail Springs Shell | AE | FRARY | 14424 N May Ave., OKC 73134 | Complete | 2020-05-22 | 2020-06-24 | 33 | Yes | 2020-08-05 | 2021-02-10 |  | 6.2791 | Complete |  | 845876 | 628337 | 137155 | 19492 | 60892 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | FRARY | 14424 N May Ave., OKC 73134 Ste A | Complete | 2020-07-29 | 2020-10-02 | 65 | Yes | 2020-09-28 | 2021-02-14 |  | 4.6179 | Complete |  | 303150 | 162612 | 95646 | 33342 | 5713 | 5837 | 0 | 0 | 0 | 0 | [6 empty] | 303150 | 0
OK2005-2 | Quail Springs - Just Kids Ped's | AE | FRARY | 14425 N May Ave., OKC 73134 Ste B | Complete | 2020-06-25 | 2020-07-17 | 22 | Yes | 2020-09-28 | 2021-02-10 |  | 4.485 | Complete |  | 222517 | 131745 | 62828 | 27944 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 222517 | 0
OK2019 | Santa Fe Development | AE | WILLIAMS | 100 Southwest 134th Street, OKC, OK 73170 | Construction | 2021-02-16 | 2021-04-16 | 59 | Yes | 2021-05-03 | 2021-11-05 |  | 6.1794 |  |  | 1181870 | 0 | 0 | 0 | 0 | 0 | 154842 | 139424 | 0 | 383465 | 150000 | 150000 | 150000 | 90000 | 47604 |  | 1265335 | 83465
OK2020-1 | Western Shell | AE | FRARY | 11521 South Western Ave., OKC, OK 73170 | Complete | 2020-08-03 | 2020-11-27 | 116 | Yes | 2020-11-09 | 2021-07-30 |  | 8.7375 | Complete |  | 1307434 | 244435 | 181308 | 16313 | 286477 | 175065 | 254689 | 149147 | 0 | 0 | [6 empty] | 1307434 | 0
OK2020-2 | Western - Scammahorn | AE | FRARY | 11522 South Western Ave., OKC, OK 73170 | Complete | 2020-08-06 | 2020-11-28 | 114 | Yes | 2020-11-09 | 2021-08-10 |  | 9.103 | Complete |  | 267572 | 46929 | 38525 | 0 | 45735 | 40858 | 33047 | 43566 | 18912 | 0 | [6 empty] | 267572 | 0
OK2020-3 | Western - Dr. Olsen | AE | FRARY | 11523 South Western Ave., OKC, OK 73170 | Complete | 2020-08-11 | 2020-11-28 | 109 | Yes | 2020-11-09 | 2021-08-02 |  | 8.8372 | Complete |  | 231276 | 34010 | 31345 | 0 | 42608 | 27037 | 28599 | 46383 | 20189 | 1105 | [6 empty] | 231276 | 0 | Do we need to bill or adjust the contract?
OK2024 | Bodyworx | AE | STROUD | 9201 S. Sooner Rd., Suite E, OKC 73135 | Complete | 2020-09-24 | 2020-12-01 | 68 | Yes | 2021-02-14 | 2021-08-04 |  | 5.6811 | Complete |  | 984546 | 230830 | 155142 | 20934 | 247073 | 88548 | 113241 | 61708 | 67070 | 0 | [6 empty] | 984546 | 0
OK2025 | Autism in Motion - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction | 2021-01-05 | 2021-04-16 | 101 | Yes | 2021-08-07 | 2021-12-28 |  | 4.7508 |  |  | 1051400 | 0 | 0 | 0 | 0 | 0 | 0 | 111250 | 14446 | 326666 | 150000 | 150000 | 150000 | 90000 | 75150 |  | 1067512 | 16112
OK2031 | T-Mobile - Guthrie | AE | WILLIAMS | 1904 S Division Street, Guthrie, OK 73044 | Complete | 2021-01-29 | 2021-03-05 | 35 | Yes | 2021-03-01 | 2021-07-16 |  | 4.5515 | Complete |  | 723062 | 0 | 0 | 0 | 79004 | 201430 | 171285 | 187324 | 84019 | 0 | [6 empty] | 723062 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction | 2021-06-15 | 2021-08-10 | 56 | Yes | 2021-07-05 | 2021-12-28 |  | 5.8472 |  |  | 1367414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99756 | 250000 | 250000 | 250000 | 250000 | 92414 |  | 1192170 | -175244
OK2033-2 | Old School Bagel - Santa Fe Dev. | AE | WILLIAMS | 112 SW 134th Street, Oklahoma City, OK | Construction | 2021-06-20 | 2021-08-15 | 56 | Yes | 2021-09-06 | 2021-12-28 |  | 3.7542 |  |  | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 80000 |  | 280000 | 0
OK2039 | Rockwell Daycare | AE | STROUD | 1213 N. Rockwell Ave., Oklahoma City, OK 73127 | Complete | 2020-12-01 | 2020-12-21 | 20 | Yes | 2021-02-01 | 2021-03-31 |  | 1.9269 | Complete |  | 81500 | 0 | 0 | 0 | 81500 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 81500 | 0
OK2110-1 | Shawnee Shell - Shawnee, OK | AE | STROUD | 4797 N. Harrison, Shawnee, OK 74804 | Construction | 2021-07-14 | 2021-09-15 | 63 | No |  |  |  | 0 |  |  | 1225500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 150000 | 250000 | 250000 | 475500 |  | 1225500 | 0
OK2110-2 | Shawnee Shell - Old School Bagel | AE | STROUD | 4799 N. Harrison, Shawnee, OK 74804 | Construction | 2021-07-14 | 2021-09-15 | 63 | No |  |  |  | 0 |  |  | 242554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25000 | 50000 | 50000 | 117554 |  | 242554 | 0
OK2110-3 | Shawnee Shell - OSO | AE | STROUD | 4795 N. Harrison, Shawnee, OK 74804 | Construction | 2021-08-06 | 2021-09-15 | 40 | No |  |  |  | 0 |  |  | 380405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25000 | 50000 | 50000 | 255405 |  | 380405 | 0
[16 empty] | 11302066 | 2047245 | 702828 | 153598 | 849658 | 538775 | 755703 | 739337 | 204636 | 810992 | 700000 | 800000 | 950000 | 830000 | 1143627 | 0 | 11226399 | -75667
Wes Gaddy |  | WG | [30 empty] | 0
OK2011-1 | Mustang Shell | WG | WILLIAMS | 1708 S Mustang Rd., Mustang, OK 73064 | Complete | 2021-05-01 | 2021-07-01 | 61 | Yes | 2020-09-01 | 2021-03-31 |  | 7.01 | Complete |  | 940687 | 720455 | 114649 | 0 | 105583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste D | Complete | 2021-05-01 | 2021-07-01 | 61 | Yes | 2020-11-01 | 2021-03-31 |  | 4.9834 | Complete |  | 226188 | 64622 | 39562 | 18328 | 101052 | 2624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226188 | 0
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste A | Complete | 2021-05-01 | 2021-07-01 | 61 | Yes | 2020-11-01 | 2021-03-31 |  | 4.9834 | Complete |  | 315962 | 124791 | 64927 | 25844 | 98461 | 1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315962 | 0
[16 empty] | 1482837 | 909868 | 219138 | 44172 | 305096 | 4563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482837 | 0
Christopher Goldsmith |  | CG | [30 empty] | 0
OK1902-1 | Empire Financial | CG | CLINTON | 12100 South Yukon Ave. Suite C, Glenpool, OK 74033 | Construction | N/A | N/A | N/A | N/A | 2021-05-14 | 2021-07-14 |  | 2.0266 |  |  | 46806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46806 | [6 empty] | 46806 | 0
OK1923-3 | Tropical Smoothie - Riverwest | CG | CLINTON | 152 W Alexander Blvd., Sand Springs, OK 74063 | Construction | 2021-06-01 | 2021-06-15 | 14 | Yes | 2021-05-28 | 2021-10-01 |  | 4.186 |  |  | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58100 | 35000 | 34125 |  |  |  |  | 127225 | 38100
OK1923-4 | Stanton Optical - Riverwest | CG | CLINTON | 153 W Alexander Blvd., Sand Springs, OK 74063 | Construction | 2021-06-01 | 2021-06-15 | 14 | Yes | 2021-06-06 | 2021-09-03 |  | 2.9568 |  |  | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75650 | 40650 | [5 empty] | 116300 | 40650
OK1936 | Dr Fischer | CG | CLINTON | 720 West 71St Street S, Tulsa, OK 74132 | Construction | 2020-04-08 | 2020-06-22 | 75 | Yes | 2020-06-22 | 2021-09-30 |  | 15.4485 |  |  | 2482030 | 1788494 | 93223 | -90886 | 247214 | 203016 | 0 | 88152 | 152817 | 0 | [6 empty] | 2482030 | 0
OK2008 | Dr. Gaches | CG | CLINTON | 11492 N. 137th E. Ave., Owasso, OK | Construction | 2020-08-28 | 2021-03-05 | 189 | Yes | 2021-04-04 | 2021-10-15 |  | 6.4452 |  |  | 683158 | 65749 | 0 | 0 | 72518 | 31182 | 36101 | 79510 | 164718 | 104045 | 90000 | 53380 |  |  |  |  | 697203 | 14045
OK2014 | Clark Plaza Shell | CG | CLINTON | 7877 E 71st South., Tulsa, OK 74133 | Construction | 2020-10-16 | 2021-02-19 | 126 | Yes | 2021-03-01 | 2021-12-27 |  | 10 |  |  | 1436404 | 91138 | 0 | 0 | 0 | 55754 | 185059 | 486176 | 117904 | 116211 | 125000 | 125000 | 100000 | 25373 |  |  | 1427615 | -8789
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | CLINTON | 7877 E 71st South Ste A, Tulsa, OK 74133 | Construction | 2020-12-03 | 2021-03-25 | 112 | Yes | 2021-03-29 | 2021-11-24 19:12 |  | 8 |  |  | 648253 | 124344 | 0 | 0 | 0 | 0 | 0 | 82390 | 0 | 125825 | 130000 | 100000 | 81519 |  |  |  | 644078 | -4175
OK2014-2 | Clark Shell - Enhance DDS | CG | CLINTON | 7877 E 71st South Ste B., Tulsa, OK 74133 | Construction | 2020-12-03 | 2021-03-25 | 112 | Yes | 2021-03-29 | 2021-11-24 |  | 7.9734 |  |  | 400187 | 14681 | 0 | 0 | 0 | 0 | 0 | 50940 | 0 | 231205 | 100000 | 100000 | 34566 |  |  |  | 531392 | 131205
OK2032-1 | Cross Roads - Shell | CG | CLINTON | 1167 N. 38th Street, Broken Arrow, OK 74014 | Construction | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | CLINTON | 1171 N. 38th Street, Broken Arrow, OK 74014 | Construction | 2021-08-11 | 2021-08-12 | 1 | Yes | 2021-09-15 | 2021-11-26 09:36 |  | 2.4053 |  |  | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 85000 | 85000 | 75000 |  |  | 330000 | 0
[16 empty] | 6191613 | 2084406 | 93223 | -90886 | 319732 | 289952 | 221160 | 787168 | 435439 | 757842 | 605650 | 497505 | 301085 | 100373 | 0 | 0 | 6402649 | 211036
Cassidy Hedrick |  | CH | [30 empty] | 0
OK2028P | Precon - Memorial Park | CH | CH |  | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 461956 | 0
OK2104 | Wimberley Walker Remodel | CH | CH | 101 Twilight Trail, Wimberly, TX 78676 | Construction | N/A | N/A | N/A | Yes | 2020-12-30 | 2021-09-30 |  | 9.103 |  |  | 500577 | 0 | 0 | 17615 | 71648 | 0 | 97695 | 103125 | 92500 | 117993 | 17994 | [5 empty] | 518570 | 17993
[16 empty] | 962533 | 0 | 353138 | 126433 | 71648 | 0 | 97695 | 103125 | 92500 | 117993 | 17994 | 0 | 0 | 0 | 0 | 0 | 980526 | 17993
Kimberly Kelly |  | KK | [30 empty] | 0
OK2038 | Dr. Farmer TI - Wonga Corner | KK | WILLIAMS | 1152 W. Douglas Midwest City, OK | Construction | 2021-02-26 | 2021-03-17 | 19 | Yes | 2021-03-17 | 2021-08-27 |  | 5.4153 |  |  | 383545 | 0 | 0 | 0 | 0 | 118932 | 110310 | 66219 | 58693 | 29391 | [6 empty] | 383545 | 0
TX1903 | Ramon Franklin Warehouse | KK | MILLER | 1308 Corporate Drive East, Arlinton, TX 76006 | Construction | 2020-12-09 | 2021-01-27 | 49 | Yes | 2021-07-05 | 2021-11-18 |  | 4.5183 |  |  | 1006579 | 131243 | 0 | 0 | 0 |  | 83010 | 67371 | 0 | 103268 | 150000 | 150000 | 149619 |  |  |  | 834511 | -172068 | Contract value needs to be increased. Submit a ProCore Change Event
TX2101 | Bob Mills - Forth Worth | KK | JOHNSON | 3600 East Long Ave., Ft Worth, TX 76111 | Construction | 2021-04-09 | 2021-06-10 | 62 | Yes | 2021-07-10 | 2021-11-08 |  | 4.0199 |  |  | 2259828 | 0 | 0 | 0 | 0 | 0 | 105517 | 201248 | 0 | 748228 | 500000 | 500000 | 400000 | 303063 |  |  | 2758056 | 498228
[16 empty] | 3649952 | 131243 | 0 | 0 | 0 | 118932 | 298837 | 334838 | 58693 | 880887 | 650000 | 650000 | 549619 | 303063 | 0 | 0 | 3976112 | 326160
Cory Muir |  | CM | [30 empty] | 0
OK2026 | Covell I35 Edmond Dev. | CM | STROUD | 5400 E. Covell Road, Edmond, OK | Construction | 2021-04-21 | 2021-08-09 | 110 | Yes | 2021-06-24 | 2021-08-23 |  | 1.9934 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
OK2034 | Dr. Rex Johnson, DVM - Covell I35 | CM | STROUD | 5401 E. Covel Rd., Edmond, OK 73034 | Construction | 2021-05-12 | 2021-08-10 | 90 | Yes | 2021-06-25 | 2022-04-22 |  | 10 |  |  | 1961016 | 0 | 0 |  |  | 233134 | 0 | 0 | 72994 | 144486 | 175000 | 190000 | 165000 | 175000 | 899888 |  | 2055502 | 94486
OK2106-1 | Fox Lake Shell | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Construction | 2021-06-22 | 2021-08-31 | 70 | No | 2021-07-22 | 2022-08-30 |  | 13.4219 |  |  | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 941343 | 1372000 | 522000 | 522000 | 772000 | 6062000 |  | 10191343 | 191343
[16 empty] | 11961016 | 0 | 0 | 0 | 0 | 233134 | 0 | 0 | 72994 | 1085829 | 1547000 | 712000 | 687000 | 947000 | 6961888 | 0 | 12246845 | 285829
Jason Nowell |  | JN | [30 empty] | 0
OK1912 | Dr. Shirley | JN |  | 2441 SW 134th, Oklahoma City, OK 73170 | Complete |  |  | 0 | Yes | 2020-01-06 | 2020-09-16 |  | 8.4385 | Complete |  | 1217703 | 1206322 | 11381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1217703 | 0
OK1931 | Dr. Crowley | JN |  | 15101 Crown at Lone Oak Rd, OKC 73013 | Complete |  |  | 0 | Yes | 2020-02-28 | 2020-12-22 |  | 9.9003 | Complete |  | 578876 | 568341 | 2335 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 | [6 empty] | 578876 | 0
[16 empty] | 1796579 | 1774663 | 13716 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1796579 | 0
Bob Solomon |  | BS | [30 empty] | 0
OK1926 | Hunter Pharmacy | BS | SMITH | 10120 Broadway Ext., OKC 73114 | Complete | 2020-05-14 | 2020-07-08 | 55 | Yes | 2020-07-21 | 2021-06-24 |  | 11.2292 |  |  | 9534114 | 4251267 | 974630 | 965506 | 726926 | 1007479 | 748387 | 599421 | 93601 | 88474 | 50000 | 36897 |  |  |  |  | 9542588 | 8474 | Revised projected billing in Aug & Sept. $36,897 may be a savings split with Hunter
OK2006 | El Reno Enhanced Dental | BS | STROUD | 1601 Investors Ave., El Reno, OK 73036 | Complete | 2020-06-16 | 2020-06-23 | 7 | Yes | 2020-10-20 | 2021-07-15 |  | 8.9037 |  |  | 1208821 | 501155 | 186495 | 202246 | 66602 | 48430 | 7649 | 118643 | 54525 | 32612 | 6000 | [5 empty] | 1224357 | 15536 | Revised projected billing in Aug. Expecting $6,000 to be returned to the Owner.
TX1901 | Dr. Dyer - Sequoia Spur | BS | STEPHENSON | 115 Shell Rd, Georgtown, TX 78633 | Construction | 2020-05-11 | 2020-07-06 | 56 | Yes | 2020-11-01 | 2021-10-29 |  | 12.0266 |  |  | 1809504 | 407476 | 214131 | 74131 | 135778 | 437832 | 31174 | 82243 | 45087 | 149925 | 100000 | 100000 | 50000 |  |  |  | 1827777 | 18273
TX2001 | Dr. Lippian - Texarkana | BS | HARRIS | 5220 Gibson Ln., Texarkana, TX 75501 | Construction | 2020-09-30 | 2020-12-29 | 90 | Yes | 2021-01-28 | 2021-10-15 |  | 8.6379 |  |  | 1641198 | 103605 | 0 | 71204 | 158532 | 124183 | 320119 | 192377 | 74223 | 357461 | 150000 | 75000 | 29784 |  |  |  | 1656488 | 15290
[16 empty] | 14193637 | 5263503 | 1375256 | 1313087 | 1087838 | 1617924 | 1107329 | 992684 | 267436 | 628472 | 306000 | 211897 | 79784 | 0 | 0 | 0 | 14251210 | 57573
Kyle Tedlock |  | KT | [30 empty] | 0
OK2016 | OneCore | KT | HALL | 100 NE 85th Street, OKC, OK 73114 | Construction | 2020-08-11 | 2020-11-12 | 93 | Yes | 2020-10-15 | 2021-12-01 |  | 13.6877 |  |  | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 950000 | 950000 | 800000 | 303147 |  |  | 13358559 | 250648
[16 empty] | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 950000 | 950000 | 800000 | 303147 | 0 | 0 | 13358559 | 250648
Kevin Trosper |  | KT | [30 empty] | 0
OK1822-3 | R&D Construction | KT | TROSPER | 901 E. Main Suite 125, Yukon, OK 73099 | Complete | N/A | N/A | N/A | N/A | 2021-07-05 | 2021-08-20 |  | 1.5282 |  |  | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28797 |  |  |  |  | 89125 |  | 117922 | 28797
OK1822-4 | Blondette | KT | TROSPER | 902 E. Main Suite 115, Yukon, OK 73099 | Complete | N/A | N/A | N/A | N/A | 2021-07-05 | 2021-08-20 |  | 1.5282 |  |  | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24902 |  |  |  |  | 75650 |  | 100552 | 24902
OK1909-3 | Allstate Insurance (Brandon) | KT | TROSPER | 1140 NW 192nd Street Suite B, Oklahoma City, OK | Complete | 2021-04-13 | 2021-04-27 | 14 | Yes | 2021-05-17 | 2021-06-09 |  | 0.76412 |  |  | 67027 | 0 | 0 | 0 | 0 | 0 | 0 | 67027 | 0 | 0 | [6 empty] | 67027 | 0
OK1917-4 | Colonial Point - Nutrition Club | KT | TROSPER | 11999 NW Expressway Yukon, OK 73099 | Construction | 2021-06-22 | 2021-07-12 | 20 | Yes | 2021-07-05 | 2021-09-10 |  | 2.2259 |  |  | 38040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38040 | [6 empty] | 38040 | 0
OK1922-3 | Coltrane Corner - Regent Bank (Mike) | KT | TROSPER | 2823 E. 2nd, Suite C, Edmond, OK | Complete | 2021-05-14 | 2021-06-15 | 32 | Yes | 2021-06-21 | 2021-08-17 |  | 1.8937 |  |  | 74344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74344 | [6 empty] | 74344 | 0
OK1922-4 | Coltrane Corner - Klassy K9 (Mike) | KT | TROSPER | 2824 E. 2nd, Edmond, OK | Complete | N/A | N/A | N/A | N/A | 2021-06-11 | 2021-07-02 |  | 0.69767 |  |  | 6336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336 | [6 empty] | 6336 | 0
TX2006-1 | Sunnyvale Shell | KT | TROSPER | 480 US Hwy 80, Sunnyvale, TX 75182 | Construction | 2021-06-22 | 2021-09-03 | 73 | No | 2021-09-07 | 2022-05-06 |  | 8.0066 |  |  | 1910050 | 0 | 0 | 0 | 0 | 0 | 0 | 119451 | 0 | 139349 | 115190 | 216487 | 291672 | 331677 | 735573 |  | 1949399 | 39349
TX2006-2 | Sunnyvale Shell - Dr. Luna | KT | TROSPER | 481 US Hwy 80, Sunnyvale, TX 75182 | Construction | 2021-09-20 | 2021-10-22 | 32 | No | 2021-09-07 | 2022-05-06 |  | 8.0066 |  |  | 288979 | 0 | 0 | 0 | 0 | 0 | 0 | 7826 | 0 | 9711 | 50000 | 50000 | 50000 | 50000 | 31153 |  | 248690 | -40289
TX2006-3 | Sunnyvale Shell - Dr. Rohani | KT | TROSPER | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction | 2021-09-27 | 2021-10-29 | 32 | No | 2021-09-07 | 2022-05-06 |  | 8.0066 |  |  | 366822 | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 0 | 12408 | 75000 | 75000 | 75000 | 75000 | 9106 |  | 329230 | -37592
OK2101 | Christian Counseling | KT | TROSPER | 12901 E. Britton Rd. Suite B, Jones, 73049 | Complete | N/A | N/A | N/A | Yes | 2021-03-01 | 2021-05-31 |  | 3.0233 |  |  | 52095 | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | 0 | 0 | [6 empty] | 52095 | 0
OK2105-1 | Valencia - Breakroom 405 (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. A, Edmond, OK 73012 | Complete | 2021-03-22 | 2021-04-16 | 25 | Yes | 2021-05-24 | 2021-08-11 |  | 2.6246 |  |  | 156692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156692 | 0 | [6 empty] | 156692 | 0
OK2105-2 | Valencia - Christfit Gym (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Complete | 2021-03-22 | 2021-04-07 | 16 | Yes | 2021-05-24 | 2021-08-09 |  | 2.5581 |  |  | 94557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94557 | 0 | [6 empty] | 94557 | 0
OK2105-4 | Valencia - Prevail Fitness | KT | TROSPER | 2215 NW 178th Street Ste. B, Edmond, OK 73012 | Construction | 2021-05-07 | 2021-06-11 | 35 | Yes | 2021-07-06 | 2021-09-10 |  | 2.1927 |  |  | 101240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36103 | 58225 | [6 empty] | 94328 | -6912
OK2105-5 | Valencia - Magnus Batting Cage (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. D, Edmond, OK 73012 | Complete | 2021-06-04 | 2021-06-21 | 17 | Yes | 2021-06-28 | 2021-08-30 |  | 2.093 |  |  | 36900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36900 | 0 | [6 empty] | 36900 | 0
OK2105-6 | Valencia - Winfield and Co. | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Construction | 2021-09-01 | 2021-09-17 | 16 | No | 2021-08-02 | 2021-09-03 |  | 1.0631 |  |  | 12885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12885 | [5 empty] | 12885 | 0
[16 empty] | 3370742 | 0 | 0 | 0 | 0 | 0 | 0 | 254115 | 324252 | 392112 | 253075 | 341487 | 416672 | 456677 | 940607 | 0 | 3378997 | 8255
Phillip Wilson |  | KT | [30 empty] | 0
TN2101 | AIM - Memphis, TN | PW | WILSON | 7007 Stage Rd., Memphis, TN 38133 | Construction | 2021-06-18 | 2021-08-30 | 73 | No | 2021-09-08 | 2022-05-06 19:12 |  | 8 |  |  | 2015533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141412 | 100000 | 300000 | 400000 | 500000 | 715533 |  | 2156945 | 141412
[16 empty] | 2015533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141412 | 100000 | 300000 | 400000 | 500000 | 715533 | 0 | 2156945 | 141412
Preconstruction | [32 empty] | 0
OK2018 | Dr. Mackey - 61st Street | CG | CLINTON | 9050 E. 61st Street, Tulsa, OK 74145 | Construction | 2020-10-03 | 2021-03-24 | 172 | Yes | 2021-07-12 | 2022-01-08 14:24 |  | 6 |  |  | 446790 | 0 | 0 | 0 | 0 | 0 | 33274 | 0 | 0 | 0 | 50000 | 50000 | 75000 | 100000 | 138516 |  | 446790 | 0
OK2033-3 | Chamberlain Realty - Santa Fe Dev. | AE | WILLIAMS | 113 SW 134th Street, Oklahoma City, OK | Preconstruction | 2021-11-01 | 2021-12-01 | 30 | No |  |  |  | 0 |  |  | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 200000 | 1700000 |  | 1900000 | 0
OK2037 | Master Hand Milling | TBD | TBD | TBD, Edmond, OK | Preconstruction | 2021-07-26 | 2021-08-28 | 33 | No | 2021-10-01 | 2022-09-27 |  | 11.9934 |  |  | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 400000 | 3600000 |  | 4000000 | 0
OK2102 | Puppy Paws East Edmond | TBD | TBD | East Edmond | Preconstruction | 2021-08-15 | 2021-10-17 | 63 | No | 2021-11-16 | 2022-09-13 |  | 10 |  |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 3000000 |  | 3000000 | 0
OK2106-2 | Fox Lake - Sidecar | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | 2022-01-01 | 2022-01-31 | 30 | No |  |  |  | 0 |  |  | 980000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 980000 |  | 980000 | 0
OK2106-3 | Fox Lake - Hatch | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | 2022-01-01 | 2022-01-31 | 30 | No |  |  |  | 0 |  |  | 1558000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1558000 |  | 1558000 | 0
OK2106-4 | Fox Lake - Enhanced Dental | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | 2022-01-01 | 2022-01-31 | 30 | No |  |  |  | 0 |  |  | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 540000 |  | 540000 | 0
OK2106-5 | Fox Lake - Open Space | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | 2022-01-01 | 2022-01-31 | 30 | No |  |  |  | 0 |  |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 800000 |  | 800000 | 0
OK2106-6 | Fox Lake Provision Concepts | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | 2022-01-01 | 2022-01-31 | 30 | No |  |  |  | 0 |  |  | 690000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 690000 |  | 690000 | 0
OK2107 | Jack Be Grocery | TBD | TBD |  | Preconstruction | 2021-06-11 | 2021-08-04 | 54 | No |  |  |  | 0 |  |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 3000000 |  | 3000000 | 0
OK2108 | Puppy Paws - Lone Oak | TBD | TBD | 15200 Crown at Lone Oak, Edmond OK 73013 | Preconstruction | 2021-06-28 | 2021-09-30 | 94 | No |  |  |  | 0 |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 150000 | 250000 | 1600000 |  | 2000000 | 0
OK2112 | Dr. Lu Dentistry - Covell 35 Dev. | CM | STROUD | 5249 E. Covel Rd., Edmond, OK 73034 | Preconstruction | 2021-10-20 | 2021-11-01 | 12 | No |  |  |  | 0 |  |  | 1325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 100000 | 1225000 |  | 1325000 | 0
OK2113 | Carlton Landing Sewer - Eufaula, OK | BS | TBD |  | Preconstruction |  |  | 0 | No |  |  |  | 0 |  |  | 82107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 30000 | 27107 |  |  |  | 82107 | 0
OK2114-1 | Chamberlain Realty - Lone Oak | TBD | TBD | 15103 Crown at Lone Oak Rd., Edmond, OK 73013 | Preconstruction | 2021-12-01 | 2022-01-15 | 45 | No |  |  |  | 0 |  |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 100000 | 250000 |  | 400000 | 0
OK2115 | Paul's Valley Development | TBD | TBD |  | Preconstruction |  |  | 0 | No |  |  |  | 0 |  |  | 1677500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1677500 |  | 1677500 | 0
OK2116 | Dollar Tree (Paul's Valley Development) | TBD | TBD |  | Preconstruction |  |  | 0 | No |  |  |  | 0 |  |  | 753000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 753000 |  | 753000 | 0
OK2117-1 | Paul's Valley Shell | TBD | TBD |  | Preconstruction |  |  | 0 | No |  |  |  | 0 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 500000 |  | 500000 | 0
OK2117-2 | Paul's Valley Shell - Enhanced Dental | TBD | TBD |  | Preconstruction |  |  | 0 | No |  |  |  | 0 |  |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 450000 |  | 450000 | 0
OK2118 | Paul's Valley Shell - TBD | TBD | TBD | [5 empty] | No | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
OK2119 | OSB - Wonga Corner | TBD | TBD | 1156 S. Douglas, Midwest City, OK 73130 | Preconstruction | 2021-10-01 | 2021-10-21 | 20 | No |  |  |  | 0 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 100000 | 200000 |  | 350000 | 0
OK2120 | Peak View Brewery and Distillery | TBD | TBD | Reservoir by Costco | Preconstruction | 2021-12-01 | 2021-12-31 | 30 | No |  |  |  | 0 |  |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 3000000 |  | 3000000 | 0
OK2121 | 15th & Bryant Development | TBD | TBD |  | Preconstruction | 2021-11-01 | 2021-12-16 | 45 | No |  |  |  | 0 |  |  | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 680000 |  | 680000 | 0
OK2122 | The Learning Experence (15th & Bryant Development) | TBD | TBD |  | Preconstruction | 2021-11-01 | 2021-12-16 | 45 | No |  |  |  | 0 |  |  | 2180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2180000 |  | 2180000 | 0
OK2123 | TBD (15th & Bryant Development) | TBD | TBD | [5 empty] | No | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
OK2124 | Bodin Chiro (Lone Oak) | TBD | TBD |  | Preconstruction |  |  | 0 | No |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
OK2125-1 | Enid Shell | TBD | TBD |  | Preconstruction | 2021-10-01 | 2021-10-31 | 30 | No |  |  |  | 0 |  |  | 1225500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1225500 |  | 1225500 | 0
OK2125-2 | OSB - Enid | TBD | TBD |  | Preconstruction | 2021-11-30 | 2021-12-30 | 30 | No |  |  |  | 0 |  |  | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 250000 |  | 250000 | 0
OK2125-3 | Enhanced Dental - Enid | TBD | TBD |  | Preconstruction | 2021-11-30 | 2021-12-30 | 30 | No |  |  |  | 0 |  |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 450000 |  | 450000 | 0
OK2126-1 | Weatherford Shell | TBD | TBD |  | Preconstruction | 2021-11-01 | 2021-12-01 | 30 | No |  |  |  | 0 |  |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1200000 |  | 1200000 | 0
OK2126-2 | Weatherford Shell - Dollar Tree | TBD | TBD | [5 empty] | No | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
OK2126-3 | Weatherford Shell - Enhanced Dental | TBD | TBD | [5 empty] | No | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
OK2127-1 | Legacy Martial Arts Shell | TBD | TBD |  | Preconstruction |  |  | 0 | No |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
OK2128 | OSB 150th and Penn | TBD | TBD | 15201 N. Penn Crossing Court, Oklahoma City, OK 73013 | Preconstruction | 2021-12-01 | 2021-12-31 | 30 | No |  |  |  | 0 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 750000 |  | 750000 | 0
Okxxxx | Regent Center (Fox Lake Similar) | TBD | TBD | Broken Arrow | Preconstruction | 2022-02-01 | 2022-04-02 | 60 | No |  |  |  | 0 |  |  | 14000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 11000000 | 3000000 | 14000000 | 0
Okxxxx | AIM Bellevue - Site Visit Needed | PW | TBD | 7734 Hwy 70 S. Nashville, TN 37221 | Preconstruction |  |  | 0 | No |  |  |  | 0 |  |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1200000 |  | 1200000 | 0
Okxxxx | Anytime Fitness - Brandon Porter | TBD | TBD |  | Preconstruction |  |  | 0 | No |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
TX2005 | McKinney Development | TBD | TBD | Virginia and Ridge Road, McKinney, TX | Preconstruction | 2021-06-10 | 2021-08-03 | 54 | No | 2022-02-01 | 2022-09-29 19:12 |  | 8 |  |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 100000 | 150000 | 300000 |  | 600000 | 0
TX2007-1 | Carrollton Shell | KT | DOYLE | Carrollton, TX | Preconstruction | 2021-09-10 | 2021-09-24 | 14 | No | 2021-09-14 | 2022-07-12 |  | 10 |  |  | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 200000 | 200000 | 200000 | 975000 |  | 1700000 | 0
TX2007-2 | Carrolton Shell - Dr. Bui | KT | DOYLE | Carrollton, TX | Preconstruction | 2021-07-09 | 2021-08-23 | 45 | No | 2021-09-22 | 2022-05-20 19:12 |  | 8 |  |  | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 50000 | 50000 | 75000 |  | 225000 | 0
TX2008 | Dr. Barbara Lee - McKinney Development | TBD | TBD | McKinney, TX | Preconstruction | 2021-07-09 | 2021-10-01 | 84 | No | 2022-02-01 | 2022-09-29 19:12 |  | 8 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 |  | 750000 | 0
TX2102-1 | San Antonio Shell | TBD | TBD | San Antonio, TX | Preconstruction | 2021-07-06 | 2021-09-27 | 83 | No |  |  |  | 0 |  |  | 2229000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2229000 |  | 2229000 | 0
TX2102-2 | Dr. Abeskharon - San Antonio | TBD | TBD | San Antonio, TX | Preconstruction | 2021-10-01 | 2021-11-15 | 45 | No |  |  |  | 0 |  |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 360000 |  | 360000 | 0
TX2103-1 | McKinney Shell (McKinney Development) | TBD | TBD | McKinney, TX |  |  |  |  | No | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
TX2103-2 | TBD (McKinney Development) | TBD | TBD | McKinney, TX |  |  |  |  | No | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
TX2103-3 | TBD (McKinney Development) | TBD | TBD | McKinney, TX |  |  |  |  | No | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
[16 empty] | 54805107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 480000 | 777107 | 1700000 | 48548000 | 3000000 | 54805107 | 0
DEAD / HOLD / SOLD | [32 empty] | 0
FL2001 | Elysee Lot 6 | SOLD | SOLD | SOLD | SOLD | SOLD | SOLD | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD | 137906 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 3503 | [7 empty] | 137906 | 0
FL2002 | Elysee Lot 7 | SOLD | SOLD | SOLD | SOLD | SOLD | SOLD | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD | 136537 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 2134 | [7 empty] | 136537 | 0
OK1922-1 | Coltrane Corner - Aya Rowe | KT | TROPSER | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
OK1924 | Yukon Development | HOLD | HOLD | HOLD | HOLD | HOLD | HOLD | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
OK2018 | Dr. Mackey - 61st Street | HOLD | HOLD | 9050 E. 61st Street, Tulsa, OK 74145 | HOLD | 2020-10-03 | 2021-03-24 | 172 | Yes | 2021-07-12 | 2022-01-08 14:24 |  | HOLD | HOLD | HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 33274 | 0 | 0 | [7 empty] | 33274 | 33274
OK2020-4 | Western - PT Central | KT | TROPSER | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
OK2028 | Precon - Memorial Park | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 461956 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15630 | 0 | 0 | 15630 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 15630 | 0
OK2032-3 | Cross Roads - State Farm | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15000 | 0 | 0 | 5720 | 0 | 9280 | 0 | 0 | 0 | [7 empty] | 15000 | 0
OK2032-5 | Cross Roads - Dispensary | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
OK2036 | Dr. Matt Cole, DDS | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 41062 | 0 | 0 | 0 | 0 | 0 | 41062 | 0 | 0 | [7 empty] | 41062 | 0
OK2103 | Bethesda - Santa Fe Dev. | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
OK2105-3 | Valencia - Custom Pools | KT | TROPSER | 2215 NW 178th Street Ste. E, Edmond, OK 73012 | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15493 | [6 empty] | 15493 | 0
OK2111 | Solara Surgery Center - Moore, OK | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
OK2109-1 | Grand Blvd. Shell - OKC, OK | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | HOLD | HOLD | HOLD | HOLD | HOLD | HOLD | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0
TX2004 | Marshall Ridge Dev. | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 37392 | 0 | 0 | 37392 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 37392 | 0
TX2009 | Alliance Pediatrics-Marsh | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 3575 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 3575 | 0
[16 empty] | 864551 | 122184 | 353138 | 171135 | 0 | 155902 | 74336 | 0 | 5637 | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 897825 | 33274
0
[13 empty] | Billing Total |  |  | 125704077 | 13135775 | 4162260 | 2539811 | 3804063 | 4027943 | 3386920 | 4748195 | 3019590 | 6352243 | 5429719 | 4942889 | 4961267 | 5140260 | 58309655 | 3000000 | 126960590 | 1256513
[16 empty] | Billing Goal | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 | 16008105
[16 empty] | Difference | -1521270 | 1364142.8571 | -667013.6429 | -204329.6429 | -291054.6429 | -1682646.6429 | -827619.6429 | -2295114.6429 | 875403 | 69760 | -1230675 | -540455 | 1273725
[16 empty] | Rev Actual |  | 2897650 | 3085444 | 3369732
[16 empty] | Rev Goal |  | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 | 12779270.2215
[16 empty] | Difference |  | 663913.0849 | 525435.8876 | 169832.1532
[16 empty] | GP Actual |  | 261214 | 325090 | 157521
[16 empty] | GP Goal |  | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 | 1403910.8085
[16 empty] | Difference |  | 15819.1266 | 43851.4788 | -194015.0348
[16 empty] | GP % Actual |  | 9.01% | 10.54% | 4.67%
[16 empty] | GP % Goal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
[16 empty] | Difference |  | -0.99% | 0.54% | -5.33%
[16 empty] | OH Actual |  | 256248 | 250107 | 305940
[16 empty] | OH Goal |  | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
[16 empty] | Difference |  | 18752 | 24893 | -30940
[16 empty] | NP Actual |  | 4126 | 74711 | -101036
[16 empty] | NP Goal |  | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 | 500000.0033
[16 empty] | Difference |  | -20413.4873 | 46587.1479 | -136189.6035
Formulas:
Permit Received = [Permit Submitted]+35
Note on O14: Bobby Snyder: Punchlist was conducted via facetime and all items have been completed. Final punch walk will occur in Sept with Rep from CA
Note on B36: Bobby Snyder: Existing Building
Note on Q36: Existing Building
Note on Q87: Bobby Snyder: Project on Hold
Note on Q138: Bobby Snyder: Project on Hold
Note on B139: Bobby Snyder: Another GC built out this space.

## 09 2021
[18 empty] | 2020 | 2021 | [11 empty] | 2022 | 2023
Job Number | Project | PM | SUP | Address | Status | Loan Close | Permit Submitted | Permit Received | Permit Approval Time | Permit Received | Start Date | Comp Date | Planned Comp Date | Duration | Punchlist Complete Date | Lessons Learned | Spectrum Value | Annual 2020 | January | February | March | April | May | June | July | August | September | October | November | December | Annual 2022 | Annual 2023 | TOTAL | DELTA | COMMENTS
Adam England |  | AE
OK2003 | Enhance Dental - Choctaw | AE | WILLIAMS | 2651 Market Blvd., Choctaw, OK 73020 | Complete |  | 2020-02-06 | 2020-05-01 | 85 | Yes | 2020-06-01 | 2020-11-20 |  | 5.7143 | Complete |  | 605990 | 568347 | 879 | 35573 | 656 | 0 | 0 | 535 | 0 | 0 | 0 | [5 empty] | 605990 | 0
OK2005 | Quail Springs Shell | AE | FRARY | 14424 N May Ave., OKC 73134 | Complete |  | 2020-05-22 | 2020-06-24 | 33 | Yes | 2020-08-05 | 2021-02-10 |  | 6.2791 | Complete |  | 845876 | 628337 | 137155 | 19492 | 60892 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | FRARY | 14424 N May Ave., OKC 73134 Ste A | Complete |  | 2020-07-29 | 2020-10-02 | 65 | Yes | 2020-09-28 | 2021-02-14 |  | 4.6179 | Complete |  | 303150 | 162612 | 95646 | 33342 | 5713 | 5837 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 303150 | 0
OK2005-2 | Quail Springs - Just Kids Ped's | AE | FRARY | 14425 N May Ave., OKC 73134 Ste B | Complete |  | 2020-06-25 | 2020-07-17 | 22 | Yes | 2020-09-28 | 2021-02-10 |  | 4.485 | Complete |  | 222517 | 131745 | 62828 | 27944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 222517 | 0
OK2019 | Santa Fe Development | AE | WILLIAMS | 100 Southwest 134th Street, OKC, OK 73170 | Construction |  | 2021-02-16 | 2021-04-16 | 59 | Yes | 2021-05-03 | 2021-11-05 |  | 6.1794 |  |  | 1181870 | 0 | 0 | 0 | 0 | 0 | 154842 | 139424 | 0 | 383465 | 27725.91 | 150000 | 150000 | 54139 |  |  | 1059595.91 | -122274.09
OK2020-1 | Western Shell | AE | FRARY | 11521 South Western Ave., OKC, OK 73170 | Complete |  | 2020-08-03 | 2020-11-27 | 116 | Yes | 2020-11-09 | 2021-07-30 |  | 8.7375 | Complete |  | 1307434 | 244435 | 181308 | 16313 | 286477 | 175065 | 254689 | 149147 | 0 | 0 | 0 | [5 empty] | 1307434 | 0
OK2020-2 | Western Shell - Scammahorn | AE | FRARY | 11522 South Western Ave., OKC, OK 73170 | Complete |  | 2020-08-06 | 2020-11-28 | 114 | Yes | 2020-11-09 | 2021-08-10 |  | 9.103 | Complete |  | 267572 | 46929 | 38525 | 0 | 45735 | 40858 | 33047 | 43566 | 18912 | 0 | 0 | [5 empty] | 267572 | 0
OK2020-3 | Western Shell - Dr. Olsen | AE | FRARY | 11523 South Western Ave., OKC, OK 73170 | Complete |  | 2020-08-11 | 2020-11-28 | 109 | Yes | 2020-11-09 | 2021-08-02 |  | 8.8372 | Complete |  | 231276 | 34010 | 31345 | 0 | 42608 | 27037 | 28599 | 46383 | 20189 | 1105 | 0 | [5 empty] | 231276 | 0 | Do we need to bill or adjust the contract?
OK2024 | Bodyworx | AE | STROUD | 9201 S. Sooner Rd., Suite E, OKC 73135 | Complete |  | 2020-09-24 | 2020-12-01 | 68 | Yes | 2021-02-14 | 2021-08-04 |  | 5.6811 | Complete |  | 984546 | 230830 | 155142 | 20934 | 247073 | 88548 | 113241 | 61708 | 67070 | 0 | 0 | [5 empty] | 984546 | 0
OK2025 | Autism in Motion - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction |  | 2021-01-05 | 2021-04-16 | 101 | Yes | 2021-08-07 | 2021-12-28 |  | 4.7508 |  |  | 1051400 | 0 | 0 | 0 | 0 | 0 | 0 | 111250 | 14446 | 326666 | 140279.29 | 150000 | 150000 | 90000 | 59038 |  | 1041679.29 | -9720.71
OK2031 | T-Mobile - Guthrie | AE | WILLIAMS | 1904 S Division Street, Guthrie, OK 73044 | Complete |  | 2021-01-29 | 2021-03-05 | 35 | Yes | 2021-03-01 | 2021-07-16 |  | 4.5515 | Complete |  | 723062 | 0 | 0 | 0 | 79004 | 201430 | 171285 | 187324 | 84019 | 0 | 0 | [5 empty] | 723062 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction |  | 2021-06-15 | 2021-08-10 | 56 | Yes | 2021-07-05 | 2021-12-28 |  | 5.8472 |  |  | 1367414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99756 | 330951.22 | 250000 | 250000 | 250000 | 267658 |  | 1448365.22 | 80951.22
OK2033-2 | Old School Bagel - Santa Fe Dev. | AE | WILLIAMS | 112 SW 134th Street, Oklahoma City, OK | Construction |  | 2021-06-20 | 2021-10-10 | 112 | Yes | 2021-09-06 | 2022-01-28 |  | 4.7841 |  |  | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 80000 |  | 230000 | -50000
OK2039 | Rockwell Daycare | AE | STROUD | 1213 N. Rockwell Ave., Oklahoma City, OK 73127 | Complete |  | 2020-12-01 | 2020-12-21 | 20 | Yes | 2021-02-01 | 2021-03-31 |  | 1.9269 | Complete |  | 81500 | 0 | 0 | 0 | 81500 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 81500 | 0
OK2110-1 | Shawnee Shell - Shawnee, OK | AE | STROUD | 4797 N. Harrison, Shawnee, OK 74804 | Construction |  | 2021-07-14 | 2021-09-17 | 65 | Yes | 2021-10-17 | 2022-06-14 19:12 |  | 8 |  |  | 1225500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 250000 | 475500 |  | 1125500 | -100000
OK2110-2 | Shawnee Shell - Old School Bagel | AE | STROUD | 4799 N. Harrison, Shawnee, OK 74804 | Construction |  | 2021-10-08 | 2021-11-22 | 45 | No | 2021-12-22 | 2022-06-20 14:24 |  | 6 |  |  | 242554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 50000 | 50000 | 117554 |  | 242554 | 0
OK2110-3 | Shawnee Shell - OSO | AE | STROUD | 4795 N. Harrison, Shawnee, OK 74804 | Construction |  | 2021-10-29 | 2021-12-13 | 45 | No | 2022-01-12 | 2022-07-11 14:24 |  | 6 |  |  | 380405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 50000 | 50000 | 255405 |  | 380405 | 0
[17 empty] | 11302066 | 2047245 | 702828 | 153598 | 849658 | 538775 | 755703 | 739337 | 204636 | 810992 | 498956.42 | 800000 | 950000 | 794139 | 1255155 | 0 | 11101022.42 | -201043.58
Wes Gaddy |  | WG | [31 empty] | 0
OK2011-1 | Mustang Shell | WG | WILLIAMS | 1708 S Mustang Rd., Mustang, OK 73064 | Complete |  | 2021-05-01 | 2021-07-01 | 61 | Yes | 2020-09-01 | 2021-03-31 |  | 7.01 | Complete |  | 940687 | 720455 | 114649 | 0 | 105583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste D | Complete |  | 2021-05-01 | 2021-07-01 | 61 | Yes | 2020-11-01 | 2021-03-31 |  | 4.9834 | Complete |  | 226188 | 64622 | 39562 | 18328 | 101052 | 2624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226188 | 0
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste A | Complete |  | 2021-05-01 | 2021-07-01 | 61 | Yes | 2020-11-01 | 2021-03-31 |  | 4.9834 | Complete |  | 315962 | 124791 | 64927 | 25844 | 98461 | 1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315962 | 0
[17 empty] | 1482837 | 909868 | 219138 | 44172 | 305096 | 4563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482837 | 0
Christopher Goldsmith |  | CG | [31 empty] | 0
OK1902-1 | Empire Financial | CG | CLINTON | 12100 South Yukon Ave. Suite C, Glenpool, OK 74033 | Construction |  | N/A | N/A | N/A | N/A | 2021-05-14 | 2021-07-14 |  | 2.0266 |  |  | 46806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46806 | 0 | [5 empty] | 46806 | 0
OK1923-3 | Tropical Smoothie - Riverwest | CG | CLINTON | 152 W Alexander Blvd., Sand Springs, OK 74063 | Construction |  | 2021-06-01 | 2021-06-15 | 14 | Yes | 2021-05-28 | 2021-10-28 |  | 5.0831 |  |  | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58100 | 0 | [5 empty] | 58100 | -31025
OK1923-4 | Stanton Optical - Riverwest | CG | CLINTON | 153 W Alexander Blvd., Sand Springs, OK 74063 | Construction |  | 2021-06-01 | 2021-06-15 | 14 | Yes | 2021-06-06 | 2021-09-03 |  | 2.9568 |  |  | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75650 | 0 | [5 empty] | 75650 | 0
OK1936 | Dr Fischer | CG | CLINTON | 720 West 71St Street S, Tulsa, OK 74132 | Construction |  | 2020-04-08 | 2020-06-22 | 75 | Yes | 2020-06-22 | 2021-09-30 |  | 15.4485 |  |  | 2482030 | 1788494 | 93223 | -90886 | 247214 | 203016 | 0 | 88152 | 152817 | 0 | 0 | [5 empty] | 2482030 | 0
OK2008 | Dr. Gaches | CG | CLINTON | 11492 N. 137th E. Ave., Owasso, OK | Construction |  | 2020-08-28 | 2021-03-05 | 189 | Yes | 2021-04-04 | 2021-10-15 |  | 6.4452 |  |  | 683158 | 65749 | 0 | 0 | 72518 | 31182 | 36101 | 79510 | 164718 | 104045 | 68162.76 | 39335 |  |  |  |  | 661320.76 | -21837.24
OK2014 | Clark Plaza Shell | CG | CLINTON | 7877 E 71st South., Tulsa, OK 74133 | Construction |  | 2020-10-16 | 2021-02-19 | 126 | Yes | 2021-03-01 | 2021-12-27 |  | 10 |  |  | 1436404 | 91138 | 0 | 0 | 0 | 55754 | 185059 | 486176 | 117904 | 116211 | 178250.15 | 125000 | 100000 | 34162 |  |  | 1489654.15 | 53250.15
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | CLINTON | 7877 E 71st South Ste A, Tulsa, OK 74133 | Construction |  | 2020-12-03 | 2021-03-25 | 112 | Yes | 2021-03-29 | 2021-11-24 19:12 |  | 8 |  |  | 648253 | 124344 | 0 | 0 | 0 | 0 | 0 | 82390 | 0 | 125825 | 199275.86 | 100000 | 85694 |  |  |  | 717528.86 | 69275.86
OK2014-2 | Clark Shell - Enhance DDS | CG | CLINTON | 7877 E 71st South Ste B., Tulsa, OK 74133 | Construction |  | 2020-12-03 | 2021-03-25 | 112 | Yes | 2021-03-29 | 2021-11-24 |  | 7.9734 |  |  | 400187 | 14681 | 0 | 0 | 0 | 0 | 0 | 50940 | 0 | 231205 | 53980.66 | 50000 | 3361 |  |  |  | 404167.66 | 3980.66
OK2032-1 | Cross Roads - Shell | CG | CLINTON | 1167 N. 38th Street, Broken Arrow, OK 74014 | Construction |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | CLINTON | 1171 N. 38th Street, Broken Arrow, OK 74014 | Construction |  | 2021-08-11 | 2021-10-08 | 58 | Yes | 2021-09-15 | 2021-11-26 09:36 |  | 2.4053 |  |  | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 85000 | 75000 |  |  | 245000 | -85000
[17 empty] | 6191613 | 2084406 | 93223 | -90886 | 319732 | 289952 | 221160 | 787168 | 435439 | 757842 | 499669.43 | 399335 | 274055 | 109162 | 0 | 0 | 6180257.43 | -11355.57
Cassidy Hedrick |  | CH | [31 empty] | 0
OK2028P | Precon - Memorial Park | CH | CH |  | Complete |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 461956 | 0
OK2104 | Wimberley Walker Remodel | CH | CH | 101 Twilight Trail, Wimberly, TX 78676 | Construction |  | N/A | N/A | N/A | Yes | 2020-12-30 | 2021-09-30 |  | 9.103 |  |  | 500577 | 0 | 0 | 17615 | 71648 | 0 | 97695 | 103125 | 92500 | 117994 | [6 empty] | 500577 | 0
[17 empty] | 962533 | 0 | 353138 | 126433 | 71648 | 0 | 97695 | 103125 | 92500 | 117994 | 0 | 0 | 0 | 0 | 0 | 0 | 962533 | 0
Kimberly Kelly |  | KK | [31 empty] | 0
OK2038 | Dr. Farmer TI - Wonga Corner | KK | WILLIAMS | 1152 W. Douglas Midwest City, OK | Construction |  | 2021-02-26 | 2021-03-17 | 19 | Yes | 2021-03-17 | 2021-08-27 |  | 5.4153 |  |  | 383545 | 0 | 0 | 0 | 0 | 118932 | 110310 | 66219 | 58693 | 29391 | 0 | [5 empty] | 383545 | 0
TX1903 | Ramon Franklin Warehouse | KK | MILLER | 1308 Corporate Drive East, Arlinton, TX 76006 | Construction |  | 2020-12-09 | 2021-01-27 | 49 | Yes | 2021-07-05 | 2021-12-10 |  | 5.2492 |  |  | 1006579 | 131243 | 0 | 0 | 0 |  | 83010 | 67371 | 0 | 103268 | 113601.11 | 225000 | 171687 |  |  |  | 895180.11 | -111398.89 | Contract value needs to be increased. Submit a ProCore Change Event
TX2101 | Bob Mills - Forth Worth | KK | JOHNSON | 3600 East Long Ave., Ft Worth, TX 76111 | Construction |  | 2021-04-09 | 2021-06-10 | 62 | Yes | 2021-07-10 | 2021-12-10 |  | 5.0831 |  |  | 2259828 | 0 | 0 | 0 | 0 | 0 | 105517 | 201248 | 0 | 748228 | 181824.92 | 400000 | 300000 | 104835 |  |  | 2041652.92 | -218175.08
[17 empty] | 3649952 | 131243 | 0 | 0 | 0 | 118932 | 298837 | 334838 | 58693 | 880887 | 295426.03 | 625000 | 471687 | 104835 | 0 | 0 | 3320378.03 | -329573.97
Cory Muir |  | CM | [31 empty] | 0
OK2026 | Covell I35 Edmond Dev. | CM | STROUD | 5400 E. Covell Road, Edmond, OK | Construction |  | 2021-04-21 | 2021-08-09 | 110 | Yes | N/A | N/A |  | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
OK2034 | Dr. Rex Johnson, DVM - Covell I35 | CM | STROUD | 5401 E. Covel Rd., Edmond, OK 73034 | Construction |  | 2021-05-12 | 2021-08-10 | 90 | Yes | 2021-06-25 | 2022-06-21 |  | 11.9934 |  |  | 1961016 | 0 | 0 |  |  | 233134 | 0 | 0 | 72994 | 144486 | 174326.34 | 190000 | 165000 | 175000 | 805402 |  | 1960342.34 | -673.66
OK2106-1 | Fox Lake Shell | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Construction |  | 2021-06-22 | 2021-09-22 | 92 | Yes | 2021-07-22 | 2022-08-30 |  | 13.4219 |  |  | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 941343 | 403549.63 | 522000 | 522000 | 772000 | 5870657 |  | 9031549.63 | -968450.37
[17 empty] | 11961016 | 0 | 0 | 0 | 0 | 233134 | 0 | 0 | 72994 | 1085829 | 577875.97 | 712000 | 687000 | 947000 | 6676059 | 0 | 10991891.97 | -969124.03
Jason Nowell |  | JN | [31 empty] | 0
OK1912 | Dr. Shirley | JN |  | 2441 SW 134th, Oklahoma City, OK 73170 | Complete |  |  |  | 0 | Yes | 2020-01-06 | 2020-09-16 |  | 8.4385 | Complete |  | 1217703 | 1206322 | 11381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1217703 | 0
OK1931 | Dr. Crowley | JN |  | 15101 Crown at Lone Oak Rd, OKC 73013 | Complete |  |  |  | 0 | Yes | 2020-02-28 | 2020-12-22 |  | 9.9003 | Complete |  | 578876 | 568341 | 2335 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 | [6 empty] | 578876 | 0
[17 empty] | 1796579 | 1774663 | 13716 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1796579 | 0
Bob Solomon |  | BS | [31 empty] | 0
OK1926 | Hunter Pharmacy | BS | SMITH | 10120 Broadway Ext., OKC 73114 | Complete |  | 2020-05-14 | 2020-07-08 | 55 | Yes | 2020-07-21 | 2021-06-24 |  | 11.2292 |  |  | 9534114 | 4251267 | 974630 | 965506 | 726926 | 1007479 | 748387 | 599421 | 93601 | 88474 | 65327.47 | 36897 |  |  |  |  | 9557915.47 | 23801.47 | Revised projected billing in Aug & Sept. $36,897 may be a savings split with Hunter
OK2006 | El Reno Enhanced Dental | BS | STROUD | 1601 Investors Ave., El Reno, OK 73036 | Complete |  | 2020-06-16 | 2020-06-23 | 7 | Yes | 2020-10-20 | 2021-07-15 |  | 8.9037 |  |  | 1258636 | 501155 | 186495 | 202246 | 66602 | 48430 | 7649 | 118643 | 54525 | 32612 | 0 | [5 empty] | 1218357 | -40279 | Revised projected billing in Aug. Expecting $6,000 to be returned to the Owner.
OK2113 | Carlton Landing Sewer - Eufaula, OK | BS | TBD |  | Preconstruction |  | N/A | N/A | N/A | No |  |  |  | 0 |  |  | 82107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 27107 |  |  |  | 57107 | -25000
TX1901 | Dr. Dyer - Sequoia Spur | BS | STEPHENSON | 115 Shell Rd, Georgtown, TX 78633 | Construction |  | 2020-05-11 | 2020-07-06 | 56 | Yes | 2020-11-01 | 2021-12-01 |  | 13.1229 |  |  | 1809504 | 407476 | 214131 | 74131 | 135778 | 437832 | 31174 | 82243 | 45087 | 149925 | 55587.04 | 100000 | 31727 |  |  |  | 1765091.04 | -44412.96
TX2001 | Dr. Lippian - Texarkana | BS | HARRIS | 5220 Gibson Ln., Texarkana, TX 75501 | Construction |  | 2020-09-30 | 2020-12-29 | 90 | Yes | 2021-01-28 | 2021-11-01 |  | 9.2027 |  |  | 1641198 | 103605 | 0 | 71204 | 158532 | 124183 | 320119 | 192377 | 74223 | 357461 | 34466.45 | 75000 | 14494 |  |  |  | 1525664.45 | -115533.55
[17 empty] | 14325559 | 5263503 | 1375256 | 1313087 | 1087838 | 1617924 | 1107329 | 992684 | 267436 | 628472 | 155380.96 | 241897 | 73328 | 0 | 0 | 0 | 14124134.96 | -201424.04
Kyle Tedlock |  | KT | [31 empty] | 0
OK2016 | OneCore | KT | HALL | 100 NE 85th Street, OKC, OK 73114 | Construction |  | 2020-08-11 | 2020-11-12 | 93 | Yes | 2020-10-15 | 2021-12-01 |  | 13.6877 |  |  | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 1384616.45 | 950000 | 800000 | 52499 |  |  | 13542527.45 | 434616.45
[17 empty] | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 1384616.45 | 950000 | 800000 | 52499 | 0 | 0 | 13542527.45 | 434616.45
Kevin Trosper |  | KT | [31 empty] | 0
OK1822-3 | R&D Construction | KT | TROSPER | 901 E. Main Suite 125, Yukon, OK 73099 | Complete |  | N/A | N/A | N/A | N/A | 2021-07-05 | 2021-08-20 |  | 1.5282 |  |  | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28797 | 8473.4 |  |  |  | 60328 |  | 97598.4 | 8473.4
OK1822-4 | Blondette | KT | TROSPER | 902 E. Main Suite 115, Yukon, OK 73099 | Complete |  | N/A | N/A | N/A | N/A | 2021-07-05 | 2021-08-20 |  | 1.5282 |  |  | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24902 | 5295.49 |  |  |  | 50748 |  | 80945.49 | 5295.49
OK1909-3 | Allstate Insurance (Brandon) | KT | TROSPER | 1140 NW 192nd Street Suite B, Oklahoma City, OK | Complete |  | 2021-04-13 | 2021-04-27 | 14 | Yes | 2021-05-17 | 2021-06-09 |  | 0.76412 |  |  | 67027 | 0 | 0 | 0 | 0 | 0 | 0 | 67027 | 0 | 0 | 0 | [5 empty] | 67027 | 0
OK1917-4 | Colonial Point - Nutrition Club | KT | TROSPER | 11999 NW Expressway Yukon, OK 73099 | Construction |  | 2021-06-22 | 2021-07-12 | 20 | Yes | 2021-07-05 | 2021-10-01 |  | 2.9236 |  |  | 38040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38040 | 0 | [5 empty] | 38040 | 0
OK1922-3 | Coltrane Corner - Regent Bank (Mike) | KT | TROSPER | 2823 E. 2nd, Suite C, Edmond, OK | Complete |  | 2021-05-14 | 2021-06-15 | 32 | Yes | 2021-06-21 | 2021-08-17 |  | 1.8937 |  |  | 74344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74344 | 0 | [5 empty] | 74344 | 0
OK1922-4 | Coltrane Corner - Klassy K9 (Mike) | KT | TROSPER | 2824 E. 2nd, Edmond, OK | Complete |  | N/A | N/A | N/A | N/A | 2021-06-11 | 2021-07-02 |  | 0.69767 |  |  | 6336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336 | 0 | [5 empty] | 6336 | 0
TX2006-1 | Sunnyvale Shell | KT | TROSPER | 480 US Hwy 80, Sunnyvale, TX 75182 | Construction |  | 2021-06-22 | 2021-10-08 | 108 | No | 2021-11-07 | 2022-04-29 |  | 5.7475 |  |  | 1910050 | 0 | 0 | 0 | 0 | 0 | 0 | 119451 | 0 | 139349 | 0 | 222000 | 175000 | 175000 | 922621 |  | 1753421 | -156629
TX2006-2 | Sunnyvale Shell - Dr. Luna | KT | TROSPER | 481 US Hwy 80, Sunnyvale, TX 75182 | Construction |  | 2021-10-15 | 2021-11-14 | 30 | No | 2021-12-14 | 2022-05-25 |  | 5.3821 |  |  | 288979 | 0 | 0 | 0 | 0 | 0 | 0 | 7826 | 0 | 9711 | 0 | 28000 | 34000 | 20000 | 182442 |  | 281979 | -7000
TX2006-3 | Sunnyvale Shell - Dr. Rohani | KT | TROSPER | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction |  | 2021-10-22 | 2021-11-21 | 30 | No | 2021-12-21 | 2022-05-25 |  | 5.1495 |  |  | 366822 | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 0 | 12408 | 0 | 36000 | 44000 | 26000 | 232698 |  | 358822 | -8000
OK2101 | Christian Counseling | KT | TROSPER | 12901 E. Britton Rd. Suite B, Jones, 73049 | Complete |  | N/A | N/A | N/A | Yes | 2021-03-01 | 2021-05-31 |  | 3.0233 |  |  | 52095 | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | 0 | 0 | 0 | [5 empty] | 52095 | 0
OK2105-1 | Valencia - Breakroom 405 (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. A, Edmond, OK 73012 | Complete |  | 2021-03-22 | 2021-04-16 | 25 | Yes | 2021-05-24 | 2021-08-11 |  | 2.6246 |  |  | 156692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156692 | 0 | 0 | [5 empty] | 156692 | 0
OK2105-2 | Valencia - Christfit Gym (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Complete |  | 2021-03-22 | 2021-04-07 | 16 | Yes | 2021-05-24 | 2021-08-09 |  | 2.5581 |  |  | 94557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94557 | 0 | 0 | [5 empty] | 94557 | 0
OK2105-3 | Valencia - Winfield and Co. | KT | TROSPER | 2216 NW 178th Street Ste. E, Edmond, OK 73012 | Construction |  | 2021-09-01 | 2021-09-16 | 15 |  | 2021-09-22 | 2021-10-17 |  | 0.83056 |  |  | 29164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6835 |  |  |  |  | 6835 | -22329
OK2105-4 | Valencia - Prevail Fitness | KT | TROSPER | 2215 NW 178th Street Ste. B, Edmond, OK 73012 | Construction |  | 2021-05-07 | 2021-06-11 | 35 | Yes | 2021-07-06 | 2021-09-17 |  | 2.4252 |  |  | 101240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36103 | 58225 | 0 | [5 empty] | 94328 | -6912
OK2105-5 | Valencia - Magnus Batting Cage (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. D, Edmond, OK 73012 | Complete |  | 2021-06-04 | 2021-06-21 | 17 | Yes | 2021-06-28 | 2021-08-30 |  | 2.093 |  |  | 36900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36900 | 0 | 0 | [5 empty] | 36900 | 0
OK2105-6 | Valencia - Breakroom 405 Warehouse | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Construction |  | 2021-09-21 | 2021-10-15 | 24 | No | 2021-09-29 | 2021-10-08 |  | 0.299 |  |  | 19970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | -19970
[17 empty] | 3406991 | 0 | 0 | 0 | 0 | 0 | 0 | 254115 | 324252 | 392112 | 13768.89 | 292835 | 253000 | 221000 | 1448837 | 0 | 3199919.89 | -207071.11
Phillip Wilson |  | KT | [31 empty] | 0
TN2101 | AIM - Memphis, TN | PW | WILSON | 7007 Stage Rd., Memphis, TN 38133 | Construction |  | 2021-06-18 | 2021-10-15 | 119 | No | 2021-10-30 | 2022-05-06 19:12 |  | 6.2724 |  |  | 2015533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141412 | 0 | 300000 | 400000 | 500000 | 574121 |  | 1915533 | -100000
[17 empty] | 2015533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141412 | 0 | 300000 | 400000 | 500000 | 574121 | 0 | 1915533 | -100000
Preconstruction | [33 empty] | 0
OK2033-3 | Chamberlain Realty - Santa Fe Dev. | AE | WILLIAMS | 113 SW 134th Street, Oklahoma City, OK | Preconstruction |  | 2021-10-15 | 2021-11-15 | 31 | No | 2021-12-15 |  |  | -1479.9003 |  |  | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 200000 | 1700000 |  | 1900000 | 0
OK2037 | Master Hand Milling | TBD | TBD | TBD, Edmond, OK | Preconstruction |  | 2022-01-03 | 2022-01-30 | 27 | No | 2023-01-01 | 2022-09-27 |  | -3.1894 |  |  | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4000000 | 4000000 | 0
OK2102 | Puppy Paws East Edmond | TBD | TBD | East Edmond | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-02-01 | 2022-09-13 |  | 7.4419 |  |  | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3000000 |  | 3000000 | 800000
OK2106-2 | Fox Lake - Sidecar | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2022-01-03 | 2022-01-13 | 10 | No | 2022-02-12 |  |  | -1481.8605 |  |  | 980000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 980000 |  | 980000 | 0
OK2106-3 | Fox Lake - Hatch | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2022-01-03 | 2022-01-31 | 28 | No | 2022-03-02 |  |  | -1482.4585 |  |  | 1558000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1558000 |  | 1558000 | 0
OK2106-4 | Fox Lake - Enhanced Dental | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2021-10-15 | 2021-11-15 | 31 | No | 2021-12-15 |  |  | -1479.9003 |  |  | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 540000 |  | 540000 | 0
OK2106-5 | Fox Lake - Open Space | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2022-01-03 | 2022-01-31 | 28 | No | 2022-03-02 |  |  | -1482.4585 |  |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 800000 |  | 800000 | 0
OK2106-6 | Fox Lake Provision Concepts | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2022-01-03 | 2022-01-31 | 28 | No | 2022-03-02 |  |  | -1482.4585 |  |  | 690000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 690000 |  | 690000 | 0
OK2107 | Jack Be Grocery | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-01 | 29 | No | 2022-03-03 |  |  | -1482.4917 |  |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3000000 |  | 3000000 | 500000
OK2108 | Puppy Paws - Lone Oak | TBD | TBD | 15200 Crown at Lone Oak, Edmond OK 73013 | Preconstruction |  | 2021-10-15 | 2021-11-14 | 30 | No | 2021-11-21 |  |  | -1479.103 |  |  | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 150000 | 250000 | 1600000 |  | 2000000 | -200000
OK2112 | Dr. Lu Dentistry - Covell 35 Dev. | CM | STROUD | 5249 E. Covel Rd., Edmond, OK 73034 | Preconstruction |  | 2021-10-19 | 2021-11-01 | 13 | No | 2021-11-15 |  | 2022-06-01 | -1478.9037 |  |  | 1325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 100000 | 1225000 |  | 1325000 | 0
OK2114-1 | Chamberlain Realty - Lone Oak | TBD | TBD | 15103 Crown at Lone Oak Rd., Edmond, OK 73013 | Preconstruction |  | 2021-12-01 | 2022-01-15 | 45 | No | 2022-02-14 |  |  | -1481.9269 |  |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 100000 | 250000 |  | 400000 | 0
OK2115 | Paul's Valley Development | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 1677500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1677500 |  | 1677500 | 0
OK2116 | Dollar Tree (Paul's Valley Development) | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 753000 |  | 753000 | 753000
OK2117-1 | Paul's Valley Shell | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 500000 |  | 500000 | 0
OK2117-2 | Paul's Valley Shell - Enhanced Dental | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 450000 |  | 450000 | -200000
OK2118 | Paul's Valley Shell - TBD | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
OK2119 | OSB - Wonga Corner | HOLD | HOLD | 1156 S. Douglas, Midwest City, OK 73130 | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 100000 | 200000 |  | 350000 | 0
OK2120 | Peak View Brewery and Distillery | TBD | TBD | Reservoir by Costco | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3000000 |  | 3000000 | -1000000
OK2121 | 15th & Bryant Development | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-02-01 |  |  | -1481.495 |  |  | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 680000 |  | 680000 | 0
OK2122 | The Learning Experence (15th & Bryant Development) | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-02-01 |  | 2022-08-01 | -1481.495 |  |  | 2180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2180000 |  | 2180000 | 0
OK2123 | TBD (15th & Bryant Development) | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
OK2124 | Bodin Chiro (Lone Oak) | TBD | TBD |  | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-01-31 |  |  | -1481.4618 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | -350000
OK2125-1 | Enid Shell | TBD | TBD |  | Preconstruction |  | 2021-11-12 | 2021-10-31 | -12 | No | 2021-03-01 |  |  | -1470.299 |  |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1225500 |  | 1225500 | -274500
OK2125-2 | OSB - Enid | TBD | TBD |  | Preconstruction |  | 2021-11-26 | 2021-11-15 | -11 | No | 2022-03-01 |  |  | -1482.4252 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 250000 |  | 250000 | -100000
OK2125-3 | Enhanced Dental - Enid | TBD | TBD |  | Preconstruction |  | 2021-11-26 | 2021-11-15 | -11 | No | 2022-03-01 |  |  | -1482.4252 |  |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 450000 |  | 450000 | 0
OK2126-1 | Weatherford Shell | TBD | TBD |  | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 |  |  | -1481.495 |  |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1200000 |  | 1200000 | 0
OK2126-2 | Weatherford Shell - Dollar Tree | TBD | TBD |  | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2021-12-31 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
OK2126-3 | Weatherford Shell - Enhanced Dental | TBD | TBD |  | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 | [5 empty] | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -350000
OK2127 | Legacy Martial Arts Shell | TBD | TBD |  | Preconstruction |  |  |  | 0 | No | 2022-01-30 |  |  | -1481.4286 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | -750000
OK2128 | OSB 150th and Penn | TBD | TBD | 15201 N. Penn Crossing Court, Oklahoma City, OK 73013 | Preconstruction |  | 2021-12-01 | 2021-12-31 | 30 | No | 2022-01-30 |  |  | -1481.4286 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 750000 |  | 750000 | 0
Okxxxx | Regent Center (Fox Lake Similar) | TBD | TBD | Broken Arrow | Preconstruction |  | 2022-02-01 | 2022-04-02 | 60 | No | 2022-05-02 |  |  | -1484.485 |  |  | 14000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11000000 | 3000000 | 14000000 | 0
Okxxxx | AIM Bellevue - Site Visit Needed | PW | TBD | 7734 Hwy 70 S. Nashville, TN 37221 | Preconstruction |  |  |  | 0 | No | 2022-04-01 |  |  | -1483.4551 |  |  | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1200000 |  | 1200000 | -1200000
Okxxxx | Anytime Fitness - Brandon Porter | TBD | TBD |  | Preconstruction |  |  |  | 0 | No | 2022-01-30 |  |  | -1481.4286 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
TX2005 | McKinney Development | TBD | TBD | Virginia and Ridge Road, McKinney, TX | Preconstruction |  | 2021-10-01 | 2021-11-15 | 45 | No | 2022-02-01 | 2022-09-29 19:12 |  | 8 |  |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 100000 | 150000 | 300000 |  | 600000 | 0
TX2007-1 | Carrollton Shell | KT | DOYLE | Carrollton, TX | Preconstruction | 2021-10-01 | 2021-06-15 | 2021-10-10 | 117 | No | 2021-11-09 | 2022-07-12 |  | 8.1395 |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 975000 |  | 1575000 | -425000
TX2007-2 | Carrolton Shell - Dr. Bui | KT | DOYLE | Carrollton, TX | Preconstruction |  | 2021-10-15 | 2021-11-29 | 45 | No | 2021-12-29 | 2022-05-20 19:12 |  | 4.7442 |  |  | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 75000 |  | 225000 | -325000
TX2008 | Dr. Barbara Lee - McKinney Development | TBD | TBD | McKinney, TX | Preconstruction |  | 2021-10-22 | 2021-12-06 | 45 | No | 2022-02-01 | 2022-09-29 19:12 |  | 8 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 |  | 600000 | -150000
TX2102-1 | San Antonio Shell | TBD | TBD | San Antonio, TX | Preconstruction |  | 2021-10-29 | 2021-12-13 | 45 | No | 2022-01-12 |  |  | -1480.8306 |  |  | 2229000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2229000 |  | 2229000 | 0
TX2102-2 | Dr. Abeskharon - San Antonio | TBD | TBD | San Antonio, TX | Preconstruction |  | 2021-10-29 | 2021-12-13 | 45 | No | 2022-01-12 |  |  | -1480.8306 |  |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 360000 |  | 360000 | 0
TX2103-1 | McKinney Shell (McKinney Development) | TBD | TBD | McKinney, TX | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 | [5 empty] | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -600000
TX2103-2 | TBD TI (McKinney Shell) | TBD | TBD | McKinney, TX | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
TX2103-3 | TBD TI (McKinney Shell) | TBD | TBD | McKinney, TX | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
[17 empty] | 58319500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 750000 | 1300000 | 44948000 | 7000000 | 54448000 | -3871500
DEAD / HOLD / SOLD | [33 empty] | 0
FL2001 | Elysee Lot 6 | SOLD | SOLD | SOLD | SOLD |  | SOLD | SOLD | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD | 137906 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 3503 | 0 | 0 | [5 empty] | 137906 | 0
FL2002 | Elysee Lot 7 | SOLD | SOLD | SOLD | SOLD |  | SOLD | SOLD | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD | 136537 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 2134 | 0 | 0 | [5 empty] | 136537 | 0
OK1922-1 | Coltrane Corner - Aya Rowe | KT | TROPSER | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
OK1924 | Yukon Development | HOLD | HOLD | HOLD | HOLD |  | HOLD | HOLD | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
OK2018 | Dr. Mackey - 61st Street | HOLD | HOLD | 9050 E. 61st Street, Tulsa, OK 74145 | HOLD |  | 2020-10-03 | 2021-03-24 | 172 | Yes | 2021-07-12 | 2022-01-08 14:24 |  | HOLD | HOLD | HOLD | 33274 | 0 | 0 | 0 | 0 | 0 | 33274 | 0 | 0 | 0 | 0 | [5 empty] | 33274 | 0
OK2020-4 | Western - PT Central | KT | TROPSER | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
OK2028 | Precon - Memorial Park | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 461956 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15630 | 0 | 0 | 15630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 15630 | 0
OK2032-3 | Cross Roads - State Farm | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15000 | 0 | 0 | 5720 | 0 | 9280 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 15000 | 0
OK2032-5 | Cross Roads - Dispensary | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
OK2036 | Dr. Matt Cole, DDS | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 41062 | 0 | 0 | 0 | 0 | 0 | 41062 | 0 | 0 | 0 | 0 | [5 empty] | 41062 | 0
OK2103 | Bethesda - Santa Fe Dev. | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
OK2105-3 | Valencia - Custom Pools | KT | TROPSER | 2215 NW 178th Street Ste. E, Edmond, OK 73012 | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15493 | 0 | [5 empty] | 15493 | 0
OK2111 | Solara Surgery Center - Moore, OK | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
OK2109-1 | Grand Blvd. Shell - OKC, OK | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | HOLD | HOLD | HOLD | HOLD |  | HOLD | HOLD | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0
TX2004 | Marshall Ridge Dev. | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 37392 | 0 | 0 | 37392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 37392 | 0
TX2009 | Alliance Pediatrics-Marsh | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 3575 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 3575 | 0
[17 empty] | 897825 | 122184 | 353138 | 171135 | 0 | 155902 | 74336 | 0 | 5637 | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 897825 | 0
0
[14 empty] | Billing Total |  |  | 129419915 | 13135775 | 4162260 | 2539811 | 3804063 | 4027943 | 3386920 | 4748195 | 3019590 | 6352244 | 3425694.15 | 4771067 | 4659070 | 4028635 | 54902172 | 7000000 | 123963439.15 | -5456475.85
[17 empty] | Billing Goal | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 | 16008105
[17 empty] | Difference | -1521270 | 1364142.8571 | -667013.6429 | -204329.6429 | -291054.6429 | -1682646.6429 | -827619.6429 | -2295114.6429 | 875404 | -1934264.85 | -1402497 | -842652 | 162100
[17 empty] | Rev Actual |  | 2897650 | 3085444 | 3369732
[17 empty] | Rev Goal |  | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 | 12779270.2215
[17 empty] | Difference |  | 663913.0849 | 525435.8876 | 169832.1532
[17 empty] | GP Actual |  | 261214 | 325090 | 157521
[17 empty] | GP Goal |  | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 | 1403910.8085
[17 empty] | Difference |  | 15819.1266 | 43851.4788 | -194015.0348
[17 empty] | GP % Actual |  | 9.01% | 10.54% | 4.67%
[17 empty] | GP % Goal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
[17 empty] | Difference |  | -0.99% | 0.54% | -5.33%
[17 empty] | OH Actual |  | 256248 | 250107 | 305940
[17 empty] | OH Goal |  | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
[17 empty] | Difference |  | 18752 | 24893 | -30940
[17 empty] | NP Actual |  | 4126 | 74711 | -101036
[17 empty] | NP Goal |  | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 | 500000.0033
[17 empty] | Difference |  | -20413.4873 | 46587.1479 | -136189.6035
Formulas:
Permit Received = [Permit Submitted]+35
Start Date = [Permit Received]+30
Comp Date = [Start Date]+(8*4.3*7)
Note on P14: Bobby Snyder: Punchlist was conducted via facetime and all items have been completed. Final punch walk will occur in Sept with Rep from CA
Note on B36: Bobby Snyder: Existing Building
Note on R36: Existing Building
Note on R138: Bobby Snyder: Project on Hold
Note on B139: Bobby Snyder: Another GC built out this space.

## 10 2021
[18 empty] | 2020 | 2021 | [11 empty] | 2022 | 2023
Job Number | Project | PM | SUP | Address | Status | Loan Close | Permit Submitted | Permit Received | Permit Approval Time | Permit Received | Start Date | Comp Date | Planned Comp Date | Duration | Punchlist Complete Date | Lessons Learned | Spectrum Value | Annual 2020 | January | February | March | April | May | June | July | August | September | October | November | December | Annual 2022 | Annual 2023 | TOTAL | DELTA | COMMENTS
Adam England |  | AE
OK2003 | Enhance Dental - Choctaw | AE | WILLIAMS | 2651 Market Blvd., Choctaw, OK 73020 | Complete |  | 2020-02-06 | 2020-05-01 | 85 | Yes | 2020-06-01 | 2020-11-20 |  | 5.7143 | Complete |  | 605990 | 568347 | 879 | 35573 | 656 | 0 | 0 | 535 | 0 | 0 | 0 | 0 |  |  |  |  | 605990 | 0
OK2005 | Quail Springs Shell | AE | FRARY | 14424 N May Ave., OKC 73134 | Complete |  | 2020-05-22 | 2020-06-24 | 33 | Yes | 2020-08-05 | 2021-02-10 |  | 6.2791 | Complete |  | 845876 | 628337 | 137155 | 19492 | 60892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | FRARY | 14424 N May Ave., OKC 73134 Ste A | Complete |  | 2020-07-29 | 2020-10-02 | 65 | Yes | 2020-09-28 | 2021-02-14 |  | 4.6179 | Complete |  | 303150 | 162612 | 95646 | 33342 | 5713 | 5837 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 303150 | 0
OK2005-2 | Quail Springs - Just Kids Ped's | AE | FRARY | 14425 N May Ave., OKC 73134 Ste B | Complete |  | 2020-06-25 | 2020-07-17 | 22 | Yes | 2020-09-28 | 2021-02-10 |  | 4.485 | Complete |  | 222517 | 131745 | 62828 | 27944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 222517 | 0
OK2019 | Santa Fe Development | AE | WILLIAMS | 100 Southwest 134th Street, OKC, OK 73170 | Construction |  | 2021-02-16 | 2021-04-16 | 59 | Yes | 2021-05-03 | 2021-11-05 |  | 6.1794 |  |  | 1181870 | 0 | 0 | 0 | 0 | 0 | 154842 | 139424 | 0 | 383465 | 27725.91 | 0 | 150000 | 176413 |  |  | 1031869.91 | -150000
OK2020-1 | Western Shell | AE | FRARY | 11521 South Western Ave., OKC, OK 73170 | Complete |  | 2020-08-03 | 2020-11-27 | 116 | Yes | 2020-11-09 | 2021-07-30 |  | 8.7375 | Complete |  | 1307434 | 244435 | 181308 | 16313 | 286477 | 175065 | 254689 | 149147 | 0 | 0 | 0 | 0 |  |  |  |  | 1307434 | 0
OK2020-2 | Western Shell - Scammahorn | AE | FRARY | 11522 South Western Ave., OKC, OK 73170 | Complete |  | 2020-08-06 | 2020-11-28 | 114 | Yes | 2020-11-09 | 2021-08-10 |  | 9.103 | Complete |  | 267572 | 46929 | 38525 | 0 | 45735 | 40858 | 33047 | 43566 | 18912 | 0 | 0 | 0 |  |  |  |  | 267572 | 0
OK2020-3 | Western Shell - Dr. Olsen | AE | FRARY | 11523 South Western Ave., OKC, OK 73170 | Complete |  | 2020-08-11 | 2020-11-28 | 109 | Yes | 2020-11-09 | 2021-08-02 |  | 8.8372 | Complete |  | 231276 | 34010 | 31345 | 0 | 42608 | 27037 | 28599 | 46383 | 20189 | 1105 | 0 | 0 |  |  |  |  | 231276 | 0 | Do we need to bill or adjust the contract?
OK2024 | Bodyworx | AE | STROUD | 9201 S. Sooner Rd., Suite E, OKC 73135 | Complete |  | 2020-09-24 | 2020-12-01 | 68 | Yes | 2021-02-14 | 2021-08-04 |  | 5.6811 | Complete |  | 984546 | 230830 | 155142 | 20934 | 247073 | 88548 | 113241 | 61708 | 67070 | 0 | 0 | 0 |  |  |  |  | 984546 | 0
OK2025 | Autism in Motion - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction |  | 2021-01-05 | 2021-04-16 | 101 | Yes | 2021-08-07 | 2021-12-28 |  | 4.7508 |  |  | 1051400 | 0 | 0 | 0 | 0 | 0 | 0 | 111250 | 14446 | 326666 | 140279.29 | 169323.9 | 150000 | 90000 | 68758.71 |  | 1070723.9 | 19320
OK2031 | T-Mobile - Guthrie | AE | WILLIAMS | 1904 S Division Street, Guthrie, OK 73044 | Complete |  | 2021-01-29 | 2021-03-05 | 35 | Yes | 2021-03-01 | 2021-07-16 |  | 4.5515 | Complete |  | 723062 | 0 | 0 | 0 | 79004 | 201430 | 171285 | 187324 | 84019 | 0 | 0 | 0 |  |  |  |  | 723062 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction |  | 2021-06-15 | 2021-08-10 | 56 | Yes | 2021-07-05 | 2021-12-28 |  | 5.8472 |  |  | 1367414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99756 | 330951.22 | 217391.16 | 250000 | 250000 | 186706.78 |  | 1334805.16 | -32610
OK2033-2 | Old School Bagel - Santa Fe Dev. | AE | WILLIAMS | 112 SW 134th Street, Oklahoma City, OK | Construction |  | 2021-06-20 | 2021-10-10 | 112 | Yes | 2021-09-06 | 2022-01-28 |  | 4.7841 |  |  | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 130000 |  | 230000 | -50000
OK2039 | Rockwell Daycare | AE | STROUD | 1213 N. Rockwell Ave., Oklahoma City, OK 73127 | Complete |  | 2020-12-01 | 2020-12-21 | 20 | Yes | 2021-02-01 | 2021-03-31 |  | 1.9269 | Complete |  | 81500 | 0 | 0 | 0 | 81500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 81500 | 0
OK2110-1 | Shawnee Shell - Shawnee, OK | AE | STROUD | 4797 N. Harrison, Shawnee, OK 74804 | Construction |  | 2021-07-14 | 2021-09-17 | 65 | Yes | 2021-10-17 | 2022-06-14 19:12 |  | 8 |  |  | 1225500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192936.95 | 250000 | 250000 | 575500 |  | 1268436.95 | 42940
OK2110-2 | Shawnee Shell - Old School Bagel | AE | STROUD | 4799 N. Harrison, Shawnee, OK 74804 | Construction |  | 2021-10-08 | 2021-11-22 | 45 | No | 2021-12-22 | 2022-06-20 14:24 |  | 6 |  |  | 242554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12582.01 | 50000 | 50000 | 117554 |  | 230136.01 | -12420
OK2110-3 | Shawnee Shell - OSO | AE | STROUD | 4795 N. Harrison, Shawnee, OK 74804 | Construction |  | 2021-10-29 | 2021-12-13 | 45 | No | 2022-01-12 | 2022-07-11 14:24 |  | 6 |  |  | 380405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34445.59 | 50000 | 50000 | 255405 |  | 389850.59 | 9450
[17 empty] | 11302066 | 2047245 | 702828 | 153598 | 849658 | 538775 | 755703 | 739337 | 204636 | 810992 | 498956.42 | 626679.61 | 950000 | 916413 | 1333924.49 | 0 | 11128745.52 | -173320
Wes Gaddy |  | WG | [31 empty] | 0
OK2011-1 | Mustang Shell | WG | WILLIAMS | 1708 S Mustang Rd., Mustang, OK 73064 | Complete |  | 2021-05-01 | 2021-07-01 | 61 | Yes | 2020-09-01 | 2021-03-31 |  | 7.01 | Complete |  | 940687 | 720455 | 114649 | 0 | 105583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste D | Complete |  | 2021-05-01 | 2021-07-01 | 61 | Yes | 2020-11-01 | 2021-03-31 |  | 4.9834 | Complete |  | 226188 | 64622 | 39562 | 18328 | 101052 | 2624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226188 | 0
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste A | Complete |  | 2021-05-01 | 2021-07-01 | 61 | Yes | 2020-11-01 | 2021-03-31 |  | 4.9834 | Complete |  | 315962 | 124791 | 64927 | 25844 | 98461 | 1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315962 | 0
[17 empty] | 1482837 | 909868 | 219138 | 44172 | 305096 | 4563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482837 | 0
Christopher Goldsmith |  | CG | [31 empty] | 0
OK1902-1 | Empire Financial | CG | CLINTON | 12100 South Yukon Ave. Suite C, Glenpool, OK 74033 | Construction |  | N/A | N/A | N/A | N/A | 2021-05-14 | 2021-07-14 |  | 2.0266 |  |  | 46806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46806 | 0 | 0 |  |  |  |  | 46806 | 0
OK1923-3 | Tropical Smoothie - Riverwest | CG | CLINTON | 152 W Alexander Blvd., Sand Springs, OK 74063 | Construction |  | 2021-06-01 | 2021-06-15 | 14 | Yes | 2021-05-28 | 2021-10-28 |  | 5.0831 |  |  | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58100 | 0 | 0 |  |  | 31025 |  | 89125 | 0
OK1923-4 | Stanton Optical - Riverwest | CG | CLINTON | 153 W Alexander Blvd., Sand Springs, OK 74063 | Construction |  | 2021-06-01 | 2021-06-15 | 14 | Yes | 2021-06-06 | 2021-09-03 |  | 2.9568 |  |  | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75650 | 0 | 0 |  |  |  |  | 75650 | 0
OK1936 | Dr Fischer | CG | CLINTON | 720 West 71St Street S, Tulsa, OK 74132 | Construction |  | 2020-04-08 | 2020-06-22 | 75 | Yes | 2020-06-22 | 2021-09-30 |  | 15.4485 |  |  | 2482030 | 1788494 | 93223 | -90886 | 247214 | 203016 | 0 | 88152 | 152817 | 0 | 0 | 0 |  |  |  |  | 2482030 | 0
OK2008 | Dr. Gaches | CG | CLINTON | 11492 N. 137th E. Ave., Owasso, OK | Construction |  | 2020-08-28 | 2021-03-05 | 189 | Yes | 2021-04-04 | 2021-10-15 |  | 6.4452 |  |  | 683158 | 65749 | 0 | 0 | 72518 | 31182 | 36101 | 79510 | 164718 | 104045 | 68162.76 | 61173.01 |  |  | 21837.24 |  | 704996.01 | 21840
OK2014 | Clark Plaza Shell | CG | CLINTON | 7877 E 71st South., Tulsa, OK 74133 | Construction |  | 2020-10-16 | 2021-02-19 | 126 | Yes | 2021-03-01 | 2021-12-27 |  | 10 |  |  | 1436404 | 91138 | 0 | 0 | 0 | 55754 | 185059 | 486176 | 117904 | 116211 | 178250.15 | 0 | 100000 | 34162 | -53250.15 |  | 1311404 | -125000
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | CLINTON | 7877 E 71st South Ste A, Tulsa, OK 74133 | Construction |  | 2020-12-03 | 2021-03-25 | 112 | Yes | 2021-03-29 | 2021-11-24 19:12 |  | 8 |  |  | 648253 | 124344 | 0 | 0 | 0 | 0 | 0 | 82390 | 0 | 125825 | 199275.86 | 49841.62 | 85694 |  | -69275.86 |  | 598094.62 | -50160
OK2014-2 | Clark Shell - Enhance DDS | CG | CLINTON | 7877 E 71st South Ste B., Tulsa, OK 74133 | Construction |  | 2020-12-03 | 2021-03-25 | 112 | Yes | 2021-03-29 | 2021-11-24 |  | 7.9734 |  |  | 400187 | 14681 | 0 | 0 | 0 | 0 | 0 | 50940 | 0 | 231205 | 53980.66 | 26603.7 | 3361 |  | -3980.66 |  | 376790.7 | -23400
OK2032-1 | Cross Roads - Shell | CG | CLINTON | 1167 N. 38th Street, Broken Arrow, OK 74014 | Construction |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | CLINTON | 1171 N. 38th Street, Broken Arrow, OK 74014 | Construction |  | 2021-08-11 | 2021-10-08 | 58 | Yes | 2021-09-15 | 2021-11-26 09:36 |  | 2.4053 |  |  | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000 | 75000 | 85000 |  | 245000 | -85000
[17 empty] | 6191613 | 2084406 | 93223 | -90886 | 319732 | 289952 | 221160 | 787168 | 435439 | 757842 | 499669.43 | 137618.33 | 274055 | 109162 | 11355.57 | 0 | 5929896.33 | -261720
Cassidy Hedrick |  | CH | [31 empty] | 0
OK2028P | Precon - Memorial Park | CH | CH |  | Complete |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 461956 | 0
OK2104 | Wimberley Walker Remodel | CH | CH | 101 Twilight Trail, Wimberly, TX 78676 | Construction |  | N/A | N/A | N/A | Yes | 2020-12-30 | 2021-09-30 |  | 9.103 |  |  | 500577 | 0 | 0 | 17615 | 71648 | 0 | 97695 | 103125 | 92500 | 117994 |  | 0.02 |  |  |  |  | 500577.02 | 0
[17 empty] | 962533 | 0 | 353138 | 126433 | 71648 | 0 | 97695 | 103125 | 92500 | 117994 | 0 | 0.02 | 0 | 0 | 0 | 0 | 962533.02 | 0
Kimberly Kelly |  | KK | [31 empty] | 0
OK2038 | Dr. Farmer TI - Wonga Corner | KK | WILLIAMS | 1152 W. Douglas Midwest City, OK | Construction |  | 2021-02-26 | 2021-03-17 | 19 | Yes | 2021-03-17 | 2021-08-27 |  | 5.4153 |  |  | 383545 | 0 | 0 | 0 | 0 | 118932 | 110310 | 66219 | 58693 | 29391 | 0 | 0 |  |  |  |  | 383545 | 0
TX1903 | Ramon Franklin Warehouse | KK | MILLER | 1308 Corporate Drive East, Arlinton, TX 76006 | Construction |  | 2020-12-09 | 2021-01-27 | 49 | Yes | 2021-07-05 | 2021-12-10 |  | 5.2492 |  |  | 1006579 | 131243 | 0 | 0 | 0 |  | 83010 | 67371 | 0 | 103268 | 113601.11 | 227523.97 | 171687 |  | 111398.89 |  | 1009102.97 | 2520 | Contract value needs to be increased. Submit a ProCore Change Event
TX2101 | Bob Mills - Forth Worth | KK | JOHNSON | 3600 East Long Ave., Ft Worth, TX 76111 | Construction |  | 2021-04-09 | 2021-06-10 | 62 | Yes | 2021-07-10 | 2021-12-10 |  | 5.0831 |  |  | 2259828 | 0 | 0 | 0 | 0 | 0 | 105517 | 201248 | 0 | 748228 | 181824.92 | 308182.91 | 300000 | 104835 | 218175.08 |  | 2168010.91 | -91820
[17 empty] | 3649952 | 131243 | 0 | 0 | 0 | 118932 | 298837 | 334838 | 58693 | 880887 | 295426.03 | 535706.88 | 471687 | 104835 | 329573.97 | 0 | 3560658.88 | -89290
Cory Muir |  | CM | [31 empty] | 0
OK2026 | Covell I35 Edmond Dev. | CM | STROUD | 5400 E. Covell Road, Edmond, OK | Construction |  | 2021-04-21 | 2021-08-09 | 110 | Yes | N/A | N/A |  | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0
OK2034 | Dr. Rex Johnson, DVM - Covell I35 | CM | STROUD | 5401 E. Covel Rd., Edmond, OK 73034 | Construction |  | 2021-05-12 | 2021-08-10 | 90 | Yes | 2021-06-25 | 2022-06-21 |  | 11.9934 |  |  | 1961016 | 0 | 0 |  |  | 233134 | 0 | 0 | 72994 | 144486 | 174326.34 | 157369.33 | 165000 | 175000 | 806075.66 |  | 1928385.33 | -32630
OK2106-1 | Fox Lake Shell | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Construction |  | 2021-06-22 | 2021-09-22 | 92 | Yes | 2021-07-22 | 2022-08-30 |  | 13.4219 |  |  | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 941343 | 403549.63 | 37623.36 | 522000 | 772000 | 6839107.37 |  | 9515623.36 | -484380
[17 empty] | 11961016 | 0 | 0 | 0 | 0 | 233134 | 0 | 0 | 72994 | 1085829 | 577875.97 | 194992.69 | 687000 | 947000 | 7645183.03 | 0 | 11444008.69 | -517010
Jason Nowell |  | JN | [31 empty] | 0
OK1912 | Dr. Shirley | JN |  | 2441 SW 134th, Oklahoma City, OK 73170 | Complete |  |  |  | 0 | Yes | 2020-01-06 | 2020-09-16 |  | 8.4385 | Complete |  | 1217703 | 1206322 | 11381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 1217703 | 0
OK1931 | Dr. Crowley | JN |  | 15101 Crown at Lone Oak Rd, OKC 73013 | Complete |  |  |  | 0 | Yes | 2020-02-28 | 2020-12-22 |  | 9.9003 | Complete |  | 578876 | 568341 | 2335 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 |  | 0 |  |  |  |  | 578876 | 0
[17 empty] | 1796579 | 1774663 | 13716 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1796579 | 0
Bob Solomon |  | BS | [31 empty] | 0
OK1926 | Hunter Pharmacy | BS | SMITH | 10120 Broadway Ext., OKC 73114 | Complete |  | 2020-05-14 | 2020-07-08 | 55 | Yes | 2020-07-21 | 2021-06-24 |  | 11.2292 |  |  | 9534114 | 4251267 | 974630 | 965506 | 726926 | 1007479 | 748387 | 599421 | 93601 | 88474 | 65327.47 | 13094.4 |  |  | -23801.47 |  | 9510311.4 | -23800 | Revised projected billing in Aug & Sept. $36,897 may be a savings split with Hunter
OK2006 | El Reno Enhanced Dental | BS | STROUD | 1601 Investors Ave., El Reno, OK 73036 | Complete |  | 2020-06-16 | 2020-06-23 | 7 | Yes | 2020-10-20 | 2021-07-15 |  | 8.9037 |  |  | 1258636 | 501155 | 186495 | 202246 | 66602 | 48430 | 7649 | 118643 | 54525 | 32612 | 0 | 0 |  |  | 40279 |  | 1258636 | 0 | Revised projected billing in Aug. Expecting $6,000 to be returned to the Owner.
OK2113 | Carlton Landing Sewer - Eufaula, OK | BS | TBD |  | Preconstruction |  | N/A | N/A | N/A | No |  |  |  | 0 |  |  | 82107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27107 |  | 25000 |  | 52107 | -30000
TX1901 | Dr. Dyer - Sequoia Spur | BS | STEPHENSON | 115 Shell Rd, Georgtown, TX 78633 | Construction |  | 2020-05-11 | 2020-07-06 | 56 | Yes | 2020-11-01 | 2021-12-01 |  | 13.1229 |  |  | 1809504 | 407476 | 214131 | 74131 | 135778 | 437832 | 31174 | 82243 | 45087 | 149925 | 55587.04 | 113628.69 | 31727 |  | 44412.96 |  | 1823132.69 | 13630
TX2001 | Dr. Lippian - Texarkana | BS | HARRIS | 5220 Gibson Ln., Texarkana, TX 75501 | Construction |  | 2020-09-30 | 2020-12-29 | 90 | Yes | 2021-01-28 | 2021-11-01 |  | 9.2027 |  |  | 1641198 | 103605 | 0 | 71204 | 158532 | 124183 | 320119 | 192377 | 74223 | 357461 | 34466.45 | 131256.06 | 14494 |  | 115533.55 |  | 1697454.06 | 56260
[17 empty] | 14325559 | 5263503 | 1375256 | 1313087 | 1087838 | 1617924 | 1107329 | 992684 | 267436 | 628472 | 155380.96 | 257979.15 | 73328 | 0 | 201424.04 | 0 | 14341641.15 | 16080
Kyle Tedlock |  | KT | [31 empty] | 0
OK2016 | OneCore | KT | HALL | 100 NE 85th Street, OKC, OK 73114 | Construction |  | 2020-08-11 | 2020-11-12 | 93 | Yes | 2020-10-15 | 2021-12-01 |  | 13.6877 |  |  | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 1384616.45 | 896696.76 | 800000 | 52499 | -434616.45 |  | 13054607.76 | -53300
[17 empty] | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 1384616.45 | 896696.76 | 800000 | 52499 | -434616.45 | 0 | 13054607.76 | -53300
Kevin Trosper |  | KT | [31 empty] | 0
OK1822-3 | R&D Construction | KT | TROSPER | 901 E. Main Suite 125, Yukon, OK 73099 | Complete |  | N/A | N/A | N/A | N/A | 2021-07-05 | 2021-08-20 |  | 1.5282 |  |  | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28797 | 8473.4 | 0 |  |  | 51854.6 |  | 89125 | 0
OK1822-4 | Blondette | KT | TROSPER | 902 E. Main Suite 115, Yukon, OK 73099 | Complete |  | N/A | N/A | N/A | N/A | 2021-07-05 | 2021-08-20 |  | 1.5282 |  |  | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24902 | 5295.49 | 0 |  |  | 45452.51 |  | 75650 | 0
OK1909-3 | Allstate Insurance (Brandon) | KT | TROSPER | 1140 NW 192nd Street Suite B, Oklahoma City, OK | Complete |  | 2021-04-13 | 2021-04-27 | 14 | Yes | 2021-05-17 | 2021-06-09 |  | 0.76412 |  |  | 67027 | 0 | 0 | 0 | 0 | 0 | 0 | 67027 | 0 | 0 | 0 | 0 |  |  |  |  | 67027 | 0
OK1917-4 | Colonial Point - Nutrition Club | KT | TROSPER | 11999 NW Expressway Yukon, OK 73099 | Construction |  | 2021-06-22 | 2021-07-12 | 20 | Yes | 2021-07-05 | 2021-10-01 |  | 2.9236 |  |  | 38040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38040 | 0 | 0 |  |  |  |  | 38040 | 0
OK1922-3 | Coltrane Corner - Regent Bank (Mike) | KT | TROSPER | 2823 E. 2nd, Suite C, Edmond, OK | Complete |  | 2021-05-14 | 2021-06-15 | 32 | Yes | 2021-06-21 | 2021-08-17 |  | 1.8937 |  |  | 74344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74344 | 0 | 0 |  |  |  |  | 74344 | 0
OK1922-4 | Coltrane Corner - Klassy K9 (Mike) | KT | TROSPER | 2824 E. 2nd, Edmond, OK | Complete |  | N/A | N/A | N/A | N/A | 2021-06-11 | 2021-07-02 |  | 0.69767 |  |  | 6336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336 | 0 | 0 |  |  |  |  | 6336 | 0
TX2006-1 | Sunnyvale Shell | KT | TROSPER | 480 US Hwy 80, Sunnyvale, TX 75182 | Construction |  | 2021-06-22 | 2021-10-08 | 108 | No | 2021-11-07 | 2022-04-29 |  | 5.7475 |  |  | 1910050 | 0 | 0 | 0 | 0 | 0 | 0 | 119451 | 0 | 139349 | 0 | 270190.83 | 175000 | 175000 | 1079250 |  | 1958240.83 | 48190
TX2006-2 | Sunnyvale Shell - Dr. Luna | KT | TROSPER | 481 US Hwy 80, Sunnyvale, TX 75182 | Construction |  | 2021-10-15 | 2021-11-14 | 30 | No | 2021-12-14 | 2022-05-25 |  | 5.3821 |  |  | 288979 | 0 | 0 | 0 | 0 | 0 | 0 | 7826 | 0 | 9711 | 0 | 0 | 34000 | 20000 | 189442 |  | 260979 | -28000
TX2006-3 | Sunnyvale Shell - Dr. Rohani | KT | TROSPER | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction |  | 2021-10-22 | 2021-11-21 | 30 | No | 2021-12-21 | 2022-05-25 |  | 5.1495 |  |  | 366822 | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 0 | 12408 | 0 | 0 | 44000 | 26000 | 240698 |  | 330822 | -36000
OK2101 | Christian Counseling | KT | TROSPER | 12901 E. Britton Rd. Suite B, Jones, 73049 | Complete |  | N/A | N/A | N/A | Yes | 2021-03-01 | 2021-05-31 |  | 3.0233 |  |  | 52095 | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | 0 | 0 | 0 | 0 |  |  | 0 |  | 52095 | 0
OK2105-1 | Valencia - Breakroom 405 (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. A, Edmond, OK 73012 | Complete |  | 2021-03-22 | 2021-04-16 | 25 | Yes | 2021-05-24 | 2021-08-11 |  | 2.6246 |  |  | 156692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156692 | 0 | 0 | 0 |  |  | 0 |  | 156692 | 0
OK2105-2 | Valencia - Christfit Gym (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Complete |  | 2021-03-22 | 2021-04-07 | 16 | Yes | 2021-05-24 | 2021-08-09 |  | 2.5581 |  |  | 94557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94557 | 0 | 0 | 13646.35 |  |  | 0 |  | 108203.35 | 13650
OK2105-3 | Valencia - Winfield and Co. | KT | TROSPER | 2216 NW 178th Street Ste. E, Edmond, OK 73012 | Construction |  | 2021-09-01 | 2021-09-16 | 15 |  | 2021-09-22 | 2021-10-17 |  | 0.83056 |  |  | 29164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 22329 |  | 22329 | -6840
OK2105-4 | Valencia - Prevail Fitness | KT | TROSPER | 2215 NW 178th Street Ste. B, Edmond, OK 73012 | Construction |  | 2021-05-07 | 2021-06-11 | 35 | Yes | 2021-07-06 | 2021-09-17 |  | 2.4252 |  |  | 101240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36103 | 58225 | 0 | 0 |  |  | 6912 |  | 101240 | 0
OK2105-5 | Valencia - Magnus Batting Cage (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. D, Edmond, OK 73012 | Complete |  | 2021-06-04 | 2021-06-21 | 17 | Yes | 2021-06-28 | 2021-08-30 |  | 2.093 |  |  | 36900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36900 | 0 | 0 | 0 |  |  | 0 |  | 36900 | 0
OK2105-6 | Valencia - Breakroom 405 Warehouse | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Construction |  | 2021-09-21 | 2021-10-15 | 24 | No | 2021-09-29 | 2021-10-08 |  | 0.299 |  |  | 19970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 19970 |  | 19970 | 0
[17 empty] | 3406991 | 0 | 0 | 0 | 0 | 0 | 0 | 254115 | 324252 | 392112 | 13768.89 | 283837.18 | 253000 | 221000 | 1655908.11 | 0 | 3397993.18 | -9000
Phillip Wilson |  | KT | [31 empty] | 0
TN2101 | AIM - Memphis, TN | PW | WILSON | 7007 Stage Rd., Memphis, TN 38133 | Construction |  | 2021-06-18 | 2021-10-15 | 119 | No | 2021-10-30 | 2022-05-06 19:12 |  | 6.2724 |  |  | 2015533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141412 | 0 | 0 | 400000 | 500000 | 674121 |  | 1715533 | -300000
[17 empty] | 2015533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141412 | 0 | 0 | 400000 | 500000 | 674121 | 0 | 1715533 | -300000
Preconstruction | [33 empty] | 0
OK2033-3 | Chamberlain Realty - Santa Fe Dev. | AE | WILLIAMS | 113 SW 134th Street, Oklahoma City, OK | Preconstruction |  | 2021-10-15 | 2021-11-15 | 31 | No | 2021-12-15 |  |  | -1479.9003 |  |  | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200000 | 1700000 |  | 1900000 | 0
OK2037 | Master Hand Milling | TBD | TBD | TBD, Edmond, OK | Preconstruction |  | 2022-01-03 | 2022-01-30 | 27 | No | 2023-01-01 | 2022-09-27 |  | -3.1894 |  |  | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4000000 | 4000000 | 0
OK2102 | Puppy Paws East Edmond | TBD | TBD | East Edmond | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-02-01 | 2022-09-13 |  | 7.4419 |  |  | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2200000 |  | 2200000 | 0
OK2106-2 | Fox Lake - Sidecar | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2022-01-03 | 2022-01-13 | 10 | No | 2022-02-12 |  |  | -1481.8605 |  |  | 980000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 980000 |  | 980000 | 0
OK2106-3 | Fox Lake - Hatch | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2022-01-03 | 2022-01-31 | 28 | No | 2022-03-02 |  |  | -1482.4585 |  |  | 1558000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1558000 |  | 1558000 | 0
OK2106-4 | Fox Lake - Enhanced Dental | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2021-10-15 | 2021-11-15 | 31 | No | 2021-12-15 |  |  | -1479.9003 |  |  | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 540000 |  | 540000 | 0
OK2106-5 | Fox Lake - Open Space | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2022-01-03 | 2022-01-31 | 28 | No | 2022-03-02 |  |  | -1482.4585 |  |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 800000 |  | 800000 | 0
OK2106-6 | Fox Lake Provision Concepts | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | 2022-01-03 | 2022-01-31 | 28 | No | 2022-03-02 |  |  | -1482.4585 |  |  | 690000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 690000 |  | 690000 | 0
OK2107 | Jack Be Grocery | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-01 | 29 | No | 2022-03-03 |  |  | -1482.4917 |  |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2500000 |  | 2500000 | 0
OK2108 | Puppy Paws - Lone Oak | TBD | TBD | 15200 Crown at Lone Oak, Edmond OK 73013 | Preconstruction |  | 2021-10-15 | 2021-11-14 | 30 | No | 2021-11-21 |  |  | -1479.103 |  |  | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 250000 | 1800000 |  | 2200000 | 0
OK2112 | Dr. Lu Dentistry - Covell 35 Dev. | CM | STROUD | 5249 E. Covel Rd., Edmond, OK 73034 | Preconstruction |  | 2021-10-19 | 2021-11-01 | 13 | No | 2021-11-15 |  | 2022-06-01 | -1478.9037 |  |  | 1325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100000 | 1225000 |  | 1325000 | 0
OK2114-1 | Chamberlain Realty - Lone Oak | TBD | TBD | 15103 Crown at Lone Oak Rd., Edmond, OK 73013 | Preconstruction |  | 2021-12-01 | 2022-01-15 | 45 | No | 2022-02-14 |  |  | -1481.9269 |  |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 100000 | 250000 |  | 400000 | 0
OK2115 | Paul's Valley Development | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 1677500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1677500 |  | 1677500 | 0
OK2116 | Dollar Tree (Paul's Valley Development) | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 753000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 753000 |  | 753000 | 0
OK2117-1 | Paul's Valley Shell | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 500000 |  | 500000 | 0
OK2117-2 | Paul's Valley Shell - Enhanced Dental | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 650000 |  | 650000 | 0
OK2118 | Paul's Valley Shell - TBD | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
OK2119 | OSB - Wonga Corner | HOLD | HOLD | 1156 S. Douglas, Midwest City, OK 73130 | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 100000 | 200000 |  | 350000 | 0
OK2120 | Peak View Brewery and Distillery | TBD | TBD | Reservoir by Costco | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 |  |  | -1482.9568 |  |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3000000 |  | 3000000 | 0
OK2121 | 15th & Bryant Development | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-02-01 |  |  | -1481.495 |  |  | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 680000 |  | 680000 | 0
OK2122 | The Learning Experence (15th & Bryant Development) | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-02-01 |  | 2022-08-01 | -1481.495 |  |  | 2180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2180000 |  | 2180000 | 0
OK2123 | TBD (15th & Bryant Development) | TBD | TBD |  | Preconstruction |  | 2022-01-03 | 2022-02-15 | 43 | No | 2022-03-17 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
OK2124 | Bodin Chiro (Lone Oak) | TBD | TBD |  | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-01-31 |  |  | -1481.4618 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 350000 |  | 350000 | 0
OK2125-1 | Enid Shell | TBD | TBD |  | Preconstruction |  | 2021-11-12 | 2021-10-31 | -12 | No | 2021-03-01 |  |  | -1470.299 |  |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1500000 |  | 1500000 | 0
OK2125-2 | OSB - Enid | TBD | TBD |  | Preconstruction |  | 2021-11-26 | 2021-11-15 | -11 | No | 2022-03-01 |  |  | -1482.4252 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 350000 |  | 350000 | 0
OK2125-3 | Enhanced Dental - Enid | TBD | TBD |  | Preconstruction |  | 2021-11-26 | 2021-11-15 | -11 | No | 2022-03-01 |  |  | -1482.4252 |  |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 450000 |  | 450000 | 0
OK2126-1 | Weatherford Shell | TBD | TBD |  | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 |  |  | -1481.495 |  |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1200000 |  | 1200000 | 0
OK2126-2 | Weatherford Shell - Dollar Tree | TBD | TBD |  | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2021-12-31 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
OK2126-3 | Weatherford Shell - Enhanced Dental | TBD | TBD |  | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 | [5 empty] | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 350000 |  | 350000 | 0
OK2127 | Legacy Martial Arts Shell | TBD | TBD |  | Preconstruction |  |  |  | 0 | No | 2022-01-30 |  |  | -1481.4286 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 750000 |  | 750000 | 0
OK2128 | OSB 150th and Penn | TBD | TBD | 15201 N. Penn Crossing Court, Oklahoma City, OK 73013 | Preconstruction |  | 2021-12-01 | 2021-12-31 | 30 | No | 2022-01-30 |  |  | -1481.4286 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 750000 |  | 750000 | 0
Okxxxx | Regent Center (Fox Lake Similar) | TBD | TBD | Broken Arrow | Preconstruction |  | 2022-02-01 | 2022-04-02 | 60 | No | 2022-05-02 |  |  | -1484.485 |  |  | 14000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 11000000 | 3000000 | 14000000 | 0
Okxxxx | AIM Bellevue - Site Visit Needed | PW | TBD | 7734 Hwy 70 S. Nashville, TN 37221 | Preconstruction |  |  |  | 0 | No | 2022-04-01 |  |  | -1483.4551 |  |  | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2400000 |  | 2400000 | 0
Okxxxx | Anytime Fitness - Brandon Porter | TBD | TBD |  | Preconstruction |  |  |  | 0 | No | 2022-01-30 |  |  | -1481.4286 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
TX2005 | McKinney Development | TBD | TBD | Virginia and Ridge Road, McKinney, TX | Preconstruction |  | 2021-10-01 | 2021-11-15 | 45 | No | 2022-02-01 | 2022-09-29 19:12 |  | 8 |  |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 150000 | 300000 |  | 550000 | -50000
TX2007-1 | Carrollton Shell | KT | DOYLE | Carrollton, TX | Preconstruction | 2021-10-01 | 2021-06-15 | 2021-10-10 | 117 | No | 2021-11-09 | 2022-07-12 |  | 8.1395 |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 1400000 |  | 1800000 | -200000
TX2007-2 | Carrolton Shell - Dr. Bui | KT | DOYLE | Carrollton, TX | Preconstruction |  | 2021-10-15 | 2021-11-29 | 45 | No | 2021-12-29 | 2022-05-20 19:12 |  | 4.7442 |  |  | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 400000 |  | 500000 | -50000
TX2008 | Dr. Barbara Lee - McKinney Development | TBD | TBD | McKinney, TX | Preconstruction |  | 2021-10-22 | 2021-12-06 | 45 | No | 2022-02-01 | 2022-09-29 19:12 |  | 8 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 300000 |  | 600000 | -150000
TX2102-1 | San Antonio Shell | TBD | TBD | San Antonio, TX | Preconstruction |  | 2021-10-29 | 2021-12-13 | 45 | No | 2022-01-12 |  |  | -1480.8306 |  |  | 2229000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2229000 |  | 2229000 | 0
TX2102-2 | Dr. Abeskharon - San Antonio | TBD | TBD | San Antonio, TX | Preconstruction |  | 2021-10-29 | 2021-12-13 | 45 | No | 2022-01-12 |  |  | -1480.8306 |  |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 360000 |  | 360000 | 0
TX2103-1 | McKinney Shell (McKinney Development) | TBD | TBD | McKinney, TX | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 | [5 empty] | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 600000 |  | 600000 | 0
TX2103-2 | TBD TI (McKinney Shell) | TBD | TBD | McKinney, TX | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
TX2103-3 | TBD TI (McKinney Shell) | TBD | TBD | McKinney, TX | Preconstruction |  | 2021-11-01 | 2021-12-01 | 30 | No | 2022-02-01 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
[17 empty] | 58072500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 1300000 | 48572500 | 7000000 | 57622500 | -450000
DEAD / HOLD / SOLD | [33 empty] | 0
FL2001 | Elysee Lot 6 | SOLD | SOLD | SOLD | SOLD |  | SOLD | SOLD | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD | 137906 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 3503 | 0 | 0 | 0 |  |  |  |  | 137906 | 0
FL2002 | Elysee Lot 7 | SOLD | SOLD | SOLD | SOLD |  | SOLD | SOLD | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD | 136537 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 2134 | 0 | 0 | 0 |  |  |  |  | 136537 | 0
OK1922-1 | Coltrane Corner - Aya Rowe | KT | TROPSER | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
OK1924 | Yukon Development | HOLD | HOLD | HOLD | HOLD |  | HOLD | HOLD | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
OK2018 | Dr. Mackey - 61st Street | HOLD | HOLD | 9050 E. 61st Street, Tulsa, OK 74145 | HOLD |  | 2020-10-03 | 2021-03-24 | 172 | Yes | 2021-07-12 | 2022-01-08 14:24 |  | HOLD | HOLD | HOLD | 33274 | 0 | 0 | 0 | 0 | 0 | 33274 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 33274 | 0
OK2020-4 | Western - PT Central | KT | TROPSER | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
OK2028 | Precon - Memorial Park | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 461956 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15630 | 0 | 0 | 15630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 15630 | 0
OK2032-3 | Cross Roads - State Farm | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15000 | 0 | 0 | 5720 | 0 | 9280 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 15000 | 0
OK2032-5 | Cross Roads - Dispensary | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
OK2036 | Dr. Matt Cole, DDS | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 41062 | 0 | 0 | 0 | 0 | 0 | 41062 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 41062 | 0
OK2103 | Bethesda - Santa Fe Dev. | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
OK2105-3 | Valencia - Custom Pools | KT | TROPSER | 2215 NW 178th Street Ste. E, Edmond, OK 73012 | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15493 | 0 | 0 |  |  |  |  | 15493 | 0
OK2111 | Solara Surgery Center - Moore, OK | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
OK2109-1 | Grand Blvd. Shell - OKC, OK | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | HOLD | HOLD | HOLD | HOLD |  | HOLD | HOLD | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
TX2004 | Marshall Ridge Dev. | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 37392 | 0 | 0 | 37392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 37392 | 0
TX2009 | Alliance Pediatrics-Marsh | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 3575 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 3575 | 0
[17 empty] | 897825 | 122184 | 353138 | 171135 | 0 | 155902 | 74336 | 0 | 5637 | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 897825 | 0
0
[14 empty] | Billing Total |  |  | 129172915 | 13135775 | 4162260 | 2539811 | 3804063 | 4027943 | 3386920 | 4748195 | 3019590 | 6352244 | 3425694.15 | 2933510.62 | 4659070 | 4150909 | 59989373.76 | 7000000 | 127335358.53 | -1837560
[17 empty] | Billing Goal | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 | 16008105
[17 empty] | Difference | -1521270 | 1364142.8571 | -667013.6429 | -204329.6429 | -291054.6429 | -1682646.6429 | -827619.6429 | -2295114.6429 | 875404 | -1934264.85 | -3240053.38 | -842652 | 284374
[17 empty] | Rev Actual |  | 2897650 | 3085444 | 3369732
[17 empty] | Rev Goal |  | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 | 12779270.2215
[17 empty] | Difference |  | 663913.0849 | 525435.8876 | 169832.1532
[17 empty] | GP Actual |  | 261214 | 325090 | 157521
[17 empty] | GP Goal |  | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 | 1403910.8085
[17 empty] | Difference |  | 15819.1266 | 43851.4788 | -194015.0348
[17 empty] | GP % Actual |  | 9.01% | 10.54% | 4.67%
[17 empty] | GP % Goal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
[17 empty] | Difference |  | -0.99% | 0.54% | -5.33%
[17 empty] | OH Actual |  | 256248 | 250107 | 305940
[17 empty] | OH Goal |  | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
[17 empty] | Difference |  | 18752 | 24893 | -30940
[17 empty] | NP Actual |  | 4126 | 74711 | -101036
[17 empty] | NP Goal |  | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 | 500000.0033
[17 empty] | Difference |  | -20413.4873 | 46587.1479 | -136189.6035
Formulas:
Permit Received = [Permit Submitted]+35
Start Date = [Permit Received]+30
Comp Date = [Start Date]+(8*4.3*7)
Note on P14: Bobby Snyder: Punchlist was conducted via facetime and all items have been completed. Final punch walk will occur in Sept with Rep from CA
Note on B36: Bobby Snyder: Existing Building
Note on R36: Existing Building
Note on R138: Bobby Snyder: Project on Hold
Note on B139: Bobby Snyder: Another GC built out this space.

## 11 2021
[22 empty] | 2020 | 2021 | [11 empty] | 2022 | [11 empty] | 2023
Job Number | Project | PM | SUP | Address | Status | Turn Over Complete | Loan Close | Anticipated Permit Submission | Actual Permit Submitted | Anticipated Permit Received | Actual Permit Received | Anticipated Approval Duration | Permit Approval Duration | Permit Received | Start Date | Comp Date | Planned Comp Date | Duration | Punchlist Complete Date | Lessons Learned | Spectrum Value | Annual 2020 | January | February | March | April | May | June | July | August | September | October | November | December | January 2022 | February 2022 | March 2022 | April 2022 | May 2022 | June 2022 | July 2022 | August 2022 | September 2022 | October 2022 | November 2022 | December 2022 | Annual 2023 | TOTAL | DELTA | COMMENTS
Adam England |  | AE
OK2003 | Enhance Dental - Choctaw | AE | WILLIAMS | 2651 Market Blvd., Choctaw, OK 73020 | Complete |  |  |  | 2020-02-06 |  | 2020-05-01 |  | 85 | Yes | 2020-06-01 | 2020-11-20 |  | 5.7143 | Complete |  | 605990 | 568347 | 879 | 35573 | 656 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 605990 | 0
OK2005 | Quail Springs Shell | AE | FRARY | 14424 N May Ave., OKC 73134 | Complete |  |  |  | 2020-05-22 |  | 2020-06-24 |  | 33 | Yes | 2020-08-05 | 2021-02-10 |  | 6.2791 | Complete |  | 845876 | 628337 | 137155 | 19492 | 60892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | FRARY | 14424 N May Ave., OKC 73134 Ste A | Complete |  |  |  | 2020-07-29 |  | 2020-10-02 |  | 65 | Yes | 2020-09-28 | 2021-02-14 |  | 4.6179 | Complete |  | 303150 | 162612 | 95646 | 33342 | 5713 | 5837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 303150 | 0
OK2005-2 | Quail Springs - Just Kids Ped's | AE | FRARY | 14425 N May Ave., OKC 73134 Ste B | Complete |  |  |  | 2020-06-25 |  | 2020-07-17 |  | 22 | Yes | 2020-09-28 | 2021-02-10 |  | 4.485 | Complete |  | 222517 | 131745 | 62828 | 27944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 222517 | 0
OK2019 | Santa Fe Development | AE | WILLIAMS | 100 Southwest 134th Street, OKC, OK 73170 | Construction |  |  |  | 2021-02-16 |  | 2021-04-16 |  | 59 | Yes | 2021-05-03 | 2021-11-05 |  | 6.1794 |  |  | 1181870 | 0 | 0 | 0 | 0 | 0 | 154842 | 139424 | 0 | 383465 | 27725.91 | 0 | 157207.64 | 226413.09 | [13 empty] | 1089077.64 | -92792.36 | Water meter issues
OK2020-1 | Western Shell | AE | FRARY | 11521 South Western Ave., OKC, OK 73170 | Complete |  |  |  | 2020-08-03 |  | 2020-11-27 |  | 116 | Yes | 2020-11-09 | 2021-07-30 |  | 8.7375 | Complete |  | 1307434 | 244435 | 181308 | 16313 | 286477 | 175065 | 254689 | 149147 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 1307434 | 0
OK2020-2 | Western Shell - Scammahorn | AE | FRARY | 11522 South Western Ave., OKC, OK 73170 | Complete |  |  |  | 2020-08-06 |  | 2020-11-28 |  | 114 | Yes | 2020-11-09 | 2021-08-10 |  | 9.103 | Complete |  | 278383 | 46929 | 38525 | 0 | 45735 | 40858 | 33047 | 43566 | 18912 | 0 | 0 | 0 | 0 | [14 empty] | 267572 | -10811
OK2020-3 | Western Shell - Dr. Olsen | AE | FRARY | 11523 South Western Ave., OKC, OK 73170 | Complete |  |  |  | 2020-08-11 |  | 2020-11-28 |  | 109 | Yes | 2020-11-09 | 2021-08-02 |  | 8.8372 | Complete |  | 231276 | 34010 | 31345 | 0 | 42608 | 27037 | 28599 | 46383 | 20189 | 1105 | 0 | 0 | 0 | [14 empty] | 231276 | 0
OK2024 | Bodyworx | AE | STROUD | 9201 S. Sooner Rd., Suite E, OKC 73135 | Complete |  |  |  | 2020-09-24 |  | 2020-12-01 |  | 68 | Yes | 2021-02-14 | 2021-08-04 |  | 5.6811 | Complete |  | 984546 | 230830 | 155142 | 20934 | 247073 | 88548 | 113241 | 61708 | 67070 | 0 | 0 | 0 | 0 | [14 empty] | 984546 | 0
OK2025 | Autism in Motion - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction |  |  |  | 2021-01-05 |  | 2021-04-16 |  | 101 | Yes | 2021-08-07 | 2021-12-28 |  | 4.7508 |  |  | 1051400 | 0 | 0 | 0 | 0 | 0 | 0 | 111250 | 14446 | 326666 | 140279.29 | 169323.9 | 144372.98 | 90000 | 49434.81 | [12 empty] | 1045772.98 | -5627.02
OK2031 | T-Mobile - Guthrie | AE | WILLIAMS | 1904 S Division Street, Guthrie, OK 73044 | Complete |  |  |  | 2021-01-29 |  | 2021-03-05 |  | 35 | Yes | 2021-03-01 | 2021-07-16 |  | 4.5515 | Complete |  | 723062 | 0 | 0 | 0 | 79004 | 201430 | 171285 | 187324 | 84019 | 0 | 0 | 0 | 0 | [14 empty] | 723062 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction |  |  |  | 2021-06-15 |  | 2021-08-10 |  | 56 | Yes | 2021-07-05 | 2021-12-28 |  | 5.8472 |  |  | 1367414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99756 | 330951.22 | 217391.16 | 176608.81 | 250000 | 219315.62 | [12 empty] | 1294022.81 | -73391.19
OK2033-2 | Old School Bagel - Santa Fe Dev. | AE | WILLIAMS | 112 SW 134th Street, Oklahoma City, OK | Construction | Yes | Yes |  | 2021-06-20 |  | 2021-12-03 |  | 166 | Yes | 2021-11-17 | 2022-01-28 |  | 2.392 |  |  | 266165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36165 | 180000 | [12 empty] | 216165 | -50000
OK2039 | Rockwell Daycare | AE | STROUD | 1213 N. Rockwell Ave., Oklahoma City, OK 73127 | Complete |  |  |  | 2020-12-01 |  | 2020-12-21 |  | 20 | Yes | 2021-02-01 | 2021-03-31 |  | 1.9269 | Complete |  | 81500 | 0 | 0 | 0 | 81500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [12 empty] | 81500 | 0
OK2110-1 | Shawnee Shell - Shawnee, OK | AE | STROUD | 4797 N. Harrison, Shawnee, OK 74804 | Construction | Yes | Yes |  | 2021-07-14 |  | 2021-09-17 |  | 65 | Yes | 2021-11-01 | 2022-06-29 19:12 |  | 8 |  |  | 1180416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192936.95 | 0 | 150000 | 150000 | 150000 | 150000 | 100000 | 100000 | 37479.05 | [7 empty] | 1030416 | -150000
OK2110-2 | Shawnee Shell - Old School Bagel | AE | STROUD | 4799 N. Harrison, Shawnee, OK 74804 | Construction | Yes | Yes |  | 2021-11-08 |  | 2021-12-09 |  | 31 | yes | 2021-12-14 | 2022-06-12 14:24 |  | 6 |  |  | 250338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12582.01 | 0 | 25000 | 25000 | 25000 | 50000 | 50000 | 25000 | 12755.99 | [7 empty] | 225338 | -25000
OK2110-3 | Shawnee Shell - OSO | AE | STROUD | 4795 N. Harrison, Shawnee, OK 74804 | Preconstruction | No | Yes |  | 2021-12-06 |  | 2022-01-14 |  | 39 | No | 2022-01-14 | 2022-07-13 14:24 |  | 6 |  |  | 402660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34445.59 | 0 | 25000 | 25000 | 75000 | 75000 | 75000 | 50000 | 18214.41 | [7 empty] | 377660 | -25000
[21 empty] | 11283997 | 2047245 | 702828 | 153598 | 849658 | 538775 | 755703 | 739337 | 204636 | 810992 | 498956.42 | 626679.61 | 478189.43 | 802578.09 | 648750.43 | 250000 | 275000 | 225000 | 175000 | 68449.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10851375.43 | -432621.57
Wes Gaddy |  | WG
OK2011-1 | Mustang Shell | WG | WILLIAMS | 1708 S Mustang Rd., Mustang, OK 73064 | Complete |  |  |  | 2021-05-01 |  | 2021-07-01 |  | 61 | Yes | 2020-09-01 | 2021-03-31 |  | 7.01 | Complete |  | 940687 | 720455 | 114649 | 0 | 105583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste D | Complete |  |  |  | 2021-05-01 |  | 2021-07-01 |  | 61 | Yes | 2020-11-01 | 2021-03-31 |  | 4.9834 | Complete |  | 226188 | 64622 | 39562 | 18328 | 101052 | 2624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 226188 | 0
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste A | Complete |  |  |  | 2021-05-01 |  | 2021-07-01 |  | 61 | Yes | 2020-11-01 | 2021-03-31 |  | 4.9834 | Complete |  | 315962 | 124791 | 64927 | 25844 | 98461 | 1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 315962 | 0
[21 empty] | 1482837 | 909868 | 219138 | 44172 | 305096 | 4563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482837 | 0
Christopher Goldsmith |  | CG
OK1902-1 | Empire Financial | CG | CLINTON | 12100 South Yukon Ave. Suite C, Glenpool, OK 74033 | Complete |  |  |  | N/A |  | N/A |  | N/A | N/A | 2021-05-14 | 2021-07-14 |  | 2.0266 |  |  | 46806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46806 | 0 | 0 | 0 | [14 empty] | 46806 | 0
OK1923-3 | Tropical Smoothie - Riverwest | CG | CLINTON | 152 W Alexander Blvd., Sand Springs, OK 74063 | Construction |  |  |  | 2021-06-01 |  | 2021-06-15 |  | 14 | Yes | 2021-05-28 | 2021-10-28 |  | 5.0831 |  |  | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58100 | 0 | 0 | 0 |  | 31025 | [12 empty] | 89125 | 0
OK1923-4 | Stanton Optical - Riverwest | CG | CLINTON | 153 W Alexander Blvd., Sand Springs, OK 74063 | Complete |  |  |  | 2021-06-01 |  | 2021-06-15 |  | 14 | Yes | 2021-06-06 | 2021-09-03 |  | 2.9568 |  |  | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75650 | 0 | 0 | 0 | [14 empty] | 75650 | 0
OK1936 | Dr Fischer | CG | CLINTON | 720 West 71St Street S, Tulsa, OK 74132 | Construction |  |  |  | 2020-04-08 |  | 2020-06-22 |  | 75 | Yes | 2020-06-22 | 2021-09-30 |  | 15.4485 |  |  | 2482030 | 1788494 | 93223 | -90886 | 247214 | 203016 | 0 | 88152 | 152817 | 0 | 0 | 0 | 0 | [14 empty] | 2482030 | 0
OK2008 | Dr. Gaches | CG | CLINTON | 11492 N. 137th E. Ave., Owasso, OK | Construction |  |  |  | 2020-08-28 |  | 2021-03-05 |  | 189 | Yes | 2021-04-04 | 2021-10-15 |  | 6.4452 |  |  | 683158 | 65749 | 0 | 0 | 72518 | 31182 | 36101 | 79510 | 164718 | 104045 | 68162.76 | 61172.24 | 0 | [14 empty] | 683158 | 0
OK2014 | Clark Plaza Shell | CG | CLINTON | 7877 E 71st South., Tulsa, OK 74133 | Construction |  |  |  | 2020-10-16 |  | 2021-02-19 |  | 126 | Yes | 2021-03-01 | 2021-12-27 |  | 10 |  |  | 1436404 | 91138 | 0 | 0 | 0 | 55754 | 185059 | 486176 | 117904 | 116211 | 178250.15 | 0 | 161504.44 | 100001.85 | [13 empty] | 1491998.44 | 55594.44
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | CLINTON | 7877 E 71st South Ste A, Tulsa, OK 74133 | Construction |  |  |  | 2020-12-03 |  | 2021-03-25 |  | 112 | Yes | 2021-03-29 | 2021-11-24 19:12 |  | 8 |  |  | 648253 | 124344 | 0 | 0 | 0 | 0 | 0 | 82390 | 0 | 125825 | 199275.86 | 49841.62 | 43397.49 | [14 empty] | 625073.97 | -23179.03
OK2014-2 | Clark Shell - Enhance DDS | CG | CLINTON | 7877 E 71st South Ste B., Tulsa, OK 74133 | Construction |  |  |  | 2020-12-03 |  | 2021-03-25 |  | 112 | Yes | 2021-03-29 | 2021-11-24 |  | 7.9734 |  |  | 400187 | 14681 | 0 | 0 | 0 | 0 | 0 | 50940 | 0 | 231205 | 53980.66 | 26603.7 | 22776.28 | [14 empty] | 400186.64 | -0.36
OK2032-1 | Cross Roads - Shell | CG | CLINTON | 1167 N. 38th Street, Broken Arrow, OK 74014 | Construction |  |  |  | N/A |  | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | CLINTON | 1171 N. 38th Street, Broken Arrow, OK 74014 | Construction | Yes | Yes |  | 2021-08-09 |  | 2021-08-10 |  | 1 | Yes | 2021-10-01 | 2022-02-04 |  | 4.186 |  |  | 355011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230079.99 | 85000 | 85000 | 85000 | 15011 | [10 empty] | 500090.99 | 145079.99
[21 empty] | 6216624 | 2084406 | 93223 | -90886 | 319732 | 289952 | 221160 | 787168 | 435439 | 757842 | 499669.43 | 137617.56 | 457758.2 | 185001.85 | 116025 | 85000 | 15011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6394119.04 | 177495.04
Cassidy Hedrick |  | CH
OK2028P | Precon - Memorial Park | CH | CH |  | Complete |  |  |  | N/A |  | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 461956 | 0
OK2104 | Wimberley Walker Remodel | CH | CH | 101 Twilight Trail, Wimberly, TX 78676 | Construction |  |  |  | N/A |  | N/A |  | N/A | Yes | 2020-12-30 | 2021-09-30 |  | 9.103 |  |  | 500577 | 0 | 0 | 17615 | 71648 | 0 | 97695 | 103125 | 92500 | 117994 | 0 | 0 | 0 | [14 empty] | 500577 | 0
[21 empty] | 962533 | 0 | 353138 | 126433 | 71648 | 0 | 97695 | 103125 | 92500 | 117994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 962533 | 0
Kimberly Kelly |  | KK | [46 empty] | 0
OK2038 | Dr. Farmer TI - Wonga Corner | KK | WILLIAMS | 1152 W. Douglas Midwest City, OK | Complete |  |  |  | 2021-02-26 |  | 2021-03-17 |  | 19 | Yes | 2021-03-17 | 2021-08-27 |  | 5.4153 |  |  | 383545 | 0 | 0 | 0 | 0 | 118932 | 110310 | 66219 | 58693 | 29391 | 0 | 0 | 0 | [14 empty] | 383545 | 0
TX1903 | Ramon Franklin Warehouse | KK | MILLER | 1308 Corporate Drive East, Arlinton, TX 76006 | Construction |  |  |  | 2020-12-09 |  | 2021-01-27 |  | 49 | Yes | 2021-07-05 | 2021-12-10 |  | 5.2492 |  |  | 1006579 | 131243 | 0 | 0 | 0 |  | 83010 | 67371 | 0 | 103268 | 113601.11 | 227523.97 | 173989.42 | 108874.92 | [13 empty] | 1008881.42 | 2302.42
TX2101 | Bob Mills - Forth Worth | KK | JOHNSON | 3600 East Long Ave., Ft Worth, TX 76111 | Construction |  |  |  | 2021-04-09 |  | 2021-06-10 |  | 62 | Yes | 2021-07-10 | 2021-12-10 |  | 5.0831 |  |  | 2259828 | 0 | 0 | 0 | 0 | 0 | 105517 | 201248 | 0 | 748228 | 181824.92 | 308182.91 | 347750.61 | 414827.17 | [13 empty] | 2307578.61 | 47750.61
[21 empty] | 3649952 | 131243 | 0 | 0 | 0 | 118932 | 298837 | 334838 | 58693 | 880887 | 295426.03 | 535706.88 | 521740.03 | 523702.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700005.03 | 50053.03
Tiffany Shiel |  | TS | [46 empty] | 0
OK2106-1 | Fox Lake Shell | TS | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Construction |  | No |  | 2021-06-22 |  | 2021-09-22 |  | 92 | Yes | 2021-07-22 | 2022-08-30 |  | 13.4219 |  |  | 12114221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 941343 | 403549.63 | 37623.36 | 1053416.41 | 772000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 437705.01 |  |  |  | 12645637.41 | 531416.41
[21 empty] | 12114221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 941343 | 403549.63 | 37623.36 | 1053416.41 | 772000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 437705.01 | 0 | 0 | 0 | 12645637.41 | 531416.41
Jason Nowell |  | JN | [46 empty] | 0
OK1912 | Dr. Shirley | JN |  | 2441 SW 134th, Oklahoma City, OK 73170 | Complete | [7 empty] | 0 | Yes | 2020-01-06 | 2020-09-16 |  | 8.4385 | Complete |  | 1217703 | 1206322 | 11381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1217703 | 0
OK1931 | Dr. Crowley | JN |  | 15101 Crown at Lone Oak Rd, OKC 73013 | Complete | [7 empty] | 0 | Yes | 2020-02-28 | 2020-12-22 |  | 9.9003 | Complete |  | 578876 | 568341 | 2335 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578876 | 0
[21 empty] | 1796579 | 1774663 | 13716 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1796579 | 0
Bob Solomon |  | BS | [46 empty] | 0
OK1926 | Hunter Pharmacy | BS | SMITH | 10120 Broadway Ext., OKC 73114 | Complete |  |  |  | 2020-05-14 |  | 2020-07-08 |  | 55 | Yes | 2020-07-21 | 2021-06-24 |  | 11.2292 |  |  | 9534114 | 4251267 | 974630 | 965506 | 726926 | 1007479 | 748387 | 599421 | 93601 | 88474 | 65327.47 | 13095.53 | -1831.09 | [14 empty] | 9532282.91 | -1831.09
OK2006 | El Reno Enhanced Dental | BS | STROUD | 1601 Investors Ave., El Reno, OK 73036 | Complete |  |  |  | 2020-06-16 |  | 2020-06-23 |  | 7 | Yes | 2020-10-20 | 2021-07-15 |  | 8.9037 |  |  | 1258636 | 501155 | 186495 | 202246 | 66602 | 48430 | 7649 | 118643 | 54525 | 32612 | 0 | 0 | 632.5 |  | 40279 | [12 empty] | 1259268.5 | 632.5
OK2034 | Dr. Rex Johnson, DVM - Covell I35 | BS | STROUD | 5401 E. Covel Rd., Edmond, OK 73034 | Construction |  |  |  | 2021-05-12 |  | 2021-08-10 |  | 90 | Yes | 2021-06-25 | 2022-06-21 |  | 11.9934 |  |  | 2124651 | 0 | 0 |  |  | 233134 | 0 | 0 | 72994 | 144486 | 174326.34 | 157369.33 | 0 | 175000 | 200000 | 200000 | 200000 | 200000 | 150000 | 52341.33 | [7 empty] | 1959651 | -165000
OK2112 | Covell 35 Dev. - Dr. Lu Dentistry | BS | STROUD | 5249 E. Covel Rd., Edmond, OK 73034 | Construction | Yes | Yes |  | 2021-10-20 |  | 2021-12-10 |  | 51 | Yes | 2021-12-24 | 2022-09-20 21:36 | 2022-06-01 | 9 |  |  | 1325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 150000 | 200000 | 200000 | 225000 | 250000 | 200000 | [7 empty] | 1325000 | 0
OK2113 | Carlton Landing Sewer - Eufaula, OK | BS | TBD |  | Construction |  |  |  | N/A |  | N/A |  | N/A | No |  |  |  | 0 |  |  | 82107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 55000 | [12 empty] | 55000 | -27107
TX1901 | Dr. Dyer - Sequoia Spur | BS | STEPHENSON | 115 Shell Rd, Georgtown, TX 78633 | Construction |  |  |  | 2020-05-11 |  | 2020-07-06 |  | 56 | Yes | 2020-11-01 | 2021-12-01 |  | 13.1229 |  |  | 1809504 | 407476 | 214131 | 74131 | 135778 | 437832 | 31174 | 82243 | 45087 | 149925 | 55587.04 | 113628.69 | 49278.8 | 30784.27 | [13 empty] | 1827055.8 | 17551.8
TX2001 | Dr. Lippian - Texarkana | BS | HARRIS | 5220 Gibson Ln., Texarkana, TX 75501 | Construction |  |  |  | 2020-09-30 |  | 2020-12-29 |  | 90 | Yes | 2021-01-28 | 2021-11-01 |  | 9.2027 |  |  | 1641198 | 103605 | 0 | 71204 | 158532 | 124183 | 320119 | 192377 | 74223 | 357461 | 34466.45 | 131256.06 | 72535.74 | [14 empty] | 1639962.25 | -1235.75
[21 empty] | 17775210 | 5263503 | 1375256 | 1313087 | 1087838 | 1851058 | 1107329 | 992684 | 340430 | 772958 | 329707.3 | 415349.61 | 120615.95 | 305784.27 | 445279 | 400000 | 400000 | 425000 | 400000 | 252341.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17598220.46 | -176989.54
Kyle Tedlock |  | KT | [46 empty] | 0
OK2016 | OneCore | KT | HALL | 100 NE 85th Street, OKC, OK 73114 | Construction |  |  |  | 2020-08-11 |  | 2020-11-12 |  | 93 | Yes | 2020-10-15 | 2021-12-01 |  | 13.6877 |  |  | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 1384616.45 | 896696.76 | 358271.54 | 171185.79 | [13 empty] | 13166182.54 | 58271.54
[21 empty] | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 1384616.45 | 896696.76 | 358271.54 | 171185.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13166182.54 | 58271.54
Kevin Trosper |  | KT | [46 empty] | 0
OK1822-3 | R&D Construction | KT | TROSPER | 901 E. Main Suite 125, Yukon, OK 73099 | Complete |  |  |  | N/A |  | N/A |  | N/A | N/A | 2021-07-05 | 2021-08-20 |  | 1.5282 |  |  | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28797 | 8473.4 | 0 | 0 |  | 51854.6 | [12 empty] | 89125 | 0
OK1822-4 | Blondette | KT | TROSPER | 902 E. Main Suite 115, Yukon, OK 73099 | Complete |  |  |  | N/A |  | N/A |  | N/A | N/A | 2021-07-05 | 2021-08-20 |  | 1.5282 |  |  | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24902 | 5295.49 | 0 | 0 |  | 45452.51 | [12 empty] | 75650 | 0
OK1909-3 | Allstate Insurance (Brandon) | KT | TROSPER | 1140 NW 192nd Street Suite B, Oklahoma City, OK | Complete |  |  |  | 2021-04-13 |  | 2021-04-27 |  | 14 | Yes | 2021-05-17 | 2021-06-09 |  | 0.76412 |  |  | 67027 | 0 | 0 | 0 | 0 | 0 | 0 | 67027 | 0 | 0 | 0 | 0 | 3185.48 | [14 empty] | 70212.48 | 3185.48
OK1917-4 | Colonial Point - Nutrition Club | KT | TROSPER | 11999 NW Expressway Yukon, OK 73099 | Construction |  |  |  | 2021-06-22 |  | 2021-07-12 |  | 20 | Yes | 2021-07-05 | 2021-10-01 |  | 2.9236 |  |  | 38040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38040 | 0 | 0 | 0 | [14 empty] | 38040 | 0
OK1922-3 | Coltrane Corner - Regent Bank (Mike) | KT | TROSPER | 2823 E. 2nd, Suite C, Edmond, OK | Complete |  |  |  | 2021-05-14 |  | 2021-06-15 |  | 32 | Yes | 2021-06-21 | 2021-08-17 |  | 1.8937 |  |  | 74344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74344 | 0 | 0 | 0 | [14 empty] | 74344 | 0
OK1922-4 | Coltrane Corner - Klassy K9 (Mike) | KT | TROSPER | 2824 E. 2nd, Edmond, OK | Complete |  |  |  | N/A |  | N/A |  | N/A | N/A | 2021-06-11 | 2021-07-02 |  | 0.69767 |  |  | 6336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336 | 0 | 0 | 0 | [14 empty] | 6336 | 0
OK2101 | Christian Counseling | KT | TROSPER | 12901 E. Britton Rd. Suite B, Jones, 73049 | Complete |  |  |  | N/A |  | N/A |  | N/A | Yes | 2021-03-01 | 2021-05-31 |  | 3.0233 |  |  | 52095 | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | 0 | 0 | 0 | 0 | 10962.16 |  | 0 | [12 empty] | 63057.16 | 10962.16
OK2105-1 | Valencia - Breakroom 405 (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. A, Edmond, OK 73012 | Complete |  |  |  | 2021-03-22 |  | 2021-04-16 |  | 25 | Yes | 2021-05-24 | 2021-08-11 |  | 2.6246 |  |  | 156692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156692 | 0 | 0 | 0 | 5333.82 |  | 0 | [12 empty] | 162025.82 | 5333.82
OK2105-2 | Valencia - Christfit Gym (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Complete |  |  |  | 2021-03-22 |  | 2021-04-07 |  | 16 | Yes | 2021-05-24 | 2021-08-09 |  | 2.5581 |  |  | 94557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94557 | 0 | 0 | 13646.35 | 0 |  | -13646.35 | [12 empty] | 94557 | 0
OK2105-3 | Valencia - Winfield and Co. | KT | TROSPER | 2216 NW 178th Street Ste. E, Edmond, OK 73012 | Construction |  |  |  | 2021-09-01 |  | 2021-09-16 |  | 15 |  | 2021-09-22 | 2021-10-17 |  | 0.83056 |  |  | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15493 | [12 empty] | 15493 | 0
OK2105-4 | Valencia - Prevail Fitness | KT | TROSPER | 2215 NW 178th Street Ste. B, Edmond, OK 73012 | Complete |  |  |  | 2021-05-07 |  | 2021-06-11 |  | 35 | Yes | 2021-07-06 | 2021-09-17 |  | 2.4252 |  |  | 101240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36103 | 58225 | 0 | 0 | 0 |  | 6912 | [12 empty] | 101240 | 0
OK2105-5 | Valencia - Magnus Batting Cage (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. D, Edmond, OK 73012 | Complete |  |  |  | 2021-06-04 |  | 2021-06-21 |  | 17 | Yes | 2021-06-28 | 2021-08-30 |  | 2.093 |  |  | 36900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36900 | 0 | 0 | 0 | 0 |  | 0 | [12 empty] | 36900 | 0
OK2105-6 | Valencia - Breakroom 405 Warehouse | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Complete |  |  |  | 2021-09-21 |  | 2021-10-15 |  | 24 | Yes | 2021-09-29 | 2021-10-08 |  | 0.299 |  |  | 12885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20166.67 |  | 12885 | [12 empty] | 33051.67 | 20166.67
TX2006-1 | Sunnyvale Shell | KT | DOYLE | 480 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | Yes |  | 2021-06-22 |  | 2021-11-09 |  | 140 | Yes | 2021-11-17 | 2022-06-01 |  | 6.5116 |  |  | 1910050 | 0 | 0 | 0 | 0 | 0 | 0 | 119451 | 0 | 139349 | 0 | 270190.83 | 61829.84 | 175000 | 250000 | 300000 | 300000 | 181059.17 | [9 empty] | 1796879.84 | -113170.16
TX2006-2 | Sunnyvale Shell - Dr. Luna | KT | DOYLE | 481 US Hwy 80, Sunnyvale, TX 75182 | Preconstruction | No | Yes | 2021-12-21 | 2021-12-13 |  | 2022-01-27 |  | 45 | No | 2022-03-07 | 2022-06-03 |  | 2.9236 |  |  | 288979 | 0 | 0 | 0 | 0 | 0 | 0 | 7826 | 0 | 9711 | 0 | 0 | 0 | 20000 | 60000 | 60000 | 60000 | 37442 | [9 empty] | 254979 | -34000
TX2006-3 | Sunnyvale Shell - Dr. Rohani | KT | DOYLE | 482 US Hwy 80, Sunnyvale, TX 75182 | Preconstruction | No | Yes | 2021-12-21 | 2021-12-21 |  | 2022-02-04 |  | 45 | No | 2022-03-07 | 2022-06-03 |  | 2.9236 |  |  | 366822 | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 0 | 12408 | 0 | 0 | 0 | 26000 | 65000 | 75000 | 75000 | 61698 | [9 empty] | 322822 | -44000
[21 empty] | 3386235 | 0 | 0 | 0 | 0 | 0 | 0 | 254115 | 324252 | 392112 | 13768.89 | 283837.18 | 101477.97 | 221000 | 493950.76 | 435000 | 435000 | 280199.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3234712.97 | -151522.03
Phillip Wilson |  | PW | [46 empty] | 0
TN2101 | AIM - Memphis, TN | PW | WILSON | 7007 Stage Rd., Memphis, TN 38133 | Construction | Yes | Yes |  | 2021-06-18 |  | 2021-10-20 |  | 124 | Yes | 2021-11-04 | 2021-03-31 |  | -7.2425 |  |  | 2015533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141412 | 0 | 0 | 146485.8 | 300000 | 300000 | 300000 | 300000 | 300000 | 74121 | [8 empty] | 1862018.8 | -153514.2
[21 empty] | 2015533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141412 | 0 | 0 | 146485.8 | 300000 | 300000 | 300000 | 300000 | 300000 | 74121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1862018.8 | -153514.2
Preconstruction | [48 empty] | 0
OK2033-3 | Chamberlain Realty - Santa Fe Dev. | AE | WILLIAMS | 113 SW 134th Street, Oklahoma City, OK | Preconstruction | No | 2021-11-12 |  | 2021-11-12 |  | 2022-01-06 |  | 55 | No | 2022-01-17 | 2022-10-14 21:36 |  | 9 |  |  | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 |  |  |  |  | 1900000 | 0
OK2037 | Master Hand Milling | TBD | TBD | TBD, Edmond, OK | Preconstruction |  | No |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2023-03-15 04:48 |  | 12 |  |  | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 200000 | 250000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 830000 | 4000000 | 0
OK2102 | Puppy Paws East Edmond | TBD | TBD | East Edmond | Preconstruction |  | Yes |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2022-12-14 21:36 |  | 9 |  |  | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 150000 | 200000 | 260000 | 260000 | 300000 | 300000 | 260000 | 260000 | 210000 |  |  | 2200000 | 0
OK2106-2 | Fox Lake - Sidecar | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | No |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2022-12-14 21:36 |  | 9 |  |  | 980000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50000 | 100000 | 125000 | 150000 | 200000 | 200000 | 155000 |  |  |  |  | 980000 | 0
OK2106-3 | Fox Lake - Hatch | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | No |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2022-12-14 21:36 |  | 9 |  |  | 1558000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50000 | 125000 | 225000 | 300000 | 300000 | 300000 | 258000 |  |  |  |  | 1558000 | 0
OK2106-4 | Fox Lake - Enhanced Dental | TS | JE | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | No |  | 2021-11-19 |  | 2022-01-03 |  | 45 | No | 2022-02-02 | 2022-08-01 14:24 |  | 6 |  |  | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 25000 | 75000 | 90000 | 100000 | 100000 | 100000 | 50000 |  |  |  |  | 540000 | 0
OK2106-5 | Fox Lake - Open Space | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | No |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2022-09-15 14:24 |  | 6 |  |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 75000 | 125000 | 125000 | 150000 | 150000 | 125000 | 50000 |  |  |  |  | 800000 | 0
OK2106-6 | Fox Lake Provision Concepts | CM | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction |  | No |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2022-09-15 14:24 |  | 6 |  |  | 690000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50000 | 100000 | 120000 | 120000 | 120000 | 120000 | 60000 |  |  |  |  | 690000 | 0
OK2107 | Jack Be Grocery | TBD | TBD |  | Preconstruction |  | 2021-12-24 |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2023-03-15 04:48 |  | 12 |  |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 75000 | 125000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 700000 | 2500000 | 0
OK2108 | Puppy Paws - Lone Oak | KT | STROUD | 15200 Crown at Lone Oak, Edmond OK 73013 | Preconstruction | No | 2021-12-21 |  | 2021-11-19 |  | 2022-01-06 |  | 48 | No | 2022-01-20 | 2022-11-17 |  | 10 |  |  | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 150000 |  |  |  | 2050000 | -150000
OK2114-1 | Chamberlain Realty - Lone Oak | TBD | TBD | 15103 Crown at Lone Oak Rd., Edmond, OK 73013 | Preconstruction |  |  |  | 2022-01-28 |  | 2022-03-14 |  | 45 | No | 2022-04-13 | 2022-10-10 14:24 |  | 6 |  |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 60000 | 60000 | 60000 | 45000 | [7 empty] | 375000 | -25000
OK2120 | Peak View Brewery and Distillery | TBD | TBD | Reservoir by Costco | Preconstruction |  |  |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2023-01-14 |  | 10 |  |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 125000 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 225000 | 3000000 | 0
OK2121 | 15th & Bryant Development | TBD | TBD |  | Preconstruction |  |  |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2022-09-15 14:24 |  | 6 |  |  | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75000 | 125000 | 125000 | 125000 | 125000 | 105000 | [7 empty] | 680000 | 0
OK2122 | The Learning Experence (15th & Bryant Development) | TBD | TBD |  | Preconstruction |  | 2021-12-15 |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2022-08-31 | 2022-08-01 | 5.4817 |  |  | 2180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 150000 | 175000 | 250000 | 250000 | 250000 | 300000 | 300000 | 300000 | 205000 |  |  |  |  | 2180000 | 0
OK2123 | TBD (15th & Bryant Development) | TBD | TBD |  | Preconstruction |  |  |  | 2022-01-03 |  | 2022-02-17 |  | 45 | No | 2022-03-19 | 2022-12-14 21:36 |  | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0
OK2125-1 | Enid Shell | TBD | TBD |  | Preconstruction |  | 2022-01-13 |  | 2021-12-13 |  | 2022-01-12 |  | 30 | No | 2022-02-11 | 2022-11-08 21:36 |  | 9 |  |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50000 | 100000 | 150000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 150000 |  | 1500000 | 0
OK2125-2 | OSB - Enid | TBD | TBD |  | Preconstruction |  | No |  | 2022-01-07 |  | 2022-02-21 |  | 45 | No | 2022-03-23 | 2022-07-21 09:36 |  | 4 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 100000 | 150000 | 50000 | [9 empty] | 350000 | 0
OK2125-3 | Enhanced Dental - Enid | TBD | TBD |  | Preconstruction |  | No |  | 2022-01-22 |  | 2022-03-08 |  | 45 | No | 2022-04-07 | 2022-10-04 14:24 |  | 6 |  |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 50000 | 75000 | 75000 | 75000 | 75000 | 75000 | 25000 |  |  |  | 450000 | 0
OK2126-1 | Weatherford Shell | KT | STEPHENSON |  | Preconstruction | No | 2021-12-30 | 2021-12-13 | 2021-12-13 |  | 2022-01-13 |  | 31 | No | 2021-01-24 | 2021-10-21 21:36 |  | 9 |  |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 50000 | 75000 | 150000 | 150000 | 200000 | 200000 | 200000 | 125000 |  |  |  |  | 1200000 | 0
OK2126-3 | Weatherford Shell - Enhanced Dental | TBD | TBD |  | Preconstruction |  | No |  | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-07-13 09:36 |  | 4 |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50000 | 75000 | 100000 | 100000 | 25000 | [6 empty] | 350000 | 0
OK2127 | Legacy Martial Arts Shell | TBD | TBD |  | Preconstruction |  |  |  | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-09-11 14:24 |  | 6 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50000 | 75000 | 130000 | 130000 | 130000 | 130000 | 105000 |  |  |  |  | 750000 | 0
OK2128 | OSB 150th and Penn | TBD | FOX | 15201 N. Penn Crossing Court, Oklahoma City, OK 73013 | Preconstruction |  |  |  | 2021-12-01 |  | 2022-01-15 |  | 45 | No | 2022-02-14 | 2022-08-13 14:24 |  | 6 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 75000 | 100000 | 125000 | 125000 | 125000 | 140000 | 60000 | [5 empty] | 750000 | 0
OK2132-1 | Seminole Shell | TBD | STRUB |  | Preconstruction |  | No |  | 2021-12-15 |  | 2022-01-29 |  |  | No | 2022-02-03 | 2022-10-31 21:36 |  | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
OK2132-2 | T-Mobile - Seminole | TBD | STRUB |  | Preconstruction |  | No |  | 2021-12-15 |  | 2022-01-29 |  | 45 | No | 2022-02-28 | 2022-08-27 14:24 |  | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
OK2132-3 | Urgent Care - Seminole | TBD | TBD |  | Preconstruction |  | No |  | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-09-11 14:24 |  | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
OK2132-4 | TBD TI #3 - Seminole | TBD | TBD |  | Preconstruction |  | No |  | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-07-13 09:36 |  | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
OK21xx | Norman Shell | TBD | TBD |  | Preconstruction |  | 2022-02-13 |  | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-12-10 21:36 |  | 9 |  |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 1200000 | 1200000 | 0
OK21xx | OSB - Norman Shell | TBD | TBD |  | Preconstruction |  | No |  | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-12-10 21:36 |  | 9 |  |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 300000 | 300000 | 0
OK21xx | TI - Norman Shell | TBD | TBD |  | Preconstruction |  | No |  | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-12-10 21:36 |  | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
OK21xx | Glenn Pool Shell | TBD | TBD | [5 empty] | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-12-10 21:36 |  | 9 |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 2000000 | 2000000 | 0
OK21xx | TI - Glenn Pool Shell | TBD | TBD | [5 empty] | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-12-10 21:36 |  | 9 |  |  | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 650000 | 650000 | 0
OK21xx | OSB Express - Glenn Pool, OK | TBD | TBD | [5 empty] | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-03-15 | 2022-12-10 21:36 |  | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
Okxxxx | Regent Center (Fox Lake Similar) | TBD | TBD | Broken Arrow | Preconstruction |  |  |  | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-09-01 | 2023-08-28 04:48 |  | 12 |  |  | 14000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1250000 | 1250000 | 1250000 | 1250000 | 9000000 | 14000000 | 0
Okxxxx | Anytime Fitness - Brandon Porter | TBD | TBD |  | Preconstruction |  |  |  | 2021-02-01 |  | 2021-03-18 |  | 45 | No | 2021-04-17 | 2021-08-15 09:36 |  | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
TNxxxx | AIM Bellevue - Site Visit Needed | PW | TBD | 7734 Hwy 70 S. Nashville, TN 37221 | Preconstruction |  |  |  | 2021-12-30 |  | 2022-02-13 |  | 45 | No | 2022-06-01 | 2023-03-29 |  | 10 |  |  | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 2400000 | 0
TX2005 | McKinney Development | TBD | DOYLE | Virginia and Ridge Road, McKinney, TX | Preconstruction |  | N/A |  | 2021-10-01 |  | 2022-01-14 |  | 105 | No | 2022-04-15 | 2023-01-10 21:36 |  | 9 |  |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 120000 |  |  |  | 600000 | 0
TX2007-1 | Carrollton Shell | TROSPER | DOYLE | Carrollton, TX | Preconstruction | No | Yes |  | 2021-10-28 |  | 2021-12-17 |  | 50 | No | 2022-01-21 | 2022-10-18 21:36 |  | 9 |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 175000 | 250000 | 250000 | 25000 | 250000 | 300000 | 300000 | 150000 | [5 empty] | 1800000 | -200000
TX2007-2 | Carrolton Shell - Dr. Bui | TROSPER | DOYLE | Carrollton, TX | Preconstruction | No | 2021-10-02 | 2021-11-26 | 2021-11-26 |  | 2022-02-24 |  | 90 | No | 2022-03-26 | 2022-07-24 09:36 |  | 4 |  |  | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 |  |  | 50000 | 100000 | 100000 | 100000 | 100000 | [6 empty] | 500000 | -50000
TX2008 | Dr. Barbara Lee (McKinney Development) | TROSPER | DOYLE | McKinney, TX | Preconstruction |  | Ready to Close |  | 2021-10-22 |  | 2022-01-14 |  | 84 | No | 2022-04-15 | 2023-01-10 21:36 |  | 9 |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 65000 | 145000 |  |  | 750000 | 0
TX2102-1 | San Antonio Shell | TBD | TBD | San Antonio, TX | Preconstruction |  |  |  | 2021-11-30 |  | 2022-02-28 |  | 90 | No | 2022-03-30 | 2022-12-25 21:36 |  | 9 |  |  | 2229000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 125000 | 175000 | 225000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 204000 |  | 2229000 | 0
TX2102-2 | Dr. Abeskharon - San Antonio | TBD | TBD | San Antonio, TX | Preconstruction |  |  |  | 2021-11-30 |  | 2022-02-28 |  | 90 | No | 2022-05-29 | 2022-09-26 09:36 |  | 4 |  |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 50000 | 75000 | 125000 | 110000 |  | 360000 | 0
TX2103-1 | McKinney Shell (McKinney Development) | KT | DOYLE | McKinney, TX | Preconstruction |  | Closed |  | 2022-02-04 |  | 2022-05-05 |  | 90 | No | 2022-04-15 | 2022-10-12 14:24 |  | 6 |  |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 25000 | 50000 | 80000 | 80000 | 80000 | 80000 | 80000 | 125000 | 600000 | 0
TX2103-2 | TBD TI (McKinney Shell) | KT | DOYLE | McKinney, TX | Preconstruction |  |  |  | 2022-02-04 |  | 2022-05-05 |  | 90 | No | 2022-06-04 | 2023-03-01 21:36 |  | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
TX2103-3 | TBD TI (McKinney Shell) | KT | DOYLE | McKinney, TX | Preconstruction |  |  |  | 2022-02-04 |  | 2022-05-05 |  | 90 | No | 2022-06-04 | 2023-03-01 21:36 |  | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
|  | TBD | TBD | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
[21 empty] | 56617000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 900000 | 1225000 | 2535000 | 3280000 | 4095000 | 4670000 | 4575000 | 4225000 | 4808000 | 3540000 | 3325000 | 2884000 | 15680000 | 56192000 | -425000
0
[18 empty] | Billing Total |  |  | 130408632 | 13013591 | 3809122 | 2368676 | 3804063 | 3872041 | 3312584 | 4748195 | 3013953 | 6336751 | 3425694.15 | 2933510.96 | 3237955.33 | 2928674 | 3255254.76 | 3445000 | 4685011 | 5285199.17 | 5569121 | 5922341.33 | 5575000 | 5225000 | 5808000 | 3977705.01 | 3325000 | 2884000 | 15680000 | 127441442.71 | -2967189.29
[21 empty] | Billing Goal | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 | 3500000 | 3500000 | 5000000 | 6000000 | 6825000 | 7100000 | 7100000 | 7000000 | 6500000 | 6500000 | 6500000 | 6500000 | 80000000
[21 empty] | Difference | -1643454 | 1011004.8571 | -838148.6429 | -204329.6429 | -446956.6429 | -1756982.6429 | -827619.6429 | -2300751.6429 | 859911 | -1934264.85 | -3240053.04 | -2263766.67 | -937861 | -244745.24 | -55000 | -314989 | -714800.83 | -1255879 | -1177658.67 | -1525000 | -1775000 | -692000 | -2522294.99 | -3175000 | -3616000 | -64320000
[46 empty] | 2021 | 45000000
[21 empty] | Rev Actual |  | 2897650 | 3085444 | 3369732 | [20 empty] | 2022 | 60000000
[21 empty] | Rev Goal |  | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 | 2794050 | [10 empty] | 2023 | 72000000
[21 empty] | Difference |  | 663913.0849 | 525435.8876 | 169832.1532 | [20 empty] | 2024 | 86400000
[46 empty] | 2025 | 99360000
[21 empty] | GP Actual |  | 261214 | 325090 | 157521 | [20 empty] | 2026 | 114264000
[21 empty] | GP Goal |  | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 | 306950 | [10 empty] | 2027 | 131403600
[21 empty] | Difference |  | 15819.1266 | 43851.4788 | -194015.0348 | [20 empty] | 2028 | 151114140
[46 empty] | 2029 | 173781261
[21 empty] | GP % Actual |  | 9.01% | 10.54% | 4.67% | [20 empty] | 2030 | 199848450.15
[21 empty] | GP % Goal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | [10 empty] | 2031 | 229825717.6725
[21 empty] | Difference |  | -0.99% | 0.54% | -5.33% | [20 empty] | 2032 | 264299575.3234
[46 empty] | 2033 | 303944511.6219
[21 empty] | OH Actual |  | 256248 | 250107 | 305940
[21 empty] | OH Goal |  | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
[21 empty] | Difference |  | 18752 | 24893 | -30940
[21 empty] | NP Actual |  | 4126 | 74711 | -101036
[21 empty] | NP Goal |  | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 | 500000.0033
[21 empty] | Difference |  | -20413.4873 | 46587.1479 | -136189.6035
DEAD / HOLD / SOLD | [48 empty] | 0
FL2001 | Elysee Lot 6 | SOLD | SOLD | SOLD | SOLD |  |  |  | SOLD |  | SOLD |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD | 137906 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 3503 | 0 | 0 | 0 | [15 empty] | 137906 | 0
FL2002 | Elysee Lot 7 | SOLD | SOLD | SOLD | SOLD |  |  |  | SOLD |  | SOLD |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD | 136537 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 2134 | 0 | 0 | 0 | [15 empty] | 136537 | 0
OK1922-1 | Coltrane Corner - Aya Rowe | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK1924 | Yukon Development | HOLD | HOLD | HOLD | HOLD |  |  |  | HOLD |  | HOLD |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2018 | Dr. Mackey - 61st Street | DEAD | DEAD | 9050 E. 61st Street, Tulsa, OK 74145 | HOLD |  |  |  | HOLD |  | HOLD |  | HOLD | Yes | HOLD | HOLD |  | HOLD | HOLD | HOLD | 33274 | 0 | 0 | 0 | 0 | 0 | 33274 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 33274 | 0
OK2119 | OSB - Wonga Corner | DEAD | DEAD | 1156 S. Douglas, Midwest City, OK 73130 | HOLD |  |  |  | HOLD |  | HOLD |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2020-4 | Western - PT Central | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2026 | Covell I35 Edmond Dev. | DEAD | DEAD | 5400 E. Covell Road, Edmond, OK | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | Yes | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [15 empty] | 0 | 0
OK2028 | Precon - Memorial Park | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 461956 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15630 | 0 | 0 | 15630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 15630 | 0
OK2032-3 | Cross Roads - State Farm | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15000 | 0 | 0 | 5720 | 0 | 9280 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 15000 | 0
OK2032-5 | Cross Roads - Dispensary | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2036 | Dr. Matt Cole, DDS | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 41062 | 0 | 0 | 0 | 0 | 0 | 41062 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 41062 | 0
OK2103 | Bethesda - Santa Fe Dev. | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2105-3 | Valencia - Custom Pools | DEAD | DEAD | 2215 NW 178th Street Ste. E, Edmond, OK 73012 | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15493 | 0 | 0 | [15 empty] | 15493 | 0
OK2109-1 | Grand Blvd. Shell - OKC, OK | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2111 | Solara Surgery Center - Moore, OK | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2115 | Paul's Valley Development | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2117-1 | Paul's Valley Shell | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2117-2 | Paul's Valley Shell - Enhanced Dental | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2118 | Paul's Valley Shell - TBD | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2116 | Dollar Tree (Paul's Valley Development) | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2124 | Bodin Chiro (Lone Oak) | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2126-2 | Weatherford Shell - Dollar Tree | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | HOLD | HOLD | HOLD | HOLD |  |  |  | HOLD |  | HOLD |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
TX2004 | Marshall Ridge Dev. | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 37392 | 0 | 0 | 37392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 37392 | 0
TX2009 | Alliance Pediatrics-Marsh | DEAD | DEAD | DEAD | DEAD |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | 3575 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 3575 | 0
[21 empty] | 897825 | 122184 | 353138 | 171135 | 0 | 155902 | 74336 | 0 | 5637 | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897825 | 0
Formulas:
Actual Permit Received = [Actual Permit Submitted]+35
Comp Date = [Start Date]+(8*4.3*7)
Comp Date = [Start Date]+(9*7*4.3)
Start Date = [Actual Permit Received]+15
Note on T14: Bobby Snyder: Punchlist was conducted via facetime and all items have been completed. Final punch walk will occur in Sept with Rep from CA
Note on B36: Bobby Snyder: Existing Building
Note on V36: Existing Building
Note on J125: Trevor Hayes: Clock Started on 10/28
Note on B169: Bobby Snyder: Another GC built out this space.

## 12 2021
Zach | Peggy | Brandon | Phillip | Trevor |  | Trevor | Jenna | Ben | Trevor | Trevor | Trevor | Trevor | Trevor | Trevor | Trevor | Brandon | Brandon | Brandon | Brandon | Peggy | Peggy | Trevor | Trevor | 2020 | 2021 | [11 empty] | 2022 | [11 empty] | 2023
Job Number | Project | PM | SUP | Address | Status | Turn Over Complete | Entity | Loan/Lease Close | Anticipated Permit Submission | Actual Permit Submitted | Anticipated Permit Received | Actual Permit Received | Anticipated Permit Duration | Permit Approval Duration | Permit Received | Start Date | Comp Date | Planned Comp Date | Duration | Punchlist Complete Date | Lessons Learned | Appraisal Budget Approved | Appraisal Value | Annual 2020 | January | February | March | April | May | June | July | August | September | October | November | December | January 2022 | February 2022 | March 2022 | April 2022 | May 2022 | June 2022 | July 2022 | August 2022 | September 2022 | October 2022 | November 2022 | December 2022 | Annual 2023 | TOTAL | DELTA | COMMENTS
Adam England |  | AE
OK2003 | Enhance Dental - Choctaw | AE | WILLIAMS | 2651 Market Blvd., Choctaw, OK 73020 | Complete | Yes | Don't Own | N/A | 2020-02-06 | 2020-02-06 | 2020-05-01 | 2020-05-01 | 85 | 85 | Yes | 2020-06-01 | 2020-11-20 | 5.7143 | 5.7143 | Complete |  | Yes | 605990 | 568347 | 879 | 35573 | 656 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 605990 | 0
OK2005 | Quail Springs Shell | AE | FRARY | 14424 N May Ave., OKC 73134 | Complete | Yes | AG Quail Springs RE Holdings LLC | Yes | 2020-05-22 | 2020-05-22 | 2020-06-24 | 2020-06-24 | 33 | 33 | Yes | 2020-08-05 | 2021-02-10 | 6.2791 | 6.2791 | Complete |  | Yes | 845876 | 628337 | 137155 | 19492 | 60892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 845876 | 0
OK2005-1 | Quail Springs - Enhanced Dental | AE | FRARY | 14424 N May Ave., OKC 73134 Ste A | Complete | Yes | AG Quail Springs RE Holdings LLC | Yes | 2020-07-29 | 2020-07-29 | 2020-10-02 | 2020-10-02 | 65 | 65 | Yes | 2020-09-28 | 2021-02-14 | 4.6179 | 4.6179 | Complete |  | Yes | 303150 | 162612 | 95646 | 33342 | 5713 | 5837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 303150 | 0
OK2005-2 | Quail Springs - Just Kids Ped's | AE | FRARY | 14425 N May Ave., OKC 73134 Ste B | Complete | Yes | AG Quail Springs RE Holdings LLC | Yes | 2020-06-25 | 2020-06-25 | 2020-07-17 | 2020-07-17 | 22 | 22 | Yes | 2020-09-28 | 2021-02-10 | 4.485 | 4.485 | Complete |  | Yes | 222517 | 131745 | 62828 | 27944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 222517 | 0
OK2110-2 | Shawnee Shell - Old School Bagel | AE | STROUD | 4799 N. Harrison, Shawnee, OK 74804 | Construction | Yes | AG Harrison RE Holdings, LLC | Yes | 2021-11-08 | 2021-11-08 | 2021-12-09 | 2021-12-09 | 31 | 31 | Yes | 2021-12-14 | 2022-03-14 07:12 | 3 | 3 |  |  | Yes | 250338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12582.01 | 0 | 83333.96 | 25000 | 50000 | 50000 | 50000 | 25000 | 12755.99 | [7 empty] | 308671.96 | 58333.96
OK2110-3 | Shawnee Shell - OSO | AE | STROUD | 4795 N. Harrison, Shawnee, OK 74804 | Preconstruction | No | AG Harrison RE Holdings, LLC | Yes | 2021-12-06 | 2021-12-06 | 2022-01-14 | 2022-01-14 | 39 | 39 | No | 2022-01-14 | 2022-05-01 | 3.5548 | 3.5548 |  |  | Yes | 402660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34445.59 | 0 | 0 | 50000 | 75000 | 75000 | 75000 | 50000 | 18214.41 | [7 empty] | 377660 | -25000
OK2019 | Santa Fe Development | AE | WILLIAMS | 100 Southwest 134th Street, OKC, OK 73170 | Construction | Yes | AG Santa Fe RE Holdings, LLC | Yes | 2021-02-16 | 2021-02-16 | 2021-04-16 | 2021-04-16 | 59 | 59 | Yes | 2021-05-03 | 2022-01-10 | 8.3721 | 8.3721 |  |  | Yes | 1181870 | 0 | 0 | 0 | 0 | 0 | 154842 | 139424 | 0 | 383465 | 27725.91 | 0 | 157207.64 | 150659.49 | 119205.45 | [12 empty] | 1132529.49 | -49340.51 | Water meter issues
OK2020-1 | Western Shell | AE | FRARY | 11521 South Western Ave., OKC, OK 73170 | Complete | Yes | AG Western RE Holdings, LLC | Yes | 2020-08-03 | 2020-08-03 | 2020-11-27 | 2020-11-27 | 116 | 116 | Yes | 2020-11-09 | 2021-07-30 | 8.7375 | 8.7375 | Complete |  | Yes | 1307434 | 244435 | 181308 | 16313 | 286477 | 175065 | 254689 | 149147 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 1307434 | 0
OK2020-2 | Western Shell - Scammahorn | AE | FRARY | 11522 South Western Ave., OKC, OK 73170 | Complete | Yes | AG Western RE Holdings, LLC | Yes | 2020-08-06 | 2020-08-06 | 2020-11-28 | 2020-11-28 | 114 | 114 | Yes | 2020-11-09 | 2021-08-10 | 9.103 | 9.103 | Complete |  | Yes | 278383 | 46929 | 38525 | 0 | 45735 | 40858 | 33047 | 43566 | 18912 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 267572 | -10811
OK2020-3 | Western Shell - Dr. Olsen | AE | FRARY | 11523 South Western Ave., OKC, OK 73170 | Complete | Yes | AG Western RE Holdings, LLC | Yes | 2020-08-11 | 2020-08-11 | 2020-11-28 | 2020-11-28 | 109 | 109 | Yes | 2020-11-09 | 2021-08-02 | 8.8372 | 8.8372 | Complete |  | Yes | 231276 | 34010 | 31345 | 0 | 42608 | 27037 | 28599 | 46383 | 20189 | 1105 | 0 | 0 | 0 | 0 | [13 empty] | 231276 | 0
OK2024 | Bodyworx | AE | STROUD | 9201 S. Sooner Rd., Suite E, OKC 73135 | Complete | Yes | King Fisher Holdings, LLC | Yes | 2020-09-24 | 2020-09-24 | 2020-12-01 | 2020-12-01 | 68 | 68 | Yes | 2021-02-14 | 2021-08-04 | 5.6811 | 5.6811 | Complete |  | Yes | 984546 | 230830 | 155142 | 20934 | 247073 | 88548 | 113241 | 61708 | 67070 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 984546 | 0
OK2025 | Autism in Motion - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction | Yes | AG AIM OK RE Holdings, LLC | Yes | 2021-01-05 | 2021-01-05 | 2021-04-16 | 2021-04-16 | 101 | 101 | Yes | 2021-08-07 | 2022-01-10 | 5.1827 | 5.1827 |  |  | Yes | 1051400 | 0 | 0 | 0 | 0 | 0 | 0 | 111250 | 14446 | 326666 | 140279.29 | 169323.9 | 144372.98 | 80695.31 | 55061.83 | [12 empty] | 1042095.31 | -9304.69
OK2031 | T-Mobile - Guthrie | AE | WILLIAMS | 1904 S Division Street, Guthrie, OK 73044 | Complete | Yes | Don't Own | Yes | 2021-01-29 | 2021-01-29 | 2021-03-05 | 2021-03-05 | 35 | 35 | Yes | 2021-03-01 | 2021-07-16 | 4.5515 | 4.5515 | Complete |  | Yes | 723062 | 0 | 0 | 0 | 79004 | 201430 | 171285 | 187324 | 84019 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 723062 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | AE | WILLIAMS | 112 Southwest 134th Street, OKC, OK 73170 | Construction | Yes | AG Santa Fe RE Holdings, LLC | Yes | 2021-06-15 | 2021-06-15 | 2021-08-10 | 2021-08-10 | 56 | 56 | Yes | 2021-07-05 | 2022-01-28 | 6.8771 | 6.8771 |  |  | Yes | 1367414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99756 | 330951.22 | 217391.16 | 176608.81 | 39511.95 | 200000 | 92706.81 | [11 empty] | 1156925.95 | -210488.05
OK2033-2 | Old School Bagel - Santa Fe Dev. | AE | WILLIAMS | 112 SW 134th Street, Oklahoma City, OK | Construction | Yes | AG Santa Fe RE Holdings, LLC | Yes | 2021-06-20 | 2021-06-20 | 2021-12-03 | 2021-12-03 | 166 | 166 | Yes | 2021-11-17 | 2022-02-15 07:12 | 3 | 3 |  |  | Yes | 266165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139535.14 | 180000 | 50000 | [11 empty] | 369535.14 | 103370.14
OK2039 | Rockwell Daycare | AE | STROUD | 1213 N. Rockwell Ave., Oklahoma City, OK 73127 | Complete | Yes | Don't Own | Yes |  | 2020-12-01 |  | 2020-12-21 | 0 | 20 | Yes | 2021-02-01 | 2021-03-31 | 1.9269 | 1.9269 | Complete |  | Yes | 81500 | 0 | 0 | 0 | 81500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 81500 | 0
OK2110-1 | Shawnee Shell - Shawnee, OK | AE | STROUD | 4797 N. Harrison, Shawnee, OK 74804 | Construction | Yes | AG Harrison RE Holdings, LLC | Yes | 2021-07-14 | 2021-07-14 | 2021-09-17 | 2021-09-17 | 65 | 65 | Yes | 2021-11-01 | 2022-04-01 | 5.0166 | 5.0166 |  |  | Yes | 1180416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192936.95 | 0 | 295412.46 | 150000 | 175000 | 175000 | 200000 | 100000 | 37479.05 | [7 empty] | 1325828.46 | 145412.46
OK2129 | Chamberlain Group (SFD) | AE | WILLIAMS | 113 SW 134th Street, Oklahoma City, OK | Construction | 2021-12-30 | AG Chamberlain RE Holdings, LLC | Yes | 2021-11-12 | 2021-11-12 | 2022-01-06 | 2021-12-30 | 55 | 48 | Yes | 2022-01-11 | 2022-08-09 16:48 | 7 | 7 |  |  | Yes | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86613.87 | 200000 | 225000 | 225000 | 250000 | 200000 | 200000 | 200000 | 200000 | 200000 |  |  |  |  | 1986613.87 | 86613.87
TN2101 | AIM - Memphis, TN | PW | WILSON | 7007 Stage Rd., Memphis, TN 38133 | Construction | Yes | AG AIM Memphis RE Holdings, LLC | Yes | 2021-06-18 | 2021-06-18 | 2021-10-20 | 2021-10-20 | 124 | 124 | Yes | 2021-11-04 | 2022-03-31 | 4.8837 | 4.8837 |  |  | Yes | 2015533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141412 | 0 | 0 | 146485.8 | 239324.07 | 300000 | 300000 | 300000 | 300000 | 227635.2 | [8 empty] | 1954857.07 | -60675.93
[23 empty] | 15199530 | 2047245 | 702828 | 153598 | 849658 | 538775 | 755703 | 739337 | 204636 | 952404 | 498956.42 | 626679.61 | 624675.23 | 1115086.25 | 1279267.28 | 967706.81 | 825000 | 875000 | 602635.2 | 268449.45 | 200000 | 200000 | 200000 | 0 | 0 | 0 | 0 | 15227640.25 | 28110.25
Wes Gaddy |  | WG
OK2011-1 | Mustang Shell | WG | WILLIAMS | 1708 S Mustang Rd., Mustang, OK 73064 | Complete | Yes | TAG Mustang RE Holdings, LLC | Yes | 2021-05-01 | 2021-05-01 | 2021-07-01 | 2021-07-01 | 61 | 61 | Yes | 2020-09-01 | 2021-03-31 | 7 | 7.01 | Complete |  | Yes | 940687 | 720455 | 114649 | 0 | 105583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 940687 | 0
OK2011-2 | Mustang - Old School Bagel | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste D | Complete | Yes | TAG Mustang RE Holdings, LLC | Yes | 2021-05-01 | 2021-05-01 | 2021-07-01 | 2021-07-01 | 61 | 61 | Yes | 2020-11-01 | 2021-03-31 | 5 | 4.9834 | Complete |  | Yes | 226188 | 64622 | 39562 | 18328 | 101052 | 2624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 226188 | 0
OK2011-3 | Mustang - Enhanced Dental | WG | WILLIAMS | 1709 S Mustang Rd., Mustang, OK 73064 Ste A | Complete | Yes | TAG Mustang RE Holdings, LLC | Yes | 2021-05-01 | 2021-05-01 | 2021-07-01 | 2021-07-01 | 61 | 61 | Yes | 2020-11-01 | 2021-03-31 | 5 | 4.9834 | Complete |  | Yes | 315962 | 124791 | 64927 | 25844 | 98461 | 1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 315962 | 0
[23 empty] | 1482837 | 909868 | 219138 | 44172 | 305096 | 4563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482837 | 0
Christopher Goldsmith |  | CG
OK1902-1 | Empire Financial | CG | CLINTON | 12100 South Yukon Ave. Suite C, Glenpool, OK 74033 | Complete | Yes | Glenpool RE Holdings, LLC | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-14 | 2021-07-14 | 2 | 2.0266 |  |  | Yes | 46806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46806 | 0 | 0 | 0 | 0 | [13 empty] | 46806 | 0
OK1923-3 | Tropical Smoothie - Riverwest | CG | CLINTON | 152 W Alexander Blvd., Sand Springs, OK 74063 | Construction | Yes | Riverwest RE Holdings, LLC | Yes | 2021-06-01 | 2021-06-01 | 2021-06-15 | 2021-06-15 | 14 | 14 | Yes | 2021-05-28 | 2021-10-28 | 5 | 5.0831 |  |  | Yes | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58100 | 0 | 0 | 0 | 0 | 31025 | [12 empty] | 89125 | 0
OK1923-4 | Stanton Optical - Riverwest | CG | CLINTON | 153 W Alexander Blvd., Sand Springs, OK 74063 | Complete | Yes | Riverwest RE Holdings, LLC | Yes | 2021-06-01 | 2021-06-01 | 2021-06-15 | 2021-06-15 | 14 | 14 | Yes | 2021-06-06 | 2021-09-03 | 3 | 2.9568 |  |  | Yes | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75650 | 0 | 0 | 0 | 0 | [13 empty] | 75650 | 0
OK1936 | Dr Fischer | CG | CLINTON | 720 West 71St Street S, Tulsa, OK 74132 | Construction | Yes | AG Medical RE Holdings ,LLC | Yes | 2020-04-08 | 2020-04-08 | 2020-06-22 | 2020-06-22 | 75 | 75 | Yes | 2020-06-22 | 2021-09-30 | 15 | 15.4485 |  |  | Yes | 2482030 | 1788494 | 93223 | -90886 | 247214 | 203016 | 0 | 88152 | 152817 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 2482030 | 0
OK2008 | Dr. Gaches | CG | CLINTON | 11492 N. 137th E. Ave., Owasso, OK | Construction | Yes | AG Hi Point RE Holdings, LLC | Yes | 2020-08-28 | 2020-08-28 | 2021-03-05 | 2021-03-05 | 189 | 189 | Yes | 2021-04-04 | 2021-10-15 | 6 | 6.4452 |  |  | Yes | 683158 | 65749 | 0 | 0 | 72518 | 31182 | 36101 | 79510 | 164718 | 104045 | 68162.76 | 61172.24 | 0 | 29209.2 | [13 empty] | 712367.2 | 29209.2
OK2014 | Clark Plaza Shell | CG | CLINTON | 7877 E 71st South., Tulsa, OK 74133 | Construction | Yes | AG Clark RE Holdings, LLC | Yes | 2020-10-16 | 2020-10-16 | 2021-02-19 | 2021-02-19 | 126 | 126 | Yes | 2021-03-01 | 2021-12-27 | 10 | 10 |  |  | Yes | 1436404 | 91138 | 0 | 0 | 0 | 55754 | 185059 | 486176 | 117904 | 116211 | 178250.15 | 0 | 161504.44 | 44407.22 | [13 empty] | 1436403.81 | -0.19
OK2014-1 | Clark Shell - Dr. Pfeffer | CG | CLINTON | 7877 E 71st South Ste A, Tulsa, OK 74133 | Construction | Yes | AG Clark RE Holdings, LLC | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 19:12 | 8 | 8 |  |  | Yes | 648253 | 124344 | 0 | 0 | 0 | 0 | 0 | 82390 | 0 | 125825 | 199275.86 | 49841.62 | 43397.49 | 23178.47 | [13 empty] | 648252.44 | -0.56
OK2014-2 | Clark Shell - Enhance DDS | CG | CLINTON | 7877 E 71st South Ste B., Tulsa, OK 74133 | Construction | Yes | AG Clark RE Holdings, LLC | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 | 8 | 7.9734 |  |  | Yes | 400187 | 14681 | 0 | 0 | 0 | 0 | 0 | 50940 | 0 | 231205 | 53980.66 | 26603.7 | 22776.28 | 0 | [13 empty] | 400186.64 | -0.36
OK2032-1 | Cross Roads - Shell | CG | CLINTON | 1167 N. 38th Street, Broken Arrow, OK 74014 | Construction | Yes | AG Broken Arrow RE Holdings, LLC | Yes | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | CG | CLINTON | 1171 N. 38th Street, Broken Arrow, OK 74014 | Construction | Yes | AG Broken Arrow RE Holdings, LLC | Yes | 2021-08-09 | 2021-08-09 | 2021-08-10 | 2021-08-10 | 1 | 1 | Yes | 2021-10-01 | 2022-02-04 | 4 | 4.186 |  |  | Yes | 355011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230079.99 | 34583.86 | 20000 | 10000 | 9931.01 | [10 empty] | 304594.86 | -50416.14
[23 empty] | 6216624 | 2084406 | 93223 | -90886 | 319732 | 289952 | 221160 | 787168 | 435439 | 757842 | 499669.43 | 137617.56 | 457758.2 | 131378.75 | 51025 | 10000 | 9931.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6195415.95 | -21208.05
Cassidy Hedrick |  | CH
OK2028P | Precon - Memorial Park | CH | CH |  | Complete |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Yes | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 461956 | 0
OK2104 | Wimberley Walker Remodel | CH | CH | 101 Twilight Trail, Wimberly, TX 78676 | Construction | Yes | Wimberley Walker RE Holdings, LLC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 2020-12-30 | 2021-09-30 | 9 | 9.103 |  |  | Yes | 500577 | 0 | 0 | 17615 | 71648 | 0 | 97695 | 103125 | 92500 | 117994 | 0 | 0 | 0 | 0 | [13 empty] | 500577 | 0
[23 empty] | 962533 | 0 | 353138 | 126433 | 71648 | 0 | 97695 | 103125 | 92500 | 117994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 962533 | 0
Kimberly Kelly |  | KK | [48 empty] | 0
OK2038 | Dr. Farmer TI - Wonga Corner | KK | WILLIAMS | 1152 W. Douglas Midwest City, OK | Complete | Yes | Wonga Corner, LLC | Yes | 2021-02-26 | 2021-02-26 | 2021-03-17 | 2021-03-17 |  | 19 | Yes | 2021-03-17 | 2021-08-27 | 5 | 5.4153 |  |  | Yes | 383545 | 0 | 0 | 0 | 0 | 118932 | 110310 | 66219 | 58693 | 29391 | 0 | 0 | 0 | 0 | [13 empty] | 383545 | 0
TX1903 | Ramon Franklin Warehouse | KK | MILLER | 1308 Corporate Drive East, Arlinton, TX 76006 | Construction | Yes | Don't Own | N/A | 2020-12-09 | 2020-12-09 | 2021-01-27 | 2021-01-27 | 49 | 49 | Yes | 2021-07-05 | 2021-12-10 | 5 | 5.2492 |  |  | Yes | 1006579 | 131243 | 0 | 0 | 0 |  | 83010 | 67371 | 0 | 103268 | 113601.11 | 227523.97 | 173989.42 | 106572.13 | [13 empty] | 1006578.63 | -0.37
TX2101 | Bob Mills - Forth Worth | KK | JOHNSON | 3600 East Long Ave., Ft Worth, TX 76111 | Construction | Yes | Don't Own | N/A | 2021-04-09 | 2021-04-09 | 2021-06-10 | 2021-06-10 | 62 | 62 | Yes | 2021-07-10 | 2021-12-10 | 5 | 5.0831 |  |  | Yes | 2259828 | 0 | 0 | 0 | 0 | 0 | 105517 | 201248 | 0 | 748228 | 181824.92 | 308182.91 | 347750.61 | 375400.32 | [13 empty] | 2268151.76 | 8323.76
[23 empty] | 3649952 | 131243 | 0 | 0 | 0 | 118932 | 298837 | 334838 | 58693 | 880887 | 295426.03 | 535706.88 | 521740.03 | 481972.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3658275.39 | 8323.39
Tiffany Shiel |  | TS | [48 empty] | 0
OK2106-1 | Fox Lake Shell | TS | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Construction | Yes | TAG Fox Lake RE Holdings, LLC | Yes | 2021-06-22 | 2021-06-22 | 2021-09-22 | 2021-09-22 | 92 | 92 | Yes | 2021-07-22 | 2022-08-30 | 13 | 13.4219 |  |  | Yes | 12114221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 941343 | 403549.63 | 37623.36 | 1053416.41 | 633081.81 | 1000000 | 1000000 | 1000000 | 1000000 | 468583.59 | 1000000 | 1000000 | 1000000 | 1000000 | 437705.01 |  |  |  | 11975302.81 | -138918.19
[23 empty] | 12114221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 941343 | 403549.63 | 37623.36 | 1053416.41 | 633081.81 | 1000000 | 1000000 | 1000000 | 1000000 | 468583.59 | 1000000 | 1000000 | 1000000 | 1000000 | 437705.01 | 0 | 0 | 0 | 11975302.81 | -138918.19
Jason Nowell |  | JN | [48 empty] | 0
OK1912 | Dr. Shirley | JN |  | 2441 SW 134th, Oklahoma City, OK 73170 | Complete | Yes | Don't Own | N/A | [5 empty] | 0 | Yes | 2020-01-06 | 2020-09-16 | 8 | 8.4385 | Complete |  | Yes | 1217703 | 1206322 | 11381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1217703 | 0
OK1931 | Dr. Crowley | JN |  | 15101 Crown at Lone Oak Rd, OKC 73013 | Complete | Yes | Don't Own | N/A | [5 empty] | 0 | Yes | 2020-02-28 | 2020-12-22 | 10 | 9.9003 | Complete |  | Yes | 578876 | 568341 | 2335 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578876 | 0
[23 empty] | 1796579 | 1774663 | 13716 | 0 | 0 | 0 | 8200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1796579 | 0
Bob Solomon |  | BS | [48 empty] | 0
OK1926 | Hunter Pharmacy | BS | SMITH | 10120 Broadway Ext., OKC 73114 | Complete | Yes | AG Kimbaco RE Holdings, LLC | Yes | 2020-05-14 | 2020-05-14 | 2020-07-08 | 2020-07-08 | 55 | 55 | Yes | 2020-07-21 | 2021-06-24 | 11 | 11.2292 |  |  | Yes | 9534114 | 4251267 | 974630 | 965506 | 726926 | 1007479 | 748387 | 599421 | 93601 | 88474 | 65327.47 | 13095.53 | -1831.09 | 0 | [13 empty] | 9532282.91 | -1831.09
OK2006 | El Reno Enhanced Dental | BS | STROUD | 1601 Investors Ave., El Reno, OK 73036 | Complete | Yes | Don't Own | Yes | 2020-06-16 | 2020-06-16 | 2020-06-23 | 2020-06-23 | 7 | 7 | Yes | 2020-10-20 | 2021-07-15 | 9 | 8.9037 |  |  | Yes | 1258636 | 501155 | 186495 | 202246 | 66602 | 48430 | 7649 | 118643 | 54525 | 32612 | 0 | 0 | 632.5 | 0 | [13 empty] | 1218989.5 | -39646.5
OK2034 | Dr. Rex Johnson, DVM - Covell I35 | BS | STROUD | 5401 E. Covel Rd., Edmond, OK 73034 | Construction | Yes | AG Waterloo RE Holdings, LLC | Yes | 2021-05-12 | 2021-05-12 | 2021-08-10 | 2021-08-10 | 90 | 90 | Yes | 2021-08-16 | 2022-05-20 | 9 | 9.2027 |  |  | Yes | 2124651 | 0 | 0 |  |  | 233134 | 0 | 0 | 72994 | 144486 | 174326.34 | 157369.33 | 0 | 170113.65 | 200000 | 200000 | 200000 | 200000 | 150000 | 52341.33 |  |  |  |  | 165000 |  |  | 2119764.65 | -4886.35
OK2113 | Carlton Landing Sewer - Eufaula, OK | BS | TBD |  | Construction | Yes | Jenna check with cassidy - CL Holding? | Yes | N/A | N/A | N/A | N/A | N/A | N/A | No |  |  | 0 | 0 |  |  | Yes | 82107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | [12 empty] | 55000 | -27107
OK2112 | Covell 35 Dev. - Dr. Lu Dentistry | BS | STROUD | 5249 E. Covel Rd., Edmond, OK 73034 | Construction | Yes | AG Medical RE Holdings, LLC | Yes | 2021-10-20 | 2021-10-20 | 2021-12-10 | 2021-12-10 | 51 | 51 | Yes | 2021-12-22 | 2022-09-18 21:36 | 9 | 9 |  |  | Yes | 1325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92185.59 | 150000 | 200000 | 200000 | 225000 | 250000 | 200000 | [7 empty] | 1317185.59 | -7814.41
TX1901 | Dr. Dyer - Sequoia Spur | BS | STEPHENSON | 115 Shell Rd, Georgtown, TX 78633 | Construction | Yes | Sequoia Spur RE Holdings, LLC | Yes | 2020-05-11 | 2020-05-11 | 2020-07-06 | 2020-07-06 | 56 | 56 | Yes | 2020-11-01 | 2021-12-01 | 13 | 13.1229 |  |  | Yes | 1809504 | 407476 | 214131 | 74131 | 135778 | 437832 | 31174 | 82243 | 45087 | 149925 | 55587.04 | 113628.69 | 49278.8 | 13280.8 | [13 empty] | 1809552.33 | 48.33
TX2001 | Dr. Lippian - Texarkana | BS | HARRIS | 5220 Gibson Ln., Texarkana, TX 75501 | Construction | Yes | Don't Own | Yes | 2020-09-30 | 2020-09-30 | 2020-12-29 | 2020-12-29 | 90 | 90 | Yes | 2021-01-28 | 2021-11-01 | 9 | 9.2027 |  |  | Yes | 1641198 | 103605 | 0 | 71204 | 158532 | 124183 | 320119 | 192377 | 74223 | 357461 | 34466.45 | 131256.06 | 72535.74 | 0 | [13 empty] | 1639962.25 | -1235.75
[23 empty] | 17775210 | 5263503 | 1375256 | 1313087 | 1087838 | 1851058 | 1107329 | 992684 | 340430 | 772958 | 329707.3 | 415349.61 | 120615.95 | 275580.04 | 405000 | 400000 | 400000 | 425000 | 400000 | 252341.33 | 0 | 0 | 0 | 0 | 165000 | 0 | 0 | 17692737.23 | -82472.77
Kyle Tedlock |  | KT | [48 empty] | 0
OK2016 | OneCore | KT | HALL | 100 NE 85th Street, OKC, OK 73114 | Construction | Yes | TAG OneCore RE Holdings, LLC | Yes | 2020-08-11 | 2020-08-11 | 2020-11-12 | 2020-11-12 | 93 | 93 | Yes | 2020-10-15 | 2021-12-01 | 14 | 13.6877 |  |  | Yes | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 1384616.45 | 896696.76 | 358271.54 | 418400.69 | [13 empty] | 13413397.44 | 305486.44
[23 empty] | 13107911 | 802663 | 1051823 | 822272 | 1170091 | 1068761 | 823660 | 1536928 | 1558003 | 1521211 | 1384616.45 | 896696.76 | 358271.54 | 418400.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13413397.44 | 305486.44
Kevin Trosper |  | KT | [48 empty] | 0
OK1822-3 | R&D Construction | KT | TROSPER | 901 E. Main Suite 125, Yukon, OK 73099 | Complete | Yes | AGRIGGS RE Holdings, LLC | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-05 | 2021-08-20 | 2 | 1.5282 |  |  | Yes | 89125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28797 | 8473.4 | 0 | 0 | 0 | 51854.6 | [12 empty] | 89125 | 0
OK1822-4 | Blondette | KT | TROSPER | 902 E. Main Suite 115, Yukon, OK 73099 | Complete | Yes | AGRIGGS RE Holdings, LLC | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-05 | 2021-08-20 | 2 | 1.5282 |  |  | Yes | 75650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24902 | 5295.49 | 0 | 0 | 0 | 45452.51 | [12 empty] | 75650 | 0
OK1909-3 | Allstate Insurance (Brandon) | KT | TROSPER | 1140 NW 192nd Street Suite B, Oklahoma City, OK | Complete | Yes | Creekwood RE Holdings, LLC | Yes | 2021-04-13 | 2021-04-13 | 2021-04-27 | 2021-04-27 | 14 | 14 | Yes | 2021-05-17 | 2021-06-09 | 1 | 0.76412 |  |  | Yes | 67027 | 0 | 0 | 0 | 0 | 0 | 0 | 67027 | 0 | 0 | 0 | 0 | 3185.48 | 0 | [13 empty] | 70212.48 | 3185.48
OK1917-4 | Colonial Point - Nutrition Club | KT | TROSPER | 11999 NW Expressway Yukon, OK 73099 | Construction | Yes | Piedmont RE Holdings, LLC | Yes | 2021-06-22 | 2021-06-22 | 2021-07-12 | 2021-07-12 | 20 | 20 | Yes | 2021-07-05 | 2021-10-01 | 3 | 2.9236 |  |  | Yes | 38040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38040 | 0 | 0 | 0 | 0 | [13 empty] | 38040 | 0
OK1922-3 | Coltrane Corner - Regent Bank (Mike) | KT | TROSPER | 2823 E. 2nd, Suite C, Edmond, OK | Complete | Yes | Coltrane RE Holdings, LLC | Yes | 2021-05-14 | 2021-05-14 | 2021-06-15 | 2021-06-15 | 32 | 32 | Yes | 2021-06-21 | 2021-08-17 | 2 | 1.8937 |  |  | Yes | 74344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74344 | 0 | 0 | 0 | 0 | [13 empty] | 74344 | 0
OK1922-4 | Coltrane Corner - Klassy K9 (Mike) | KT | TROSPER | 2824 E. 2nd, Edmond, OK | Complete | Yes | Coltrane RE Holdings, LLC | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-11 | 2021-07-02 | 1 | 0.69767 |  |  | Yes | 6336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6336 | 0 | 0 | 0 | 0 | [13 empty] | 6336 | 0
OK2101 | Christian Counseling | KT | TROSPER | 12901 E. Britton Rd. Suite B, Jones, 73049 | Complete | Yes | Britton Holdings, LLC | Yes | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 2021-03-01 | 2021-05-31 | 3 | 3.0233 |  |  | Yes | 52095 | 0 | 0 | 0 | 0 | 0 | 0 | 52095 | 0 | 0 | 0 | 0 | 10962.16 | 0 | 0 | [12 empty] | 63057.16 | 10962.16
OK2105-1 | Valencia - Breakroom 405 (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. A, Edmond, OK 73012 | Complete | Yes | AG Valencia RE Holdings, LLC | Yes | 2021-03-22 | 2021-03-22 | 2021-04-16 | 2021-04-16 | 25 | 25 | Yes | 2021-05-24 | 2021-08-11 | 3 | 2.6246 |  |  | Yes | 156692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156692 | 0 | 0 | 0 | 5333.82 | 0 | 0 | [12 empty] | 162025.82 | 5333.82
OK2105-2 | Valencia - Christfit Gym (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Complete | Yes | AG Valencia RE Holdings, LLC | Yes | 2021-03-22 | 2021-03-22 | 2021-04-07 | 2021-04-07 | 16 | 16 | Yes | 2021-05-24 | 2021-08-09 | 3 | 2.5581 |  |  | Yes | 94557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94557 | 0 | 0 | 13646.35 | 0 | 0 | -13646.35 | [12 empty] | 94557 | 0
OK2105-3 | Valencia - Winfield and Co. | KT | TROSPER | 2216 NW 178th Street Ste. E, Edmond, OK 73012 | Construction | Yes | AG Valencia RE Holdings, LLC | Yes | 2021-09-01 | 2021-09-01 | 2021-09-16 | 2021-09-16 | 15 | 15 |  | 2021-09-22 | 2021-10-17 | 1 | 0.83056 |  |  | Yes | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15493 | [12 empty] | 15493 | 0
OK2105-4 | Valencia - Prevail Fitness | KT | TROSPER | 2215 NW 178th Street Ste. B, Edmond, OK 73012 | Complete | Yes | AG Valencia RE Holdings, LLC | Yes | 2021-05-07 | 2021-05-07 | 2021-06-11 | 2021-06-11 | 35 | 35 | Yes | 2021-07-06 | 2021-09-17 | 2 | 2.4252 |  |  | Yes | 101240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36103 | 58225 | 0 | 0 | 0 | 0 | 6912 | [12 empty] | 101240 | 0
OK2105-5 | Valencia - Magnus Batting Cage (Cory) | KT | TROSPER | 2215 NW 178th Street Ste. D, Edmond, OK 73012 | Complete | Yes | AG Valencia RE Holdings, LLC | Yes | 2021-06-04 | 2021-06-04 | 2021-06-21 | 2021-06-21 | 17 | 17 | Yes | 2021-06-28 | 2021-08-30 | 2 | 2.093 |  |  | Yes | 36900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36900 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 36900 | 0
OK2105-6 | Valencia - Breakroom 405 Warehouse | KT | TROSPER | 2215 NW 178th Street Ste. C, Edmond, OK 73012 | Complete | Yes | AG Valencia RE Holdings, LLC | Yes | 2021-09-21 | 2021-09-21 | 2021-10-15 | 2021-10-15 | 24 | 24 | Yes | 2021-09-29 | 2021-10-08 | 0 | 0.299 |  |  | Yes | 12885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20166.67 | 0 | [13 empty] | 20166.67 | 7281.67
TX2006-1 | Sunnyvale Shell | KT | DOYLE | 480 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | AG Sunnyvale RE Holdings, LLC | Yes | 2021-06-22 | 2021-06-22 | 2021-11-09 | 2021-11-09 | 140 | 140 | Yes | 2021-11-17 | 2022-06-01 | 7 | 6.5116 |  |  | Yes | 1910050 | 0 | 0 | 0 | 0 | 0 | 0 | 119451 | 0 | 139349 | 0 | 270190.83 | 61829.84 | 301196.25 | 250000 | 300000 | 300000 | 294229.33 | [9 empty] | 2036246.25 | 126196.25
TX2006-2 | Sunnyvale Shell - Dr. Luna | TROSPER | DOYLE | 481 US Hwy 80, Sunnyvale, TX 75182 | Preconstruction | Yes | AG Sunnyvale RE Holdings, LLC | Yes | 2021-12-21 | 2021-12-13 | 2022-01-27 | 2022-01-24 | 37 | 42 | Yes | 2022-03-07 | 2022-06-03 | 3 | 2.9236 |  |  | Yes | 288979 | 0 | 0 | 0 | 0 | 0 | 0 | 7826 | 0 | 9711 | 0 | 0 | 0 | 0 |  | 60000 | 60000 | 60000 | 60000 | [5 empty] | 31442 |  |  | 288979 | 0
TX2006-3 | Sunnyvale Shell - Dr. Rohani | TROSPER | DOYLE | 482 US Hwy 80, Sunnyvale, TX 75182 | Preconstruction | Yes | AG Sunnyvale RE Holdings, LLC | Yes | 2021-12-21 | 2021-12-29 | 2022-02-04 | 2022-01-24 | 45 | 26 | Yes | 2022-03-07 | 2022-06-03 | 3 | 2.9236 |  |  | Yes | 366822 | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 0 | 12408 | 0 | 0 | 0 | 0 |  | 75000 | 75000 | 75000 | 62000 | [5 empty] | 59698 |  |  | 366822 | 0
[23 empty] | 3386235 | 0 | 0 | 0 | 0 | 0 | 0 | 254115 | 324252 | 392112 | 13768.89 | 283837.18 | 101477.97 | 301196.25 | 356065.76 | 435000 | 435000 | 429229.33 | 122000 | 0 | 0 | 0 | 0 | 0 | 91140 | 0 | 0 | 3539194.38 | 152959.38
Preconstruction | [50 empty] | 0
OK2037 | Master Hand Milling | TBD | TBD | TBD, Edmond, OK | Preconstruction | No | TBD | No | 2022-06-01 | 2022-06-01 | 2022-07-16 | 2022-07-16 | 45 | 45 | No | 2022-08-15 | 2023-08-11 04:48 | 12 | 12 |  |  |  | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 200000 | 250000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 830000 | 4000000 | 0
OK2102 | Puppy Paws East Edmond | TROSPER | TBD | East Edmond | Preconstruction | No | AG Puppy Covell RE Holdings, LLC | 2022-02-14 | 2022-02-05 | 2022-02-15 | 2022-04-16 | 2022-04-16 | 70 | 60 | No | 2022-05-01 | 2023-01-26 21:36 | 9 | 9 |  |  |  | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 150000 | 200000 | 260000 | 260000 | 300000 | 300000 | 260000 | 260000 | 210000 |  |  | 2200000 | 0
OK2106-2 | Fox Lake - Sidecar | TS | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC | Yes | 2022-01-03 | 2022-01-03 | 2022-02-17 | 2022-02-17 | 45 | 45 | No | 2022-04-01 | 2022-12-27 21:36 | 9 | 9 |  |  |  | 980000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 100000 | 125000 | 150000 | 200000 | 200000 | 155000 |  |  |  |  | 980000 | 0
OK2106-3 | Fox Lake - Hatch | TS | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC | Yes | 2022-01-03 | 2022-01-03 | 2022-02-17 | 2022-02-17 | 45 | 45 | No | 2022-04-01 | 2022-12-27 21:36 | 9 | 9 |  |  |  | 1558000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 125000 | 225000 | 300000 | 300000 | 300000 | 258000 |  |  |  |  | 1558000 | 0
OK2106-4 | Fox Lake - Enhanced Dental | TS | JE | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC | Yes | 2022-01-17 | 2022-01-17 | 2022-03-03 | 2022-03-03 | 45 | 45 | No | 2022-04-02 | 2022-09-29 14:24 | 6 | 6 |  |  |  | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25000 | 75000 | 90000 | 100000 | 100000 | 100000 | 50000 |  |  |  |  | 540000 | 0
OK2106-5 | Fox Lake - Open Space | TS | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC | Yes | 2022-01-03 | 2022-01-03 | 2022-02-17 | 2022-02-17 | 45 | 45 | No | 2022-04-01 | 2022-09-28 14:24 | 6 | 6 |  |  |  | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 75000 | 125000 | 125000 | 150000 | 150000 | 125000 | 50000 |  |  |  |  | 800000 | 0
OK2106-6 | Fox Lake Provision Concepts | TS | SMITH | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC | Yes | 2022-01-03 | 2022-01-03 | 2022-02-17 | 2022-02-17 | 45 | 45 | No | 2022-04-01 | 2022-09-28 14:24 | 6 | 6 |  |  |  | 690000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 100000 | 120000 | 120000 | 120000 | 120000 | 60000 |  |  |  |  | 690000 | 0
OK2107 | Jack Be Grocery | TBD | TBD |  | Preconstruction | No | AG May RE Holdings, LLC | 2022-02-28 | 2022-01-31 | 2022-01-31 | 2022-03-17 | 2022-03-17 | 45 | 45 | No | 2022-03-18 | 2022-09-14 14:24 | 6 | 6 |  |  |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 75000 | 125000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 700000 | 2500000 | 0
OK2108 | Puppy Paws - Lone Oak | KT | STROUD | 15200 Crown at Lone Oak, Edmond OK 73013 | Preconstruction | No | AG Puppy West RE Holdings, LLC | Yes | 2021-11-19 | 2021-11-19 | 2022-01-06 | 2022-01-06 | 48 | 48 | No | 2022-01-20 | 2022-10-17 21:36 | 9 | 9 |  |  |  | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 150000 | 150000 |  |  | 2050000 | -150000
OK2114-1 | Chamberlain Realty - Lone Oak | TBD | TBD | 15103 Crown at Lone Oak Rd., Edmond, OK 73013 | Preconstruction | No | AG Chamberlain West RE Holdings, LLC | 2022-06-01 | 2022-04-17 | 2022-04-17 | 2022-06-01 | 2022-06-01 | 45 | 45 | No | 2022-06-01 | 2022-11-28 14:24 | 6 | 6 |  |  |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 60000 | 60000 | 60000 | 45000 |  |  |  |  | 25000 |  |  | 350000 | -50000
OK2120 | Peak View Brewery and Distillery | TBD | TBD | Reservoir by Costco | Preconstruction | No | Don't know | 2022-04-01 | 2022-04-17 | 2022-04-17 | 2022-06-01 | 2022-06-01 | 45 | 45 | No | 2022-06-01 | 2023-03-29 | 10 | 10 |  |  |  | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 125000 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 225000 | 3000000 | 0
OK2121 | 15th & Bryant Development | TBD | TBD |  | Preconstruction | Yes | AG Fifteen RE Holdings, LLC | 2021-12-14 | 2022-01-03 | 2022-01-28 | 2022-02-27 | 2022-02-27 | 55 | 30 | No | 2022-02-21 | 2022-08-20 14:24 | 6 | 6 |  |  |  | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269645.4 |  |  | 125000 | 125000 | 125000 | 105000 |  |  |  |  | 200000 |  |  | 949645.4 | 269645.4
OK2122 | The Learning Experence (15th & Bryant Development) | TBD | TBD |  | Preconstruction | No | AG Fifteen RE Holdings, LLC | 2021-12-14 | 2022-01-28 | 2022-01-28 | 2022-02-27 | 2022-02-27 | 30 | 30 | No | 2022-02-21 | 2022-08-31 | 6.3455 | 6.3455 |  |  | Yes | 2859947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 250000 | 250000 | 250000 | 300000 | 300000 | 300000 | 205000 |  | 325000 |  |  | 2180000 | -679947
OK2125-1 | Enid Shell | BS | TBD |  | Preconstruction | No | AG Enid RE Holdings, LLC | 2022-01-13 | 2021-12-13 | 2022-01-14 | 2022-01-17 | 2022-01-17 | 35 | 3 | No | 2022-01-17 | 2022-10-14 21:36 | 9 | 9 |  |  |  | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 100000 | 150000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 150000 |  | 1500000 | 0
OK2125-2 | OSB - Enid | TBD | TBD |  | Preconstruction | No | AG Enid RE Holdings, LLC | 2022-01-13 | 2022-01-14 | 2022-01-14 | 2022-02-28 | 2022-02-28 | 45 | 45 | No | 2022-03-30 | 2022-07-28 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 150000 | 50000 | [6 empty] | 150000 |  |  | 350000 | 0
OK2125-3 | Enhanced Dental - Enid | TBD | TBD |  | Preconstruction | No | AG Enid RE Holdings, LLC | 2022-01-13 | 2022-01-14 | 2022-01-14 | 2022-02-28 | 2022-02-28 | 45 | 45 | No | 2022-03-30 | 2022-07-28 09:36 | 4 | 4 |  |  |  | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 50000 | 75000 | 75000 | 75000 | 75000 | 75000 | 25000 |  |  |  | 450000 | 0
OK2126-1 | Weatherford Shell | KT | STEPHENSON |  | Preconstruction | No | AG Weatherford RE Holdings, LLC | 2022-01-14 | 2021-12-13 | 2022-01-14 | 2022-01-13 | 2022-01-21 | 31 | 7 | Yes | 2022-02-14 | 2022-10-12 19:12 | 8 | 8 |  |  |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 75000 | 150000 | 150000 | 200000 | 200000 | 200000 | 125000 |  |  |  |  | 1200000 | 0
OK2126-3 | Weatherford Shell - Enhanced Dental | TBD | TBD |  | Preconstruction | No | AG Weatherford RE Holdings, LLC | 2022-01-14 | 2021-12-30 | 2022-01-30 | 2022-03-16 | 2022-03-16 | 76 | 45 | No | 2022-04-15 | 2022-08-13 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 75000 | 100000 | 100000 | 25000 | [6 empty] | 350000 | 0
OK2127 | Legacy Martial Arts Shell | TBD | TBD |  | Preconstruction | No | Don't know | No | 2022-06-01 | 2022-06-01 | 2022-07-16 | 2022-07-16 | 45 | 45 | No | 2022-08-15 | 2023-02-11 14:24 | 6 | 6 |  |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 75000 | 130000 | 130000 | 130000 | 130000 | 105000 |  |  |  |  | 750000 | 0
OK2128 | OSB 150th and Penn | TBD | FOX | 15201 N. Penn Crossing Court, Oklahoma City, OK 73013 | Preconstruction | No | TAG Penn OSB RE Holdings,LLC | 2022-02-25 | 2022-01-19 | 2022-01-19 | 2022-03-05 | 2022-03-05 | 45 | 45 | No | 2022-04-04 | 2022-10-01 14:24 | 6 | 6 |  |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75000 | 100000 | 125000 | 125000 | 125000 | 140000 | 60000 | [5 empty] | 750000 | 0
OK2132-1 | Seminole Shell | TBD | STRUB |  | Preconstruction | No | AG Seminole RE Holdings, LLC | 2022-02-18 | 2022-01-30 | 2022-01-30 | 2022-03-01 | 2022-03-01 | 30 | 30 | No | 2022-03-06 | 2022-12-01 21:36 | 9 | 9 |  |  |  | 1360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 1360000 |  | 1360000 | 0
OK2132-2 | T-Mobile - Seminole | TBD | STRUB |  | Preconstruction | No | AG Seminole RE Holdings, LLC | 2022-02-18 | 2022-01-30 | 2022-01-30 | 2022-03-16 | 2022-03-16 | 45 | 45 | No | 2022-04-15 | 2022-10-12 14:24 | 6 | 6 |  |  |  | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 175000 |  | 175000 | 0
OK2132-3 | Urgent Care - Seminole | TBD | STRUB |  | Preconstruction | No | AG Seminole RE Holdings, LLC | 2022-02-18 | 2022-01-30 | 2022-01-30 | 2022-03-16 | 2022-03-16 | 45 | 45 | No | 2022-04-15 | 2022-10-12 14:24 | 6 | 6 |  |  |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 300000 |  | 300000 | 0
OK2132-4 | TBD TI #3 P - Seminole | TBD | STRUB |  | Preconstruction | No | AG Seminole RE Holdings, LLC | 2022-02-18 | 2022-01-30 | 2022-01-30 | 2022-03-16 | 2022-03-16 | 45 | 45 | No | 2022-04-15 | 2022-08-13 09:36 | 4 | 4 |  |  |  | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 95000 |  | 95000 | 0
OK21xx | Norman Shell | TBD | TBD |  | Preconstruction | No | TAG Norman RE Holdings, LLC | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-03-26 | 2022-03-26 | 45 | 45 | No | 2022-04-25 | 2023-01-20 21:36 | 9 | 9 |  |  |  | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 1200000 | 1200000 | 0
OK21xx | OSB - Norman Shell | TBD | TBD |  | Preconstruction | No | TAG Norman RE Holdings, LLC | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-03-26 | 2022-03-26 | 45 | 45 | No | 2022-04-25 | 2023-01-20 21:36 | 9 | 9 |  |  |  | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 300000 | 300000 | 0
OK21xx | TI - Norman Shell | TBD | TBD |  | Preconstruction | No | TAG Norman RE Holdings, LLC | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-03-26 | 2022-03-26 | 45 | 45 | No | 2022-04-25 | 2023-01-20 21:36 | 9 | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0
OK2134-1 | Glenn Pool Shell | TBD | TBD | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC | 2022-02-15 | 2022-01-30 | 2022-01-30 | 2022-03-01 | 2022-03-01 | 30 | 30 | No | 2022-03-01 | 2022-11-26 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 2000000 | 2000000 | 0
OK2134-2 | TI #1 - Glenn Pool Shell | TBD | TBD | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC | 2022-02-15 | 2021-12-30 | 2021-12-30 | 2022-02-13 | 2022-02-13 | 45 | 45 | No | 2022-03-15 | 2022-12-10 21:36 | 9 | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 650000 | 650000 | 650000
OK2134-3 | TI #2 - Glenn Pool Shell | TBD | TBD | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC | 2022-02-15 | 2021-12-30 | 2021-12-30 | 2022-02-13 | 2022-02-13 | 45 | 45 | No | 2022-03-15 | 2022-12-10 21:36 | 9 | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 650000 | 650000 | 650000
OK2134-4 | TI #3 - Glenn Pool Shell | TBD | TBD | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC | 2022-02-15 | 2021-12-30 | 2021-12-30 | 2022-02-13 | 2022-02-13 | 45 | 45 | No | 2022-03-15 | 2022-12-10 21:36 | 9 | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 650000 | 650000 | 650000
OK2134-5 | TI #4 - Glenn Pool Shell | TBD | TBD | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC | 2022-02-15 | 2021-12-30 | 2021-12-30 | 2022-02-13 | 2022-02-13 | 45 | 45 | No | 2022-03-15 | 2022-12-10 21:36 | 9 | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 650000 | 650000 | 650000
OK2134-6 | TI #5 - Glenn Pool Shell | TBD | TBD | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC | 2022-02-15 | 2021-12-30 | 2021-12-30 | 2022-02-13 | 2022-02-13 | 45 | 45 | No | 2022-03-15 | 2022-12-10 21:36 | 9 | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 650000 | 650000 | 650000
OK1925 | OSB Express - Glenn Pool, OK (Stand Alone) | TBD | TBD | Glenn Pool, OK | Preconstruction | No | TAG Glenpool OSB RE Holdings,LLC | 2022-02-09 | 2022-02-09 | 2022-02-09 | 2022-02-28 | 2022-02-28 | 19 | 19 | No | 2022-02-14 | 2022-05-01 | 2.5249 | 2.5249 |  |  |  | 725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 725000 |  | 725000 | 0
Okxxxx | Regent Corner (Fox Lake Similar) | Tedlock | TBD | Broken Arrow, OK | Preconstruction | No | AG Regent BA RE Holdings, LLC | No | 2022-05-01 | 2022-05-01 | 2022-06-30 | 2022-06-30 | 60 | 60 | No | 2022-07-30 | 2023-07-26 04:48 | 12 | 12 |  |  |  | 14000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 1250000 | 1250000 | 1250000 | 1250000 | 9000000 | 14000000 | 0
OKxxxxTI | Yukon Nail Salon (Full Build) | TBD | TBD |  | Preconstruction | No | AGRIGGS RE Holdings, LLC | 2022-01-05 |  |  |  |  | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0
OKxxxxTI | Cross Roads - Broken Arrow - Dr. Shambille (WGS) | TBD | TBD | Broken Arrow, OK | Preconstruction | No | AG Broken Arrow RE Holdings, LLC | 2021-12-21 |  |  |  |  | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0
OKxxxxTI | Glenn Pool Shell - Montap Fyzical Theropy (White Box) | TBD | TBD | Glenn Pool, OK | Preconstruction | No | Glenpool RE Holdings, LLC | 2022-01-05 |  |  |  |  | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0
TX2005 | McKinney Development | TBD | DOYLE | Virginia and Ridge Road, McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC | N/A | 2021-10-01 | 2021-10-01 | 2022-01-14 | 2022-01-14 | 105 | 105 | No | 2022-04-15 | 2023-01-10 21:36 | 9 | 9 |  |  |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 120000 |  |  |  | 600000 | 0
TX2103-1 | McKinney Shell (McKinney Development) | KT | DOYLE | McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC | Yes | 2022-02-04 | 2022-02-04 | 2022-05-05 | 2022-05-05 | 90 | 90 | No | 2022-04-15 | 2022-10-12 14:24 | 6 | 6 |  |  |  | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 25000 | 50000 | 80000 | 80000 | 80000 | 80000 | 80000 | 125000 | 600000 | 0
TX2103-2 | TBD TI (McKinney Shell) | KT | DOYLE | McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC | No | 2022-02-04 | 2022-02-04 | 2022-05-05 | 2022-05-05 | 90 | 90 | No | 2022-06-04 | 2023-03-01 21:36 | 9 | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0
TX2103-3 | TBD TI (McKinney Shell) | KT | DOYLE | McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC | No | 2022-02-04 | 2022-02-04 | 2022-05-05 | 2022-05-05 | 90 | 90 | No | 2022-06-04 | 2023-03-01 21:36 | 9 | 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0
TX2006-4 | Sunnyvale Shell - GI Alliance | TROSPER | DOYLE | 482 US Hwy 80, Sunnyvale, TX 75182 | Preconstruction | No | AG Sunnyvale RE Holdings, LLC | Yes | 2021-12-21 | N/A | N/A | N/A | N/A | N/A | No | 2022-03-07 | 2022-06-03 | 2.9236 | 2.9236 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 0 | 12408 | 0 | 0 | 0 | 0 | [11 empty] | -20124 |  | 0 | 0
TX2007-1 | Carrollton Shell | TROSPER | DOYLE | Carrollton, TX | Preconstruction | No | AG Carrolton RE Holdings, LLC | Yes | 2021-10-28 | 2021-06-15 | 2021-12-17 | 2022-02-07 | 50 | 237 | No | 2022-02-14 | 2022-11-11 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 250000 | 25000 | 250000 | 300000 | 300000 | 150000 |  |  |  | 725000 |  | 2000000 | 0
TX2007-2 | Carrolton Shell - Dr. Bui | TROSPER | DOYLE | Carrollton, TX | Preconstruction | No | AG Carrolton RE Holdings, LLC | Yes | 2021-11-26 | 2021-11-26 | 2022-02-24 | 2022-02-24 | 90 | 90 | No | 2022-03-26 | 2022-07-24 09:36 | 4 | 4 |  |  |  | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 | 100000 | 100000 | 100000 | 100000 |  |  |  |  | 50000 |  | 500000 | -50000
TX2008 | Dr. Barbara Lee (McKinney Development) | TROSPER | DOYLE | McKinney, TX | Preconstruction | No | AG Virginia RE Holdings, LLC | Yes | 2021-10-22 | 2021-10-22 | 2022-01-14 | 2022-01-14 | 84 | 84 | No | 2022-04-15 | 2023-01-10 21:36 | 9 | 9 |  |  |  | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 65000 | 145000 |  |  | 750000 | 0
TX2102-1 | San Antonio Shell | TBD | TBD | San Antonio, TX | Preconstruction | No | AG 281 RE Holdings, LLC | Yes | 2021-11-30 | 2021-11-30 | 2022-02-28 | 2022-02-28 | 90 | 90 | No | 2022-03-30 | 2022-12-25 21:36 | 9 | 9 |  |  |  | 2229000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 125000 | 175000 | 225000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 204000 |  | 2229000 | 0
TX2102-2 | Dr. Abeskharon - San Antonio | TBD | TBD | San Antonio, TX | Preconstruction | No | AG 281 RE Holdings, LLC | Yes | 2021-11-30 | 2021-11-30 | 2022-02-28 | 2022-02-28 | 90 | 90 | No | 2022-05-29 | 2022-09-26 09:36 | 4 | 4 |  |  |  | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 50000 | 75000 | 125000 | 110000 | [5 empty] | 360000 | 0
| Fayetteville Development |  |  | Fayetteville, AR |  |  | AG Fayetteville RE Holdings, LLC | 2022-06-10 |  |  |  |  | 0 | 0 | No | [20 empty] | 0 | [13 empty] | 0
| Cleveland Enhanced Dental |  |  | Cleveland, OK |  |  | AG Cleveland RE Holdings, LLC | 2022-04-04 |  |  |  |  | 0 | 0 | No | [20 empty] | 0 | [13 empty] | 0
FL2101 | 248 Blue Mountain Beach | [5 empty] | Blue Mountain RE Holdings, LLC | [28 empty] | 96582.13
0
0
0
0
0
0
[24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0
[23 empty] | 55001947 | 0 | 0 | 0 | 0 | 0 | 0 | 7716 | 0 | 12408 | 0 | 0 | 0 | 366227.53 | 250000 | 375000 | 2335000 | 3080000 | 3945000 | 4295000 | 4250000 | 3885000 | 4308000 | 3215000 | 3800000 | 5933876 | 17630000 | 57591645.4 | 2589698.4
0
[19 empty] | Billing Total |  |  |  | 130693579 | 13013591 | 3809122 | 2368676 | 3804063 | 3872041 | 3312584 | 4755911 | 3013953 | 6349159 | 3425694.15 | 2933510.96 | 3237955.33 | 3722923.77 | 3341358.04 | 3187706.81 | 5004931.01 | 5809229.33 | 5538218.79 | 5815790.78 | 5450000 | 5085000 | 5508000 | 3652705.01 | 4056140 | 5933876 | 17630000 | 133535557.85 | 2841978.85
[23 empty] | Billing Goal | 14657045 | 2798117.1429 | 3206824.6429 | 4008392.6429 | 4318997.6429 | 5069566.6429 | 5575814.6429 | 5314704.6429 | 5476840 | 5359959 | 6173564 | 5501722 | 3866535 | 3500000 | 3500000 | 5000000 | 6000000 | 6825000 | 7100000 | 7100000 | 7000000 | 6500000 | 6500000 | 6500000 | 6500000 | 80000000
[23 empty] | Difference | -1643454 | 1011004.8571 | -838148.6429 | -204329.6429 | -446956.6429 | -1756982.6429 | -819903.6429 | -2300751.6429 | 872319 | -1934264.85 | -3240053.04 | -2263766.67 | -143611.23 | -158641.96 | -312293.19 | 4931.01 | -190770.67 | -1286781.21 | -1284209.22 | -1650000 | -1915000 | -992000 | -2847294.99 | -2443860 | -566124 | -62370000
[48 empty] | 2021 | 45000000
[23 empty] | Rev Actual |  | 2897650 | 3085444 | 3369732 | [20 empty] | 2022 | 60000000
[23 empty] | Rev Goal |  | 2233736.9151 | 2560008.1124 | 3199899.8468 | 3447855.8183 | 4047035.051 | 4451172.8294 | 4242728.7164 | 4372161.372 | 4278855.2697 | 4928356.1412 | 4392024.6726 | 3086654.8905 | 2794050 | [10 empty] | 2023 | 72000000
[23 empty] | Difference |  | 663913.0849 | 525435.8876 | 169832.1532 | [20 empty] | 2024 | 86400000
[48 empty] | 2025 | 99360000
[23 empty] | GP Actual |  | 261214 | 325090 | 157521 | [20 empty] | 2026 | 114264000
[23 empty] | GP Goal |  | 245394.8734 | 281238.5212 | 351536.0348 | 378776.0933 | 444600.9946 | 488998.9442 | 466099.5972 | 480318.868 | 470068.4043 | 541421.5628 | 482501.0194 | 339095.1195 | 306950 | [10 empty] | 2027 | 131403600
[23 empty] | Difference |  | 15819.1266 | 43851.4788 | -194015.0348 | [20 empty] | 2028 | 151114140
[48 empty] | 2029 | 173781261
[23 empty] | GP % Actual |  | 9.01% | 10.54% | 4.67% | [20 empty] | 2030 | 199848450.15
[23 empty] | GP % Goal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | [10 empty] | 2031 | 229825717.6725
[23 empty] | Difference |  | -0.99% | 0.54% | -5.33% | [20 empty] | 2032 | 264299575.3234
[48 empty] | 2033 | 303944511.6219
[23 empty] | OH Actual |  | 256248 | 250107 | 305940
[23 empty] | OH Goal |  | 275000 | 275000 | 275000 | 293000 | 293000 | 293000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
[23 empty] | Difference |  | 18752 | 24893 | -30940
[23 empty] | NP Actual |  | 4126 | 74711 | -101036
[23 empty] | NP Goal |  | 24539.4873 | 28123.8521 | 35153.6035 | 37877.6093 | 44460.0995 | 48899.8944 | 46609.9597 | 48031.8868 | 47006.8404 | 54142.1563 | 48250.1019 | 36904.512 | 500000.0033
[23 empty] | Difference |  | -20413.4873 | 46587.1479 | -136189.6035
DEAD / HOLD / SOLD | [50 empty] | 0
FL2001 | Elysee Lot 6 | SOLD | SOLD | SOLD | SOLD |  |  |  |  | SOLD |  | SOLD |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD |  | 137906 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 3503 | 0 | 0 | 0 | [15 empty] | 137906 | 0
FL2002 | Elysee Lot 7 | SOLD | SOLD | SOLD | SOLD |  |  |  |  | SOLD |  | SOLD |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD |  | 136537 | 61092 | 0 | 0 | 0 | 73311 | 0 | 0 | 2134 | 0 | 0 | 0 | [15 empty] | 136537 | 0
OK1922-1 | Coltrane Corner - Aya Rowe | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK1924 | Yukon Development | HOLD | HOLD | HOLD | HOLD |  |  |  |  | HOLD |  | HOLD |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2018 | Dr. Mackey - 61st Street | DEAD | DEAD | 9050 E. 61st Street, Tulsa, OK 74145 | HOLD |  |  |  |  | HOLD |  | HOLD |  | HOLD | Yes | HOLD | HOLD |  | HOLD | HOLD | HOLD |  | 33274 | 0 | 0 | 0 | 0 | 0 | 33274 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 33274 | 0
OK2119 | OSB - Wonga Corner | DEAD | DEAD | 1156 S. Douglas, Midwest City, OK 73130 | HOLD |  |  |  |  | HOLD |  | HOLD |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2020-4 | Western - PT Central | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2026 | Covell I35 Edmond Dev. | DEAD | DEAD | 5400 E. Covell Road, Edmond, OK | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | Yes | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [15 empty] | 0 | 0
OK2028 | Precon - Memorial Park | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 461956 | 0 | 353138 | 108818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 461956 | 0
OK2032-2 | Cross Roads - Dr. Rhodes | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15630 | 0 | 0 | 15630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 15630 | 0
OK2032-3 | Cross Roads - State Farm | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15000 | 0 | 0 | 5720 | 0 | 9280 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 15000 | 0
OK2032-5 | Cross Roads - Dispensary | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2036 | Dr. Matt Cole, DDS | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 41062 | 0 | 0 | 0 | 0 | 0 | 41062 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 41062 | 0
OK2103 | Bethesda - Santa Fe Dev. | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2105-3 | Valencia - Custom Pools | DEAD | DEAD | 2215 NW 178th Street Ste. E, Edmond, OK 73012 | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15493 | 0 | 0 | [15 empty] | 15493 | 0
OK2109-1 | Grand Blvd. Shell - OKC, OK | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2111 | Solara Surgery Center - Moore, OK | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2115 | Paul's Valley Development | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2117-1 | Paul's Valley Shell | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2117-2 | Paul's Valley Shell - Enhanced Dental | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2118 | Paul's Valley Shell - TBD | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2116 | Dollar Tree (Paul's Valley Development) | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2123 | TBD (15th & Bryant Development) | DEAD | DEAD | DEAD | DEAD | No |  | DEAD |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0
OK2124 | Bodin Chiro (Lone Oak) | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OK2126-2 | Weatherford Shell - Dollar Tree | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | HOLD | HOLD | HOLD | HOLD |  |  |  |  | HOLD |  | HOLD |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0
Okxxxx | Anytime Fitness - Brandon Porter | HOLD | HOLD | HOLD | HOLD | No |  | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0
TNxxxx | AIM Bellevue - Site Visit Needed | PW | TBD | 7734 Hwy 70 S. Nashville, TN 37221 | Preconstruction | No | AG AIM Bellevue RE Holdings, LLC | 2022-01-31 |  | DEAD | DEAD | DEAD | DEAD | DEAD | No | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD |  | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 2400000 | 0
TX2004 | Marshall Ridge Dev. | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 37392 | 0 | 0 | 37392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 37392 | 0
TX2009 | Alliance Pediatrics-Marsh | DEAD | DEAD | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 3575 | 0 | 0 | 3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 3575 | 0
[23 empty] | 3297825 | 122184 | 353138 | 171135 | 0 | 155902 | 74336 | 0 | 5637 | 15493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 3297825 | 0
Formulas:
Brandon = [Brandon]+(3*4.3*7)
Brandon = [Brandon]+(7*7*4.3)
Trevor = [Trevor]+35
Note on U16: Bobby Snyder: Punchlist was conducted via facetime and all items have been completed. Final punch walk will occur in Sept with Rep from CA
Note on B38: Bobby Snyder: Existing Building
Note on X38: Existing Building
Note on M83: Bobby Snyder: Need approval on additional parking for GI Alliance 2006-4
Note on R99: Bobby Snyder: Hard completion date prior to LDs
Note on R100: Bobby Snyder: Hard completion date of Aug to prevent LDs
Note on I108: Bobby Snyder: Don't close land until permit is in hand. Land close can be pushed
Note on K108: Bobby Snyder: Push design forward
Note on I112: Bobby Snyder: Don't close loan until permit is in hand
Note on I115: Bobby Snyder: Don't close loan until permit is in hand
Note on K116: Bobby Snyder: Add 6 months to permits on TI
Note on K121: Bobby Snyder: Get early site release prior to full permit
Note on K126: Bobby Snyder: Need a permit from Trevor
Note on K130: Bobby Snyder: Cold dark shell
Note on K131: Trevor Hayes: Clock Started on 10/28
Note on K134: Bobby Snyder: Need update from Trevor. 3' of undercut over entire site.
Note on B180: Bobby Snyder: Another GC built out this space.

## 01 2022
Zach | Peggy | Brandon | Phillip | Bobby | Jenna | Brandon | Trevor | Jenna | Ben | Ben | Trevor | Trevor | Trevor | Trevor | Bobby | Trevor | Trevor | Trevor | Brandon | Brandon | Brandon | Brandon | Peggy | Peggy | Trevor | Trevor |  | 2022 | [11 empty] | 2023
Job Number | Project | PM | SUP | Dev. Director | Address | Status | Turn Over Complete | Entity | LOI | Loan/Lease Close | Anticipated Permit Submission | Actual Permit Submitted | Anticipated Permit Received | Actual Permit Received | Delta Btwn Loan Close and Permit | Anticipated Permit Duration | Permit Approval Duration | Permit Received | Start Date | Comp Date | Planned Duration | Actual Duration | Punchlist Complete Date | Lessons Learned | Appraisal Budget Approved | Appraisal Value | Previously Billed | January 2022 | February 2022 | March 2022 | April 2022 | May 2022 | June 2022 | July 2022 | August 2022 | September 2022 | October 2022 | November 2022 | December 2022 | Annual 2023 | TOTAL | DELTA | COMMENTS
Adam England |  | ENGLAND
OK2019 | Santa Fe Development | ENGLAND | STROUD | N/A | 100 Southwest 134th Street, OKC, OK 73170 | Construction | Yes | AG Santa Fe RE Holdings, LLC |  | Yes | 2021-02-16 | 2021-02-16 | 2021-04-16 | 2021-04-16 | #VALUE! | 59 | 59 | Yes | 2021-05-03 | 2022-01-10 | 8.3721 | 8.3721 |  |  | Yes | 1181869.7 | 1013323.83 | 59705.08 | [12 empty] | 1073028.91 | -108840.79 | Water meter issues
OK2025 | Autism in Motion - Santa Fe Dev. | ENGLAND | WILLIAMS | N/A | 112 Southwest 134th Street, OKC, OK 73170 | Construction | Yes | AG AIM OK RE Holdings, LLC |  | Yes | 2021-01-05 | 2021-01-05 | 2021-04-16 | 2021-04-16 | #VALUE! | 101 | 101 | Yes | 2021-08-07 | 2022-01-25 | 5.1827 | 5.6811 |  |  | Yes | 1051400.45 | 987033.51 | 64366.94 | [12 empty] | 1051400.45 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | ENGLAND | STROUD | N/A | 112 Southwest 134th Street, OKC, OK 73170 | Construction | Yes | AG Santa Fe RE Holdings, LLC |  | Yes | 2021-06-15 | 2021-06-15 | 2021-08-10 | 2021-08-10 | #VALUE! | 56 | 56 | Yes | 2021-07-05 | 2022-01-28 | 6.8771 | 6.8771 |  |  | Yes | 1367413.55 | 864219.08 | 83841.4 | 92706.81 | [11 empty] | 1040767.29 | -326646.26
OK2033-2 | Old School Bagel - Santa Fe Dev. | ENGLAND | STROUD | N/A | 112 SW 134th Street, Oklahoma City, OK | Construction | Yes | AG Santa Fe RE Holdings, LLC |  | Yes | 2021-06-20 | 2021-06-20 | 2021-12-03 | 2021-12-03 | #VALUE! | 166 | 166 | Yes | 2021-11-17 | 2022-05-01 | 3 | 5.4817 |  |  | Yes | 272915 | 139535.14 | 39753.44 | 50000 | [11 empty] | 229288.58 | -43626.42
OK2110-1 | Shawnee Shell - Shawnee, OK | ENGLAND | STROUD | N/A | 4797 N. Harrison, Shawnee, OK 74804 | Construction | Yes | AG Harrison RE Holdings, LLC |  | Yes | 2021-07-14 | 2021-07-14 | 2021-09-17 | 2021-09-17 | #VALUE! | 65 | 65 | Yes | 2021-11-30 | 2022-05-11 | 5.0166 | 5.3821 |  |  | Yes | 1180416.18 | 488349.41 | 162144.05 | 175000 | 175000 | 200000 | 100000 | 37479.05 | [7 empty] | 1337972.51 | 157556.33
OK2110-2 | Shawnee Shell - Old School Bagel | ENGLAND | STROUD | N/A | 4799 N. Harrison, Shawnee, OK 74804 | Construction | Yes | AG Harrison RE Holdings, LLC |  | Yes | 2021-11-08 | 2021-11-08 | 2021-12-09 | 2021-12-09 | #VALUE! | 31 | 31 | Yes | 2022-02-17 | 2022-05-01 | 3 | 2.4252 |  |  | Yes | 253338.08 | 95915.97 | 0 | 50000 | 50000 | 50000 | 25000 | 12755.99 | [7 empty] | 283671.96 | 30333.88
OK2110-3 | Shawnee Shell - OSO | ENGLAND | STROUD | N/A | 4795 N. Harrison, Shawnee, OK 74804 | Construction | Yes | AG Harrison RE Holdings, LLC |  | Yes | 2021-12-06 | 2021-12-06 | 2022-01-14 | 2022-01-28 | #VALUE! | 39 | 53 | Yes | 2022-02-14 | 2022-07-14 | 3.5548 | 4.9834 |  |  | Yes | 402660.29 | 34445.59 | 0 | 75000 | 75000 | 75000 | 50000 | 43214.7 | [7 empty] | 352660.29 | -50000
OK2128 | OSB 150th and Penn | ENGLAND | WILLIAMS | N/A | 15201 N. Penn Crossing Court, Oklahoma City, OK 73013 | Preconstruction | No | TAG Penn OSB RE Holdings,LLC |  | 2022-03-18 | 2022-01-19 | 2022-02-01 | 2022-03-05 | 2022-03-18 | 0 | 45 | 45 | No | 2022-04-02 | 2022-09-29 14:24 | 6 | 6 |  |  |  | 750000 | 0 | 0 | 75000 | 100000 | 125000 | 125000 | 125000 | 140000 | 60000 | [5 empty] | 750000 | 0
OK2129 | Chamberlain Group (SFD) | ENGLAND | STROUD | N/A | 113 SW 134th Street, Oklahoma City, OK | Construction | Yes | AG Chamberlain RE Holdings, LLC |  | Yes | 2021-11-12 | 2021-11-12 | 2022-01-06 | 2021-12-30 | #VALUE! | 55 | 48 | Yes | 2022-01-11 | 2022-09-01 | 7 | 7.7409 |  |  | Yes | 1353098.44 | 86613.87 | 120514.88 | 225000 | 225000 | 250000 | 200000 | 200000 | 200000 | 200000 | 200000 |  |  |  |  | 1907128.75 | 554030.31
TN2101 | AIM - Memphis, TN | ENGLAND | N/A | N/A | 7007 Stage Rd., Memphis, TN 38133 | Construction | Yes | AG AIM Memphis RE Holdings, LLC |  | Yes | 2021-06-18 | 2021-06-18 | 2021-10-20 | 2021-10-20 | #VALUE! | 124 | 124 | Yes | 2021-11-04 | 2022-03-31 | 4.8837 | 4.8837 |  |  | Yes | 1207444.74 | 527222.16 | 0 | 300000 | 300000 | 300000 | 227635.2 | [8 empty] | 1654857.36 | 447412.62
[26 empty] | 9020556.43 | 4236658.56 | 530325.79 | 1042706.81 | 925000 | 1000000 | 727635.2 | 418449.74 | 340000 | 260000 | 200000 | 0 | 0 | 0 | 0 | 9680776.1 | 660219.67
Kevin Tedlock |  | TEDLOCK
OK1923-6 | OSB - Riverwest | TEDLOCK | RONS | HAYES | 152 W Alexander Blvd., Sand Springs, OK 74063 | Construction | Yes | Riverwest RE Holdings, LLC |  | Yes | 2021-06-01 | 2021-06-01 | 2021-06-15 | 2021-06-15 | #VALUE! | 14 | 14 | Yes | 2021-05-28 | 2021-10-28 | 5 | 5.0831 |  |  | Yes | 89125 | 58100 | 0 | [12 empty] | 58100 | -31025
OK1936 | Dr Fischer | TEDLOCK | RONS | N/A | 720 West 71St Street S, Tulsa, OK 74132 | Construction | Yes | AG Medical RE Holdings ,LLC |  | Yes | 2020-04-08 | 2020-04-08 | 2020-06-22 | 2020-06-22 | #VALUE! | 75 | 75 | Yes | 2020-06-22 | 2021-09-30 | 15 | 15.4485 |  |  | Yes | 2482029.51 | 2482029.51 | 0 | [12 empty] | 2482029.51 | 0
OK2008 | Dr. Gaches | TEDLOCK | RONS | N/A | 11492 N. 137th E. Ave., Owasso, OK | Construction | Yes | AG Hi Point RE Holdings, LLC |  | Yes | 2020-08-28 | 2020-08-28 | 2021-03-05 | 2021-03-05 | #VALUE! | 189 | 189 | Yes | 2021-04-04 | 2021-10-15 | 6 | 6.4452 |  |  | Yes | 712367.43 | 712367.43 | 0 | [12 empty] | 712367.43 | 0
OK2014 | Clark Plaza Shell | TEDLOCK | RONS | N/A | 7877 E 71st South., Tulsa, OK 74133 | Construction | Yes | AG Clark RE Holdings, LLC |  | Yes | 2020-10-16 | 2020-10-16 | 2021-02-19 | 2021-02-19 | #VALUE! | 126 | 126 | Yes | 2021-03-01 | 2021-12-27 | 10 | 10 |  |  | Yes | 1436404.19 | 1436404.19 | 0 | [12 empty] | 1436404.19 | 0
OK2014-1 | Clark Shell - Dr. Pfeffer | TEDLOCK | RONS | N/A | 7877 E 71st South Ste A, Tulsa, OK 74133 | Construction | Yes | AG Clark RE Holdings, LLC |  | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | #VALUE! | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 19:12 | 8 | 8 |  |  | Yes | 648252.98 | 648252.98 | 0 | [12 empty] | 648252.98 | 0
OK2014-2 | Clark Shell - Enhance DDS | TEDLOCK | RONS | N/A | 7877 E 71st South Ste B., Tulsa, OK 74133 | Construction | Yes | AG Clark RE Holdings, LLC |  | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | #VALUE! | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 | 8 | 7.9734 |  |  | Yes | 400186.6 | 400186.6 | 0 | [12 empty] | 400186.6 | 0
OK2016 | OneCore | TEDLOCK | HALL | N/A | 100 NE 85th Street, OKC, OK 73114 | Construction | Yes | TAG OneCore RE Holdings, LLC |  | Yes | 2020-08-11 | 2020-08-11 | 2020-11-12 | 2020-11-12 | #VALUE! | 93 | 93 | Yes | 2020-10-15 | 2021-12-01 | 14 | 13.6877 |  |  | Yes | 14188397.56 | 13413397.56 | 812671.7 | [12 empty] | 14226069.26 | 37671.7
OK2032-1 | Cross Roads - Shell | TEDLOCK | RONS | N/A | 1167 N. 38th Street, Broken Arrow, OK 74014 | Construction | Yes | AG Broken Arrow RE Holdings, LLC |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | [12 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | TEDLOCK | RONS | N/A | 1171 N. 38th Street, Broken Arrow, OK 74014 | Construction | Yes | AG Broken Arrow RE Holdings, LLC |  | Yes | 2021-08-09 | 2021-08-09 | 2021-08-10 | 2021-08-10 | #VALUE! | 1 | 1 | Yes | 2021-10-01 | 2022-03-08 | 4 | 5.2492 |  |  | Yes | 295011.29 | 264663.85 | 0 | 10000 | 9931.01 | [10 empty] | 284594.86 | -10416.43
[26 empty] | 20251774.56 | 19415402.12 | 812671.7 | 10000 | 9931.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20248004.83 | -3769.73
Kimberly Kelly |  | KELLY | [39 empty] | 0
TX1903 | Ramon Franklin Warehouse | KELLY | MILLER | N/A | 1308 Corporate Drive East, Arlinton, TX 76006 | Construction | Yes | Don't Own |  | N/A | 2020-12-09 | 2020-12-09 | 2021-01-27 | 2021-01-27 | #VALUE! | 49 | 49 | Yes | 2021-07-05 | 2021-12-10 | 5 | 5.2492 |  |  | Yes | 1006578.9 | 1006578.9 | 0 | [12 empty] | 1006578.9 | 0
TX2101 | Bob Mills - Forth Worth | KELLY | JOHNSON | N/A | 3600 East Long Ave., Ft Worth, TX 76111 | Construction | Yes | Don't Own |  | N/A | 2021-04-09 | 2021-04-09 | 2021-06-10 | 2021-06-10 | #VALUE! | 62 | 62 | Yes | 2021-07-10 | 2021-12-10 | 5 | 5.0831 |  |  | Yes | 2315782.2 | 2304152.2 | 38625.5 | [12 empty] | 2342777.7 | 26995.5
[26 empty] | 3322361.1 | 3310731.1 | 38625.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3349356.6 | 26995.5
Tiffany Shiel |  | SHIEL | [39 empty] | 0
OK2106-1 | Fox Lake Shell | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Construction | Yes | TAG Fox Lake RE Holdings, LLC |  | Yes | 2021-06-22 | 2021-06-22 | 2021-09-22 | 2021-09-22 | #VALUE! | 92 | 92 | Yes | 2021-07-22 | 2022-11-15 | 13 | 15.9801 |  |  | Yes | 12193746.8 | 3069014.06 | 532188.35 | 1000000 | 1000000 | 1000000 | 468583.59 | 1000000 | 1000000 | 1000000 | 1000000 | 656149.15 |  |  |  | 11725935.15 | -467811.65
[26 empty] | 12193746.8 | 3069014.06 | 532188.35 | 1000000 | 1000000 | 1000000 | 468583.59 | 1000000 | 1000000 | 1000000 | 1000000 | 656149.15 | 0 | 0 | 0 | 11725935.15 | -467811.65
Bob Solomon |  | SOLOMON | [39 empty] | 0
OK2034 | Dr. Rex Johnson, DVM - Covell I35 | SOLOMON | WILLIAMS | N/A | 5401 E. Covel Rd., Edmond, OK 73034 | Construction | Yes | AG Waterloo RE Holdings, LLC |  | Yes | 2021-05-12 | 2021-05-12 | 2021-08-10 | 2021-08-10 | #VALUE! | 90 | 90 | Yes | 2021-08-16 | 2022-05-20 | 9 | 9.2027 |  |  | Yes | 1961015.83 | 952423.73 | 173273.61 | 200000 | 200000 | 200000 | 150000 | 52341.33 |  |  |  |  | 165000 |  |  | 2093038.67 | 132022.84
OK2112 | Covell 35 Dev. - Dr. Lu Dentistry | SOLOMON | WILLIAMS | N/A | 5249 E. Covel Rd., Edmond, OK 73034 | Construction | Yes | AG Medical RE Holdings, LLC |  | Yes | 2021-10-20 | 2021-10-20 | 2021-12-10 | 2021-12-10 | #VALUE! | 51 | 51 | Yes | 2021-12-22 | 2022-06-30 | 9 | 6.3123 |  |  | Yes | 762952.96 | 92185.59 | 111281.22 | 200000 | 200000 | 225000 | 250000 | 200000 | [7 empty] | 1278466.81 | 515513.85
OK2113 | Carlton Landing Sewer - Eufaula, OK | SOLOMON | N/A | N/A |  | Construction | Yes | Jenna check with cassidy - CL Holding? |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No |  |  | 0 | 0 |  |  | No | 0 | 0 | 0 | [12 empty] | 0 | 0
OK2125-1 | Enid Shell | SOLOMON | RONS | N/A |  | Construction | Yes | AG Enid RE Holdings, LLC |  | 2022-01-13 | 2021-12-13 | 2022-01-14 | 2022-01-17 | 2022-02-23 | 41 | 35 | 40 | Yes | 2022-02-28 | 2022-09-16 | 9 | 6.6445 |  |  |  | 1500000 | 0 | 0 |  | 50000 | 100000 | 150000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 150000 |  | 1500000 | 0
OK2125-2 | Enid - OSB | SOLOMON | RONS | N/A |  | Preconstruction | No | AG Enid RE Holdings, LLC |  | 2022-01-13 | 2022-01-14 | 2022-02-18 | 2022-02-28 | 2022-03-20 | 66 | 45 | 30 | No | 2022-06-18 | 2022-10-16 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 |  | 150000 | 150000 | 50000 | [8 empty] | 350000 | 0
OK2125-3 | Enid - Enhanced Dental | SOLOMON | RONS | N/A |  | Preconstruction | No | AG Enid RE Holdings, LLC |  | 2022-01-13 | 2022-01-14 | 2022-02-18 | 2022-02-28 | 2022-03-20 | 66 | 45 | 30 | No | 2022-06-28 | 2022-10-26 09:36 | 4 | 4 |  |  |  | 450000 | 0 | 0 |  |  | 50000 | 75000 | 75000 | 75000 | 75000 | 75000 | 25000 |  |  |  | 450000 | 0
[26 empty] | 5023968.79 | 1044609.32 | 284554.83 | 400000 | 600000 | 725000 | 675000 | 502341.33 | 250000 | 250000 | 250000 | 200000 | 340000 | 150000 | 0 | 2093038.67 | -2930930.12
Kevin Trosper |  | TROSPER | [39 empty] | 0
OK2105-3 | Valencia - Winfield and Co. | TROSPER | TROSPER | N/A | 2216 NW 178th Street Ste. E, Edmond, OK 73012 | Construction | Yes | AG Valencia RE Holdings, LLC |  | Yes | 2021-09-01 | 2021-09-01 | 2021-09-16 | 2021-09-16 | #VALUE! | 15 | 15 |  | 2021-09-22 | 2021-10-17 | 1 | 0.83056 |  |  | Yes | 27626.4 | 11493 | 16133.4 | [12 empty] | 27626.4 | 0
OK2108 | Puppy Paws - Lone Oak | TROSPER | WILLIAMS | HAYES | 15200 Crown at Lone Oak, Edmond OK 73013 | Construction | Yes | AG Puppy West RE Holdings, LLC |  | Yes | 2021-11-19 | 2021-11-19 | 2022-01-06 | 2022-02-14 | #VALUE! | 48 | 87 | Yes | 2022-02-21 | 2022-11-30 | 9 | 9.3688 |  |  |  | 2200000 | 0 | 0 | 200000 | 200000 | 200000 | 250000 | 250000 | 250000 | 250000 | 250000 | 200000 |  |  |  | 2050000 | -150000
OK2126-1 | Weatherford Shell | TROSPER | STEPHENSON | N/A |  | Construction | Yes | AG Weatherford RE Holdings, LLC |  | 2022-01-14 | 2021-12-13 | 2022-01-14 | 2022-01-13 | 2022-01-21 | 7 | 31 | 7 | Yes | 2022-02-14 | 2022-08-19 | 8 | 6.1794 |  |  |  | 1200000 | 0 | 0 | 50000 | 75000 | 150000 | 150000 | 200000 | 200000 | 200000 | 125000 |  |  |  |  | 1150000 | -50000
OK2126-3 | Weatherford Shell - Enhanced Dental | TROSPER | STEPHENSON | N/A |  | Preconstruction | No | AG Weatherford RE Holdings, LLC |  | 2022-01-14 | 2021-12-30 | 2022-02-16 | 2022-03-16 | 2022-03-02 | 47 | 76 | 14 | No | 2022-05-06 | 2022-09-03 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 |  | 50000 | 75000 | 100000 | 100000 | 25000 | [6 empty] | 350000 | 0
TX2006-1 | Sunnyvale Shell | TROSPER | DOYLE | N/A | 480 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | AG Sunnyvale RE Holdings, LLC |  | Yes | 2021-06-22 | 2021-06-22 | 2021-11-09 | 2021-11-09 | #VALUE! | 140 | 140 | Yes | 2021-11-17 | 2022-06-01 | 7 | 6.5116 |  |  | Yes | 1910049.56 | 892016.83 | 304883.09 | 300000 | 300000 | 168032.73 | [9 empty] | 1964932.65 | 54883.09
TX2006-2 | Sunnyvale Shell - Dr. Luna | TROSPER | DOYLE | N/A | 481 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | AG Sunnyvale RE Holdings, LLC |  | Yes | 2021-12-21 | 2021-12-13 | 2022-01-27 | 2022-01-24 | #VALUE! | 37 | 42 | Yes | 2022-02-07 | 2022-07-02 | 3 | 4.8173 |  |  | Yes | 288979.2 | 17537.69 | 0 | 60000 | 90000 | 90000 | 31441.51 | [8 empty] | 288979.2 | 0
TX2006-3 | Sunnyvale Shell - Dr. Rohani | TROSPER | DOYLE | N/A | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | AG Sunnyvale RE Holdings, LLC |  | Yes | 2021-12-21 | 2021-12-29 | 2022-02-04 | 2022-01-24 | #VALUE! | 45 | 26 | Yes | 2022-02-07 | 2022-07-02 | 3 | 4.8173 |  |  | Yes | 376822.32 | 20124 | 0 | 75000 | 75000 | 75000 | 75000 | 56698.32 | [7 empty] | 376822.32 | 0
TX2006-4 | Sunnyvale Shell - GI Alliance | TROSPER | DOYLE | N/A | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | AG Sunnyvale RE Holdings, LLC |  | Yes | 2021-12-21 | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0 | 0 | [12 empty] | 0 | 0
[26 empty] | 6353477.48 | 941171.52 | 321016.49 | 685000 | 790000 | 758032.73 | 606441.51 | 606698.32 | 475000 | 450000 | 375000 | 200000 | 0 | 0 | 0 | 6208360.57 | -145116.91
Preconstruction | [41 empty] | 0
OK1925 | OSB Express - Glenn Pool, OK (Stand Alone) | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool OSB RE Holdings,LLC |  | 2022-04-05 | 2022-02-09 | 2022-04-04 | 2022-02-28 | 2022-05-04 | 29 | 19 | 30 | No | 2022-05-04 | 2022-10-01 | 2.5249 | 4.9834 |  |  |  | 725000 | 0 | 0 | [10 empty] | 725000 |  | 725000 | 0
OK2037 | Master Hand Milling | TBD | TBD | TBD | TBD, Edmond, OK | Preconstruction | No | TBD |  | No | 2022-06-01 | 2022-05-23 | 2022-07-16 | 2022-06-22 | #VALUE! | 45 | 30 | No | 2022-07-22 | 2023-07-18 04:48 | 12 | 12 |  |  |  | 4000000 | 0 | 0 |  | 200000 | 250000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 830000 | 4000000 | 0
OK2102 | Puppy Paws East Edmond | TROSPER | TBD | HAYES | East Edmond | Preconstruction | No | AG Puppy Covell RE Holdings, LLC |  | 2022-02-14 | 2022-02-05 | 2022-05-11 | 2022-04-16 | 2022-07-10 | 146 | 70 | 60 | No | 2022-05-01 | 2023-01-26 21:36 | 9 | 9 |  |  |  | 2200000 | 0 | 0 |  | 150000 | 200000 | 260000 | 260000 | 300000 | 300000 | 260000 | 260000 | 210000 |  |  | 2200000 | 0
OK2106-2 | Fox Lake - Sidecar | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-05-09 | 2022-05-11 | 2022-02-17 | 2022-06-25 | #VALUE! | -81 | 45 | No | 2022-07-01 | 2023-03-28 21:36 | 6 | 9 |  |  |  | 980000 | 0 | 0 |  | 50000 | 100000 | 125000 | 150000 | 200000 | 200000 | 155000 |  |  |  |  | 980000 | 0
OK2106-3 | Fox Lake - Hatch | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-05-09 | 2022-05-11 | 2022-02-17 | 2022-06-25 | #VALUE! | -81 | 45 | No | 2022-07-01 | 2023-03-28 21:36 | 6 | 9 |  |  |  | 1558000 | 0 | 0 |  | 50000 | 125000 | 225000 | 300000 | 300000 | 300000 | 258000 |  |  |  |  | 1558000 | 0
OK2106-4 | Fox Lake - Enhanced Dental | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-03-02 | 2022-03-01 | 2022-03-03 | 2022-04-15 | #VALUE! | 1 | 45 | No | 2022-05-15 | 2022-11-11 14:24 | 6 | 6 |  |  |  | 540000 | 0 | 0 |  | 25000 | 75000 | 90000 | 100000 | 100000 | 100000 | 50000 |  |  |  |  | 540000 | 0
OK2106-5 | Fox Lake - Chicago Title | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-04-11 | 2022-04-15 | 2022-02-17 | 2022-05-30 | #VALUE! | -53 | 45 | No | 2022-04-01 | 2022-09-28 14:24 | 6 | 6 |  |  |  | 800000 | 0 | 0 |  | 75000 | 125000 | 125000 | 150000 | 150000 | 125000 | 50000 |  |  |  |  | 800000 | 0
OK2106-6 | Fox Lake Provision Concepts | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-05-09 | 2022-06-23 | 2022-02-17 | 2022-08-07 | #VALUE! | -81 | 45 | No | 2022-04-01 | 2022-09-28 14:24 | 6 | 6 |  |  |  | 690000 | 0 | 0 |  | 50000 | 100000 | 120000 | 120000 | 120000 | 120000 | 60000 |  |  |  |  | 690000 | 0
OK2106-7 | Fox Lake TBD |  |  | HAMMOND | [5 empty] | Yes |  | 2022-06-23 |  | 2022-08-07 | #VALUE! |  | 45 | No | [8 empty] | 0 | 0
OK2106-8 | Fox Lake Chicken Foote |  |  | HAMMOND | [5 empty] | Yes | 2022-05-09 | 2022-06-23 |  | 2022-08-07 | #VALUE! |  | 45 | No | [8 empty] | 0 | 0
OK2106-9 | Fox Lake Regent Bank |  |  | HAMMOND | [5 empty] | Yes | 2022-05-09 | N/A |  | N/A | #VALUE! |  | N/A | N/A | [8 empty] | 0 | 0
OK2107 | Jack Be Grocery | SOLOMON | STRUB | CISPER |  | Preconstruction | 2022-02-24 | AG May RE Holdings, LLC |  | 2022-03-11 | 2022-01-31 | 2022-02-03 | 2022-03-17 | 2022-03-05 | -6 | 45 | 30 | No | 2022-03-18 | 2022-09-14 14:24 | 6 | 6 |  |  |  | 2500000 | 0 | 0 |  | 75000 | 125000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 700000 | 2500000 | 0
OK2114-1 | Chamberlain Realty - Lone Oak | TBD | TBD | HAYES | 15103 Crown at Lone Oak Rd., Edmond, OK 73013 | Preconstruction | No | AG Chamberlain West RE Holdings, LLC |  | 2022-06-01 | 2022-04-17 | 2022-05-01 | 2022-06-01 | 2022-06-15 | 14 | 45 | 45 | No | 2022-06-01 | 2022-11-28 14:24 | 6 | 6 |  |  |  | 400000 | 0 | 0 | 50000 | 60000 | 60000 | 60000 | 45000 |  |  |  |  | 25000 |  |  | 300000 | -100000
OK2120 | Peak View Brewery and Distillery | TBD | TBD | TBD | Reservoir by Costco | Preconstruction | No | Don't know |  | 2022-04-01 | 2022-04-17 | 2022-07-10 | 2022-06-01 | 2022-08-24 | 145 | 45 | 45 | No | 2022-06-01 | 2023-03-29 | 10 | 10 |  |  |  | 3000000 | 0 | 0 |  | 125000 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 225000 | 3000000 | 0
OK2122 | The Learning Experence (15th & Bryant Development) | TEDLOCK | WILLIAMS | HAMMOND |  | Preconstruction | No | AG Fifteen RE Holdings, LLC |  | 2021-12-14 | 2022-01-28 | 2021-12-02 | 2022-02-27 | 2022-03-14 | 90 | 30 | 102 | No | 2022-03-12 | 2022-08-31 | 6.3455 | 5.7143 |  |  | Yes | 2860072 | 0 | 0 |  | 250000 | 250000 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 310072 |  | 2860072 | 0
OK2127 | Legacy Martial Arts Shell | TBD | TBD | TBD |  | Preconstruction | No | Don't know |  | No | 2022-06-01 | 2022-06-01 | 2022-07-16 | 2022-07-16 | #VALUE! | 45 | 45 | No | 2022-08-15 | 2023-02-11 14:24 | 6 | 6 |  |  |  | 750000 | 0 | 0 |  | 50000 | 75000 | 130000 | 130000 | 130000 | 130000 | 105000 |  |  |  |  | 750000 | 0
OK2132-1 | Seminole Shell | ENGLAND | STROUD | HAYES |  | Preconstruction | 2022-02-18 | AG Seminole RE Holdings, LLC |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-01 | 2022-02-17 | -1 | 30 | 16 | Yes | 2022-03-07 | 2022-11-02 | 9 | 7.9734 |  |  |  | 1360000 | 0 | 0 | [10 empty] | 1360000 |  | 1360000 | 0
OK2132-2 | Seminole Shell - T-Mobile | ENGLAND | STROUD | HAYES |  | Preconstruction | 2022-02-18 | AG Seminole RE Holdings, LLC |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-16 | 2022-02-17 | -1 | 45 | 16 | Yes | 2022-03-19 | 2022-09-15 14:24 | 5 | 6 |  |  |  | 175000 | 0 | 0 | [10 empty] | 175000 |  | 175000 | 0
OK2132-3 | Seminole Shell - Urgent Care | ENGLAND | STROUD | HAYES |  | Preconstruction | 2022-02-18 | AG Seminole RE Holdings, LLC |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-16 | 2022-02-17 | -1 | 45 | 16 | Yes | 2022-03-19 | 2022-09-15 14:24 | 5 | 6 |  |  |  | 300000 | 0 | 0 | [10 empty] | 300000 |  | 300000 | 0
OK2132-4 | Seminole Shell TBD TI #3 | ENGLAND | STROUD | HAYES |  | Preconstruction | 2022-02-18 | AG Seminole RE Holdings, LLC |  | 2022-02-18 | 2022-01-30 | 2022-06-01 | 2022-03-16 | 2022-07-16 | 148 | 45 | 45 | No | 2022-08-15 | 2022-12-13 09:36 | 5 | 4 |  |  |  | 95000 | 0 | 0 | [10 empty] | 95000 |  | 95000 | 0
OK2134-1 | Glenn Pool Shell | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | 2022-02-18 | TAG Glenpool RE Holdings, LLC |  | 2022-03-14 | 2022-01-30 | 2022-01-15 | 2022-03-01 | 2022-03-14 | 0 | 30 | 58 | No | 2022-03-15 | 2022-12-10 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 | [11 empty] | 2000000 | 2000000 | 0
OKxxxxTI | Glenn Pool Shell - Montap Fyzical Theropy (White Box) | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | Glenpool RE Holdings, LLC |  | 2022-01-05 |  |  |  |  | -44566 | 0 | 0 | No | [8 empty] | 0 | 0 | [12 empty] | 0 | 0
OK2134-2 | TI #1 - Glenn Pool Shell | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | [12 empty] | 0 | 0
OK2134-3 | TI #2 - Glenn Pool Shell | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | [12 empty] | 0 | 0
OK2134-4 | TI #3 - Glenn Pool Shell | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | [12 empty] | 0 | 0
OK2134-5 | TI #4 - Glenn Pool Shell | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | [12 empty] | 0 | 0
OK2134-6 | TI #5 - Glenn Pool Shell | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | [12 empty] | 0 | 0
OK21xx | Norman Shell | ENGLAND | STROUD | CISPER |  | Preconstruction | 2022-02-18 | TAG Norman RE Holdings, LLC |  | 2022-02-24 | 2022-02-09 | 2022-02-01 | 2022-03-26 | 2022-03-01 | 5 | 45 | 28 | Yes | 2022-03-21 | 2022-12-16 21:36 | 9 | 9 |  |  |  | 1200000 | 0 | 0 |  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | [5 empty] | 1200000 | 0
OK21xx | OSB - Norman Shell | ENGLAND | STROUD | CISPER |  | Preconstruction | 2022-02-18 | TAG Norman RE Holdings, LLC |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  | 300000 | 0 | 0 | [11 empty] | 300000 | 300000 | 0
OK21xx | SWIG - Norman Shell | ENGLAND | STROUD | CISPER |  | Preconstruction | 2022-02-18 | TAG Norman RE Holdings, LLC |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | [12 empty] | 0 | 0
OK21xx | TI - Norman Shell | ENGLAND | STROUD | CISPER |  | Preconstruction | 2022-02-18 | TAG Norman RE Holdings, LLC |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | [12 empty] | 0 | 0
OK22xx | 9A Lake Eufalla | SOLOMON | N/A | N/A |  | Preconstruction | No | [7 empty] | 0 | [11 empty] | 0 | 0
Okxxxx | Regent Corner (Fox Lake Similar) | TEDLOCK | RONS | CISPER | Broken Arrow, OK | Preconstruction | No | AG Regent BA RE Holdings, LLC |  | No | 2022-05-01 | 2022-07-10 | 2022-06-30 | 2022-09-08 | #VALUE! | 60 | 60 | No | 2022-10-08 | 2023-10-04 04:48 | 12 | 12 |  |  |  | 14000000 | 0 | 0 | [7 empty] | 1250000 | 1250000 | 1250000 | 1250000 | 9000000 | 14000000 | 0
OKxxxxTI | Yukon Nail Salon (Full Build) | TBD | TBD | HAYES |  | Preconstruction | No | AGRIGGS RE Holdings, LLC |  | 2022-01-05 |  |  |  |  | -44566 | 0 | 0 | No | [8 empty] | 0 | 0 | [12 empty] | 0 | 0
OKxxxxTI | Cross Roads - Broken Arrow - Dr. Shambille (WGS) | TBD | TBD | HAYES | Broken Arrow, OK | Preconstruction | No | AG Broken Arrow RE Holdings, LLC |  | 2021-12-21 |  |  |  |  | -44551 | 0 | 0 | No | [8 empty] | 0 | 0 | [12 empty] | 0 | 0
TX2005 | McKinney Development | TROSPER | DOYLE | CISPER | Virginia and Ridge Road, McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC |  | N/A | 2021-10-01 | 2021-10-01 | 2022-01-14 | 2022-01-14 | #VALUE! | 105 | 105 | No | 2022-04-15 | 2023-01-10 21:36 | 9 | 9 |  |  |  | 600000 | 0 | 0 |  |  | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 120000 |  |  |  | 600000 | 0
TX2008 | Dr. Barbara Lee (McKinney Development) | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No | AG Virginia RE Holdings, LLC |  | Yes | 2021-10-22 | 2022-07-10 | 2022-05-22 | 2022-09-08 | #VALUE! | -49 | 60 | No | 2022-04-15 | 2023-01-10 21:36 | 9 | 9 |  |  |  | 750000 | 0 | 0 |  |  | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 65000 | 145000 |  |  | 750000 | 0
TX2103-1 | McKinney Shell (McKinney Development) | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC |  | Yes | 2022-02-04 | 2022-07-10 | 2022-05-22 | 2022-09-08 | #VALUE! | -49 | 60 | No | 2022-04-15 | 2022-10-12 14:24 | 6 | 6 |  |  |  | 600000 | 0 | 0 |  |  |  |  | 25000 | 50000 | 80000 | 80000 | 80000 | 80000 | 80000 | 125000 | 600000 | 0
TX2103-2 | TBD TI (McKinney Shell) | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC |  | No | 2022-02-04 | 2022-07-10 | 2022-05-05 | 2022-08-24 | #VALUE! | 90 | 45 | No | 2022-09-23 | 2022-12-22 07:12 | 9 | 3 |  |  |  |  | 0 | 0 | [12 empty] | 0 | 0
TX2103-3 | TBD TI (McKinney Shell) | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC |  | No | 2022-02-04 | 2022-07-10 | 2022-05-05 | 2022-08-24 | #VALUE! | 90 | 45 | No | 2022-09-23 | 2022-12-22 07:12 | 9 | 3 |  |  |  |  | 0 | 0 | [12 empty] | 0 | 0
TX2007-1 | Carrollton Shell | TROSPER | DOYLE | CISPER | Carrollton, TX | Preconstruction | 2022-02-18 | AG Carrolton RE Holdings, LLC |  | Yes | 2021-10-28 | 2021-06-15 | 2021-12-17 | 2022-03-15 | #VALUE! | 50 | 273 | No | 2022-03-29 | 2022-12-24 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 |  | 250000 | 25000 | 250000 | 300000 | 300000 | 150000 |  |  |  | 725000 |  | 2000000 | 0
TX2007-2 | Carrolton Shell - Dr. Bui | TROSPER | DOYLE | CISPER | Carrollton, TX | Preconstruction | 2022-02-18 | AG Carrolton RE Holdings, LLC |  | Yes | 2021-11-26 | 2022-07-10 | 2022-02-24 | 2022-09-08 | #VALUE! | 90 | 60 | No | 2022-12-21 | 2023-04-20 09:36 | 4 | 4 |  |  |  | 550000 | 0 | 0 |  | 50000 | 100000 | 150000 | 150000 | 100000 | [6 empty] | 550000 | 0
TX2102-1 | San Antonio Shell | TBD | TBD | HAMMOND | San Antonio, TX | Preconstruction | No | AG 281 RE Holdings, LLC |  | Yes | 2022-02-18 | 2022-02-18 | 2022-02-28 | 2022-05-19 | #VALUE! | 10 | 90 | No | 2022-06-18 | 2023-03-15 21:36 | 9 | 9 |  |  |  | 2229000 | 0 | 0 |  | 125000 | 175000 | 225000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 204000 |  | 2229000 | 0
TX2102-2 | Dr. Abeskharon - San Antonio | TBD | TBD | HAMMOND | San Antonio, TX | Preconstruction | No | AG 281 RE Holdings, LLC |  | Yes | 2021-11-30 | 2022-05-19 | 2022-02-28 | 2022-07-03 | #VALUE! | 90 | 45 | No | 2022-10-01 | 2023-01-29 09:36 | 4 | 4 |  |  |  | 360000 | 0 | 0 |  |  |  | 50000 | 75000 | 125000 | 110000 | [5 empty] | 360000 | 0
| Fayetteville Development | TBD | TBD | HAYES | Fayetteville, AR | Preconstruction | No | AG Fayetteville RE Holdings, LLC |  | 2022-06-10 |  | ? |  |  | -44722 | 0 | #VALUE! | No | [8 empty] | 0 | 0 | [12 empty] | 0
| Cleveland Enhanced Dental | TBD | TBD | HAYES | Cleveland, OK | Preconstruction | No | AG Cleveland RE Holdings, LLC |  | 2022-04-04 |  | 2022-05-09 |  | 2022-05-19 | 45 | 0 | 10 | No | [8 empty] | 0 | 0 | [12 empty] | 0
FL2101 | 248 Blue Mountain Beach | TBD | TBD | NOWELL |  | Preconstruction | No | Blue Mountain RE Holdings, LLC | [6 empty] | 0 |  | 0 | [9 empty] | 96582.13 | 0
| Anna Shell TX | TBD | TBD | HAYES |  | Preconstruction | [5 empty] | 2022-08-19 |  | 2022-09-27 | 44831 |  | 39 |  | 2022-08-15 | [6 empty] | 5000000 | 0 | 0
| Hough Ear - OKC | TBD | TBD | NOWELL |  | Preconstruction | [5 empty] | Q3 |  |  | 0 |  |  |  | 2022-09-15 | [6 empty] | 8000000 | 0 | 0
| Mingee LVM Investments | TBD | TBD | HAMMOND |  | Preconstruction | [5 empty] | Q3 |  |  | 0 | [11 empty] | 0 | 0
| Dr. Kramer - Edmond Family Dental Designs | TBD | TBD | HAMMOND |  | Preconstruction | [5 empty] | Q3 |  |  | 0 | [11 empty] | 0 | 0
| JackBe Santa Fe | [25 empty] | 0 | 0
[27 empty] | 0 | 0 | [12 empty] | 0 | 0
[26 empty] | 60522072 | 96582.13 | 0 | 50000 | 1785000 | 2405000 | 3270000 | 3565000 | 3635000 | 3375000 | 3828000 | 3165000 | 3100000 | 6064072 | 13180000 | 94567134.63 | 34045062.63
0
[22 empty] | Billing Total |  |  |  | 116687957.16 | 32114168.81 | 2519382.66 | 3187706.81 | 5109931.01 | 5888032.73 | 5747660.3 | 6092489.39 | 5700000 | 5335000 | 5653000 | 4221149.15 | 3440000 | 6214072 | 13180000 | 104306010.73 | -12381946.43
[26 empty] | Billing Goal |  | 3500000 | 3500000 | 5000000 | 6000000 | 6825000 | 7100000 | 7100000 | 7000000 | 6500000 | 6500000 | 6500000 | 6500000 | 80000000
[26 empty] | Difference |  | -980617.34 | -312293.19 | 109931.01 | -111967.27 | -1077339.7 | -1007510.61 | -1400000 | -1665000 | -847000 | -2278850.85 | -3060000 | -285928 | -66820000
[39 empty] | 2021 | 45000000
[26 empty] | Rev Actual | [12 empty] | 2022 | 60000000
[26 empty] | Rev Goal |  | 2794050 | [10 empty] | 2023 | 72000000
[26 empty] | Difference |  |  |  | 0.62383 | [8 empty] | 2024 | 86400000
[39 empty] | 2025 | 99360000
[26 empty] | GP Actual | [12 empty] | 2026 | 114264000
[26 empty] | GP Goal |  | 306950 | [10 empty] | 2027 | 131403600
[26 empty] | Difference | [12 empty] | 2028 | 151114140
[39 empty] | 2029 | 173781261
[26 empty] | GP % Actual | [12 empty] | 2030 | 199848450.15
[26 empty] | GP % Goal |  | 10% | [10 empty] | 2031 | 229825717.6725
[26 empty] | Difference | [12 empty] | 2032 | 264299575.3234
[39 empty] | 2033 | 303944511.6219
OH Actual
[26 empty] | OH Goal |  | 300000
Difference
NP Actual
[26 empty] | NP Goal |  | #REF!
Difference
DEAD / HOLD / SOLD | [41 empty] | 0
FL2001 | Elysee Lot 6 | SOLD | SOLD |  | SOLD | SOLD | [5 empty] | SOLD |  | SOLD |  |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD |  | 137906 | [14 empty] | 0 | -137906
FL2002 | Elysee Lot 7 | SOLD | SOLD |  | SOLD | SOLD | [5 empty] | SOLD |  | SOLD |  |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD |  | 136537 | [14 empty] | 0 | -136537
OK1922-1 | Coltrane Corner - Aya Rowe | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK1924 | Yukon Development | HOLD | HOLD |  | HOLD | HOLD | [5 empty] | HOLD |  | HOLD |  |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | [16 empty] | 0 | 0
OK2018 | Dr. Mackey - 61st Street | DEAD | DEAD |  | 9050 E. 61st Street, Tulsa, OK 74145 | HOLD | [5 empty] | HOLD |  | HOLD |  |  | HOLD | Yes | HOLD | HOLD |  | HOLD | HOLD | HOLD |  | 33274 | [14 empty] | 0 | -33274
OK2119 | OSB - Wonga Corner | DEAD | DEAD |  | 1156 S. Douglas, Midwest City, OK 73130 | HOLD | [5 empty] | HOLD |  | HOLD |  |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | [16 empty] | 0 | 0
OK2020-4 | Western - PT Central | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2026 | Covell I35 Edmond Dev. | DEAD | DEAD |  | 5400 E. Covell Road, Edmond, OK | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | Yes | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2028 | Precon - Memorial Park | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 461956 | [14 empty] | 0 | -461956
OK2032-2 | Cross Roads - Dr. Rhodes | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15630 | [14 empty] | 0 | -15630
OK2032-3 | Cross Roads - State Farm | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15000 | [14 empty] | 0 | -15000
OK2032-5 | Cross Roads - Dispensary | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2036 | Dr. Matt Cole, DDS | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 41062 | [14 empty] | 0 | -41062
OK2103 | Bethesda - Santa Fe Dev. | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2105-3 | Valencia - Custom Pools | DEAD | DEAD |  | 2215 NW 178th Street Ste. E, Edmond, OK 73012 | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15493 | [14 empty] | 0 | -15493
OK2109-1 | Grand Blvd. Shell - OKC, OK | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2111 | Solara Surgery Center - Moore, OK | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2115 | Paul's Valley Development | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2117-1 | Paul's Valley Shell | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2117-2 | Paul's Valley Shell - Enhanced Dental | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2118 | Paul's Valley Shell - TBD | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2116 | Dollar Tree (Paul's Valley Development) | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2121 | 15th & Bryant Development | TROSPER | WILLIAMS |  | Combined with OK2122 | Combined | Yes | AG Fifteen RE Holdings, LLC |  | 2021-12-14 | 2022-01-03 | 2022-01-28 | 2022-02-27 | 2022-02-27 |  | 55 | 30 | No | 2022-02-21 | 2022-08-20 14:24 | 6 | 6 |  |  |  | 2860071.9 | 269645.4 |  |  | 125000 | 125000 | 125000 | 105000 |  |  |  |  | 200000 |  |  | 949645.4 | -1910426.5
OK2123 | TBD (15th & Bryant Development) | DEAD | DEAD |  | DEAD | DEAD | No |  |  | DEAD |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | [15 empty] | 0
OK2124 | Bodin Chiro (Lone Oak) | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2126-2 | Weatherford Shell - Dollar Tree | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | HOLD | HOLD |  | HOLD | HOLD | [5 empty] | HOLD |  | HOLD |  |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | [16 empty] | 0 | 0
Okxxxx | Anytime Fitness - Brandon Porter | HOLD | HOLD |  | HOLD | HOLD | No |  |  | DEAD | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | No | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
TNxxxx | AIM Bellevue - Site Visit Needed | PW | TBD |  | 7734 Hwy 70 S. Nashville, TN 37221 | Preconstruction | No | AG AIM Bellevue RE Holdings, LLC |  | 2022-01-31 |  | DEAD | DEAD | DEAD |  | DEAD | DEAD | No | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD |  | 2400000 | [6 empty] | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 2400000 | 0
TX2004 | Marshall Ridge Dev. | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 37392 | [14 empty] | 0 | -37392
TX2009 | Alliance Pediatrics-Marsh | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 3575 | [14 empty] | 0 | -3575
[26 empty] | 6157896.9 |  | 0 | 0 | 125000 | 125000 | 125000 | 355000 | 250000 | 250000 | 250000 | 250000 | 450000 | 250000 | 650000 | 3080000 | -3077896.9
Formulas:
Trevor = [Trevor]+45
Trevor = [Trevor, row above]
Brandon = [Trevor]+15
Brandon = [Brandon]+(6*4.3*7)
Note on B23: Bobby Snyder: Existing Building
Note on O37: Bobby Snyder: Need SS to be moved prior to release of permit.
Note on O43: Bobby Snyder: Variance meeting 2/1. We have earthwork permit in hand.
Note on O46: Bobby Snyder: Need approval on additional parking for GI Alliance 2006-4
Note on M49: Bobby Snyder: Cold dark shell
Note on M52: Bobby Snyder: Get early site release prior to full permit
Note on M54: Trevor Hayes: Site plan application made 2/8. Can not submit until planning commision meeting.
Note on U63: Bobby Snyder: Open and opperating on 10/14/22
Note on O66: Bobby Snyder: We have earthwork permit in hand.
Note on U66: Bobby Snyder: Hard completion date of Aug to prevent LDs
Note on K68: Bobby Snyder: Don't close land until permit is in hand. Land close can be pushed
Note on M68: Bobby Snyder: Push design forward
Note on O68: Trevor Hayes: Demo Permit rcvd 2/9
Note on K72: Bobby Snyder: Don't close loan until permit is in hand Lot Split
Note on O72: Trevor Hayes: Title company needs to file lot split.
Note on K74: Bobby Snyder: Add 6 months to permits on TI
Note on M74: Bobby Snyder: Add 6 months to permits on TI
Note on K79: Bobby Snyder: Don't close loan until permit is in hand
Note on M87: Bobby Snyder: Need a permit from Trevor
Note on M92: Trevor Hayes: Clock Started on 10/28
Note on M94: Bobby Snyder: Need update from Trevor. 3' of undercut over entire site. Need updated Civils to submit to SAWS -Updated civils ready 2/18. - Approvals needed: TCEQ, SAWS, Building Permit
Note on B143: Bobby Snyder: Another GC built out this space.
Note on U159: Bobby Snyder: Hard completion date prior to LDs

## 02 2022
Zach | Peggy | Brandon | Phillip | Bobby | Jenna | Brandon | Trevor | Jenna | Ben | Ben | Trevor | Trevor | Trevor | Trevor | Bobby | Trevor | Trevor | Trevor | Brandon | Brandon | Brandon | Brandon | Peggy | Peggy | Trevor | Trevor |  | 2022 | [11 empty] | 2023
Job Number | Project | PM | SUP | Dev. Director | Address | Status | Turn Over Complete | Entity | LOI | Loan/Lease Close | Anticipated Permit Submission | Actual Permit Submitted | Anticipated Permit Received | Actual Permit Received | Delta Btwn Loan Close and Permit | Anticipated Permit Duration | Permit Approval Duration | Permit Received | Start Date | Comp Date | Planned Duration | Actual Duration | Punchlist Complete Date | Lessons Learned | Appraisal Budget Approved | Appraisal Value | Previously Billed | January 2022 | February 2022 | March 2022 | April 2022 | May 2022 | June 2022 | July 2022 | August 2022 | September 2022 | October 2022 | November 2022 | December 2022 | Annual 2023 | TOTAL | DELTA | COMMENTS
Adam England |  | ENGLAND
OK2019 | Santa Fe Development | ENGLAND | STROUD | N/A | 100 Southwest 134th Street, OKC, OK 73170 | Construction | Yes | AG Santa Fe RE Holdings, LLC |  | Yes | 2021-02-16 | 2021-02-16 | 2021-04-16 | 2021-04-16 | #VALUE! | 59 | 59 | Yes | 2021-05-03 | 2022-01-10 | 8.3721 | 8.3721 |  |  | Yes | 1181869.7 | 1013323.83 | 59705.08 | 0 | [11 empty] | 1073028.91 | -108840.79 | Water meter issues
OK2025 | Autism in Motion - Santa Fe Dev. | ENGLAND | WILLIAMS | N/A | 112 Southwest 134th Street, OKC, OK 73170 | Construction | Yes | AG AIM OK RE Holdings, LLC |  | Yes | 2021-01-05 | 2021-01-05 | 2021-04-16 | 2021-04-16 | #VALUE! | 101 | 101 | Yes | 2021-08-07 | 2022-01-25 | 5.1827 | 5.6811 |  |  | Yes | 1051400.45 | 987033.51 | 64366.94 | 0 | [11 empty] | 1051400.45 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | ENGLAND | STROUD | N/A | 112 Southwest 134th Street, OKC, OK 73170 | Construction | Yes | AG Santa Fe RE Holdings, LLC |  | Yes | 2021-06-15 | 2021-06-15 | 2021-08-10 | 2021-08-10 | #VALUE! | 56 | 56 | Yes | 2021-07-05 | 2022-01-28 | 6.8771 | 6.8771 |  |  | Yes | 1367413.55 | 864219.08 | 83841.4 | 12631.18 | [11 empty] | 960691.66 | -406721.89
OK2033-2 | Santa Fe Dev. - Old School Bagel | ENGLAND | STROUD | N/A | 112 SW 134th Street, Oklahoma City, OK | Construction | Yes | AG Santa Fe RE Holdings, LLC |  | Yes | 2021-06-20 | 2021-06-20 | 2021-12-03 | 2021-12-03 | #VALUE! | 166 | 166 | Yes | 2021-11-17 | 2022-05-23 | 3 | 6.2126 |  |  | Yes | 272915 | 139535.14 | 39753.44 | 25717.67 | 25000 | 25000 | 18626.42 | [8 empty] | 273632.67 | 717.67
OK2110-1 | Shawnee Shell - Shawnee, OK | ENGLAND | STROUD | N/A | 4797 N. Harrison, Shawnee, OK 74804 | Construction | Yes | AG Harrison RE Holdings, LLC |  | Yes | 2021-07-14 | 2021-07-14 | 2021-09-17 | 2021-09-17 | #VALUE! | 65 | 65 | Yes | 2021-11-30 | 2022-05-25 | 5.0166 | 5.8472 |  |  | Yes | 1180416.18 | 488349.41 | 162144.05 | 91072.9 | 150000 | 150000 | 75000 | 4922.72 | [7 empty] | 1121489.08 | -58927.1
OK2110-2 | Shawnee Shell - Old School Bagel | ENGLAND | STROUD | N/A | 4799 N. Harrison, Shawnee, OK 74804 | Construction | Yes | AG Harrison RE Holdings, LLC |  | Yes | 2021-11-08 | 2021-11-08 | 2021-12-09 | 2021-12-09 | #VALUE! | 31 | 31 | Yes | 2022-02-17 | 2022-06-01 | 3 | 3.4551 |  |  | Yes | 253338.08 | 95915.97 | 0 | 69507.91 | 40000 | 40000 | 25000 | 12422.11 | [7 empty] | 282845.99 | 29507.91
OK2110-3 | Shawnee Shell - OSO | ENGLAND | STROUD | N/A | 4795 N. Harrison, Shawnee, OK 74804 | Construction | Yes | AG Harrison RE Holdings, LLC |  | Yes | 2021-12-06 | 2021-12-06 | 2022-01-14 | 2022-01-28 | #VALUE! | 39 | 53 | Yes | 2022-02-14 | 2022-05-11 | 3.5548 | 2.8571 |  |  | Yes | 402660.29 | 34445.59 | 0 | 54102 | 75000 | 75000 | 75000 | 68214.7 | [7 empty] | 381762.29 | -20898
OK2128 | 150th and Penn - Old School Bagel | ENGLAND | WILLIAMS | N/A | 15201 N. Penn Crossing Court, Oklahoma City, OK 73013 | Construction | Yes | TAG Penn OSB RE Holdings,LLC |  | 2022-03-18 | 2022-01-19 | 2022-02-01 | 2022-03-05 | 2022-03-18 | 0 | 45 | 45 |  | 2022-04-02 | 2022-09-29 14:24 | 6 | 6 |  |  |  | 750000 | 0 | 0 | 0 | 125000 | 125000 | 150000 | 150000 | 140000 | 60000 | [5 empty] | 750000 | 0
OK2129 | Chamberlain Group (SFD) | ENGLAND | STROUD | N/A | 113 SW 134th Street, Oklahoma City, OK | Construction | Yes | AG Chamberlain RE Holdings, LLC |  | Yes | 2021-11-12 | 2021-11-12 | 2022-01-06 | 2021-12-30 | #VALUE! | 55 | 48 | Yes | 2022-01-11 | 2022-09-01 | 7 | 7.7409 |  |  | Yes | 1353098.44 | 86613.87 | 120514.88 | 152425.42 | 150000 | 150000 | 150000 | 150000 | 175000 | 175000 | 45969.69 |  |  |  |  | 1355523.86 | 2425.42
TN2101 | AIM - Memphis, TN | ENGLAND | N/A | N/A | 7007 Stage Rd., Memphis, TN 38133 | Construction | Yes | AG AIM Memphis RE Holdings, LLC |  | Yes | 2021-06-18 | 2021-06-18 | 2021-10-20 | 2021-10-20 | #VALUE! | 124 | 124 | Yes | 2021-11-04 | 2022-03-31 | 4.8837 | 4.8837 |  |  | Yes | 1207444.74 | 527222.16 | 0 | 255699 | 350000 | 30222.58 | [9 empty] | 1163143.74 | -44301
[26 empty] | 9020556.43 | 4236658.56 | 530325.79 | 661156.08 | 915000 | 595222.58 | 493626.42 | 385559.53 | 315000 | 235000 | 45969.69 | 0 | 0 | 0 | 0 | 8413518.65 | -607037.78
Kyle Tedlock |  | TEDLOCK
OK1923-6 | Riverwest - Old School Bagel | TEDLOCK | RONS | HAYES | 152 W Alexander Blvd., Sand Springs, OK 74063 | Construction | Yes | Riverwest RE Holdings, LLC |  | Yes | 2021-06-01 | 2021-06-01 | 2021-06-15 | 2021-06-15 | #VALUE! | 14 | 14 | Yes | 2021-05-28 | 2021-10-28 | 5 | 5.0831 |  |  | Yes | 89125 | 58100 | 0 | 0 | [11 empty] | 58100 | -31025
OK1936 | Dr Fischer | TEDLOCK | RONS | N/A | 720 West 71St Street S, Tulsa, OK 74132 | Construction | Yes | AG Medical RE Holdings ,LLC |  | Yes | 2020-04-08 | 2020-04-08 | 2020-06-22 | 2020-06-22 | #VALUE! | 75 | 75 | Yes | 2020-06-22 | 2021-09-30 | 15 | 15.4485 |  |  | Yes | 2482029.51 | 2482029.51 | 0 | 0 | [11 empty] | 2482029.51 | 0
OK2008 | Dr. Gaches | TEDLOCK | RONS | N/A | 11492 N. 137th E. Ave., Owasso, OK | Construction | Yes | AG Hi Point RE Holdings, LLC |  | Yes | 2020-08-28 | 2020-08-28 | 2021-03-05 | 2021-03-05 | #VALUE! | 189 | 189 | Yes | 2021-04-04 | 2021-10-15 | 6 | 6.4452 |  |  | Yes | 712367.43 | 712367.43 | 0 | 0 | [11 empty] | 712367.43 | 0
OK2014 | Clark Plaza Shell | TEDLOCK | RONS | N/A | 7877 E 71st South., Tulsa, OK 74133 | Construction | Yes | AG Clark RE Holdings, LLC |  | Yes | 2020-10-16 | 2020-10-16 | 2021-02-19 | 2021-02-19 | #VALUE! | 126 | 126 | Yes | 2021-03-01 | 2021-12-27 | 10 | 10 |  |  | Yes | 1436404.19 | 1436404.19 | 0 | 0 | [11 empty] | 1436404.19 | 0
OK2014-1 | Clark Shell - Dr. Pfeffer | TEDLOCK | RONS | N/A | 7877 E 71st South Ste A, Tulsa, OK 74133 | Construction | Yes | AG Clark RE Holdings, LLC |  | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | #VALUE! | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 19:12 | 8 | 8 |  |  | Yes | 648252.98 | 648252.98 | 0 | 0 | [11 empty] | 648252.98 | 0
OK2014-2 | Clark Shell - Enhance DDS | TEDLOCK | RONS | N/A | 7877 E 71st South Ste B., Tulsa, OK 74133 | Construction | Yes | AG Clark RE Holdings, LLC |  | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | #VALUE! | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 | 8 | 7.9734 |  |  | Yes | 400186.6 | 400186.6 | 0 | 0 | [11 empty] | 400186.6 | 0
OK2016 | OneCore | TEDLOCK | HALL | N/A | 100 NE 85th Street, OKC, OK 73114 | Construction | Yes | TAG OneCore RE Holdings, LLC |  | Yes | 2020-08-11 | 2020-08-11 | 2020-11-12 | 2020-11-12 | #VALUE! | 93 | 93 | Yes | 2020-10-15 | 2021-12-01 | 14 | 13.6877 |  |  | Yes | 14188397.56 | 13413397.56 | 812671.7 | 0 | [11 empty] | 14226069.26 | 37671.7
OK2032-1 | Cross Roads - Shell | TEDLOCK | RONS | N/A | 1167 N. 38th Street, Broken Arrow, OK 74014 | Construction | Yes | AG Broken Arrow RE Holdings, LLC |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | TEDLOCK | RONS | N/A | 1171 N. 38th Street, Broken Arrow, OK 74014 | Construction | Yes | AG Broken Arrow RE Holdings, LLC |  | Yes | 2021-08-09 | 2021-08-09 | 2021-08-10 | 2021-08-10 | #VALUE! | 1 | 1 | Yes | 2021-10-01 | 2022-03-08 | 4 | 5.2492 |  |  | Yes | 295011.29 | 264663.85 | 0 | 0 | 15347.44 | [10 empty] | 280011.29 | -15000
[26 empty] | 20251774.56 | 19415402.12 | 812671.7 | 0 | 15347.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20243421.26 | -8353.3
Kimberly Kelly |  | KELLY | [39 empty] | 0
TX1903 | Ramon Franklin Warehouse | KELLY | MILLER | N/A | 1308 Corporate Drive East, Arlinton, TX 76006 | Construction | Yes | Don't Own |  | N/A | 2020-12-09 | 2020-12-09 | 2021-01-27 | 2021-01-27 | #VALUE! | 49 | 49 | Yes | 2021-07-05 | 2021-12-10 | 5 | 5.2492 |  |  | Yes | 1006578.9 | 1006578.9 | 0 | 413409.04 | [11 empty] | 1419987.94 | 413409.04
TX2101 | Bob Mills - Forth Worth | KELLY | JOHNSON | N/A | 3600 East Long Ave., Ft Worth, TX 76111 | Construction | Yes | Don't Own |  | N/A | 2021-04-09 | 2021-04-09 | 2021-06-10 | 2021-06-10 | #VALUE! | 62 | 62 | Yes | 2021-07-10 | 2021-12-10 | 5 | 5.0831 |  |  | Yes | 2315782.2 | 2304152.2 | 38625.5 | 0 | [11 empty] | 2342777.7 | 26995.5
[26 empty] | 3322361.1 | 3310731.1 | 38625.5 | 413409.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762765.64 | 440404.54
Tiffany Shiel |  | SHIEL | [39 empty] | 0
OK2106-1 | Fox Lake Shell | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Construction | Yes | TAG Fox Lake RE Holdings, LLC |  | Yes | 2021-06-22 | 2021-06-22 | 2021-09-22 | 2021-09-22 | #VALUE! | 92 | 92 | Yes | 2021-07-22 | 2022-11-15 | 13 | 15.9801 |  |  | Yes | 12193746.8 | 3069014.06 | 532188.35 | 1527507.98 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 592544.39 |  |  |  | 12721254.78 | 527507.98
[26 empty] | 12193746.8 | 3069014.06 | 532188.35 | 1527507.98 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 592544.39 | 0 | 0 | 0 | 12721254.78 | 527507.98
Bob Solomon |  | SOLOMON | [39 empty] | 0
OK2034 | Dr. Rex Johnson, DVM - Covell I35 | SOLOMON | WILLIAMS | N/A | 5401 E. Covel Rd., Edmond, OK 73034 | Construction | Yes | AG Waterloo RE Holdings, LLC |  | Yes | 2021-05-12 | 2021-05-12 | 2021-08-10 | 2021-08-10 | #VALUE! | 90 | 90 | Yes | 2021-08-16 | 2022-05-20 | 9 | 9.2027 |  |  | Yes | 1961015.83 | 952423.73 | 173273.61 | 93239.18 | 200000 | 200000 | 150000 | 85318.49 | [7 empty] | 1854255.01 | -106760.82
OK2112 | Covell 35 Dev. - Dr. Lu Dentistry | SOLOMON | WILLIAMS | N/A | 5249 E. Covel Rd., Edmond, OK 73034 | Construction | Yes | AG Medical RE Holdings, LLC |  | Yes | 2021-10-20 | 2021-10-20 | 2021-12-10 | 2021-12-10 | #VALUE! | 51 | 51 | Yes | 2021-12-22 | 2022-06-30 | 9 | 6.3123 |  |  | Yes | 762952.96 | 92185.59 | 111281.22 | 64974.74 | 125000 | 125000 | 125000 | 84486.15 | [7 empty] | 727927.7 | -35025.26
OK2113 | Carlton Landing Sewer - Eufaula, OK | SOLOMON | N/A | N/A |  | Construction | Yes | Jenna check with cassidy - CL Holding? |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No |  |  | 0 | 0 |  |  | No | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2125-1 | Enid Shell | TEDLOCK | RONS | N/A |  | Construction | Yes | AG Enid RE Holdings, LLC |  | 2022-01-13 | 2021-12-13 | 2022-01-14 | 2022-01-17 | 2022-02-23 | 41 | 35 | 40 | Yes | 2022-02-28 | 2022-09-16 | 9 | 6.6445 |  |  |  | 1500000 | 0 | 0 | 192361.11 | 50000 | 100000 | 150000 | 175000 | 175000 | 175000 | 175000 | 175000 | 175000 | 150000 |  | 1692361.11 | 192361.11
OK2125-2 | Enid - Old School Bagel | TEDLOCK | RONS | N/A |  | Preconstruction | No | AG Enid RE Holdings, LLC |  | 2022-01-13 | 2022-01-14 | 2022-02-18 | 2022-02-28 | 2022-03-16 | 62 | 45 | 26 | Yes | 2022-06-14 | 2022-10-12 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 | 0 | 150000 | 150000 | 50000 | [8 empty] | 350000 | 0
OK2125-3 | Enid - Enhanced Dental | TEDLOCK | RONS | N/A |  | Preconstruction | No | AG Enid RE Holdings, LLC |  | 2022-01-13 | 2022-01-14 | 2022-02-18 | 2022-02-28 | 2022-03-16 | 62 | 45 | 26 | Yes | 2022-06-24 | 2022-10-22 09:36 | 4 | 4 |  |  |  | 450000 | 0 | 0 | 0 |  | 50000 | 75000 | 75000 | 75000 | 75000 | 75000 | 25000 |  |  |  | 450000 | 0
[26 empty] | 5023968.79 | 1044609.32 | 284554.83 | 350575.03 | 525000 | 625000 | 550000 | 419804.64 | 250000 | 250000 | 250000 | 200000 | 175000 | 150000 | 0 | 5074543.82 | 50575.03
Kevin Trosper |  | TROSPER | [39 empty] | 0
OK2105-3 | Valencia - Winfield and Co. | TROSPER | TROSPER | N/A | 2216 NW 178th Street Ste. E, Edmond, OK 73012 | Construction | Yes | AG Valencia RE Holdings, LLC |  | Yes | 2021-09-01 | 2021-09-01 | 2021-09-16 | 2021-09-16 | #VALUE! | 15 | 15 |  | 2021-09-22 | 2021-10-17 | 1 | 0.83056 |  |  | Yes | 27626.4 | 11493 | 16133.4 | 0 | [11 empty] | 27626.4 | 0
OK2108 | Puppy Paws - Lone Oak | TROSPER | WILLIAMS | HAYES | 15200 Crown at Lone Oak, Edmond OK 73013 | Construction | Yes | AG Puppy West RE Holdings, LLC |  | Yes | 2021-11-19 | 2021-11-19 | 2022-01-06 | 2022-02-14 | #VALUE! | 48 | 87 | Yes | 2022-02-21 | 2022-11-30 | 9 | 9.3688 |  |  |  | 2200000 | 0 | 0 | 212179 | 225000 | 250000 | 275000 | 300000 | 250000 | 250000 | 250000 | 200000 |  |  |  | 2212179 | 12179
OK2126-1 | Weatherford Shell | TROSPER | STEPHENSON | N/A |  | Construction | Yes | AG Weatherford RE Holdings, LLC |  | 2022-01-14 | 2021-12-13 | 2022-01-14 | 2022-01-13 | 2022-01-21 | 7 | 31 | 7 | Yes | 2022-02-14 | 2022-08-19 | 8 | 6.1794 |  |  |  | 1200000 | 0 | 0 | 240339.48 | 75000 | 150000 | 150000 | 200000 | 200000 | 200000 | 175000 |  |  |  |  | 1390339.48 | 190339.48
OK2126-3 | Weatherford Shell - Enhanced Dental | TROSPER | STEPHENSON | N/A |  | Preconstruction | No | AG Weatherford RE Holdings, LLC |  | 2022-01-14 | 2021-12-30 | 2022-02-16 | 2022-03-16 | 2022-03-23 | 68 | 76 | 35 | No | 2022-05-27 | 2022-09-24 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 | 0 | 50000 | 75000 | 100000 | 100000 | 25000 | [6 empty] | 350000 | 0
TX2006-1 | Sunnyvale Shell | TROSPER | DOYLE | N/A | 480 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | AG Sunnyvale RE Holdings, LLC |  | Yes | 2021-06-22 | 2021-06-22 | 2021-11-09 | 2021-11-09 | #VALUE! | 140 | 140 | Yes | 2021-11-17 | 2022-06-01 | 7 | 6.5116 |  |  | Yes | 1910049.56 | 892016.83 | 304883.09 | 284226.25 | 300000 | 113149.64 | [9 empty] | 1894275.81 | -15773.75
TX2006-2 | Sunnyvale Shell - Dr. Luna | TROSPER | DOYLE | N/A | 481 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | AG Sunnyvale RE Holdings, LLC |  | Yes | 2021-12-21 | 2021-12-13 | 2022-01-27 | 2022-01-24 | #VALUE! | 37 | 42 | Yes | 2022-02-07 | 2022-07-02 | 3 | 4.8173 |  |  | Yes | 288979.2 | 17537.69 | 0 | 0 | 90000 | 90000 | 31441.51 | [8 empty] | 228979.2 | -60000
TX2006-3 | Sunnyvale Shell - Dr. Rohani | TROSPER | DOYLE | N/A | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | AG Sunnyvale RE Holdings, LLC |  | Yes | 2021-12-21 | 2021-12-29 | 2022-02-04 | 2022-01-24 | #VALUE! | 45 | 26 | Yes | 2022-02-07 | 2022-07-02 | 3 | 4.8173 |  |  | Yes | 376822.32 | 20124 | 0 | 0 | 75000 | 75000 | 75000 | 56698.32 | [7 empty] | 301822.32 | -75000
TX2006-4 | Sunnyvale Shell - GI Alliance | TROSPER | DOYLE | N/A | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction | Yes | AG Sunnyvale RE Holdings, LLC |  | Yes | 2021-12-21 | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0 | 0 | 0 | [11 empty] | 0 | 0
[26 empty] | 6353477.48 | 941171.52 | 321016.49 | 736744.73 | 815000 | 753149.64 | 631441.51 | 656698.32 | 475000 | 450000 | 425000 | 200000 | 0 | 0 | 0 | 6405222.21 | 51744.73
Preconstruction | [41 empty] | 0
OK1925 | Glenn Pool - Old School Bagel Express (Stand Alone) | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool OSB RE Holdings,LLC |  | 2022-04-05 | 2022-02-09 | 2022-03-31 | 2022-02-28 | 2022-04-30 | 25 | 19 | 30 | No | 2022-04-30 | 2022-09-27 | 2.5249 | 4.9834 |  |  |  | 725000 | 0 | 0 | #REF! | [9 empty] | 725000 |  | #REF! | #REF!
OK2037 | Master Hand Milling | TBD | TBD | TBD | TBD, Edmond, OK | Preconstruction | No | TBD |  | No | 2022-06-01 | 2022-06-01 | 2022-07-16 | 2022-07-16 | #VALUE! | 45 | 45 | No | 2022-08-15 | 2023-08-11 04:48 | 12 | 12 |  |  |  | 4000000 | 0 | 0 | 0 | 200000 | 250000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 830000 | 4000000 | 0
OK2102 | Puppy Paws East Edmond | TROSPER | TBD | HAYES | East Edmond | Preconstruction | No | AG Puppy Covell RE Holdings, LLC |  | 2022-03-21 | 2022-02-05 | 2022-04-05 | 2022-04-16 | 2022-06-04 | 75 | 70 | 60 | No | 2022-05-01 | 2023-01-26 21:36 | 9 | 9 |  |  |  | 2200000 | 0 | 0 | 0 | 150000 | 200000 | 260000 | 260000 | 300000 | 300000 | 260000 | 260000 | 210000 |  |  | 2200000 | 0
OK2106-2 | Fox Lake - Sidecar | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-05-09 | 2022-05-09 | 2022-02-17 | 2022-06-23 | #VALUE! | -81 | 45 | No | 2022-07-01 | 2022-12-28 14:24 | 6 | 6 |  |  |  | 980000 | 0 | 0 | 0 | 50000 | 100000 | 125000 | 150000 | 200000 | 200000 | 155000 |  |  |  |  | 980000 | 0
OK2106-3 | Fox Lake - Hatch | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-05-09 | 2022-05-09 | 2022-02-17 | 2022-06-23 | #VALUE! | -81 | 45 | No | 2022-07-01 | 2022-12-28 14:24 | 6 | 6 |  |  |  | 1558000 | 0 | 0 | 0 | 50000 | 125000 | 225000 | 300000 | 300000 | 300000 | 258000 |  |  |  |  | 1558000 | 0
OK2106-4 | Fox Lake - Enhanced Dental | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-03-02 | 2022-03-02 | 2022-03-03 | 2022-04-01 | #VALUE! | 1 | 30 | No | 2022-05-01 | 2022-10-28 14:24 | 6 | 6 |  |  |  | 540000 | 0 | 0 | 0 | 25000 | 75000 | 90000 | 100000 | 100000 | 100000 | 50000 |  |  |  |  | 540000 | 0
OK2106-5 | Fox Lake - Chicago Title | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-04-11 | 2022-04-11 | 2022-02-17 | 2022-05-26 | #VALUE! | -53 | 45 | No | 2022-04-01 | 2022-09-28 14:24 | 6 | 6 |  |  |  | 800000 | 0 | 0 | 0 | 75000 | 125000 | 125000 | 150000 | 150000 | 125000 | 50000 |  |  |  |  | 800000 | 0
OK2106-6 | Fox Lake Provision Concepts | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-05-09 | 2022-05-09 | 2022-02-17 | 2022-06-23 | #VALUE! | -81 | 45 | No | 2022-04-01 | 2022-09-28 14:24 | 6 | 6 |  |  |  | 690000 | 0 | 0 | 0 | 50000 | 100000 | 120000 | 120000 | 120000 | 120000 | 60000 |  |  |  |  | 690000 | 0
OK2106-7 | Fox Lake TBD |  |  | HAMMOND | 852 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes |  | 2022-05-09 |  | 2022-06-23 | #VALUE! |  | 45 | No | [8 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2106-8 | Fox Lake Chicken Foote |  |  | HAMMOND | 853 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-05-09 | 2022-05-09 |  | 2022-06-23 | #VALUE! |  | 45 | No | [8 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2106-9 | Fox Lake Regent Bank |  |  | HAMMOND | 854 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | TAG Fox Lake RE Holdings, LLC |  | Yes | 2022-05-09 | 2022-05-09 |  | 2022-06-23 | #VALUE! |  | 45 | No | [8 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2107 | Jack Be Grocery | SOLOMON | STRUB | CISPER | 855 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No | AG May RE Holdings, LLC |  | 2022-03-11 | 2022-01-31 | 2022-02-03 | 2022-03-17 | 2022-05-04 | 54 | 45 | 90 | No | 2022-05-04 | 2022-10-31 14:24 | 6 | 6 |  |  |  | 2500000 | 0 | 0 | 0 | 75000 | 125000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 700000 | 2500000 | 0
OK2114-1 | Chamberlain Realty - Lone Oak | TBD | TBD | HAYES | 15103 Crown at Lone Oak Rd., Edmond, OK 73013 | Preconstruction | No | AG Chamberlain West RE Holdings, LLC |  | 2022-06-01 | 2022-04-17 | 2022-04-17 | 2022-06-01 | 2022-06-01 | 0 | 45 | 45 | No | 2022-06-01 | 2022-11-28 14:24 | 6 | 6 |  |  |  | 400000 | 0 | 0 | 0 | 75000 | 75000 | 100000 | 75000 |  |  |  |  | 25000 |  |  | 350000 | -50000
OK2120 | Peak View Brewery and Distillery | TBD | TBD | TBD | Reservoir by Costco | Preconstruction | No | Don't know |  | 2022-04-01 | 2022-04-17 | 2022-04-17 | 2022-06-01 | 2022-06-01 | 61 | 45 | 45 | No | 2022-06-01 | 2023-03-29 | 10 | 10 |  |  |  | 3000000 | 0 | 0 | 0 | 125000 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 225000 | 3000000 | 0
OK2122 | The Learning Experence (15th & Bryant Development) | TEDLOCK | WILLIAMS | HAMMOND |  | Preconstruction | No | AG Fifteen RE Holdings, LLC |  | 2021-12-14 | 2022-01-28 | 2021-12-02 | 2022-02-27 | 2022-03-21 | 97 | 30 | 109 | No | 2022-03-21 | 2022-08-31 | 6.3455 | 5.4153 |  |  | Yes | 2860072 | 0 | 0 | 125981 | 250000 | 250000 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 310072 |  | 2986053 | 125981
OK2127 | Legacy Martial Arts Shell | TBD | TBD | TBD |  | Preconstruction | No | Don't know |  | No | 2022-06-01 | 2022-06-01 | 2022-07-16 | 2022-07-16 | #VALUE! | 45 | 45 | No | 2022-08-15 | 2023-02-11 14:24 | 6 | 6 |  |  |  | 750000 | 0 | 0 | 0 | 50000 | 75000 | 130000 | 130000 | 130000 | 130000 | 105000 |  |  |  |  | 750000 | 0
OK2132-1 | Seminole Shell | ENGLAND | STROUD | HAYES |  | Constuction | 2022-02-23 | AG Seminole RE Holdings, LLC |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-01 | 2022-02-17 | -1 | 30 | 16 | Yes | 2022-03-16 | 2022-11-02 | 9 | 7.6744 |  |  |  | 1360000 | 0 | 0 | 170543 | [9 empty] | 1360000 |  | 1530543 | 170543
OK2132-2 | Seminole Shell - T-Mobile | ENGLAND | STROUD | HAYES |  | Constuction | 2022-02-23 | AG Seminole RE Holdings, LLC |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-16 | 2022-02-17 | -1 | 45 | 16 | Yes | 2022-05-03 | 2022-10-30 14:24 | 5 | 6 |  |  |  | 175000 | 0 | 0 | 0 | [9 empty] | 175000 |  | 175000 | 0
OK2132-3 | Seminole Shell - Urgent Care | ENGLAND | STROUD | HAYES |  | Constuction | 2022-02-23 | AG Seminole RE Holdings, LLC |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-16 | 2022-02-17 | -1 | 45 | 16 | Yes | 2022-05-03 | 2022-10-30 14:24 | 5 | 6 |  |  |  | 300000 | 0 | 0 | 0 | [9 empty] | 300000 |  | 300000 | 0
OK2132-4 | Seminole Shell TBD TI #3 | ENGLAND | STROUD | HAYES |  | Constuction | 2022-02-23 | AG Seminole RE Holdings, LLC |  | 2022-02-18 | 2022-01-30 | 2022-06-01 | 2022-03-16 | 2022-07-16 | 148 | 45 | 45 | No | 2022-08-15 | 2022-12-13 09:36 | 5 | 4 |  |  |  | 95000 | 0 | 0 | 0 | [9 empty] | 95000 |  | 95000 | 0
OK2134-1 | Glenn Pool Shell | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-04-30 | 2022-01-30 | 2022-01-15 | 2022-03-01 | 2022-04-30 | 0 | 30 | 105 | No | 2022-04-30 | 2023-01-25 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 | 0 | [10 empty] | 2000000 | 2000000 | 0
OKxxxxTI | Glenn Pool Shell - Montap Fyzical Theropy (White Box) | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | Glenpool RE Holdings, LLC |  | 2022-01-05 |  |  |  |  | -44566 | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2134-2 | Glenn Pool Shell - TI #1 | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2134-3 | Glenn Pool Shell - TI #2 | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2134-4 | Glenn Pool Shell - TI #3 | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2134-5 | Glenn Pool Shell - TI #4 | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2134-6 | Glenn Pool Shell - TI #5 | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No | TAG Glenpool RE Holdings, LLC |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-02-13 | 2022-07-29 | 45 | -121 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2135-1 | Norman Shell | ENGLAND | STROUD | CISPER |  | Preconstruction | 2022-03-01 | TAG Norman RE Holdings, LLC |  | 2022-02-24 | 2022-02-09 | 2022-02-01 | 2022-03-26 | 2022-03-11 | 15 | 45 | 38 | Yes | 2022-03-31 | 2022-12-26 21:36 | 9 | 9 |  |  |  | 1200000 | 0 | 0 | 129788.5 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | [5 empty] | 1329788.5 | 129788.5
OK2135-2 | Norman Shell - TI | ENGLAND | STROUD | CISPER |  | Preconstruction | TBD | TAG Norman RE Holdings, LLC |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 0 | 0
OK2135-3 | Norman Shell - Old School Bagel | ENGLAND | STROUD | CISPER |  | Constuction | 2022-03-01 | TAG Norman RE Holdings, LLC |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  | 300000 | 0 | 0 | 0 | [10 empty] | 300000 | 300000 | 0
OK2135-4 | Norman Shell - SWIG | ENGLAND | STROUD | CISPER |  | Preconstruction | TBD | TAG Norman RE Holdings, LLC |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 0 | 0
OK22xx | 9A Lake Eufalla | SOLOMON | N/A | N/A |  | Preconstruction | No | [7 empty] | 0 | [11 empty] | 0 | 0 | 0 | [12 empty] | 0
Okxxxx | Regent Corner (Fox Lake Similar) | TEDLOCK | RONS | CISPER | Broken Arrow, OK | Preconstruction | No | AG Regent BA RE Holdings, LLC |  | No | 2022-05-01 | 2022-05-01 | 2022-06-30 | 2022-06-30 | #VALUE! | 60 | 60 | No | 2022-07-30 | 2023-07-26 04:48 | 12 | 12 |  |  |  | 14000000 | 0 | 0 | 0 | [6 empty] | 1250000 | 1250000 | 1250000 | 1250000 | 9000000 | 14000000 | 0
OKxxxxTI | Yukon Nail Salon (Full Build) | TBD | TBD | HAYES |  | Preconstruction | No | AGRIGGS RE Holdings, LLC |  | 2022-01-05 |  |  |  |  | -44566 | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
OKxxxxTI | Cross Roads - Broken Arrow - Dr. Shambille (WGS) | TBD | TBD | HAYES | Broken Arrow, OK | Preconstruction | No | AG Broken Arrow RE Holdings, LLC |  | 2021-12-21 |  |  |  |  | -44551 | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
TX2005 | McKinney Development | TROSPER | DOYLE | CISPER | Virginia and Ridge Road, McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC |  | N/A | 2021-10-01 | 2021-10-01 | 2022-01-14 | 2022-01-14 | #VALUE! | 105 | 105 | No | 2022-04-15 | 2023-01-10 21:36 | 9 | 9 |  |  |  | 600000 | 0 | 0 | 0 |  | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 120000 |  |  |  | 600000 | 0
TX2008 | Dr. Barbara Lee (McKinney Development) | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No | AG Virginia RE Holdings, LLC |  | Yes | 2021-10-22 | 2022-03-23 | 2022-05-22 | 2022-05-22 | #VALUE! | 60 | 60 | No | 2022-04-15 | 2023-01-10 21:36 | 9 | 9 |  |  |  | 750000 | 0 | 0 | 0 |  | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 65000 | 145000 |  |  | 750000 | 0
TX2103-1 | McKinney Shell (McKinney Development) | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC |  | Yes | 2022-02-04 | 2022-03-23 | 2022-05-22 | 2022-05-22 | #VALUE! | 60 | 60 | No | 2022-04-15 | 2022-10-12 14:24 | 6 | 6 |  |  |  | 600000 | 0 | 0 | 0 |  |  |  | 25000 | 50000 | 80000 | 80000 | 80000 | 80000 | 80000 | 125000 | 600000 | 0
TX2103-2 | TBD TI (McKinney Shell) | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC |  | Yes | 2022-02-04 | 2022-05-01 | 2022-05-05 | 2022-06-15 | #VALUE! | 90 | 45 | No | 2022-07-15 | 2022-10-13 07:12 | 9 | 3 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 0 | 0
TX2103-3 | TBD TI (McKinney Shell) | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No | AG Virginia Ridge RE Holdings, LLC |  | Yes | 2022-02-04 | 2022-05-01 | 2022-05-05 | 2022-06-15 | #VALUE! | 90 | 45 | No | 2022-07-15 | 2022-10-13 07:12 | 9 | 3 |  |  |  |  | 0 | 0 | 0 | [11 empty] | 0 | 0
TX2007-1 | Carrollton Shell | TROSPER | DOYLE | CISPER | Carrollton, TX | Preconstruction | 2022-03-25 | AG Carrolton RE Holdings, LLC |  | Yes | 2021-10-28 | 2021-06-15 | 2021-12-17 | 2022-03-15 | #VALUE! | 50 | 273 | No | 2022-03-29 | 2022-12-24 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 | 210901.5 | 250000 | 25000 | 250000 | 300000 | 300000 | 150000 |  |  |  | 725000 |  | 2210901.5 | 210901.5
TX2007-2 | Carrolton Shell - Dr. Bui | TROSPER | DOYLE | CISPER | Carrollton, TX | Preconstruction | 2022-03-25 | AG Carrolton RE Holdings, LLC |  | Yes | 2021-11-26 | 2022-03-16 | 2022-02-24 | 2022-05-15 | #VALUE! | 90 | 60 | No | 2022-08-27 | 2022-12-25 09:36 | 4 | 4 |  |  |  | 550000 | 0 | 0 | 43599.5 | 50000 | 100000 | 150000 | 150000 | 100000 | [6 empty] | 593599.5 | 43599.5
TX2102-1 | San Antonio Shell | TBD | TBD | HAMMOND | San Antonio, TX | Preconstruction | No | AG 281 RE Holdings, LLC |  | Yes | 2022-02-18 | 2022-02-18 | 2022-02-28 | 2022-05-19 | #VALUE! | 10 | 90 | No | 2022-06-18 | 2023-03-15 21:36 | 9 | 9 |  |  |  | 2229000 | 0 | 0 | 201811 | 125000 | 175000 | 225000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 204000 |  | 2430811 | 201811
TX2102-2 | Dr. Abeskharon - San Antonio | TBD | TBD | HAMMOND | San Antonio, TX | Preconstruction | No | AG 281 RE Holdings, LLC |  | Yes | 2021-11-30 | 2022-05-19 | 2022-02-28 | 2022-08-17 | #VALUE! | 90 | 90 | No | 2022-11-15 | 2023-03-15 09:36 | 4 | 4 |  |  |  | 360000 | 0 | 0 | 21249 |  |  | 50000 | 75000 | 125000 | 110000 | [5 empty] | 381249 | 21249
| Fayetteville Development | TBD | TBD | HAYES | Fayetteville, AR | Preconstruction | No | AG Fayetteville RE Holdings, LLC |  | 2022-06-10 |  |  |  |  | -44722 | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
| Cleveland Enhanced Dental | TBD | TBD | HAYES | Cleveland, OK | Preconstruction | No | AG Cleveland RE Holdings, LLC |  | 2022-04-04 |  |  |  |  | -44655 | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
FL2101 | 248 Blue Mountain Beach | TBD | TBD | NOWELL |  | Preconstruction | No | Blue Mountain RE Holdings, LLC | [6 empty] | 0 | [10 empty] | 96582.13 | 96582.13 | 0 | 0 | [11 empty] | 96582.13 | 0
| Anna Shell TX | TBD | TBD | HAYES |  | Preconstruction | No | [7 empty] | 0 |  |  |  | 2022-08-15 | [6 empty] | 5000000 | 0 | 0 | 0 | [9 empty] | 5000000 |  | 5000000 | 0
| Hough Ear - OKC | TBD | TBD | NOWELL |  | Preconstruction | No | [7 empty] | 0 |  |  |  | 2022-09-15 | [6 empty] | 8000000 | 0 | 0 | 0 | [9 empty] | 8000000 |  | 8000000 | 0
| Mingee LVM Investments | TBD | TBD | HAMMOND |  | Preconstruction | No | [7 empty] | 0 | [11 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
| Dr. Kramer - Edmond Family Dental Designs | TBD | TBD | HAMMOND |  | Preconstruction | No | [7 empty] | 0 | [11 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
| JackBe Mustang |  |  | CISPER | Mustang, OK | Preconstruction | No | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
[27 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
[26 empty] | 60618654.13 | 96582.13 | 0 | #REF! | 1800000 | 2420000 | 3310000 | 3595000 | 3635000 | 3375000 | 3828000 | 3165000 | 3100000 | 19064072 | 13180000 | #REF! | #REF!
0
[22 empty] | Billing Total |  |  |  | 116784539.29 | 32114168.81 | 2519382.66 | #REF! | 5070347.44 | 5161679 | 5799709 | 5992605 | 5940000 | 6300000 | 5992200 | 5492435 | 6248440 | 5475600 | 13180000 | #REF! | #REF!
[26 empty] | Billing Goal |  | 3086105 | 3235500 | 4441510 | 6000000 | 6825000 | 7100000 | 7100000 | 7000000 | 6500000 | 6500000 | 6500000 | 6500000 | 80000000
[26 empty] | Difference |  | -566722.34 | #REF! | 628837.44 | -838321 | -1025291 | -1107395 | -1160000 | -700000 | -507800 | -1007565 | -251560 | -1024400 | -66820000
[39 empty] | 2021 | 45000000
[26 empty] | Rev Actual | [12 empty] | 2022 | 60000000
[26 empty] | Rev Goal |  | 2463637.6215 | [10 empty] | 2023 | 72000000
[26 empty] | Difference | [12 empty] | 2024 | 86400000
[39 empty] | 2025 | 99360000
[26 empty] | GP Actual | [12 empty] | 2026 | 114264000
[26 empty] | GP Goal |  | 270651.4085 | [10 empty] | 2027 | 131403600
[26 empty] | Difference | [12 empty] | 2028 | 151114140
[39 empty] | 2029 | 173781261
[26 empty] | GP % Actual | [12 empty] | 2030 | 199848450.15
[26 empty] | GP % Goal |  | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 2031 | 229825717.6725
[26 empty] | Difference | [12 empty] | 2032 | 264299575.3234
[39 empty] | 2033 | 303944511.6219
OH Actual
[26 empty] | OH Goal |  | 300000
Difference
NP Actual
[26 empty] | NP Goal |  | #REF!
Difference
DEAD / HOLD / SOLD | [41 empty] | 0
FL2001 | Elysee Lot 6 | SOLD | SOLD |  | SOLD | SOLD | [5 empty] | SOLD |  | SOLD |  |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD |  | 137906 | [14 empty] | 0 | -137906
FL2002 | Elysee Lot 7 | SOLD | SOLD |  | SOLD | SOLD | [5 empty] | SOLD |  | SOLD |  |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD |  | 136537 | [14 empty] | 0 | -136537
OK1922-1 | Coltrane Corner - Aya Rowe | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK1924 | Yukon Development | HOLD | HOLD |  | HOLD | HOLD | [5 empty] | HOLD |  | HOLD |  |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | [16 empty] | 0 | 0
OK2018 | Dr. Mackey - 61st Street | DEAD | DEAD |  | 9050 E. 61st Street, Tulsa, OK 74145 | HOLD | [5 empty] | HOLD |  | HOLD |  |  | HOLD | Yes | HOLD | HOLD |  | HOLD | HOLD | HOLD |  | 33274 | [14 empty] | 0 | -33274
OK2119 | OSB - Wonga Corner | DEAD | DEAD |  | 1156 S. Douglas, Midwest City, OK 73130 | HOLD | [5 empty] | HOLD |  | HOLD |  |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | [16 empty] | 0 | 0
OK2020-4 | Western - PT Central | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2026 | Covell I35 Edmond Dev. | DEAD | DEAD |  | 5400 E. Covell Road, Edmond, OK | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | Yes | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2028 | Precon - Memorial Park | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 461956 | [14 empty] | 0 | -461956
OK2032-2 | Cross Roads - Dr. Rhodes | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15630 | [14 empty] | 0 | -15630
OK2032-3 | Cross Roads - State Farm | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15000 | [14 empty] | 0 | -15000
OK2032-5 | Cross Roads - Dispensary | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2036 | Dr. Matt Cole, DDS | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 41062 | [14 empty] | 0 | -41062
OK2103 | Bethesda - Santa Fe Dev. | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2105-3 | Valencia - Custom Pools | DEAD | DEAD |  | 2215 NW 178th Street Ste. E, Edmond, OK 73012 | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15493 | [14 empty] | 0 | -15493
OK2109-1 | Grand Blvd. Shell - OKC, OK | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2111 | Solara Surgery Center - Moore, OK | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2115 | Paul's Valley Development | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2117-1 | Paul's Valley Shell | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2117-2 | Paul's Valley Shell - Enhanced Dental | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2118 | Paul's Valley Shell - TBD | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2116 | Dollar Tree (Paul's Valley Development) | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2121 | 15th & Bryant Development | TROSPER | WILLIAMS |  | Combined with OK2122 | Combined | Yes | AG Fifteen RE Holdings, LLC |  | 2021-12-14 | 2022-01-03 | 2022-01-28 | 2022-02-27 | 2022-02-27 |  | 55 | 30 | No | 2022-02-21 | 2022-08-20 14:24 | 6 | 6 |  |  |  | 2860071.9 | 269645.4 |  |  | 125000 | 125000 | 125000 | 105000 |  |  |  |  | 200000 |  |  | 949645.4 | -1910426.5
OK2123 | TBD (15th & Bryant Development) | DEAD | DEAD |  | DEAD | DEAD | No |  |  | DEAD |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | [15 empty] | 0
OK2124 | Bodin Chiro (Lone Oak) | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2126-2 | Weatherford Shell - Dollar Tree | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OKxxxx | Dr. Brad Mitchell Development | HOLD | HOLD |  | HOLD | HOLD | [5 empty] | HOLD |  | HOLD |  |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | [16 empty] | 0 | 0
Okxxxx | Anytime Fitness - Brandon Porter | HOLD | HOLD |  | HOLD | HOLD | No |  |  | DEAD | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | No | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
TNxxxx | AIM Bellevue - Site Visit Needed | PW | TBD |  | 7734 Hwy 70 S. Nashville, TN 37221 | Preconstruction | No | AG AIM Bellevue RE Holdings, LLC |  | 2022-01-31 |  | DEAD | DEAD | DEAD |  | DEAD | DEAD | No | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD |  | 2400000 | [6 empty] | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 2400000 | 0
TX2004 | Marshall Ridge Dev. | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 37392 | [14 empty] | 0 | -37392
TX2009 | Alliance Pediatrics-Marsh | DEAD | DEAD |  | DEAD | DEAD | [5 empty] | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 3575 | [14 empty] | 0 | -3575
[26 empty] | 6157896.9 |  | 0 | 0 | 125000 | 125000 | 125000 | 355000 | 250000 | 250000 | 250000 | 250000 | 450000 | 250000 | 650000 | 3080000 | -3077896.9
Formulas:
Trevor = [Trevor]+45
Trevor = [Trevor, row above]
Brandon = [Trevor]+15
Brandon = [Brandon]+(6*4.3*7)
Note on B23: Bobby Snyder: Existing Building
Note on O37: Bobby Snyder: Need SS to be moved prior to release of permit.
Note on O43: Bobby Snyder: Variance meeting 2/1. We have earthwork permit in hand.
Note on O46: Bobby Snyder: Need approval on additional parking for GI Alliance 2006-4
Note on M49: Bobby Snyder: Cold dark shell
Note on M52: Bobby Snyder: Get early site release prior to full permit
Note on M54: Trevor Hayes: Site plan application made 2/8. Can not submit until planning commision meeting.
Note on O63: Bobby Snyder: The sewer easement is holding up the permit
Note on U63: Bobby Snyder: Open and opperating on 10/14/22. We have communicated with JackBe that this completion date may be in jepordy.
Note on O66: Bobby Snyder: We have earthwork permit in hand.
Note on U66: Bobby Snyder: Hard completion date of Aug to prevent LDs
Note on K68: Bobby Snyder: Don't close land until permit is in hand. Land close can be pushed
Note on M68: Bobby Snyder: Push design forward
Note on O68: Trevor Hayes: Demo Permit rcvd 2/9
Note on K72: Bobby Snyder: Don't close loan until permit is in hand Lot Split
Note on O72: Trevor Hayes: Title company needs to file lot split.
Note on K74: Bobby Snyder: Add 6 months to permits on TI
Note on M74: Bobby Snyder: Add 6 months to permits on TI
Note on K79: Bobby Snyder: Don't close loan until permit is in hand
Note on M87: Bobby Snyder: Need a permit from Trevor
Note on M92: Trevor Hayes: Clock Started on 10/28
Note on M94: Bobby Snyder: Need update from Trevor. 3' of undercut over entire site. Need updated Civils to submit to SAWS -Updated civils ready 2/18. - Approvals needed: TCEQ, SAWS, Building Permit
Note on B139: Bobby Snyder: Another GC built out this space.
Note on U155: Bobby Snyder: Hard completion date prior to LDs

## 03 2022
Peggy | Peggy | Ben | Phillip | Bobby | Danny | Brandon | Danny | Ben | Ben | Trevor | Trevor | Trevor | Trevor | Bobby | Trevor | Trevor | Trevor | Brandon | Brandon | Brandon | Brandon | Peggy | Peggy | Trevor | Trevor |  | 2022 | [11 empty] | 2023
Job Number | Project | Entity | SUP | Dev. Director | Address | Status | Turn Over Complete | LOI | Loan/Lease Close | Anticipated Permit Submission | Actual Permit Submitted | Anticipated Permit Received | Actual Permit Received | Delta Btwn Loan Close and Permit | Anticipated Permit Duration | Permit Approval Duration | Permit Received | Start Date | Comp Date | Planned Duration | Actual Duration | Punchlist Complete Date | Scope of Work Approved | Appraisal Budget Approved | Appraisal Value | Previously Billed | January 2022 | February 2022 | March 2022 | April 2022 | May 2022 | June 2022 | July 2022 | August 2022 | September 2022 | October 2022 | November 2022 | December 2022 | Annual 2023 | TOTAL | DELTA | COMMENTS
Adam England
OK2019 | Santa Fe Development | AG Santa Fe RE Holdings, LLC | STROUD | HAYES | 100 Southwest 134th Street, OKC, OK 73170 | Construction | 2021-04-15 |  | Yes | 2021-02-16 | 2021-02-16 | 2021-04-16 | 2021-04-16 | #VALUE! | 59 | 59 | Yes | 2021-05-03 | 2022-01-10 | 8.3721 | 8.3721 |  |  | Yes | 1181869.7 | 1013323.83 | 59705.08 | 0 | 0 | [10 empty] | 1073028.91 | -108840.79
OK2025 | Autism in Motion - Santa Fe Dev. | AG AIM OK RE Holdings, LLC | WILLIAMS | HAYES | 112 Southwest 134th Street, OKC, OK 73170 | Construction | 2021-05-21 |  | Yes | 2021-01-05 | 2021-01-05 | 2021-04-16 | 2021-04-16 | #VALUE! | 101 | 101 | Yes | 2021-08-07 | 2022-01-25 | 5.1827 | 5.6811 |  |  | Yes | 1051400.45 | 987033.51 | 64366.94 | 0 | 0 | [10 empty] | 1051400.45 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | AG Santa Fe RE Holdings, LLC | STROUD | HAYES | 112 Southwest 134th Street, OKC, OK 73170 | Construction | 2021-06-16 |  | Yes | 2021-06-15 | 2021-06-15 | 2021-08-10 | 2021-08-10 | #VALUE! | 56 | 56 | Yes | 2021-07-05 | 2022-01-28 | 6.8771 | 6.8771 |  |  | Yes | 1367413.55 | 864219.08 | 83841.4 | 12631.18 | 89678.37 | [10 empty] | 1050370.03 | -317043.52
OK2033-2 | Santa Fe Dev. - Old School Bagel | AG Santa Fe RE Holdings, LLC | STROUD | HAYES | 112 SW 134th Street, Oklahoma City, OK | Construction | 2021-06-16 |  | Yes | 2021-06-20 | 2021-06-20 | 2021-12-03 | 2021-12-03 | #VALUE! | 166 | 166 | Yes | 2021-11-17 | 2022-05-23 | 3 | 6.2126 |  |  | Yes | 272915 | 139535.14 | 39753.44 | 25717.67 | 39311.75 | 25000 | 17908.75 | [8 empty] | 287226.75 | 14311.75
OK2110-1 | Shawnee Shell - Shawnee, OK | AG Harrison RE Holdings, LLC | STROUD | HAYES | 4797 N. Harrison, Shawnee, OK 74804 | Construction | 2021-09-01 |  | Yes | 2021-07-14 | 2021-07-14 | 2021-09-17 | 2021-09-17 | #VALUE! | 65 | 65 | Yes | 2021-11-30 | 2022-05-25 | 5.0166 | 5.8472 |  |  | Yes | 1180416.18 | 488349.41 | 162144.05 | 91072.9 | 280084.05 | 150000 | 75000 | 63849.82 | [7 empty] | 1310500.23 | 130084.05
OK2110-2 | Shawnee Shell - Old School Bagel | AG Harrison RE Holdings, LLC | STROUD | HAYES | 4799 N. Harrison, Shawnee, OK 74804 | Construction | 2021-11-19 |  | Yes | 2021-11-08 | 2021-11-08 | 2021-12-09 | 2021-12-09 | #VALUE! | 31 | 31 | Yes | 2022-02-17 | 2022-06-01 | 3 | 3.4551 |  |  | Yes | 253338.08 | 95915.97 | 0 | 69507.91 | 48892.5 | 35000 | 15000 | 2914.2 | [7 empty] | 267230.58 | 13892.5
OK2110-3 | Shawnee Shell - OSO | AG Harrison RE Holdings, LLC | STROUD | HAYES | 4795 N. Harrison, Shawnee, OK 74804 | Construction | 2021-11-19 |  | Yes | 2021-12-06 | 2021-12-06 | 2022-01-14 | 2022-01-28 | #VALUE! | 39 | 53 | Yes | 2022-02-14 | 2022-05-11 | 3.5548 | 2.8571 |  |  | Yes | 402660.29 | 34445.59 | 0 | 54102 | 0 | 80000 | 80000 | 79112.7 | [7 empty] | 327660.29 | -75000
OK2128 | 150th and Penn - Old School Bagel | TAG Penn OSB RE Holdings,LLC | WILLIAMS | HAYES | 15201 N. Penn Crossing Court, Oklahoma City, OK 73013 | Construction | 2022-03-04 |  | 2022-04-01 | 2022-01-19 | 2022-02-01 | 2022-03-05 | 2022-04-06 | 5 | 45 | 64 | No | 2022-04-21 | 2022-10-18 14:24 | 6 | 6 |  |  |  | 750000 | 0 | 0 | 0 | 0 | 125000 | 150000 | 150000 | 140000 | 60000 | [5 empty] | 625000 | -125000
OK2129 | Chamberlain Group (SFD) | AG Chamberlain RE Holdings, LLC | STROUD | HAYES | 113 SW 134th Street, Oklahoma City, OK | Construction | 2021-12-15 |  | Yes | 2021-11-12 | 2021-11-12 | 2022-01-06 | 2021-12-30 | #VALUE! | 55 | 48 | Yes | 2022-01-11 | 2022-09-01 | 7 | 7.7409 |  |  | Yes | 1353098.44 | 86613.87 | 120514.88 | 152425.42 | 0 | 150000 | 150000 | 150000 | 175000 | 175000 | 43544.27 |  |  |  |  | 1203098.44 | -150000
OK2132-1 | Seminole Shell | AG Seminole RE Holdings, LLC | STROUD | HAYES |  | Constuction | 2022-02-23 |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-01 | 2022-02-17 | -1 | 30 | 16 | Yes | 2022-03-16 | 2022-11-02 | 9 | 7.6744 |  |  |  | 1360000 | 0 | 0 | 170543 | 136059.07 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 139457 |  |  |  | 1346059.07 | -13940.93
OK2132-2 | Seminole Shell - T-Mobile | AG Seminole RE Holdings, LLC | STROUD | HAYES |  | Constuction | 2022-02-23 |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-16 | 2022-02-17 | -1 | 45 | 16 | Yes | 2022-05-03 | 2022-10-30 14:24 | 5 | 6 |  |  |  | 175000 | 0 | 0 | 0 | 0 |  | 15000 | 15000 | 20000 | 50000 | 50000 | 25000 |  |  |  | 175000 | 0
OK2132-3 | Seminole Shell - Urgent Care | AG Seminole RE Holdings, LLC | STROUD | HAYES |  | Constuction | 2022-02-23 |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-16 | 2022-02-17 | -1 | 45 | 16 | Yes | 2022-05-03 | 2022-10-30 14:24 | 5 | 6 |  | 2022-04-05 |  | 300000 | 0 | 0 | 0 | 0 |  | 50000 | 50000 | 50000 | 75000 | 50000 | 25000 |  |  |  | 300000 | 0
OK2132-4 | Seminole Shell TBD TI Pharmacy | AG Seminole RE Holdings, LLC | STROUD | HAYES |  | Preconstruction | No |  | 2022-02-18 | 2022-01-30 | 2022-06-01 | 2022-03-16 | 2022-07-16 | 148 | 45 | 45 | No | 2022-08-15 | 2022-12-13 09:36 | 5 | 4 |  |  |  | 95000 | 0 | 0 | 0 | 0 |  |  |  |  | 30000 | 35000 | 30000 |  |  |  | 95000 | 0
OK2135-1 | Norman Shell | TAG Norman RE Holdings, LLC | STROUD | CISPER |  | Construction | 2022-03-01 |  | 2022-02-24 | 2022-02-09 | 2022-02-01 | 2022-03-26 | 2022-03-03 | 7 | 45 | 30 | Yes | 2022-03-28 | 2022-12-23 21:36 | 9 | 9 |  |  |  | 1200000 | 0 | 0 | 129788.5 | 138269.44 | 100000 | 100000 | 100000 | 125000 | 125000 | 125000 | 125000 | 125000 | 45211.5 |  | 1238269.44 | 38269.44
OK2135-2 | Norman Shell - TI | TAG Norman RE Holdings, LLC | STROUD | CISPER |  | Preconstruction | No |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2135-3 | Norman Shell - Old School Bagel | TAG Norman RE Holdings, LLC | STROUD | CISPER |  | Constuction | 2022-03-01 |  | 2022-02-24 | 2022-02-09 | 2022-03-18 | 2022-03-26 | 2022-04-13 | 48 | 45 | 26 | No | 2022-05-13 | 2022-09-10 09:36 | 4 | 4 |  |  |  | 300000 | 0 | 0 | 0 | 0 | [5 empty] | 50000 | 50000 | 75000 | 75000 | 50000 | 300000 | 0
OK2135-4 | Norman Shell - SWIG | TAG Norman RE Holdings, LLC | STROUD | CISPER |  | Preconstruction | No |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
TN2101 | AIM - Memphis, TN | AG AIM Memphis RE Holdings, LLC | N/A | HAYES | 7007 Stage Rd., Memphis, TN 38133 | Construction | 2021-11-01 |  | Yes | 2021-06-18 | 2021-06-18 | 2021-10-20 | 2021-10-20 | #VALUE! | 124 | 124 | Yes | 2021-11-04 | 2022-03-31 | 4.8837 | 4.8837 |  |  | Yes | 1207444.74 | 527222.16 | 0 | 255699 | 424523.58 | 74523.58 | [9 empty] | 1281968.32 | 74523.58
[25 empty] | 12450556.43 | 4236658.56 | 530325.79 | 961487.58 | 1156818.76 | 889523.58 | 802908.75 | 760876.72 | 660000 | 665000 | 503544.27 | 394457 | 200000 | 120211.5 | 50000 | 11931812.51 | -518743.92
Kyle Tedlock | [40 empty] | 0
OK1923-6 | Riverwest - Old School Bagel | Riverwest RE Holdings, LLC | RONS | HAYES | 152 W Alexander Blvd., Sand Springs, OK 74063 | Construction | 2021-02-11 |  | Yes | 2021-06-01 | 2021-06-01 | 2021-06-15 | 2021-06-15 | #VALUE! | 14 | 14 | Yes | 2021-05-28 | 2021-10-28 | 5 | 5.0831 |  |  | Yes | 89125 | 58100 | 0 | 0 | 80387.15 | [10 empty] | 138487.15 | 49362.15
OK1925 | Glenn Pool - Old School Bagel Express (Stand Alone) | TAG Glenpool OSB RE Holdings,LLC | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-04-30 | 2022-02-09 | 2022-04-04 | 2022-02-28 | 2022-05-04 | 4 | 19 | 30 | No | 2022-05-04 | 2022-10-01 | 2.5249 | 4.9834 |  |  |  | 725000 | 0 | 0 | 0 | 0 | [8 empty] | 725000 |  | 725000 | 0
OK2016 | OneCore | TAG OneCore RE Holdings, LLC | HALL | N/A | 100 NE 85th Street, OKC, OK 73114 | Construction | 2020-10-01 |  | Yes | 2020-08-11 | 2020-08-11 | 2020-11-12 | 2020-11-12 | #VALUE! | 93 | 93 | Yes | 2020-10-15 | 2021-12-01 | 14 | 13.6877 |  |  | Yes | 14188397.56 | 13413397.56 | 812671.7 | 0 | 81884 | [10 empty] | 14307953.26 | 119555.7
OK2032-1 | Cross Roads - Shell | AG Broken Arrow RE Holdings, LLC | RONS | HAYES | 1167 N. 38th Street, Broken Arrow, OK 74014 | Construction | N/A |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | AG Broken Arrow RE Holdings, LLC | RONS | HAYES | 1171 N. 38th Street, Broken Arrow, OK 74014 | Construction | 2021-09-15 |  | Yes | 2021-08-09 | 2021-08-09 | 2021-08-10 | 2021-08-10 | #VALUE! | 1 | 1 | Yes | 2021-10-01 | 2022-03-08 | 4 | 5.2492 |  |  | Yes | 295011.29 | 264663.85 | 0 | 0 | 36793.4 | [10 empty] | 301457.25 | 6445.96
OK2122 | The Learning Experence (15th & Bryant Development) | AG Fifteen RE Holdings, LLC | WILLIAMS | HAMMOND |  | Construction | 2022-03-24 |  | 2021-12-14 | 2022-01-28 | 2021-12-02 | 2022-02-27 | 2022-03-31 | 107 | 30 | 119 | Yes | 2022-03-31 | 2022-08-31 | 6.3455 | 5.0831 |  |  | Yes | 2860072 | 0 | 0 | 125981 | 53207.75 | 250000 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 184091 |  | 2663279.75 | -196792.25
OK2134-1 | Glenn Pool Shell | TAG Glenpool RE Holdings, LLC | RONS | HAYES | Glenn Pool, OK | Preconstruction | 2022-04-15 |  | 2022-04-08 | 2022-01-30 | 2022-01-15 | 2022-03-01 | 2022-04-15 | 7 | 30 | 90 | No | 2022-04-30 | 2023-01-25 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 | 0 | 0 | 100000 | 150000 | 200000 | 200000 | 200000 | 250000 | 250000 | 250000 | 200000 | 200000 | 2000000 | 0
OK2134-2 | Glenn Pool Shell - TI #1 | TAG Glenpool RE Holdings, LLC | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2134-3 | Glenn Pool Shell - TI #2 | TAG Glenpool RE Holdings, LLC | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2134-4 | Glenn Pool Shell - TI #3 | TAG Glenpool RE Holdings, LLC | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2134-5 | Glenn Pool Shell - TI #4 | TAG Glenpool RE Holdings, LLC | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2134-6 | Glenn Pool Shell - TI #5 | TAG Glenpool RE Holdings, LLC | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
[25 empty] | 20157605.85 | 13736161.41 | 812671.7 | 125981 | 252272.3 | 350000 | 400000 | 500000 | 500000 | 500000 | 550000 | 550000 | 550000 | 1109091 | 200000 | 20136177.41 | -21428.44
Kimberly Kelly | [40 empty] | 0
TX1903 | Ramon Franklin Warehouse | Don't Own | MILLER | N/A | 1308 Corporate Drive East, Arlinton, TX 76006 | Construction | 2020-06-18 |  | N/A | 2020-12-09 | 2020-12-09 | 2021-01-27 | 2021-01-27 | N/A | 49 | 49 | Yes | 2021-07-05 | 2021-12-10 | 5 | 5.2492 |  |  | Yes | 1006578.9 | 1006578.9 | 0 | 413409.04 | 0 | [10 empty] | 1419987.94 | 413409.04
TX2101 | Bob Mills - Forth Worth | Don't Own | JOHNSON | N/A | 3600 East Long Ave., Ft Worth, TX 76111 | Construction | 2021-05-20 |  | N/A | 2021-04-09 | 2021-04-09 | 2021-06-10 | 2021-06-10 | N/A | 62 | 62 | Yes | 2021-07-10 | 2021-12-10 | 5 | 5.0831 |  |  | Yes | 2315782.2 | 2304152.2 | 38625.5 | 0 | 0 | [10 empty] | 2342777.7 | 26995.5
[25 empty] | 3322361.1 | 3310731.1 | 38625.5 | 413409.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762765.64 | 440404.54
Tiffany Shiel | [40 empty] | 0
OK2106-1 | Fox Lake Shell | TAG Fox Lake RE Holdings, LLC | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Construction | 2021-07-01 |  | Yes | 2021-06-22 | 2021-06-22 | 2021-09-22 | 2021-09-22 | #VALUE! | 92 | 92 | Yes | 2021-07-22 | 2022-11-15 | 13 | 15.9801 |  |  | Yes | 12193746.8 | 3069014.06 | 532188.35 | 1527507.98 | 798302.17 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 750000 | 250000 | 65036.41 |  |  | 11992048.97 | -201697.83
OK2106-2 | Fox Lake - Sidecar | TAG Fox Lake RE Holdings, LLC | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-05-11 | 2022-06-23 | 2022-06-25 | #VALUE! | 45 | 45 | No | 2022-07-01 | 2022-12-28 14:24 | 6 | 6 |  |  |  | 980000 | 0 | 0 | 0 | 0 | 100000 | 125000 | 150000 | 200000 | 200000 | 155000 |  |  |  |  | 930000 | -50000
OK2106-3 | Fox Lake - Hatch | TAG Fox Lake RE Holdings, LLC | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-05-11 | 2022-06-23 | 2022-06-25 | #VALUE! | 45 | 45 | No | 2022-07-01 | 2022-12-28 14:24 | 6 | 6 |  |  |  | 1558000 | 0 | 0 | 0 | 0 | 125000 | 225000 | 300000 | 300000 | 300000 | 258000 |  |  |  |  | 1508000 | -50000
OK2106-4 | Fox Lake - Enhanced Dental | TAG Fox Lake RE Holdings, LLC | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-03-02 | 2022-03-02 | 2022-04-08 | 2022-04-08 | #VALUE! | 37 | 37 | No | 2022-05-08 | 2022-11-04 14:24 | 6 | 6 |  |  |  | 540000 | 0 | 0 | 0 | 0 | 75000 | 90000 | 100000 | 100000 | 100000 | 50000 |  |  |  |  | 515000 | -25000
OK2106-5 | Fox Lake - Chicago Title | TAG Fox Lake RE Holdings, LLC | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-04-11 | 2022-04-15 | 2022-05-26 | 2022-05-30 | #VALUE! | 45 | 45 | No | 2022-04-01 | 2022-09-28 14:24 | 6 | 6 |  |  |  | 800000 | 0 | 0 | 0 | 0 | 125000 | 125000 | 150000 | 150000 | 125000 | 50000 |  |  |  |  | 725000 | -75000
OK2106-6 | Fox Lake Provision Concepts | TAG Fox Lake RE Holdings, LLC | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-06-23 | 2022-06-23 | 2022-08-07 | #VALUE! | 45 | 45 | No | 2022-04-01 | 2022-09-28 14:24 | 6 | 6 |  |  |  | 690000 | 0 | 0 | 0 | 0 | 100000 | 120000 | 120000 | 120000 | 120000 | 60000 |  |  |  |  | 640000 | -50000
OK2106-7 | Fox Lake TBD | TAG Fox Lake RE Holdings, LLC | ECKER | HAMMOND | 852 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-06-23 | 2022-06-23 | 2022-08-07 | #VALUE! | 45 | 45 | No |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2106-8 | Fox Lake Chicken Foote | TAG Fox Lake RE Holdings, LLC | ECKER | HAMMOND | 853 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-06-23 | 2022-06-23 | 2022-08-07 | #VALUE! | 45 | 45 | No | 2022-08-07 | 2023-02-01 |  | 5.9136 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2106-9 | Fox Lake Regent Bank | TAG Fox Lake RE Holdings, LLC | ECKER | HAMMOND | 854 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
[25 empty] | 12193746.8 | 3069014.06 | 532188.35 | 1527507.98 | 798302.17 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 750000 | 250000 | 65036.41 | 0 | 0 | 11992048.97 | -201697.83
Bob Solomon | [40 empty] | 0
OK2034 | Dr. Rex Johnson, DVM - Covell I35 | AG Waterloo RE Holdings, LLC | WILLIAMS | HAYES | 5401 E. Covel Rd., Edmond, OK 73034 | Construction | 2021-06-11 |  | Yes | 2021-05-12 | 2021-05-12 | 2021-08-10 | 2021-08-10 | #VALUE! | 90 | 90 | Yes | 2021-08-16 | 2022-05-20 | 9 | 9.2027 |  |  | Yes | 1961015.83 | 952423.73 | 173273.61 | 93239.18 | 115103.75 | 225000 | 225000 | 67079.31 | [7 empty] | 1851119.58 | -109896.25
OK2107 | Jack Be Grocery | AG May RE Holdings, LLC | STRUB | CISPER | 855 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | 2022-04-11 |  | 2022-03-30 | 2022-01-31 | 2022-02-03 | 2022-03-17 | 2022-03-05 | -25 | 45 | 30 | No | 2022-03-05 | 2022-09-01 14:24 | 6 | 6 |  |  |  | 2500000 | 0 | 0 | 0 | 0 | 125000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 700000 | 2425000 | -75000
OK2112 | Covell 35 Dev. - Dr. Lu Dentistry | AG Medical RE Holdings, LLC | WILLIAMS | HAYES | 5249 E. Covel Rd., Edmond, OK 73034 | Construction | 2021-11-19 |  | Yes | 2021-10-20 | 2021-10-20 | 2021-12-10 | 2021-12-10 | #VALUE! | 51 | 51 | Yes | 2021-12-22 | 2022-06-30 | 9 | 6.3123 |  |  | Yes | 762952.96 | 92185.59 | 111281.22 | 64974.74 | 100946.93 | 100000 | 125000 | 100000 | 69511.41 | [6 empty] | 763899.89 | 946.93
OK2125-1 | Enid Shell | AG Enid RE Holdings, LLC | RONS | HAYES |  | Construction | 2022-01-27 |  | 2022-01-13 | 2021-12-13 | 2022-01-14 | 2022-01-17 | 2022-02-23 | 41 | 35 | 40 | Yes | 2022-02-28 | 2022-09-16 | 9 | 6.6445 |  |  |  | 1500000 | 0 | 0 | 192361.11 | 27166.45 | 100000 | 150000 | 175000 | 175000 | 175000 | 175000 | 175000 | 100000 | 32638.89 |  | 1477166.45 | -22833.55
OK2125-2 | Enid - Old School Bagel | AG Enid RE Holdings, LLC | RONS | HAYES |  | Preconstruction | 2022-04-15 |  | 2022-01-13 | 2022-01-14 | 2022-02-18 | 2022-02-28 | 2022-03-16 | 62 | 45 | 26 | Yes | 2022-05-09 | 2022-09-06 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 | 0 | 75975.43 | 150000 | 50000 | [8 empty] | 275975.43 | -74024.57
OK2125-3 | Enid - Enhanced Dental | AG Enid RE Holdings, LLC | RONS | HAYES |  | Preconstruction | 2022-04-15 |  | 2022-01-13 | 2022-01-14 | 2022-02-18 | 2022-02-28 | 2022-03-16 | 62 | 45 | 26 | Yes | 2022-05-09 | 2022-09-06 09:36 | 4 | 4 |  |  |  | 450000 | 0 | 0 | 0 | 26192.88 | 50000 | 75000 | 75000 | 75000 | 75000 | 75000 | 25000 |  |  |  | 476192.88 | 26192.88
[25 empty] | 7523968.79 | 1044609.32 | 284554.83 | 350575.03 | 345385.44 | 750000 | 825000 | 617079.31 | 519511.41 | 450000 | 450000 | 400000 | 300000 | 232638.89 | 700000 | 7269354.23 | -254614.56
Kevin Trosper | [40 empty] | 0
OK2102 | Puppy Paws East Edmond | AG Puppy Covell RE Holdings, LLC | TBD | HAYES | East Edmond | Preconstruction | No |  | 2022-03-21 | 2022-02-05 | 2022-05-11 | 2022-04-16 | 2022-07-10 | 111 | 70 | 60 | No | 2022-06-04 | 2023-03-01 21:36 | 9 | 9 |  |  |  | 2200000 | 0 | 0 | 0 | 147115.94 | 200000 | 260000 | 260000 | 300000 | 300000 | 260000 | 260000 | 210000 |  |  | 2197115.94 | -2884.06
OK2105-3 | Valencia - Winfield and Co. | AG Valencia RE Holdings, LLC | TROSPER | N/A | 2216 NW 178th Street Ste. E, Edmond, OK 73012 | Construction | 2021-09-15 |  | Yes | 2021-09-01 | 2021-09-01 | 2021-09-16 | 2021-09-16 | #VALUE! | 15 | 15 |  | 2021-09-22 | 2021-10-17 | 1 | 0.83056 |  |  | Yes | 27626.4 | 11493 | 16133.4 | 0 | 0 | [10 empty] | 27626.4 | 0
OK2108 | Puppy Paws - Lone Oak | AG Puppy West RE Holdings, LLC | WILLIAMS | HAYES | 15200 Crown at Lone Oak, Edmond OK 73013 | Construction | 2022-01-14 |  | Yes | 2021-11-19 | 2021-11-19 | 2022-01-06 | 2022-02-14 | #VALUE! | 48 | 87 | Yes | 2022-02-21 | 2022-11-30 | 9 | 9.3688 |  |  |  | 2200000 | 0 | 0 | 212179 | 291481.14 | 250000 | 275000 | 300000 | 250000 | 250000 | 250000 | 187821 |  |  |  | 2266481.14 | 66481.14
OK2126-1 | Weatherford Shell | AG Weatherford RE Holdings, LLC | STEPHENSON | HAMMOND |  | Construction | 2022-01-27 |  | 2022-01-14 | 2021-12-13 | 2022-01-14 | 2022-01-13 | 2022-01-21 | 7 | 31 | 7 | Yes | 2022-02-14 | 2022-08-19 | 8 | 6.1794 |  |  |  | 1200000 | 0 | 0 | 240339.48 | 284536.77 | 150000 | 150000 | 200000 | 200000 | 100000 | 84660.52 |  |  |  |  | 1409536.77 | 209536.77
OK2126-3 | Weatherford Shell - Enhanced Dental | AG Weatherford RE Holdings, LLC | STEPHENSON | HAMMOND |  | Construction | No |  | 2022-01-14 | 2021-12-30 | 2022-02-16 | 2022-03-16 | 2022-03-23 | 68 | 76 | 35 | Yes | 2022-04-21 | 2022-08-19 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 | 0 | 0 | 75000 | 100000 | 100000 | 25000 | [6 empty] | 300000 | -50000
TX2006-1 | Sunnyvale Shell | AG Sunnyvale RE Holdings, LLC | DOYLE | CISPER | 480 US Hwy 80, Sunnyvale, TX 75182 | Construction | 2022-08-10 |  | Yes | 2021-06-22 | 2021-06-22 | 2021-11-09 | 2021-11-09 | #VALUE! | 140 | 140 | Yes | 2021-11-17 | 2022-06-01 | 7 | 6.5116 |  |  | Yes | 1910049.56 | 892016.83 | 304883.09 | 284226.25 | 241178.58 | 128923.39 | [9 empty] | 1851228.14 | -58821.42
TX2006-2 | Sunnyvale Shell - Dr. Luna | AG Sunnyvale RE Holdings, LLC | DOYLE | CISPER | 481 US Hwy 80, Sunnyvale, TX 75182 | Construction | 2022-08-10 |  | Yes | 2021-12-21 | 2021-12-13 | 2022-01-27 | 2022-01-24 | #VALUE! | 37 | 42 | Yes | 2022-02-07 | 2022-07-02 | 3 | 4.8173 |  |  | Yes | 288979.2 | 17537.69 | 0 | 0 | 171149.96 | 95000 | 76441.51 | [8 empty] | 360129.16 | 71149.96
TX2006-3 | Sunnyvale Shell - Dr. Rohani | AG Sunnyvale RE Holdings, LLC | DOYLE | CISPER | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction | 2022-08-10 |  | Yes | 2021-12-21 | 2021-12-29 | 2022-02-04 | 2022-01-24 | #VALUE! | 45 | 26 | Yes | 2022-02-07 | 2022-07-02 | 3 | 4.8173 |  |  | Yes | 376822.32 | 20124 | 0 | 0 | 203849.39 | 100000 | 100000 | 31698.32 | [7 empty] | 455671.71 | 78849.39
TX2005 | McKinney Development | AG Virginia Ridge RE Holdings, LLC | DOYLE | CISPER | Virginia and Ridge Road, McKinney, TX | Preconstruction | No |  | Yes | 2021-10-01 | 2021-10-01 | 2022-01-14 | 2022-05-22 | #VALUE! | 105 | 233 | No | 2022-06-01 | 2023-02-26 21:36 | 9 | 9 |  |  |  | 600000 | 0 | 0 | 0 | 63350.47 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 120000 |  |  |  | 663350.47 | 63350.47
TX2006-4 | Sunnyvale Shell - GI Alliance | AG Sunnyvale RE Holdings, LLC | DOYLE | CISPER | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction | N/A |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
TX2008 | Dr. Barbara Lee (McKinney Development) | AG Virginia RE Holdings, LLC | DOYLE | CISPER | McKinney, TX | Preconstruction | No |  | Yes | 2021-10-22 | 2021-10-01 | 2022-05-22 | 2022-05-22 | #VALUE! | 233 | 233 | No | 2022-06-01 | 2023-02-26 21:36 | 9 | 9 |  |  |  | 750000 | 0 | 0 | 0 | 0 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 65000 | 145000 |  |  | 750000 | 0
TX2103-1 | McKinney Shell (McKinney Development) | AG Virginia Ridge RE Holdings, LLC | DOYLE | CISPER | McKinney, TX | Preconstruction | No |  | Yes | 2022-02-04 | 2021-10-01 | 2022-05-22 | 2022-05-22 | #VALUE! | 233 | 233 | No | 2022-06-01 | 2022-11-28 14:24 | 6 | 6 |  |  |  | 600000 | 0 | 0 | 0 | 78765.18 |  |  | 25000 | 50000 | 80000 | 80000 | 80000 | 80000 | 80000 | 125000 | 678765.18 | 78765.18
TX2103-2 | TBD TI (McKinney Shell) | AG Virginia Ridge RE Holdings, LLC | DOYLE | CISPER | McKinney, TX | Preconstruction | No |  | Yes | 2022-02-04 | 2022-10-01 | 2022-05-05 | 2023-05-22 | #VALUE! | 90 | 233 | No | 2023-06-21 | 2023-09-19 07:12 | 9 | 3 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
TX2103-3 | TBD TI (McKinney Shell) | AG Virginia Ridge RE Holdings, LLC | DOYLE | CISPER | McKinney, TX | Preconstruction | No |  | Yes | 2022-02-04 | 2022-10-01 | 2022-05-05 | 2023-05-22 | #VALUE! | 90 | 233 | No | 2023-06-21 | 2023-09-19 07:12 | 9 | 3 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
TX2007-1 | Carrollton Shell | AG Carrolton RE Holdings, LLC | DOYLE | CISPER | Carrollton, TX | Preconstruction | 2022-05-01 |  | Yes | 2021-10-28 | 2021-06-15 | 2021-12-17 | 2022-05-31 | #VALUE! | 50 | 350 | No | 2022-06-01 | 2023-02-26 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 | 210901.5 | 0 | 125000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 164098.5 |  | 1900000 | -100000
TX2007-2 | Carrolton Shell - Dr. Bui | AG Carrolton RE Holdings, LLC | DOYLE | CISPER | Carrollton, TX | Preconstruction | 2022-05-01 |  | Yes | 2021-11-26 | 2022-07-10 | 2022-02-24 | 2022-09-08 | #VALUE! | 90 | 60 | No | 2022-08-30 | 2023-02-26 14:24 | 4 | 6 |  |  |  | 550000 | 0 | 0 | 43599.5 | 0 |  |  |  |  | 100000 | 100000 | 125000 | 100000 | 81400.5 |  | 550000 | 0
[25 empty] | 13053477.48 | 941171.52 | 321016.49 | 991245.73 | 1481427.43 | 1293923.39 | 1331441.51 | 1286698.32 | 1195000 | 1200000 | 1144660.52 | 1037821 | 735000 | 325499 | 125000 | 13409904.91 | 356427.43
Preconstruction | [40 empty] | 0
OK2037 | Master Hand Milling | TBD | TBD | TBD | TBD, Edmond, OK | Preconstruction | No |  | No | 2022-06-01 | 2022-05-23 | 2022-07-16 | 2022-07-07 | #VALUE! | 45 | 45 | No | 2022-08-06 | 2023-08-02 04:48 | 12 | 12 |  |  |  | 4000000 | 0 | 0 | 0 | 0 | 250000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 830000 | 3800000 | -200000
OK2114-1 | Chamberlain Realty - Lone Oak | AG Chamberlain West RE Holdings, LLC | TBD | HAYES | 15103 Crown at Lone Oak Rd., Edmond, OK 73013 | Preconstruction | No |  | 2022-06-01 | 2022-04-17 | 2022-05-01 | 2022-06-01 | 2022-05-29 | -3 | 45 | 28 | No | 2022-06-01 | 2022-11-28 14:24 | 6 | 6 |  |  |  | 988611 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 |  |  |  |  | 25000 |  | 588611 | 913611 | -75000
OK2120 | Peak View Brewery and Distillery | Don't know | TBD | TBD | Reservoir by Costco | Preconstruction | No |  | 2022-04-01 | 2022-04-17 | 2022-07-10 | 2022-06-01 | 2022-08-24 | 145 | 45 | 45 | No | 2022-06-01 | 2023-03-29 | 10 | 10 |  |  |  | 3000000 | 0 | 0 | 0 | 0 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 225000 | 2875000 | -125000
Okxxxx | Regent Corner (Fox Lake Similar) | AG Regent BA RE Holdings, LLC | RONS | CISPER | Broken Arrow, OK | Preconstruction | No |  | 2023-02-01 | 2022-05-01 | 2022-08-05 | 2022-06-30 | 2023-02-01 | 0 | 60 | 180 | No | 2023-03-03 | 2024-02-27 04:48 | 12 | 12 |  |  |  | 14000000 | 0 | 0 | 0 | 0 | [5 empty] | 1250000 | 1250000 | 1250000 | 1250000 | 9000000 | 14000000 | 0
OKxxxxTI | Cross Roads - Broken Arrow - Dr. Shambille (WGS) | AG Broken Arrow RE Holdings, LLC | TBD | HAYES | Broken Arrow, OK | Preconstruction | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
TX2102-1 | San Antonio Shell | AG 281 RE Holdings, LLC | TBD | HAMMOND | San Antonio, TX | Preconstruction | No |  | Yes | 2022-02-18 | 2022-02-18 | 2022-02-28 | 2022-05-19 | #VALUE! | 10 | 90 | No | 2022-05-19 | 2023-02-13 21:36 | 9 | 9 |  |  |  | 2229000 | 0 | 0 | 201811 | 0 |  |  | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 204000 | 323189 | 2229000 | 0
TX2102-2 | Dr. Abeskharon - San Antonio | AG 281 RE Holdings, LLC | TBD | HAMMOND | San Antonio, TX | Preconstruction | No |  | Yes | 2021-11-30 | 2022-05-19 | 2022-02-28 | 2022-07-03 | #VALUE! | 90 | 45 | No | 2022-10-01 | 2023-01-29 09:36 | 4 | 4 |  |  |  | 360000 | 0 | 0 | 21249 | 0 | [7 empty] | 125000 | 125000 | 88751 | 360000 | 0
| Fayetteville Development | AG Fayetteville RE Holdings, LLC | TBD | HAYES | Fayetteville, AR | Preconstruction | No |  | 2022-06-10 | 2022-07-01 | 2022-07-01 | 2022-08-20 | 2022-08-20 | 71 | 50 | 50 | No | 2022-08-20 | 2023-08-16 04:48 | 4 | 12 |  |  |  | 3000000 | 0 | 0 | 0 | 0 | [9 empty] | 3000000 | 3000000 | 0
| Cleveland Enhanced Dental | AG Cleveland RE Holdings, LLC | TBD | HAYES | Cleveland, OK | Preconstruction | No |  | 2022-04-08 | 2022-05-09 | 2022-05-09 | 2022-06-28 | 2022-06-28 | 81 | 50 | 50 | No | 2022-06-28 | 2022-12-25 14:24 | 4 | 6 |  |  |  | 900000 | 0 | 0 | 0 | 0 | [9 empty] | 900000 | 900000 | 0
| Anna Shell TX | AG Anna RE Holdings, LLC | TBD | HAYES |  | Preconstruction | No |  | 2022-07-06 | 2022-08-19 | 2022-08-19 | 2022-09-28 | 2022-09-28 | 84 | 40 | 40 | No | 2022-07-06 | 2023-07-02 04:48 | 4 | 12 |  |  |  | 5000000 | 0 | 0 | 0 | 0 |  |  |  |  | 250000 | 250000 | 250000 | 250000 | 250000 | 3750000 | 5000000 | 0
| Hough Ear - OKC | AG Artesian RE Holdings, LLC | TBD |  |  | Preconstruction | No |  | 2022-07-26 | 2022-05-27 | 2022-05-27 | 2022-07-26 | 2022-07-26 | 0 | 60 | 60 | No | 2022-09-15 | 2023-09-11 04:48 | 4 | 12 |  |  |  | 8000000 | 0 | 0 | 0 | 0 | [5 empty] | 250000 | 275000 | 275000 | 275000 | 6925000 | 8000000 | 0
| Mingee LVM Investments | AG Half RE Holdings, LLC | TBD | HAMMOND |  | Preconstruction | No |  | 2022-08-01 | 2022-06-17 | 2022-06-17 | 2022-08-01 | 2022-08-01 | 0 | 45 | 45 | No | 2022-08-01 | 2023-07-28 04:48 | 4 | 12 |  |  | 2022-05-20 | 9600000 | 0 | 0 | 0 | 0 | [9 empty] | 9600000 | 9600000 | 0
| Dr. Kramer - Edmond Family Dental Designs |  | TBD | HAMMOND |  | Preconstruction | No |  | 2022-09-12 | 2022-05-15 | 2022-05-15 | 2022-09-12 | 2022-09-12 | 0 | 120 | 120 | No | 2022-09-12 | 2023-03-11 14:24 | 6 | 6 |  |  | 2022-06-29 | 1800000 | 0 | 0 | 0 | 0 | [9 empty] | 1800000 | 1800000 | 0
| JackBe Mustang |  | TBD | CISPER | Mustang, OK | Preconstruction | No |  | 2022-06-21 | 2022-05-17 | 2022-05-17 | 2022-07-01 | 2022-07-01 | 10 | 45 | 45 | No | 2022-07-01 | 2022-12-28 14:24 | 6 | 6 |  |  |  | 3200000 | 0 | 0 | 0 | 0 | [9 empty] | 3200000 | 3200000 | 0
| JackBe Edmond |  | TBD | CISPER |  | Preconstruction | No |  | 2022-05-23 | 2022-04-29 | 2022-04-29 | 2022-05-29 | 2022-05-29 | 6 | 30 | 30 | No | 2022-05-29 | 2022-09-30 | 4 | 4.1196 |  |  |  | 1500000 | 0 | 0 | 0 | 0 | [9 empty] | 1500000 | 1500000 | 0
[25 empty] | 118307646.02 | 22043587.41 | 1989056.87 | 3631778.78 | 2797000.19 | 4518923.39 | 4981441.51 | 5213777.63 | 4974511.41 | 5135000 | 6107660.52 | 4902821 | 4465036.41 | 4411228.89 | 42755551 | 117927375.01 | -380271.01
0
[21 empty] | Billing Total |  |  |  | 130847327.45 | 26338345.97 | 2519382.66 | 4593266.36 | 4034206.1 | 5161679 | 5799709 | 5992605 | 5940000 | 6300000 | 5992200 | 5492435 | 6248440 | 5475600 | 42805551 | 129997674.67 | -849652.78
[25 empty] | Billing Goal |  | 3086105 | 3235500 | 4441510 | 6000000 | 6825000 | 7100000 | 7100000 | 7000000 | 6500000 | 6500000 | 6500000 | 6500000 | 80000000
[25 empty] | Difference |  | -566722.34 | 1357766.36 | -407303.9 | -838321 | -1025291 | -1107395 | -1160000 | -700000 | -507800 | -1007565 | -251560 | -1024400 | -37194449
[38 empty] | 2021 | 45000000
COMPLETED | [40 empty] | 0
OK1936 | Dr Fischer | AG Medical RE Holdings ,LLC | RONS | N/A | 720 West 71St Street S, Tulsa, OK 74132 | Construction | 2020-05-28 |  | Yes | 2020-04-08 | 2020-04-08 | 2020-06-22 | 2020-06-22 | #VALUE! | 75 | 75 | Yes | 2020-06-22 | 2021-09-30 | 15 | 15.4485 |  |  | Yes | 2482029.51 | 2482029.51 | 0 | 0 | 0 | [10 empty] | 2482029.51 | 0
OK2008 | Dr. Gaches | AG Hi Point RE Holdings, LLC | RONS | N/A | 11492 N. 137th E. Ave., Owasso, OK | Construction | 2021-04-01 |  | Yes | 2020-08-28 | 2020-08-28 | 2021-03-05 | 2021-03-05 | #VALUE! | 189 | 189 | Yes | 2021-04-04 | 2021-10-15 | 6 | 6.4452 |  |  | Yes | 712367.43 | 712367.43 | 0 | 0 | 0 | [10 empty] | 712367.43 | 0
OK2014 | Clark Plaza Shell | AG Clark RE Holdings, LLC | RONS | N/A | 7877 E 71st South., Tulsa, OK 74133 | Construction | Yes |  | Yes | 2020-10-16 | 2020-10-16 | 2021-02-19 | 2021-02-19 | #VALUE! | 126 | 126 | Yes | 2021-03-01 | 2021-12-27 | 10 | 10 |  |  | Yes | 1436404.19 | 1436404.19 | 0 | 0 | 0 | [10 empty] | 1436404.19 | 0
OK2014-1 | Clark Shell - Dr. Pfeffer | AG Clark RE Holdings, LLC | RONS | N/A | 7877 E 71st South Ste A, Tulsa, OK 74133 | Construction | 2021-01-19 |  | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | #VALUE! | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 19:12 | 8 | 8 |  |  | Yes | 648252.98 | 648252.98 | 0 | 0 | 0 | [10 empty] | 648252.98 | 0
OK2014-2 | Clark Shell - Enhance DDS | AG Clark RE Holdings, LLC | RONS | N/A | 7877 E 71st South Ste B., Tulsa, OK 74133 | Construction | 2021-01-19 |  | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | #VALUE! | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 | 8 | 7.9734 |  |  | Yes | 400186.6 | 400186.6 | 0 | 0 | 0 | [10 empty] | 400186.6 | 0
OKxxxxTI | Montapp Retail Fyzical Theropy (White Box) | Glenpool RE Holdings, LLC | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-01-05 |  |  |  |  | -44566 | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
DEAD / HOLD / SOLD | [40 empty] | 0
FL2001 | Elysee Lot 6 |  | SOLD |  | SOLD | SOLD |  |  |  |  | SOLD |  | SOLD |  |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD |  | 137906 | [14 empty] | 0 | -137906
FL2002 | Elysee Lot 7 |  | SOLD |  | SOLD | SOLD |  |  |  |  | SOLD |  | SOLD |  |  | SOLD | No | SOLD | SOLD |  | SOLD | SOLD | SOLD |  | 136537 | [14 empty] | 0 | -136537
OK1922-1 | Coltrane Corner - Aya Rowe |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK1924 | Yukon Development |  | HOLD |  | HOLD | HOLD |  |  |  |  | HOLD |  | HOLD |  |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | [16 empty] | 0 | 0
OK2018 | Dr. Mackey - 61st Street |  | DEAD |  | 9050 E. 61st Street, Tulsa, OK 74145 | HOLD |  |  |  |  | HOLD |  | HOLD |  |  | HOLD | Yes | HOLD | HOLD |  | HOLD | HOLD | HOLD |  | 33274 | [14 empty] | 0 | -33274
OK2119 | OSB - Wonga Corner |  | DEAD |  | 1156 S. Douglas, Midwest City, OK 73130 | HOLD |  |  |  |  | HOLD |  | HOLD |  |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | [16 empty] | 0 | 0
OK2020-4 | Western - PT Central |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2026 | Covell I35 Edmond Dev. |  | DEAD |  | 5400 E. Covell Road, Edmond, OK | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | Yes | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2028 | Precon - Memorial Park |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 461956 | [14 empty] | 0 | -461956
OK2032-2 | Cross Roads - Dr. Rhodes |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15630 | [14 empty] | 0 | -15630
OK2032-3 | Cross Roads - State Farm |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15000 | [14 empty] | 0 | -15000
OK2032-5 | Cross Roads - Dispensary |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2036 | Dr. Matt Cole, DDS |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 41062 | [14 empty] | 0 | -41062
OK2103 | Bethesda - Santa Fe Dev. |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2105-3 | Valencia - Custom Pools |  | DEAD |  | 2215 NW 178th Street Ste. E, Edmond, OK 73012 | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 15493 | [14 empty] | 0 | -15493
OK2109-1 | Grand Blvd. Shell - OKC, OK |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2111 | Solara Surgery Center - Moore, OK |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2115 | Paul's Valley Development |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2117-1 | Paul's Valley Shell |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2117-2 | Paul's Valley Shell - Enhanced Dental |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2118 | Paul's Valley Shell - TBD |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2116 | Dollar Tree (Paul's Valley Development) |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2121 | 15th & Bryant Development | AG Fifteen RE Holdings, LLC | WILLIAMS |  | Combined with OK2122 | Combined | Yes |  | 2021-12-14 | 2022-01-03 | 2022-01-28 | 2022-02-27 | 2022-02-27 |  | 55 | 30 | No | 2022-02-21 | 2022-08-20 14:24 | 6 | 6 |  |  |  | 2860071.9 | 269645.4 |  |  | 125000 | 125000 | 125000 | 105000 |  |  |  |  | 200000 |  |  | 949645.4 | -1910426.5
OK2123 | TBD (15th & Bryant Development) |  | DEAD |  | DEAD | DEAD | No |  | DEAD |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 0 | [15 empty] | 0
OK2124 | Bodin Chiro (Lone Oak) |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2126-2 | Weatherford Shell - Dollar Tree |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
OK2127 | Legacy Martial Arts Shell | Don't know | TBD | TBD |  | Preconstruction | No |  | No | 2022-06-01 | 2022-06-01 | 2022-07-16 | 2022-07-16 | #VALUE! | 45 | 45 | No | 2022-08-15 | 2023-02-11 14:24 | 6 | 6 |  |  |  | 750000 | 0 | 0 | 0 | 50000 | 75000 | 130000 | 130000 | 130000 | 130000 | 105000 |  |  |  |  | 750000 | 0
OKxxxx | Dr. Brad Mitchell Development |  | HOLD |  | HOLD | HOLD |  |  |  |  | HOLD |  | HOLD |  |  | HOLD | No | HOLD | HOLD |  | HOLD | HOLD | HOLD | [16 empty] | 0 | 0
Okxxxx | Anytime Fitness - Brandon Porter |  | HOLD |  | HOLD | HOLD | No |  | DEAD | DEAD | DEAD | DEAD | DEAD |  | DEAD | DEAD | No | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD | [16 empty] | 0 | 0
TNxxxx | AIM Bellevue - Site Visit Needed | AG AIM Bellevue RE Holdings, LLC | TBD |  | 7734 Hwy 70 S. Nashville, TN 37221 | Preconstruction | No |  | 2022-01-31 |  | DEAD | DEAD | DEAD |  | DEAD | DEAD | No | DEAD | DEAD | DEAD | DEAD | DEAD | DEAD |  | 2400000 | [6 empty] | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 2400000 | 0
TX2004 | Marshall Ridge Dev. |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 37392 | [14 empty] | 0 | -37392
TX2009 | Alliance Pediatrics-Marsh |  | DEAD |  | DEAD | DEAD |  |  |  |  | DEAD |  | DEAD |  |  | DEAD | No | DEAD | DEAD |  | DEAD | DEAD | DEAD |  | 3575 | [14 empty] | 0 | -3575
OKxxxxTI | Yukon Nail Salon (Full Build) | AGRIGGS RE Holdings, LLC | TBD | HAYES |  | Preconstruction | No |  | 2022-01-05 |  |  |  |  | -44566 | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
[25 empty] | 6907896.9 |  | 0 | 0 | 175000 | 200000 | 255000 | 485000 | 380000 | 380000 | 355000 | 250000 | 450000 | 250000 | 650000 | 3830000 | -3077896.9
Formulas:
Brandon = [Trevor]+15
Brandon = [Brandon]+(6*4.3*7)
Trevor = [Trevor]+45
Trevor = [Trevor, row above]
Note on J13: Bobby Snyder: Don't close land until permit is in hand. Land close can be pushed
Note on L13: Bobby Snyder: Push design forward
Note on N13: Trevor Hayes: Demo Permit rcvd 2/9
Note on J17: Bobby Snyder: Don't close loan until permit is in hand
Note on L25: Bobby Snyder: Get early site release prior to full permit
Note on B27: Bobby Snyder: Existing Building
Note on T29: Bobby Snyder: Hard completion date of Aug to prevent LDs
Note on J30: Bobby Snyder: Don't close loan until permit is in hand Lot Split
Note on N30: Trevor Hayes: Title company needs to file lot split.
Note on S30: Bobby Snyder: Don't start work until the ok from DG
Note on J31: Bobby Snyder: Add 6 months to permits on TI
Note on L31: Bobby Snyder: Add 6 months to permits on TI
Note on N54: Bobby Snyder: The sewer easement is holding up the permit
Note on T54: Bobby Snyder: Open and opperating on 10/14/22. We have communicated with JackBe that this completion date may be in jepordy.
Note on N56: Bobby Snyder: Need SS to be moved prior to release of permit.
Note on L61: Trevor Hayes: Site plan application made 2/8. Can not submit until planning commision meeting.
Note on N63: Bobby Snyder: Variance meeting 2/1. We have earthwork permit in hand.
Note on N66: Bobby Snyder: Need approval on additional parking for GI Alliance 2006-4
Note on L69: Bobby Snyder: Need a permit from Trevor
Note on L70: Bobby Snyder: Cold dark shell
Note on L75: Trevor Hayes: Clock Started on 10/28
Note on L84: Bobby Snyder: Need update from Trevor. 3' of undercut over entire site. Need updated Civils to submit to SAWS -Updated civils ready 2/18. - Approvals needed: TCEQ, SAWS, Building Permit
Note on T93: Bobby Snyder: Must complete by 10/01/22
Note on B128: Bobby Snyder: Another GC built out this space.
Note on T144: Bobby Snyder: Hard completion date prior to LDs

## 04 2022
Peggy | Peggy | Ben |  | Phillip | Bobby | Danny | Brandon | Danny | Ben | Ben | Trevor | Trevor | Trevor | Trevor | Bobby | Trevor | Trevor | Trevor | Brandon | Brandon | Brandon | Brandon | Peggy | Peggy | Trevor | Trevor |  | 2022 | [11 empty] | 2023
Job Number | Project | Entity |  | SUP | Dev. Director | Address | Status | Turn Over Complete | LOI | Loan/Lease Close | Anticipated Permit Submission | Actual Permit Submitted | Anticipated Permit Received | Actual Permit Received | Delta Btwn Loan Close and Permit | Anticipated Permit Duration | Permit Approval Duration | Permit Received | Start Date | Comp Date | Planned Duration | Actual Duration | Punchlist Complete Date | Scope of Work Approved | Appraisal Budget Approved | Appraisal Value | Previously Billed | January 2022 | February 2022 | March 2022 | April 2022 | May 2022 | June 2022 | July 2022 | August 2022 | September 2022 | October 2022 | November 2022 | December 2022 | Annual 2023 | TOTAL | DELTA | COMMENTS
Adam England
OK2019 | Santa Fe Development | AG Santa Fe RE Holdings, LLC | ENGLAND | STROUD | HAYES | 100 Southwest 134th Street, OKC, OK 73170 | Construction | 2021-04-15 |  | Yes | 2021-02-16 | 2021-02-16 | 2021-04-16 | 2021-04-16 | #VALUE! | 59 | 59 | Yes | 2021-05-03 | 2022-01-10 | 8.3721 | 8.3721 |  |  | Yes | 1181869.7 | 1013323.83 | 59705.08 | 0 | 0 | [10 empty] | 1073028.91 | -108840.79
OK2025 | Autism in Motion - Santa Fe Dev. | AG AIM OK RE Holdings, LLC | ENGLAND | WILLIAMS | HAYES | 112 Southwest 134th Street, OKC, OK 73170 | Construction | 2021-05-21 |  | Yes | 2021-01-05 | 2021-01-05 | 2021-04-16 | 2021-04-16 | #VALUE! | 101 | 101 | Yes | 2021-08-07 | 2022-01-25 | 5.1827 | 5.6811 |  |  | Yes | 1051400.45 | 987033.51 | 64366.94 | 0 | 0 | [10 empty] | 1051400.45 | 0
OK2033-1 | Santa Fe Shell - Santa Fe Dev. | AG Santa Fe RE Holdings, LLC | ENGLAND | STROUD | HAYES | 112 Southwest 134th Street, OKC, OK 73170 | Construction | 2021-06-16 |  | Yes | 2021-06-15 | 2021-06-15 | 2021-08-10 | 2021-08-10 | #VALUE! | 56 | 56 | Yes | 2021-07-05 | 2022-01-28 | 6.8771 | 6.8771 |  |  | Yes | 1367413.55 | 864219.08 | 83841.4 | 12631.18 | 89678.37 | [10 empty] | 1050370.03 | -317043.52
OK2033-2 | Santa Fe Dev. - Old School Bagel | AG Santa Fe RE Holdings, LLC | ENGLAND | STROUD | HAYES | 112 SW 134th Street, Oklahoma City, OK | Construction | 2021-06-16 |  | Yes | 2021-06-20 | 2021-06-20 | 2021-12-03 | 2021-12-03 | #VALUE! | 166 | 166 | Yes | 2021-11-17 | 2022-05-23 | 3 | 6.2126 |  |  | Yes | 272915 | 139535.14 | 39753.44 | 25717.67 | 39311.75 | 25000 | 17908.75 | [8 empty] | 287226.75 | 14311.75
OK2110-1 | Shawnee Shell - Shawnee, OK | AG Harrison RE Holdings, LLC | ENGLAND | STROUD | HAYES | 4797 N. Harrison, Shawnee, OK 74804 | Construction | 2021-09-01 |  | Yes | 2021-07-14 | 2021-07-14 | 2021-09-17 | 2021-09-17 | #VALUE! | 65 | 65 | Yes | 2021-11-30 | 2022-05-25 | 5.0166 | 5.8472 |  |  | Yes | 1180416.18 | 488349.41 | 162144.05 | 91072.9 | 280084.05 | 150000 | 75000 | 63849.82 | [7 empty] | 1310500.23 | 130084.05
OK2110-2 | Shawnee Shell - Old School Bagel | AG Harrison RE Holdings, LLC | ENGLAND | STROUD | HAYES | 4799 N. Harrison, Shawnee, OK 74804 | Construction | 2021-11-19 |  | Yes | 2021-11-08 | 2021-11-08 | 2021-12-09 | 2021-12-09 | #VALUE! | 31 | 31 | Yes | 2022-02-17 | 2022-06-01 | 3 | 3.4551 |  |  | Yes | 253338.08 | 95915.97 | 0 | 69507.91 | 48892.5 | 35000 | 15000 | 2914.2 | [7 empty] | 267230.58 | 13892.5
OK2110-3 | Shawnee Shell - OSO | AG Harrison RE Holdings, LLC | ENGLAND | STROUD | HAYES | 4795 N. Harrison, Shawnee, OK 74804 | Construction | 2021-11-19 |  | Yes | 2021-12-06 | 2021-12-06 | 2022-01-14 | 2022-01-28 | #VALUE! | 39 | 53 | Yes | 2022-02-14 | 2022-05-11 | 3.5548 | 2.8571 |  |  | Yes | 402660.29 | 34445.59 | 0 | 54102 | 0 | 80000 | 80000 | 79112.7 | [7 empty] | 327660.29 | -75000
OK2128 | 150th and Penn - Old School Bagel | TAG Penn OSB RE Holdings,LLC | ENGLAND | WILLIAMS | HAYES | 15201 N. Penn Crossing Court, Oklahoma City, OK 73013 | Construction | 2022-03-04 |  | 2022-04-06 | 2022-01-19 | 2022-02-01 | 2022-03-05 | 2022-04-13 | 7 | 45 | 71 | No | 2022-04-28 | 2022-10-25 14:24 | 6 | 6 |  |  |  | 750000 | 0 | 0 | 0 | 0 | 125000 | 150000 | 150000 | 140000 | 60000 | [5 empty] | 625000 | -125000
OK2129 | Chamberlain Group (SFD) | AG Chamberlain RE Holdings, LLC | ENGLAND | STROUD | HAYES | 113 SW 134th Street, Oklahoma City, OK | Construction | 2021-12-15 |  | Yes | 2021-11-12 | 2021-11-12 | 2022-01-06 | 2021-12-30 | #VALUE! | 55 | 48 | Yes | 2022-01-11 | 2022-09-01 | 7 | 7.7409 |  |  | Yes | 1353098.44 | 86613.87 | 120514.88 | 152425.42 | 0 | 150000 | 150000 | 150000 | 175000 | 175000 | 43544.27 |  |  |  |  | 1203098.44 | -150000
OK2132-1 | Seminole Shell | AG Seminole RE Holdings, LLC | ENGLAND | STROUD | HAYES |  | Constuction | 2022-02-23 |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-01 | 2022-02-17 | -1 | 30 | 16 | Yes | 2022-03-16 | 2022-11-02 | 9 | 7.6744 |  |  |  | 1360000 | 0 | 0 | 170543 | 136059.07 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 139457 |  |  |  | 1346059.07 | -13940.93
OK2132-2 | Seminole Shell - T-Mobile | AG Seminole RE Holdings, LLC | ENGLAND | STROUD | HAYES |  | Constuction | 2022-02-23 |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-16 | 2022-02-17 | -1 | 45 | 16 | Yes | 2022-05-03 | 2022-10-30 14:24 | 5 | 6 |  |  |  | 175000 | 0 | 0 | 0 | 0 |  | 15000 | 15000 | 20000 | 50000 | 50000 | 25000 |  |  |  | 175000 | 0
OK2132-3 | Seminole Shell - Urgent Care | AG Seminole RE Holdings, LLC | ENGLAND | STROUD | HAYES |  | Constuction | 2022-02-23 |  | 2022-02-18 | 2022-01-30 | 2022-02-01 | 2022-03-16 | 2022-02-17 | -1 | 45 | 16 | Yes | 2022-05-03 | 2022-10-30 14:24 | 5 | 6 |  | 2022-04-05 |  | 300000 | 0 | 0 | 0 | 0 |  | 50000 | 50000 | 50000 | 75000 | 50000 | 25000 |  |  |  | 300000 | 0
OK2132-4 | Seminole Shell TBD TI Pharmacy | AG Seminole RE Holdings, LLC | ENGLAND | STROUD | HAYES |  | Preconstruction | No |  | 2022-02-18 | 2022-01-30 | 2022-06-01 | 2022-03-16 | 2022-07-16 | 148 | 45 | 45 | No | 2022-08-15 | 2022-12-13 09:36 | 5 | 4 |  |  |  | 95000 | 0 | 0 | 0 | 0 |  |  |  |  | 30000 | 35000 | 30000 |  |  |  | 95000 | 0
OK2135-1 | Norman Shell | TAG Norman RE Holdings, LLC | ENGLAND | STROUD | CISPER |  | Construction | 2022-03-01 |  | 2022-02-24 | 2022-02-09 | 2022-02-01 | 2022-03-26 | 2022-03-03 | 7 | 45 | 30 | Yes | 2022-03-28 | 2022-12-23 21:36 | 9 | 9 |  |  |  | 1200000 | 0 | 0 | 129788.5 | 138269.44 | 100000 | 100000 | 100000 | 125000 | 125000 | 125000 | 125000 | 125000 | 45211.5 |  | 1238269.44 | 38269.44
OK2135-2 | Norman Shell - TI | TAG Norman RE Holdings, LLC | ENGLAND | STROUD | CISPER |  | Preconstruction | No |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2135-3 | Norman Shell - Old School Bagel | TAG Norman RE Holdings, LLC | ENGLAND | STROUD | CISPER |  | Constuction | 2022-03-01 |  | 2022-02-24 | 2022-02-09 | 2022-03-18 | 2022-03-26 | 2022-04-13 | 48 | 45 | 26 | No | 2022-05-13 | 2022-09-10 09:36 | 4 | 4 |  |  |  | 300000 | 0 | 0 | 0 | 0 | [5 empty] | 50000 | 50000 | 75000 | 75000 | 50000 | 300000 | 0
OK2135-4 | Norman Shell - SWIG | TAG Norman RE Holdings, LLC | ENGLAND | STROUD | CISPER |  | Preconstruction | No |  | 2022-02-24 | 2022-02-09 | 2022-07-01 | 2022-03-26 | 2022-08-15 | 172 | 45 | 45 | No | 2022-09-14 | 2023-01-12 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
TN2101 | AIM - Memphis, TN | AG AIM Memphis RE Holdings, LLC | ENGLAND | N/A | HAYES | 7007 Stage Rd., Memphis, TN 38133 | Construction | 2021-11-01 |  | Yes | 2021-06-18 | 2021-06-18 | 2021-10-20 | 2021-10-20 | #VALUE! | 124 | 124 | Yes | 2021-11-04 | 2022-03-31 | 4.8837 | 4.8837 |  |  | Yes | 1207444.74 | 527222.16 | 0 | 255699 | 424523.58 | 74523.58 | [9 empty] | 1281968.32 | 74523.58
[26 empty] | 12450556.43 | 4236658.56 | 530325.79 | 961487.58 | 1156818.76 | 889523.58 | 802908.75 | 760876.72 | 660000 | 665000 | 503544.27 | 394457 | 200000 | 120211.5 | 50000 | 11931812.51 | -518743.92
Kyle Tedlock | [41 empty] | 0
OK1923-6 | Riverwest - Old School Bagel | Riverwest RE Holdings, LLC | TEDLOCK | RONS | HAYES | 152 W Alexander Blvd., Sand Springs, OK 74063 | Construction | 2021-02-11 |  | Yes | 2021-06-01 | 2021-06-01 | 2021-06-15 | 2021-06-15 | #VALUE! | 14 | 14 | Yes | 2021-05-28 | 2021-10-28 | 5 | 5.0831 |  |  | Yes | 89125 | 58100 | 0 | 0 | 80387.15 | [10 empty] | 138487.15 | 49362.15
OK1925 | Glenn Pool - Old School Bagel Express (Stand Alone) | TAG Glenpool OSB RE Holdings,LLC | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-04-30 | 2022-02-09 | 2022-04-04 | 2022-02-28 | 2022-05-04 | 4 | 19 | 30 | No | 2022-05-04 | 2022-10-01 | 2.5249 | 4.9834 |  |  |  | 725000 | 0 | 0 | 0 | 0 | [8 empty] | 725000 |  | 725000 | 0
OK2016 | OneCore | TAG OneCore RE Holdings, LLC | TEDLOCK | HALL | N/A | 100 NE 85th Street, OKC, OK 73114 | Construction | 2020-10-01 |  | Yes | 2020-08-11 | 2020-08-11 | 2020-11-12 | 2020-11-12 | #VALUE! | 93 | 93 | Yes | 2020-10-15 | 2021-12-01 | 14 | 13.6877 |  |  | Yes | 14188397.56 | 13413397.56 | 812671.7 | 0 | 81884 | [10 empty] | 14307953.26 | 119555.7
OK2032-1 | Cross Roads - Shell | AG Broken Arrow RE Holdings, LLC | TEDLOCK | RONS | HAYES | 1167 N. 38th Street, Broken Arrow, OK 74014 | Construction | N/A |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2032-4 | Cross Roads - Old School Bagel | AG Broken Arrow RE Holdings, LLC | TEDLOCK | RONS | HAYES | 1171 N. 38th Street, Broken Arrow, OK 74014 | Construction | 2021-09-15 |  | Yes | 2021-08-09 | 2021-08-09 | 2021-08-10 | 2021-08-10 | #VALUE! | 1 | 1 | Yes | 2021-10-01 | 2022-03-08 | 4 | 5.2492 |  |  | Yes | 295011.29 | 264663.85 | 0 | 0 | 36793.4 | [10 empty] | 301457.25 | 6445.96
OK2122 | The Learning Experence (15th & Bryant Development) | AG Fifteen RE Holdings, LLC | TEDLOCK | WILLIAMS | HAMMOND |  | Construction | 2022-03-24 |  | 2021-12-14 | 2022-01-28 | 2021-12-02 | 2022-02-27 | 2022-03-31 | 107 | 30 | 119 | Yes | 2022-03-31 | 2022-08-31 | 6.3455 | 5.0831 |  |  | Yes | 2860072 | 0 | 0 | 125981 | 53207.75 | 250000 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 184091 |  | 2663279.75 | -196792.25
OK2134-1 | Glenn Pool Shell | TAG Glenpool RE Holdings, LLC | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | 2022-04-15 |  | 2022-04-08 | 2022-01-30 | 2022-01-15 | 2022-03-01 | 2022-04-04 | -4 | 30 | 79 | No | 2022-04-30 | 2023-01-25 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 | 0 | 0 | 100000 | 150000 | 200000 | 200000 | 200000 | 250000 | 250000 | 250000 | 200000 | 200000 | 2000000 | 0
OK2134-2 | Glenn Pool Shell - TI #1 | TAG Glenpool RE Holdings, LLC | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2134-3 | Glenn Pool Shell - TI #2 | TAG Glenpool RE Holdings, LLC | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2134-4 | Glenn Pool Shell - TI #3 | TAG Glenpool RE Holdings, LLC | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2134-5 | Glenn Pool Shell - TI #4 | TAG Glenpool RE Holdings, LLC | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2134-6 | Glenn Pool Shell - TI #5 | TAG Glenpool RE Holdings, LLC | TEDLOCK | RONS | HAYES | Glenn Pool, OK | Preconstruction | No |  | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-07-29 | 2022-07-29 | 45 | 45 | 45 | No | 2022-08-18 | 2022-12-16 09:36 | 4 | 4 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
[26 empty] | 20157605.85 | 13736161.41 | 812671.7 | 125981 | 252272.3 | 350000 | 400000 | 500000 | 500000 | 500000 | 550000 | 550000 | 550000 | 1109091 | 200000 | 20136177.41 | -21428.44
Kimberly Kelly | [41 empty] | 0
TX1903 | Ramon Franklin Warehouse | Don't Own | KELLY | MILLER | N/A | 1308 Corporate Drive East, Arlinton, TX 76006 | Construction | 2020-06-18 |  | N/A | 2020-12-09 | 2020-12-09 | 2021-01-27 | 2021-01-27 | N/A | 49 | 49 | Yes | 2021-07-05 | 2021-12-10 | 5 | 5.2492 |  |  | Yes | 1006578.9 | 1006578.9 | 0 | 413409.04 | 0 | [10 empty] | 1419987.94 | 413409.04
TX2101 | Bob Mills - Forth Worth | Don't Own | KELLY | JOHNSON | N/A | 3600 East Long Ave., Ft Worth, TX 76111 | Construction | 2021-05-20 |  | N/A | 2021-04-09 | 2021-04-09 | 2021-06-10 | 2021-06-10 | N/A | 62 | 62 | Yes | 2021-07-10 | 2021-12-10 | 5 | 5.0831 |  |  | Yes | 2315782.2 | 2304152.2 | 38625.5 | 0 | 0 | [10 empty] | 2342777.7 | 26995.5
[26 empty] | 3322361.1 | 3310731.1 | 38625.5 | 413409.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762765.64 | 440404.54
Tiffany Shiel | [41 empty] | 0
OK2106-1 | Fox Lake Shell | TAG Fox Lake RE Holdings, LLC | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Construction | 2021-07-01 |  | Yes | 2021-06-22 | 2021-06-22 | 2021-09-22 | 2021-09-22 | #VALUE! | 92 | 92 | Yes | 2021-07-22 | 2022-11-15 | 13 | 15.9801 |  |  | Yes | 12193746.8 | 3069014.06 | 532188.35 | 1527507.98 | 798302.17 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 750000 | 250000 | 65036.41 |  |  | 11992048.97 | -201697.83
OK2106-2 | Fox Lake - Sidecar | TAG Fox Lake RE Holdings, LLC | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-05-11 | 2022-06-23 | 2022-06-25 | #VALUE! | 45 | 45 | No | 2022-07-01 | 2022-12-28 14:24 | 6 | 6 |  |  |  | 980000 | 0 | 0 | 0 | 0 | 100000 | 125000 | 150000 | 200000 | 200000 | 155000 |  |  |  |  | 930000 | -50000
OK2106-3 | Fox Lake - Hatch | TAG Fox Lake RE Holdings, LLC | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-05-11 | 2022-06-23 | 2022-06-25 | #VALUE! | 45 | 45 | No | 2022-07-01 | 2022-12-28 14:24 | 6 | 6 |  |  |  | 1558000 | 0 | 0 | 0 | 0 | 125000 | 225000 | 300000 | 300000 | 300000 | 258000 |  |  |  |  | 1508000 | -50000
OK2106-4 | Fox Lake - Enhanced Dental | TAG Fox Lake RE Holdings, LLC | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-03-02 | 2022-03-02 | 2022-04-08 | 2022-04-15 | #VALUE! | 37 | 44 | No | 2022-05-15 | 2022-11-11 14:24 | 6 | 6 |  |  |  | 540000 | 0 | 0 | 0 | 0 | 75000 | 90000 | 100000 | 100000 | 100000 | 50000 |  |  |  |  | 515000 | -25000
OK2106-5 | Fox Lake - Chicago Title | TAG Fox Lake RE Holdings, LLC | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-04-11 | 2022-04-15 | 2022-05-26 | 2022-05-30 | #VALUE! | 45 | 45 | No | 2022-06-29 | 2022-12-26 14:24 | 6 | 6 |  |  |  | 800000 | 0 | 0 | 0 | 0 | 125000 | 125000 | 150000 | 150000 | 125000 | 50000 |  |  |  |  | 725000 | -75000
OK2106-6 | Fox Lake Provision Concepts | TAG Fox Lake RE Holdings, LLC | SHIEL | ECKER | HAMMOND | 851 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-06-23 | 2022-06-23 | 2022-08-07 | #VALUE! | 45 | 45 | No | 2022-09-06 | 2023-03-05 14:24 | 6 | 6 |  |  |  | 690000 | 0 | 0 | 0 | 0 | 100000 | 120000 | 120000 | 120000 | 120000 | 60000 |  |  |  |  | 640000 | -50000
OK2106-7 | Fox Lake TBD | TAG Fox Lake RE Holdings, LLC | SHIEL | ECKER | HAMMOND | 852 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-06-23 | 2022-06-23 | 2022-08-07 | #VALUE! | 45 | 45 | No | 2022-09-06 |  |  | -1488.7043 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2106-8 | Fox Lake Chicken Foote | TAG Fox Lake RE Holdings, LLC | SHIEL | ECKER | HAMMOND | 853 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | 2022-05-09 | 2022-06-23 | 2022-06-23 | 2022-08-07 | #VALUE! | 45 | 45 | No | 2022-09-06 | 2023-02-01 |  | 4.9169 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OK2106-9 | Fox Lake Regent Bank | TAG Fox Lake RE Holdings, LLC | SHIEL | ECKER | HAMMOND | 854 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | No |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
[26 empty] | 16761746.8 | 3069014.06 | 532188.35 | 1527507.98 | 798302.17 | 1525000 | 1685000 | 1820000 | 1870000 | 1845000 | 1323000 | 250000 | 65036.41 | 0 | 0 | 16310048.97 | -451697.83
Bob Solomon | [41 empty] | 0
OK2034 | Dr. Rex Johnson, DVM - Covell I35 | AG Waterloo RE Holdings, LLC | SOLOMON | WILLIAMS | HAYES | 5401 E. Covel Rd., Edmond, OK 73034 | Construction | 2021-06-11 |  | Yes | 2021-05-12 | 2021-05-12 | 2021-08-10 | 2021-08-10 | #VALUE! | 90 | 90 | Yes | 2021-08-16 | 2022-05-20 | 9 | 9.2027 |  |  | Yes | 1961015.83 | 952423.73 | 173273.61 | 93239.18 | 115103.75 | 225000 | 225000 | 67079.31 | [7 empty] | 1851119.58 | -109896.25
OK2107 | Jack Be Grocery - Edmond | AG May RE Holdings, LLC | SOLOMON | STRUB | CISPER | 855 W. I35 Access Rd., Edmond, OK 73034 | Preconstruction | 2022-04-11 |  | 2022-03-30 | 2022-01-31 | 2022-02-03 | 2022-03-17 | 2022-04-15 | 16 | 45 | 71 | No | 2022-04-15 | 2022-10-12 14:24 | 6 | 6 |  |  |  | 2500000 | 0 | 0 | 0 | 0 | 125000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 700000 | 2425000 | -75000
OK2112 | Covell 35 Dev. - Dr. Lu Dentistry | AG Medical RE Holdings, LLC | SOLOMON | WILLIAMS | HAYES | 5249 E. Covel Rd., Edmond, OK 73034 | Construction | 2021-11-19 |  | Yes | 2021-10-20 | 2021-10-20 | 2021-12-10 | 2021-12-10 | #VALUE! | 51 | 51 | Yes | 2021-12-22 | 2022-06-30 | 9 | 6.3123 |  |  | Yes | 762952.96 | 92185.59 | 111281.22 | 64974.74 | 100946.93 | 100000 | 125000 | 100000 | 69511.41 | [6 empty] | 763899.89 | 946.93
OK2125-1 | Enid Shell | AG Enid RE Holdings, LLC | SOLOMON | RONS | HAYES |  | Construction | 2022-01-27 |  | 2022-01-13 | 2021-12-13 | 2022-01-14 | 2022-01-17 | 2022-02-23 | 41 | 35 | 40 | Yes | 2022-02-28 | 2022-09-16 | 9 | 6.6445 |  |  |  | 1500000 | 0 | 0 | 192361.11 | 27166.45 | 100000 | 150000 | 175000 | 175000 | 175000 | 175000 | 175000 | 100000 | 32638.89 |  | 1477166.45 | -22833.55
OK2125-2 | Enid - Old School Bagel | AG Enid RE Holdings, LLC | SOLOMON | RONS | HAYES |  | Preconstruction | 2022-04-15 |  | 2022-01-13 | 2022-01-14 | 2022-02-18 | 2022-02-28 | 2022-03-16 | 62 | 45 | 26 | Yes | 2022-05-09 | 2022-09-06 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 | 0 | 75975.43 | 150000 | 50000 | [8 empty] | 275975.43 | -74024.57
OK2125-3 | Enid - Enhanced Dental | AG Enid RE Holdings, LLC | SOLOMON | RONS | HAYES |  | Preconstruction | 2022-04-15 |  | 2022-01-13 | 2022-01-14 | 2022-02-18 | 2022-02-28 | 2022-03-16 | 62 | 45 | 26 | Yes | 2022-05-09 | 2022-09-06 09:36 | 4 | 4 |  |  |  | 450000 | 0 | 0 | 0 | 26192.88 | 50000 | 75000 | 75000 | 75000 | 75000 | 75000 | 25000 |  |  |  | 476192.88 | 26192.88
[26 empty] | 7523968.79 | 1044609.32 | 284554.83 | 350575.03 | 345385.44 | 750000 | 825000 | 617079.31 | 519511.41 | 450000 | 450000 | 400000 | 300000 | 232638.89 | 700000 | 7269354.23 | -254614.56
Kevin Trosper | [41 empty] | 0
OK2102 | Puppy Paws East Edmond | AG Puppy Covell RE Holdings, LLC | TROSPER | TBD | HAYES | East Edmond | Preconstruction | No |  | 2022-03-21 | 2022-02-05 | 2022-05-11 | 2022-04-16 | 2022-07-10 | 111 | 70 | 60 | No | 2022-06-04 | 2023-03-01 21:36 | 9 | 9 |  |  |  | 2200000 | 0 | 0 | 0 | 147115.94 | 200000 | 260000 | 260000 | 300000 | 300000 | 260000 | 260000 | 210000 |  |  | 2197115.94 | -2884.06
OK2105-3 | Valencia - Winfield and Co. | AG Valencia RE Holdings, LLC | TROSPER | TROSPER | N/A | 2216 NW 178th Street Ste. E, Edmond, OK 73012 | Construction | 2021-09-15 |  | Yes | 2021-09-01 | 2021-09-01 | 2021-09-16 | 2021-09-16 | #VALUE! | 15 | 15 |  | 2021-09-22 | 2021-10-17 | 1 | 0.83056 |  |  | Yes | 27626.4 | 11493 | 16133.4 | 0 | 0 | [10 empty] | 27626.4 | 0
OK2108 | Puppy Paws - Lone Oak | AG Puppy West RE Holdings, LLC | TROSPER | WILLIAMS | HAYES | 15200 Crown at Lone Oak, Edmond OK 73013 | Construction | 2022-01-14 |  | Yes | 2021-11-19 | 2021-11-19 | 2022-01-06 | 2022-02-14 | #VALUE! | 48 | 87 | Yes | 2022-02-21 | 2022-11-30 | 9 | 9.3688 |  |  |  | 2200000 | 0 | 0 | 212179 | 291481.14 | 250000 | 275000 | 300000 | 250000 | 250000 | 250000 | 187821 |  |  |  | 2266481.14 | 66481.14
OK2126-1 | Weatherford Shell | AG Weatherford RE Holdings, LLC | TROSPER | STEPHENSON | HAYES |  | Construction | 2022-01-27 |  | 2022-01-14 | 2021-12-13 | 2022-01-14 | 2022-01-13 | 2022-01-21 | 7 | 31 | 7 | Yes | 2022-02-14 | 2022-08-19 | 8 | 6.1794 |  |  |  | 1200000 | 0 | 0 | 240339.48 | 284536.77 | 150000 | 150000 | 200000 | 200000 | 100000 | 84660.52 |  |  |  |  | 1409536.77 | 209536.77
OK2126-3 | Weatherford Shell - Enhanced Dental | AG Weatherford RE Holdings, LLC | TROSPER | STEPHENSON | HAYES |  | Construction | No |  | 2022-01-14 | 2021-12-30 | 2022-02-16 | 2022-03-16 | 2022-03-23 | 68 | 76 | 35 | Yes | 2022-04-21 | 2022-08-19 09:36 | 4 | 4 |  |  |  | 350000 | 0 | 0 | 0 | 0 | 75000 | 100000 | 100000 | 25000 | [6 empty] | 300000 | -50000
TX2006-1 | Sunnyvale Shell | AG Sunnyvale RE Holdings, LLC | TROSPER | DOYLE | CISPER | 480 US Hwy 80, Sunnyvale, TX 75182 | Construction | 2022-08-10 |  | Yes | 2021-06-22 | 2021-06-22 | 2021-11-09 | 2021-11-09 | #VALUE! | 140 | 140 | Yes | 2021-11-17 | 2022-06-01 | 7 | 6.5116 |  |  | Yes | 1910049.56 | 892016.83 | 304883.09 | 284226.25 | 241178.58 | 128923.39 | [9 empty] | 1851228.14 | -58821.42
TX2006-2 | Sunnyvale Shell - Dr. Luna | AG Sunnyvale RE Holdings, LLC | TROSPER | DOYLE | CISPER | 481 US Hwy 80, Sunnyvale, TX 75182 | Construction | 2022-08-10 |  | Yes | 2021-12-21 | 2021-12-13 | 2022-01-27 | 2022-01-24 | #VALUE! | 37 | 42 | Yes | 2022-02-07 | 2022-07-02 | 3 | 4.8173 |  |  | Yes | 288979.2 | 17537.69 | 0 | 0 | 171149.96 | 95000 | 76441.51 | [8 empty] | 360129.16 | 71149.96
TX2006-3 | Sunnyvale Shell - Dr. Rohani | AG Sunnyvale RE Holdings, LLC | TROSPER | DOYLE | CISPER | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction | 2022-08-10 |  | Yes | 2021-12-21 | 2021-12-29 | 2022-02-04 | 2022-01-24 | #VALUE! | 45 | 26 | Yes | 2022-02-07 | 2022-07-02 | 3 | 4.8173 |  |  | Yes | 376822.32 | 20124 | 0 | 0 | 203849.39 | 100000 | 100000 | 31698.32 | [7 empty] | 455671.71 | 78849.39
TX2006-4 | Sunnyvale Shell - GI Alliance | AG Sunnyvale RE Holdings, LLC | TROSPER | DOYLE | CISPER | 482 US Hwy 80, Sunnyvale, TX 75182 | Construction | N/A |  | Yes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
TX2005 | McKinney Development | AG Virginia Ridge RE Holdings, LLC | TROSPER | DOYLE | CISPER | Virginia and Ridge Road, McKinney, TX | Preconstruction | No |  | Yes | 2021-10-01 | 2021-10-01 | 2022-01-14 | 2022-11-01 | #VALUE! | 105 | 396 | No | 2022-11-08 | 2023-08-05 21:36 | 9 | 9 |  |  |  | 600000 | 0 | 0 | 0 | 63350.47 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 120000 |  |  |  | 663350.47 | 63350.47
TX2008 | Dr. Barbara Lee (McKinney Development) | AG Virginia RE Holdings, LLC | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No |  | 2022-04-13 | 2021-10-22 | 2021-10-01 | 2022-05-22 | 2022-11-01 | 202 | 233 | 396 | No | 2022-11-08 | 2023-08-05 21:36 | 9 | 9 |  |  |  | 750000 | 0 | 0 | 0 | 0 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 65000 | 145000 |  |  | 750000 | 0
TX2103-1 | McKinney Shell (McKinney Development) | AG Virginia Ridge RE Holdings, LLC | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No |  | Yes | 2022-02-04 | 2021-10-01 | 2022-05-22 | 2022-11-01 | #VALUE! | 233 | 396 | No | 2022-11-08 | 2023-05-07 14:24 | 6 | 6 |  |  |  | 600000 | 0 | 0 | 0 | 78765.18 |  |  | 25000 | 50000 | 80000 | 80000 | 80000 | 80000 | 80000 | 125000 | 678765.18 | 78765.18
TX2103-2 | TBD TI (McKinney Shell) | AG Virginia Ridge RE Holdings, LLC | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No |  | Yes | 2022-02-04 | 2022-10-01 | 2022-05-05 | 2022-11-01 | #VALUE! | 90 | 31 | No | 2022-11-08 | 2023-02-06 07:12 | 9 | 3 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
TX2103-3 | TBD TI (McKinney Shell) | AG Virginia Ridge RE Holdings, LLC | TROSPER | DOYLE | CISPER | McKinney, TX | Preconstruction | No |  | Yes | 2022-02-04 | 2022-10-01 | 2022-05-05 | 2022-11-01 | #VALUE! | 90 | 31 | No | 2022-11-08 | 2023-02-06 07:12 | 9 | 3 |  |  |  |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
TX2007-1 | Carrollton Shell | AG Carrolton RE Holdings, LLC | TROSPER | DOYLE | CISPER | Carrollton, TX | Preconstruction | 2022-05-01 |  | Yes | 2021-10-28 | 2021-06-15 | 2021-12-17 | 2022-05-31 | #VALUE! | 50 | 350 | No | 2022-06-01 | 2023-02-26 21:36 | 9 | 9 |  |  |  | 2000000 | 0 | 0 | 210901.5 | 0 | 125000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 164098.5 |  | 1900000 | -100000
TX2007-2 | Carrolton Shell - Dr. Bui | AG Carrolton RE Holdings, LLC | TROSPER | DOYLE | CISPER | Carrollton, TX | Preconstruction | 2022-05-01 |  | Yes | 2021-11-26 | 2022-07-10 | 2022-02-24 | 2022-09-08 | #VALUE! | 90 | 60 | No | 2022-08-30 | 2023-02-26 14:24 | 4 | 6 |  |  |  | 550000 | 0 | 0 | 43599.5 | 0 |  |  |  |  | 100000 | 100000 | 125000 | 100000 | 81400.5 |  | 550000 | 0
[26 empty] | 13053477.48 | 941171.52 | 321016.49 | 991245.73 | 1481427.43 | 1293923.39 | 1331441.51 | 1286698.32 | 1195000 | 1200000 | 1144660.52 | 1037821 | 735000 | 325499 | 125000 | 13409904.91 | 356427.43
Preconstruction | [41 empty] | 0
OK2037 | Master Hand Milling | TBD | TBD | TBD | TBD | TBD, Edmond, OK | Preconstruction | No |  | No | 2022-06-01 | 2022-05-23 | 2022-07-16 | 2022-07-07 | #VALUE! | 45 | 45 | No | 2022-08-06 | 2023-08-02 04:48 | 12 | 12 |  |  |  | 4000000 | 0 | 0 | 0 | 0 | 250000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 830000 | 3800000 | -200000
OK2114-1 | Chamberlain Realty - Lone Oak | AG Chamberlain West RE Holdings, LLC | TBD | TBD | HAYES | 15103 Crown at Lone Oak Rd., Edmond, OK 73013 | Preconstruction | No |  | 2022-06-01 | 2022-04-17 | 2022-05-01 | 2022-06-01 | 2022-05-29 | -3 | 45 | 28 | No | 2022-06-01 | 2022-11-28 14:24 | 6 | 6 |  |  |  | 988611 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 |  |  |  |  | 25000 |  | 588611 | 913611 | -75000
OK2120 | Peak View Brewery and Distillery | Don't know | TBD | TBD | TBD | Reservoir by Costco | Preconstruction | No |  | 2022-08-24 | 2022-04-17 | 2022-07-10 | 2022-06-01 | 2022-08-24 | 0 | 45 | 45 | No | 2022-06-01 | 2023-03-29 | 10 | 10 |  |  |  | 3000000 | 0 | 0 | 0 | 0 | 250000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 225000 | 2875000 | -125000
OK2130 | Regent Center Development | AG Regent BA RE Holdings, LLC | TEDLOCK | RONS | CISPER | Broken Arrow, OK | Preconstruction | No |  | 2023-02-01 | 2022-05-01 | 2022-08-05 | 2022-06-30 | 2023-02-01 | 0 | 60 | 180 | No | 2023-03-03 | 2024-02-27 04:48 | 12 | 12 |  |  |  | 14000000 | 0 | 0 | 0 | 0 | [5 empty] | 1250000 | 1250000 | 1250000 | 1250000 | 9000000 | 14000000 | 0
TX2102-1 | San Antonio Shell | AG 281 RE Holdings, LLC | TBD | TBD | HAMMOND | San Antonio, TX | Preconstruction | No |  | Yes | 2022-02-18 | 2022-02-18 | 2022-02-28 | 2022-06-06 | #VALUE! | 10 | 108 | No | 2022-06-13 | 2023-03-10 21:36 | 9 | 9 |  |  |  | 2229000 | 0 | 0 | 201811 | 0 |  |  | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 204000 | 323189 | 2229000 | 0
TX2102-2 | Dr. Abeskharon - San Antonio | AG 281 RE Holdings, LLC | TBD | TBD | HAMMOND | San Antonio, TX | Preconstruction | No |  | Yes | 2021-11-30 | 2022-06-06 | 2022-02-28 | 2022-07-21 | #VALUE! | 90 | 45 | No | 2022-10-19 | 2023-02-16 09:36 | 4 | 4 |  |  |  | 360000 | 0 | 0 | 21249 | 0 | [7 empty] | 125000 | 125000 | 88751 | 360000 | 0
| Cleveland Enhanced Dental | AG Cleveland RE Holdings, LLC | TBD | TBD | HAYES | Cleveland, OK | Preconstruction | No |  | 2022-05-23 | 2022-05-09 | 2022-05-09 | 2022-06-28 | 2022-05-23 | 0 | 50 | 14 | No | 2022-05-23 | 2022-11-19 14:24 | 4 | 6 |  |  |  | 900000 | 0 | 0 | 0 | 0 | [9 empty] | 900000 | 900000 | 0
| Anna Shell TX | AG Anna RE Holdings, LLC | TBD | TBD | HAYES |  | Preconstruction | No |  | 2022-07-06 | 2022-08-19 | 2022-08-19 | 2022-09-28 | 2022-09-28 | 84 | 40 | 40 | No | 2022-10-05 | 2023-10-01 04:48 | 4 | 12 |  |  |  | 5000000 | 0 | 0 | 0 | 0 |  |  |  |  | 250000 | 250000 | 250000 | 250000 | 250000 | 3750000 | 5000000 | 0
| Hough Ear - OKC | AG Artesian RE Holdings, LLC | TBD | TBD |  |  | Preconstruction | No |  | 2022-07-26 | 2022-05-27 | 2022-05-27 | 2022-07-26 | 2022-07-26 | 0 | 60 | 60 | No | 2022-08-02 | 2023-07-29 04:48 | 4 | 12 |  |  |  | 8000000 | 0 | 0 | 0 | 0 | [5 empty] | 250000 | 275000 | 275000 | 275000 | 6925000 | 8000000 | 0
| Mingee LVM Investments | AG Half RE Holdings, LLC | TBD | TBD | HAMMOND |  | Preconstruction | No |  | 2022-08-01 | 2022-06-17 | 2022-06-17 | 2022-08-01 | 2022-08-01 | 0 | 45 | 45 | No | 2022-08-08 | 2023-08-04 04:48 | 4 | 12 |  |  | 2022-05-20 | 9600000 | 0 | 0 | 0 | 0 | [9 empty] | 9600000 | 9600000 | 0
| Dr. Kramer - Edmond Family Dental Designs |  | TBD | TBD | HAMMOND |  | Preconstruction | No |  | 2022-09-12 | 2022-05-15 | 2022-05-15 | 2022-09-12 | 2022-09-12 | 0 | 120 | 120 | No | 2022-09-19 | 2023-03-18 14:24 | 6 | 6 |  |  | 2022-06-29 | 1800000 | 0 | 0 | 0 | 0 | [9 empty] | 1800000 | 1800000 | 0
| JackBe Mustang |  | TBD | TBD | CISPER | Mustang, OK | Preconstruction | No |  | 2022-06-21 | 2022-05-17 | 2022-05-17 | 2022-07-01 | 2022-07-01 | 10 | 45 | 45 | No | 2022-07-08 | 2023-01-04 14:24 | 6 | 6 |  |  |  | 3200000 | 0 | 0 | 0 | 0 | [9 empty] | 3200000 | 3200000 | 0
| JackBe Edmond |  | TBD | TBD | CISPER |  | Preconstruction | No |  | 2022-05-23 | 2022-04-29 | 2022-04-29 | 2022-05-29 | 2022-05-29 | 6 | 30 | 30 | No | 2022-06-05 | 2022-09-30 | 4 | 3.887 |  |  |  | 1500000 | 0 | 0 | 0 | 0 | [9 empty] | 1500000 | 1500000 | 0
| Yukon TI-Chamberlin Realty |  | TBD | TBD | [15 empty] | 2022-06-30 | 3
[26 empty] | 54577611 | 0 | 0 | 223060 | 0 | 600000 | 740000 | 990000 | 890000 | 1140000 | 2640000 | 2665000 | 2815000 | 2744000 | 38730551 | 54177611 | -400000
0
[22 empty] | Billing Total |  |  |  | 182424938.45 | 26338345.97 | 2519382.66 | 4816326.36 | 4034206.1 | 5161679 | 5799709 | 5992605 | 5940000 | 6300000 | 5992200 | 5492435 | 6248440 | 5475600 | 78536102 | 181175285.67 | -1249652.78
[26 empty] | Billing Goal |  | 3086105 | 3235500 | 4441510 | 6000000 | 6825000 | 7100000 | 7100000 | 7000000 | 6500000 | 6500000 | 6500000 | 6500000 | 80000000
[26 empty] | Difference |  | -566722.34 | 1580826.36 | -407303.9 | -838321 | -1025291 | -1107395 | -1160000 | -700000 | -507800 | -1007565 | -251560 | -1024400 | -1463898
[39 empty] | 2021 | 45000000
COMPLETED | [41 empty] | 0
OK1936 | Dr Fischer | AG Medical RE Holdings ,LLC |  | RONS | N/A | 720 West 71St Street S, Tulsa, OK 74132 | Construction | 2020-05-28 |  | Yes | 2020-04-08 | 2020-04-08 | 2020-06-22 | 2020-06-22 | #VALUE! | 75 | 75 | Yes | 2020-06-22 | 2021-09-30 | 15 | 15.4485 |  |  | Yes | 2482029.51 | 2482029.51 | 0 | 0 | 0 | [10 empty] | 2482029.51 | 0
OK2008 | Dr. Gaches | AG Hi Point RE Holdings, LLC |  | RONS | N/A | 11492 N. 137th E. Ave., Owasso, OK | Construction | 2021-04-01 |  | Yes | 2020-08-28 | 2020-08-28 | 2021-03-05 | 2021-03-05 | #VALUE! | 189 | 189 | Yes | 2021-04-04 | 2021-10-15 | 6 | 6.4452 |  |  | Yes | 712367.43 | 712367.43 | 0 | 0 | 0 | [10 empty] | 712367.43 | 0
OK2014 | Clark Plaza Shell | AG Clark RE Holdings, LLC |  | RONS | N/A | 7877 E 71st South., Tulsa, OK 74133 | Construction | Yes |  | Yes | 2020-10-16 | 2020-10-16 | 2021-02-19 | 2021-02-19 | #VALUE! | 126 | 126 | Yes | 2021-03-01 | 2021-12-27 | 10 | 10 |  |  | Yes | 1436404.19 | 1436404.19 | 0 | 0 | 0 | [10 empty] | 1436404.19 | 0
OK2014-1 | Clark Shell - Dr. Pfeffer | AG Clark RE Holdings, LLC |  | RONS | N/A | 7877 E 71st South Ste A, Tulsa, OK 74133 | Construction | 2021-01-19 |  | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | #VALUE! | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 19:12 | 8 | 8 |  |  | Yes | 648252.98 | 648252.98 | 0 | 0 | 0 | [10 empty] | 648252.98 | 0
OK2014-2 | Clark Shell - Enhance DDS | AG Clark RE Holdings, LLC |  | RONS | N/A | 7877 E 71st South Ste B., Tulsa, OK 74133 | Construction | 2021-01-19 |  | Yes | 2020-12-03 | 2020-12-03 | 2021-03-25 | 2021-03-25 | #VALUE! | 112 | 112 | Yes | 2021-03-29 | 2021-11-24 | 8 | 7.9734 |  |  | Yes | 400186.6 | 400186.6 | 0 | 0 | 0 | [10 empty] | 400186.6 | 0
OKxxxxTI | Montapp Retail Fyzical Theropy (White Box) | Glenpool RE Holdings, LLC |  | RONS | HAYES | Glenn Pool, OK | Preconstruction | Yes |  | 2022-01-05 |  |  |  |  | -44566 | 0 | 0 | No | [8 empty] | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
OKxxxxTI | Cross Roads - Broken Arrow - Dr. Shambille (WGS) | AG Broken Arrow RE Holdings, LLC |  | TBD | HAYES | Broken Arrow, OK | Preconstruction | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
DEAD / HOLD / SOLD | [41 empty] | 0
FL2001 | Elysee Lot 6 |  |  | SOLD |  |  | SOLD | [18 empty] | 137906 | [14 empty] | 0 | -137906
FL2002 | Elysee Lot 7 |  |  | SOLD |  |  | SOLD | [18 empty] | 136537 | [14 empty] | 0 | -136537
OK1922-1 | Coltrane Corner - Aya Rowe |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK1924 | Yukon Development |  |  | DEAD |  |  | HOLD | [33 empty] | 0 | 0
OK2018 | Dr. Mackey - 61st Street |  |  | DEAD |  | 9050 E. 61st Street, Tulsa, OK 74145 | HOLD | [18 empty] | 33274 | [14 empty] | 0 | -33274
OK2119 | OSB - Wonga Corner |  |  | DEAD |  | 1156 S. Douglas, Midwest City, OK 73130 | HOLD | [33 empty] | 0 | 0
OK2020-4 | Western - PT Central |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2026 | Covell I35 Edmond Dev. |  |  | DEAD |  | 5400 E. Covell Road, Edmond, OK | DEAD | [33 empty] | 0 | 0
OK2028 | Precon - Memorial Park |  |  | DEAD |  |  | DEAD | [18 empty] | 461956 | [14 empty] | 0 | -461956
OK2032-2 | Cross Roads - Dr. Rhodes |  |  | DEAD |  |  | DEAD | [18 empty] | 15630 | [14 empty] | 0 | -15630
OK2032-3 | Cross Roads - State Farm |  |  | DEAD |  |  | DEAD | [18 empty] | 15000 | [14 empty] | 0 | -15000
OK2032-5 | Cross Roads - Dispensary |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2036 | Dr. Matt Cole, DDS |  |  | DEAD |  |  | DEAD | [18 empty] | 41062 | [14 empty] | 0 | -41062
OK2103 | Bethesda - Santa Fe Dev. |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2105-3 | Valencia - Custom Pools |  |  | DEAD |  | 2215 NW 178th Street Ste. E, Edmond, OK 73012 | DEAD | [18 empty] | 15493 | [14 empty] | 0 | -15493
OK2109-1 | Grand Blvd. Shell - OKC, OK |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2111 | Solara Surgery Center - Moore, OK |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2115 | Paul's Valley Development |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2117-1 | Paul's Valley Shell |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2117-2 | Paul's Valley Shell - Enhanced Dental |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2118 | Paul's Valley Shell - TBD |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2116 | Dollar Tree (Paul's Valley Development) |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2121 | 15th & Bryant Development | AG Fifteen RE Holdings, LLC |  | Combined |  | Combined with OK2122 | Combined | [18 empty] | 2860071.9 | 269645.4 |  |  | 125000 | 125000 | 125000 | 105000 |  |  |  |  | 200000 |  |  | 949645.4 | -1910426.5
OK2123 | TBD (15th & Bryant Development) |  |  | DEAD |  |  | DEAD | [18 empty] | 0 | [15 empty] | 0
OK2124 | Bodin Chiro (Lone Oak) |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2126-2 | Weatherford Shell - Dollar Tree |  |  | DEAD |  |  | DEAD | [33 empty] | 0 | 0
OK2127 | Legacy Martial Arts Shell | Don't know |  | DEAD |  |  | DEAD | [18 empty] | 750000 | 0 | 0 | 0 | 50000 | 75000 | 130000 | 130000 | 130000 | 130000 | 105000 |  |  |  |  | 750000 | 0
OKxxxx | Dr. Brad Mitchell Development |  |  | DEAD |  |  | HOLD | [33 empty] | 0 | 0
Okxxxx | Anytime Fitness - Brandon Porter |  |  | DEAD |  |  | HOLD | [33 empty] | 0 | 0
TNxxxx | AIM Bellevue - Site Visit Needed | AG AIM Bellevue RE Holdings, LLC |  | DEAD |  | 7734 Hwy 70 S. Nashville, TN 37221 | DEAD | [18 empty] | 2400000 | [6 empty] | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 2400000 | 0
TX2004 | Marshall Ridge Dev. |  |  | DEAD |  |  | DEAD | [18 empty] | 37392 | [14 empty] | 0 | -37392
TX2009 | Alliance Pediatrics-Marsh |  |  | DEAD |  |  | DEAD | [18 empty] | 3575 | [14 empty] | 0 | -3575
| Yukon Nail Salon (Full Build) | AGRIGGS RE Holdings, LLC |  | DEAD |  |  | DEAD | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0
| Fayetteville Development-Dead | AG Fayetteville RE Holdings, LLC |  | DEAD |  |  | DEAD | [18 empty] | 3000000 | 0 | 0 | 0 | 0 | [9 empty] | 3000000 | 3000000 | 0
[26 empty] | 6907896.9 |  | 0 | 0 | 175000 | 200000 | 255000 | 485000 | 380000 | 380000 | 355000 | 250000 | 450000 | 250000 | 650000 | 3830000 | -3077896.9
Formulas:
Brandon = [Trevor]+15
Brandon = [Brandon]+(6*4.3*7)
Trevor = [Trevor]+45
Trevor = [Trevor, row above]
Note on K13: Bobby Snyder: Don't close land until permit is in hand. Land close can be pushed
Note on M13: Bobby Snyder: Push design forward
Note on O13: Trevor Hayes: Demo Permit rcvd 2/9
Note on K17: Bobby Snyder: Don't close loan until permit is in hand
Note on M25: Bobby Snyder: Get early site release prior to full permit
Note on B27: Bobby Snyder: Existing Building
Note on U29: Bobby Snyder: Hard completion date of Aug to prevent LDs
Note on K30: Bobby Snyder: Don't close loan until permit is in hand Lot Split
Note on O30: Trevor Hayes: Title company needs to file lot split.
Note on T30: Bobby Snyder: Don't start work until the ok from DG
Note on K31: Bobby Snyder: Add 6 months to permits on TI
Note on M31: Bobby Snyder: Add 6 months to permits on TI
Note on O54: Bobby Snyder: The sewer easement is holding up the permit
Note on U54: Bobby Snyder: Open and opperating on 10/14/22. We have communicated with JackBe that this completion date may be in jepordy.
Note on O56: Bobby Snyder: Need SS to be moved prior to release of permit.
Note on M61: Trevor Hayes: Site plan application made 2/8. Can not submit until planning commision meeting.
Note on O63: Bobby Snyder: Variance meeting 2/1. We have earthwork permit in hand.
Note on O66: Bobby Snyder: Need approval on additional parking for GI Alliance 2006-4
Note on M69: Bobby Snyder: Cold dark shell
Note on M70: Bobby Snyder: Need a permit from Trevor
Note on M75: Trevor Hayes: Clock Started on 10/28
Note on O79: Brandon Chaney: On Hold Per Denver
Note on M84: Bobby Snyder: Need update from Trevor. 3' of undercut over entire site. Need updated Civils to submit to SAWS -Updated civils ready 2/18. - Approvals needed: TCEQ, SAWS, Building Permit
Note on U92: Bobby Snyder: Must complete by 10/01/22
Note on U93: Brandon Chaney: Hard date per Denver 6-30-22
Note on B128: Bobby Snyder: Another GC built out this space.
Note on U144: Bobby Snyder: Hard completion date prior to LDs