## Project Progress Status Sample
Project Title | Project ID | Task Order ID | Responsible Branch | Project Customer | Project Status | Project Stage | Project Assigned To (Resource) | Project Value Area | Application Area | Priority | Project Issues (Risks) | Project Start Date | Project Actual Release Date | Project Target Date (Estimate) | Project Status Change Date
Title 1 | 37020 | 75234 | Branch A | Customer A | Status A | New | Eng.A | Process Improvement | Process | 1 |  | 2022-01-15 |  | 2022-08-15
Title 1 | 37020 | 75234 | Branch A | Customer A | Status B | Inprogress | Eng.A | Process Improvement | Process | 1 | Risk A | 2022-01-15 |  | 2022-08-15 | 2022-02-15
Title 2 | 16316 | 57859 | Branch B | Customer D | Status A | New | Eng.B | Business | Construction | 1 |  | 2021-06-18 |  | 2022-05-09
Title 2 | 16316 | 57859 | Branch B | Customer D | Status B | Inprogress | Eng.B | Business | Construction | 1 | Risk B | 2021-06-18 |  | 2022-05-09 | 2021-09-27
Title 3 | 16315 | 67334 | Branch C | Customer B | Status A | New | Eng.E | Operations | Electrical | 2 |  | 2021-04-06 |  | 2021-11-11
Title 4 | 24652 | 67890 | Branch D | Customer C | Status A | New | Eng.F | User experience | Product Design Improvement | 2 |  | 2021-03-19 |  | 2021-08-14
Title 4 | 24652 | 67890 | Branch D | Customer C | Status B | Inprogress | Eng.F | User experience | Product Design Improvement | 2 | Rsik C | 2021-03-19 |  | 2021-08-14 | 2021-05-01
Title 4 | 24652 | 67890 | Branch D | Customer C | Status C | Inprogress | Eng.F | User experience | Product Design Improvement | 2 | Risk D | 2021-03-19 |  | 2021-08-14 | 2021-06-01
Title 4 | 24652 | 67890 | Branch D | Customer C | Status G | Done | Eng.F | User experience | Product Design Improvement | 2 |  | 2021-03-19 | 2021-09-22 | 2021-08-14 | 2021-09-21
Title 5 | 15221 | 74332 | Branch E | Customer E | Status A | New | Eng.D | Business | IT | 3 |  | 2021-10-01 |  | 2022-01-26
Title 5 | 15221 | 74332 | Branch E | Customer E | Status E | Onhold | Eng.D | Business | IT | 3 | Risk E | 2021-10-01 |  | 2022-01-26 | 2021-11-25
Title 6 | 24653 | 57890 | Branch F | Cusomer B | Status A | New | Eng.C | Process Improvement | Product Design Improvement | 3 |  | 2020-07-02 |  | 2021-03-02
Title 6 | 24653 | 57890 | Branch F | Cusomer B | Status F | Cancelled | Eng.C | Process Improvement | Product Design Improvement | 3 | Risk F | 2020-07-02 |  | 2021-03-02 | 2020-09-19
Title 7 | 12558 | 45678 | Branch A | Customer A | Status A | New | Eng.A | Security Compliance | Construction | 3 |  | 2021-03-09 |  | 2021-12-19
Title 7 | 12558 | 45678 | Branch A | Customer A | Status B | Inprogress | Eng.A | Security Compliance | Construction | 3 | Risk A | 2021-03-09 |  | 2021-12-19 | 2021-04-09
Title 7 | 12558 | 45678 | Branch A | Customer A | Status C | Inprogress | Eng.A | Security Compliance | Construction | 3 | Risk B | 2021-03-09 |  | 2021-12-19 | 2021-05-09
Title 7 | 12558 | 45678 | Branch A | Customer A | Status D | Inprogress | Eng.A | Security Compliance | Construction | 3 |  | 2021-03-09 |  | 2021-12-19 | 2021-06-09
Title 7 | 12558 | 45678 | Branch A | Customer A | Status E | Onhold | Eng.A | Security Compliance | Construction | 3 | Risk C | 2021-03-09 |  | 2022-02-01 | 2021-07-09
Title 7 | 12558 | 45678 | Branch A | Customer A | Status C | Inprogress | Eng.A | Security Compliance | Construction | 3 |  | 2021-03-09 |  | 2022-02-01 | 2021-09-09
Title 7 | 12558 | 45678 | Branch A | Customer A | Status G | Done | Eng.A | Security Compliance | Construction | 3 |  | 2021-03-09 | 2022-01-17 | 2022-02-01 | 2022-01-16
Title 8 | 36195 | 78904 | Branch D | Customer C | Status A | New | Eng.C | Operations | Electrical | 1 |  | 2022-03-11 |  | 2022-07-02
Title 9 | 48922 | 12356 | Branch E | Customer F | Status A | New | Eng.B | Business | Process | 2 |  | 2022-04-01 |  | 2022-09-06
Title 10 | 48925 | 67845 | Branch B | Customer D | Status A | New | Eng.F | User experience | IT | 3 |  | 2021-10-01 |  | 2022-02-15
Title 10 | 48925 | 67845 | Branch B | Customer D | Status B | Inprogress | Eng.F | User experience | IT | 3 | Risk B | 2021-10-01 |  | 2022-02-15 | 2021-12-14
Title 11 | 48924 | 56734 | Branch B | Customer D | Status A | New | Eng.A | Process Improvement | Process | 2 |  | 2021-09-16 |  | 2022-03-16
Title 11 | 48924 | 56734 | Branch B | Customer D | Status B | Inprogress | Eng.A | Process Improvement | Process | 2 | Risk C | 2021-09-16 |  | 2022-03-16 | 2021-10-01
Title 12 | 34918 | 17890 | Branch F | Customer G | Status A | New | Eng.D | Business | Construction | 2 |  | 2021-02-11 |  | 2021-09-09
Title 12 | 34918 | 17890 | Branch F | Customer G | Status B | Inprogress | Eng.D | Business | Construction | 2 | Rsik D | 2021-02-11 |  | 2021-09-09 | 2021-04-14
Title 12 | 34918 | 17890 | Branch F | Customer G | Status E | Onhold | Eng.D | Business | Construction | 2 | Risk D | 2021-02-11 |  | 2021-09-09 | 2021-06-19
Title 13 | 34916 | 89045 | Branch E | Customer E | Status A | New | Eng.C | Operations | Electrical | 2 |  | 2022-01-17 |  | 2022-05-07
Title 13 | 34916 | 89045 | Branch E | Customer E | Status B | Inprogress | Eng.C | Operations | Electrical | 2 | Risk E | 2022-01-17 |  | 2022-05-07 | 2022-02-14
Title 13 | 34916 | 89045 | Branch E | Customer E | Status E | Onhold | Eng.C | Operations | Electrical | 2 | Risk E | 2022-01-17 |  | 2022-05-07 | 2022-02-15
Title 13 | 34916 | 89045 | Branch E | Customer E | Status F | Cancelled | Eng.C | Operations | Electrical | 2 |  | 2022-01-17 |  | 2022-05-07 | 2022-03-16
Title 14 | 34922 | 65321 | Branch A | Customer B | Status A | New | Eng.B | Business | Product Design Improvement | 3 |  | 2021-10-22 |  | 2022-01-24
Title 14 | 34922 | 65321 | Branch A | Customer B | Status B | Inprogress | Eng.B | Business | Product Design Improvement | 3 | Risk F | 2021-10-22 |  | 2022-01-24 | 2021-11-14
Title 14 | 34922 | 65321 | Branch A | Customer B | Status C | Inprogress | Eng.B | Business | Product Design Improvement | 3 | Risk G | 2021-10-22 |  | 2022-01-24 | 2021-12-09
Title 14 | 34922 | 65321 | Branch A | Customer B | Status G | Done | Eng.B | Business | Product Design Improvement | 3 |  | 2021-10-22 | 2022-01-24 | 2022-01-24 | 2022-01-24
Title 15 | 16321 | 34234 | Branch E | Customer G | Status A | New | Eng.A | Business | IT | 2 |  | 2021-04-12
Title 15 | 16321 | 34234 | Branch E | Customer G | Status C | Inprogress | Eng.A | Business | IT | 2 |  | 2021-04-12 |  |  | 2020-02-22
Title 16 | 11222 | 58229 | Branch E | Customer G | Status A | New | Eng.A | Business | IT | 2 |  | 2022-03-27 |  | 2022-07-01