## Sheet1
WBS | WBS Category | WBS Name | WBS Path | Activity ID | Activity Name | Physical % Complete | BL Project Start | BL Project Finish | Start | Finish | Schedule % Complete | Performance % Complete | Earned Value Cost | Planned Value Cost | Schedule Variance | Schedule Performance Index | Budgeted Total Cost | Units % Complete | Labor Units % Complete | data date
Retaining Walls for School at Eighteen Rawalpindi Revised (BL) R-01 Updated 2023 Jan 28 |  |  | RETG-WALL-R-6 |  |  |  | 2022-07-20 | 2023-01-15 | 20-Jul-22 A | 2023-03-03 | 100% | 84.22% | 215047388.96 | 255345318.64 | -40297929.68 | 84% | 255345318.64 | 88.72% | 93.61% | 2023-01-28
Milestones |  |  | RETG-WALL-R-6.6 |  |  |  | 2022-07-20 | 2023-01-15 | 20-Jul-22 A | 2023-03-03 | 0% | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.6 |  | Milestones | 6 | A3810 | Project Start | 100% | 2022-07-20 |  | 20-Jul-22 A |  | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.6 |  | Milestones | 6 | A3820 | Project Finish | 0% |  | 2023-01-15 |  | 2023-03-03 | 100% | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
Mobilization/ Preliminaries |  |  | RETG-WALL-R-6.2 |  |  |  | 2022-07-20 | 2022-08-09 | 20-Jul-22 A | 09-Aug-22 A | 0% | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.2 |  | Mobilization/ Preliminaries | 2 | A3830 | Notice to proceed | 100% | 2022-07-20 |  | 20-Jul-22 A |  | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.2 |  | Mobilization/ Preliminaries | 2 | A3840 | Mobilization of resources | 100% | 2022-07-20 | 2022-08-09 | 20-Jul-22 A | 09-Aug-22 A | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.2 |  | Mobilization/ Preliminaries | 2 | A3850 | Access to site | 100% | 2022-07-20 |  | 20-Jul-22 A |  | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
Engineering |  |  | RETG-WALL-R-6.7 |  |  |  | 2022-07-20 | 2022-08-14 | 20-Jul-22 A | 07-Aug-22 A | 0% | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.7 |  | Engineering | 7 | A3870 | Submission of Shop drawings | 100% | 2022-07-25 | 2022-07-31 | 25-Jul-22 A | 31-Jul-22 A | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.7 |  | Engineering | 7 | A3880 | Approval of Material submittals | 100% | 2022-08-01 | 2022-08-07 | 01-Aug-22 A | 07-Aug-22 A | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.7 |  | Engineering | 7 | A3890 | Approval of Shop drawings | 100% | 2022-08-01 | 2022-08-14 | 01-Aug-22 A | 07-Aug-22 A | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.7 |  | Engineering | 7 | A3900 | Submission of Material submittals | 100% | 2022-07-25 | 2022-07-31 | 25-Jul-22 A | 31-Jul-22 A | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.7 |  | Engineering | 7 | A3910 | Submission of Method statements | 100% | 2022-07-25 | 2022-07-31 | 25-Jul-22 A | 31-Jul-22 A | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.7 |  | Engineering | 7 | A3920 | Approval of Method statements | 100% | 2022-08-01 | 2022-08-07 | 01-Aug-22 A | 07-Aug-22 A | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.7 |  | Engineering | 7 | A3930 | Provision of IFC drawings | 100% | 2022-07-20 | 2022-07-24 | 20-Jul-22 A | 24-Jul-22 A | 100% | 100% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
Procurement |  |  | RETG-WALL-R-6.8 |  |  |  | 2022-08-08 | 2022-12-16 | 08-Aug-22 A | 2023-02-21 | 0% | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.8 |  | Procurement | 8 | A3940 | Procurement of Steel | 60% | 2022-08-08 | 2022-12-16 | 08-Aug-22 A | 2023-02-21 | 100% | 60% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.8 |  | Procurement | 8 | A3950 | Procurement of Concrete | 60% | 2022-08-08 | 2022-12-16 | 08-Aug-22 A | 2023-02-21 | 100% | 60% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
Construction |  |  | RETG-WALL-R-6.1 |  |  |  | 2022-08-10 | 2023-01-05 | 20-Aug-22 A | 2023-02-10 | 100% | 84.22% | 215047388.96 | 255345318.64 | -40297929.68 | 84% | 255345318.64 | 88.72% | 93.61% | 2023-01-28
Zone 3 RCC Wall A (20' High) 190 ft Length |  |  | RETG-WALL-R-6.1.3 |  |  |  | 2022-08-10 | 2022-11-19 | 20-Aug-22 A | 2023-02-10 | 100% | 74.72% | 54757385.64 | 73286420.76 | -18529035.11 | 75% | 73286420.76 | 88.28% | 93.69% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3320 | Excavation | 100% | 2022-08-10 | 2022-08-14 | 20-Aug-22 A | 24-Aug-22 A | 100% | 100% | 1735376.19 | 1735376.19 | 0 | 100% | 1735376.19 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3330 | Piling Works | 100% | 2022-08-16 | 2022-08-28 | 26-Aug-22 A | 07-Sep-22 A | 100% | 100% | 24448580.06 | 24448580.06 | 0 | 100% | 24448580.06 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3350 | Stem wall Steel, Formwork and Concrete | 100% | 2022-08-30 | 2022-09-03 | 08-Sep-22 A | 26-Oct-22 A | 100% | 100% | 4022614.66 | 4022614.66 | 0 | 100% | 4022614.66 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3360 | Backfilling | 100% | 2022-09-05 | 2022-09-07 | 30-Oct-22 A | 05-Nov-22 A | 100% | 100% | 1068204.68 | 1068204.68 | 0 | 100% | 1068204.68 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3370 | Fixing of Steel Reinforcement of Raft | 100% | 2022-09-09 | 2022-09-17 | 07-Nov-22 A | 01-Dec-22 A | 100% | 100% | 659133.53 | 659133.53 | 0 | 100% | 659133.53 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3380 | Form Work Fixing of Raft | 100% | 2022-09-19 | 2022-09-21 | 07-Nov-22 A | 10-Dec-22 A | 100% | 100% | 215256.8 | 215256.8 | 0 | 100% | 215256.8 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3390 | Concrete of Raft | 100% | 2022-09-23 | 2022-09-24 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 10708549.79 | 10708549.79 | 0 | 100% | 10708549.79 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3400 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-09-26 | 2022-10-04 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 659133.53 | 659133.53 | 0 | 100% | 659133.53 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3410 | Concrete of Wall till 8' | 100% | 2022-10-06 | 2022-10-07 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 3363481.12 | 3363481.12 | 0 | 100% | 3363481.12 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3420 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-10-12 | 2022-10-20 | 01-Dec-22 A | 17-Dec-22 A | 100% | 100% | 659133.53 | 659133.53 | 0 | 100% | 659133.53 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3430 | Concrete of Wall till 16' | 100% | 2022-10-22 | 2022-10-23 | 20-Dec-22 A | 24-Dec-22 A | 100% | 100% | 3363481.12 | 3363481.12 | 0 | 100% | 3363481.12 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3440 | Steel and Formwork fixing of Wall till 20' | 100% | 2022-10-27 | 2022-11-03 | 20-Dec-22 A | 24-Dec-22 A | 100% | 100% | 659133.53 | 659133.53 | 0 | 100% | 659133.53 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3450 | Concrete of Wall till 20' | 95% | 2022-11-05 | 2022-11-05 | 24-Dec-22 A | 2023-01-28 | 100% | 95% | 3195307.07 | 3363481.12 | -168174.06 | 95% | 3363481.12 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3460 | Backfilling | 0% | 2022-11-06 | 2022-11-19 | 2023-01-28 | 2023-02-10 | 100% | 0% | 0 | 18360861.06 | -18360861.06 | 0% | 18360861.06 | 0% | 0% | 2023-01-28
Zone 2 RCC Wall B (30 ' High) 173 ft Length |  |  | RETG-WALL-R-6.1.2 |  |  |  | 2022-08-15 | 2022-12-05 | 25-Aug-22 A | 2023-02-10 | 100% | 91.65% | 61156532.3 | 66729214.69 | -5572682.39 | 92% | 66729214.69 | 88.03% | 93.49% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3640 | Excavation | 100% | 2022-08-15 | 2022-08-19 | 25-Aug-22 A | 29-Aug-22 A | 100% | 100% | 1580105.69 | 1580105.69 | 0 | 100% | 1580105.69 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3650 | Piling Works | 100% | 2022-08-29 | 2022-09-09 | 14-Sep-22 A | 19-Sep-22 A | 100% | 100% | 22261075.53 | 22261075.53 | 0 | 100% | 22261075.53 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3670 | Stem wall Steel, Formwork and Concrete | 100% | 2022-09-11 | 2022-09-16 | 20-Sep-22 A | 15-Oct-22 A | 100% | 100% | 3662696.51 | 3662696.51 | 0 | 100% | 3662696.51 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3680 | Backfilling | 100% | 2022-09-18 | 2022-09-22 | 26-Oct-22 A | 31-Oct-22 A | 100% | 100% | 972628.47 | 972628.47 | 0 | 100% | 972628.47 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3690 | Fixing of Steel Reinforcement of Raft | 100% | 2022-09-24 | 2022-09-30 | 01-Nov-22 A | 02-Nov-22 A | 100% | 100% | 600158.43 | 600158.43 | 0 | 100% | 600158.43 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3700 | Form Work Fixing of Raft | 100% | 2022-10-02 | 2022-10-03 | 03-Nov-22 A | 05-Nov-22 A | 100% | 100% | 195996.98 | 195996.98 | 0 | 100% | 195996.98 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3710 | Concrete of Raft | 100% | 2022-10-05 | 2022-10-06 | 06-Nov-22 A | 08-Nov-22 A | 100% | 100% | 9750416.39 | 9750416.39 | 0 | 100% | 9750416.39 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3720 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-10-08 | 2022-10-16 | 19-Nov-22 A | 24-Nov-22 A | 100% | 100% | 600158.43 | 600158.43 | 0 | 100% | 600158.43 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3730 | Concrete of Wall till 8' | 100% | 2022-10-18 | 2022-10-19 | 25-Nov-22 A | 01-Dec-22 A | 100% | 100% | 3062538.08 | 3062538.08 | 0 | 100% | 3062538.08 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3740 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-10-23 | 2022-10-29 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 600158.43 | 600158.43 | 0 | 100% | 600158.43 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3750 | Concrete of Wall till 16' | 100% | 2022-10-31 | 2022-11-01 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 3062538.08 | 3062538.08 | 0 | 100% | 3062538.08 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3760 | Steel and Formwork fixing of Wall till 24' | 100% | 2022-11-03 | 2022-11-09 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 600158.43 | 600158.43 | 0 | 100% | 600158.43 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3770 | Concrete of Wall till 24' | 100% | 2022-11-11 | 2022-11-12 | 16-Dec-22 A | 17-Dec-22 A | 100% | 100% | 3062538.08 | 3062538.08 | 0 | 100% | 3062538.08 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3780 | Steel and Formwork fixing of Wall till 30' | 100% | 2022-11-14 | 2022-11-19 | 16-Dec-22 A | 23-Dec-22 A | 100% | 100% | 5572682.39 | 5572682.39 | 0 | 100% | 5572682.39 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3790 | Concrete of Wall till 30' | 100% | 2022-11-21 | 2022-11-21 | 23-Dec-22 A | 07-Jan-23 A | 100% | 100% | 5572682.39 | 5572682.39 | 0 | 100% | 5572682.39 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3800 | Backfilling | 0% | 2022-11-22 | 2022-12-05 | 2023-01-28 | 2023-02-10 | 100% | 0% | 0 | 5572682.39 | -5572682.39 | 0% | 5572682.39 | 0% | 0% | 2023-01-28
Zone 4 RCC Wall B (35.75'High) 174 ft Length |  |  | RETG-WALL-R-6.1.4 |  |  |  | 2022-08-15 | 2023-01-05 | 14-Sep-22 A | 2023-02-03 | 100% | 89.98% | 60389059.38 | 67114932.69 | -6725873.31 | 90% | 67114932.69 | 94.22% | 96.28% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3000 | Excavation | 100% | 2022-08-15 | 2022-08-19 | 14-Sep-22 A | 21-Sep-22 A | 100% | 100% | 1589239.25 | 1589239.25 | 0 | 100% | 1589239.25 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3010 | Piling Works | 100% | 2022-09-16 | 2022-09-27 | 22-Sep-22 A | 20-Oct-22 A | 100% | 100% | 22389752.27 | 22389752.27 | 0 | 100% | 22389752.27 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3030 | Stem wall Steel, Formwork and Concrete | 100% | 2022-09-29 | 2022-10-04 | 21-Oct-22 A | 21-Nov-22 A | 100% | 100% | 3683868.16 | 3683868.16 | 0 | 100% | 3683868.16 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3040 | Backfilling | 100% | 2022-10-06 | 2022-10-11 | 19-Nov-22 A | 25-Nov-22 A | 100% | 100% | 978250.6 | 978250.6 | 0 | 100% | 978250.6 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3050 | Fixing of Steel Reinforcement of Raft | 100% | 2022-10-13 | 2022-10-19 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 603627.55 | 603627.55 | 0 | 100% | 603627.55 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3060 | Form Work Fixing of Raft | 100% | 2022-10-21 | 2022-10-22 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 197129.91 | 197129.91 | 0 | 100% | 197129.91 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3070 | Concrete of Raft | 100% | 2022-10-24 | 2022-10-25 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 9806777.18 | 9806777.18 | 0 | 100% | 9806777.18 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3080 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-11-12 | 2022-11-15 | 16-Dec-22 A | 24-Dec-22 A | 100% | 100% | 603627.55 | 603627.55 | 0 | 100% | 603627.55 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3090 | Concrete of Wall till 8' | 100% | 2022-11-17 | 2022-11-18 | 16-Dec-22 A | 24-Dec-22 A | 100% | 100% | 3080240.61 | 3080240.61 | 0 | 100% | 3080240.61 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3100 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-11-22 | 2022-11-25 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 603627.55 | 603627.55 | 0 | 100% | 603627.55 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3110 | Concrete of Wall till 16' | 100% | 2022-11-27 | 2022-11-28 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 3080240.61 | 3080240.61 | 0 | 100% | 3080240.61 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3120 | Steel and Formwork fixing of Wall till 24' | 100% | 2022-12-02 | 2022-12-07 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 603627.55 | 603627.55 | 0 | 100% | 603627.55 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3130 | Concrete of Wall till 24' | 100% | 2022-12-09 | 2022-12-10 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 3080240.61 | 3080240.61 | 0 | 100% | 3080240.61 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3140 | Steel and Formwork fixing of Wall till 32' | 100% | 2022-12-14 | 2022-12-17 | 07-Jan-23 A | 28-Jan-23 A | 100% | 100% | 3362936.66 | 3362936.66 | 0 | 100% | 3362936.66 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3150 | Concrete of Wall till 32' | 100% | 2022-12-19 | 2022-12-19 | 07-Jan-23 A | 28-Jan-23 A | 100% | 100% | 3362936.66 | 3362936.66 | 0 | 100% | 3362936.66 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3160 | Steel and Formwork fixing of Wall till 35.75' | 100% | 2022-12-23 | 2022-12-29 | 07-Jan-23 A | 28-Jan-23 A | 100% | 100% | 3362936.66 | 3362936.66 | 0 | 100% | 3362936.66 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3170 | Concrete of Wall till 35.75' | 0% | 2022-12-31 | 2022-12-31 | 2023-01-29 | 2023-01-29 | 100% | 0% | 0 | 3362936.66 | -3362936.66 | 0% | 3362936.66 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3180 | Backfilling | 0% | 2023-01-01 | 2023-01-05 | 2023-01-30 | 2023-02-03 | 100% | 0% | 0 | 3362936.66 | -3362936.66 | 0% | 3362936.66 | 0% | 0% | 2023-01-28
Zone 1 RCC Wall A (27.25' High) 80 ft Length |  |  | RETG-WALL-R-6.1.5 |  |  |  | 2022-08-20 | 2022-11-24 | 30-Aug-22 A | 2023-02-10 | 100% | 74.95% | 23126551.45 | 30857440.32 | -7730888.87 | 75% | 30857440.32 | 81.58% | 89.86% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2360 | Excavation | 100% | 2022-08-20 | 2022-08-24 | 30-Aug-22 A | 03-Sep-22 A | 100% | 100% | 730684.71 | 730684.71 | 0 | 100% | 730684.71 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2370 | Piling Works | 100% | 2022-09-10 | 2022-09-15 | 08-Sep-22 A | 13-Sep-22 A | 100% | 100% | 10294138.97 | 10294138.97 | 0 | 100% | 10294138.97 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2380 | Stem wall Steel, Formwork and Concrete | 100% | 2022-09-17 | 2022-09-21 | 14-Sep-22 A | 08-Oct-22 A | 100% | 100% | 1693732.49 | 1693732.49 | 0 | 100% | 1693732.49 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2390 | Backfilling | 100% | 2022-09-23 | 2022-09-25 | 20-Oct-22 A | 24-Oct-22 A | 100% | 100% | 449770.39 | 449770.39 | 0 | 100% | 449770.39 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2410 | Fixing of Steel Reinforcement of Raft | 100% | 2022-09-27 | 2022-10-01 | 23-Oct-22 A | 24-Oct-22 A | 100% | 100% | 277529.91 | 277529.91 | 0 | 100% | 277529.91 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2420 | Form Work Fixing of Raft | 100% | 2022-10-03 | 2022-10-05 | 01-Nov-22 A | 03-Nov-22 A | 100% | 100% | 90634.44 | 90634.44 | 0 | 100% | 90634.44 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2430 | Concrete of Raft | 100% | 2022-10-07 | 2022-10-07 | 04-Nov-22 A | 05-Nov-22 A | 100% | 100% | 4508863.07 | 4508863.07 | 0 | 100% | 4508863.07 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2440 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-10-10 | 2022-10-15 | 05-Nov-22 A | 09-Nov-22 A | 100% | 100% | 277529.91 | 277529.91 | 0 | 100% | 277529.91 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2450 | Concrete of Wall till 8' | 100% | 2022-10-17 | 2022-10-17 | 10-Nov-22 A | 10-Nov-22 A | 100% | 100% | 1416202.58 | 1416202.58 | 0 | 100% | 1416202.58 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2460 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-10-21 | 2022-10-27 | 19-Nov-22 A | 23-Nov-22 A | 100% | 100% | 277529.91 | 277529.91 | 0 | 100% | 277529.91 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2470 | Concrete of Wall till 16' | 100% | 2022-10-29 | 2022-10-29 | 24-Nov-22 A | 25-Nov-22 A | 100% | 100% | 1416202.58 | 1416202.58 | 0 | 100% | 1416202.58 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2480 | Steel and Formwork fixing of Wall till 20.67' | 100% | 2022-11-02 | 2022-11-08 | 26-Nov-22 A | 17-Dec-22 A | 100% | 100% | 277529.91 | 277529.91 | 0 | 100% | 277529.91 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2490 | Concrete of Wall till 20.67' | 100% | 2022-11-10 | 2022-11-10 | 26-Nov-22 A | 17-Dec-22 A | 100% | 100% | 1416202.58 | 1416202.58 | 0 | 100% | 1416202.58 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2500 | Backfilling | 0% | 2022-11-11 | 2022-11-24 | 2023-01-28 | 2023-02-10 | 100% | 0% | 0 | 7730888.87 | -7730888.87 | 0% | 7730888.87 | 0% | 0% | 2023-01-28
Zone 5 RCC Wall B (35.75'High) 45 ft Length |  |  | RETG-WALL-R-6.1.6 |  |  |  | 2022-08-20 | 2023-01-01 | 20-Sep-22 A | 2023-02-05 | 100% | 89.98% | 15617860.18 | 17357310.18 | -1739449.99 | 90% | 17357310.18 | 89.33% | 93.33% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2680 | Excavation | 100% | 2022-08-20 | 2022-08-22 | 20-Sep-22 A | 30-Sep-22 A | 100% | 100% | 411010.15 | 411010.15 | 0 | 100% | 411010.15 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2690 | Piling Works | 100% | 2022-09-28 | 2022-09-30 | 30-Sep-22 A | 10-Oct-22 A | 100% | 100% | 5790453.17 | 5790453.17 | 0 | 100% | 5790453.17 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2710 | Stem wall Steel, Formwork and Concrete | 100% | 2022-10-02 | 2022-10-07 | 21-Oct-22 A | 25-Oct-22 A | 100% | 100% | 952724.52 | 952724.52 | 0 | 100% | 952724.52 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2720 | Backfilling | 100% | 2022-10-10 | 2022-10-14 | 19-Nov-22 A | 25-Nov-22 A | 100% | 100% | 252995.85 | 252995.85 | 0 | 100% | 252995.85 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2730 | Fixing of Steel Reinforcement of Raft | 100% | 2022-10-16 | 2022-10-19 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 156110.57 | 156110.57 | 0 | 100% | 156110.57 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2740 | Form Work Fixing of Raft | 100% | 2022-10-21 | 2022-10-21 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 50981.87 | 50981.87 | 0 | 100% | 50981.87 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2750 | Concrete of Raft | 100% | 2022-10-23 | 2022-10-23 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 2536235.48 | 2536235.48 | 0 | 100% | 2536235.48 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2760 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-11-12 | 2022-11-15 | 16-Dec-22 A | 24-Dec-22 A | 100% | 100% | 156110.57 | 156110.57 | 0 | 100% | 156110.57 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2770 | Concrete of Wall till 8' | 100% | 2022-11-17 | 2022-11-17 | 16-Dec-22 A | 24-Dec-22 A | 100% | 100% | 796613.95 | 796613.95 | 0 | 100% | 796613.95 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2780 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-11-21 | 2022-11-24 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 156110.57 | 156110.57 | 0 | 100% | 156110.57 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2790 | Concrete of Wall till 16' | 100% | 2022-11-26 | 2022-11-26 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 796613.95 | 796613.95 | 0 | 100% | 796613.95 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2800 | Steel and Formwork fixing of Wall till 24' | 100% | 2022-11-30 | 2022-12-03 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 156110.57 | 156110.57 | 0 | 100% | 156110.57 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2810 | Concrete of Wall till 24' | 100% | 2022-12-05 | 2022-12-05 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 796613.95 | 796613.95 | 0 | 100% | 796613.95 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2820 | Steel and Formwork fixing of Wall till 32' | 100% | 2022-12-09 | 2022-12-12 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 869725 | 869725 | 0 | 100% | 869725 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2830 | Concrete of Wall till 32' | 100% | 2022-12-14 | 2022-12-14 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 869725 | 869725 | 0 | 100% | 869725 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2840 | Steel and Formwork fixing of Wall till 35.75' | 100% | 2022-12-18 | 2022-12-21 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 869725 | 869725 | 0 | 100% | 869725 | 100% | 100% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2850 | Concrete of Wall till 35.75' | 0% | 2022-12-23 | 2022-12-23 | 2023-01-28 | 2023-01-28 | 100% | 0% | 0 | 869725 | -869725 | 0% | 869725 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2860 | Backfilling | 0% | 2022-12-24 | 2023-01-01 | 2023-01-29 | 2023-02-05 | 100% | 0% | 0 | 869725 | -869725 | 0% | 869725 | 0% | 0% | 2023-01-28
Handover/Closeout |  |  | RETG-WALL-R-6.3 |  |  |  | 2023-01-06 | 2023-01-15 | 2023-02-22 | 2023-03-03 | 0% | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.3 |  | Handover/Closeout | 3 | A3960 | Inspection, Punchlist & snag rectification | 0% | 2023-01-06 | 2023-01-15 | 2023-02-22 | 2023-03-03 | 100% | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
RETG-WALL-R-6.3 |  | Handover/Closeout | 3 | A3970 | Handover Date | 0% |  | 2023-01-15 |  | 2023-03-03 | 100% | 0% | 0 | 0 | 0 | 0% | 0 | 0% | 0% | 2023-01-28
Retaining Walls for School at Eighteen Rawalpindi Revised (BL) R-01 Updated 2023 Jan 21 | [6 empty] | 2022-07-20 | 2023-01-15 | 20-Jul-22 A | 2023-02-25 | 100% | 79.25% | 202349404 | 255345318.64 | -52995914.64 | 0.79 | 255345318.64 | 78.6% | 82.72% | 2023-01-21
Milestones | [6 empty] | 2022-07-20 | 2023-01-15 | 20-Jul-22 A | 2023-02-25 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.6 |  | Milestones | 6 | A3810 | Project Start | 100% | 2022-07-20 |  | 20-Jul-22 A |  | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.6 |  | Milestones | 6 | A3820 | Project Finish | 0% |  | 2023-01-15 |  | 2023-02-25 | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
Mobilization/ Preliminaries | [6 empty] | 2022-07-20 | 2022-08-09 | 20-Jul-22 A | 09-Aug-22 A | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.2 |  | Mobilization/ Preliminaries | 2 | A3830 | Notice to proceed | 100% | 2022-07-20 |  | 20-Jul-22 A |  | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.2 |  | Mobilization/ Preliminaries | 2 | A3840 | Mobilization of resources | 100% | 2022-07-20 | 2022-08-09 | 20-Jul-22 A | 09-Aug-22 A | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.2 |  | Mobilization/ Preliminaries | 2 | A3850 | Access to site | 100% | 2022-07-20 |  | 20-Jul-22 A |  | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
Engineering | [6 empty] | 2022-07-20 | 2022-08-14 | 20-Jul-22 A | 07-Aug-22 A | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.7 |  | Engineering | 7 | A3870 | Submission of Shop drawings | 100% | 2022-07-25 | 2022-07-31 | 25-Jul-22 A | 31-Jul-22 A | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.7 |  | Engineering | 7 | A3880 | Approval of Material submittals | 100% | 2022-08-01 | 2022-08-07 | 01-Aug-22 A | 07-Aug-22 A | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.7 |  | Engineering | 7 | A3890 | Approval of Shop drawings | 100% | 2022-08-01 | 2022-08-14 | 01-Aug-22 A | 07-Aug-22 A | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.7 |  | Engineering | 7 | A3900 | Submission of Material submittals | 100% | 2022-07-25 | 2022-07-31 | 25-Jul-22 A | 31-Jul-22 A | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.7 |  | Engineering | 7 | A3910 | Submission of Method statements | 100% | 2022-07-25 | 2022-07-31 | 25-Jul-22 A | 31-Jul-22 A | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.7 |  | Engineering | 7 | A3920 | Approval of Method statements | 100% | 2022-08-01 | 2022-08-07 | 01-Aug-22 A | 07-Aug-22 A | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.7 |  | Engineering | 7 | A3930 | Provision of IFC drawings | 100% | 2022-07-20 | 2022-07-24 | 20-Jul-22 A | 24-Jul-22 A | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
Procurement | [6 empty] | 2022-08-08 | 2022-12-16 | 08-Aug-22 A | 2023-02-14 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.8 |  | Procurement | 8 | A3940 | Procurement of Steel | 60% | 2022-08-08 | 2022-12-16 | 08-Aug-22 A | 2023-02-14 | 100% | 60% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.8 |  | Procurement | 8 | A3950 | Procurement of Concrete | 60% | 2022-08-08 | 2022-12-16 | 08-Aug-22 A | 2023-02-14 | 100% | 60% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
Construction | [6 empty] | 2022-08-10 | 2023-01-05 | 20-Aug-22 A | 2023-02-15 | 100% | 79.25% | 202349404 | 255345318.64 | -52995914.64 | 0.79 | 255345318.64 | 78.6% | 82.72% | 2023-01-21
Zone 3 RCC Wall A (20' High) 190 ft Length | [6 empty] | 2022-08-10 | 2022-11-19 | 20-Aug-22 A | 2023-02-03 | 100% | 74.72% | 54757385.64 | 73286420.76 | -18529035.11 | 0.75 | 73286420.76 | 88.28% | 93.69% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3320 | Excavation | 100% | 2022-08-10 | 2022-08-14 | 20-Aug-22 A | 24-Aug-22 A | 100% | 100% | 1735376.19 | 1735376.19 | 0 | 1 | 1735376.19 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3330 | Piling Works | 100% | 2022-08-16 | 2022-08-28 | 26-Aug-22 A | 07-Sep-22 A | 100% | 100% | 24448580.06 | 24448580.06 | 0 | 1 | 24448580.06 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3350 | Stem wall Steel, Formwork and Concrete | 100% | 2022-08-30 | 2022-09-03 | 08-Sep-22 A | 26-Oct-22 A | 100% | 100% | 4022614.66 | 4022614.66 | 0 | 1 | 4022614.66 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3360 | Backfilling | 100% | 2022-09-05 | 2022-09-07 | 30-Oct-22 A | 05-Nov-22 A | 100% | 100% | 1068204.68 | 1068204.68 | 0 | 1 | 1068204.68 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3370 | Fixing of Steel Reinforcement of Raft | 100% | 2022-09-09 | 2022-09-17 | 07-Nov-22 A | 01-Dec-22 A | 100% | 100% | 659133.53 | 659133.53 | 0 | 1 | 659133.53 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3380 | Form Work Fixing of Raft | 100% | 2022-09-19 | 2022-09-21 | 07-Nov-22 A | 10-Dec-22 A | 100% | 100% | 215256.8 | 215256.8 | 0 | 1 | 215256.8 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3390 | Concrete of Raft | 100% | 2022-09-23 | 2022-09-24 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 10708549.79 | 10708549.79 | 0 | 1 | 10708549.79 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3400 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-09-26 | 2022-10-04 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 659133.53 | 659133.53 | 0 | 1 | 659133.53 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3410 | Concrete of Wall till 8' | 100% | 2022-10-06 | 2022-10-07 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 3363481.12 | 3363481.12 | 0 | 1 | 3363481.12 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3420 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-10-12 | 2022-10-20 | 01-Dec-22 A | 17-Dec-22 A | 100% | 100% | 659133.53 | 659133.53 | 0 | 1 | 659133.53 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3430 | Concrete of Wall till 16' | 100% | 2022-10-22 | 2022-10-23 | 20-Dec-22 A | 24-Dec-22 A | 100% | 100% | 3363481.12 | 3363481.12 | 0 | 1 | 3363481.12 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3440 | Steel and Formwork fixing of Wall till 20' | 100% | 2022-10-27 | 2022-11-03 | 20-Dec-22 A | 24-Dec-22 A | 100% | 100% | 659133.53 | 659133.53 | 0 | 1 | 659133.53 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3450 | Concrete of Wall till 20' | 95% | 2022-11-05 | 2022-11-05 | 24-Dec-22 A | 2023-01-21 | 100% | 95% | 3195307.07 | 3363481.12 | -168174.06 | 0.95 | 3363481.12 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.3 |  | Zone 3 RCC Wall A (20' High) 190 ft Length | 1.3 | A3460 | Backfilling | 0% | 2022-11-06 | 2022-11-19 | 2023-01-21 | 2023-02-03 | 100% | 0% | 0 | 18360861.06 | -18360861.06 | 0 | 18360861.06 | 0% | 0% | 2023-01-21
Zone 2 RCC Wall B (30 ' High) 173 ft Length | [6 empty] | 2022-08-15 | 2022-12-05 | 25-Aug-22 A | 2023-02-03 | 100% | 91.65% | 61156532.3 | 66729214.69 | -5572682.39 | 0.92 | 66729214.69 | 88.03% | 93.49% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3640 | Excavation | 100% | 2022-08-15 | 2022-08-19 | 25-Aug-22 A | 29-Aug-22 A | 100% | 100% | 1580105.69 | 1580105.69 | 0 | 1 | 1580105.69 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3650 | Piling Works | 100% | 2022-08-29 | 2022-09-09 | 14-Sep-22 A | 19-Sep-22 A | 100% | 100% | 22261075.53 | 22261075.53 | 0 | 1 | 22261075.53 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3670 | Stem wall Steel, Formwork and Concrete | 100% | 2022-09-11 | 2022-09-16 | 20-Sep-22 A | 15-Oct-22 A | 100% | 100% | 3662696.51 | 3662696.51 | 0 | 1 | 3662696.51 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3680 | Backfilling | 100% | 2022-09-18 | 2022-09-22 | 26-Oct-22 A | 31-Oct-22 A | 100% | 100% | 972628.47 | 972628.47 | 0 | 1 | 972628.47 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3690 | Fixing of Steel Reinforcement of Raft | 100% | 2022-09-24 | 2022-09-30 | 01-Nov-22 A | 02-Nov-22 A | 100% | 100% | 600158.43 | 600158.43 | 0 | 1 | 600158.43 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3700 | Form Work Fixing of Raft | 100% | 2022-10-02 | 2022-10-03 | 03-Nov-22 A | 05-Nov-22 A | 100% | 100% | 195996.98 | 195996.98 | 0 | 1 | 195996.98 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3710 | Concrete of Raft | 100% | 2022-10-05 | 2022-10-06 | 06-Nov-22 A | 08-Nov-22 A | 100% | 100% | 9750416.39 | 9750416.39 | 0 | 1 | 9750416.39 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3720 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-10-08 | 2022-10-16 | 19-Nov-22 A | 24-Nov-22 A | 100% | 100% | 600158.43 | 600158.43 | 0 | 1 | 600158.43 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3730 | Concrete of Wall till 8' | 100% | 2022-10-18 | 2022-10-19 | 25-Nov-22 A | 01-Dec-22 A | 100% | 100% | 3062538.08 | 3062538.08 | 0 | 1 | 3062538.08 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3740 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-10-23 | 2022-10-29 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 600158.43 | 600158.43 | 0 | 1 | 600158.43 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3750 | Concrete of Wall till 16' | 100% | 2022-10-31 | 2022-11-01 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 3062538.08 | 3062538.08 | 0 | 1 | 3062538.08 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3760 | Steel and Formwork fixing of Wall till 24' | 100% | 2022-11-03 | 2022-11-09 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 600158.43 | 600158.43 | 0 | 1 | 600158.43 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3770 | Concrete of Wall till 24' | 100% | 2022-11-11 | 2022-11-12 | 16-Dec-22 A | 17-Dec-22 A | 100% | 100% | 3062538.08 | 3062538.08 | 0 | 1 | 3062538.08 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3780 | Steel and Formwork fixing of Wall till 30' | 100% | 2022-11-14 | 2022-11-19 | 16-Dec-22 A | 23-Dec-22 A | 100% | 100% | 5572682.39 | 5572682.39 | 0 | 1 | 5572682.39 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3790 | Concrete of Wall till 30' | 100% | 2022-11-21 | 2022-11-21 | 23-Dec-22 A | 07-Jan-23 A | 100% | 100% | 5572682.39 | 5572682.39 | 0 | 1 | 5572682.39 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.2 |  | Zone 2 RCC Wall B (30 ' High) 173 ft Length | 1.2 | A3800 | Backfilling | 0% | 2022-11-22 | 2022-12-05 | 2023-01-21 | 2023-02-03 | 100% | 0% | 0 | 5572682.39 | -5572682.39 | 0 | 5572682.39 | 0% | 0% | 2023-01-21
Zone 4 RCC Wall B (35.75'High) 174 ft Length | [6 empty] | 2022-08-15 | 2023-01-05 | 14-Sep-22 A | 2023-02-14 | 100% | 74.95% | 50300249.41 | 67114932.69 | -16814683.28 | 0.75 | 67114932.69 | 67.11% | 67.91% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3000 | Excavation | 100% | 2022-08-15 | 2022-08-19 | 14-Sep-22 A | 21-Sep-22 A | 100% | 100% | 1589239.25 | 1589239.25 | 0 | 1 | 1589239.25 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3010 | Piling Works | 100% | 2022-09-16 | 2022-09-27 | 22-Sep-22 A | 20-Oct-22 A | 100% | 100% | 22389752.27 | 22389752.27 | 0 | 1 | 22389752.27 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3030 | Stem wall Steel, Formwork and Concrete | 100% | 2022-09-29 | 2022-10-04 | 21-Oct-22 A | 21-Nov-22 A | 100% | 100% | 3683868.16 | 3683868.16 | 0 | 1 | 3683868.16 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3040 | Backfilling | 100% | 2022-10-06 | 2022-10-11 | 19-Nov-22 A | 25-Nov-22 A | 100% | 100% | 978250.6 | 978250.6 | 0 | 1 | 978250.6 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3050 | Fixing of Steel Reinforcement of Raft | 100% | 2022-10-13 | 2022-10-19 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 603627.55 | 603627.55 | 0 | 1 | 603627.55 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3060 | Form Work Fixing of Raft | 100% | 2022-10-21 | 2022-10-22 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 197129.91 | 197129.91 | 0 | 1 | 197129.91 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3070 | Concrete of Raft | 100% | 2022-10-24 | 2022-10-25 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 9806777.18 | 9806777.18 | 0 | 1 | 9806777.18 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3080 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-11-12 | 2022-11-15 | 16-Dec-22 A | 24-Dec-22 A | 100% | 100% | 603627.55 | 603627.55 | 0 | 1 | 603627.55 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3090 | Concrete of Wall till 8' | 100% | 2022-11-17 | 2022-11-18 | 16-Dec-22 A | 24-Dec-22 A | 100% | 100% | 3080240.61 | 3080240.61 | 0 | 1 | 3080240.61 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3100 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-11-22 | 2022-11-25 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 603627.55 | 603627.55 | 0 | 1 | 603627.55 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3110 | Concrete of Wall till 16' | 100% | 2022-11-27 | 2022-11-28 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 3080240.61 | 3080240.61 | 0 | 1 | 3080240.61 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3120 | Steel and Formwork fixing of Wall till 24' | 100% | 2022-12-02 | 2022-12-07 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 603627.55 | 603627.55 | 0 | 1 | 603627.55 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3130 | Concrete of Wall till 24' | 100% | 2022-12-09 | 2022-12-10 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 3080240.61 | 3080240.61 | 0 | 1 | 3080240.61 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3140 | Steel and Formwork fixing of Wall till 32' | 0% | 2022-12-14 | 2022-12-17 | 2023-01-24 | 2023-01-27 | 100% | 0% | 0 | 3362936.66 | -3362936.66 | 0 | 3362936.66 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3150 | Concrete of Wall till 32' | 0% | 2022-12-19 | 2022-12-19 | 2023-01-29 | 2023-01-29 | 100% | 0% | 0 | 3362936.66 | -3362936.66 | 0 | 3362936.66 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3160 | Steel and Formwork fixing of Wall till 35.75' | 0% | 2022-12-23 | 2022-12-29 | 2023-02-02 | 2023-02-07 | 100% | 0% | 0 | 3362936.66 | -3362936.66 | 0 | 3362936.66 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3170 | Concrete of Wall till 35.75' | 0% | 2022-12-31 | 2022-12-31 | 2023-02-09 | 2023-02-09 | 100% | 0% | 0 | 3362936.66 | -3362936.66 | 0 | 3362936.66 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.4 |  | Zone 4 RCC Wall B (35.75'High) 174 ft Length | 1.4 | A3180 | Backfilling | 0% | 2023-01-01 | 2023-01-05 | 2023-02-10 | 2023-02-14 | 100% | 0% | 0 | 3362936.66 | -3362936.66 | 0 | 3362936.66 | 0% | 0% | 2023-01-21
Zone 1 RCC Wall A (27.25' High) 80 ft Length | [6 empty] | 2022-08-20 | 2022-11-24 | 30-Aug-22 A | 2023-02-03 | 100% | 74.95% | 23126551.45 | 30857440.32 | -7730888.87 | 0.75 | 30857440.32 | 81.58% | 89.86% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2360 | Excavation | 100% | 2022-08-20 | 2022-08-24 | 30-Aug-22 A | 03-Sep-22 A | 100% | 100% | 730684.71 | 730684.71 | 0 | 1 | 730684.71 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2370 | Piling Works | 100% | 2022-09-10 | 2022-09-15 | 08-Sep-22 A | 13-Sep-22 A | 100% | 100% | 10294138.97 | 10294138.97 | 0 | 1 | 10294138.97 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2380 | Stem wall Steel, Formwork and Concrete | 100% | 2022-09-17 | 2022-09-21 | 14-Sep-22 A | 08-Oct-22 A | 100% | 100% | 1693732.49 | 1693732.49 | 0 | 1 | 1693732.49 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2390 | Backfilling | 100% | 2022-09-23 | 2022-09-25 | 20-Oct-22 A | 24-Oct-22 A | 100% | 100% | 449770.39 | 449770.39 | 0 | 1 | 449770.39 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2410 | Fixing of Steel Reinforcement of Raft | 100% | 2022-09-27 | 2022-10-01 | 23-Oct-22 A | 24-Oct-22 A | 100% | 100% | 277529.91 | 277529.91 | 0 | 1 | 277529.91 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2420 | Form Work Fixing of Raft | 100% | 2022-10-03 | 2022-10-05 | 01-Nov-22 A | 03-Nov-22 A | 100% | 100% | 90634.44 | 90634.44 | 0 | 1 | 90634.44 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2430 | Concrete of Raft | 100% | 2022-10-07 | 2022-10-07 | 04-Nov-22 A | 05-Nov-22 A | 100% | 100% | 4508863.07 | 4508863.07 | 0 | 1 | 4508863.07 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2440 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-10-10 | 2022-10-15 | 05-Nov-22 A | 09-Nov-22 A | 100% | 100% | 277529.91 | 277529.91 | 0 | 1 | 277529.91 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2450 | Concrete of Wall till 8' | 100% | 2022-10-17 | 2022-10-17 | 10-Nov-22 A | 10-Nov-22 A | 100% | 100% | 1416202.58 | 1416202.58 | 0 | 1 | 1416202.58 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2460 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-10-21 | 2022-10-27 | 19-Nov-22 A | 23-Nov-22 A | 100% | 100% | 277529.91 | 277529.91 | 0 | 1 | 277529.91 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2470 | Concrete of Wall till 16' | 100% | 2022-10-29 | 2022-10-29 | 24-Nov-22 A | 25-Nov-22 A | 100% | 100% | 1416202.58 | 1416202.58 | 0 | 1 | 1416202.58 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2480 | Steel and Formwork fixing of Wall till 20.67' | 100% | 2022-11-02 | 2022-11-08 | 26-Nov-22 A | 17-Dec-22 A | 100% | 100% | 277529.91 | 277529.91 | 0 | 1 | 277529.91 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2490 | Concrete of Wall till 20.67' | 100% | 2022-11-10 | 2022-11-10 | 26-Nov-22 A | 17-Dec-22 A | 100% | 100% | 1416202.58 | 1416202.58 | 0 | 1 | 1416202.58 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.5 |  | Zone 1 RCC Wall A (27.25' High) 80 ft Length | 1.5 | A2500 | Backfilling | 0% | 2022-11-11 | 2022-11-24 | 2023-01-21 | 2023-02-03 | 100% | 0% | 0 | 7730888.87 | -7730888.87 | 0 | 7730888.87 | 0% | 0% | 2023-01-21
Zone 5 RCC Wall B (35.75'High) 45 ft Length | [6 empty] | 2022-08-20 | 2023-01-01 | 20-Sep-22 A | 2023-02-15 | 100% | 74.95% | 13008685.19 | 17357310.18 | -4348624.99 | 0.75 | 17357310.18 | 65.17% | 67.27% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2680 | Excavation | 100% | 2022-08-20 | 2022-08-22 | 20-Sep-22 A | 30-Sep-22 A | 100% | 100% | 411010.15 | 411010.15 | 0 | 1 | 411010.15 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2690 | Piling Works | 100% | 2022-09-28 | 2022-09-30 | 30-Sep-22 A | 10-Oct-22 A | 100% | 100% | 5790453.17 | 5790453.17 | 0 | 1 | 5790453.17 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2710 | Stem wall Steel, Formwork and Concrete | 100% | 2022-10-02 | 2022-10-07 | 21-Oct-22 A | 25-Oct-22 A | 100% | 100% | 952724.52 | 952724.52 | 0 | 1 | 952724.52 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2720 | Backfilling | 100% | 2022-10-10 | 2022-10-14 | 19-Nov-22 A | 25-Nov-22 A | 100% | 100% | 252995.85 | 252995.85 | 0 | 1 | 252995.85 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2730 | Fixing of Steel Reinforcement of Raft | 100% | 2022-10-16 | 2022-10-19 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 156110.57 | 156110.57 | 0 | 1 | 156110.57 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2740 | Form Work Fixing of Raft | 100% | 2022-10-21 | 2022-10-21 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 50981.87 | 50981.87 | 0 | 1 | 50981.87 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2750 | Concrete of Raft | 100% | 2022-10-23 | 2022-10-23 | 01-Dec-22 A | 10-Dec-22 A | 100% | 100% | 2536235.48 | 2536235.48 | 0 | 1 | 2536235.48 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2760 | Steel and Formwork fixing of Wall till 8 ' | 100% | 2022-11-12 | 2022-11-15 | 16-Dec-22 A | 24-Dec-22 A | 100% | 100% | 156110.57 | 156110.57 | 0 | 1 | 156110.57 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2770 | Concrete of Wall till 8' | 100% | 2022-11-17 | 2022-11-17 | 16-Dec-22 A | 24-Dec-22 A | 100% | 100% | 796613.95 | 796613.95 | 0 | 1 | 796613.95 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2780 | Steel and Formwork fixing of Wall till 16' | 100% | 2022-11-21 | 2022-11-24 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 156110.57 | 156110.57 | 0 | 1 | 156110.57 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2790 | Concrete of Wall till 16' | 100% | 2022-11-26 | 2022-11-26 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 796613.95 | 796613.95 | 0 | 1 | 796613.95 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2800 | Steel and Formwork fixing of Wall till 24' | 100% | 2022-11-30 | 2022-12-03 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 156110.57 | 156110.57 | 0 | 1 | 156110.57 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2810 | Concrete of Wall till 24' | 100% | 2022-12-05 | 2022-12-05 | 07-Jan-23 A | 21-Jan-23 A | 100% | 100% | 796613.95 | 796613.95 | 0 | 1 | 796613.95 | 100% | 100% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2820 | Steel and Formwork fixing of Wall till 32' | 0% | 2022-12-09 | 2022-12-12 | 2023-01-24 | 2023-01-27 | 100% | 0% | 0 | 869725 | -869725 | 0 | 869725 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2830 | Concrete of Wall till 32' | 0% | 2022-12-14 | 2022-12-14 | 2023-01-29 | 2023-01-29 | 100% | 0% | 0 | 869725 | -869725 | 0 | 869725 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2840 | Steel and Formwork fixing of Wall till 35.75' | 0% | 2022-12-18 | 2022-12-21 | 2023-02-02 | 2023-02-05 | 100% | 0% | 0 | 869725 | -869725 | 0 | 869725 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2850 | Concrete of Wall till 35.75' | 0% | 2022-12-23 | 2022-12-23 | 2023-02-07 | 2023-02-07 | 100% | 0% | 0 | 869725 | -869725 | 0 | 869725 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.1.6 |  | Zone 5 RCC Wall B (35.75'High) 45 ft Length | 1.6 | A2860 | Backfilling | 0% | 2022-12-24 | 2023-01-01 | 2023-02-08 | 2023-02-15 | 100% | 0% | 0 | 869725 | -869725 | 0 | 869725 | 0% | 0% | 2023-01-21
Handover/Closeout | [6 empty] | 2023-01-06 | 2023-01-15 | 2023-02-16 | 2023-02-25 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.3 |  | Handover/Closeout | 3 | A3960 | Inspection, Punchlist & snag rectification | 0% | 2023-01-06 | 2023-01-15 | 2023-02-16 | 2023-02-25 | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21
RETG-WALL-R-6.3 |  | Handover/Closeout | 3 | A3970 | Handover Date | 0% |  | 2023-01-15 |  | 2023-02-25 | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2023-01-21

## Sheet2
WBS Name | WBS Code | WBS Path
Retaining Walls for School at Eighteen Rawalpindi Revised (BL) R-01 Updated 2023 Jan 28 | RETG-WALL-R-6 | RETG-WALL-R-6
Milestones | RETG-WALL-R-6.6 | 6
Mobilization/ Preliminaries | RETG-WALL-R-6.2 | 2
Engineering | RETG-WALL-R-6.7 | 7
Procurement | RETG-WALL-R-6.8 | 8
Construction | RETG-WALL-R-6.1 | 1
Zone 3 RCC Wall A (20' High) 190 ft Length | RETG-WALL-R-6.1.3 | 1.3
Zone 2 RCC Wall B (30 ' High) 173 ft Length | RETG-WALL-R-6.1.2 | 1.2
Zone 4 RCC Wall B (35.75'High) 174 ft Length | RETG-WALL-R-6.1.4 | 1.4
Zone 1 RCC Wall A (27.25' High) 80 ft Length | RETG-WALL-R-6.1.5 | 1.5
Zone 5 RCC Wall B (35.75'High) 45 ft Length | RETG-WALL-R-6.1.6 | 1.6
Handover/Closeout | RETG-WALL-R-6.3 | 3

## scurve
| 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01
Planned Value Cost | 37669310.81 | 79430016.23 | 49864753.94 | 60630120.63 | 24279464.74 | 3471652.28
Earned Value Cost | 15905114.27 | 60098707.37 | 28361719.01 | 26396797.0204 | 60133822.5374 | 24151228.7522
Cum Planned Value Cost | 37669310.81 | 117099327.04 | 166964080.98 | 227594201.61 | 251873666.35 | 255345318.63
Cum Earned Value Cost | 15905114.27 | 76003821.64 | 104365540.65 | 130762337.6704 | 190896160.2078 | 215047388.96