## Sheet1
Input
Activity ID | Description | MILESTONE_LABEL_1_PERCENTAGE | MILESTONE_LABEL_1_DESCRIPTION | Step 1 - Progress % | EARNED_MAN_HOURS_PHASE_1 | PLANNED_DATE_1 | ACTUAL_DATE_1 | FORECAST_DATE_1 | PRIMAVERA_CODE_1 | MILESTONE_LABEL_2_DESCRIPTION | MILESTONE_LABEL_2_PERCENTAGE | Step 2 - Progress % | EARNED_MAN_HOURS_PHASE_2 | PLANNED_DATE_2 | ACTUAL_DATE_2 | FORECAST_DATE_2 | PRIMAVERA_CODE_2
AI1000 | ABC | 10% | M1 | 10% | 23 | 2024-03-23 | 2024-03-15 | 2024-04-15 | HSE 1111 | M2 | 20% | 20% | 345 | 2024-04-24 |  | 2024-04-30 | HSE123
Output
Activity ID | Description | MILESTONE_LABEL_PERCENTAGE | MILESTONE_LABEL_DESCRIPTION | Step - Progress % | EARNED_MAN_HOURS_PHASE | PLANNED_DATE | ACTUAL_DATE | FORECAST_DATE | PRIMAVERA_CODE
AI1000 | ABC | 10% | M1 | 10% | 23 | 2024-03-23 | 2024-03-15 | 2024-04-15 | HSE 1111
AI1000 | ABC | 20% | M2 | 20% | 345 | 2024-04-24 |  | 2024-04-30 | HSE123