CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | 0 | [15 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | IAIN | ALLRED | Truck Driver/CDL |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 |  | 80 |  | 5 | 5 | 440 | 0 | [15 empty] | 440 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | 0 | [15 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | 0 | [15 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | 0 | [15 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | 0 | [15 empty] | 46 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | 0 | [15 empty] | 230 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | 0 | [15 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | 0 | [15 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | 0 | [15 empty] | 452.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | 0 | [15 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP8 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | 0 | [15 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Hammer Attachment | 5 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | MATT | LINDLEY | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | 0 | [15 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | MATT | LINDLEY | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | 0 | [15 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | MATT | LINDLEY | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | NICHOLAS | BLANCO | Laborer | 3 |  |  | 1 | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 10 |  | 3 | 2 | 302 | 0 | [15 empty] | 302 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | NICHOLAS | BLANCO | Laborer | 2 |  |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 5 |  | 2 | 1 | 99 | 0 | [15 empty] | 99 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | NICHOLAS | BLANCO | Laborer | 3 | 2 |  |  | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 10 |  | 5 | 2 | 277 | 0 | [15 empty] | 277 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | DANIEL | MENDOZA | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | 0 | [15 empty] | 347.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | DANIEL | MENDOZA | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | 0 | [15 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | DANIEL | MENDOZA | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | 0 | [15 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | JESUS | MENDOZA | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 138 |  | 3 | 3 | 430 | 0 | [15 empty] | 430 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | JESUS | MENDOZA | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | 0 | [15 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | JESUS | MENDOZA | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 230 |  | 5 | 5 | 497 | 0 | [15 empty] | 497 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | TYLER | BIGG | Truck Driver/CDL | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 | 151 | 48 |  | 3 | 3 | 359.5 | 0 | [15 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | TYLER | BIGG | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | 0 | [15 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | TYLER | BIGG | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | 0 | [15 empty] | 384.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | 0 | [15 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | 0 | [15 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | [7 empty] | Hammer Attachment | 3 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44132-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | Held JSA meeting, broke out rock. NDE made assessment. Sandblasted pipe, cleaned up sand. NDE returned and mapped out dent and gathered information. | [7 empty] | Hammer Attachment | 5 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | MATTHEW | LINDLEY | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | Barbed wire | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 | 0 | 1 | 1 | 87 | 0 | [15 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | MATTHEW | LINDLEY | Foreman | 2 | 4 |  |  | Pickup-F150 or F250 or equal | 6 | HR | MATTHEW | T-Posts | 7 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 548 |  | 78 | 0 | 6 | 6 | 626 | 0 | [15 empty] | 626 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | W. MONROE | LINDLEY | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 | 151 | 13 |  | 1 | 1 | 225.5 | 0 | [15 empty] | 225.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | W. MONROE | LINDLEY | Operator II | 7 | 3 |  |  | Pickup-F150 or F250 or equal | 10 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 679.5 |  | 130 |  | 10 | 10 | 809.5 | 0 | [15 empty] | 809.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | LUTHER | LINDLEY | Laborer | 1 |  |  | 1 | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 | 151 | 5 |  | 1 | 1 | 203 | 0 | [15 empty] | 203 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | LUTHER | LINDLEY | Laborer | 7 | 3 |  |  | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 518 |  | 20 |  | 10 | 4 | 538 | 0 | [15 empty] | 538 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | DEMETRIUS | DOBY | Laborer | 1 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 | 151 | 90.5 |  | 1 | 1 | 288.5 | 0 | [15 empty] | 288.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | DEMETRIUS | DOBY | Laborer | 7 | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 518 |  | 905 |  | 10 | 10 | 1423 | 0 | [15 empty] | 1423 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP3 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP3 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | 0 | [15 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | [7 empty] | Padding Bucket | 1 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-31230-44132-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | Had JSA meeting. Finished pothole adjacent line. Excavated at surveyed stakes for anomaly. While digging bellhole, found exsisting repair. Realized survey stakes were a joint downstream so it moved the anomaly location 51ft from original survey. Backfilled hole and built temporary fence. Majority of work being charged for downtime due to using the day digging in wrong location from bad survey markings. | [7 empty] | Padding Bucket | 10 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | URIEL | VALENCIA | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | URIEL | Mats | 18 | Ea | BADGER1 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | BADGER1 | [15 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | URIEL | VALENCIA | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | URIEL | T-Posts | 15 | Ea | BADGER2 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 52 | 0 | 4 | 4 | 348 | BADGER2 | [15 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [11 empty] | Safety Fence | 150 | Ft | BADGER3 | 0 | 0 | 0 | [5 empty] | 0 |  |  |  | 0 |  |  |  | BADGER3 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | HECTOR | VALDEZ NEVAREZ | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | HECTOR | VALDEZ NEVAREZ | Operator II | 4 | 3 |  |  | Pickup-F150 or F250 or equal | 7 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 495 |  | 91 |  | 7 | 7 | 586 | [16 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | HECTOR | VALDEZ NEVAREZ | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | ALEJANDRO | CRUZ CONRERAS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | ALEJANDRO | CRUZ CONRERAS | Laborer | 4 | 3 |  |  | Pickup-F150 or F250 or equal | 7 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 377 |  | 91 |  | 7 | 7 | 468 | [16 empty] | 468 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | ALEJANDRO | CRUZ CONRERAS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | IVAN | MADRID | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | IVAN | MADRID | Laborer | 4 | 3 |  |  | Tool Trailer | 7 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 377 |  | 35 |  | 7 | 7 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | IVAN | MADRID | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | ROBERTO | RODRIGUEZ | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | ROBERTO | RODRIGUEZ | Laborer | 4 | 3 |  |  | 40' Flatbed trailer or equal | 7 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 377 |  | 129.5 |  | 7 | 7 | 506.5 | [16 empty] | 506.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | ROBERTO | RODRIGUEZ | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | JOEL | VALDEZ NEVAREZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | JOEL | VALDEZ NEVAREZ | Laborer | 4 | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 377 |  | 322 |  | 7 | 7 | 699 | [16 empty] | 699 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | JOEL | VALDEZ NEVAREZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | HECTOR | QUINTANA VALDEZ | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | HECTOR | QUINTANA VALDEZ | Laborer | 4 | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 377 |  | 633.5 |  | 7 | 7 | 1010.5 | [16 empty] | 1010.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | HECTOR | QUINTANA VALDEZ | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | ASTOLFO | FLORES | Laborer | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 | 151 | 64 |  | 4 | 4 | 403 | [16 empty] | 403 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | ASTOLFO | FLORES | Laborer | 4 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | R19130 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 377 |  | 112 |  | 7 | 7 | 489 | [16 empty] | 489 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | ASTOLFO | FLORES | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19130 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | MATTHEW | SCHMITT | Truck Driver/CDL | 4 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [7 empty] | 53.5 | 72 | 0 | 151 | 27.5 |  | 214 | 151 | 110 |  | 4 | 4 | 475 | [16 empty] | 475 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | MATTHEW | SCHMITT | Truck Driver/CDL | 4 | 3 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | 7160 | [7 empty] | 53.5 | 72 | 0 | 151 | 27.5 |  | 430 |  | 192.5 |  | 7 | 7 | 622.5 | [16 empty] | 622.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | 7160 | [7 empty] | 53.5 | 72 | 0 | 151 | 27.5 |  | 72 |  | 27.5 |  | 1 | 1 | 99.5 | [16 empty] | 99.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Light Tower 6000 Watt | 7 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 91 |  |  | 7 | 91 | [16 empty] | 91 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Hammer Attachment | 7 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Hammer Attachment | 1 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Padding Bucket | 4 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Padding Bucket | 7 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Padding Bucket | 1 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44132-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | Jsa meeting. Noticed slot trenching starting to have cave ins due to sand at botttom. Got with operations to see how to proceed. (3) hydro vac trucks used to start on new area. Put together both trench boxes. Added (18) mats to entrance for slurry pit. Area was fenced off and cleaned. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB7 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | RENE | CASAREZ | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | RENE | Silt Fence | 25 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | 0 | [15 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | RENE | CASAREZ | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RENE | T-Posts | 16 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | RENE | CASAREZ | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RENE | T-Post Caps | 16 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | 0 | [15 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | RENE | CASAREZ | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RENE | Sand | 2 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | 0 | [15 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | DONALD | TIGUE | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | 0 | [15 empty] | 523.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | DONALD | TIGUE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | DONALD | TIGUE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | 0 | [15 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | DONALD | TIGUE | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | 0 | [15 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | DAVID | LOPEZ | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 230 |  | 5 | 5 | 616 | 0 | [15 empty] | 616 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | DAVID | LOPEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | 0 | [15 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | DAVID | LOPEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | 0 | [15 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | DAVID | LOPEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | 0 | [15 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | FERNANDO | GARCIA | Laborer | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 235 | 151 | 452.5 |  | 5 | 5 | 838.5 | 0 | [15 empty] | 838.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | FERNANDO | GARCIA | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | 0 | [15 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | FERNANDO | GARCIA | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | 0 | [15 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | FERNANDO | GARCIA | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | 0 | [15 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | ADDEY | BENNETT | Laborer | 5 |  |  | 1 | Hammer Attachment | 5 | HR | RHA0141a | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 235 | 151 | 0 |  | 5 | 5 | 386 | 0 | [15 empty] | 386 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | ADDEY | BENNETT | Laborer | 2 |  |  |  | Hammer Attachment | 2 | HR | RHA0141A | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 94 |  | 0 |  | 2 | 2 | 94 | 0 | [15 empty] | 94 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | ADDEY | BENNETT | Laborer | 1 |  |  |  | Hammer Attachment | 1 | HR | RHA0141A | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 47 |  | 0 |  | 1 | 1 | 47 | 0 | [15 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | ADDEY | BENNETT | Laborer |  | 2 |  |  | Hammer Attachment | 2 | HR | RHA0141A | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 126 |  | 0 |  | 2 | 2 | 126 | 0 | [15 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | MARGIL | GARZA | Laborer | 5 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC7892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 235 | 151 | 137.5 |  | 5 | 5 | 523.5 | 0 | [15 empty] | 523.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | MARGIL | GARZA | Laborer | 2 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC7892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 |  | 55 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | MARGIL | GARZA | Laborer | 1 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC7892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 |  | 27.5 |  | 1 | 1 | 74.5 | 0 | [15 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | MARGIL | GARZA | Laborer |  | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC7892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 126 |  | 55 |  | 2 | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | JODY | HASTON | Truck Driver/CDL | 5 |  |  | 1 | Padding Bucket | 5 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 267.5 | 151 | 0 |  | 5 | 5 | 418.5 | 0 | [15 empty] | 418.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | JODY | HASTON | Truck Driver/CDL | 2 |  |  |  | Padding Bucket | 2 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 107 |  | 0 |  | 2 | 2 | 107 | 0 | [15 empty] | 107 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | JODY | HASTON | Truck Driver/CDL | 1 |  |  |  | Padding Bucket | 1 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 53.5 |  | 0 |  | 1 | 1 | 53.5 | 0 | [15 empty] | 53.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | JODY | HASTON | Truck Driver/CDL |  | 2 |  |  | Padding Bucket | 2 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 144 |  | 0 |  | 2 | 2 | 144 | 0 | [15 empty] | 144 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44132-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | Sent driver to get good hammer. Used pneumatic hammer to finish hammering rock under pipe, hand dug under pipe and cleaned ditch with excavator. Installed new hammer, hammered rock, cleaned out ditch. NDE inspected, sandblasted pipe. NDE did final inspection. Finished hand digging. Cleaned up site. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP9 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | 0 | [15 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | 0 | [15 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | 0 | [15 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | 0 | [15 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | 0 | [15 empty] | 853 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 214 | 151 | 52 |  | 4 | 4 | 417 | 0 | [15 empty] | 417 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | 0 | [15 empty] | 1073 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | 0 | [15 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | 0 | [15 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | 0 | [15 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | 0 | [15 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | 0 | [15 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | 0 | [15 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | 0 | [15 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Matches crew 6 | [7 empty] | Kubota UTV | 0 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 0 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | JONATHAN | HOLLEY | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | 0 | [15 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | RYAN | FARINELLI | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | GREG | MCMILLIAN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | 0 | [15 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | JERMAINE | EVANS | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | 0 | [15 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | DEMETRIUS | MCDONALD | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | 0 | [15 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | JOSE | ORTIZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | 0 | [15 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | ROBERT | FOSTER | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | 0 | [15 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | BRIAN | RANDLE | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | 0 | [15 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | [7 empty] | Sullair Air Compressor (186 to 250 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 22.5 |  |  |  | 90 |  |  | 4 | 90 | 0 | [15 empty] | 90 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP1 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | [7 empty] | Hammer Attachment | 4 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44133-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-29 | Rained out | [7 empty] | Padding Bucket | 4 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | MATTHEW | LINDLEY | Foreman | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | MATTHEW | 2888 Coating | 3 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 518 | 151 | 91 | 0 | 7 | 7 | 760 | 0 | [15 empty] | 760 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | MATTHEW | LINDLEY | Foreman | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | T-Posts | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 174 |  | 26 | 0 | 2 | 2 | 200 | 0 | [15 empty] | 200 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | MATTHEW | LINDLEY | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | Safety Fence | 120 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | 0 | [15 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | MATTHEW | LINDLEY | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | 0 | [15 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | W. MONROE | LINDLEY | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 369 | 151 | 78 |  | 6 | 6 | 598 | 0 | [15 empty] | 598 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | W. MONROE | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | W. MONROE | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | 0 | [15 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | W. MONROE | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | 0 | [15 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | LUTHER | LINDLEY | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | 0 | [15 empty] | 511 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | LUTHER | LINDLEY | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | 0 | [15 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | 0 | [15 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | 0 | [15 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | DEMETRIUS | DOBY | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | 0 | [15 empty] | 463 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | DEMETRIUS | DOBY | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | DEMETRIUS | DOBY | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | 0 | [15 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | DEMETRIUS | DOBY | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | 0 | [15 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | NICHOLAS | BLANCO | Laborer | 6 |  |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 282 | 151 | 111 |  | 6 | 6 | 544 | 0 | [15 empty] | 544 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | NICHOLAS | BLANCO | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | 0 | [15 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | NICHOLAS | BLANCO | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | 0 | [15 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | NICHOLAS | BLANCO | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | 0 | [15 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | DANIEL | MENDOZA | Laborer | 7 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 329 | 151 | 276 |  | 7 | 6 | 756 | 0 | [15 empty] | 756 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | DANIEL | MENDOZA | Laborer | 1 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 110 |  | 92 |  | 2 | 2 | 202 | 0 | [15 empty] | 202 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | DANIEL | MENDOZA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | 0 | [15 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | DANIEL | MENDOZA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | 0 | [15 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | JESUS | MENDOZA | Laborer | 6 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 282 | 151 | 543 |  | 6 | 6 | 976 | 0 | [15 empty] | 976 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | JESUS | MENDOZA | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | 0 | [15 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | JESUS | MENDOZA | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | 0 | [15 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | JESUS | MENDOZA | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | 0 | [15 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | TYLER | BIGG | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | 0 | [15 empty] | 568 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | TYLER | BIGG | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | 0 | [15 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | TYLER | BIGG | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | 0 | [15 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | TYLER | BIGG | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | 0 | [15 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | 0 | [15 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Light Tower 6000 Watt | 6 | HR | RLP3 | [11 empty] | 13 |  |  |  | 78 |  |  | 6 | 78 | 0 | [15 empty] | 78 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP3 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP3 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP3 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Hammer Attachment | 6 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Hammer Attachment | 1 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Hammer Attachment | 1 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Padding Bucket | 6 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Padding Bucket | 1 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31230-44133-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-29 | Pot holed, excavated. Located clock position up stream, redug, finished bellhole. Decided to use ladders in and out of bellhole. (2) hours downtime waiting on decision. Wire brushed and sandpaper used to repair coating. Installed safety fence. | [7 empty] | Padding Bucket | 1 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | GERALD | SMITH | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 104 |  | 10 | 8 | 1047 | 0 | [15 empty] | 1047 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | MICHAEL | RATLIFF | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | OJ | SEALS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | 0 | [15 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | RICHARD | ADKINS | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | 0 | [15 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | BARRETT | WISE | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | 0 | [15 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | MICHAEL | ELLIOTT | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | 0 | [15 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | DAVID | RATLIFF | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | 0 | [15 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | STEVE | CLARK | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | 0 | [15 empty] | 568 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858b | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | 0 | [15 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | [7 empty] | Hammer Attachment | 4 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44133-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-29 | Went to jobsite and waited to see if rain would pass. Rained out | [7 empty] | Padding Bucket | 4 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Material - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Material | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | CALEB | HOLTON | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | 0 | [15 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | CALEB | HOLTON | Foreman | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 422 |  | 65 |  | 5 | 5 | 487 | 0 | [15 empty] | 487 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | THOMAS | FRANKLIN | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Material - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Material | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | MICHAEL | ANISZEWSKI | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | 0 | [15 empty] | 451 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | MICHAEL | ANISZEWSKI | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | 0 | [15 empty] | 332 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | BOLDBAUTOR | ZORIGT | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | 0 | [15 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Material - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Material | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | JORDAN | WIGGINS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 74 |  | 5 | 4 | 460 | 0 | [15 empty] | 460 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | JORDAN | WIGGINS | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 184 |  | 5 | 4 | 451 | 0 | [15 empty] | 451 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | DAVID | KNOTTS | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | 0 | [15 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | TANNER | BRITT | Laborer | 4 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 188 | 151 | 110 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | ALDO | RENYA | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 192 |  | 12 | 12 | 1059 | 0 | [15 empty] | 1059 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | [7 empty] | Padding Bucket | 4 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44133-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-29 | Raining and put most of crew on rain out. Foreman and (2) labors on stand by waiting on sleeve from Arkansas. Driver drove to KY to deliver paperwork and pick up supplies | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | 0 | [15 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | BARKLEY | BROWN | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | 0 | [15 empty] | 1073 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | JOSHUA | MENDARIES | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | 0 | [15 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | WAYLON | GREEN | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | 0 | [15 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | JOSE | VALLES | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | 0 | [15 empty] | 567 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | REYMUNDO | REYES | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | 0 | [15 empty] | 675 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | MARCELO | GOMEZ | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | 0 | [15 empty] | 895 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | ANTHONY | MORENO | Laborer | 8 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 376 | 151 | 724 |  | 8 | 8 | 1251 | 0 | [15 empty] | 1251 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | EFREM | LEE | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | 0 | [15 empty] | 707 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | 0 | [15 empty] | 220 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP6 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | [7 empty] | Hammer Attachment | 8 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | [7 empty] | Brush Hog | 8 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-58100-44133-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-29 | Site is in floodzone. Had crew pull everything out before it flooded out. Driver and labor went to get supplies and parts. Foreman is getting prepared for tomorrow. | [7 empty] | Padding Bucket | 8 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | URIEL | VALENCIA | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15349 |  |  |  | BADGER1 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | BADGER1 | [15 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | HECTOR | VALDEZ NEVAREZ | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | HECTOR |  |  |  | BADGER2 | 0 | 0 | 0 | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | BADGER2 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | ALEJANDRO | CRUZ CONTRERAS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | ASTOLFO | FLORES | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | IVAN | MADRID | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | ROBERTO | RODRIGUEZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | JOEL | VALDEZ NEVAREZ | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | HECTOR | QUINTANA VALDEZ | Laborer | 4 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 188 | 151 | 110 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | MATTHEW | SCHMITT | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | [7 empty] | Padding Bucket | 4 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-110-44133-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | Rain out | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB7 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-29250-44133-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-29 | Rain out | GARRETT | DICKSON | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | 0 | [15 empty] | 847 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-29250-44133-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-29 | Rain out | SHAWN | ROSE | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-29250-44133-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-29 | Rain out | GAGE | BURKS | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | 0 | [15 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-29250-44133-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-29 | Rain out | ZACHARY | POWDERS | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | 0 | [15 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-29250-44133-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-29 | Rain out | COLTON | ROBERTS | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | 0 | [15 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-29250-44133-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-29 | Rain out | MICHAEL | TATUM | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | 0 | [15 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-29250-44133-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-29 | Rain out | DANIEL | MARTIN | Laborer | 4 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 188 | 151 | 110 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-29250-44133-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-29 | Rain out | IAIN | ALLRED | Truck Driver/CDL | 4 |  |  | 1 | Light Tower 6000 Watt | 4 | HR | RLP8 | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 214 | 151 | 52 |  | 4 | 4 | 417 | 0 | [15 empty] | 417 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-29250-44133-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-29 | Rain out | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-10630-44133-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-29 | Went to site to evaluate conditions. Determined rain out | RENE | CASAREZ | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RENE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 52 |  | 10 | 4 | 995 | 0 | [15 empty] | 995 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-10630-44133-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-29 | Went to site to evaluate conditions. Determined rain out | DONALD | TIGUE | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-10630-44133-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-29 | Went to site to evaluate conditions. Determined rain out | DAVID | LOPEZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | 0 | [15 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-10630-44133-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-29 | Went to site to evaluate conditions. Determined rain out | FERNANDO | GARCIA | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX02778 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | 0 | [15 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-10630-44133-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-29 | Went to site to evaluate conditions. Determined rain out | ADDEY | BENNETT | Laborer | 4 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC7892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 188 | 151 | 110 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-10630-44133-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-29 | Went to site to evaluate conditions. Determined rain out | MARGIL | GARZA | Laborer | 4 |  |  | 1 | Hammer Attachment | 4 | HR | RHA0141B | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 188 | 151 | 0 |  | 4 | 4 | 339 | 0 | [15 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-10630-44133-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-29 | Went to site to evaluate conditions. Determined rain out | JODY | HASTON | Truck Driver/CDL | 4 |  |  | 1 | Padding Bucket | 4 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 214 | 151 | 0 |  | 4 | 4 | 365 | 0 | [15 empty] | 365 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-10630-44133-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-29 | Went to site to evaluate conditions. Determined rain out | [31 empty] | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44133-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-29 | Had JSA, finished backfilling and started spreading topsoil. Then rain came | KYLE | BONNEAU | Foreman | 8 | 1 |  | 1 | Pickup-F150 or F250 or equal | 0 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 692 | 151 | 0 |  | 9 | 0 | 843 | 0 | [15 empty] | 843 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44133-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-29 | Had JSA, finished backfilling and started spreading topsoil. Then rain came | JESSE | BERTHIAUME | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 0 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 0 |  | 8 | 0 | 643 | 0 | [15 empty] | 643 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44133-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-29 | Had JSA, finished backfilling and started spreading topsoil. Then rain came | JACOB | CAPITANO | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 0 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 0 |  | 8 | 0 | 527 | 0 | [15 empty] | 527 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44133-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-29 | Had JSA, finished backfilling and started spreading topsoil. Then rain came | BROC | CALIGER | Laborer | 8 |  |  | 1 | Tool Trailer | 0 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 0 |  | 8 | 0 | 527 | 0 | [15 empty] | 527 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44133-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-29 | Had JSA, finished backfilling and started spreading topsoil. Then rain came | CODY | GAXIOLA | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 0 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 0 |  | 8 | 0 | 527 | 0 | [15 empty] | 527 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44133-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-29 | Had JSA, finished backfilling and started spreading topsoil. Then rain came | HEATHER | ENGLE | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 0 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 0 |  | 8 | 0 | 527 | 0 | [15 empty] | 527 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44133-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-29 | Had JSA, finished backfilling and started spreading topsoil. Then rain came | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 0 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 0 |  | 8 | 0 | 579 | 0 | [15 empty] | 579 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1492 - MC.400216.032 - 674.399 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1492 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 236624.47 | 61420 | Central | IN | 674.399 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1493 - MC.400216.032 - 682.498 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1493 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 279423.05 | 72330 | Central | IN | 682.498 | 2020-10-14 | [32 empty] | CROSS COUNTRY | 4080338 | COATING SUPPLIES | 990.29 | 79.2232 |  | 1069.5132 | [9 empty] | 1069.5132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1493 - MC.400216.032 - 682.498 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-1493 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 279423.05 | 72330 | Central | IN | 682.498 | 2020-10-15 | [32 empty] | CROSS COUNTRY | 4080371 | COATING SUPPLIES | 1277.84 | 102.2272 |  | 1380.0672 | [9 empty] | 1380.0672 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 1 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-15 | [32 empty] | CROSS COUNTRY | 4080371 | COATING SUPPLIES | 1277.84 | 102.2272 |  | 1380.0672 | [9 empty] | 1380.0672 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1492 - MC.400216.032 - 674.399 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1492 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 236624.47 | 61420 | Central | IN | 674.399 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1493 - MC.400216.032 - 682.498 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1493 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 279423.05 | 72330 | Central | IN | 682.498 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1493 - MC.400216.032 - 682.498 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-1493 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 279423.05 | 72330 | Central | IN | 682.498 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 1 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-23 | [32 empty] | CROSS COUNTRY | 4080755 | ROCKSHIELD | 572.4 | 45.792 |  | 618.192 | [9 empty] | 618.192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 1 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | [32 empty] | HERCRENTALS | 31721032-001 | TELEHANDLER | 226.67 | 18.1336 |  | 244.8036 | [9 empty] | 244.8036 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 1 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | [32 empty] | HERCRENTALS | 31721032-001 | TELEHANDLER | 226.67 | 18.1336 |  | 244.8036 | [9 empty] | 244.8036 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | [32 empty] | HERCRENTALS | 31721032-001 | TELEHANDLER | 226.67 | 18.1336 |  | 244.8036 | [9 empty] | 244.8036 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | [32 empty] | HERCRENTALS | 31721032-001 | TELEHANDLER | 226.67 | 18.1336 |  | 244.8036 | [9 empty] | 244.8036 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1492 - MC.400216.032 - 674.399 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1492 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 236624.47 | 61420 | Central | IN | 674.399 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1493 - MC.400216.032 - 682.498 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 1 | DIG-1493 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 279423.05 | 72330 | Central | IN | 682.498 | 2020-10-20 | [32 empty] | PSS | 2396700-00 | TRASH BAGS / WET FILM | 47.15 | 3.772 |  | 50.922 | [9 empty] | 50.922 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-27 | [32 empty] | PSS | 2401640-00 | SIGNAGE | 170.87 | 13.6696 |  | 184.5396 | [9 empty] | 184.5396 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 1 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | [32 empty] | PSS | 2401640-00 | SIGNAGE | 170.87 | 13.6696 |  | 184.5396 | [9 empty] | 184.5396 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 1 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | [32 empty] | PSS | 2401640-00 | SIGNAGE | 170.87 | 13.6696 |  | 184.5396 | [9 empty] | 184.5396 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 1 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-27 | [32 empty] | PSS | 2401640-00 | SIGNAGE | 170.87 | 13.6696 |  | 184.5396 | [9 empty] | 184.5396 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 1 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | [32 empty] | PSS | 2401640-00 | SIGNAGE | 170.87 | 13.6696 |  | 184.5396 | [9 empty] | 184.5396 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 1 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | [32 empty] | TROPHY LOGISTICS | 10577A | 3RD PARTY TRUCKING | 325 | 26 |  | 351 | [9 empty] | 351 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 1 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-21 | [32 empty] | TROPHY LOGISTICS | 10577A | 3RD PARTY TRUCKING | 325 | 26 |  | 351 | [9 empty] | 351 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 1 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-21 | [32 empty] | TROPHY LOGISTICS | 10577A | 3RD PARTY TRUCKING | 325 | 26 |  | 351 | [9 empty] | 351 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 1 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-21 | [32 empty] | TROPHY LOGISTICS | 10577A | 3RD PARTY TRUCKING | 325 | 26 |  | 351 | [9 empty] | 351 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 1 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-23 | [32 empty] | UNITED RENTALS | 3521550 | TRENCH BOX | 501.3333 | 40.1067 |  | 541.44 | [9 empty] | 541.44 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 1 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-23 | [32 empty] | UNITED RENTALS | 3521550 | TRENCH BOX | 501.3333 | 40.1067 |  | 541.44 | [9 empty] | 541.44 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 1 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-23 | [32 empty] | UNITED RENTALS | 3521550 | TRENCH BOX | 501.3333 | 40.1067 |  | 541.44 | [9 empty] | 541.44 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 1 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-23 | [32 empty] | UNITED RENTALS | 3521550 | TRENCH BOX | 501.3333 | 40.1067 |  | 541.44 | [9 empty] | 541.44 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 1 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-23 | [32 empty] | UNITED RENTALS | 3521550 | TRENCH BOX | 501.3333 | 40.1067 |  | 541.44 | [9 empty] | 541.44 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 1 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-23 | [32 empty] | UNITED RENTALS | 3521550 | TRENCH BOX | 501.3333 | 40.1067 |  | 541.44 | [9 empty] | 541.44 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | [32 empty] | WILKINSON HARDWOODS, LLC | E05840222 | MATS | 3845 | 307.6 |  | 4152.6 | [9 empty] | 4152.6 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | RENE | CASAREZ | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RENE | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 | 151 | 26 | 0 | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | RENE | CASAREZ | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | RENE | Sand | 6 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | RENE | CASAREZ | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | RENE | 2888 Coating | 5 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 500 |  | 65 | 0 | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | DONALD | TIGUE | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | DONALD | 4888 Coating | 4 | L |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 123 | 151 | 26 | 0 | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | DONALD | TIGUE | Operator II | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | DONALD | Brushes | 18 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 227.5 |  | 39 | 0 | 3 | 3 | 266.5 | [16 empty] | 266.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | DONALD | TIGUE | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | DAVID | LOPEZ | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | DAVID | LOPEZ | Laborer | 1 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 173 |  | 138 |  | 3 | 3 | 311 | [16 empty] | 311 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | DAVID | LOPEZ | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | FERNANDO | GARCIA | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | FERNANDO | GARCIA | Laborer | 1 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 173 |  | 271.5 |  | 3 | 3 | 444.5 | [16 empty] | 444.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | FERNANDO | GARCIA | Laborer |  | 5 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 |  | 452.5 |  | 5 | 5 | 767.5 | [16 empty] | 767.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | ADDEY | BENNETT | Laborer | 2 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC77892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 | 151 | 55 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | ADDEY | BENNETT | Laborer | 1 | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC77892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 173 |  | 82.5 |  | 3 | 3 | 255.5 | [16 empty] | 255.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | ADDEY | BENNETT | Laborer |  | 5 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC77892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 315 |  | 137.5 |  | 5 | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | MARGIL | GARZA | Laborer | 2 |  |  | 1 | Hammer Attachment | 2 | HR | RHA10141 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 94 | 151 | 0 |  | 2 | 2 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | MARGIL | GARZA | Laborer | 1 | 2 |  |  | Hammer Attachment | 3 | HR | RHA10141 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 173 |  | 0 |  | 3 | 3 | 173 | [16 empty] | 173 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | MARGIL | GARZA | Laborer |  | 5 |  |  | Hammer Attachment | 5 | HR | RHA10141 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 315 |  | 0 |  | 5 | 5 | 315 | [16 empty] | 315 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | JODY | HASTON | Truck Driver/CDL | 2 |  |  | 1 | Padding Bucket | 2 | HR | RPB17093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 107 | 151 | 0 |  | 2 | 2 | 258 | [16 empty] | 258 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | JODY | HASTON | Truck Driver/CDL | 1 | 2 |  |  | Padding Bucket | 3 | HR | RPB17093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 197.5 |  | 0 |  | 3 | 3 | 197.5 | [16 empty] | 197.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | JODY | HASTON | Truck Driver/CDL |  | 5 |  |  | Padding Bucket | 5 | HR | RPB17093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 360 |  | 0 |  | 5 | 5 | 360 | [16 empty] | 360 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP9 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10630-44134-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-30 | Pumped water. Set up tp sandblast pipe. NDE assessed and gave approval to coat pipe. Jeeped downhill section where anomaly was supposed to be. Rocksheild downhill section. Started backfilling | [7 empty] | Water Pump (3") | 2 | HR | 3INP9 | [11 empty] | 12 |  |  |  | 24 |  |  | 2 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-29300-44134-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-30 | Fire watch for NDE. | JESUS | MENDOZA | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Repair - Grind Out - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Grind Out | 3500028468-29300-44134-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-30 | Fire watch for NDE. | JESUS | MENDOZA | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | MATTHEW | LINDLEY | Foreman |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 | 151 | 65 |  | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | MATTHEW | LINDLEY | Foreman |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 600 |  | 78 |  | 6 | 6 | 678 | [16 empty] | 678 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | W. MONROE | LINDLEY | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 | 151 | 65 |  | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | W. MONROE | LINDLEY | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | LUTHER | LINDLEY | Laborer |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 | 151 | 65 |  | 5 | 5 | 531 | [16 empty] | 531 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | LUTHER | LINDLEY | Laborer |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 |  | 65 |  | 5 | 5 | 380 | [16 empty] | 380 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | DEMETRIUS | DOBY | Laborer |  | 5 |  | 1 | Tool Trailer | 5 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 | 151 | 25 |  | 5 | 5 | 491 | [16 empty] | 491 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | DEMETRIUS | DOBY | Laborer |  | 5 |  |  | Tool Trailer | 5 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 |  | 25 |  | 5 | 5 | 340 | [16 empty] | 340 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | NICHOLAS | BLANCO | Laborer |  | 5 |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 | 151 | 92.5 |  | 5 | 5 | 558.5 | [16 empty] | 558.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | NICHOLAS | BLANCO | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 92.5 |  | 5 | 5 | 407.5 | [16 empty] | 407.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | DANIEL | MENDOZA | Laborer |  | 5 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 | 151 | 230 |  | 5 | 5 | 696 | [16 empty] | 696 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | DANIEL | MENDOZA | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | JESUS | MENDOZA | Laborer |  | 5 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 | 151 | 452.5 |  | 5 | 5 | 918.5 | [16 empty] | 918.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | JESUS | MENDOZA | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 452.5 |  | 2 | 5 | 578.5 | [16 empty] | 578.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | TYLER | BIGG | Truck Driver/CDL |  | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 | 151 | 80 |  | 5 | 5 | 591 | [16 empty] | 591 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | TYLER | BIGG | Truck Driver/CDL |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 |  | 80 |  | 5 | 5 | 440 | [16 empty] | 440 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | [7 empty] | Hammer Attachment | 5 | HR | RHA3 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | [7 empty] | Hammer Attachment | 5 | HR | RHA3 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | [7 empty] | Padding Bucket | 5 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | [7 empty] | Padding Bucket | 5 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP3 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44134-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-30 | Padded pipe and backfilled. Began spreading topsoil, cleaned up site, reinstalled pipeline marker. Prepared to MOB to 1553 | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP3 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [16 empty] | 1541 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | TOME | KIRKLAND | Superintendent |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1512 | 151 | 156 |  | 12 | 12 | 1819 | [16 empty] | 1819 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | MICHAEL | GOSS | Truck Driver/CDL |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | MICHAEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 792 | 151 | 143 |  | 11 | 11 | 1086 | [16 empty] | 1086 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | JASON | JONES | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 156 |  | 12 | 12 | 1171 | [16 empty] | 1171 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | JUANITO | RODRIGUEZ | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | SCOTT | MERRY | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 11 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 462 |  | 10 | 11 | 1601 | [16 empty] | 1601 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | [7 empty] | Tractor/Semi | 12 | HR | 1376 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | [7 empty] | Tractor/Semi | 12 | HR | R1371 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | [7 empty] | Lowboy Trailer | 11 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 203.5 |  |  | 11 | 203.5 | [16 empty] | 203.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | [7 empty] | Lowboy Trailer | 12 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | Matches crew 7 | [7 empty] | Kubota UTV | 10 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | JONATHAN | HOLLEY | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | RYAN | FARINELLI | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | GREG | MCMILLIAN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | JERMAINE | EVANS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | JOSE | ORTIZ | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | ROBERT | FOSTER | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | BRIAN | RANDLE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | [7 empty] | Hammer Attachment | 1 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | [7 empty] | Padding Bucket | 1 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44134-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-30 | Jeeped and repaired coating | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP1 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | JONATHAN | HOLLEY | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | 2888 Coating | 10 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | JONATHAN | HOLLEY | Foreman | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JONATHAN | Brushes | 13 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 448 |  | 65 | 0 | 5 | 5 | 513 | [16 empty] | 513 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | RYAN | FARINELLI | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYAN | Sand | 5 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 246 | 151 | 52 | 0 | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | RYAN | FARINELLI | Operator II | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 372 |  | 65 |  | 5 | 5 | 437 | [16 empty] | 437 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | GREG | MCMILLIAN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | GREG | MCMILLIAN | Laborer | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 283 |  | 65 |  | 5 | 5 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | JERMAINE | EVANS | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | JERMAINE | EVANS | Laborer | 2 | 3 |  |  | Tool Trailer | 5 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 283 |  | 25 |  | 5 | 5 | 308 | [16 empty] | 308 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | DEMETRIUS | MCDONALD | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | DEMETRIUS | MCDONALD | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 92.5 |  | 1 | 5 | 139.5 | [16 empty] | 139.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | JOSE | ORTIZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | JOSE | ORTIZ | Laborer | 2 | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 283 |  | 230 |  | 5 | 5 | 513 | [16 empty] | 513 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | ROBERT | FOSTER | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | ROBERT | FOSTER | Laborer | 2 | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 283 |  | 452.5 |  | 5 | 5 | 735.5 | [16 empty] | 735.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | BRIAN | RANDLE | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | BRIAN | RANDLE | Truck Driver/CDL | 2 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 323 |  | 80 |  | 5 | 5 | 403 | [16 empty] | 403 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP1 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP1 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | [7 empty] | Hammer Attachment | 4 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | [7 empty] | Hammer Attachment | 5 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | [7 empty] | Padding Bucket | 4 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | [7 empty] | Padding Bucket | 5 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44134-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-30 | Sandblasted and coated | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 4 | HR | RSP1 | [11 empty] | 23.5 |  |  |  | 94 |  |  | 4 | 94 | [16 empty] | 94 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | KYLE | BONNEAU | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | KYLE | Seed Mix | 75 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 600 | 151 | 78 | 0 | 6 | 6 | 829 | [16 empty] | 829 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | Fertilizer | 100 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | JESSE | BERTHIAUME | Operator II |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JESSE | Straw Bales | 40 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 498 | 151 | 78 | 0 | 6 | 6 | 727 | [16 empty] | 727 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | JACOB | CAPITANO | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | JACOB | CAPITANO | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | BROC | CALIGER | Laborer |  | 6 |  | 1 | Tool Trailer | 6 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 | 151 | 30 |  | 6 | 6 | 559 | [16 empty] | 559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | BROC | CALIGER | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | CODY | GAXIOLA | Laborer |  | 6 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 | 151 | 111 |  | 6 | 6 | 640 | [16 empty] | 640 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | CODY | GAXIOLA | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | HEATHER | ENGLE | Laborer |  | 6 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 378 | 151 | 276 |  | 6 | 6 | 805 | [16 empty] | 805 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | HEATHER | ENGLE | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 | 151 | 96 |  | 6 | 6 | 679 | [16 empty] | 679 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Hammer Attachment | 6 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Hammer Attachment | 1 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Brush Hog | 6 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Brush Hog | 1 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Padding Bucket | 6 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Padding Bucket | 1 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Light Tower 6000 Watt | 6 | HR | RLP2 | [11 empty] | 13 |  |  |  | 78 |  |  | 6 | 78 | [16 empty] | 78 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-17790-44134-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | Had JHA, finished spreading topsoil, fertilized, seeded, mulched and cleaned up access road. Tightened up ECD's Demob | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP2 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | Silt Fence | 450 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | KYLE | BONNEAU | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | JESSE | BERTHIAUME | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | JACOB | CAPITANO | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | JACOB | CAPITANO | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | BROC | CALIGER | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | BROC | CALIGER | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | CODY | GAXIOLA | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | CODY | GAXIOLA | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | HEATHER | ENGLE | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | HEATHER | ENGLE | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Hammer Attachment | 1 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Hammer Attachment | 3 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Brush Hog | 1 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Brush Hog | 3 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Padding Bucket | 1 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Padding Bucket | 3 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP2 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28570-44134-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-30 | Mob into site. Installed ECD's mechanic came and installed quick connects to excavator | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP2 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | GERALD | SMITH | Foreman |  | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | GERALD | Fertilizer | 100 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 16 | 0 | 500 | 151 | 80 | 0 | 5 | 5 | 731 | [16 empty] | 731 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | GERALD | SMITH | Foreman |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | GERALD | Seed Mix | 20 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 16 | 0 | 100 |  | 16 | 0 | 1 | 1 | 116 | [16 empty] | 116 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | MICHAEL | RATLIFF | Operator II | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | MICHAELR | Lime | 4 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 16 | 0 | 307.5 | 151 | 80 | 0 | 5 | 5 | 538.5 | [16 empty] | 538.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | MICHAEL | RATLIFF | Operator II |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | MICHAELR | Straw Bales | 15 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 16 | 0 | 83 |  | 16 | 0 | 1 | 1 | 99 | [16 empty] | 99 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | OJ | SEALS | Laborer | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 235 | 151 | 80 |  | 5 | 5 | 466 | [16 empty] | 466 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | OJ | SEALS | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | RICHARD | ADKINS | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | RICHARD | ADKINS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | BARRETT | WISE | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 230 |  | 5 | 5 | 616 | [16 empty] | 616 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | BARRETT | WISE | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | DAVID | RATLIFF | Laborer | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 235 | 151 | 452.5 |  | 5 | 5 | 838.5 | [16 empty] | 838.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | DAVID | RATLIFF | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | STEVE | CLARK | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | [7 empty] | Hammer Attachment | 5 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | [7 empty] | Hammer Attachment | 1 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | [7 empty] | Padding Bucket | 5 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44134-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-30 | Finished grassing and clean up on site. Demob Equipment to 1556 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | GERALD | SMITH | Foreman |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 300 |  | 80 |  | 3 | 5 | 380 | [16 empty] | 380 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | GERALD | SMITH | Foreman |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 200 |  | 16 |  | 2 | 1 | 216 | [16 empty] | 216 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | MICHAEL | RATLIFF | Operator II |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 166 |  | 80 |  | 2 | 5 | 246 | [16 empty] | 246 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | MICHAEL | RATLIFF | Operator II |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 166 |  | 16 |  | 2 | 1 | 182 | [16 empty] | 182 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | OJ | SEALS | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 80 |  | 2 | 5 | 206 | [16 empty] | 206 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | OJ | SEALS | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 16 |  | 2 | 1 | 142 | [16 empty] | 142 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | RICHARD | ADKINS | Laborer |  | 2 |  |  | Tool Trailer | 5 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 25 |  | 2 | 5 | 151 | [16 empty] | 151 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | RICHARD | ADKINS | Laborer |  | 2 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 5 |  | 2 | 1 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | BARRETT | WISE | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 230 |  | 2 | 5 | 356 | [16 empty] | 356 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | BARRETT | WISE | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 46 |  | 2 | 1 | 172 | [16 empty] | 172 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | DAVID | RATLIFF | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 452.5 |  | 2 | 5 | 578.5 | [16 empty] | 578.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | DAVID | RATLIFF | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 90.5 |  | 2 | 1 | 216.5 | [16 empty] | 216.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | STEVE | CLARK | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 80 |  | 4 | 5 | 368 | [16 empty] | 368 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | [7 empty] | Hammer Attachment | 5 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | [7 empty] | Hammer Attachment | 1 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | [7 empty] | Padding Bucket | 5 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51610-44134-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | MOB into site with equipment and supplies. Got to the ROW and dig site, got set up. | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | CALEB | HOLTON | Foreman |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 | 151 | 52 |  | 4 | 4 | 603 | [16 empty] | 603 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | THOMAS | FRANKLIN | Operator II |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 | 151 | 52 |  | 4 | 4 | 535 | [16 empty] | 535 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | MICHAEL | ANISZEWSKI | Laborer |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 | 151 | 52 |  | 4 | 4 | 455 | [16 empty] | 455 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | BOLDBAUTOR | ZORIGT | Laborer |  | 4 |  | 1 | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 | 151 | 20 |  | 4 | 4 | 423 | [16 empty] | 423 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | JORDAN | WIGGINS | Laborer |  | 4 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 | 151 | 74 |  | 4 | 4 | 477 | [16 empty] | 477 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | DAVID | KNOTTS | Laborer |  | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 | 151 | 184 |  | 4 | 4 | 587 | [16 empty] | 587 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | TANNER | BRITT | Laborer |  | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 | 151 | 362 |  | 4 | 4 | 765 | [16 empty] | 765 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | ALDO | RENYA | Truck Driver/CDL |  | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 | 151 | 64 |  | 4 | 4 | 503 | [16 empty] | 503 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-9400-44134-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-30 | Demob to 1476 | [7 empty] | Padding Bucket | 4 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | CALEB | HOLTON | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | CALEB |  |  |  | State Line Service | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | State Line Service | [15 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | CALEB | HOLTON | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | THOMAS | FRANKLIN | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | THOMAS | FRANKLIN | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | MICHAEL | ANISZEWSKI | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | MICHAEL | ANISZEWSKI | Laborer |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 |  | 65 |  | 5 | 5 | 380 | [16 empty] | 380 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | BOLDBAUTOR | ZORIGT | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | BOLDBAUTOR | ZORIGT | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | JORDAN | WIGGINS | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | JORDAN | WIGGINS | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 74 |  | 5 | 4 | 389 | [16 empty] | 389 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | DAVID | KNOTTS | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | DAVID | KNOTTS | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | TANNER | BRITT | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | TANNER | BRITT | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | ALDO | RENYA | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | ALDO | RENYA | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Padding Bucket | 4 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Padding Bucket | 4 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44134-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-30 | Pumped water and cleaned bellhole. Welders prepped sleeves. Oce measurements were done, lowered sleeves and fitted sleeves over anomaly. Welded on sleeves | [7 empty] | Water Pump ( up to 2") | 4 | HR | 2INP5 | [11 empty] | 6 |  |  |  | 24 |  |  | 4 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | BARKLEY | BROWN | Foreman |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 500 | 151 | 65 | 0 | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | JOSHUA | MENDARIES | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 | 151 | 65 |  | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | WAYLON | GREEN | Laborer |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 | 151 | 65 |  | 5 | 5 | 531 | [16 empty] | 531 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | JOSE | VALLES | Laborer |  | 5 |  | 1 | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 | 151 | 25 |  | 5 | 5 | 491 | [16 empty] | 491 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | REYMUNDO | REYES | Laborer |  | 5 |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 | 151 | 92.5 |  | 5 | 5 | 558.5 | [16 empty] | 558.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | MARCELO | GOMEZ | Laborer |  | 5 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 | 151 | 230 |  | 5 | 5 | 696 | [16 empty] | 696 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | ANTHONY | MORENO | Laborer |  | 5 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 | 151 | 452.5 |  | 5 | 5 | 918.5 | [16 empty] | 918.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | EFREM | LEE | Truck Driver/CDL |  | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 | 151 | 80 |  | 5 | 5 | 591 | [16 empty] | 591 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Brush Hog | 5 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Hammer Attachment | 5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP6 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44134-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Water Pump (3") | 5 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 60 |  |  | 5 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | BARKLEY | BROWN | Foreman |  | 6 |  |  | Pickup-F150 or F250 or equal | 5 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 600 |  | 65 | 0 | 6 | 5 | 665 | [16 empty] | 665 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | JOSHUA | MENDARIES | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | WAYLON | GREEN | Laborer |  | 6 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 |  | 65 |  | 6 | 5 | 443 | [16 empty] | 443 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | JOSE | VALLES | Laborer |  | 5 |  |  | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 |  | 25 |  | 5 | 5 | 340 | [16 empty] | 340 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | REYMUNDO | REYES | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 92.5 |  | 5 | 5 | 407.5 | [16 empty] | 407.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | MARCELO | GOMEZ | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | ANTHONY | MORENO | Laborer |  | 5 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 |  | 452.5 |  | 5 | 5 | 767.5 | [16 empty] | 767.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | EFREM | LEE | Truck Driver/CDL |  | 6 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 |  | 80 |  | 6 | 5 | 512 | [16 empty] | 512 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Brush Hog | 5 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Hammer Attachment | 5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP6 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44134-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-30 | Pumped water out of bellholes since in flood zone and amount of rain. Cleaned up site to set up to sandblast next day. | [7 empty] | Water Pump (3") | 5 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 60 |  |  | 5 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | URIEL | VALENCIA | Foreman |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | R15349 | Silt Fence | 100 | Ft | BADGER1 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 1200 | 151 | 156 | 0 | 12 | 12 | 1507 | BADGER1 | [15 empty] | 1507 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | HECTOR | VALDEZ NEVAREZ | Operator II |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | HECTOR | Filter Bag | 3 | Ea | BADGER2 | 0 | 0 | 0 | 61.5 | 83 | 0 | 151 | 13 | 0 | 996 | 151 | 156 | 0 | 12 | 12 | 1303 | BADGER2 | [15 empty] | 1303 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 756 | 151 | 156 |  | 12 | 12 | 1063 | [16 empty] | 1063 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | ASTOLFO | FLORES | Laborer |  | 12 |  | 1 | Tool Trailer | 12 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 756 | 151 | 60 |  | 12 | 12 | 967 | [16 empty] | 967 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | IVAN | MADRID | Laborer |  | 12 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 756 | 151 | 222 |  | 12 | 12 | 1129 | [16 empty] | 1129 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | ROBERTO | RODRIGUEZ | Laborer |  | 12 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 756 | 151 | 552 |  | 12 | 12 | 1459 | [16 empty] | 1459 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | JOEL | VALDEZ NEVAREZ | Laborer |  | 12 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 12 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 756 | 151 | 1086 |  | 12 | 12 | 1993 | [16 empty] | 1993 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | HECTOR | QUINTANA VALDEZ | Laborer |  | 12 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 12 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 756 | 151 | 330 |  | 12 | 12 | 1237 | [16 empty] | 1237 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | MATTHEW | SCHMITT | Truck Driver/CDL |  | 12 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 864 | 151 | 192 |  | 12 | 12 | 1207 | [16 empty] | 1207 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | [7 empty] | Hammer Attachment | 12 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | [7 empty] | Padding Bucket | 12 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | [7 empty] | Light Tower 6000 Watt | 12 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 156 |  |  | 12 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44134-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-30 | jsa MEETING. Badger slot trenched around anomaly site. Once reached 4ft, excavator removed 3ft of soil and badger continued to slot trench another 4ft. Area was fenced off and work site cleaned up | [7 empty] | Water Pump (3") | 12 | HR | 3INP7 | [11 empty] | 12 |  |  |  | 144 |  |  | 12 | 144 | [16 empty] | 144 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | GARRETT | DICKSON | Foreman |  | 8 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15318 | 4888 Coating | 10 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 800 | 151 | 104 | 0 | 8 | 8 | 1055 | [16 empty] | 1055 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Brushes | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | SHAWN | ROSE | Operator II |  | 8 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 664 | 151 | 104 |  | 8 | 8 | 919 | [16 empty] | 919 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | SHAWN | ROSE | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | SHAWN | ROSE | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | SHAWN | ROSE | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | GAGE | BURKS | Laborer | 5 | 3 |  | 1 | Tool Trailer | 8 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 424 | 151 | 40 |  | 8 | 8 | 615 | [16 empty] | 615 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | GAGE | BURKS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | GAGE | BURKS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | GAGE | BURKS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | ZACHARY | POWDERS | Laborer |  | 8 |  | 1 | 40' Flatbed trailer or equal | 8 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 504 | 151 | 148 |  | 8 | 8 | 803 | [16 empty] | 803 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | ZACHARY | POWDERS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | ZACHARY | POWDERS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | ZACHARY | POWDERS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | COLTON | ROBERTS | Laborer |  | 8 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 504 | 151 | 368 |  | 8 | 8 | 1023 | [16 empty] | 1023 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | MICHEAL | TATUM | Laborer | 6 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 408 | 151 | 724 |  | 8 | 8 | 1283 | [16 empty] | 1283 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | MICHEAL | TATUM | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | MICHEAL | TATUM | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | MICHEAL | TATUM | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | DANIEL | MARTIN | Laborer | 6 | 2 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 408 | 151 | 220 |  | 8 | 8 | 779 | [16 empty] | 779 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | DANIEL | MARTIN | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | DANIEL | MARTIN | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | DANIEL | MARTIN | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | IAIN | ALLRED | Truck Driver/CDL |  | 8 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 576 | 151 | 128 |  | 8 | 8 | 855 | [16 empty] | 855 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Hammer Attachment | 8 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP8 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Water Pump (3") | 8 | HR | 3INP8 | [11 empty] | 12 |  |  |  | 96 |  |  | 8 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44134-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-30 | Had JSA. Began to pump water out of bellhole, there was feet of water in it. Crew began to prep ditch to sandblast. Blasted pipe and NDE assessed pipe. Crew began applying coating. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP8 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44134-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-30 | MOB excavator to site and unloaded | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44134-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-30 | MOB excavator to site and unloaded | SHAWN | ROSE | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44134-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-30 | MOB excavator to site and unloaded | GAGE | BURKS | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44134-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-30 | MOB excavator to site and unloaded | ZACHARY | POWDERS | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44134-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-30 | MOB excavator to site and unloaded | COLTON | ROBERTS | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44134-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-30 | MOB excavator to site and unloaded | MICHEAL | TATUM | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44134-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-30 | MOB excavator to site and unloaded | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | MATTHEW | LINDLEY | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | Sand | 5 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 | 151 | 26 | 0 | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | MATTHEW | LINDLEY | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | 2888 Coating | 6 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | MATTHEW | LINDLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | Brushes | 14 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | MATTHEW | LINDLEY | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | W. MONROE | LINDLEY | Operator II |  | 1 |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 | 151 | 13 |  | 1 | 1 | 247 | [16 empty] | 247 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | W. MONROE | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | W. MONROE | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | W. MONROE | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | LUTHER | LINDLEY | Laborer |  | 1 |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 | 151 | 13 |  | 1 | 1 | 227 | [16 empty] | 227 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | DEMETRIUS | DOBY | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | DEMETRIUS | DOBY | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | DEMETRIUS | DOBY | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | DEMETRIUS | DOBY | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | NICHOLAS | BLANCO | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | NICHOLAS | BLANCO | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | NICHOLAS | BLANCO | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | NICHOLAS | BLANCO | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | DANIEL | MENDOZA | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | DANIEL | MENDOZA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | DANIEL | MENDOZA | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | DANIEL | MENDOZA | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | JESUS | MENDOZA | Laborer |  | 2 |  | 1 | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 2 | HR | REX592 | [7 empty] | 47 | 63 | 0 | 151 | 145 |  | 126 | 151 | 290 |  | 2 | 2 | 567 | [16 empty] | 567 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | JESUS | MENDOZA | Laborer |  | 1 |  |  | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 1 | HR | REX592 | [7 empty] | 47 | 63 | 0 | 151 | 145 |  | 63 |  | 145 |  | 1 | 1 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | JESUS | MENDOZA | Laborer |  | 3 |  |  | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 3 | HR | REX592 | [7 empty] | 47 | 63 | 0 | 151 | 145 |  | 189 |  | 435 |  | 3 | 3 | 624 | [16 empty] | 624 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | JESUS | MENDOZA | Laborer |  | 4 |  |  | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 4 | HR | REX592 | [7 empty] | 47 | 63 | 0 | 151 | 145 |  | 252 |  | 580 |  | 4 | 4 | 832 | [16 empty] | 832 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | TYLER | BIGG | Truck Driver/CDL |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 151 | 32 |  | 2 | 2 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | TYLER | BIGG | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | TYLER | BIGG | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | TYLER | BIGG | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Hammer Attachment | 2 | HR | RHA3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Hammer Attachment | 1 | HR | RHA3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Hammer Attachment | 3 | HR | RHA3 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Hammer Attachment | 4 | HR | RHA3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Padding Bucket | 1 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Padding Bucket | 3 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Padding Bucket | 4 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP3 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP3 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP3 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP3 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29300-44135-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-31 | Had to wait for conditions to improve to go up hill. Waited on NDE to return. Blasted and coated pipe. Cleaned up site. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | RSP3 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44135-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-31 | Cleaned topsoil and moved everything down the hill to demob site | MATTHEW | LINDLEY | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44135-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-31 | Cleaned topsoil and moved everything down the hill to demob site | W.MONROE | LINDLEY | Operator II |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 498 |  | 78 |  | 6 | 6 | 576 | [16 empty] | 576 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44135-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-31 | Cleaned topsoil and moved everything down the hill to demob site | LUTHER | LINDLEY | Laborer |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 |  | 78 |  | 6 | 6 | 456 | [16 empty] | 456 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | RENE | CASAREZ | Foreman |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | RENE | Brushes | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 500 | 151 | 65 | 0 | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | RENE | CASAREZ | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | RENE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | DONALD | TIGUE | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 | 151 | 65 |  | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | DONALD | TIGUE | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | DAVID | LOPEZ | Laborer |  | 5 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 | 151 | 230 |  | 5 | 5 | 696 | [16 empty] | 696 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | DAVID | LOPEZ | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | FERNANDO | GARCIA | Laborer |  | 5 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 | 151 | 452.5 |  | 5 | 5 | 918.5 | [16 empty] | 918.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | FERNANDO | GARCIA | Laborer |  | 5 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 |  | 452.5 |  | 5 | 5 | 767.5 | [16 empty] | 767.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | ADDEY | BENNETT | Laborer |  | 5 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC77892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 315 | 151 | 137.5 |  | 5 | 5 | 603.5 | [16 empty] | 603.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | ADDEY | BENNETT | Laborer |  | 6 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC77892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 378 |  | 137.5 |  | 6 | 5 | 515.5 | [16 empty] | 515.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | MARGIL | GARZA | Laborer |  | 5 |  | 1 | Hammer Attachment | 5 | HR | RHA10141 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 315 | 151 | 0 |  | 5 | 5 | 466 | [16 empty] | 466 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | MARGIL | GARZA | Laborer |  | 5 |  |  | Hammer Attachment | 5 | HR | RHA10141 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 315 |  | 0 |  | 5 | 5 | 315 | [16 empty] | 315 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | JODY | HASTON | Truck Driver/CDL |  | 5 |  | 1 | Padding Bucket | 5 | HR | RPB17093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 360 | 151 | 0 |  | 5 | 5 | 511 | [16 empty] | 511 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | JODY | HASTON | Truck Driver/CDL |  | 5 |  |  | Padding Bucket | 5 | HR | RPB17093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 360 |  | 0 |  | 5 | 5 | 360 | [16 empty] | 360 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | [7 empty] | Tool Trailer | 5 | HR | UTT9 | [11 empty] | 5 |  |  |  | 25 |  |  | 5 | 25 | [16 empty] | 25 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-10630-44135-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-31 | Dried pipe. NED assesed, jeeped pipe, fixed holidays, installed 30ft rockshield. Finished backfilling downhill side and started backfilling uphill side. | [7 empty] | Tool Trailer | 5 | HR | UTT9 | [11 empty] | 5 |  |  |  | 25 |  |  | 5 | 25 | [16 empty] | 25 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [16 empty] | 1541 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | TOME | KIRKLAND | Superintendent |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1512 | 151 | 156 |  | 12 | 12 | 1819 | [16 empty] | 1819 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | JASON | JONES | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | JUANITO | RODRIGUEZ | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | SCOTT | MERRY | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | [7 empty] | Tractor/Semi | 10 | HR | R1371 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | [7 empty] | Lowboy Trailer | 10 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Matches crew 8 | [7 empty] | Kubota UTV | 10 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | JONATHAN | HOLLEY | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | 2888 Coating | 1 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 | 151 | 26 | 0 | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | JONATHAN | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | Brushes | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | RYAN | FARINELLI | Operator II |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 | 151 | 26 |  | 2 | 2 | 343 | [16 empty] | 343 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | RYAN | FARINELLI | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | GREG | MCMILLIAN | Laborer |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 | 151 | 26 |  | 2 | 2 | 303 | [16 empty] | 303 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | GREG | MCMILLIAN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | JERMAINE | EVANS | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | JERMAINE | EVANS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | JOSE | ORTIZ | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | JOSE | ORTIZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | ROBERT | FOSTER | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | ROBERT | FOSTER | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 151 | 32 |  | 2 | 2 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44135-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | JONATHAN | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | 2888 Coating | 1 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | JONATHAN | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | Brushes | 3 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | RYAN | FARINELLI | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | RYAN | FARINELLI | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | GREG | MCMILLIAN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | GREG | MCMILLIAN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | JERMAINE | EVANS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | JERMAINE | EVANS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | JOSE | ORTIZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | JOSE | ORTIZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | ROBERT | FOSTER | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | ROBERT | FOSTER | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-16230-44135-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-31 | Jeeped and repaired coating | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | KYLE | BONNEAU | Foreman |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | KYLE | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 500 | 151 | 65 | 0 | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | KYLE | BONNEAU | Foreman |  | 7 |  |  | Pickup-F150 or F250 or equal | 7 | HR | KYLE | Straw Bales | 10 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 700 |  | 91 | 0 | 7 | 7 | 791 | [16 empty] | 791 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | JESSE | BERTHIAUME | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JESSE | Sand | 10 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 415 | 151 | 65 | 0 | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | JESSE | BERTHIAUME | Operator II |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | JESSE | 2888 Coating | 18 | L |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 498 |  | 78 | 0 | 6 | 6 | 576 | [16 empty] | 576 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | JACOB | CAPITANO | Laborer |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15335 | Silt Fence | 30 | Ft |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 315 | 151 | 65 | 0 | 5 | 5 | 531 | [16 empty] | 531 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | JACOB | CAPITANO | Laborer |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 |  | 78 |  | 6 | 6 | 456 | [16 empty] | 456 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | BROC | CALIGER | Laborer |  | 5 |  | 1 | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 | 151 | 25 |  | 5 | 5 | 491 | [16 empty] | 491 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | BROC | CALIGER | Laborer |  | 6 |  |  | Tool Trailer | 6 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 |  | 30 |  | 6 | 6 | 408 | [16 empty] | 408 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | CODY | GAXIOLA | Laborer |  | 5 |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 | 151 | 92.5 |  | 5 | 5 | 558.5 | [16 empty] | 558.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | CODY | GAXIOLA | Laborer |  | 6 |  |  | 40' Flatbed trailer or equal | 6 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 |  | 111 |  | 6 | 6 | 489 | [16 empty] | 489 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | HEATHER | ENGLE | Laborer |  | 5 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 | 151 | 230 |  | 5 | 5 | 696 | [16 empty] | 696 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | HEATHER | ENGLE | Laborer |  | 6 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 378 |  | 276 |  | 6 | 6 | 654 | [16 empty] | 654 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 | 151 | 80 |  | 5 | 5 | 591 | [16 empty] | 591 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 6 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 |  | 96 |  | 6 | 6 | 528 | [16 empty] | 528 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Hammer Attachment | 5 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Hammer Attachment | 6 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Brush Hog | 5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Brush Hog | 6 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Padding Bucket | 5 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Padding Bucket | 6 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 5 | HR | RSP2 | [11 empty] | 23.5 |  |  |  | 117.5 |  |  | 5 | 117.5 | [16 empty] | 117.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44135-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | Had JSA, pumped water and installed ECD's. Set up tents, blasted and coated 20ft. | [7 empty] | Water Pump (3") | 5 | HR | 3INP | [11 empty] | 12 |  |  |  | 60 |  |  | 5 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | GERALD | SMITH | Foreman |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | GERALD | Sand | 25 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 16 | 0 | 200 | 151 | 32 | 0 | 2 | 2 | 383 | [16 empty] | 383 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | GERALD | SMITH | Foreman |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | GERALD | 2888 Coating | 30 | L |  |  |  |  | 74 | 100 | 0 | 151 | 16 | 0 | 300 |  | 48 | 0 | 3 | 3 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | GERALD | SMITH | Foreman |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | GERALD | Brushes | 15 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 16 | 0 | 100 |  | 16 | 0 | 1 | 1 | 116 | [16 empty] | 116 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | GERALD | SMITH | Foreman |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 400 |  | 64 |  | 4 | 4 | 464 | [16 empty] | 464 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | MICHAEL | RATLIFF | Operator II |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 166 | 151 | 32 |  | 2 | 2 | 349 | [16 empty] | 349 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | MICHAEL | RATLIFF | Operator II |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 249 |  | 48 |  | 3 | 3 | 297 | [16 empty] | 297 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | MICHAEL | RATLIFF | Operator II |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 83 |  | 16 |  | 1 | 1 | 99 | [16 empty] | 99 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | MICHAEL | RATLIFF | Operator II |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 332 |  | 64 |  | 4 | 4 | 396 | [16 empty] | 396 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | OJ | SEALS | Laborer |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 | 151 | 32 |  | 2 | 2 | 309 | [16 empty] | 309 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | OJ | SEALS | Laborer |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 189 |  | 48 |  | 3 | 3 | 237 | [16 empty] | 237 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | OJ | SEALS | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | OJ | SEALS | Laborer |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 252 |  | 64 |  | 4 | 4 | 316 | [16 empty] | 316 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | RICHARD | ADKINS | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | RICHARD | ADKINS | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | RICHARD | ADKINS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | RICHARD | ADKINS | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | BARRETT | WISE | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | BARRETT | WISE | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | BARRETT | WISE | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | BARRETT | WISE | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | DAVID | RATLIFF | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | DAVID | RATLIFF | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | DAVID | RATLIFF | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | DAVID | RATLIFF | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | STEVE | CLARK | Truck Driver/CDL |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 151 | 32 |  | 2 | 2 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | STEVE | CLARK | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | STEVE | CLARK | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | STEVE | CLARK | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Hammer Attachment | 2 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Hammer Attachment | 3 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Hammer Attachment | 1 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Hammer Attachment | 4 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Padding Bucket | 2 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Padding Bucket | 3 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Padding Bucket | 4 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Water Pump ( up to 2") | 2 | HR | 2INP4 | [11 empty] | 6 |  |  |  | 12 |  |  | 2 | 12 | [16 empty] | 12 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Water Pump ( up to 2") | 2 | HR | 2INP4B | [11 empty] | 6 |  |  |  | 12 |  |  | 2 | 12 | [16 empty] | 12 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44135-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-31 | Pumped water out of hole. Cleaned out and dried with excavator. Put plastic in hole and sandblasted about 1/2 length. NDE assessed. Recoated that length that was blasted | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | RSPM923 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | CALEB | HOLTON | Foreman |  | 8 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | CALEB |  |  |  | State Line Service | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 800 | 151 | 52 |  | 8 | 4 | 1003 | State Line Service | [15 empty] | 1003 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | CALEB | HOLTON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 65 |  | 3 | 5 | 365 | [16 empty] | 365 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | THOMAS | FRANKLIN | Operator II |  | 8 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 664 | 151 | 52 |  | 8 | 4 | 867 | [16 empty] | 867 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | THOMAS | FRANKLIN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 52 |  | 2 | 4 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | MICHAEL | ANISZEWSKI | Laborer |  | 8 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 504 | 151 | 52 |  | 8 | 4 | 707 | [16 empty] | 707 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | MICHAEL | ANISZEWSKI | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 65 |  | 3 | 5 | 254 | [16 empty] | 254 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | BOLDBAUTOR | ZORIGT | Laborer |  | 8 |  | 1 | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 504 | 151 | 20 |  | 8 | 4 | 675 | [16 empty] | 675 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | BOLDBAUTOR | ZORIGT | Laborer |  | 2 |  |  | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 20 |  | 2 | 4 | 146 | [16 empty] | 146 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | JORDAN | WIGGINS | Laborer |  | 8 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 504 | 151 | 74 |  | 8 | 4 | 729 | [16 empty] | 729 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | JORDAN | WIGGINS | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 74 |  | 3 | 4 | 263 | [16 empty] | 263 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | DAVID | KNOTTS | Laborer |  | 8 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 504 | 151 | 184 |  | 8 | 4 | 839 | [16 empty] | 839 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | DAVID | KNOTTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 184 |  | 2 | 4 | 310 | [16 empty] | 310 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | TANNER | BRITT | Laborer |  | 8 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 504 | 151 | 362 |  | 8 | 4 | 1017 | [16 empty] | 1017 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | TANNER | BRITT | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 362 |  | 2 | 4 | 488 | [16 empty] | 488 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | ALDO | RENYA | Truck Driver/CDL |  | 8 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 576 | 151 | 64 |  | 8 | 4 | 791 | [16 empty] | 791 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | ALDO | RENYA | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 64 |  | 2 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Sleeve | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | [7 empty] | Padding Bucket | 4 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44135-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-31 | Statred welding on sleeves. Took (8) hours on welding. Sandblasted coating off sleeves | [7 empty] | Padding Bucket | 4 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | BARKLEY | BROWN | Foreman |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 500 | 151 | 65 | 0 | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Sand | 3 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | 4888 Coating | 9 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | BARKLEY | BROWN | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Brushes | 21 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | JOSHUA | MENDARIES | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | WAYLON | GREEN | Laborer |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 | 151 | 65 |  | 5 | 5 | 531 | [16 empty] | 531 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | WAYLON | GREEN | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | JOSE | VALLES | Laborer |  | 4 |  | 1 | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 | 151 | 20 |  | 4 | 4 | 423 | [16 empty] | 423 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | JOSE | VALLES | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | REYMUNDO | REYES | Laborer |  | 10 |  | 1 | Water Pump (3") | 0 | HR | 3INP6 | [7 empty] | 47 | 63 | 0 | 151 | 12 |  | 630 | 151 | 0 |  | 10 | 0 | 781 | [16 empty] | 781 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | MARCELO | GOMEZ | Laborer |  | 4 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 | 151 | 74 |  | 4 | 4 | 477 | [16 empty] | 477 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | MARCELO | GOMEZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | MARCELO | GOMEZ | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | MARCELO | GOMEZ | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | ANTHONY | MORENO | Laborer |  | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 | 151 | 184 |  | 4 | 4 | 587 | [16 empty] | 587 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | ANTHONY | MORENO | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | ANTHONY | MORENO | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | EFREM | LEE | Truck Driver/CDL |  | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373A | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 288 | 151 | 362 |  | 4 | 4 | 801 | [16 empty] | 801 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373A | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 144 |  | 181 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | EFREM | LEE | Truck Driver/CDL |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373A | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 72 |  | 90.5 |  | 1 | 1 | 162.5 | [16 empty] | 162.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | EFREM | LEE | Truck Driver/CDL |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373A | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 216 |  | 271.5 |  | 3 | 3 | 487.5 | [16 empty] | 487.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Brush Hog | 3 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44135-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-31 | Fixed access road in and blasted pipe. NDE assesed pipe. Coated pipe and cleaned up site. Fixed access road going out. Still very muddy due to being in flood zone | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | URIEL | VALENCIA | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | R15349 |  |  |  | BADGER1 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 600 | 151 | 78 |  | 6 | 6 | 829 | BADGER1 | [15 empty] | 829 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | URIEL | VALENCIA | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15349 |  |  |  | BADGER2 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | BADGER2 | [15 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | HECTOR | VALDEZ NEVAREZ | Operator II |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 498 | 151 | 78 |  | 6 | 6 | 727 | [16 empty] | 727 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | HECTOR | VALDEZ NEVAREZ | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | ASTOLFO | FLORES | Laborer |  | 6 |  | 1 | Tool Trailer | 6 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 | 151 | 30 |  | 6 | 6 | 559 | [16 empty] | 559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | ASTOLFO | FLORES | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | IVAN | MADRID | Laborer |  | 6 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 | 151 | 111 |  | 6 | 6 | 640 | [16 empty] | 640 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | IVAN | MADRID | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | ROBERTO | RODRIGUEZ | Laborer |  | 6 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 378 | 151 | 276 |  | 6 | 6 | 805 | [16 empty] | 805 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | ROBERTO | RODRIGUEZ | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | JOEL | VALDEZ NEVAREZ | Laborer |  | 6 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 378 | 151 | 543 |  | 6 | 6 | 1072 | [16 empty] | 1072 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | JOEL | VALDEZ NEVAREZ | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | HECTOR | QUINTANA VALDEZ | Laborer |  | 6 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 378 | 151 | 165 |  | 6 | 6 | 694 | [16 empty] | 694 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | HECTOR | QUINTANA VALDEZ | Laborer |  | 4 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 252 |  | 110 |  | 4 | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 | 151 | 96 |  | 6 | 6 | 679 | [16 empty] | 679 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | [7 empty] | Hammer Attachment | 6 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | [7 empty] | Padding Bucket | 6 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44135-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-31 | JSA meeting. Hydrovac continuedf with slot trenching 4ft. Excavator removed 3ft. Once got to a depth of 6ft, slot trench began to cave in. Work was stopped being that it was unsafe for work to continue. Waiting on Enbridge to decide on plan for excavation. | [7 empty] | Padding Bucket | 4 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | GARRETT | DICKSON | Foreman |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 | 151 | 39 |  | 3 | 3 | 490 | [16 empty] | 490 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | GARRETT | DICKSON | Foreman |  | 10 |  |  | Pickup-F150 or F250 or equal | 10 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 |  | 130 |  | 10 | 10 | 1130 | [16 empty] | 1130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | SHAWN | ROSE | Operator II |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 | 151 | 39 |  | 3 | 3 | 439 | [16 empty] | 439 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | SHAWN | ROSE | Operator II |  | 9 |  |  | Pickup-F150 or F250 or equal | 9 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 747 |  | 117 |  | 9 | 9 | 864 | [16 empty] | 864 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | GAGE | BURKS | Laborer |  | 3 |  | 1 | Tool Trailer | 3 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 | 151 | 15 |  | 3 | 3 | 355 | [16 empty] | 355 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | GAGE | BURKS | Laborer |  | 9 |  |  | Tool Trailer | 9 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 567 |  | 45 |  | 9 | 9 | 612 | [16 empty] | 612 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | ZACHARY | POWDERS | Laborer |  | 3 |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 | 151 | 55.5 |  | 3 | 3 | 395.5 | [16 empty] | 395.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | ZACHARY | POWDERS | Laborer |  | 9 |  |  | 40' Flatbed trailer or equal | 9 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 567 |  | 166.5 |  | 9 | 9 | 733.5 | [16 empty] | 733.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | COLTON | ROBERTS | Laborer |  | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 | 151 | 138 |  | 3 | 3 | 478 | [16 empty] | 478 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | COLTON | ROBERTS | Laborer |  | 9 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 9 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 567 |  | 414 |  | 9 | 9 | 981 | [16 empty] | 981 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | MICHEAL | TATUM | Laborer |  | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 | 151 | 271.5 |  | 3 | 3 | 611.5 | [16 empty] | 611.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | MICHEAL | TATUM | Laborer |  | 9 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 9 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 567 |  | 814.5 |  | 9 | 9 | 1381.5 | [16 empty] | 1381.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | DANIEL | MARTIN | Laborer |  | 3 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 189 | 151 | 82.5 |  | 3 | 3 | 422.5 | [16 empty] | 422.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | DANIEL | MARTIN | Laborer |  | 9 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 9 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 567 |  | 247.5 |  | 9 | 9 | 814.5 | [16 empty] | 814.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | IAIN | ALLRED | Truck Driver/CDL |  | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 | 151 | 48 |  | 3 | 3 | 415 | [16 empty] | 415 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | IAIN | ALLRED | Truck Driver/CDL |  | 9 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 9 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 648 |  | 144 |  | 9 | 9 | 792 | [16 empty] | 792 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | [7 empty] | Hammer Attachment | 3 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-29250-44135-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-31 | Had JSA meeting. Crew waited on NDE to arrive. NDE assessed pipe. Crew began to backfill and clean up site. | [7 empty] | Hammer Attachment | 9 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 9 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | JASON | JONES | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | [7 empty] | Tractor/Semi | 12 | HR | 1376 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | [7 empty] | Tractor/Semi | 10 | HR | R1371 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Matches crew 2 | [7 empty] | Lowboy Trailer | 10 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | MATTHEW | LINDEY | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | MATTHEW | LINDEY | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | MATTHEW | LINDEY | Foreman | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 448 |  | 65 |  | 5 | 5 | 513 | [16 empty] | 513 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | W. MONROE | LINDEY | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | LUTHER | LINDEY | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | DEMETRIUS | DOBY | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | DEMETRIUS | DOBY | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | DEMETRIUS | DOBY | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | NICHOLAS | BLANCO | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | NICHOLAS | BLANCO | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | NICHOLAS | BLANCO | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | DANIEL | MENDOZA | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | DANIEL | MENDOZA | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | DANIEL | MENDOZA | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 230 |  | 5 | 5 | 497 | [16 empty] | 497 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | JESUS | MENDOZA | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | JESUS | MENDOZA | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | JESUS | MENDOZA | Laborer | 3 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX3802 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 267 |  | 452.5 |  | 5 | 5 | 719.5 | [16 empty] | 719.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | TYLER | BIGG | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | TYLER | BIGG | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | TYLER | BIGG | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Hammer Attachment | 4 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Hammer Attachment | 1 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Hammer Attachment | 5 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Padding Bucket | 4 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Padding Bucket | 1 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Padding Bucket | 5 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Pipe Jeep (includes spring) | 1 | HR | PJP3 | [11 empty] | 7 |  |  |  | 7 |  |  | 1 | 7 | [16 empty] | 7 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44137-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-02 | MOB cat 315 and hammer to site. Broke down large rocks to safely backfill. Jeeped pipe and patched jeeps. Took measurements at 0547 and 1553 for quanilites of seed and straw. Padded pipe and began backfilling | [7 empty] | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 10 | HR | REX592 | [11 empty] | 145 |  |  |  | 1450 |  |  | 10 | 1450 | [16 empty] | 1450 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | RENE | CASAREZ | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | RENE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 444 | 151 | 78 |  | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | RENE | CASAREZ | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RENE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | DONALD | TIGUE | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DONALDT | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | DAVID | LOPEZ | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RC3860 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | FERNANDO | GARCIA | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT9 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | ADDEY | BENNETT | Laborer | 6 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC77892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 282 | 151 | 165 |  | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | ADDEY | BENNETT | Laborer | 2 | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC77892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 157 |  | 82.5 |  | 3 | 3 | 239.5 | [16 empty] | 239.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | MARGIL | GARZA | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | JODY | HASTON | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF5509 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | [16 empty] | 568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | JODY | HASTON | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF5509 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX10278 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | [7 empty] | Hammer Attachment | 10 | HR | RHA10141 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44137-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | Cleaned up site and start demob of equipment | [7 empty] | Padding Bucket | 10 | HR | RPB17093 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44137-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-02 | Started MOB of equipment. Inspected dig site | RENE | CASAREZ | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RENE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44137-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-02 | Started MOB of equipment. Inspected dig site | ADDEY | BENNETT | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44137-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-02 | Started MOB of equipment. Inspected dig site | JODY | HASTON | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RC23860 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | JONATHAN | HOLLEY | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | JONATHAN | 2888 Coating | 1 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | RYAN | FARINELLI | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | RYAN | Brushes | 3 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 184.5 | 151 | 39 | 0 | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | GREG | MCMILLIAN | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 | 151 | 39 |  | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | JERMAINE | EVANS | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | JOSE | ORTIZ | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | ROBERT | FOSTER | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 138 |  | 3 | 3 | 430 | [16 empty] | 430 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | BRIAN | RANDLE | Truck Driver/CDL | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 | 151 | 48 |  | 3 | 3 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | [7 empty] | Hammer Attachment | 3 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | [7 empty] | Padding Bucket | 3 | HR | RBP1 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-14960-44137-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-02 | Jeeped and repaired 1546 to be ready for rocksheild. | [7 empty] | Pipe Jeep (includes spring) | 3 | HR | PJP1 | [11 empty] | 7 |  |  |  | 21 |  |  | 3 | 21 | [16 empty] | 21 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | JONATHAN | HOLLEY | Foreman | 5 | 2 |  |  | Pickup-F150 or F250 or equal | 7 | HR | JONATHAN | Mats | 16 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 570 |  | 91 | 0 | 7 | 7 | 661 | [16 empty] | 661 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | RYAN | FARINELLI | Operator II | 5 | 2 |  |  | Pickup-F150 or F250 or equal | 7 | HR | RYAN | Filter Bag | 1 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 473.5 |  | 91 | 0 | 7 | 7 | 564.5 | [16 empty] | 564.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | GREG | MCMILLIAN | Laborer | 5 | 2 |  |  | Pickup-F150 or F250 or equal | 7 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 361 |  | 91 |  | 7 | 7 | 452 | [16 empty] | 452 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | JERMAINE | EVANS | Laborer | 5 | 2 |  |  | Tool Trailer | 7 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 361 |  | 35 |  | 7 | 7 | 396 | [16 empty] | 396 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | JOSE | ORTIZ | Laborer | 5 | 2 |  |  | 40' Flatbed trailer or equal | 7 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 361 |  | 129.5 |  | 7 | 7 | 490.5 | [16 empty] | 490.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | ROBERT | FOSTER | Laborer | 5 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 361 |  | 322 |  | 7 | 7 | 683 | [16 empty] | 683 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | BRIAN | RANDLE | Truck Driver/CDL | 5 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 411.5 |  | 112 |  | 7 | 7 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 633.5 |  |  | 7 | 633.5 | [16 empty] | 633.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 192.5 |  |  | 7 | 192.5 | [16 empty] | 192.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | [7 empty] | Hammer Attachment | 7 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | [7 empty] | Padding Bucket | 7 | HR | RBP1 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | [7 empty] | Water Pump (3") | 7 | HR | 3INP1 | [11 empty] | 12 |  |  |  | 84 |  |  | 7 | 84 | [16 empty] | 84 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-15400-44137-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-02 | Built mat bridge to access 1547. Pumped water | [47 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | GARRETT | DICKSON | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | SHAWN | ROSE | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | GAGE | BURKS | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | GAGE | BURKS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | GAGE | BURKS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | ZACHARY | POWDERS | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | ZACHARY | POWDERS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | ZACHARY | POWDERS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | COLTON | ROBERTS | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | COLTON | ROBERTS | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | COLTON | ROBERTS | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | MICHEAL | TATUM | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | MICHEAL | TATUM | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | MICHEAL | TATUM | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | DANIEL | MARTIN | Laborer | 4 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 188 | 151 | 110 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | DANIEL | MARTIN | Laborer | 1 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 |  | 27.5 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | DANIEL | MARTIN | Laborer | 1 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 |  | 27.5 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | IAIN | ALLRED | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29250-44137-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-02 | JSA meeting. Finished backfill. Cleaned up site completely. Demob to 1475 | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-33820-44137-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-02 | Unloaded equipment. Began to pull trench box and break it down for off rent. Crew cleaned up site and prepped for backfill. | GARRETT | DICKSON | Foreman | 2 | 5 |  |  | Pickup-F150 or F250 or equal | 7 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 648 |  | 91 |  | 7 | 7 | 739 | [16 empty] | 739 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-33820-44137-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-02 | Unloaded equipment. Began to pull trench box and break it down for off rent. Crew cleaned up site and prepped for backfill. | SHAWN | ROSE | Operator II | 2 | 4 |  |  | Pickup-F150 or F250 or equal | 6 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 455 |  | 78 |  | 6 | 6 | 533 | [16 empty] | 533 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-33820-44137-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-02 | Unloaded equipment. Began to pull trench box and break it down for off rent. Crew cleaned up site and prepped for backfill. | GAGE | BURKS | Laborer | 2 | 4 |  |  | Tool Trailer | 6 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 346 |  | 30 |  | 6 | 6 | 376 | [16 empty] | 376 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-33820-44137-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-02 | Unloaded equipment. Began to pull trench box and break it down for off rent. Crew cleaned up site and prepped for backfill. | ZACHARY | POWDERS | Laborer | 2 | 4 |  |  | 40' Flatbed trailer or equal | 6 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 346 |  | 111 |  | 6 | 6 | 457 | [16 empty] | 457 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-33820-44137-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-02 | Unloaded equipment. Began to pull trench box and break it down for off rent. Crew cleaned up site and prepped for backfill. | COLTON | ROBERTS | Laborer | 2 | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 346 |  | 276 |  | 6 | 6 | 622 | [16 empty] | 622 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-33820-44137-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-02 | Unloaded equipment. Began to pull trench box and break it down for off rent. Crew cleaned up site and prepped for backfill. | MICHEAL | TATUM | Laborer | 2 | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 346 |  | 543 |  | 6 | 6 | 889 | [16 empty] | 889 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-33820-44137-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-02 | Unloaded equipment. Began to pull trench box and break it down for off rent. Crew cleaned up site and prepped for backfill. | DANIEL | MARTIN | Laborer | 2 | 4 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 346 |  | 165 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-33820-44137-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-02 | Unloaded equipment. Began to pull trench box and break it down for off rent. Crew cleaned up site and prepped for backfill. | IAIN | ALLRED | Truck Driver/CDL | 2 | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 395 |  | 96 |  | 6 | 6 | 491 | [16 empty] | 491 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-33820-44137-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-02 | Unloaded equipment. Began to pull trench box and break it down for off rent. Crew cleaned up site and prepped for backfill. | [7 empty] | Hammer Attachment | 6 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | URIEL | VALENCIA | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | R15349 |  |  |  | BADGER1 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | BADGER1 | [15 empty] | 1186 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | HECTOR | VALDEZ NEVAREZ | Operator II | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | HECTOR |  |  |  | WATER TRUCK | 0 | 0 | 0 | 61.5 | 83 | 0 | 151 | 13 |  | 741 | 151 | 143 |  | 11 | 11 | 1035 | WATER TRUCK | [15 empty] | 1035 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | ALEJANDRO | CRUZ CONTRERAS | Laborer | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 565 | 151 | 143 |  | 11 | 11 | 859 | [16 empty] | 859 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | ASTOLFO | FLORES | Laborer | 8 | 3 |  | 1 | Tool Trailer | 11 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 565 | 151 | 55 |  | 11 | 11 | 771 | [16 empty] | 771 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | IVAN | MADRID | Laborer | 8 | 3 |  | 1 | 40' Flatbed trailer or equal | 11 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 565 | 151 | 203.5 |  | 11 | 11 | 919.5 | [16 empty] | 919.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | ROBERTO | RODRIGUEZ | Laborer | 8 | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 11 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 565 | 151 | 506 |  | 11 | 11 | 1222 | [16 empty] | 1222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | JOEL | VALDEZ NEVAREZ | Laborer | 8 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 11 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 565 | 151 | 995.5 |  | 11 | 11 | 1711.5 | [16 empty] | 1711.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | HECTOR | QUINTANA VALDEZ | Laborer | 8 | 3 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 11 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 565 | 151 | 302.5 |  | 11 | 11 | 1018.5 | [16 empty] | 1018.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 11 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 644 | 151 | 176 |  | 11 | 11 | 971 | [16 empty] | 971 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | [7 empty] | Hammer Attachment | 11 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44137-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-02 | Began walking with inspection and Enbridge to discuss continuing excavation. Decided to slope ditch back to make safer for hydrovac. JSA meeting. Hydrovac began to slot trench. Waiting for hydrovac so we can slope ditch. Area was secured fot the night. Work area cleaned up | [7 empty] | Padding Bucket | 11 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | CALEB | HOLTON | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | CALEB | Sand | 5 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 444 | 151 | 78 | 0 | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | CALEB | HOLTON | Foreman | 2 | 5 |  |  | Pickup-F150 or F250 or equal | 7 | HR | CALEB | 2888 Coating | 9 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 648 |  | 91 | 0 | 7 | 7 | 739 | [16 empty] | 739 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | THOMAS | FRANKLIN | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | THOMASF | Brushes | 15 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 369 | 151 | 78 | 0 | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | THOMAS | FRANKLIN | Operator II | 2 | 4 |  |  | Pickup-F150 or F250 or equal | 6 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 455 |  | 78 |  | 6 | 6 | 533 | [16 empty] | 533 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | MICHAEL | ANISZEWSKI | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | MICHAEL | ANISZEWSKI | Laborer | 2 | 5 |  |  | Pickup-F150 or F250 or equal | 7 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 409 |  | 91 |  | 7 | 7 | 500 | [16 empty] | 500 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | BOLDBAUTOR | ZORIGT | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | BOLDBAUTOR | ZORIGT | Laborer | 2 | 4 |  |  | Tool Trailer | 6 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 346 |  | 30 |  | 6 | 6 | 376 | [16 empty] | 376 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | JORDAN | WIGGINS | Laborer | 6 |  |  | 1 | 40' Flatbed trailer or equal | 6 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 282 | 151 | 111 |  | 6 | 6 | 544 | [16 empty] | 544 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | JORDAN | WIGGINS | Laborer | 2 | 5 |  |  | 40' Flatbed trailer or equal | 7 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 409 |  | 129.5 |  | 7 | 7 | 538.5 | [16 empty] | 538.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | DAVID | KNOTTS | Laborer | 6 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 282 | 151 | 276 |  | 6 | 6 | 709 | [16 empty] | 709 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | DAVID | KNOTTS | Laborer | 2 | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 346 |  | 276 |  | 6 | 6 | 622 | [16 empty] | 622 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | TANNER | BRITT | Laborer | 6 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 282 | 151 | 543 |  | 6 | 6 | 976 | [16 empty] | 976 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | TANNER | BRITT | Laborer | 2 | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 346 |  | 543 |  | 6 | 6 | 889 | [16 empty] | 889 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | ALDO | RENYA | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | [16 empty] | 568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | ALDO | RENYA | Truck Driver/CDL | 2 | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 395 |  | 96 |  | 6 | 6 | 491 | [16 empty] | 491 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Hammer Attachment | 6 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Hammer Attachment | 6 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Padding Bucket | 6 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Padding Bucket | 6 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 6 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 147 |  |  | 6 | 147 | [16 empty] | 147 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 6 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 147 |  |  | 6 | 147 | [16 empty] | 147 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Pipe Jeep (includes spring) | 1 | HR | PJP5 | [11 empty] | 7 |  |  |  | 7 |  |  | 1 | 7 | [16 empty] | 7 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Pickup-F150 or F250 or equal | 6 | HR | RCT5164 | [11 empty] | 13 |  |  |  | 78 |  |  | 6 | 78 | [16 empty] | 78 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-35680-44137-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-02 | Reblasted pipe and sleeve. Began coating on 20ft section. Jeeped pipe when dry | [7 empty] | Pickup-F150 or F250 or equal | 7 | HR | RCT5164 | [11 empty] | 13 |  |  |  | 91 |  |  | 7 | 91 | [16 empty] | 91 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | GERALD | SMITH | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | GERALD | Sand | 20 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | GERALD | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | GERALD | 2888 Coating | 25 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | GERALD | SMITH | Foreman | 3 | 3 |  |  | Pickup-F150 or F250 or equal | 6 | HR | GERALD | Brushes | 15 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 522 |  | 78 | 0 | 6 | 6 | 600 | [16 empty] | 600 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | MICHAEL | RATLIFF | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | MICHAEL | RATLIFF | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | MICHAEL | RATLIFF | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | OJ | SEALS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | OJ | SEALS | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | RICHARD | ADKINS | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | RICHARD | ADKINS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | RICHARD | ADKINS | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | BARRETT | WISE | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | BARRETT | WISE | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | BARRETT | WISE | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | DAVID | RATLIFF | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | DAVID | RATLIFF | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | DAVID | RATLIFF | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 230 |  | 5 | 5 | 497 | [16 empty] | 497 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | STEVE | CLARK | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | STEVE | CLARK | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | STEVE | CLARK | Truck Driver/CDL | 2 | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 395 |  | 96 |  | 6 | 6 | 491 | [16 empty] | 491 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Hammer Attachment | 4 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Hammer Attachment | 5 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Padding Bucket | 4 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Padding Bucket | 5 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51610-44137-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-02 | Finished sandblasting pipe. NDE assessed. Finished recoat on pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 4 | HR | RSP4 | [11 empty] | 23.5 |  |  |  | 94 |  |  | 4 | 94 | [16 empty] | 94 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | BARKLEY | BROWN | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | Filer Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Mats | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | BARKLEY | BROWN | Foreman | 3 | 3 |  |  | Pickup-F150 or F250 or equal | 6 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 522 |  | 78 |  | 6 | 6 | 600 | [16 empty] | 600 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | JOSHUA | MENDARIES | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | JOSHUA | MENDARIES | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | JOSHUA | MENDARIES | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | WAYLON | GREEN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | WAYLON | GREEN | Laborer | 3 | 3 |  |  | Pickup-F150 or F250 or equal | 6 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 330 |  | 78 |  | 6 | 6 | 408 | [16 empty] | 408 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | JOSE | VALLES | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | JOSE | VALLES | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | REYMUNDO | REYES | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | REYMUNDO | REYES | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | REYMUNDO | REYES | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | MARCELO | GOMEZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | MARCELO | GOMEZ | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 230 |  | 5 | 5 | 497 | [16 empty] | 497 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | ANTHONY | MORENO | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | ANTHONY | MORENO | Laborer | 3 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 267 |  | 452.5 |  | 5 | 5 | 719.5 | [16 empty] | 719.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | EFREM | LEE | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | EFREM | LEE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | EFREM | LEE | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Hammer Attachment | 5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Padding Bucket | 5 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Brush Hog | 5 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Pipe Jeep (includes spring) | 1 | HR | PJP6 | [11 empty] | 7 |  |  |  | 7 |  |  | 1 | 7 | [16 empty] | 7 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-51460-44137-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-02 | Pumped water. Removed all skids and plyboard out of bellhole. Cleaned site. Jeeped pipe, backfilled pipe and started cleanup | [7 empty] | Water Pump (3") | 4 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 48 |  |  | 4 | 48 | [16 empty] | 48 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | KYLE | BONNEAU | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | KYLE | Sand | 15 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 444 | 151 | 78 | 0 | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | 2888 Coating | 24 | L |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 658 | 151 | 130 | 0 | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | Brushes | 48 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 502 | 151 | 130 | 0 | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | CODY | GAXIOLA | Laborer | 6 |  |  | 1 | Lowboy Trailer | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 282 | 151 | 185 |  | 6 | 10 | 618 | [16 empty] | 618 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | HEATHER | ENGLE | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | [7 empty] | Hammer Attachment | 10 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | [7 empty] | Padding Bucket | 10 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | [7 empty] | Water Pump (3") | 10 | HR | 3INP2 | [11 empty] | 12 |  |  |  | 120 |  |  | 10 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP2 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | [7 empty] | Pipe Jeep (includes spring) | 2 | HR | PJP2 | [11 empty] | 7 |  |  |  | 14 |  |  | 2 | 14 | [16 empty] | 14 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44137-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | Had JSA meeting. Pumped water, blasted and coated 24ft. Repaired jeeps on 20ft section. Total dig covered 44ft. | [47 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44137-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-02 | Firewatched for NDE while they ground the pipe | KYLE | BONNEAU | Foreman | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 448 |  | 65 |  | 5 | 5 | 513 | [16 empty] | 513 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44137-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-02 | Firewatched for NDE while they ground the pipe | CODY | GAXIOLA | Laborer | 2 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 220 |  |  |  | 4 |  | 220 | [16 empty] | 220 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 16 |  | 1000 | 151 | 160 |  | 10 | 10 | 1311 | [16 empty] | 1311 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 16 |  | 1252 | 151 | 192 |  | 12 | 12 | 1595 | [16 empty] | 1595 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 16 |  | 1050 | 151 | 160 |  | 10 | 10 | 1361 | [16 empty] | 1361 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | JASON | JONES | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 792 | 151 | 160 |  | 10 | 10 | 1103 | [16 empty] | 1103 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 792 | 151 | 160 |  | 10 | 10 | 1103 | [16 empty] | 1103 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 658 | 151 | 160 |  | 10 | 10 | 969 | [16 empty] | 969 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | [7 empty] | Tractor/Semi | 10 | HR | R1371 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Matches crew 8 | [7 empty] | Lowboy Trailer | 10 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44138-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-03 | Sand blasted and coated | KYLE | BONNEAU | Foreman | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | KYLE | Sand | 9 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 174 |  | 26 | 0 | 2 | 2 | 200 | [16 empty] | 200 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28110-44138-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-03 | Sand blasted and coated | KYLE | BONNEAU | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | KYLE | 2888 Coating | 10 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44138-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-03 | Sand blasted and coated | JACOB | CAPITANO | Laborer | 2 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8545 | Brushes | 24 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 27.5 | 0 | 94 |  | 55 | 0 | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28110-44138-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-03 | Sand blasted and coated | JACOB | CAPITANO | Laborer |  | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8545 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 126 |  | 55 |  | 2 | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44138-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-03 | Sand blasted and coated | BROC | CALIGER | Laborer | 2 |  |  |  | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP2 | [7 empty] | 47 | 63 | 0 | 151 | 23.5 |  | 94 |  | 47 |  | 2 | 2 | 141 | [16 empty] | 141 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28110-44138-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-03 | Sand blasted and coated | BROC | CALIGER | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44138-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-03 | Sand blasted and coated | CODY | GAXIOLA | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28110-44138-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-03 | Sand blasted and coated | CODY | GAXIOLA | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | KYLE | BONNEAU | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | KYLE | 2888 Coating | 2 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | KYLE | BONNEAU | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | KYLE | Brushes | 6 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 52 | 0 | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | JESSE | BERTHIAUME | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JESSE | Sand | 30 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 369 | 151 | 78 | 0 | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | JESSE | BERTHIAUME | Operator II | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 289 |  | 52 |  | 4 | 4 | 341 | [16 empty] | 341 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | JACOB | CAPITANO | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | BROC | CALIGER | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | CODY | GAXIOLA | Laborer | 6 |  |  | 1 | Tool Trailer | 4 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 20 |  | 6 | 4 | 453 | [16 empty] | 453 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | HEATHER | ENGLE | Laborer | 6 |  |  | 1 | Pipe Jeep (includes spring) | 3 | HR | PJP2 | [7 empty] | 47 | 63 | 0 | 151 | 7 |  | 282 | 151 | 21 |  | 6 | 3 | 454 | [16 empty] | 454 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | HEATHER | ENGLE | Laborer | 2 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 220 |  |  |  | 4 |  | 220 | [16 empty] | 220 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | [16 empty] | 568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 2 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 251 |  | 64 |  | 4 | 4 | 315 | [16 empty] | 315 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | 40' Flatbed trailer or equal | 6 | HR | GNT0705 | [11 empty] | 18.5 |  |  |  | 111 |  |  | 6 | 111 | [16 empty] | 111 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | 40' Flatbed trailer or equal | 4 | HR | GNT0705 | [11 empty] | 18.5 |  |  |  | 74 |  |  | 4 | 74 | [16 empty] | 74 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9350 | [11 empty] | 46 |  |  |  | 276 |  |  | 6 | 276 | [16 empty] | 276 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9350 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | [16 empty] | 184 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Hammer Attachment | 6 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Hammer Attachment | 4 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Padding Bucket | 6 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Padding Bucket | 4 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Brush Hog | 6 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Brush Hog | 4 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-28570-44138-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | Had JSA meeting. Pumped water, jeeped pipe repaired coating, made a pile of padding material. Final jeeped after coating dried. Installed sandbag pillars to support pipe. Began backfill | [7 empty] | Water Pump (3") | 6 | HR | 3INP2 | [11 empty] | 12 |  |  |  | 72 |  |  | 6 | 72 | [16 empty] | 72 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 19120 | Sand | 4 | Bag |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 | 151 | 26 | 0 | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | 2888 Coating | 6 | L |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 |  | 26 | 0 | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RCT5164 | Brushes | 7 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 | 151 | 26 | 0 | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | JORDAN | WIGGINS | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | JORDAN | WIGGINS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | TANNER | BRITT | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | TANNER | BRITT | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | ALDO | RENYA | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | ALDO | RENYA | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44138-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP5 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | Sand | 3 | Bag |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 |  | 26 | 0 | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | MICHAEL | ANISZEWSKI | Laborer | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19120 | 2888 Coating | 5 | L |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 157 |  | 39 | 0 | 3 | 3 | 196 | [16 empty] | 196 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RCT5164 | Brushes | 7 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 |  | 26 | 0 | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 39 |  | 2 | 3 | 133 | [16 empty] | 133 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | JORDAN | WIGGINS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | JORDAN | WIGGINS | Laborer | 2 | 1 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 157 |  | 10 |  | 3 | 2 | 167 | [16 empty] | 167 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | TANNER | BRITT | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | TANNER | BRITT | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | ALDO | RENYA | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | ALDO | RENYA | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44138-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP5 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | Sand | 3 | Bag |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 126 |  | 26 | 0 | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | 2888 Coating | 5 | L |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 126 |  | 26 | 0 | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | BOLDBAUTOR | ZORIGT | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RCT5164 | Brushes | 7 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 126 |  | 26 | 0 | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | BOLDBAUTOR | ZORIGT | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | JORDAN | WIGGINS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | JORDAN | WIGGINS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | TANNER | BRITT | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | TANNER | BRITT | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | ALDO | RENYA | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | ALDO | RENYA | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44138-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-03 | Had JSA meeting sandblasted and coated | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP5 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44138-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-03 | Loaded out 7 dump trucks of rock/dirt, brought in 3 loads of fill dirt | CALEB | HOLTON | Foreman | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1092 | 151 | 169 |  | 13 | 13 | 1412 | [16 empty] | 1412 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44138-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-03 | Loaded out 7 dump trucks of rock/dirt, brought in 3 loads of fill dirt | THOMAS | FRANKLIN | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 824 | 151 | 156 |  | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44138-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-03 | Loaded out 7 dump trucks of rock/dirt, brought in 3 loads of fill dirt | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 12 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 1086 |  |  | 12 | 1086 | [16 empty] | 1086 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-43000-44138-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-03 | Pumped water | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | Filter Bag | 1 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 |  | 26 | 0 | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-43000-44138-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-03 | Pumped water | JOSE | VALLES | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-43000-44138-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-03 | Pumped water | REYMUNDO | REYES | Laborer | 2 |  |  |  | Water Pump (3") | 2 | HR | 3INP6 | [7 empty] | 47 | 63 | 0 | 151 | 12 |  | 94 |  | 24 |  | 2 | 2 | 118 | [16 empty] | 118 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-43000-44138-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-03 | Pumped water | MARCELO | GOMEZ | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-43000-44138-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-03 | Pumped water | ANTHONY | MORENO | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-43000-44138-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-03 | Pumped water | EFREM | LEE | Truck Driver/CDL | 2 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 107 |  |  |  | 2 |  | 107 | [16 empty] | 107 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | BARKLEY | BROWN | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | JOSHUA | MENDARIES | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | WAYLON | GREEN | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | JOSE | VALLES | Laborer | 6 |  |  | 1 | Tool Trailer | 10 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 50 |  | 6 | 10 | 483 | [16 empty] | 483 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | REYMUNDO | REYES | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | MARCELO | GOMEZ | Laborer | 6 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 282 | 151 | 460 |  | 6 | 10 | 893 | [16 empty] | 893 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | ANTHONY | MORENO | Laborer | 6 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 282 | 151 | 905 |  | 6 | 10 | 1338 | [16 empty] | 1338 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | EFREM | LEE | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | [16 empty] | 568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44138-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-03 | Cleaned up at dig, cleaned up 7/10 of access road. Delivered (2) sleeves to Enbridge station in Frenchlick Indiana | [7 empty] | Brush Hog | 10 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-54330-44138-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-03 | Pumped water | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | Filter Bag | 1 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 |  | 26 | 0 | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-54330-44138-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-03 | Pumped water | JOSE | VALLES | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-54330-44138-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-03 | Pumped water | REYMUNDO | REYES | Laborer | 2 |  |  |  | Water Pump (3") | 2 | HR | 3INP6 | [7 empty] | 47 | 63 | 0 | 151 | 12 |  | 94 |  | 24 |  | 2 | 2 | 118 | [16 empty] | 118 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-54330-44138-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-03 | Pumped water | MARCELO | GOMEZ | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-54330-44138-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-03 | Pumped water | ANTHONY | MORENO | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-54330-44138-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-03 | Pumped water | EFREM | LEE | Truck Driver/CDL | 2 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 107 |  |  |  | 2 |  | 107 | [16 empty] | 107 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Held JSA meeting. Received (4) loads of backfill material/removed (4) loads of material and started backfilling. Site is 80% backfilled, top soil needs to be placed. | GARRETT | DICKSON | Foreman | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1092 | 151 | 169 |  | 13 | 13 | 1412 | [16 empty] | 1412 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Held JSA meeting. Received (4) loads of backfill material/removed (4) loads of material and started backfilling. Site is 80% backfilled, top soil needs to be placed. | SHAWN | ROSE | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 824 | 151 | 156 |  | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Held JSA meeting. Received (4) loads of backfill material/removed (4) loads of material and started backfilling. Site is 80% backfilled, top soil needs to be placed. | GAGE | BURKS | Laborer | 8 | 4 |  | 1 | Tool Trailer | 12 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 60 |  | 12 | 12 | 839 | [16 empty] | 839 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Held JSA meeting. Received (4) loads of backfill material/removed (4) loads of material and started backfilling. Site is 80% backfilled, top soil needs to be placed. | ZACHARY | POWDERS | Laborer | 8 | 4 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 628 | 151 | 222 |  | 12 | 12 | 1001 | [16 empty] | 1001 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Held JSA meeting. Received (4) loads of backfill material/removed (4) loads of material and started backfilling. Site is 80% backfilled, top soil needs to be placed. | COLTON | ROBERTS | Laborer | 8 | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 628 | 151 | 552 |  | 12 | 12 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Held JSA meeting. Received (4) loads of backfill material/removed (4) loads of material and started backfilling. Site is 80% backfilled, top soil needs to be placed. | MICHEAL | TATUM | Laborer | 8 | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 12 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 628 | 151 | 1086 |  | 12 | 12 | 1865 | [16 empty] | 1865 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Held JSA meeting. Received (4) loads of backfill material/removed (4) loads of material and started backfilling. Site is 80% backfilled, top soil needs to be placed. | DANIEL | MARTIN | Laborer | 8 | 4 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 12 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 628 | 151 | 330 |  | 12 | 12 | 1109 | [16 empty] | 1109 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Held JSA meeting. Received (4) loads of backfill material/removed (4) loads of material and started backfilling. Site is 80% backfilled, top soil needs to be placed. | IAIN | ALLRED | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 192 |  | 12 | 12 | 1059 | [16 empty] | 1059 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44138-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-03 | Held JSA meeting. Received (4) loads of backfill material/removed (4) loads of material and started backfilling. Site is 80% backfilled, top soil needs to be placed. | [7 empty] | Hammer Attachment | 12 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | GERLAD | SMITH | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | GERALD | 2888 Coating | 8 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 444 | 151 | 78 | 0 | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | GERLAD | SMITH | Foreman | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | GERALD | Brushes | 6 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 448 |  | 65 | 0 | 5 | 5 | 513 | [16 empty] | 513 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | MICHAEL | RATLIFF | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | MICHAELR | Rockshield | 36 | LnFt |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 369 | 151 | 78 | 0 | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | MICHAEL | RATLIFF | Operator II | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 289 |  | 52 |  | 4 | 4 | 341 | [16 empty] | 341 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | OJ | SEALS | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | OJ | SEALS | Laborer | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 220 |  | 52 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | RICHARD | ADKINS | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | RICHARD | ADKINS | Laborer | 2 | 2 |  |  | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 220 |  | 20 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | BARRETT | WISE | Laborer | 6 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 282 | 151 | 276 |  | 6 | 6 | 709 | [16 empty] | 709 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | BARRETT | WISE | Laborer | 2 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 220 |  | 184 |  | 4 | 4 | 404 | [16 empty] | 404 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | DAVID | RATLIFF | Laborer | 6 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 282 | 151 | 543 |  | 6 | 6 | 976 | [16 empty] | 976 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | DAVID | RATLIFF | Laborer | 2 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 220 |  | 362 |  | 4 | 4 | 582 | [16 empty] | 582 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | [7 empty] | Hammer Attachment | 6 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | [7 empty] | Hammer Attachment | 4 | HR | RHA0141B | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | [7 empty] | Padding Bucket | 6 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | [7 empty] | Padding Bucket | 4 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-51610-44138-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | Jeeped and made repairs to coating. Put on 36ft of rockshield, started backfilling | [7 empty] | Pipe Jeep (includes spring) | 6 | HR | PJP4 | [11 empty] | 7 |  |  |  | 42 |  |  | 6 | 42 | [16 empty] | 42 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | RENE | CASAREZ | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | RENE | Seed Mix | 50 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 444 | 151 | 78 | 0 | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | RENE | CASAREZ | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RENE | Fertilizer | 20 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | DONALD | TIGUE | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | DONALD | Lime | 2 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 369 | 151 | 78 | 0 | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | DONALD | TIGUE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | DONALD | Straw Bales | 20 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 123 |  | 26 | 0 | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | DAVID | LOPEZ | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | RC23860 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | DAVID | LOPEZ | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RC23860 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | FERNANDO | GARCIA | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT9 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | FERNANDO | GARCIA | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT9 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | ADDEY | BENNETT | Laborer | 7 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 329 | 151 | 322 |  | 7 | 7 | 802 | [16 empty] | 802 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | ADDEY | BENNETT | Laborer | 1 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 110 |  | 92 |  | 2 | 2 | 202 | [16 empty] | 202 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | MARGIL | GARZA | Laborer | 6 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 282 | 151 | 543 |  | 6 | 6 | 976 | [16 empty] | 976 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | MARGIL | GARZA | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | JODY | HASTON | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF5509 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | [16 empty] | 568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | JODY | HASTON | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF5509 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC77892 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC77892 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | [7 empty] | Hammer Attachment | 6 | HR | RHA10141 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | [7 empty] | Hammer Attachment | 2 | HR | RHA10141 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | [7 empty] | Padding Bucket | 6 | HR | RPB17093 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-10630-44138-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | Seeded and fertilized access and site. Spread straw. Walked excavator (2) miles out to Demob | [7 empty] | Padding Bucket | 2 | HR | RPB17093 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | RENE | CASAREZ | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RENE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | DONALD | TIGUE | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | DAVID | LOPEZ | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RC23860 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | FERNANDO | GARCIA | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT9 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | ADDEY | BENNETT | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | MARGIL | GARZA | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | JODY | HASTON | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF5509 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC77892 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | [7 empty] | Hammer Attachment | 2 | HR | RHA10141 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-16230-44138-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | MOB into site. Installed rockshield on pipe, installed padding bucket | [7 empty] | Padding Bucket | 2 | HR | RPB17093 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | URIEL | VALCIENA | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | R15349 |  |  |  | BADGER1 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | BADGER1 | [15 empty] | 1186 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | HECTOR | VALDEZ NEVAREZ | Operator II | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | HECTOR |  |  |  | WATER TRUCK | 0 | 0 | 0 | 61.5 | 83 | 0 | 151 | 13 |  | 741 | 151 | 143 |  | 11 | 11 | 1035 | WATER TRUCK | [15 empty] | 1035 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 565 | 151 | 143 |  | 11 | 11 | 859 | [16 empty] | 859 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | ASTOLFO | FLORES | Laborer | 8 | 3 |  | 1 | Tool Trailer | 11 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 565 | 151 | 55 |  | 11 | 11 | 771 | [16 empty] | 771 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | IVAN | MADRID | Laborer | 8 | 3 |  | 1 | 40' Flatbed trailer or equal | 11 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 565 | 151 | 203.5 |  | 11 | 11 | 919.5 | [16 empty] | 919.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | ROBERTO | RODRIGUEZ | Laborer | 8 | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 11 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 565 | 151 | 506 |  | 11 | 11 | 1222 | [16 empty] | 1222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | JOEL | VALDEZ NEVAREZ | Laborer | 8 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 11 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 565 | 151 | 995.5 |  | 11 | 11 | 1711.5 | [16 empty] | 1711.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | HECTOR | QUINTANA VALDEZ | Laborer | 8 | 3 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 11 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 565 | 151 | 302.5 |  | 11 | 11 | 1018.5 | [16 empty] | 1018.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 11 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 644 | 151 | 176 |  | 11 | 11 | 971 | [16 empty] | 971 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | [7 empty] | Hammer Attachment | 11 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | [7 empty] | Padding Bucket | 11 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44138-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-03 | Held JSA meeting Hydro vac finished with 5ft trench around 3pm. Excavator was able to slope all banks so hydro vac could safely enter ditch. Bellhole was sniffed for gas and bellhole permit issued. Cleaned site and put up safety fence. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 11 | HR | RTB7 | [11 empty] | 24.5 |  |  |  | 269.5 |  |  | 11 | 269.5 | [16 empty] | 269.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | RYAN | FARINELLI | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | JOSE | ORTIZ | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | ROBERT | FOSTER | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | BRIAN | RANDLE | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8762 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [16 empty] | 460 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | [7 empty] | Hammer Attachment | 10 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44138-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-03 | Assisted crew 9 | [7 empty] | Padding Bucket | 10 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | MATTHEW | LINDLEY | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | MATTHEW | LINDLEY | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 |  | 52 |  | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | MATTHEW | LINDLEY | Foreman | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 448 |  | 65 |  | 5 | 5 | 513 | [16 empty] | 513 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | W. MONROE | LINDLEY | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 | 151 | 13 |  | 1 | 1 | 225.5 | [16 empty] | 225.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | W. MONROE | LINDLEY | Operator II | 7 | 2 |  |  | Pickup-F150 or F250 or equal | 9 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 596.5 |  | 117 |  | 9 | 9 | 713.5 | [16 empty] | 713.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | LUTHER | LINDLEY | Laborer | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 | 151 | 13 |  | 1 | 1 | 211 | [16 empty] | 211 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | LUTHER | LINDLEY | Laborer | 7 | 2 |  |  | Pickup-F150 or F250 or equal | 9 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 455 |  | 117 |  | 9 | 9 | 572 | [16 empty] | 572 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | DEMETRIUS | DOBY | Laborer | 1 |  |  | 1 | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 | 151 | 5 |  | 1 | 1 | 203 | [16 empty] | 203 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | DEMETRIUS | DOBY | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | DEMETRIUS | DOBY | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | NICHOLAS | BLANCO | Laborer | 1 |  |  | 1 | 40' Flatbed trailer or equal | 1 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 | 151 | 18.5 |  | 1 | 1 | 216.5 | [16 empty] | 216.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | NICHOLAS | BLANCO | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | NICHOLAS | BLANCO | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | DANIEL | MENDOZA | Laborer | 1 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 | 151 | 46 |  | 1 | 1 | 244 | [16 empty] | 244 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | DANIEL | MENDOZA | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | DANIEL | MENDOZA | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 230 |  | 5 | 5 | 497 | [16 empty] | 497 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | JESUS | MENDOZA | Laborer | 1 |  |  | 1 | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 1 | HR | REX592 | [7 empty] | 47 | 63 | 0 | 151 | 145 |  | 47 | 151 | 145 |  | 1 | 1 | 343 | [16 empty] | 343 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | JESUS | MENDOZA | Laborer | 4 |  |  |  | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 4 | HR | REX592 | [7 empty] | 47 | 63 | 0 | 151 | 145 |  | 188 |  | 580 |  | 4 | 4 | 768 | [16 empty] | 768 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | JESUS | MENDOZA | Laborer | 3 | 2 |  |  | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 5 | HR | REX592 | [7 empty] | 47 | 63 | 0 | 151 | 145 |  | 267 |  | 725 |  | 5 | 5 | 992 | [16 empty] | 992 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | TYLER | BIGG | Truck Driver/CDL | 1 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 | 151 | 16 |  | 1 | 1 | 220.5 | [16 empty] | 220.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | TYLER | BIGG | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44138-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-03 | Padded pipe by hand, backfilled excavation, began site demob | TYLER | BIGG | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | JASON | JONES | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | [7 empty] | Tractor/Semi | 10 | HR | R1371 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | Matches crew 7 | [7 empty] | Lowboy Trailer | 10 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44139-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | 35ft of coating. Installed silt fence along mat bridge | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44139-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | 35ft of coating. Installed silt fence along mat bridge | RYAN | FARINELLI | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44139-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | 35ft of coating. Installed silt fence along mat bridge | JERMAINE | EVANS | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44139-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | 35ft of coating. Installed silt fence along mat bridge | JOSE | ORTIZ | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44139-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | 35ft of coating. Installed silt fence along mat bridge | ROBERT | FOSTER | Laborer | 8 | 2 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC8430 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 502 | 151 | 275 |  | 10 | 10 | 928 | [16 empty] | 928 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44139-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | 35ft of coating. Installed silt fence along mat bridge | BRIAN | RANDLE | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-28110-44139-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-04 | Jeeped pipe, patched jeeps | JACOB | CAPITANO | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15335 | 2888 Coating | 1 | L |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 126 |  | 26 | 0 | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-28110-44139-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-04 | Jeeped pipe, patched jeeps | BROC | CALIGER | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF1040 | Brushes | 2 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 16 | 0 | 126 |  | 32 | 0 | 2 | 2 | 158 | [16 empty] | 158 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-28110-44139-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-04 | Jeeped pipe, patched jeeps | CODY | GAXIOLA | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-28110-44139-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-04 | Jeeped pipe, patched jeeps | HEATHER | ENGLE | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-28110-44139-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-04 | Jeeped pipe, patched jeeps | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 2 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 144 |  |  |  | 2 |  | 144 | [16 empty] | 144 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | JACOB | CAPITANO | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | BROC | CALIGER | Laborer | 8 |  |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 50 |  | 8 | 10 | 577 | [16 empty] | 577 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | CODY | GAXIOLA | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 185 |  | 8 | 10 | 712 | [16 empty] | 712 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | HEATHER | ENGLE | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 460 |  | 8 | 10 | 987 | [16 empty] | 987 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | [16 empty] | 707 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | [7 empty] | Hammer Attachment | 10 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | [7 empty] | Padding Bucket | 10 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28570-44139-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | Had JSA, pumped water. Cleaned site and backfilled. Hauled trash and scattered out topsoil to dry. | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | NATTHEW | LINDLEY | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | MATTHEW | LINDLEY | Foreman | 6 | 3 |  |  | Pickup-F150 or F250 or equal | 9 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 744 |  | 117 |  | 9 | 9 | 861 | [16 empty] | 861 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | W. MONROE | LINDLEY | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 | 151 | 13 |  | 1 | 1 | 225.5 | [16 empty] | 225.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | W. MONROE | LINDLEY | Operator II | 7 | 2 |  |  | Pickup-F150 or F250 or equal | 9 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 596.5 |  | 117 |  | 9 | 9 | 713.5 | [16 empty] | 713.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | LUTHER | LINDLEY | Laborer | 1 |  |  | 1 | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 1 | HR | REX592 | [7 empty] | 47 | 63 | 0 | 151 | 145 |  | 47 | 151 | 145 |  | 1 | 1 | 343 | [16 empty] | 343 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | LUTHER | LINDLEY | Laborer | 7 | 2 |  |  | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 9 | HR | REX592 | [7 empty] | 47 | 63 | 0 | 151 | 145 |  | 455 |  | 1305 |  | 9 | 9 | 1760 | [16 empty] | 1760 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | NICHOLAS | BLANCO | Laborer | 1 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 47 | 151 |  |  | 1 |  | 198 | [16 empty] | 198 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | NICHOLAS | BLANCO | Laborer | 7 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 455 |  |  |  | 9 |  | 455 | [16 empty] | 455 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | DANIEL | MENDOZA | Laborer | 1 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 47 | 151 |  |  | 1 |  | 198 | [16 empty] | 198 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | DANIEL | MENDOZA | Laborer | 7 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 455 |  |  |  | 9 |  | 455 | [16 empty] | 455 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Access | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | JESUS | MENDOZA | Laborer | 1 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 47 | 151 |  |  | 1 |  | 198 | [16 empty] | 198 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-29300-44139-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | Put back topsoil and water bars on top of hill. Roughed in and put back water bars on hillside. Demob site except 329 and mop pipe. Took all equipment including crew truck to yard. | JESUS | MENDOZA | Laborer | 7 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 455 |  |  |  | 9 |  | 455 | [16 empty] | 455 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | GERALD | SMITH | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | GERALD | Fertilizer | 100 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | GERALD | SMITH | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | GERALD | Seed Mix | 15 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | GERALD | SMITH | Foreman | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | GERALD | Straw Bales | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 174 |  | 26 | 0 | 2 | 2 | 200 | [16 empty] | 200 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | MICHAEL | RATLIFF | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | MICHAEL | RATLIFF | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | MICHAEL | RATLIFF | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | OJ | SEALS | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | OJ | SEALS | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | OJ | SEALS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | RICHARD | ADKINS | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | RICHARD | ADKINS | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | RICHARD | ADKINS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | BARRETT | WISE | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 230 |  | 5 | 5 | 616 | [16 empty] | 616 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | BARRETT | WISE | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | BARRETT | WISE | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | DAVID | RATLIFF | Laborer | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 235 | 151 | 452.5 |  | 5 | 5 | 838.5 | [16 empty] | 838.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | DAVID | RATLIFF | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | DAVID | RATLIFF | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | STEVE | CLARK | Truck Driver/CDL |  | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 | 151 | 80 |  | 5 | 5 | 591 | [16 empty] | 591 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-51610-44139-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | Finished backfilling and clean up on site. Demob to next dig site | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44139-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | MOB equipment to site | GERALD | SMITH | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44139-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | MOB equipment to site | MICHAEL | RATLIFF | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44139-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | MOB equipment to site | OJ | SEALS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44139-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | MOB equipment to site | RICHARD | ADKINS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44139-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | MOB equipment to site | BARRETT | WISE | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44139-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | MOB equipment to site | DAVID | RATLIFF | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44139-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | MOB equipment to site | STEVE | CLARK | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44139-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | MOB equipment to site | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44139-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | MOB equipment to site | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | CALEB | HOLTON | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | CALEB | Seed Mix | 25 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MICHAELA | Rockshield | 6 | LnFt |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 | 151 | 26 | 0 | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELA | Straw Bales | 2 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 47 |  | 13 | 0 | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | BOLDBAUTOR | ZORIGT | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | JORDAN | WIGGINS | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | JORDAN | WIGGINS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | ALDO | RENYA | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | ALDO | RENYA | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Tool Trailer | 2 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 10 |  |  | 2 | 10 | [16 empty] | 10 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Tool Trailer | 1 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 5 |  |  | 1 | 5 | [16 empty] | 5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | 40' Flatbed trailer or equal | 1 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 18.5 |  |  | 1 | 18.5 | [16 empty] | 18.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | CALEB | HOLTON | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | CALEB | Seed Mix | 25 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAELA | Rockshield | 6 | LnFt |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 |  | 26 | 0 | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELA | Straw Bales | 2 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 47 |  | 13 | 0 | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | BOLDBAUTOR | ZORIGT | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | JORDAN | WIGGINS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | JORDAN | WIGGINS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | ALDO | RENYA | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | ALDO | RENYA | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Tool Trailer | 2 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 10 |  |  | 2 | 10 | [16 empty] | 10 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Tool Trailer | 1 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 5 |  |  | 1 | 5 | [16 empty] | 5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | 40' Flatbed trailer or equal | 1 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 18.5 |  |  | 1 | 18.5 | [16 empty] | 18.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | CALEB | HOLTON | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | CALEB | Seed Mix | 25 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAELA | Rockshield | 6 | LnFt |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 |  | 26 | 0 | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELA | Straw Bales | 2 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 63 |  | 13 | 0 | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | BOLDBAUTOR | ZORIGT | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | JORDAN | WIGGINS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | JORDAN | WIGGINS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | ALDO | RENYA | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | ALDO | RENYA | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Tool Trailer | 2 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 10 |  |  | 2 | 10 | [16 empty] | 10 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Tool Trailer | 1 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 5 |  |  | 1 | 5 | [16 empty] | 5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | 40' Flatbed trailer or equal | 1 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 18.5 |  |  | 1 | 18.5 | [16 empty] | 18.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | Backfilled and cleaned up dig | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | CALEB | HOLTON | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | THOMAS | FRANKLIN | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 824 | 151 | 156 |  | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | MICHAEL | ANISZEWSKI | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | BOLDBAUTOR | ZORIGT | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | JORDAN | WIGGINS | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | TANNER | BRITT | Laborer | 8 | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 628 | 151 | 552 |  | 12 | 12 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | ALDO | RENYA | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 3 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 73.5 |  |  | 3 | 73.5 | [16 empty] | 73.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | [7 empty] | Hammer Attachment | 3 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-35680-44139-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | backfilled bellhole | [7 empty] | Padding Bucket | 3 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-43000-44139-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-04 | Coated pipe | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | 4888 Coating | 9 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-43000-44139-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-04 | Coated pipe | WAYLON | GREEN | Laborer | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19115 | Brushes | 21 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 157 |  | 39 | 0 | 3 | 3 | 196 | [16 empty] | 196 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-43000-44139-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-04 | Coated pipe | JOSE | VALLES | Laborer | 2 | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 157 |  |  |  | 3 |  | 157 | [16 empty] | 157 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-43000-44139-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-04 | Coated pipe | MARCELO | GOMEZ | Laborer | 2 | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 157 |  |  |  | 3 |  | 157 | [16 empty] | 157 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-43000-44139-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-04 | Coated pipe | EFREM | LEE | Truck Driver/CDL | 2 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 179 |  | 48 |  | 3 | 3 | 227 | [16 empty] | 227 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | BARKLEY | BROWN | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | JOSHUA | MENDARIES | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | WAYLON | GREEN | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | JOSE | VALLES | Laborer | 5 |  |  | 1 | Tool Trailer | 10 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 50 |  | 5 | 10 | 436 | [16 empty] | 436 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | REYMUNDO | REYES | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | MARCELO | GOMEZ | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 460 |  | 5 | 10 | 846 | [16 empty] | 846 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | EFREM | LEE | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | ANTHONY | MORENO | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 905 |  | 4 | 10 | 1244 | [16 empty] | 1244 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | [7 empty] | Brush Hog | 10 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44139-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | Finished clean up at site. Spread 21 loads of #2 rock | [47 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44139-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-04 | Pumped water | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | Filter Bag | 4 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 | 0 | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44139-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-04 | Pumped water | JOSE | VALLES | Laborer |  | 2 |  |  | Water Pump (3") | 2 | HR | 3INP6A | [7 empty] | 47 | 63 | 0 | 151 | 12 |  | 126 |  | 24 |  | 2 | 2 | 150 | [16 empty] | 150 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44139-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-04 | Pumped water | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Water Pump (3") | 2 | HR | 3INP6B | [7 empty] | 47 | 63 | 0 | 151 | 12 |  | 126 |  | 24 |  | 2 | 2 | 150 | [16 empty] | 150 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44139-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-04 | Pumped water | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44139-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-04 | Pumped water | [7 empty] | Water Pump (3") | 2 | HR | 3INP6C | [11 empty] | 12 |  |  |  | 24 |  |  | 2 | 24 | [16 empty] | 24 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44139-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-04 | Pumped water | [7 empty] | Water Pump ( up to 2") | 2 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 12 |  |  | 2 | 12 | [16 empty] | 12 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | URIEL | VALENCIA | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15349 |  |  |  | BADGER1 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | BADGER1 | [15 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | HECTOR | VALDEZ NEVAREZ | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | HECTOR |  |  |  | WATER TRUCK | 0 | 0 | 0 | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | WATER TRUCK | [15 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | ASTOLFO | FLORES | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | IVAN | MADRID | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | ROBERTO | RODRIGUEZ | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | JOEL | VALDEZ NEVAREZ | Laborer | 8 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 502 | 151 | 905 |  | 10 | 10 | 1558 | [16 empty] | 1558 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | HECTOR | QUINTANA NEVAREZ | Laborer | 8 | 2 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 502 | 151 | 275 |  | 10 | 10 | 928 | [16 empty] | 928 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | [7 empty] | Hammer Attachment | 10 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | [7 empty] | Padding Bucket | 10 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44139-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | JSA meeting. Badger continued to slot trench until 2pm. Excavator was able to take down ditch to depth. Trench box was set into bellhole and sides were backfilled in for safe entry. Exit sides were sloped back and excavation was fenced off for the day. Trash was picked up and tools put away. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB7 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | GARRETT | DICKSON | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15318 | Seed Mix | 10 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Straw Bales | 8 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | SHAWN | ROSE | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | GAGE | BURKS | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | GAGE | BURKS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | ZACHARY | POWDERS | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | ZACHARY | POWDERS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | COLTON | ROBERTS | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 138 |  | 3 | 3 | 430 | [16 empty] | 430 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | COLTON | ROBERTS | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | MICHEAL | TATUM | Laborer | 3 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 | 151 | 271.5 |  | 3 | 3 | 563.5 | [16 empty] | 563.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | MICHEAL | TATUM | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | DANIEL | MARTIN | Laborer | 3 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 141 | 151 | 82.5 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | DANIEL | MARTIN | Laborer | 1 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 |  | 27.5 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | IAIN | ALLRED | Truck Driver/CDL | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 | 151 | 48 |  | 3 | 3 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | [7 empty] | Hammer Attachment | 3 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23260-44139-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | Backfilled and seeded/strawed | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | GARRETT | DICKSON | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | Seed Mix | 10 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Straw Bales | 7 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | SHAWN | ROSE | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | GAGE | BURKS | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | GAGE | BURKS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | ZACHARY | POWDERS | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | ZACHARY | POWDERS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | COLTON | ROBERTS | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | COLTON | ROBERTS | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | MICHEAL | TATUM | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | MICHEAL | TATUM | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | DANIEL | MARTIN | Laborer | 3 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 141 |  | 82.5 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | DANIEL | MARTIN | Laborer | 1 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 |  | 27.5 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | IAIN | ALLRED | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | [7 empty] | Hammer Attachment | 3 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-23770-44139-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | Backfilled and seeded/strawed | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | BACKFILLED | GARRETT | DICKSON | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | BACKFILLED | SHAWN | ROSE | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | BACKFILLED | GAGE | BURKS | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | BACKFILLED | ZACHARY | POWDERS | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | BACKFILLED | COLTON | ROBERTS | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | BACKFILLED | MICHEAL | TATUM | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | BACKFILLED | DANIEL | MARTIN | Laborer |  | 4 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 252 |  | 110 |  | 4 | 4 | 362 | [16 empty] | 362 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | BACKFILLED | IAIN | ALLRED | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-27760-44139-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | BACKFILLED | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-14960-44139-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-04 | Began padding and backfill. Jeeped pipe and fixed jeeps. When coating dried, installed 55ft rock shield. | RENE | CASAREZ | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RENE | Sand | 25 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-14960-44139-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-04 | Began padding and backfill. Jeeped pipe and fixed jeeps. When coating dried, installed 55ft rock shield. | DONALD | TIGUE | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DONALDT | Rockshield | 55 | LnFt |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 166 |  | 26 | 0 | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44139-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-04 | Began padding and backfill. Jeeped pipe and fixed jeeps. When coating dried, installed 55ft rock shield. | FERNANDO | GARCIA | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RC23860 | Brushes | 3 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 63 |  | 13 | 0 | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-14960-44139-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-04 | Began padding and backfill. Jeeped pipe and fixed jeeps. When coating dried, installed 55ft rock shield. | ADDEY | BENNETT | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX10563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 181 |  | 3 | 2 | 370 | [16 empty] | 370 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44139-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-04 | Began padding and backfill. Jeeped pipe and fixed jeeps. When coating dried, installed 55ft rock shield. | MARGIL | GARZA | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC77892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44139-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-04 | Began padding and backfill. Jeeped pipe and fixed jeeps. When coating dried, installed 55ft rock shield. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP9 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44139-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | Blasted and did 35ft of coating, installed silt fence along mat bridge | FERNANDO | GARCIA | Laborer | 8 | 1 |  | 1 | Pickup-F150 or F250 or equal | 9 | HR | ERC23860 | 2888 Coating | 56 | L |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 439 | 151 | 117 | 0 | 9 | 9 | 707 | [16 empty] | 707 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44139-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | Blasted and did 35ft of coating, installed silt fence along mat bridge | MARGIL | GARZA | Laborer | 8 | 1 |  | 1 |  |  |  |  | Brushes | 40 | Ea |  |  |  |  | 47 | 63 | 0 | 151 |  | 0 | 439 | 151 |  | 0 | 9 |  | 590 | [16 empty] | 590 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | RENE | CASAREZ | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | RENE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | DONALD | TIGUE | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | DAVID | LOPEZ | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | RC23860 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | DAVID | LOPEZ | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RC23860 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | ADDEY | BENNETT | Laborer | 8 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX10563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 376 | 151 | 724 |  | 8 | 8 | 1251 | [16 empty] | 1251 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | JODY | HASTON | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | RF5509 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | [16 empty] | 707 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | JODY | HASTON | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF5509 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [7 empty] | Tool Trailer | 8 | HR | UTT9 | [11 empty] | 5 |  |  |  | 40 |  |  | 8 | 40 | [16 empty] | 40 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [7 empty] | Tool Trailer | 2 | HR | UTT9 | [11 empty] | 5 |  |  |  | 10 |  |  | 2 | 10 | [16 empty] | 10 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS11304 | [11 empty] | 46 |  |  |  | 368 |  |  | 8 | 368 | [16 empty] | 368 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS11304 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [7 empty] | Hammer Attachment | 8 | HR | RHA00847 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [7 empty] | Hammer Attachment | 2 | HR | RHA00847 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [7 empty] | Padding Bucket | 8 | HR | RPB19021 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [7 empty] | Padding Bucket | 2 | HR | RPB19021 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [47 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44139-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | Completely backfilled and tracked excavator to 1546 | [47 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | TOME | KIRKLAND | Superintendent | 4 | 8 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1382 | 151 | 156 |  | 12 | 12 | 1689 | [16 empty] | 1689 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | JASON | JONES | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | [7 empty] | Tractor/Semi | 12 | HR | R1371 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Matches crew 9 | [7 empty] | Lowboy Trailer | 12 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | JONATHAN | HOLLEY | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | JPO | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | JOSE | ORTIZ | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | [16 empty] | 567 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | JOSE | ORTIZ | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | DEMETRIUS | DOBY | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | [16 empty] | 675 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | DEMETRIUS | DOBY | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | ROBERT | FOSTER | Laborer | 8 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 376 | 151 | 724 |  | 8 | 8 | 1251 | [16 empty] | 1251 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | ROBERT | FOSTER | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | BRIAN | RANDLE | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | [16 empty] | 707 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | [7 empty] | Hammer Attachment | 8 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | [7 empty] | Padding Bucket | 8 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe. Fixed holidays, rejeeped pipe. Once approved, installed 35 ft of rockshield. | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | KYLE | BONNEAU | Foreman | 7 | 4 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | Fertilizer | 100 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 918 | 151 | 143 | 0 | 11 | 11 | 1212 | [16 empty] | 1212 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | Seed Mix | 100 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 658 | 151 | 130 | 0 | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | Straw Bales | 36 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 502 | 151 | 130 | 0 | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | T-Posts | 7 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 5 | 0 | 502 | 151 | 50 | 0 | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | HEATHER | ENGLE | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | [7 empty] | Hammer Attachment | 10 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28570-44140-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-05 | Had JSA meeting. Spread topsoil, fertilized, seed and strawed. Put up electric fence (100FT). Took out bridge. 90% complete | [7 empty] | Padding Bucket | 10 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | GERALD | SMITH | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | GERALD | Sand | 50 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | GERALD | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | GERALD | 2888 Coating | 70 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | GERALD | SMITH | Foreman | 2 | 4 |  |  | Pickup-F150 or F250 or equal | 6 | HR | GERALD | Brushes | 72 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 548 |  | 78 | 0 | 6 | 6 | 626 | [16 empty] | 626 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | MICHAEL | RATLIFF | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | MICHAEL | RATLIFF | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | MICHAEL | RATLIFF | Operator II | 4 | 2 |  |  | Pickup-F150 or F250 or equal | 6 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 412 |  | 78 |  | 6 | 6 | 490 | [16 empty] | 490 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | OJ | SEALS | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 | 151 | 39 |  | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | OJ | SEALS | Laborer | 4 | 2 |  |  | Pickup-F150 or F250 or equal | 6 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 314 |  | 78 |  | 6 | 6 | 392 | [16 empty] | 392 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | RICHARD | ADKINS | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | RICHARD | ADKINS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | RICHARD | ADKINS | Laborer | 4 | 2 |  |  | Tool Trailer | 6 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 314 |  | 30 |  | 6 | 6 | 344 | [16 empty] | 344 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | BARRETT | WISE | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 138 |  | 3 | 3 | 430 | [16 empty] | 430 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | BARRETT | WISE | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | BARRETT | WISE | Laborer | 4 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 314 |  | 276 |  | 6 | 6 | 590 | [16 empty] | 590 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | DAVID | RATLIFF | Laborer | 3 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858B | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 141 | 151 | 82.5 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | DAVID | RATLIFF | Laborer | 1 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858B | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 |  | 27.5 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | DAVID | RATLIFF | Laborer | 4 | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC0858B | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 314 |  | 165 |  | 6 | 6 | 479 | [16 empty] | 479 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | STEVE | CLARK | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 160 |  | 8 | 10 | 739 | [16 empty] | 739 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | STEVE | CLARK | Truck Driver/CDL |  | 2 |  |  | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 144 |  | 185 |  | 2 | 10 | 329 | [16 empty] | 329 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | RSPM923 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0278 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0278 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44140-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | Sandblasted pipe, NDE did assessment. Recoated 42ft of pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0278 | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | CALEB | HOLTON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | CALEB | Sand | 15 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | CALEB | HOLTON | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | CALEB | 2888 Coating | 22 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 400 |  | 52 | 0 | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | THOMAS | FRANKLIN | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | THOMASF | Brushes | 7 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 249 |  | 39 | 0 | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | THOMAS | FRANKLIN | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | MICHAEL | ANISZEWSKI | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | MICHAEL | ANISZEWSKI | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | BOLDBAUTOR | ZORIGT | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | BOLDBAUTOR | ZORIGT | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | JORDAN | WIGGINS | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | JORDAN | WIGGINS | Laborer |  | 4 |  |  | Tool Trailer | 3 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 15 |  | 4 | 3 | 267 | [16 empty] | 267 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | TANNER | BRITT | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | TANNER | BRITT | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | ALDO | RENYA | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | ALDO | RENYA | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Hammer Attachment | 3 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Hammer Attachment | 3 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Padding Bucket | 3 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Padding Bucket | 3 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 3 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 73.5 |  |  | 3 | 73.5 | [16 empty] | 73.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 3 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 73.5 |  |  | 3 | 73.5 | [16 empty] | 73.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44140-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-05 | Unloaed excavator, tracked in. Sandblasted and coated pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | RSP5 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | CALEB | HOLTON | Foreman | 2 | 4 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 548 | 151 | 78 |  | 6 | 6 | 777 | [16 empty] | 777 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | THOMAS | FRANKLIN | Operator II | 4 | 2 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 412 | 151 | 78 |  | 6 | 6 | 641 | [16 empty] | 641 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | MICHAEL | ANISZEWSKI | Laborer | 1 | 5 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 362 | 151 | 78 |  | 6 | 6 | 591 | [16 empty] | 591 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | BOLDBAUTOR | ZORIGT | Laborer | 4 | 2 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 314 | 151 | 78 |  | 6 | 6 | 543 | [16 empty] | 543 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | JORDAN | WIGGINS | Laborer | 1 | 5 |  | 1 | Tool Trailer | 6 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 362 | 151 | 30 |  | 6 | 6 | 543 | [16 empty] | 543 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | TANNER | BRITT | Laborer | 4 | 2 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 314 | 151 | 111 |  | 6 | 6 | 576 | [16 empty] | 576 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | ALDO | RENYA | Truck Driver/CDL | 4 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 358 | 151 | 96 |  | 6 | 6 | 605 | [16 empty] | 605 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 276 |  |  | 6 | 276 | [16 empty] | 276 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | [7 empty] | Hammer Attachment | 6 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 6 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 147 |  |  | 6 | 147 | [16 empty] | 147 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-27760-44140-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-05 | Had JSA meeting. Loaded excavator, demob | [7 empty] | Padding Bucket | 6 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | GARRETT | DICKSON | Foreman | 1 | 2 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 274 | 151 | 39 |  | 3 | 3 | 464 | [16 empty] | 464 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | GARRETT | DICKSON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | SHAWN | ROSE | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | SHAWN | ROSE | Operator II | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 227.5 |  | 39 |  | 3 | 3 | 266.5 | [16 empty] | 266.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | GAGE | BURKS | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | GAGE | BURKS | Laborer | 1 | 2 |  |  | Tool Trailer | 3 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 173 |  | 15 |  | 3 | 3 | 188 | [16 empty] | 188 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | ZACHARY | POWDERS | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | ZACHARY | POWDERS | Laborer | 1 | 2 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 173 |  | 55.5 |  | 3 | 3 | 228.5 | [16 empty] | 228.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | COLTON | ROBERTS | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 138 |  | 3 | 3 | 430 | [16 empty] | 430 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | COLTON | ROBERTS | Laborer | 1 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 173 |  | 138 |  | 3 | 3 | 311 | [16 empty] | 311 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | MICHEAL | TATUM | Laborer | 3 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 | 151 | 271.5 |  | 3 | 3 | 563.5 | [16 empty] | 563.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | MICHEAL | TATUM | Laborer | 1 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 173 |  | 271.5 |  | 3 | 3 | 444.5 | [16 empty] | 444.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | DANIEL | MARTIN | Laborer | 3 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 141 | 151 | 82.5 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | DANIEL | MARTIN | Laborer | 1 | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 173 |  | 82.5 |  | 3 | 3 | 255.5 | [16 empty] | 255.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | IAIN | ALLRED | Truck Driver/CDL | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 | 151 | 48 |  | 3 | 3 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | IAIN | ALLRED | Truck Driver/CDL | 1 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 197.5 |  | 48 |  | 3 | 3 | 245.5 | [16 empty] | 245.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | [7 empty] | Hammer Attachment | 3 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | [7 empty] | Hammer Attachment | 3 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | [7 empty] | Padding Bucket | 3 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | [7 empty] | Padding Bucket | 3 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP8 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44140-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-05 | Had JSA meeting. Cleaned up and removed everything from site. Staged trench box to be off rented. Bellhole is 80% filled. Needs topsoil placed. Began to load equipment to 1485 | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP8 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | GARRETT | DICKSON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | SHAWN | ROSE | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | SHAWN | ROSE | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | GAGE | BURKS | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | GAGE | BURKS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | ZACHARY | POWDERS | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | ZACHARY | POWDERS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | COLTON | ROBERTS | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | MICHEAL | TATUM | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | MICHEAL | TATUM | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | DANIEL | MARTIN | Laborer |  | 3 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 189 |  | 82.5 |  | 3 | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | DANIEL | MARTIN | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | IAIN | ALLRED | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | [7 empty] | Hammer Attachment | 3 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | [7 empty] | Padding Bucket | 3 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | [7 empty] | Padding Bucket | 1 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP8 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Arrived at site. Began to backfill and clean up site. Bellhole is 80% | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-14960-44140-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-05 | Padded and backfilled dig. | RENE | CASAREZ | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RENE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-14960-44140-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-05 | Padded and backfilled dig. | DONALD | TIGUE | Operator II | 7 | 2 |  |  | Pickup-F150 or F250 or equal | 9 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 596.5 |  | 117 |  | 9 | 9 | 713.5 | [16 empty] | 713.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-14960-44140-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-05 | Padded and backfilled dig. | DAVID | LOPEZ | Laborer | 7 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 9 | HR | REX10563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 455 |  | 814.5 |  | 9 | 9 | 1269.5 | [16 empty] | 1269.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-14960-44140-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-05 | Padded and backfilled dig. | ADDEY | BENNETT | Laborer | 7 | 4 |  | 1 | Hammer Attachment | 10 | HR | RHA00847 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 581 | 151 | 0 |  | 11 | 10 | 732 | [16 empty] | 732 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-14960-44140-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-05 | Padded and backfilled dig. | [7 empty] | Padding Bucket | 10 | HR | RPB19021 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe, fixed holidays, jeeped pipe. Once approved installed 35ft rockshield. Began backfill. Had (4) loads rock hauled in for repair of access road. | FERNANDO | GARCIA | Laborer | 5 | 2 |  |  | Pipe Jeep (includes spring) | 1 | HR | PJP9 | Rockshield | 35 | LnFt |  |  |  |  | 47 | 63 | 0 | 151 | 7 | 0 | 361 |  | 7 | 0 | 7 | 1 | 368 | [16 empty] | 368 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe, fixed holidays, jeeped pipe. Once approved installed 35ft rockshield. Began backfill. Had (4) loads rock hauled in for repair of access road. | DONALD | TIGUE | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | DONALD | Brushes | 2 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 61.5 | 151 | 13 | 0 | 1 | 1 | 225.5 | [16 empty] | 225.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44140-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | Jeeped pipe, fixed holidays, jeeped pipe. Once approved installed 35ft rockshield. Began backfill. Had (4) loads rock hauled in for repair of access road. | DAVID | LOPEZ | Laborer | 1 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX10563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 | 151 | 90.5 |  | 1 | 1 | 288.5 | [16 empty] | 288.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Finished dressing up access road and dig site. Seeded and strawed. | FERNANDO | GARCIA | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | RC23860 | Seed Mix | 50 | lbs |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 141 | 151 | 39 | 0 | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Finished dressing up access road and dig site. Seeded and strawed. | MARGIL | GARZA | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT9 | Fertilizer | 25 | lbs |  |  |  |  | 47 | 63 | 0 | 151 | 5 | 0 | 502 | 151 | 50 | 0 | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Finished dressing up access road and dig site. Seeded and strawed. | JODY | HASTON | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF5509 | Lime | 1 | Bag |  |  |  |  | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 | 0 | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-16230-44140-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-05 | Finished dressing up access road and dig site. Seeded and strawed. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS11304 | Straw Bales | 7 | Ea | [8 empty] | 46 | 0 |  |  | 460 | 0 |  | 10 | 460 | [16 empty] | 460 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Jeeped pipe. NDE did assessment. | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Jeeped pipe. NDE did assessment. | WAYLON | GREEN | Laborer | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 52 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Jeeped pipe. NDE did assessment. | JOSE | VALLES | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Jeeped pipe. NDE did assessment. | MARCELO | GOMEZ | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Jeeped pipe. NDE did assessment. | EFREM | LEE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Jeeped pipe. NDE did assessment. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | [16 empty] | 184 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Jeeped pipe. NDE did assessment. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Jeeped pipe. NDE did assessment. | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Post Repair Assessment | 3500028468-43000-44140-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-05 | Jeeped pipe. NDE did assessment. | [7 empty] | Pipe Jeep (includes spring) | 1 | HR | PJP6 | [11 empty] | 7 |  |  |  | 7 |  |  | 1 | 7 | [16 empty] | 7 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | BARKLEY | BROWN | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | JOSHUA | MENDARIES | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | WAYLON | GREEN | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | JOSE | VALLES | Laborer | 2 |  |  | 1 | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 25 |  | 2 | 5 | 270 | [16 empty] | 270 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | REYMUNDO | REYES | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 92.5 |  | 10 | 5 | 745.5 | [16 empty] | 745.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | MARCELO | GOMEZ | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 230 |  | 2 | 5 | 475 | [16 empty] | 475 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | EFREM | LEE | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | [7 empty] | Hammer Attachment | 10 | HR | RHA1055B | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | [7 empty] | Padding Bucket | 5 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-51460-44140-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-05 | Finished clean up | [7 empty] | Brush Hog | 5 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Sand | 3 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | BARKLEY | BROWN | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | 4888 Coating | 4 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | WAYLON | GREEN | Laborer | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | Brushes | 12 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 110 |  | 26 | 0 | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | WAYLON | GREEN | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | MARCELO | GOMEZ | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | MARCELO | GOMEZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | EFREM | LEE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44140-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-05 | Sandblasted and coated pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | URIEL | VALENCIA | Foreman | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | R15349 |  |  |  | BADGER1 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 518 | 151 | 91 |  | 7 | 7 | 760 | BADGER1 | [15 empty] | 760 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | URIEL | VALENCIA | Foreman | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | R15349 |  |  |  | BADGER2 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 274 |  | 39 |  | 3 | 3 | 313 | BADGER2 | [15 empty] | 313 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | URIEL | VALENCIA | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15349 |  |  |  | WATER TRUCK | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | WATER TRUCK | [15 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | HECTOR | VALDEZ NEVAREZ | Operator II | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 430.5 | 151 | 91 |  | 7 | 7 | 672.5 | [16 empty] | 672.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | HECTOR | VALDEZ NEVAREZ | Operator II | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 227.5 |  | 39 |  | 3 | 3 | 266.5 | [16 empty] | 266.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | HECTOR | VALDEZ NEVAREZ | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | ALEJANDRO | CRUZ CONTRERAS | Laborer | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 329 | 151 | 91 |  | 7 | 7 | 571 | [16 empty] | 571 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | ALEJANDRO | CRUZ CONTRERAS | Laborer | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 173 |  | 39 |  | 3 | 3 | 212 | [16 empty] | 212 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | ASTOLFO | FLORES | Laborer | 7 |  |  | 1 | Tool Trailer | 7 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 329 | 151 | 35 |  | 7 | 7 | 515 | [16 empty] | 515 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | ASTOLFO | FLORES | Laborer | 1 | 2 |  |  | Tool Trailer | 3 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 173 |  | 15 |  | 3 | 3 | 188 | [16 empty] | 188 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | ASTOLFO | FLORES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | IVAN | MADRID | Laborer | 7 |  |  | 1 | 40' Flatbed trailer or equal | 7 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 329 | 151 | 129.5 |  | 7 | 7 | 609.5 | [16 empty] | 609.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | IVAN | MADRID | Laborer | 1 | 2 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 173 |  | 55.5 |  | 3 | 3 | 228.5 | [16 empty] | 228.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | IVAN | MADRID | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | ROBERTO | RODRIGUEZ | Laborer | 7 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 329 | 151 | 322 |  | 7 | 7 | 802 | [16 empty] | 802 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | ROBERTO | RODRIGUEZ | Laborer | 1 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 173 |  | 138 |  | 3 | 3 | 311 | [16 empty] | 311 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | ROBERTO | RODRIGUEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | JOEL | VALDEZ NEVAREZ | Laborer | 7 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 329 | 151 | 633.5 |  | 7 | 7 | 1113.5 | [16 empty] | 1113.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | JOEL | VALDEZ NEVAREZ | Laborer | 1 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 173 |  | 271.5 |  | 3 | 3 | 444.5 | [16 empty] | 444.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | JOEL | VALDEZ NEVAREZ | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | HECTOR | QUINTANA VALDEZ | Laborer | 7 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 329 | 151 | 192.5 |  | 7 | 7 | 672.5 | [16 empty] | 672.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | HECTOR | QUINTANA VALDEZ | Laborer | 1 | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 173 |  | 82.5 |  | 3 | 3 | 255.5 | [16 empty] | 255.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | HECTOR | QUINTANA VALDEZ | Laborer |  | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 126 |  | 55 |  | 2 | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | MATTHEW | SCHMITT | Truck Driver/CDL | 7 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 374.5 | 151 | 112 |  | 7 | 7 | 637.5 | [16 empty] | 637.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | MATTHEW | SCHMITT | Truck Driver/CDL | 1 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 197.5 |  | 48 |  | 3 | 3 | 245.5 | [16 empty] | 245.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | MATTHEW | SCHMITT | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Excavation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | [7 empty] | Hammer Attachment | 7 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | [7 empty] | Hammer Attachment | 3 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44140-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-05 | Had JSA meeting. Hydro vac continued to clean around pipe inside trench box. Once clean up was complete, we checked pipe for defects. NDE layered area for pipe blasting. Sand blasted was completed and NDE began initial assessment | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 19 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 247 |  | 10 | 19 | 1658 | [16 empty] | 1658 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | TOME | KIRKLAND | Superintendent |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1512 | 151 | 156 |  | 12 | 12 | 1819 | [16 empty] | 1819 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 156 |  | 12 | 12 | 1171 | [16 empty] | 1171 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | JASON | JONES | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | JUANITO | RODRIGUEZ | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | SCOTT | MERRY | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15722 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | [7 empty] | Tractor/Semi | 12 | HR | 1376 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | [7 empty] | Tractor/Semi | 10 | HR | R1371 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Matches crew 5 | [7 empty] | Lowboy Trailer | 10 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | KYLE | BONNEAU | Foreman |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | KYLE | Fertilizer | 50 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 500 | 151 | 65 | 0 | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | KYLE | BONNEAU | Foreman |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | KYLE | Seed Mix | 150 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 600 |  | 78 | 0 | 6 | 6 | 678 | [16 empty] | 678 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | JESSE | BERTHIAUME | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JESSE | Straw Bales | 30 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 415 | 151 | 65 | 0 | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | JESSE | BERTHIAUME | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JESSE | Rockshield | 21 | LnFt |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 415 |  | 65 | 0 | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | JACOB | CAPITANO | Laborer |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 | 151 | 65 |  | 5 | 5 | 531 | [16 empty] | 531 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | JACOB | CAPITANO | Laborer |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 |  | 65 |  | 5 | 5 | 380 | [16 empty] | 380 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | BROC | CALIGER | Laborer |  | 5 |  | 1 | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 | 151 | 25 |  | 5 | 5 | 491 | [16 empty] | 491 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | BROC | CALIGER | Laborer |  | 5 |  |  | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 |  | 25 |  | 5 | 5 | 340 | [16 empty] | 340 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | CODY | GAXIOLA | Laborer |  | 5 |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 | 151 | 92.5 |  | 5 | 5 | 558.5 | [16 empty] | 558.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | CODY | GAXIOLA | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 92.5 |  | 5 | 5 | 407.5 | [16 empty] | 407.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | HEATHER | ENGLE | Laborer |  | 5 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 | 151 | 230 |  | 5 | 5 | 696 | [16 empty] | 696 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | HEATHER | ENGLE | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 | 151 | 80 |  | 5 | 5 | 591 | [16 empty] | 591 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 |  | 80 |  | 5 | 5 | 440 | [16 empty] | 440 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | [7 empty] | Padding Bucket | 5 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44141-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | Held JSA meeting. Loaded mats on trailer, hauled mats and trash to yard. Used 21ft rockshield on pipe. Backfilled and started spreading topsoil. Seeded, fertilized and straw site. | [7 empty] | Padding Bucket | 5 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | GERALD | SMITH | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | GERALD | 2888 Coating | 15 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 600 | 151 | 78 | 0 | 6 | 6 | 829 | [16 empty] | 829 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | GERALD | SMITH | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | GERALD | Brushes | 24 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 500 |  | 65 | 0 | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | MICHAEL | RATLIFF | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MICHAELR | Sand | 25 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 415 | 151 | 65 | 0 | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | MICHAEL | RATLIFF | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | OJ | SEALS | Laborer |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 | 151 | 65 |  | 5 | 5 | 531 | [16 empty] | 531 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | OJ | SEALS | Laborer |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 |  | 65 |  | 5 | 5 | 380 | [16 empty] | 380 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | RICHARD | ADKINS | Laborer |  | 5 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 | 151 | 230 |  | 5 | 5 | 696 | [16 empty] | 696 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | RICHARD | ADKINS | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | BARRETT | WISE | Laborer |  | 5 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858B | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 315 | 151 | 137.5 |  | 5 | 5 | 603.5 | [16 empty] | 603.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | BARRETT | WISE | Laborer |  | 5 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858B | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 315 |  | 137.5 |  | 5 | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | DAIVD | RATLIFF | Laborer |  | 5 |  | 1 | Sandblaster & Safety Equipment (Single Nozzle) | 5 | HR | RSPM923 | [7 empty] | 47 | 63 | 0 | 151 | 23.5 |  | 315 | 151 | 117.5 |  | 5 | 5 | 583.5 | [16 empty] | 583.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Recoat | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | DAIVD | RATLIFF | Laborer |  | 5 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 315 |  |  |  | 5 |  | 315 | [16 empty] | 315 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-10008649-44141-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-06 | Had to reblast pipe in places, mills too thick. Recoat | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | CALEB | HOLTON | Foreman |  | 13 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1300 | 151 | 169 |  | 13 | 13 | 1620 | [16 empty] | 1620 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | THOMAS | FRANKLIN | Operator II |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 996 | 151 | 156 |  | 12 | 12 | 1303 | [16 empty] | 1303 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | MICHAEL | ANISZEWSKI | Laborer |  | 13 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 819 | 151 | 169 |  | 13 | 13 | 1139 | [16 empty] | 1139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | BOLDBAUTOR | ZORIGT | Laborer |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 756 | 151 | 156 |  | 12 | 12 | 1063 | [16 empty] | 1063 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | JORDAN | WIGGINS | Laborer |  | 13 |  | 1 | Tool Trailer | 12 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 819 | 151 | 60 |  | 13 | 12 | 1030 | [16 empty] | 1030 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | TANNER | BRITT | Laborer |  | 12 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 756 | 151 | 222 |  | 12 | 12 | 1129 | [16 empty] | 1129 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | ALDO | REYNA | Truck Driver/CDL |  | 12 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 864 | 151 | 192 |  | 12 | 12 | 1207 | [16 empty] | 1207 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 552 |  |  | 12 | 552 | [16 empty] | 552 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 12 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 1086 |  |  | 12 | 1086 | [16 empty] | 1086 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 12 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 330 |  |  | 12 | 330 | [16 empty] | 330 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | [7 empty] | Light Tower 6000 Watt | 12 | HR | RLP5 | [11 empty] | 13 |  |  |  | 156 |  |  | 12 | 156 | [16 empty] | 156 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | [7 empty] | Hammer Attachment | 12 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | [7 empty] | Padding Bucket | 12 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-57880-44141-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | Held JSA meeting. Pulled out trench box and started backfilling. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 12 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 294 |  |  | 12 | 294 | [16 empty] | 294 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | BARKLEY | BROWN | Foreman |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Mats | 36 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 | 151 | 39 | 0 | 3 | 3 | 490 | [16 empty] | 490 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | BARKLEY | BROWN | Foreman |  | 11 |  |  | Pickup-F150 or F250 or equal | 11 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1100 |  | 143 |  | 11 | 11 | 1243 | [16 empty] | 1243 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | JOSHUA | MENDARIES | Operator II |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 | 151 | 39 |  | 3 | 3 | 439 | [16 empty] | 439 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | JOSHUA | MENDARIES | Operator II |  | 10 |  |  | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 |  | 130 |  | 10 | 10 | 960 | [16 empty] | 960 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | WAYLON | GREEN | Laborer |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 | 151 | 39 |  | 3 | 3 | 379 | [16 empty] | 379 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | WAYLON | GREEN | Laborer |  | 11 |  |  | Pickup-F150 or F250 or equal | 11 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 693 |  | 143 |  | 11 | 11 | 836 | [16 empty] | 836 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | JOSE | VALLES | Laborer |  | 3 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 189 | 151 |  |  | 3 |  | 340 | [16 empty] | 340 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | JOSE | VALLES | Laborer |  | 10 |  |  | Water Pump (3") | 10 | HR | 3INP6 | [7 empty] | 47 | 63 | 0 | 151 | 12 |  | 630 |  | 120 |  | 10 | 10 | 750 | [16 empty] | 750 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | REYMUNDO | REYES | Laborer |  | 3 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 189 | 151 |  |  | 3 |  | 340 | [16 empty] | 340 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | REYMUNDO | REYES | Laborer |  | 10 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 630 |  |  |  | 10 |  | 630 | [16 empty] | 630 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | MARCELO | GOMEZ | Laborer |  | 3 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 189 | 151 |  |  | 3 |  | 340 | [16 empty] | 340 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | MARCELO | GOMEZ | Laborer |  | 10 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 630 |  |  |  | 10 |  | 630 | [16 empty] | 630 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Mobilization | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | EFREM | LEE | Truck Driver/CDL |  | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 | 151 | 48 |  | 3 | 3 | 415 | [16 empty] | 415 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | MOB from Seymour IN to Gas City IN. Met with inspector. Started cleaning out hydro pit. X-ray showed at 1pm. | EFREM | LEE | Truck Driver/CDL |  | 10 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 |  | 160 |  | 10 | 10 | 880 | [16 empty] | 880 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | URIEL | VALENCIA | Foreman |  | 8 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 800 | 151 | 104 |  | 8 | 8 | 1055 | [16 empty] | 1055 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | HECTOR | VALDEZ NEVAREZ | Operator II |  | 8 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 664 | 151 | 104 |  | 8 | 8 | 919 | [16 empty] | 919 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 8 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 504 | 151 | 104 |  | 8 | 8 | 759 | [16 empty] | 759 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | ASTOLFO | FLORES | Laborer |  | 8 |  | 1 | Tool Trailer | 10 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 504 | 151 | 50 |  | 8 | 10 | 705 | [16 empty] | 705 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | IVAN | MADRID | Laborer |  | 8 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 504 | 151 | 185 |  | 8 | 10 | 840 | [16 empty] | 840 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | ROBERTO | RODRIGUEZ | Laborer |  | 8 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 504 | 151 | 460 |  | 8 | 10 | 1115 | [16 empty] | 1115 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | JOEL | VALDEZ NEVAREZ | Laborer |  | 8 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 504 | 151 | 905 |  | 8 | 10 | 1560 | [16 empty] | 1560 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | HECTOR | QUINTANA VALDEZ | Laborer |  | 8 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 504 | 151 | 275 |  | 8 | 10 | 930 | [16 empty] | 930 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 8 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 576 | 151 | 128 |  | 8 | 8 | 855 | [16 empty] | 855 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB7 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | [7 empty] | Hammer Attachment | 10 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-110-44141-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-06 | Held JSA meeting. Waited on X-Ray until 1pm, sent to engineer, waiting on repair decision. | [7 empty] | Padding Bucket | 10 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | GARRETT | DICKSON | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 | 151 | 26 |  | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | SHAWN | ROSE | Operator II |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 | 151 | 26 |  | 2 | 2 | 343 | [16 empty] | 343 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | GAGE | BURKS | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | ZACHARY | POWDERS | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | COLTON | ROBERTS | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | MICHEAL | TATUM | Laborer |  | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 | 151 | 181 |  | 2 | 2 | 458 | [16 empty] | 458 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | DANIEL | MARTIN | Laborer |  | 2 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 126 | 151 | 55 |  | 2 | 2 | 332 | [16 empty] | 332 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 151 | 32 |  | 2 | 2 | 327 | [16 empty] | 327 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-33820-44141-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-06 | Demob from site. Loaded blast media from sites and took to French Lick Station | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | GARRETT | DICKSON | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | SHAWN | ROSE | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | SHAWN | ROSE | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | GAGE | BURKS | Laborer |  | 5 |  |  | Tool Trailer | 5 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 |  | 25 |  | 5 | 5 | 340 | [16 empty] | 340 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | GAGE | BURKS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | ZACHARY | POWDERS | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 92.5 |  | 5 | 5 | 407.5 | [16 empty] | 407.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | ZACHARY | POWDERS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | COLTON | ROBERTS | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | COLTON | ROBERTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | MICHAEL | TATUM | Laborer |  | 5 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 |  | 452.5 |  | 5 | 5 | 767.5 | [16 empty] | 767.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | MICHAEL | TATUM | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | DANIEL | MARTIN | Laborer |  | 5 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 315 |  | 137.5 |  | 5 | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | DANIEL | MARTIN | Laborer |  | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 126 |  | 55 |  | 2 | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | IAIN | ALLRED | Truck Driver/CDL |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 |  | 80 |  | 5 | 5 | 440 | [16 empty] | 440 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP8 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | [7 empty] | Hammer Attachment | 5 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-43000-44141-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-06 | MOB into site. Completely backfilled and cleaned up site. Demob to 1491 | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | SHAWN | ROSE | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | GAGE | BURKS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | ZACHARY | POWDERS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 18.5 |  | 2 | 1 | 144.5 | [16 empty] | 144.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | MICHEAL | TATUM | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | DANIEL | MARTIN | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Site Prep | 3500028468-58100-44141-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-06 | Prepped site for backfill | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44141-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-06 | Spread topsoil | DONALD | TIGUE | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | DONALDT | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44141-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-06 | Spread topsoil | DAVID | LOPEZ | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX10563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | RENE | CASAREZ | Foreman |  | 7 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | RENE | Seed Mix | 100 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 700 | 151 | 91 | 0 | 7 | 7 | 942 | [16 empty] | 942 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | RENE | CASAREZ | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | RENE | Straw Bales | 7 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | DONALD | TIGUE | Operator II |  | 7 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | DONALDT | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 581 | 151 | 91 |  | 7 | 7 | 823 | [16 empty] | 823 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | DAVID | LOPEZ | Laborer |  | 7 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | RC23860 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 441 | 151 | 91 |  | 7 | 7 | 683 | [16 empty] | 683 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | DEMETRIUS | DOBY | Laborer |  | 7 |  | 1 | Tool Trailer | 10 | HR | UTT9 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 441 | 151 | 50 |  | 7 | 10 | 642 | [16 empty] | 642 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | JOSE | ORTIZ | Laborer |  | 7 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 441 | 151 | 460 |  | 7 | 10 | 1052 | [16 empty] | 1052 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | FERNANDO | GARCIA | Laborer |  | 6 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 378 | 151 |  |  | 6 |  | 529 | [16 empty] | 529 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | FERNANDO | GARCIA | Laborer |  | 4 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 252 |  |  |  | 4 |  | 252 | [16 empty] | 252 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | MARGIL | GARZA | Laborer |  | 6 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 378 | 151 |  |  | 6 |  | 529 | [16 empty] | 529 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | MARGIL | GARZA | Laborer |  | 4 |  |  | Padding Bucket | 10 | HR | RPB19021 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 252 |  | 0 |  | 4 | 10 | 252 | [16 empty] | 252 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Backfill | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | ADDEY | BENNETT | Laborer |  | 8 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX10563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 504 | 151 | 905 |  | 8 | 10 | 1560 | [16 empty] | 1560 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Demobilization | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | ADDEY | BENNETT | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | BRIAN | RANDLE | Truck Driver/CDL |  | 10 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 720 | 151 |  |  | 10 |  | 871 | [16 empty] | 871 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-09 | 2 | BL |  | Clean-up / Remediation | 3500028468-15400-44141-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-06 | Finished seeding between dig 1548/1547. Fixed road with skid steer and spread rock. Padded and backfilled dig. Spread topsoil. Loaded up padding bucket and hauled to yard once finsihed with backfill. | JODY | HASTON | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF5509 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JODY | BROOM | Superintendent |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 630 | 151 | 65 |  | 5 | 5 | 846 | [16 empty] | 846 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JODY | BROOM | Superintendent |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 630 |  | 65 |  | 5 | 5 | 695 | [16 empty] | 695 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | TOME | KIRKLAND | Superintendent |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | TOME | [7 empty] | 105 | 126 | 0 | 151 | 13 |  | 756 | 151 | 78 |  | 6 | 6 | 985 | [16 empty] | 985 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | TOME | KIRKLAND | Superintendent |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 756 |  | 78 |  | 6 | 6 | 834 | [16 empty] | 834 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JAY | MASEY | Quality Assurance Inspector | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 525 | 151 | 65 |  | 5 | 5 | 741 | [16 empty] | 741 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JAY | MASEY | Quality Assurance Inspector | 5 |  |  |  | Pickup-F150 or F250 or equal | 5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 525 |  | 65 |  | 5 | 5 | 590 | [16 empty] | 590 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | MICHAEL | GOSS | Truck Driver/CDL |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 360 | 151 | 65 |  | 5 | 5 | 576 | [16 empty] | 576 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | MICHAEL | GOSS | Truck Driver/CDL |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 360 |  | 65 |  | 5 | 5 | 425 | [16 empty] | 425 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 360 | 151 | 65 |  | 5 | 5 | 576 | [16 empty] | 576 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 360 |  | 65 |  | 5 | 5 | 425 | [16 empty] | 425 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JASON | JONES | Truck Driver/CDL |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 360 | 151 | 65 |  | 5 | 5 | 576 | [16 empty] | 576 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JASON | JONES | Truck Driver/CDL |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 360 |  | 65 |  | 5 | 5 | 425 | [16 empty] | 425 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JUANITO | RODRIGUEZ | Safety Person |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 | 151 | 65 |  | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | JUANITO | RODRIGUEZ | Safety Person |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | SCOTT | MERRY | Safety Person |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 | 151 | 65 |  | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | SCOTT | MERRY | Safety Person |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | DANIEL | YOUNG | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 | 151 | 65 |  | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | DANIEL | YOUNG | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | KIM | FORNALL | Project Coordinator | 5 |  |  | 1 | Tractor/Semi | 5 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 494 | 151 | 210 |  | 5 | 5 | 855 | [16 empty] | 855 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | KIM | FORNALL | Project Coordinator | 5 |  |  |  | Tractor/Semi | 5 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 494 |  | 210 |  | 5 | 5 | 704 | [16 empty] | 704 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Tractor/Semi | 5 | HR | 1376 | [11 empty] | 42 |  |  |  | 210 |  |  | 5 | 210 | [16 empty] | 210 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Tractor/Semi | 5 | HR | 1376 | [11 empty] | 42 |  |  |  | 210 |  |  | 5 | 210 | [16 empty] | 210 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Tractor/Semi | 5 | HR | R1371 | [11 empty] | 42 |  |  |  | 210 |  |  | 5 | 210 | [16 empty] | 210 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Tractor/Semi | 5 | HR | R1371 | [11 empty] | 42 |  |  |  | 210 |  |  | 5 | 210 | [16 empty] | 210 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Lowboy Trailer | 5 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Lowboy Trailer | 5 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Lowboy Trailer | 5 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Lowboy Trailer | 5 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Lowboy Trailer | 5 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Matches crew 4 | [7 empty] | Lowboy Trailer | 5 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44142-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | Harley raked entire site and extra work space. Spread seed, fertilizer and straw. Fixed rock approach, reinstalled pipeline marker. Cleaned site 100% | KYLE | BONNEAU | Foreman |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | Seed Mix | 200 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 1100 | 151 | 143 | 0 | 11 | 11 | 1394 | [16 empty] | 1394 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44142-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | Harley raked entire site and extra work space. Spread seed, fertilizer and straw. Fixed rock approach, reinstalled pipeline marker. Cleaned site 100% | JESSE | BERTHIAUME | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | Fertilizer | 125 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 830 | 151 | 130 | 0 | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44142-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | Harley raked entire site and extra work space. Spread seed, fertilizer and straw. Fixed rock approach, reinstalled pipeline marker. Cleaned site 100% | JACOB | CAPITANO | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | Straw Bales | 53 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 630 | 151 | 130 | 0 | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44142-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | Harley raked entire site and extra work space. Spread seed, fertilizer and straw. Fixed rock approach, reinstalled pipeline marker. Cleaned site 100% | BROC | CALIGER | Laborer |  | 10 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 630 | 151 | 50 |  | 10 | 10 | 831 | [16 empty] | 831 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44142-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | Harley raked entire site and extra work space. Spread seed, fertilizer and straw. Fixed rock approach, reinstalled pipeline marker. Cleaned site 100% | CODY | GAXIOLA | Laborer |  | 10 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 630 | 151 | 185 |  | 10 | 10 | 966 | [16 empty] | 966 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44142-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | Harley raked entire site and extra work space. Spread seed, fertilizer and straw. Fixed rock approach, reinstalled pipeline marker. Cleaned site 100% | HEATHER | ENGLE | Laborer |  | 10 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 630 | 151 | 460 |  | 10 | 10 | 1241 | [16 empty] | 1241 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44142-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | Harley raked entire site and extra work space. Spread seed, fertilizer and straw. Fixed rock approach, reinstalled pipeline marker. Cleaned site 100% | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44142-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | Harley raked entire site and extra work space. Spread seed, fertilizer and straw. Fixed rock approach, reinstalled pipeline marker. Cleaned site 100% | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-28110-44142-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | Harley raked entire site and extra work space. Spread seed, fertilizer and straw. Fixed rock approach, reinstalled pipeline marker. Cleaned site 100% | [7 empty] | Padding Bucket | 10 | HR | RBP2 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | GERALD | SMITH | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | GERALD | Brushes | 6 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 600 | 151 | 78 | 0 | 6 | 6 | 829 | [16 empty] | 829 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | GERALD | SMITH | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | GERALD | Rockshield | 44 | LnFt |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 500 |  | 65 | 0 | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | MICHAEL | RATLIFF | Operator II |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 498 | 151 | 78 |  | 6 | 6 | 727 | [16 empty] | 727 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | MICHAEL | RATLIFF | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | OJ | SEALS | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | OJ | SEALS | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | RICHARD | ADKINS | Laborer |  | 6 |  | 1 | Tool Trailer | 6 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 | 151 | 30 |  | 6 | 6 | 559 | [16 empty] | 559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | RICHARD | ADKINS | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | BARRETT | WISE | Laborer |  | 6 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 378 | 151 | 276 |  | 6 | 6 | 805 | [16 empty] | 805 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | BARRETT | WISE | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | DAVID | RATLIFF | Laborer |  | 6 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 378 | 151 | 543 |  | 6 | 6 | 1072 | [16 empty] | 1072 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | DAVID | RATLIFF | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 96 |  | 10 | 6 | 967 | [16 empty] | 967 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | [7 empty] | 40' Flatbed trailer or equal | 4 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 74 |  |  | 4 | 74 | [16 empty] | 74 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-10008649-44142-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | Jeeped and repaired coating. Put on 44ft of rockshield, started backfilling | [7 empty] | Pipe Jeep (includes spring) | 1 | HR | PJP4 | [11 empty] | 7 |  |  |  | 7 |  |  | 1 | 7 | [16 empty] | 7 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | CALEB | HOLTON | Foreman |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | CALEB | Curlex | 4480 | Sq. ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 1100 | 151 | 143 | 0 | 11 | 11 | 1394 | [16 empty] | 1394 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | MATTHEW | LINDLEY | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEWL | Netted Straw | 700 | Sq yd |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 | 0 | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | THOMAS | FRANKLIN | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | MICHAEL | ANISZEWSKI | Laborer |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 693 | 151 | 143 |  | 11 | 11 | 987 | [16 empty] | 987 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | BOLDBAUTOR | ZORIGT | Laborer |  | 12 |  | 1 | Tool Trailer | 12 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 756 | 151 | 60 |  | 12 | 12 | 967 | [16 empty] | 967 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | JORDAN | WIGGINS | Laborer |  | 13 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 819 | 151 | 222 |  | 13 | 12 | 1192 | [16 empty] | 1192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | TANNER | BRITT | Laborer |  | 12 |  | 1 | Cat 262C Skid Steer/ASV (cap 2351 to 2700 lbs) or equal* | 12 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 29.5 |  | 756 | 151 | 354 |  | 12 | 12 | 1261 | [16 empty] | 1261 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | ALDO | REYNA | Truck Driver/CDL |  | 12 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 864 | 151 | 192 |  | 12 | 12 | 1207 | [16 empty] | 1207 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 12 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 1086 |  |  | 12 | 1086 | [16 empty] | 1086 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 12 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 330 |  |  | 12 | 330 | [16 empty] | 330 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | [7 empty] | Hammer Attachment | 12 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | [7 empty] | Padding Bucket | 12 | HR | RBP5 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-57880-44142-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | Held JHA meeting. Rolled out curlex, mopped back topsoil and cleaned up site. | [7 empty] | Light Tower 6000 Watt | 12 | HR | RLP5 | [11 empty] | 13 |  |  |  | 156 |  |  | 12 | 156 | [16 empty] | 156 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | BARKLEY | BROWN | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Sand | 13 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 | 151 | 26 | 0 | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | 2888 Coating | 25 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | BARKLEY | BROWN | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | Brushes | 34 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 400 |  | 52 | 0 | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | BARKLEY | BROWN | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | JOSHUA | MENDARIES | Operator II |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 | 151 | 26 |  | 2 | 2 | 343 | [16 empty] | 343 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | JOSHUA | MENDARIES | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | JOSHUA | MENDARIES | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | JOSHUA | MENDARIES | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | WAYLON | GREEN | Laborer |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 | 151 | 26 |  | 2 | 2 | 303 | [16 empty] | 303 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | WAYLON | GREEN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | WAYLON | GREEN | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | JOSE | VALLES | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | JOSE | VALLES | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | REYMUNDO | REYES | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | REYMUNDO | REYES | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | REYMUNDO | REYES | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | REYMUNDO | REYES | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | MARCELO | GOMEZ | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | MARCELO | GOMEZ | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | EFREM | LEE | Truck Driver/CDL |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 151 | 32 |  | 2 | 2 | 327 | [16 empty] | 327 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | EFREM | LEE | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Initial Coating Inspection | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Recoat | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Pipe Preparation | 3500028468-110-44142-rev1 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-07 | Pumped water. Sandblasted pipe, NDE assessed pipe. Unloaded extra excavator per inspector to remove trench box. Waited for coating to cure | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | GARRETT | DICKSON | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 | 151 | 26 |  | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | SHAWN | ROSE | Operator II |  | 1 |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 | 151 | 13 |  | 1 | 1 | 247 | [16 empty] | 247 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | GAGE | BURKS | Laborer |  | 1 |  | 1 | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 | 151 | 5 |  | 1 | 1 | 219 | [16 empty] | 219 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | ZACHARY | POWDERS | Laborer |  | 1 |  | 1 | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 | 151 | 18.5 |  | 1 | 1 | 232.5 | [16 empty] | 232.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | COLTON | ROBERTS | Laborer |  | 1 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 | 151 | 46 |  | 1 | 1 | 260 | [16 empty] | 260 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | MICHEAL | TATUM | Laborer |  | 1 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 | 151 | 90.5 |  | 1 | 1 | 304.5 | [16 empty] | 304.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | DANIEL | MARTIN | Laborer |  | 1 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 | 151 | 27.5 |  | 1 | 1 | 241.5 | [16 empty] | 241.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 | 151 | 16 |  | 1 | 1 | 239 | [16 empty] | 239 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Demobilization | 3500028468-35680-44142-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | Hauled equipment to 1491. Driver loaded blast media and hauled to French Lick station. | [7 empty] | Padding Bucket | 1 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | GARRETT | DICKSON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | GARRETT | DICKSON | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | SHAWN | ROSE | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | SHAWN | ROSE | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | SHAWN | ROSE | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | SHAWNR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | ZACHARY | POWDERS | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | ZACHARY | POWDERS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | ZACHARY | POWDERS | Laborer |  | 5 |  |  | Tool Trailer | 5 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 |  | 25 |  | 5 | 5 | 340 | [16 empty] | 340 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | GAGE | BURKS | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | GAGE | BURKS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | GAGE | BURKS | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 92.5 |  | 5 | 5 | 407.5 | [16 empty] | 407.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | COLTON | ROBERTS | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | COLTON | ROBERTS | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | MICHEAL | TATUM | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | MICHEAL | TATUM | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | MICHEAL | TATUM | Laborer |  | 5 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 |  | 452.5 |  | 5 | 5 | 767.5 | [16 empty] | 767.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | DANIEL | MARTIN | Laborer |  | 3 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 189 |  | 82.5 |  | 3 | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | DANIEL | MARTIN | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | DANIEL | MARTIN | Laborer |  | 5 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 315 |  | 137.5 |  | 5 | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | IAIN | ALLRED | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19109 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19109 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | IAIN | ALLRED | Truck Driver/CDL |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19109 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 |  | 80 |  | 5 | 5 | 440 | [16 empty] | 440 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP8 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP8 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Hammer Attachment | 3 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Hammer Attachment | 5 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Mobilization | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Padding Bucket | 3 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Padding Bucket | 1 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Backfill | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Padding Bucket | 5 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Post Repair Assessment | 3500028468-58100-44142-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | Arrived on location and crew jeeped pipe. Backfilled 100% on site. Equipment is loaded and ready for demob | [7 empty] | Pipe Jeep (includes spring) | 1 | HR | PJP8 | [11 empty] | 7 |  |  |  | 7 |  |  | 1 | 7 | [16 empty] | 7 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | RENE | CASAREZ | Foreman |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | RENE | Seed Mix | 200 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 1100 | 151 | 143 | 0 | 11 | 11 | 1394 | [16 empty] | 1394 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | DONALD | TIGUE | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DONALD | Straw Bales | 10 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 830 | 151 | 130 | 0 | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | DAVID | LOPEZ | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RC23860 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | FERNANDO | GARCIA | Laborer |  | 10 |  | 1 | Tool Trailer | 10 | HR | UTT9 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 630 | 151 | 50 |  | 10 | 10 | 831 | [16 empty] | 831 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | ADDEY | BENNETT | Laborer |  | 11 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT9 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 693 | 151 | 185 |  | 11 | 10 | 1029 | [16 empty] | 1029 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | MARGIL | GARZA | Laborer |  | 10 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS11304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 630 | 151 | 460 |  | 10 | 10 | 1241 | [16 empty] | 1241 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | DEMETRIUS | DOBY | Laborer |  | 10 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 630 | 151 |  |  | 10 |  | 781 | [16 empty] | 781 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | JOSE | ORTIZ | Laborer |  | 10 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 630 | 151 |  |  | 10 |  | 781 | [16 empty] | 781 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | BRIAN | RANDLE | Truck Driver/CDL |  | 10 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 720 | 151 |  |  | 10 |  | 871 | [16 empty] | 871 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-14960-44142-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-07 | Finished fixing road and spreading gravel. Removed mat bridge and hauled to load onto gooseneck trailer. Unloaded mats out where they could be picked up at a later time. Continued site restoration. Spread seed and straw. | JODY | HASTON | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF5509 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | BARKLEY | BROWN | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | JOSHUA | MENDARIES | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | WAYLON | GREEN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | JOSE | VALLES | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | REYMUNDO | REYES | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | MARCELO | GOMEZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP6 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-10 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44143-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-08 | Removed water from hydro pit. Top soil will be brought in tomorrow to mix with solids that in the pit. As of now, the inspector said the person in charge on environmental at this station needs top soil mixed in with soilds and then spread on top of the ground. | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | JASON | JONES | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 12 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 504 |  | 10 | 12 | 1643 | [16 empty] | 1643 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | [7 empty] | Tractor/Semi | 12 | HR | 1376 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | [7 empty] | Tractor/Semi | 12 | HR | R1371 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | [7 empty] | Lowboy Trailer | 12 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | [7 empty] | Lowboy Trailer | 12 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Matches crew 2 | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Had JHA meeting. Loaded excavator to send to TN. Truck driver to get 120 straw bales and seed. Picked up trash. Harley raked ROW, spread seed, fertilizer and straw. | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | Seed Mix | 200 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 892 | 151 | 143 | 0 | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Had JHA meeting. Loaded excavator to send to TN. Truck driver to get 120 straw bales and seed. Picked up trash. Harley raked ROW, spread seed, fertilizer and straw. | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | Fertilizer | 100 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 658 | 151 | 130 | 0 | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Had JHA meeting. Loaded excavator to send to TN. Truck driver to get 120 straw bales and seed. Picked up trash. Harley raked ROW, spread seed, fertilizer and straw. | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | Straw Bales | 60 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 502 | 151 | 130 | 0 | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Had JHA meeting. Loaded excavator to send to TN. Truck driver to get 120 straw bales and seed. Picked up trash. Harley raked ROW, spread seed, fertilizer and straw. | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Had JHA meeting. Loaded excavator to send to TN. Truck driver to get 120 straw bales and seed. Picked up trash. Harley raked ROW, spread seed, fertilizer and straw. | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Had JHA meeting. Loaded excavator to send to TN. Truck driver to get 120 straw bales and seed. Picked up trash. Harley raked ROW, spread seed, fertilizer and straw. | HEATHER | ENGLE | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Had JHA meeting. Loaded excavator to send to TN. Truck driver to get 120 straw bales and seed. Picked up trash. Harley raked ROW, spread seed, fertilizer and straw. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Had JHA meeting. Loaded excavator to send to TN. Truck driver to get 120 straw bales and seed. Picked up trash. Harley raked ROW, spread seed, fertilizer and straw. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-29300-44144-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | Had JHA meeting. Loaded excavator to send to TN. Truck driver to get 120 straw bales and seed. Picked up trash. Harley raked ROW, spread seed, fertilizer and straw. | [7 empty] | Padding Bucket | 10 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | GERALD | SMITH | Foreman | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 348 |  | 52 |  | 4 | 4 | 400 | [16 empty] | 400 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | GERALD | SMITH | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | MICHAEL | RATLIFF | Operator II | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 267.5 |  | 52 |  | 4 | 4 | 319.5 | [16 empty] | 319.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | MICHAEL | RATLIFF | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | OJ | SEALS | Laborer | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 204 |  | 52 |  | 4 | 4 | 256 | [16 empty] | 256 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | OJ | SEALS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | RICHARD | ADKINS | Laborer | 3 | 1 |  |  | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 204 |  | 20 |  | 4 | 4 | 224 | [16 empty] | 224 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | RICHARD | ADKINS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | BARRETT | WISE | Laborer | 3 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 204 |  | 184 |  | 4 | 4 | 388 | [16 empty] | 388 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | BARRETT | WISE | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | STEVE | CLARK | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-15400-44144-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | Picked up (18) mats on site and hauled to yard. Finished clean up on travel lane out | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | GERALD | SMITH | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | GERALD | SMITH | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | MICHAEL | RATLIFF | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | MICHAEL | RATLIFF | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | OJ | SEALS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | RICHARD | ADKINS | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | RICHARD | ADKINS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | BARRETT | WISE | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | BARRETT | WISE | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | STEVE | CLARK | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44144-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-09 | Put topsoil back and cleaned site. Demob from site. | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | CALEB | HOLTON | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | CALEB | HOLTON | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | SHAWN | ROSE | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | SHAWN | ROSE | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | MICHAEL | ANISZEWSKI | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | MICHAEL | ANISZEWSKI | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | BOLDBAUTOR | ZORIGT | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | BOLDBAUTOR | ZORIGT | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | JORDAN | WIGGINS | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | JORDAN | WIGGINS | Laborer |  | 4 |  |  | Tool Trailer | 3 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 15 |  | 4 | 3 | 267 | [16 empty] | 267 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | TANNER | BRITT | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | TANNER | BRITT | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | ALDO | REYNA | Truck Driver/CDL | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8664 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 160.5 |  | 138 |  | 3 | 3 | 298.5 | [16 empty] | 298.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | ALDO | REYNA | Truck Driver/CDL |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8664 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 216 |  | 138 |  | 3 | 3 | 354 | [16 empty] | 354 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | DANIEL | MARTIN | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | DANIEL | MARTIN | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | MICHEAL | TATUM | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | MICHEAL | TATUM | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | MATTHEW | LINDLEY | Foreman | 3 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC4049 | [7 empty] | 74 | 100 | 0 | 151 | 27.5 |  | 222 |  | 82.5 |  | 3 | 3 | 304.5 | [16 empty] | 304.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | MATTHEW | LINDLEY | Foreman |  | 4 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC4049 | [7 empty] | 74 | 100 | 0 | 151 | 27.5 |  | 400 |  | 82.5 |  | 4 | 3 | 482.5 | [16 empty] | 482.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | MATTHEW | SCHMITT | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 48 |  | 6 | 3 | 520 | [16 empty] | 520 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | MATTHEW | SCHMITT | Truck Driver/CDL | 2 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 323 |  | 48 |  | 5 | 3 | 371 | [16 empty] | 371 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | [7 empty] | Hammer Attachment | 3 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Foreman held meeting to know what was completed on site. Crew pulled trench box and started backfilling, mixing topsoil in the mud pit behind station. | [7 empty] | Hammer Attachment | 3 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | CALEB | HOLTON | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | SHAWN | ROSE | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | MICHAEL | ANISZEWSKI | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | BOLDBAUTOR | ZORIGT | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | JORDAN | WIGGINS | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | TANNER | BRITT | Laborer | 5 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 235 | 151 | 137.5 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | ALDO | RENYA | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | DANIEL | MARTIN | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | MICHEAL | TATUM | Laborer | 5 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 235 | 151 |  |  | 5 |  | 386 | [16 empty] | 386 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-57880-44144-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-09 | Held JHA meeting. Loaded up tool trailer and sandblaster to demob to 0872. | MATTHEW | LINDLEY | Foreman | 5 |  |  | 1 | [11 empty] | 74 | 100 | 0 | 151 |  |  | 370 | 151 |  |  | 5 |  | 521 | [16 empty] | 521 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | BARKLEY | BROWN | Foreman | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | 2888 Coating | 1 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 | 151 | 13 | 0 | 1 | 1 | 238 | [16 empty] | 238 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | BARKLEY | BROWN | Foreman | 7 | 3 |  |  | Pickup-F150 or F250 or equal | 10 | HR | BARKLEY | Brushes | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 818 |  | 130 | 0 | 10 | 10 | 948 | [16 empty] | 948 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | JOSHUA | MENDARIES | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 | 151 | 13 |  | 1 | 1 | 225.5 | [16 empty] | 225.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | JOSHUA | MENDARIES | Operator II | 7 | 2 |  |  | Pickup-F150 or F250 or equal | 9 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 596.5 |  | 117 |  | 9 | 9 | 713.5 | [16 empty] | 713.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | WAYLON | GREEN | Laborer | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | THOMASF | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 | 151 | 13 |  | 1 | 1 | 211 | [16 empty] | 211 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | WAYLON | GREEN | Laborer | 7 | 2 |  |  | Pickup-F150 or F250 or equal | 9 | HR | THOMASF | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 455 |  | 117 |  | 9 | 9 | 572 | [16 empty] | 572 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | JOSE | VALLES | Laborer | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 | 151 | 13 |  | 1 | 1 | 211 | [16 empty] | 211 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | JOSE | VALLES | Laborer | 7 | 2 |  |  | Pickup-F150 or F250 or equal | 9 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 455 |  | 117 |  | 9 | 9 | 572 | [16 empty] | 572 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | REYMUNDO | REYES | Laborer | 1 |  |  | 1 | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 | 151 | 5 |  | 1 | 1 | 203 | [16 empty] | 203 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | REYMUNDO | REYES | Laborer | 7 | 2 |  |  | Tool Trailer | 9 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 455 |  | 45 |  | 9 | 9 | 500 | [16 empty] | 500 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | MARCELO | GOMEZ | Laborer | 1 |  |  | 1 | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 | 151 | 18.5 |  | 1 | 1 | 216.5 | [16 empty] | 216.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | MARCELO | GOMEZ | Laborer | 7 | 2 |  |  | 40' Flatbed trailer or equal | 9 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 455 |  | 166.5 |  | 9 | 9 | 621.5 | [16 empty] | 621.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | EFREM | LEE | Truck Driver/CDL | 1 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 | 151 | 16 |  | 1 | 1 | 220.5 | [16 empty] | 220.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | EFREM | LEE | Truck Driver/CDL | 7 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 9 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 518.5 |  | 144 |  | 9 | 9 | 662.5 | [16 empty] | 662.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | ZACHARY | POWDERS | Laborer | 1 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 | 151 | 90.5 |  | 1 | 1 | 288.5 | [16 empty] | 288.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | ZACHARY | POWDERS | Laborer | 7 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 9 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 455 |  | 814.5 |  | 9 | 9 | 1269.5 | [16 empty] | 1269.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | COLTON | ROBERTS | Laborer | 1 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 | 151 | 90.5 |  | 1 | 1 | 288.5 | [16 empty] | 288.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | COLTON | ROBERTS | Laborer | 7 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 9 | HR | REX10278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 455 |  | 814.5 |  | 9 | 9 | 1269.5 | [16 empty] | 1269.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | GAGE | BURKS | Laborer | 1 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 | 151 | 27.5 |  | 1 | 1 | 225.5 | [16 empty] | 225.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | GAGE | BURKS | Laborer | 7 | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 9 | HR | RAC0858A | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 455 |  | 247.5 |  | 9 | 9 | 702.5 | [16 empty] | 702.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 | 151 | 16 |  | 1 | 1 | 220.5 | [16 empty] | 220.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | IAIN | ALLRED | Truck Driver/CDL | 7 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 9 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 518.5 |  | 144 |  | 9 | 9 | 662.5 | [16 empty] | 662.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Post Repair Assessment | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | THOMAS | FRANKLIN | Operator II | 1 |  |  | 1 | Hammer Attachment | 1 | HR | RHA1055 | [7 empty] | 61.5 | 83 | 0 | 151 | 0 |  | 61.5 | 151 | 0 |  | 1 | 1 | 212.5 | [16 empty] | 212.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-110-44144-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | Jeeped pipe. Fixed holidays. Waited on coating to dry. Cleaned out bellhole, pulled out trench box, backfilled and started cleaning hydro pit. Had 6 dump trucks that delivered 120 tons of topsoil for hydro pit and to and to finish back filling bellhole. | THOMAS | FRANKLIN | Operator II | 7 | 2 |  |  | Hammer Attachment | 9 | HR | RHA1055 | [7 empty] | 61.5 | 83 | 0 | 151 | 0 |  | 596.5 |  | 0 |  | 9 | 9 | 596.5 | [16 empty] | 596.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | JASON | JONES | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 12 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 504 |  | 10 | 12 | 1643 | [16 empty] | 1643 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | [7 empty] | Tractor/Semi | 12 | HR | 1376 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | [7 empty] | Tractor/Semi | 10 | HR | R1371 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | [7 empty] | Lowboy Trailer | 10 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Matches crew 5 | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44145-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-10 | Held JHA meeting. Harley raked site, seed, fertilized and straw site, Installed cattle gate (3 6x6 posts, 1 4x6 post, 1 12ft cattle gate) and mended fence. Removed everything from site to make 100% complete. Finished mulching dig 1553 and harley raked 1778. | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | KYLE | Seed Mix | 200 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 892 | 151 | 130 | 0 | 11 | 10 | 1173 | [16 empty] | 1173 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44145-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-10 | Held JHA meeting. Harley raked site, seed, fertilized and straw site, Installed cattle gate (3 6x6 posts, 1 4x6 post, 1 12ft cattle gate) and mended fence. Removed everything from site to make 100% complete. Finished mulching dig 1553 and harley raked 1778. | JESSE | BERTHAIUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | Fertilizer | 100 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 658 | 151 | 130 | 0 | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44145-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-10 | Held JHA meeting. Harley raked site, seed, fertilized and straw site, Installed cattle gate (3 6x6 posts, 1 4x6 post, 1 12ft cattle gate) and mended fence. Removed everything from site to make 100% complete. Finished mulching dig 1553 and harley raked 1778. | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | Straw Bales | 60 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 502 | 151 | 130 | 0 | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44145-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-10 | Held JHA meeting. Harley raked site, seed, fertilized and straw site, Installed cattle gate (3 6x6 posts, 1 4x6 post, 1 12ft cattle gate) and mended fence. Removed everything from site to make 100% complete. Finished mulching dig 1553 and harley raked 1778. | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44145-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-10 | Held JHA meeting. Harley raked site, seed, fertilized and straw site, Installed cattle gate (3 6x6 posts, 1 4x6 post, 1 12ft cattle gate) and mended fence. Removed everything from site to make 100% complete. Finished mulching dig 1553 and harley raked 1778. | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44145-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-10 | Held JHA meeting. Harley raked site, seed, fertilized and straw site, Installed cattle gate (3 6x6 posts, 1 4x6 post, 1 12ft cattle gate) and mended fence. Removed everything from site to make 100% complete. Finished mulching dig 1553 and harley raked 1778. | HEATHER | ENGLE | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44145-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-10 | Held JHA meeting. Harley raked site, seed, fertilized and straw site, Installed cattle gate (3 6x6 posts, 1 4x6 post, 1 12ft cattle gate) and mended fence. Removed everything from site to make 100% complete. Finished mulching dig 1553 and harley raked 1778. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-31230-44145-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-10 | Held JHA meeting. Harley raked site, seed, fertilized and straw site, Installed cattle gate (3 6x6 posts, 1 4x6 post, 1 12ft cattle gate) and mended fence. Removed everything from site to make 100% complete. Finished mulching dig 1553 and harley raked 1778. | [7 empty] | Cat 328 LCR/330 Excavator or equal* (65,001 to 75,000 lbs) | 10 | HR | REX10278 | [11 empty] | 145 |  |  |  | 1450 |  |  | 10 | 1450 | [16 empty] | 1450 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | GERALD | SMITH | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | GERALD | Seed Mix | 20 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 444 | 151 | 78 | 0 | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | GERALD | SMITH | Foreman | 2 | 4 |  |  | Pickup-F150 or F250 or equal | 6 | HR | GERALD | Straw Bales | 25 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 548 |  | 78 | 0 | 6 | 6 | 626 | [16 empty] | 626 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | MICHAEL | RATLIFF | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | MICHAEL | RATLIFF | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | OJ | SEALS | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | OJ | SEALS | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | RICHARD | ADKINS | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | RICHARD | ADKINS | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | BARRETT | WISE | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 230 |  | 5 | 5 | 616 | [16 empty] | 616 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | BARRETT | WISE | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 230 |  | 5 | 5 | 497 | [16 empty] | 497 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | STEVE | CLARK | Truck Driver/CDL | 8 | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 860 | 151 | 160 |  | 14 | 10 | 1171 | [16 empty] | 1171 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-10008649-44145-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-10 | Finished clean up on site. Demob equipment | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | CALEB | HOLTON | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | CALEB | Seed Mix | 20 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 992 | 151 | 156 | 0 | 12 | 12 | 1299 | [16 empty] | 1299 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | SHAWN | ROSE | Operator II | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | MATTHEW | Straw Bales | 4 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 741 | 151 | 143 | 0 | 11 | 11 | 1035 | [16 empty] | 1035 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | MICHAEL | ANISZEWSKI | Laborer | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 628 | 151 | 156 |  | 12 | 12 | 935 | [16 empty] | 935 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | BOLDBAUTOR | ZORIGT | Laborer | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 565 | 151 | 156 |  | 11 | 12 | 872 | [16 empty] | 872 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | JORDAN | WIGGINS | Laborer | 8 | 4 |  | 1 | Tool Trailer | 11 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 55 |  | 12 | 11 | 834 | [16 empty] | 834 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | TANNER | BRITT | Laborer | 8 | 3 |  | 1 | 40' Flatbed trailer or equal | 11 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 565 | 151 | 203.5 |  | 11 | 11 | 919.5 | [16 empty] | 919.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 192 |  | 12 | 12 | 1059 | [16 empty] | 1059 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | DANIEL | MARTIN | Laborer | 8 | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 11 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 565 | 151 | 506 |  | 11 | 11 | 1222 | [16 empty] | 1222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | MICHEAL | TATUM | Laborer | 8 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 11 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 565 | 151 | 995.5 |  | 11 | 11 | 1711.5 | [16 empty] | 1711.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | MATTHEW | LINDLEY | Foreman | 8 | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 11 | HR | REX4155 | [7 empty] | 74 | 100 | 0 | 151 | 90.5 |  | 992 | 151 | 995.5 |  | 12 | 11 | 2138.5 | [16 empty] | 2138.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 11 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 302.5 |  |  | 11 | 302.5 | [16 empty] | 302.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44145-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | Held JHA meeting. Started cleaning and spreading topsoil. Had (3) loads of dirt hauled in. Seeded and spread straw. Gathered mats from mud pit, mixed dry dirt in with mud and spread it out. | [7 empty] | Hammer Attachment | 11 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | BARKLEY | BROWN | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | BARKLEY | Mats | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | BARKLEY | BROWN | Foreman | 3 | 3 |  |  | Pickup-F150 or F250 or equal | 6 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 522 |  | 78 |  | 6 | 6 | 600 | [16 empty] | 600 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | JOSHUA | MENDARIES | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | JOSHUA | MENDARIES | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | WAYLON | GREEN | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | WAYLON | GREEN | Laborer | 3 | 3 |  |  | Pickup-F150 or F250 or equal | 6 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 330 |  | 78 |  | 6 | 6 | 408 | [16 empty] | 408 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | JOSE | VALLES | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | JOSE | VALLES | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | REYMUNDO | REYES | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | REYMUNDO | REYES | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | MARCELO | GOMEZ | Laborer | 5 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858A | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 235 | 151 | 137.5 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | MARCELO | GOMEZ | Laborer | 3 | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858A | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 267 |  | 137.5 |  | 5 | 5 | 404.5 | [16 empty] | 404.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | EFREM | LEE | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | EFREM | LEE | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | ZACHARY | POWDERS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | ZACHARY | POWDERS | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | COLTON | ROBERTS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | COLTON | ROBERTS | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | GAGE | BURKS | Laborer | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 235 | 151 | 452.5 |  | 5 | 5 | 838.5 | [16 empty] | 838.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | GAGE | BURKS | Laborer | 3 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 267 |  | 452.5 |  | 5 | 5 | 719.5 | [16 empty] | 719.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | IAIN | ALLRED | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | IAIN | ALLRED | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | THOMAS | FRANKLIN | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | THOMAS | FRANKLIN | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | [7 empty] | Hammer Attachment | 5 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | [7 empty] | Hammer Attachment | 5 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | [7 empty] | Hammer Attachment | 5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 3500028468-81940-44145-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-10 | Moved from 0872 to 2088 in TN. Unloaded (2) excavators, utility trailer, (2) Hammer attachments, (4) mats, sand, air compressor and sandpot. | [7 empty] | Hammer Attachment | 5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | [16 empty] | 1559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 644 | 151 | 143 |  | 11 | 11 | 938 | [16 empty] | 938 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | JASON | JONES | Truck Driver/CDL | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 644 | 151 | 143 |  | 11 | 11 | 938 | [16 empty] | 938 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | JUANITO | RODRIGUEZ | Safety Person | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 12 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 504 |  | 10 | 12 | 1643 | [16 empty] | 1643 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | [7 empty] | Tractor/Semi | 11 | HR | 1376 | [11 empty] | 42 |  |  |  | 462 |  |  | 11 | 462 | [16 empty] | 462 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | [7 empty] | Tractor/Semi | 11 | HR | R1371 | [11 empty] | 42 |  |  |  | 462 |  |  | 11 | 462 | [16 empty] | 462 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | [7 empty] | Lowboy Trailer | 12 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | [7 empty] | Lowboy Trailer | 11 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 203.5 |  |  | 11 | 203.5 | [16 empty] | 203.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Matches crew 3 | [7 empty] | Lowboy Trailer | 11 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 203.5 |  |  | 11 | 203.5 | [16 empty] | 203.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Had detailed JHA. Loaded out excavator to 1551, hauled to yard. Moved equipment to yard, organized tool trailer, cleaned equipment, prepped for winter. | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Had detailed JHA. Loaded out excavator to 1551, hauled to yard. Moved equipment to yard, organized tool trailer, cleaned equipment, prepped for winter. | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Had detailed JHA. Loaded out excavator to 1551, hauled to yard. Moved equipment to yard, organized tool trailer, cleaned equipment, prepped for winter. | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Had detailed JHA. Loaded out excavator to 1551, hauled to yard. Moved equipment to yard, organized tool trailer, cleaned equipment, prepped for winter. | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Had detailed JHA. Loaded out excavator to 1551, hauled to yard. Moved equipment to yard, organized tool trailer, cleaned equipment, prepped for winter. | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Had detailed JHA. Loaded out excavator to 1551, hauled to yard. Moved equipment to yard, organized tool trailer, cleaned equipment, prepped for winter. | HEATHER | ENGLE | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Had detailed JHA. Loaded out excavator to 1551, hauled to yard. Moved equipment to yard, organized tool trailer, cleaned equipment, prepped for winter. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44146-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-11 | Started pumping water to backfill | MATTHEW | LINDLEY | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATT | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44146-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-11 | Started pumping water to backfill | DANIEL | MARTIN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44146-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-11 | Started pumping water to backfill | MICHEAL | TATUM | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44146-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-11 | Started pumping water to backfill | ZACHARY | POWDERS | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Mopped out the tracks and picked up trash and debris on site. Will have to complete mulching, haul mats and final clean up with skid steer. Hauled excavator to 1491. Hauled tool trailer to 1474. Started pumping water 1490 | MATT | LINDLEY | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | MATT | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Mopped out the tracks and picked up trash and debris on site. Will have to complete mulching, haul mats and final clean up with skid steer. Hauled excavator to 1491. Hauled tool trailer to 1474. Started pumping water 1490 | DANIEL | MARTIN | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15318 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Mopped out the tracks and picked up trash and debris on site. Will have to complete mulching, haul mats and final clean up with skid steer. Hauled excavator to 1491. Hauled tool trailer to 1474. Started pumping water 1490 | MICHEAL | TATUM | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | [16 empty] | 567 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Mopped out the tracks and picked up trash and debris on site. Will have to complete mulching, haul mats and final clean up with skid steer. Hauled excavator to 1491. Hauled tool trailer to 1474. Started pumping water 1490 | ZACHARY | POWDERS | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | [16 empty] | 675 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Mopped out the tracks and picked up trash and debris on site. Will have to complete mulching, haul mats and final clean up with skid steer. Hauled excavator to 1491. Hauled tool trailer to 1474. Started pumping water 1490 | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS49350 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [16 empty] | 460 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-58100-44146-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-11 | Mopped out the tracks and picked up trash and debris on site. Will have to complete mulching, haul mats and final clean up with skid steer. Hauled excavator to 1491. Hauled tool trailer to 1474. Started pumping water 1490 | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 724 |  |  | 8 | 724 | [16 empty] | 724 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Demob at yard | GERALD | SMITH | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Demob at yard | OJ | SEALS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Demob at yard | RICHARD | ADKINS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Demob at yard | BARRETT | WISE | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-28110-44146-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | Demob at yard | STEVE | CLARK | Truck Driver/CDL | 8 | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 14 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 860 | 151 | 224 |  | 14 | 14 | 1235 | [16 empty] | 1235 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | CALEB | HOLTON | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | CALEB | Straw Bales | 9 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 992 | 151 | 156 | 0 | 12 | 12 | 1299 | [16 empty] | 1299 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | SHAWN | ROSE | Operator II | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | SHAWN | Silt Fence | 200 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 741 | 151 | 143 | 0 | 11 | 11 | 1035 | [16 empty] | 1035 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | MICHAEL | ANISZEWSKI | Laborer | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 628 | 151 | 156 |  | 12 | 12 | 935 | [16 empty] | 935 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | BOLDBAUTOR | ZORIGT | Laborer | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 565 | 151 | 143 |  | 11 | 11 | 859 | [16 empty] | 859 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | JORDAN | WIGGINS | Laborer | 8 | 4 |  | 1 | Tool Trailer | 11 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 55 |  | 12 | 11 | 834 | [16 empty] | 834 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | TANNER | BRITT | Laborer | 8 | 3 |  | 1 | 40' Flatbed trailer or equal | 11 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 565 | 151 | 203.5 |  | 11 | 11 | 919.5 | [16 empty] | 919.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 11 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 644 | 151 | 176 |  | 11 | 11 | 971 | [16 empty] | 971 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 11 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 506 |  |  | 11 | 506 | [16 empty] | 506 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 11 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 995.5 |  |  | 11 | 995.5 | [16 empty] | 995.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 11 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 302.5 |  |  | 11 | 302.5 | [16 empty] | 302.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44146-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | Held JHA meeting. Finished mopping out mud pit, hauled in (6) loads of rock. Put up 200ft silt fence and used (9) straw bales | [7 empty] | Hammer Attachment | 11 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | JOSHUA | MENDARIES | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAM | Safety Fence | 120 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 307.5 | 151 | 65 | 0 | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | JOSHUA | MENDARIES | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JOSHUAM | T-Posts | 8 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 61.5 |  | 13 | 0 | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | JOSHUA | MENDARIES | Operator II | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | Sand | 8 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 289 |  | 52 | 0 | 4 | 4 | 341 | [16 empty] | 341 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | WAYLON | GREEN | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | WAYLON | GREEN | Laborer | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 283 |  | 65 |  | 5 | 5 | 348 | [16 empty] | 348 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | JOSE | VALLES | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | THOMAS | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | JOSE | VALLES | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | THOMAS | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | JOSE | VALLES | Laborer | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | THOMAS | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 220 |  | 52 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | REYMUNDO | REYES | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | REYMUNDO | REYES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | REYMUNDO | REYES | Laborer | 2 | 2 |  |  | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 220 |  | 20 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | MARCELO | GOMEZ | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | MARCELO | GOMEZ | Laborer | 2 | 2 |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 220 |  | 20 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | EFREM | LEE | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | EFREM | LEE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | EFREM | LEE | Truck Driver/CDL | 2 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 251 |  | 64 |  | 4 | 4 | 315 | [16 empty] | 315 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | COLTON | ROBERTS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | COLTON | ROBERTS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | COLTON | ROBERTS | Laborer | 2 | 2 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 220 |  | 74 |  | 4 | 4 | 294 | [16 empty] | 294 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | GAGE | BURKS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | GAGE | BURKS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | GAGE | BURKS | Laborer | 2 | 2 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 220 |  | 74 |  | 4 | 4 | 294 | [16 empty] | 294 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | IAIN | ALLRED | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | IAIN | ALLRED | Truck Driver/CDL | 2 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 251 |  | 64 |  | 4 | 4 | 315 | [16 empty] | 315 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | THOMAS | FRANKLIN | Operator II | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX10278 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 307.5 | 151 | 452.5 |  | 5 | 5 | 911 | [16 empty] | 911 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | THOMAS | FRANKLIN | Operator II | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX10278 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 61.5 |  | 90.5 |  | 1 | 1 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | THOMAS | FRANKLIN | Operator II | 2 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX10278 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 289 |  | 362 |  | 4 | 4 | 651 | [16 empty] | 651 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 5 | HR | REX4074 | [11 empty] | 105 |  |  |  | 525 |  |  | 5 | 525 | [16 empty] | 525 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 1 | HR | REX4074 | [11 empty] | 105 |  |  |  | 105 |  |  | 1 | 105 | [16 empty] | 105 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 4 | HR | REX4074 | [11 empty] | 105 |  |  |  | 420 |  |  | 4 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Hammer Attachment | 5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Hammer Attachment | 5 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44146-rev1 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | Located line, potholed in (3) places to verify pipe. Started digging excavation, used hammer hoe to break rock. Sandblasted for NDE to do assessment on pipe. Put up safety fence and electric fence around excavation. Used 120ft electric fence, 1 solar panel box for electric fence | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44147-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-12 | Arrived at yard and had detailed JHA. Took equipment inventory, removed sandpots from compressors and put on pallets. Picked up trash, unloaded mats. Drove to sites and picked up road signs and tires. | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44147-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-12 | Arrived at yard and had detailed JHA. Took equipment inventory, removed sandpots from compressors and put on pallets. Picked up trash, unloaded mats. Drove to sites and picked up road signs and tires. | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44147-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-12 | Arrived at yard and had detailed JHA. Took equipment inventory, removed sandpots from compressors and put on pallets. Picked up trash, unloaded mats. Drove to sites and picked up road signs and tires. | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44147-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-12 | Arrived at yard and had detailed JHA. Took equipment inventory, removed sandpots from compressors and put on pallets. Picked up trash, unloaded mats. Drove to sites and picked up road signs and tires. | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44147-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-12 | Arrived at yard and had detailed JHA. Took equipment inventory, removed sandpots from compressors and put on pallets. Picked up trash, unloaded mats. Drove to sites and picked up road signs and tires. | HEATHER | ENGLE | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44147-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-12 | Arrived at yard and had detailed JHA. Took equipment inventory, removed sandpots from compressors and put on pallets. Picked up trash, unloaded mats. Drove to sites and picked up road signs and tires. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | MATTHEW | LINDLEY | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MATTHEW | Straw Bales | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | MATTHEW | LINDLEY | Foreman | 3 | 3 |  |  | Pickup-F150 or F250 or equal | 6 | HR | MATTHEW | Seed Mix | 15 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 522 |  | 78 | 0 | 6 | 6 | 600 | [16 empty] | 600 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | DANIEL | MARTIN | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15318 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | DANIEL | MARTIN | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15318 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | MICHEAL | TATUM | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT0384 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | MICHEAL | TATUM | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT0384 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | ZACHARY | POWDERS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | ZACHARY | POWDERS | Laborer | 3 | 3 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 330 |  | 92.5 |  | 6 | 5 | 422.5 | [16 empty] | 422.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS49350 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS49350 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44147-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-12 | Pumped water, mucked out excavation. Backfilled put back top soil and cleaned up. Seeded and mulched. Loaded out hammer. Assessed other sites to have a plan of action to get them finaled. Removed all debris to edge of access to have hauled off. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-18890-44147-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-12 | Getting equipment ready to demob. Continued cleaning yard | GERALD | SMITH | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-18890-44147-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-12 | Getting equipment ready to demob. Continued cleaning yard | OJ | SEALS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-18890-44147-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-12 | Getting equipment ready to demob. Continued cleaning yard | RICHARD | ADKINS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-18890-44147-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-12 | Getting equipment ready to demob. Continued cleaning yard | BARRETT | WISE | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Demobilization | 3500028468-18890-44147-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-12 | Getting equipment ready to demob. Continued cleaning yard | STEVE | CLARK | Truck Driver/CDL | 8 | 6 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 860 | 151 |  |  | 14 |  | 1011 | [16 empty] | 1011 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | CALEB | HOLTON | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | SHAWN | ROSE | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | MICHAEL | ANISZEWSKI | Laborer | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 565 | 151 | 143 |  | 11 | 11 | 859 | [16 empty] | 859 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | BOLDBAUTOR | ZORIGT | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 169 |  | 10 | 13 | 822 | [16 empty] | 822 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | JORDAN | WIGGINS | Laborer | 8 | 5 |  | 1 | Tool Trailer | 10 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 691 | 151 | 50 |  | 13 | 10 | 892 | [16 empty] | 892 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | TANNER | BRITT | Laborer | 8 | 5 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 691 | 151 | 185 |  | 13 | 10 | 1027 | [16 empty] | 1027 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 11 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 644 | 151 | 176 |  | 11 | 11 | 971 | [16 empty] | 971 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [16 empty] | 460 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44147-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-12 | Held JHA meeting. Finished spreading gravel, cleaned up all trash. Street sweeper attachment was picked up. (2) hands went to IL to get excavator loaded. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | JOSHUA | MENDARIES | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JOSHUAM | Sand | 8 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 369 | 151 | 78 | 0 | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | JOSHUA | MENDARIES | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | 4888 Coating | 10 | L |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 123 |  | 26 | 0 | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | JOSHUA | MENDARIES | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | Brushes | 16 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 166 |  | 26 | 0 | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | WAYLON | GREEN | Laborer | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | THOMASF | T-Posts | 2 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 329 | 151 | 91 | 0 | 7 | 7 | 571 | [16 empty] | 571 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | WAYLON | GREEN | Laborer | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | THOMASF | Safety Fence | 30 | Ft |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 110 |  | 26 | 0 | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | THOMASF | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | JOSE | VALLES | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | JOSE | VALLES | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | JOSE | VALLES | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | REYMUNDO | REYES | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | REYMUNDO | REYES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | REYMUNDO | REYES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | MARCELO | GOMEZ | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | MARCELO | GOMEZ | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | EFREM | LEE | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | [16 empty] | 568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | EFREM | LEE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | COLTON | ROBERTS | Laborer | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | R19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 282 | 151 | 96 |  | 6 | 6 | 529 | [16 empty] | 529 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | COLTON | ROBERTS | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | COLTON | ROBERTS | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 32 |  | 2 | 2 | 158 | [16 empty] | 158 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | GAGE | BURKS | Laborer | 6 |  |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 282 | 151 | 111 |  | 6 | 6 | 544 | [16 empty] | 544 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | GAGE | BURKS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | GAGE | BURKS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | IAIN | ALLRED | Truck Driver/CDL | 6 |  |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT0229 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 321 | 151 | 111 |  | 6 | 6 | 583 | [16 empty] | 583 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | IAIN | ALLRED | Truck Driver/CDL | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0229 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 107 |  | 37 |  | 2 | 2 | 144 | [16 empty] | 144 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0229 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 144 |  | 37 |  | 2 | 2 | 181 | [16 empty] | 181 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | THOMAS | FRANKLIN | Operator II | 6 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4074 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 369 | 151 | 543 |  | 6 | 6 | 1063 | [16 empty] | 1063 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | THOMAS | FRANKLIN | Operator II | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 123 |  | 181 |  | 2 | 2 | 304 | [16 empty] | 304 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | THOMAS | FRANKLIN | Operator II |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 166 |  | 181 |  | 2 | 2 | 347 | [16 empty] | 347 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 6 | HR | REX10278 | [11 empty] | 105 |  |  |  | 630 |  |  | 6 | 630 | [16 empty] | 630 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 2 | HR | REX10278 | [11 empty] | 105 |  |  |  | 210 |  |  | 2 | 210 | [16 empty] | 210 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 2 | HR | REX10278 | [11 empty] | 105 |  |  |  | 210 |  |  | 2 | 210 | [16 empty] | 210 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Hammer Attachment | 6 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Hammer Attachment | 6 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Continued to excavate dig. Exposed 4ft assessment needed. Brand Safway removed coal tar coating from assessment area. Sandblasted pipe for NDE assessment. NDE confirmed as a recoat around 2:30pm. Began recoat around 3pm. Used 30ft electrical wire for livestock control. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JODY | BROOM | Superintendent | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 561 | 151 | 78 |  | 6 | 6 | 790 | [16 empty] | 790 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JODY | BROOM | Superintendent | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 |  | 26 |  | 2 | 2 | 213 | [16 empty] | 213 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JODY | BROOM | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | TOME | KIRKLAND | Superintendent | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 561 | 151 | 78 |  | 6 | 6 | 790 | [16 empty] | 790 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | TOME | KIRKLAND | Superintendent | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 |  | 26 |  | 2 | 2 | 213 | [16 empty] | 213 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | TOME | KIRKLAND | Superintendent |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 504 |  | 52 |  | 4 | 4 | 556 | [16 empty] | 556 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 630 | 151 | 78 |  | 6 | 6 | 859 | [16 empty] | 859 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | MICHAEL | GOSS | Truck Driver/CDL | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 321 | 151 | 78 |  | 6 | 6 | 550 | [16 empty] | 550 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | MICHAEL | GOSS | Truck Driver/CDL | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 107 |  | 26 |  | 2 | 2 | 133 | [16 empty] | 133 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | MICHAEL | GOSS | Truck Driver/CDL |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 288 |  | 52 |  | 4 | 4 | 340 | [16 empty] | 340 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 321 | 151 | 78 |  | 6 | 6 | 550 | [16 empty] | 550 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 107 |  | 26 |  | 2 | 2 | 133 | [16 empty] | 133 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 288 |  | 52 |  | 4 | 4 | 340 | [16 empty] | 340 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JASON | JONES | Truck Driver/CDL | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 321 | 151 | 78 |  | 6 | 6 | 550 | [16 empty] | 550 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JASON | JONES | Truck Driver/CDL | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 107 |  | 26 |  | 2 | 2 | 133 | [16 empty] | 133 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JASON | JONES | Truck Driver/CDL |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 288 |  | 52 |  | 4 | 4 | 340 | [16 empty] | 340 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 444 | 151 | 78 |  | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | SCOTT | MERRY | Safety Person | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 444 | 151 | 78 |  | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | SCOTT | MERRY | Safety Person | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | SCOTT | MERRY | Safety Person |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | DANIEL | YOUNG | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 369 | 151 | 78 |  | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | DANIEL | YOUNG | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | DANIEL | YOUNG | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 6 |  |  | 1 | Tractor/Semi | 6 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 592.8 | 151 | 252 |  | 6 | 6 | 995.8 | [16 empty] | 995.8 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Tractor/Semi | 2 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 197.6 |  | 84 |  | 2 | 2 | 281.6 | [16 empty] | 281.6 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Tractor/Semi | 4 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 197.6 |  | 168 |  | 2 | 4 | 365.6 | [16 empty] | 365.6 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Tractor/Semi | 6 | HR | 1376 | [11 empty] | 42 |  |  |  | 252 |  |  | 6 | 252 | [16 empty] | 252 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Tractor/Semi | 2 | HR | 1376 | [11 empty] | 42 |  |  |  | 84 |  |  | 2 | 84 | [16 empty] | 84 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Tractor/Semi | 4 | HR | 1376 | [11 empty] | 42 |  |  |  | 168 |  |  | 4 | 168 | [16 empty] | 168 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Tractor/Semi | 6 | HR | R1371 | [11 empty] | 42 |  |  |  | 252 |  |  | 6 | 252 | [16 empty] | 252 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Tractor/Semi | 2 | HR | R1371 | [11 empty] | 42 |  |  |  | 84 |  |  | 2 | 84 | [16 empty] | 84 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Tractor/Semi | 4 | HR | R1371 | [11 empty] | 42 |  |  |  | 168 |  |  | 4 | 168 | [16 empty] | 168 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Lowboy Trailer | 6 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 111 |  |  | 6 | 111 | [16 empty] | 111 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Lowboy Trailer | 2 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Lowboy Trailer | 4 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 74 |  |  | 4 | 74 | [16 empty] | 74 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Lowboy Trailer | 6 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 111 |  |  | 6 | 111 | [16 empty] | 111 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Lowboy Trailer | 2 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Lowboy Trailer | 4 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 74 |  |  | 4 | 74 | [16 empty] | 74 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Lowboy Trailer | 6 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 111 |  |  | 6 | 111 | [16 empty] | 111 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Lowboy Trailer | 2 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 3500028468-81940-44147-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-12 | Matches crew 6 | [7 empty] | Lowboy Trailer | 4 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 74 |  |  | 4 | 74 | [16 empty] | 74 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 | 0 | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | [32 empty] | TROPHY LOGISTICS | 10610A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10609A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10608A | TRUCKING | 130 | 10.4 |  | 140.4 | [9 empty] | 140.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10607A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10607A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10607A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10607A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10607A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | [32 empty] | TROPHY LOGISTICS | 10607A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10606A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10606A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10606A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10606A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10606A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 5 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | [32 empty] | TROPHY LOGISTICS | 10606A | TRUCKING | 216.67 | 17.3336 |  | 234.0036 | [9 empty] | 234.0036 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1465 - MC.400216.032 - 629.925 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | [32 empty] | PSS | 240030500 | SITE MATERIALS | 324.36 | 25.9488 | 19.5 | 369.8088 | [9 empty] | 369.8088 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Backfill | 5 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081280 | ROCKSHIELD | 1193.55 | 95.484 | 71.61 | 1360.644 | [9 empty] | 1360.644 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081273 | SITE MATERIALS | 187.83 | 15.0264 | 11.27 | 214.1264 | [9 empty] | 214.1264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081273 | SITE MATERIALS | 187.83 | 15.0264 | 11.27 | 214.1264 | [9 empty] | 214.1264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081273 | SITE MATERIALS | 187.83 | 15.0264 | 11.27 | 214.1264 | [9 empty] | 214.1264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081273 | SITE MATERIALS | 187.83 | 15.0264 | 11.27 | 214.1264 | [9 empty] | 214.1264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081273 | SITE MATERIALS | 187.83 | 15.0264 | 11.27 | 214.1264 | [9 empty] | 214.1264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | [32 empty] | CROSS COUNTRY | 4081273 | SITE MATERIALS | 187.83 | 15.0264 | 11.27 | 214.1264 | [9 empty] | 214.1264 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497623 | COATING REMOVAL | 3972 | 317.76 |  | 4289.76 | [9 empty] | 4289.76 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497615 | COATING REMOVAL | 3766.15 | 301.292 |  | 4067.442 | [9 empty] | 4067.442 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497600 | COATING REMOVAL | 5730 | 458.4 |  | 6188.4 | [9 empty] | 6188.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Pipe Preparation | 5 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-10 | [32 empty] | BRAND SAFWAY | 951497600 | COATING REMOVAL | 5730 | 458.4 |  | 6188.4 | [9 empty] | 6188.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 5 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | [32 empty] | BADGER | 2131969 | HYDROVAC | 57493.86 | 4599.5088 |  | 62093.3688 | [9 empty] | 62093.3688 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-08 | [32 empty] | LOWE'S | 22177798 | SILT FENCE, STAKES | 24.97 | 1.9976 | 2.43 | 29.3976 | [9 empty] | 29.3976 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-08 | [32 empty] | LOWE'S | 22177798 | SILT FENCE, STAKES | 24.97 | 1.9976 | 2.43 | 29.3976 | [9 empty] | 29.3976 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-08 | [32 empty] | LOWE'S | 22177798 | SILT FENCE, STAKES | 24.97 | 1.9976 | 2.43 | 29.3976 | [9 empty] | 29.3976 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-08 | [32 empty] | LOWE'S | 22177798 | SILT FENCE, STAKES | 24.97 | 1.9976 | 2.44 | 29.4076 | [9 empty] | 29.4076 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-08 | [32 empty] | LOWE'S | 22177798 | SILT FENCE, STAKES | 24.98 | 1.9984 | 2.44 | 29.4184 | [9 empty] | 29.4184 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | [32 empty] | LOWE'S | 22177798 | SILT FENCE, STAKES | 24.98 | 1.9984 | 2.44 | 29.4184 | [9 empty] | 29.4184 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.01 | 3.3608 | 2.52 | 47.8908 | [9 empty] | 47.8908 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.02 | 3.3616 | 2.52 | 47.9016 | [9 empty] | 47.9016 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.02 | 3.3616 | 2.52 | 47.9016 | [9 empty] | 47.9016 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.02 | 3.3616 | 2.52 | 47.9016 | [9 empty] | 47.9016 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.02 | 3.3616 | 2.52 | 47.9016 | [9 empty] | 47.9016 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.02 | 3.3616 | 2.52 | 47.9016 | [9 empty] | 47.9016 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-08 | [32 empty] | LOWE'S | 71200702 | SILT FENCE, BARBED WIRE | 42.02 | 3.3616 | 2.53 | 47.9116 | [9 empty] | 47.9116 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | [32 empty] | TRACTOR SUPPLY | 629851 | SAFETY FENCE | 79.96 | 6.3968 | 5.6 | 91.9568 | [9 empty] | 91.9568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | [32 empty] | SPRINGS VALLEY SUPPLY | I10364620 | T-POSTS | 93.8 | 7.504 | 6.57 | 107.874 | [9 empty] | 107.874 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-15 | [32 empty] | SPRINGS VALLEY SUPPLY | I10365008 | T-POSTS | 187.6 | 15.008 | 13.13 | 215.738 | [9 empty] | 215.738 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | [32 empty] | TRACTOR SUPPLY | 196962 | T-POST CAPS | 74.95 | 5.996 | 5.25 | 86.196 | [9 empty] | 86.196 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | [32 empty] | SIGMA STEEL | BQk4 | MATERIAL FOR BUTTER BARS ON CREW 5 | 92.99 | 7.4392 | 6.51 | 106.9392 | [9 empty] | 106.9392 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-17 | [32 empty] | SPRINGS VALLEY SUPPLY | I10365293 | CLEAR POLY FILM | 125.97 | 10.0776 | 8.81 | 144.8576 | [9 empty] | 144.8576 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | [32 empty] | TRACTOR SUPPLY | 196887 | SAFETY FENCE, PLASTIC FILM | 89.96 | 7.1968 | 6.3 | 103.4568 | [9 empty] | 103.4568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | [32 empty] | SPRINGS VALLEY SUPPLY | I10365112 | T-POSTS | 72.01 | 5.7608 | 5.04 | 82.8108 | [9 empty] | 82.8108 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-13 | [32 empty] | SPRINGS VALLEY SUPPLY | I10364579 | SAFETY FENCE AND SILT FENCE | 244.92 | 19.5936 | 17.14 | 281.6536 | [9 empty] | 281.6536 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-14 | [32 empty] | TRACTOR SUPPLY | 662899 | T-POSTS | 38.88 | 3.1104 | 2.72 | 44.7104 | [9 empty] | 44.7104 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 2 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | [32 empty] | JEFFRIES FEED SEED & SUPPLY | 414352 | SEED & STRAW | 588.45 | 47.076 | 35.31 | 670.836 | [9 empty] | 670.836 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 2 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | [32 empty] | SOUTHERN STATES | J371751 | STRAW BALES | 210 | 16.8 | 12.6 | 239.4 | [9 empty] | 239.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | [32 empty] | ACE HARDWARE | 618533 | FENCING MATERIAL | 42.45 | 3.396 | 2.97 | 48.816 | [9 empty] | 48.816 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | [32 empty] | ACE HARDWARE | 618533 | FENCING MATERIAL | 42.45 | 3.396 | 2.97 | 48.816 | [9 empty] | 48.816 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | [32 empty] | ACE HARDWARE | 618533 | FENCING MATERIAL | 42.45 | 3.396 | 2.97 | 48.816 | [9 empty] | 48.816 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-15 | [32 empty] | ACE HARDWARE | 618533 | FENCING MATERIAL | 42.45 | 3.396 | 2.97 | 48.816 | [9 empty] | 48.816 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-11 | [32 empty] | HOME DEPOT | 72431 | SAFETY FENCE, STAKES, POLY SHEETING | 117.82 | 9.4256 | 8.24 | 135.4856 | [9 empty] | 135.4856 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-11 | [32 empty] | HOME DEPOT | 72431 | SAFETY FENCE, STAKES, POLY SHEETING | 117.82 | 9.4256 | 8.25 | 135.4956 | [9 empty] | 135.4956 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-11 | [32 empty] | HOME DEPOT | 72431 | SAFETY FENCE, STAKES, POLY SHEETING | 117.82 | 9.4256 | 8.25 | 135.4956 | [9 empty] | 135.4956 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-11 | [32 empty] | HOME DEPOT | 72431 | SAFETY FENCE, STAKES, POLY SHEETING | 117.82 | 9.4256 | 8.25 | 135.4956 | [9 empty] | 135.4956 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-11 | [32 empty] | HOME DEPOT | 72431 | SAFETY FENCE, STAKES, POLY SHEETING | 117.82 | 9.4256 | 8.25 | 135.4956 | [9 empty] | 135.4956 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | [32 empty] | HOME DEPOT | 77444 | U-POSTS, BARRIERS, SILT FENCE | 136.52 | 10.9216 | 9.55 | 156.9916 | [9 empty] | 156.9916 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-15 | [32 empty] | HOME DEPOT | 77444 | U-POSTS, BARRIERS, SILT FENCE | 136.52 | 10.9216 | 9.56 | 157.0016 | [9 empty] | 157.0016 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 2 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | [32 empty] | JEFFRIES FEED SEED & SUPPLY | 10142020 | STRAW BALES | 182.6 | 14.608 | 10.95 | 208.158 | [9 empty] | 208.158 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 2 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | [32 empty] | JEFFRIES FEED SEED & SUPPLY | 10142020 | STRAW BALES | 182.6 | 14.608 | 10.95 | 208.158 | [9 empty] | 208.158 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-12 | [32 empty] | LOWE'S | 7515651 | SILT FENCE, SAFETY FENCE | 121.89 | 9.7512 | 7.31 | 138.9512 | [9 empty] | 138.9512 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-12 | [32 empty] | LOWE'S | 7515651 | SILT FENCE, SAFETY FENCE | 121.89 | 9.7512 | 7.32 | 138.9612 | [9 empty] | 138.9612 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | [32 empty] | LOWE'S | 7515651 | SILT FENCE, SAFETY FENCE | 121.9 | 9.752 | 7.31 | 138.962 | [9 empty] | 138.962 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-14 | [32 empty] | SPRINGS VALLEY SUPPLY | SO00005667 | SILT FENCE AND STAKES | 408.19 | 32.6552 | 28.57 | 469.4152 | [9 empty] | 469.4152 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | [32 empty] | SPRINGS VALLEY SUPPLY | SO00005667 | SILT FENCE AND STAKES | 408.2 | 32.656 | 28.57 | 469.426 | [9 empty] | 469.426 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | [32 empty] | SPRINGS VALLEY SUPPLY | SO00005667 | SILT FENCE AND STAKES | 408.2 | 32.656 | 28.58 | 469.436 | [9 empty] | 469.436 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-14 | [32 empty] | SPRINGS VALLEY SUPPLY | SO00005667 | SILT FENCE AND STAKES | 408.2 | 32.656 | 25.58 | 466.436 | [9 empty] | 466.436 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Recoat | 2 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | [32 empty] | LOWE'S | 10201133 | PLASTIC SHEETING | 171.96 | 13.7568 | 10.32 | 196.0368 | [9 empty] | 196.0368 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | [32 empty] | LOWE'S | 10037772 | PLASTIC SHEETING | 159.96 | 12.7968 | 9.6 | 182.3568 | [9 empty] | 182.3568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | [32 empty] | DARKE COUNTY TILE CO | 10242020 | MATERIAL TO REPAIR 8" DRAIN LINE IN FIELD | 166 | 13.28 | 0 | 179.28 | [9 empty] | 179.28 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | [32 empty] | LOWE'S | 29318340 | PLASTIC SHEETING | 109.96 | 8.7968 | 7.7 | 126.4568 | [9 empty] | 126.4568 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | [32 empty] | TRACTOR SUPPLY | 428336 | CONTAINMENT TUB FOR DEWATERING | 22.99 | 1.8392 | 1.61 | 26.4392 | [9 empty] | 26.4392 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 2 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | [32 empty] | SPRINGS VALLEY SUPPLY | I10365696 | SAFETY FENCE & PLASTIC SHEETING | 245.93 | 19.6744 | 17.22 | 282.8244 | [9 empty] | 282.8244 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Mobilization | 2 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-22 | [32 empty] | TRACTOR SUPPLY | 665033 | BINDER CHAIN TO MOB PIPE | 89.99 | 7.1992 | 6.3 | 103.4892 | [9 empty] | 103.4892 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Clean-up / Remediation | 2 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-22 | [32 empty] | CALDWELL STONE | 285296 | STONE | 428.46 | 34.2768 | 25.7 | 488.4368 | [9 empty] | 488.4368 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | [32 empty] | SPRINGS VALLEY SUPPLY | I10365737 | T-POSTS | 68.85 | 5.508 | 4.82 | 79.178 | [9 empty] | 79.178 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 2 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-21 | [32 empty] | SPRINGS VALLEY SUPPLY | I10365737 | T-POSTS | 68.85 | 5.508 | 4.82 | 79.178 | [9 empty] | 79.178 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-09 | [32 empty] | BOYD CAT | R47341-001 | HAMMER ATTACH | 1250 | 437.5 | 75 | 1762.5 | [9 empty] | 1762.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-09 | [32 empty] | BOYD CAT | R47341-001 | HAMMER ATTACH | 1250 | 437.5 | 75 | 1762.5 | [9 empty] | 1762.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-09 | [32 empty] | BOYD CAT | R47341-001 | HAMMER ATTACH | 1250 | 437.5 | 75 | 1762.5 | [9 empty] | 1762.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-09 | [32 empty] | BOYD CAT | R47341-001 | HAMMER ATTACH | 1250 | 437.5 | 75 | 1762.5 | [9 empty] | 1762.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1465 - MC.400216.032 - 629.925 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1492 - MC.400216.032 - 674.399 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1492 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 236624.47 | 61420 | Central | IN | 674.399 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1493 - MC.400216.032 - 682.498 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1493 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 279423.05 | 72330 | Central | IN | 682.498 | 2020-11-04 | [32 empty] | HERC RENTALS | 31751593-001 | UTV | 81.98 | 28.693 | 4.92 | 115.593 | [9 empty] | 115.593 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Access | 6 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-04 | [32 empty] | HERC RENTALS | 31741542-003 | UTV | 72.5 | 25.375 | 4.35 | 102.225 | [9 empty] | 102.225 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-08 | [32 empty] | HERC RENTALS | 31734630-001 | BRUSH CUTTER | 590 | 206.5 | 35.4 | 831.9 | [9 empty] | 831.9 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-08 | [32 empty] | HERC RENTALS | 31734630-001 | BRUSH CUTTER | 590 | 206.5 | 35.4 | 831.9 | [9 empty] | 831.9 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-08 | [32 empty] | HERC RENTALS | 31734630-001 | BRUSH CUTTER | 590 | 206.5 | 35.4 | 831.9 | [9 empty] | 831.9 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-08 | [32 empty] | HERC RENTALS | 31734630-001 | BRUSH CUTTER | 590 | 206.5 | 35.4 | 831.9 | [9 empty] | 831.9 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-08 | [32 empty] | HERC RENTALS | 31734630-001 | BRUSH CUTTER | 590 | 206.5 | 35.4 | 831.9 | [9 empty] | 831.9 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-07 | [32 empty] | HERC RENTALS | 31731082-001 | BRUSH CUTTER | 425 | 148.75 | 25.5 | 599.25 | [9 empty] | 599.25 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-07 | [32 empty] | HERC RENTALS | 31731082-001 | BRUSH CUTTER | 425 | 148.75 | 25.5 | 599.25 | [9 empty] | 599.25 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-07 | [32 empty] | HERC RENTALS | 31731082-001 | BRUSH CUTTER | 425 | 148.75 | 25.5 | 599.25 | [9 empty] | 599.25 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-07 | [32 empty] | HERC RENTALS | 31731082-001 | BRUSH CUTTER | 425 | 148.75 | 25.5 | 599.25 | [9 empty] | 599.25 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-07 | [32 empty] | HERC RENTALS | 31731068-001 | BRUSH CUTTER | 340 | 119 | 20.4 | 479.4 | [9 empty] | 479.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-11-07 | [32 empty] | HERC RENTALS | 31731068-001 | BRUSH CUTTER | 340 | 119 | 20.4 | 479.4 | [9 empty] | 479.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-07 | [32 empty] | HERC RENTALS | 31731068-001 | BRUSH CUTTER | 340 | 119 | 20.4 | 479.4 | [9 empty] | 479.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-07 | [32 empty] | HERC RENTALS | 31731068-001 | BRUSH CUTTER | 340 | 119 | 20.4 | 479.4 | [9 empty] | 479.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Site Prep | 6 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | [32 empty] | HERC RENTALS | 31731068-001 | BRUSH CUTTER | 340 | 119 | 20.4 | 479.4 | [9 empty] | 479.4 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339-002 | HAMMER ATTACH | 927.17 | 324.5095 | 17.77 | 1269.4495 | [9 empty] | 1269.4495 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339-002 | HAMMER ATTACH | 927.17 | 324.5095 | 17.77 | 1269.4495 | [9 empty] | 1269.4495 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339-002 | HAMMER ATTACH | 927.17 | 324.5095 | 17.77 | 1269.4495 | [9 empty] | 1269.4495 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339-002 | HAMMER ATTACH | 927.17 | 324.5095 | 17.77 | 1269.4495 | [9 empty] | 1269.4495 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339-002 | HAMMER ATTACH | 927.17 | 324.5095 | 17.77 | 1269.4495 | [9 empty] | 1269.4495 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339-002 | HAMMER ATTACH | 927.17 | 324.5095 | 17.77 | 1269.4495 | [9 empty] | 1269.4495 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339-002 | HAMMER ATTACH | 927.17 | 324.5095 | 17.77 | 1269.4495 | [9 empty] | 1269.4495 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375239 | HAMMER ATTACH | 1545.63 | 540.9705 | 92.74 | 2179.3405 | [9 empty] | 2179.3405 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375239 | HAMMER ATTACH | 1545.63 | 540.9705 | 92.74 | 2179.3405 | [9 empty] | 2179.3405 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375239 | HAMMER ATTACH | 1545.63 | 540.9705 | 92.74 | 2179.3405 | [9 empty] | 2179.3405 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375239 | HAMMER ATTACH | 1545.63 | 540.9705 | 92.74 | 2179.3405 | [9 empty] | 2179.3405 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375237 | HAMMER ATTACH | 1030.42 | 360.647 | 61.83 | 1452.897 | [9 empty] | 1452.897 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375237 | HAMMER ATTACH | 1030.42 | 360.647 | 61.83 | 1452.897 | [9 empty] | 1452.897 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375237 | HAMMER ATTACH | 1030.42 | 360.647 | 61.83 | 1452.897 | [9 empty] | 1452.897 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375237 | HAMMER ATTACH | 1030.42 | 360.647 | 61.83 | 1452.897 | [9 empty] | 1452.897 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375237 | HAMMER ATTACH | 1030.42 | 360.647 | 61.83 | 1452.897 | [9 empty] | 1452.897 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-11 | [32 empty] | CROSS COUNTRY | 375237 | HAMMER ATTACH | 1030.42 | 360.647 | 61.83 | 1452.897 | [9 empty] | 1452.897 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-10 | [32 empty] | CROSS COUNTRY | 375165 | PADDING BUCKET | 1968.63 | 689.0205 | 118.12 | 2775.7705 | [9 empty] | 2775.7705 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-10 | [32 empty] | CROSS COUNTRY | 375165 | PADDING BUCKET | 1968.63 | 689.0205 | 118.12 | 2775.7705 | [9 empty] | 2775.7705 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-10 | [32 empty] | CROSS COUNTRY | 375165 | PADDING BUCKET | 1968.63 | 689.0205 | 118.12 | 2775.7705 | [9 empty] | 2775.7705 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-10 | [32 empty] | CROSS COUNTRY | 375165 | PADDING BUCKET | 1968.63 | 689.0205 | 118.12 | 2775.7705 | [9 empty] | 2775.7705 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374926 | PADDING BUCKET | 1465 | 512.75 | 87.9 | 2065.65 | [9 empty] | 2065.65 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374926 | PADDING BUCKET | 1465 | 512.75 | 87.9 | 2065.65 | [9 empty] | 2065.65 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374926 | PADDING BUCKET | 1465 | 512.75 | 87.9 | 2065.65 | [9 empty] | 2065.65 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374926 | PADDING BUCKET | 1465 | 512.75 | 87.9 | 2065.65 | [9 empty] | 2065.65 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374926 | PADDING BUCKET | 1465 | 512.75 | 87.9 | 2065.65 | [9 empty] | 2065.65 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374925 | HAMMER ATTACH | 1556.25 | 544.6875 | 93.38 | 2194.3175 | [9 empty] | 2194.3175 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374925 | HAMMER ATTACH | 1556.25 | 544.6875 | 93.38 | 2194.3175 | [9 empty] | 2194.3175 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374925 | HAMMER ATTACH | 1556.25 | 544.6875 | 93.38 | 2194.3175 | [9 empty] | 2194.3175 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374925 | HAMMER ATTACH | 1556.25 | 544.6875 | 93.38 | 2194.3175 | [9 empty] | 2194.3175 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374924 | HAMMER ATTACH | 1568.75 | 549.0625 | 94.13 | 2211.9425 | [9 empty] | 2211.9425 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374924 | HAMMER ATTACH | 1568.75 | 549.0625 | 94.13 | 2211.9425 | [9 empty] | 2211.9425 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374924 | HAMMER ATTACH | 1568.75 | 549.0625 | 94.13 | 2211.9425 | [9 empty] | 2211.9425 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-11 | 2 | BL |  | Excavation | 6 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-03 | [32 empty] | CROSS COUNTRY | 374924 | HAMMER ATTACH | 1568.75 | 549.0625 | 94.13 | 2211.9425 | [9 empty] | 2211.9425 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [16 empty] | 1541 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | TOME | KIRKLAND | Superintendent |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1512 | 151 | 156 |  | 12 | 12 | 1819 | [16 empty] | 1819 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | STEVE | CLARK | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 156 |  | 12 | 12 | 1171 | [16 empty] | 1171 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 156 |  | 12 | 12 | 1171 | [16 empty] | 1171 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | JASON | JONES | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 130 |  | 12 | 10 | 1145 | [16 empty] | 1145 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | JUANITO | RODRIGUEZ | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | SCOTT | MERRY | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Tractor/Semi | 12 | HR | 1368 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 830 | 151 | 504 |  | 10 | 12 | 1485 | [16 empty] | 1485 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 12 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 504 |  | 10 | 12 | 1643 | [16 empty] | 1643 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | [7 empty] | Tractor/Semi | 12 | HR | R1371 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | MATCHES CREW 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44148-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-13 | Held JHA meeting. Checked equipment at yard. Inspected sites. Hooked F550 and gooseneck trail for mat haul. | KYLE | BONNEAU | Foreman |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1100 | 151 | 143 |  | 11 | 11 | 1394 | [16 empty] | 1394 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44148-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-13 | Held JHA meeting. Checked equipment at yard. Inspected sites. Hooked F550 and gooseneck trail for mat haul. | JACOB | CAPITANO | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44148-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-13 | Held JHA meeting. Checked equipment at yard. Inspected sites. Hooked F550 and gooseneck trail for mat haul. | BROC | CALIGER | Laborer |  | 10 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 630 | 151 | 222 |  | 10 | 12 | 1003 | [16 empty] | 1003 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-19030-44148-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-13 | Held JHA meeting. Checked equipment at yard. Inspected sites. Hooked F550 and gooseneck trail for mat haul. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 12 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 864 | 151 | 192 |  | 12 | 12 | 1207 | [16 empty] | 1207 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44148-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-13 | Hauled mats from 1491, 1475, 1476. Staged at 1474. Cleaned up site | MATTHEW | LINDLEY | Foreman |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 | 151 | 65 |  | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44148-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-13 | Hauled mats from 1491, 1475, 1476. Staged at 1474. Cleaned up site | DANIEL | MARTIN | Laborer |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15318 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 | 151 | 65 |  | 5 | 5 | 531 | [16 empty] | 531 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44148-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-13 | Hauled mats from 1491, 1475, 1476. Staged at 1474. Cleaned up site | MICHEAL | TATUM | Laborer |  | 5 |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 | 151 | 92.5 |  | 5 | 5 | 558.5 | [16 empty] | 558.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44148-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-13 | Hauled mats from 1491, 1475, 1476. Staged at 1474. Cleaned up site | ZACHARY | POWDERS | Laborer |  | 5 |  | 1 | Tool Trailer | 5 | HR | UTT2187 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 | 151 | 25 |  | 5 | 5 | 491 | [16 empty] | 491 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44148-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-13 | Hauled mats from 1491, 1475, 1476. Staged at 1474. Cleaned up site | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-33820-44148-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-13 | Hauled mats from 1491, 1475, 1476. Staged at 1474. Cleaned up site | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS49350 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44148-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-13 | Cleaned site | MATTHEW | LINDLEY | Foreman |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 600 |  | 78 |  | 6 | 6 | 678 | [16 empty] | 678 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44148-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-13 | Cleaned site | DANIEL | MARTIN | Laborer |  | 5 |  |  | Pickup-F150 or F250 or equal | 6 | HR | 15318 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 |  | 78 |  | 5 | 6 | 393 | [16 empty] | 393 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44148-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-13 | Cleaned site | MICHEAL | TATUM | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 92.5 |  | 5 | 5 | 407.5 | [16 empty] | 407.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44148-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-13 | Cleaned site | ZACHARY | POWDERS | Laborer |  | 6 |  |  | Tool Trailer | 5 | HR | UTT2187 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 |  | 25 |  | 6 | 5 | 403 | [16 empty] | 403 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-43000-44148-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-13 | Cleaned site | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS49350 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | CALEB | HOLTON | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | MICHAEL | ANISZEWSKI | Laborer |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 756 | 151 | 156 |  | 12 | 12 | 1063 | [16 empty] | 1063 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | BOLDBAUTOR | ZORIGT | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | JORDAN | WIGGINS | Laborer |  | 13 |  | 1 | Tool Trailer | 10 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 819 | 151 | 50 |  | 13 | 10 | 1020 | [16 empty] | 1020 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | TANNER | BRITT | Laborer |  | 13 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 819 | 151 | 185 |  | 13 | 10 | 1155 | [16 empty] | 1155 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 10 | HR | REX0369 | [11 empty] | 105 |  |  |  | 1050 |  |  | 10 | 1050 | [16 empty] | 1050 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [16 empty] | 460 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44148-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-13 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | JOSHUA | MENDARIES | Operator II |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 498 | 151 | 78 |  | 6 | 6 | 727 | [16 empty] | 727 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | JOSHUA | MENDARIES | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | WAYLON | GREEN | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | THOMASF | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | WAYLON | GREEN | Laborer |  | 5 |  |  | Pickup-F150 or F250 or equal | 4 | HR | THOMASF | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 |  | 52 |  | 5 | 4 | 367 | [16 empty] | 367 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | JOSE | VALLES | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | JOSE | VALLES | Laborer |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 |  | 65 |  | 5 | 5 | 380 | [16 empty] | 380 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | REYMUNDO | REYES | Laborer |  | 6 |  | 1 | Tool Trailer | 6 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 | 151 | 30 |  | 6 | 6 | 559 | [16 empty] | 559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | REYMUNDO | REYES | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | MARCELO | GOMEZ | Laborer |  | 6 |  | 1 | Tool Trailer | 6 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 | 151 | 30 |  | 6 | 6 | 559 | [16 empty] | 559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | MARCELO | GOMEZ | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | EFREM | LEE | Truck Driver/CDL |  | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 | 151 | 96 |  | 6 | 6 | 679 | [16 empty] | 679 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | EFREM | LEE | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | COLTON | ROBERTS | Laborer |  | 6 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 | 151 | 111 |  | 6 | 6 | 640 | [16 empty] | 640 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | COLTON | ROBERTS | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | GAGE | BURKS | Laborer |  | 6 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 | 151 | 111 |  | 6 | 6 | 640 | [16 empty] | 640 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | GAGE | BURKS | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | IAIN | ALLRED | Truck Driver/CDL |  | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 | 151 | 96 |  | 6 | 6 | 679 | [16 empty] | 679 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | IAIN | ALLRED | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | THOMAS | FRANKLIN | Operator II |  | 6 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4074 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 498 | 151 | 543 |  | 6 | 6 | 1192 | [16 empty] | 1192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | THOMAS | FRANKLIN | Operator II |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 332 |  | 362 |  | 4 | 4 | 694 | [16 empty] | 694 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 6 | HR | REX10278 | [11 empty] | 105 |  |  |  | 630 |  |  | 6 | 630 | [16 empty] | 630 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 4 | HR | REX10278 | [11 empty] | 105 |  |  |  | 420 |  |  | 4 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | [7 empty] | Hammer Attachment | 6 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Excavation | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | [7 empty] | Hammer Attachment | 6 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Initial Coating Inspection | 3500028468-81940-44148-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-13 | Jeeped pipe, fixed jeeps. Removed rock and stationed equipment | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JODY | BROOM | Superintendent |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 630 | 151 | 65 |  | 5 | 5 | 846 | [16 empty] | 846 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JODY | BROOM | Superintendent |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 630 |  | 65 |  | 5 | 5 | 695 | [16 empty] | 695 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | TOME | KIRKLAND | Superintendent |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 630 | 151 | 65 |  | 5 | 5 | 846 | [16 empty] | 846 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | TOME | KIRKLAND | Superintendent |  | 7 |  |  | Pickup-F150 or F250 or equal | 7 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 882 |  | 91 |  | 7 | 7 | 973 | [16 empty] | 973 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 525 | 151 | 65 |  | 5 | 5 | 741 | [16 empty] | 741 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 5 |  |  |  | Pickup-F150 or F250 or equal | 5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 525 |  | 65 |  | 5 | 5 | 590 | [16 empty] | 590 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | MICHAEL | GOSS | Truck Driver/CDL |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 360 | 151 | 65 |  | 5 | 5 | 576 | [16 empty] | 576 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | MICHAEL | GOSS | Truck Driver/CDL |  | 7 |  |  | Pickup-F150 or F250 or equal | 7 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 504 |  | 91 |  | 7 | 7 | 595 | [16 empty] | 595 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 360 | 151 | 65 |  | 5 | 5 | 576 | [16 empty] | 576 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 7 |  |  | Pickup-F150 or F250 or equal | 7 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 504 |  | 91 |  | 7 | 7 | 595 | [16 empty] | 595 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JASON | JONES | Truck Driver/CDL |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 360 | 151 | 65 |  | 5 | 5 | 576 | [16 empty] | 576 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JASON | JONES | Truck Driver/CDL |  | 7 |  |  | Pickup-F150 or F250 or equal | 7 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 504 |  | 91 |  | 7 | 7 | 595 | [16 empty] | 595 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 | 151 | 65 |  | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | SCOTT | MERRY | Safety Person |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 | 151 | 65 |  | 5 | 5 | 716 | [16 empty] | 716 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | SCOTT | MERRY | Safety Person |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | DANIEL | YOUNG | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 | 151 | 65 |  | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | DANIEL | YOUNG | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 5 |  |  | 1 | Tractor/Semi | 5 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 494 | 151 | 210 |  | 5 | 5 | 855 | [16 empty] | 855 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 5 |  |  |  | Tractor/Semi | 7 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 494 |  | 294 |  | 5 | 7 | 788 | [16 empty] | 788 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Tractor/Semi | 5 | HR | 1376 | [11 empty] | 42 |  |  |  | 210 |  |  | 5 | 210 | [16 empty] | 210 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Tractor/Semi | 7 | HR | 1376 | [11 empty] | 42 |  |  |  | 294 |  |  | 7 | 294 | [16 empty] | 294 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Tractor/Semi | 5 | HR | R1371 | [11 empty] | 42 |  |  |  | 210 |  |  | 5 | 210 | [16 empty] | 210 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Tractor/Semi | 7 | HR | R1371 | [11 empty] | 42 |  |  |  | 294 |  |  | 7 | 294 | [16 empty] | 294 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Lowboy Trailer | 5 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Lowboy Trailer | 7 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 129.5 |  |  | 7 | 129.5 | [16 empty] | 129.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Lowboy Trailer | 5 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Lowboy Trailer | 7 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 129.5 |  |  | 7 | 129.5 | [16 empty] | 129.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Lowboy Trailer | 5 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Matches crew 6 | [7 empty] | Lowboy Trailer | 7 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 129.5 |  |  | 7 | 129.5 | [16 empty] | 129.5 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | CALEB | HOLTON | Foreman |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1100 | 151 | 143 |  | 11 | 11 | 1394 | [16 empty] | 1394 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | MICHAEL | ANISZEWSKI | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | BOLDBAUTOR | ZORIGT | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | JORDAN | WIGGINS | Laborer |  | 13 |  | 1 | Tool Trailer | 10 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 819 | 151 | 50 |  | 13 | 10 | 1020 | [16 empty] | 1020 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | TANNER | BRITT | Laborer |  | 13 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 819 | 151 | 185 |  | 13 | 10 | 1155 | [16 empty] | 1155 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 10 | HR | REX0369 | [11 empty] | 105 |  |  |  | 1050 |  |  | 10 | 1050 | [16 empty] | 1050 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [16 empty] | 460 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44149-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-14 | Held JHA meeting. Cleaned site and hauled equipment to KY yard. | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | JOSHUA | MENDARIES | Operator II |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 498 | 151 | 78 |  | 6 | 6 | 727 | [16 empty] | 727 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | JOSHUA | MENDARIES | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | WAYLON | GREEN | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | THOMASF | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | WAYLON | GREEN | Laborer |  | 5 |  |  | Pickup-F150 or F250 or equal | 4 | HR | THOMASF | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 |  | 52 |  | 5 | 4 | 367 | [16 empty] | 367 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | JOSE | VALLES | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | JOSE | VALLES | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 65 |  | 4 | 5 | 317 | [16 empty] | 317 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | REYMUNDO | REYES | Laborer |  | 6 |  | 1 | Tool Trailer | 6 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 | 151 | 30 |  | 6 | 6 | 559 | [16 empty] | 559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | REYMUNDO | REYES | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | MARCELO | GOMEZ | Laborer |  | 6 |  | 1 | Tool Trailer | 6 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 | 151 | 30 |  | 6 | 6 | 559 | [16 empty] | 559 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | MARCELO | GOMEZ | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | EFREM | LEE | Truck Driver/CDL |  | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 | 151 | 96 |  | 6 | 6 | 679 | [16 empty] | 679 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | EFREM | LEE | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | COLTON | ROBERTS | Laborer |  | 6 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 | 151 | 111 |  | 6 | 6 | 640 | [16 empty] | 640 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | COLTON | ROBERTS | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | GAGE | BURKS | Laborer |  | 6 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 | 151 | 111 |  | 6 | 6 | 640 | [16 empty] | 640 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | GAGE | BURKS | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | IAIN | ALLRED | Truck Driver/CDL |  | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 | 151 | 96 |  | 6 | 6 | 679 | [16 empty] | 679 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | IAIN | ALLRED | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | THOMAS | FRANKLIN | Operator II |  | 6 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4074 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 498 | 151 | 543 |  | 6 | 6 | 1192 | [16 empty] | 1192 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | THOMAS | FRANKLIN | Operator II |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 61.5 | 83 | 0 | 151 | 90.5 |  | 332 |  | 362 |  | 4 | 4 | 694 | [16 empty] | 694 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 6 | HR | REX10278 | [11 empty] | 105 |  |  |  | 630 |  |  | 6 | 630 | [16 empty] | 630 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 4 | HR | REX10278 | [11 empty] | 105 |  |  |  | 420 |  |  | 4 | 420 | [16 empty] | 420 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | [7 empty] | Hammer Attachment | 6 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Post Repair Assessment | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | [7 empty] | Hammer Attachment | 6 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-16 | 2 | BL |  | Backfill | 3500028468-81940-44149-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-14 | Waited for coating to set up with a Shore D of 80 in order to backfill. Bass excavating hauled (4) load of clean fill material and hauled out (4) loads of rock material. Waiting on more fill material to be hauled in on Monday 11/16/20 | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-04 | ABC 3500028468-04
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | [16 empty] | 1559 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | STEVE | CLARK | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 156 |  | 12 | 12 | 1023 | [16 empty] | 1023 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | JASON | JONES | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 130 |  | 12 | 10 | 997 | [16 empty] | 997 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Tractor/Semi | 12 | HR | 1368 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 658 | 151 | 504 |  | 10 | 12 | 1313 | [16 empty] | 1313 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 12 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 504 |  | 10 | 12 | 1643 | [16 empty] | 1643 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | [7 empty] | Tractor/Semi | 12 | HR | R1371 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Matches crew 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | CALEB | HOLTON | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 444 | 151 | 78 |  | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | CALEB | HOLTON | Foreman | 2 | 4 |  |  | Pickup-F150 or F250 or equal | 6 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 548 |  | 78 |  | 6 | 6 | 626 | [16 empty] | 626 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | BOLDBAUTOR | ZORIGT | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | BOLDBAUTOR | ZORIGT | Laborer | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 283 |  | 65 |  | 5 | 5 | 348 | [16 empty] | 348 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | JORDAN | WIGGINS | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | JORDAN | WIGGINS | Laborer | 2 | 5 |  |  | Tool Trailer | 5 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 409 |  | 25 |  | 7 | 5 | 434 | [16 empty] | 434 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | MATTHEW | SCHMITT | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | [16 empty] | 568 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | MATTHEW | SCHMITT | Truck Driver/CDL | 2 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 323 |  | 80 |  | 5 | 5 | 403 | [16 empty] | 403 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | [7 empty] | 40' Flatbed trailer or equal | 6 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 111 |  |  | 6 | 111 | [16 empty] | 111 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 276 |  |  | 6 | 276 | [16 empty] | 276 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-110-44151-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-16 | Held JHA, covid screening. Cleaned excavators and loaded to be returned to rental company. Finished cleaning site and demob to 1490 | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Seeded, fertilized and layed straw | MICHAEL | ANISZEWSKI | Laborer | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | RCT5164 | Seed Mix | 75 | lbs |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 628 | 151 | 156 | 0 | 12 | 12 | 935 | [16 empty] | 935 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Seeded, fertilized and layed straw | TANNER | BRITT | Laborer | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | MATTHEWL | Fertilizer | 50 | lbs |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 691 | 151 | 156 | 0 | 13 | 12 | 998 | [16 empty] | 998 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44151-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | Seeded, fertilized and layed straw | MATTHEW | LINDLEY | Operator II | 8 | 4 |  | 1 |  |  |  |  | Straw Bales | 28 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 |  | 0 | 824 | 151 |  | 0 | 12 |  | 975 | [16 empty] | 975 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | THOMAS | FRANKLIN | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | WAYLON | GREEN | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | JOSE | VALLES | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | MARCELO | GOMEZ | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | EFREM | LEE | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | COLTON | ROBERTS | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | GAGE | BURKS | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 10 | HR | REX10278 | [11 empty] | 105 |  |  |  | 1050 |  |  | 10 | 1050 | [16 empty] | 1050 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | [7 empty] | Hammer Attachment | 10 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Backfill | 3500028468-81940-44151-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-16 | Hauled (3) loads of backfill dirt and removed (3) loads of rock | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JODY | BROOM | Superintendent | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 467.5 | 151 | 65 |  | 5 | 5 | 683.5 | [16 empty] | 683.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JODY | BROOM | Superintendent | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 532.5 |  | 65 |  | 5 | 5 | 597.5 | [16 empty] | 597.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | TOME | KIRKLAND | Superintendent | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | TOME | [7 empty] | 47 | 126 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | TOME | KIRKLAND | Superintendent | 3 | 4 |  |  | Pickup-F150 or F250 or equal | 7 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 784.5 |  | 91 |  | 7 | 7 | 875.5 | [16 empty] | 875.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 525 | 151 | 65 |  | 5 | 5 | 741 | [16 empty] | 741 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 5 |  |  |  | Pickup-F150 or F250 or equal | 5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 525 |  | 65 |  | 5 | 5 | 590 | [16 empty] | 590 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | STEVE | CLARK | Truck Driver/CDL | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 267.5 | 151 | 65 |  | 5 | 5 | 483.5 | [16 empty] | 483.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | STEVE | CLARK | Truck Driver/CDL | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 304.5 |  | 65 |  | 5 | 5 | 369.5 | [16 empty] | 369.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 267.5 | 151 | 65 |  | 5 | 5 | 483.5 | [16 empty] | 483.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 3 | 4 |  |  | Pickup-F150 or F250 or equal | 7 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 448.5 |  | 91 |  | 7 | 7 | 539.5 | [16 empty] | 539.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JASON | JONES | Truck Driver/CDL | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 267.5 | 151 | 65 |  | 5 | 5 | 483.5 | [16 empty] | 483.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JASON | JONES | Truck Driver/CDL | 3 | 4 |  |  | Pickup-F150 or F250 or equal | 7 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 448.5 |  | 91 |  | 7 | 7 | 539.5 | [16 empty] | 539.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 422 |  | 65 |  | 5 | 5 | 487 | [16 empty] | 487 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | SCOTT | MERRY | Safety Person | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | SCOTT | MERRY | Safety Person | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 422 |  | 65 |  | 5 | 5 | 487 | [16 empty] | 487 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | DANIEL | YOUNG | Operator II | 5 |  |  | 1 | Tractor/Semi | 5 | HR | 1368 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 307.5 | 151 | 210 |  | 5 | 5 | 668.5 | [16 empty] | 668.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | DANIEL | YOUNG | Operator II | 3 | 2 |  |  | Tractor/Semi | 5 | HR | 1368 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 350.5 |  | 210 |  | 5 | 5 | 560.5 | [16 empty] | 560.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 5 |  |  | 1 | Tractor/Semi | 5 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 494 | 151 | 210 |  | 5 | 5 | 855 | [16 empty] | 855 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 5 |  |  |  | Tractor/Semi | 7 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 494 |  | 294 |  | 5 | 7 | 788 | [16 empty] | 788 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | [7 empty] | Tractor/Semi | 5 | HR | R1371 | [11 empty] | 42 |  |  |  | 210 |  |  | 5 | 210 | [16 empty] | 210 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | [7 empty] | Tractor/Semi | 7 | HR | R1371 | [11 empty] | 42 |  |  |  | 294 |  |  | 7 | 294 | [16 empty] | 294 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 7 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 129.5 |  |  | 7 | 129.5 | [16 empty] | 129.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 7 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 129.5 |  |  | 7 | 129.5 | [16 empty] | 129.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44152-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | Cleaned site. Removed all trash. Seeded, fertilized and spread straw. Had (1) load of #8 gravel delivered and spread. | CALEB | HOLTON | Foreman | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | CALEB | Seed Mix | 100 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 1092 | 151 | 169 | 0 | 13 | 13 | 1412 | [16 empty] | 1412 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44152-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | Cleaned site. Removed all trash. Seeded, fertilized and spread straw. Had (1) load of #8 gravel delivered and spread. | MATTHEW | LINDLEY | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | MATTHEWL | Fertilizer | 100 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 824 | 151 | 156 | 0 | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44152-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | Cleaned site. Removed all trash. Seeded, fertilized and spread straw. Had (1) load of #8 gravel delivered and spread. | MICHAEL | ANISZEWSKI | Laborer | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | RCT5164 | Straw Bales | 20 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 691 | 151 | 169 | 0 | 13 | 13 | 1011 | [16 empty] | 1011 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44152-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | Cleaned site. Removed all trash. Seeded, fertilized and spread straw. Had (1) load of #8 gravel delivered and spread. | BOLDBAUTOR | ZORIGT | Laborer | 8 | 4 |  | 1 | Tool Trailer | 12 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 60 |  | 12 | 12 | 839 | [16 empty] | 839 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44152-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | Cleaned site. Removed all trash. Seeded, fertilized and spread straw. Had (1) load of #8 gravel delivered and spread. | JORDAN | WIGGINS | Laborer | 8 | 4 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 628 | 151 | 222 |  | 12 | 12 | 1001 | [16 empty] | 1001 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44152-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | Cleaned site. Removed all trash. Seeded, fertilized and spread straw. Had (1) load of #8 gravel delivered and spread. | TANNER | BRITT | Laborer | 8 | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 628 | 151 | 552 |  | 12 | 12 | 1331 | [16 empty] | 1331 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44152-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | Cleaned site. Removed all trash. Seeded, fertilized and spread straw. Had (1) load of #8 gravel delivered and spread. | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 192 |  | 12 | 12 | 1059 | [16 empty] | 1059 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44152-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | Cleaned site. Removed all trash. Seeded, fertilized and spread straw. Had (1) load of #8 gravel delivered and spread. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 12 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 330 |  |  | 12 | 330 | [16 empty] | 330 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44152-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | Cleaned site. Removed all trash. Seeded, fertilized and spread straw. Had (1) load of #8 gravel delivered and spread. | [7 empty] | Hammer Attachment | 12 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | JONATHAN | HOLLEY | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | JONATHAN | HOLLEY | Foreman | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 422 |  | 65 |  | 5 | 5 | 487 | [16 empty] | 487 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | THOMAS | FRANKLIN | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | THOMAS | FRANKLIN | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | WAYLON | GREEN | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | WAYLON | GREEN | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | JOSE | VALLES | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | JOSE | VALLES | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | MARCELO | GOMEZ | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | MARCELO | GOMEZ | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | EFREM | LEE | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | EFREM | LEE | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | COLTON | ROBERTS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | COLTON | ROBERTS | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | GAGE | BURKS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | GAGE | BURKS | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | IAIN | ALLRED | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | IAIN | ALLRED | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | [7 empty] | Hammer Attachment | 5 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | [7 empty] | Hammer Attachment | 5 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 5 | HR | REX10278 | [11 empty] | 105 |  |  |  | 525 |  |  | 5 | 525 | [16 empty] | 525 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-18 | 2 | BL |  | Demobilization | 3500028468-81940-44152-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-17 | Received (1) load of top soil and removed (1) load of rock. Clean up dig and placed top soil to prepare for seed and mulch. Started moving attachment back to Thompsonville | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 5 | HR | REX10278 | [11 empty] | 105 |  |  |  | 525 |  |  | 5 | 525 | [16 empty] | 525 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44153-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | Seeded and mulched. Loaded material and trash on trailers and cleaned site to demob tomorrow | CALEB | HOLTON | Foreman | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | CALEB | Seed Mix | 50 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 1092 | 151 | 169 | 0 | 13 | 13 | 1412 | [16 empty] | 1412 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44153-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | Seeded and mulched. Loaded material and trash on trailers and cleaned site to demob tomorrow | MATTHEW | LINDLEY | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | MATTHEWL | Fertilizer | 50 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 824 | 151 | 156 | 0 | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44153-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | Seeded and mulched. Loaded material and trash on trailers and cleaned site to demob tomorrow | MICHAEL | ANISZEWSKI | Laborer | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | RCT5164 | Straw Bales | 25 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 691 | 151 | 169 | 0 | 13 | 13 | 1011 | [16 empty] | 1011 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44153-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | Seeded and mulched. Loaded material and trash on trailers and cleaned site to demob tomorrow | BOLDBAUTOR | ZORIGT | Laborer | 8 | 4 |  | 1 | Tool Trailer | 12 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 60 |  | 12 | 12 | 839 | [16 empty] | 839 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44153-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | Seeded and mulched. Loaded material and trash on trailers and cleaned site to demob tomorrow | JORDAN | WIGGINS | Laborer | 8 | 4 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 628 | 151 | 222 |  | 12 | 12 | 1001 | [16 empty] | 1001 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44153-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | Seeded and mulched. Loaded material and trash on trailers and cleaned site to demob tomorrow | TANNER | BRITT | Laborer | 8 | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 628 | 151 | 552 |  | 12 | 12 | 1331 | [16 empty] | 1331 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44153-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | Seeded and mulched. Loaded material and trash on trailers and cleaned site to demob tomorrow | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 192 |  | 12 | 12 | 1059 | [16 empty] | 1059 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44153-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | Seeded and mulched. Loaded material and trash on trailers and cleaned site to demob tomorrow | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 12 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 330 |  |  | 12 | 330 | [16 empty] | 330 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44153-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | Seeded and mulched. Loaded material and trash on trailers and cleaned site to demob tomorrow | [7 empty] | Hammer Attachment | 12 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | JONATHAN | HOLLEY | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JONATHAN | Seed Mix | 50 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | JONATHAN | HOLLEY | Foreman | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JONATHAN | Straw Bales | 20 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 422 |  | 65 | 0 | 5 | 5 | 487 | [16 empty] | 487 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | THOMAS | FRANKLIN | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | THOMAS | FRANKLIN | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | WAYLON | GREEN | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | WAYLON | GREEN | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | JOSE | VALLES | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | JOSE | VALLES | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | MARCELO | GOMEZ | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | MARCELO | GOMEZ | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | EFREM | LEE | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | EFREM | LEE | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | COLTON | ROBERTS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | COLTON | ROBERTS | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | GAGE | BURKS | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | GAGE | BURKS | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | IAIN | ALLRED | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | IAIN | ALLRED | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 5 | HR | REX10278 | [11 empty] | 105 |  |  |  | 525 |  |  | 5 | 525 | [16 empty] | 525 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Seeded and mulched. Moved (3) mats, pup pipe and mop pipe to thompsonville station | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 5 | HR | REX10278 | [11 empty] | 105 |  |  |  | 525 |  |  | 5 | 525 | [16 empty] | 525 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JODY | BROOM | Superintendent | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 467.5 | 151 | 65 |  | 5 | 5 | 683.5 | [16 empty] | 683.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JODY | BROOM | Superintendent | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 532.5 |  | 65 |  | 5 | 5 | 597.5 | [16 empty] | 597.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | TOME | KIRKLAND | Superintendent | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 467.5 | 151 | 65 |  | 5 | 5 | 683.5 | [16 empty] | 683.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | TOME | KIRKLAND | Superintendent | 3 | 4 |  |  | Pickup-F150 or F250 or equal | 7 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 784.5 |  | 91 |  | 7 | 7 | 875.5 | [16 empty] | 875.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 525 | 151 | 65 |  | 5 | 5 | 741 | [16 empty] | 741 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 5 |  |  |  | Pickup-F150 or F250 or equal | 5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 525 |  | 65 |  | 5 | 5 | 590 | [16 empty] | 590 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | STEVE | CLARK | Truck Driver/CDL | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 267.5 | 151 | 65 |  | 5 | 5 | 483.5 | [16 empty] | 483.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | STEVE | CLARK | Truck Driver/CDL | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 304.5 |  | 65 |  | 5 | 5 | 369.5 | [16 empty] | 369.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 267.5 | 151 | 65 |  | 5 | 5 | 483.5 | [16 empty] | 483.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 3 | 4 |  |  | Pickup-F150 or F250 or equal | 7 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 448.5 |  | 91 |  | 7 | 7 | 539.5 | [16 empty] | 539.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JASON | JONES | Truck Driver/CDL | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 267.5 | 151 | 65 |  | 5 | 5 | 483.5 | [16 empty] | 483.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JASON | JONES | Truck Driver/CDL | 3 | 4 |  |  | Pickup-F150 or F250 or equal | 7 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 448.5 |  | 91 |  | 7 | 7 | 539.5 | [16 empty] | 539.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 422 |  | 65 |  | 5 | 5 | 487 | [16 empty] | 487 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | SCOTT | MERRY | Safety Person | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | SCOTT | MERRY | Safety Person | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 422 |  | 65 |  | 5 | 5 | 487 | [16 empty] | 487 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | DANIEL | YOUNG | Operator II | 5 |  |  | 1 | Tractor/Semi | 5 | HR | 1368 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 307.5 | 151 | 210 |  | 5 | 5 | 668.5 | [16 empty] | 668.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | DANIEL | YOUNG | Operator II | 3 | 2 |  |  | Tractor/Semi | 5 | HR | 1368 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 350.5 |  | 210 |  | 5 | 5 | 560.5 | [16 empty] | 560.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 5 |  |  | 1 | Tractor/Semi | 5 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 494 | 151 | 210 |  | 5 | 5 | 855 | [16 empty] | 855 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 5 |  |  |  | Tractor/Semi | 7 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 494 |  | 294 |  | 5 | 7 | 788 | [16 empty] | 788 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | [7 empty] | Tractor/Semi | 5 | HR | R1371 | [11 empty] | 42 |  |  |  | 210 |  |  | 5 | 210 | [16 empty] | 210 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | [7 empty] | Tractor/Semi | 7 | HR | R1371 | [11 empty] | 42 |  |  |  | 294 |  |  | 7 | 294 | [16 empty] | 294 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 7 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 129.5 |  |  | 7 | 129.5 | [16 empty] | 129.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Clean-up / Remediation | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-19 | 2 | BL |  | Demobilization | 3500028468-81940-44153-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | Matches crew 6 | [7 empty] | 40' Flatbed trailer or equal | 7 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 129.5 |  |  | 7 | 129.5 | [16 empty] | 129.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | TOME | KIRKLAND | Superintendent | 4 | 8 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1382 | 151 | 156 |  | 12 | 12 | 1689 | [16 empty] | 1689 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | STEVE | CLARK | Truck Driver/CDL | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 716 | 151 | 130 |  | 12 | 10 | 997 | [16 empty] | 997 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 4 | 8 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 790 | 151 | 156 |  | 12 | 12 | 1097 | [16 empty] | 1097 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | JASON | JONES | Truck Driver/CDL | 4 | 8 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 790 | 151 | 156 |  | 12 | 12 | 1097 | [16 empty] | 1097 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Tractor/Semi | 12 | HR | 1368 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 658 | 151 | 504 |  | 10 | 12 | 1313 | [16 empty] | 1313 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 12 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 504 |  | 10 | 12 | 1643 | [16 empty] | 1643 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | [7 empty] | Tractor/Semi | 12 | HR | R1371 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Matches crew 5 | [7 empty] | Lowboy Trailer | 12 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Loaded everything up and hauled to Thompsonville station | CALEB | HOLTON | Foreman | 2 | 11 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1248 | 151 | 169 |  | 13 | 13 | 1568 | [16 empty] | 1568 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Loaded everything up and hauled to Thompsonville station | MATTHEW | LINDLEY | Operator II | 4 | 8 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | MATTHEWL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 910 | 151 | 156 |  | 12 | 12 | 1217 | [16 empty] | 1217 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Loaded everything up and hauled to Thompsonville station | MICHAEL | ANISZEWSKI | Laborer | 3 | 10 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 771 | 151 | 169 |  | 13 | 13 | 1091 | [16 empty] | 1091 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Loaded everything up and hauled to Thompsonville station | BOLDBAUTOR | ZORIGT | Laborer | 5 | 7 |  | 1 | Tool Trailer | 12 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 676 | 151 | 60 |  | 12 | 12 | 887 | [16 empty] | 887 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Loaded everything up and hauled to Thompsonville station | JORDAN | WIGGINS | Laborer | 3 | 10 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 771 | 151 | 222 |  | 13 | 12 | 1144 | [16 empty] | 1144 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Loaded everything up and hauled to Thompsonville station | TANNER | BRITT | Laborer | 3 | 9 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 708 | 151 | 552 |  | 12 | 12 | 1411 | [16 empty] | 1411 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44154-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-19 | Loaded everything up and hauled to Thompsonville station | MATTHEW | SCHMITT | Truck Driver/CDL | 4 | 8 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 790 | 151 | 192 |  | 12 | 12 | 1133 | [16 empty] | 1133 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | THOMAS | FRANKLIN | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | WAYLON | GREEN | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | JOSE | VALLES | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | MARCELO | GOMEZ | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | EFREM | LEE | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | COLTON | ROBERTS | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | GAGE | BURKS | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44154-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | Moved (2) excavators to Thompsonville yard. Moved tool trailer to yard. Cleaned up area at road. Finished and cleaned up. | [7 empty] | Cat 324/325 Excavator or equal* (53,001 to 65,000 lbs) | 10 | HR | REX10278 | [11 empty] | 105 |  |  |  | 1050 |  |  | 10 | 1050 | [16 empty] | 1050 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [16 empty] | 1541 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | TOME | KIRKLAND | Superintendent |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1512 | 151 | 156 |  | 12 | 12 | 1819 | [16 empty] | 1819 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | STEVE | CLARK | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 130 |  | 12 | 10 | 1145 | [16 empty] | 1145 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 156 |  | 10 | 12 | 1027 | [16 empty] | 1027 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | JASON | JONES | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 130 |  | 12 | 10 | 1145 | [16 empty] | 1145 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | JUANITO | RODRIGUEZ | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | SCOTT | MERRY | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Tractor/Semi | 12 | HR | 1368 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 830 | 151 | 504 |  | 10 | 12 | 1485 | [16 empty] | 1485 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | [7 empty] | Tractor/Semi | 12 | HR | R1371 | [11 empty] | 42 |  |  |  | 504 |  |  | 12 | 504 | [16 empty] | 504 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | [7 empty] | Lowboy Trailer | 12 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Matches crew 6 | [7 empty] | Lowboy Trailer | 12 | HR | 2455 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44155-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | Loaded equipment and hauled to Thompsonville station | CALEB | HOLTON | Foreman |  | 14 |  | 1 | Pickup-F150 or F250 or equal | 14 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1400 | 151 | 182 |  | 14 | 14 | 1733 | [16 empty] | 1733 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44155-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | Loaded equipment and hauled to Thompsonville station | MATTHEW | LINDLEY | Operator II |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | MATTHEWL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 996 | 151 | 156 |  | 12 | 12 | 1303 | [16 empty] | 1303 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44155-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | Loaded equipment and hauled to Thompsonville station | MICHAEL | ANISZEWSKI | Laborer |  | 13 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 819 | 151 | 169 |  | 13 | 13 | 1139 | [16 empty] | 1139 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44155-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | Loaded equipment and hauled to Thompsonville station | BOLDBAUTOR | ZORIGT | Laborer |  | 13 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 819 | 151 | 169 |  | 13 | 13 | 1139 | [16 empty] | 1139 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44155-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | Loaded equipment and hauled to Thompsonville station | JORDAN | WIGGINS | Laborer |  | 13 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 819 | 151 | 552 |  | 13 | 12 | 1522 | [16 empty] | 1522 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44155-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | Loaded equipment and hauled to Thompsonville station | TANNER | BRITT | Laborer |  | 12 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 13 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 756 | 151 | 208 |  | 12 | 13 | 1115 | [16 empty] | 1115 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 3500028468-54330-44155-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | Loaded equipment and hauled to Thompsonville station | MATTHEW | SCHMITT | Truck Driver/CDL |  | 13 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 936 | 151 |  |  | 13 |  | 1087 | [16 empty] | 1087 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Moved off 2088 | JONATHAN | HOLLEY | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Moved off 2088 | THOMAS | FRANKLIN | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Moved off 2088 | WAYLON | GREEN | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Moved off 2088 | JOSE | VALLES | Laborer |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 630 | 151 | 160 |  | 10 | 10 | 941 | [16 empty] | 941 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Moved off 2088 | MARCELO | GOMEZ | Laborer |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | R19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 630 | 151 | 192 |  | 10 | 12 | 973 | [16 empty] | 973 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Moved off 2088 | EFREM | LEE | Truck Driver/CDL |  | 10 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 720 | 151 | 185 |  | 10 | 10 | 1056 | [16 empty] | 1056 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Moved off 2088 | COLTON | ROBERTS | Laborer |  | 10 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 630 | 151 | 185 |  | 10 | 10 | 966 | [16 empty] | 966 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Moved off 2088 | GAGE | BURKS | Laborer |  | 10 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 630 | 151 |  |  | 10 |  | 781 | [16 empty] | 781 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-81940-44155-rev0 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-20 | Moved off 2088 | IAIN | ALLRED | Truck Driver/CDL |  | 12 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 864 | 151 |  |  | 12 |  | 1015 | [16 empty] | 1015 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [16 empty] | 1541 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | TOME | KIRKLAND | Superintendent |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1512 | 151 | 156 |  | 12 | 12 | 1819 | [16 empty] | 1819 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | STEVE | CLARK | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 130 |  | 12 | 10 | 1145 | [16 empty] | 1145 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | JASON | JONES | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | JUANITO | RODRIGUEZ | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | SCOTT | MERRY | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 830 | 151 | 420 |  | 10 | 10 | 1401 | [16 empty] | 1401 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Matches crew 5 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Finished hauling equipment to station and demob | CALEB | HOLTON | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Finished hauling equipment to station and demob | MATTHEW | LINDLEY | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEWL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Finished hauling equipment to station and demob | MICHAEL | ANISZEWSKI | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Finished hauling equipment to station and demob | BOLDBAUTOR | ZORIGT | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Finished hauling equipment to station and demob | JORDAN | WIGGINS | Laborer |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 630 | 151 | 160 |  | 10 | 10 | 941 | [16 empty] | 941 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Finished hauling equipment to station and demob | TANNER | BRITT | Laborer |  | 10 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 630 | 151 |  |  | 10 |  | 781 | [16 empty] | 781 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Demobilization | 3500028468-54330-44156-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-21 | Finished hauling equipment to station and demob | MATTHEW | SCHMITT | Truck Driver/CDL |  | 10 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 720 | 151 |  |  | 10 |  | 871 | [16 empty] | 871 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1489 - MC.400216.032 - 667.112 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Repair - Install Sleeve | 7 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | [32 empty] | STATE LINE SERVICE | 1 | WELDING | 600 | 48 | 12 | 660 | [9 empty] | 660 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-30 | [32 empty] | DAY AND DAY FEED | 412887 | STRAW | 257.57 | 20.6056 | 15.45 | 293.6256 | [9 empty] | 293.6256 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | [32 empty] | HAYDON MATERIALS | 192771 | STONE | 386.31 | 30.9048 | 23.18 | 440.3948 | [9 empty] | 440.3948 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | [32 empty] | BURKMANN FEEDS | 362515 | FERTILIZER/LIME | 107.04 | 8.5632 |  | 115.6032 | [9 empty] | 115.6032 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Prep | 7 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-28 | [32 empty] | TRACTOR SUPPLY | 414461 | SAFETY FENCE | 121.77 | 9.7416 | 8.52 | 140.0316 | [9 empty] | 140.0316 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Prep | 7 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | [32 empty] | TRACTOR SUPPLY | 414097 | T-POSTS | 65.8 | 5.264 | 4.61 | 75.674 | [9 empty] | 75.674 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Access | 7 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-29 | [32 empty] | BIG JOHNS PORTABLE TOILETS | 20740 | PORT-A-CANS | 145 | 11.6 |  | 156.6 | [9 empty] | 156.6 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | [32 empty] | LOWES | 1550 | QUICKRETE | 4.75 | 0.38 | 0.33 | 5.46 | [9 empty] | 5.46 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | [32 empty] | ENERGY CULVERT CO | 1163 | CURLEX | 492.54 | 39.4032 |  | 531.9432 | [9 empty] | 531.9432 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-06 | [32 empty] | ENERGY CULVERT CO | 20201182 | DBL NET STRAW | 272 | 21.76 | 22.44 | 316.2 | [9 empty] | 316.2 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-27 | [32 empty] | SPRING VALLEY | 10366430 | SEED | 78.92 | 6.3136 | 5.52 | 90.7536 | [9 empty] | 90.7536 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-02 | [32 empty] | DAY AND DAY FEED | 413303 | SEED/STRAW/LIME/FERT | 252.54 | 20.2032 | 15.15 | 287.8932 | [9 empty] | 287.8932 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-03 | [32 empty] | LOWES | 2570 | ASPHALT | 104.8 | 8.384 | 6.29 | 119.474 | [9 empty] | 119.474 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-06 | [32 empty] | DAY AND DAY FEED | 413796 | SEED | 205.98 | 16.4784 | 12.36 | 234.8184 | [9 empty] | 234.8184 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | [32 empty] | BURKMANN FEEDS | 363145 | SEED | 105.07 | 8.4056 |  | 113.4756 | [9 empty] | 113.4756 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | [32 empty] | HINKLE CONTRACTING | 503041063 | STONE | 384.38 | 30.7504 | 23.06 | 438.1904 | [9 empty] | 438.1904 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | [32 empty] | HINKLE CONTRACTING | 503041094 | STONE | 406.25 | 32.5 | 24.38 | 463.13 | [9 empty] | 463.13 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | [32 empty] | HINKLE CONTRACTING | 503041088 | STONE | 397.78 | 31.8224 | 23.87 | 453.4724 | [9 empty] | 453.4724 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-05 | [32 empty] | HINKLE CONTRACTING | 503041113 | STONE | 398.09 | 31.8472 | 23.89 | 453.8272 | [9 empty] | 453.8272 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-07 | [32 empty] | BURKMANN FEEDS | 481875 | STRAW | 240 | 19.2 |  | 259.2 | [9 empty] | 259.2 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | [32 empty] | DAY AND DAY FEED | 413776 | SEED/FERTILIZER | 417.57 | 33.4056 | 25.05 | 476.0256 | [9 empty] | 476.0256 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Prep | 7 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-31 | [32 empty] | ACE HARDWARE | 17177 | VISQUEEN | 159.98 | 12.7984 | 9.6 | 182.3784 | [9 empty] | 182.3784 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-02 | [32 empty] | SOUTHERN STATES | 11022020 | STRAW/SEED | 217.77 | 17.4216 | 13.06 | 248.2516 | [9 empty] | 248.2516 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-09 | [32 empty] | JEFFRIES FEED AND SEED | 415319 | SEED/FERTILIZER | 910 | 72.8 | 54.6 | 1037.4 | [9 empty] | 1037.4 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Prep | 7 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-30 | [32 empty] | LOWES | 4882 | VISQUEEN | 199.96 | 15.9968 | 12 | 227.9568 | [9 empty] | 227.9568 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1778 - MC.400216.085 - 384.804 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Access | 7 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | [32 empty] | CENTRAL KY OUTHOUSES | 10272020 | PORT-A-CANS | 159 | 12.72 |  | 171.72 | [9 empty] | 171.72 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-05 | [32 empty] | JEFFRIES FEED AND SEED | 415138 | STRAW/LIME/FERTILIZER | 218.8 | 17.504 | 13.13 | 249.43 | [9 empty] | 249.43 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1778 - MC.400216.085 - 384.804 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Prep | 7 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | [32 empty] | TRACTOR SUPPLY | 482011 | SAFETY FENCE/VISQUEEN | 283.75 | 22.7 | 17.03 | 323.48 | [9 empty] | 323.48 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Prep | 7 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-11 | [32 empty] | TRACTOR SUPPLY | 311753 | SOLAR FENCE | 182.46 | 14.5968 | 17.79 | 214.8468 | [9 empty] | 214.8468 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | [32 empty] | JEFFRIES FEED AND SEED | 414821 | SEED/STRAW/LIME/FERT | 167.3 | 13.384 | 10.04 | 190.724 | [9 empty] | 190.724 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | [32 empty] | JEFFRIES FEED AND SEED | 414821 | SEED/STRAW/LIME/FERT | 167.3 | 13.384 | 10.04 | 190.724 | [9 empty] | 190.724 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1475 - MC.400216.032 - 654.578 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Repair - Install Sleeve | 7 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | [32 empty] | L&N WELDING | 10232020 | WELDING BUTTER BARS | 840.25 | 67.22 |  | 907.47 | [9 empty] | 907.47 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Repair - Install Sleeve | 7 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | [32 empty] | L&N WELDING | 10232020 | WELDING BUTTER BARS | 840.25 | 67.22 |  | 907.47 | [9 empty] | 907.47 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Prep | 7 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-10-29 | [32 empty] | HOME DEPOT | 2318 | VISQUEEN | 39.99 | 3.1992 | 2.4 | 45.5892 | [9 empty] | 45.5892 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Prep | 7 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-29 | [32 empty] | HOME DEPOT | 2318 | VISQUEEN | 39.99 | 3.1992 | 2.4 | 45.5892 | [9 empty] | 45.5892 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Site Prep | 7 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-25 | [32 empty] | LOWES | 8550 | SAFETY FENCE/TPOSTS | 336.42 | 26.9136 | 20.19 | 383.5236 | [9 empty] | 383.5236 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-04 | [32 empty] | KIRBY HARDWARE | 11042020 | SEED/SEED MATERIAL | 58.67 | 4.6936 | 4.11 | 67.4736 | [9 empty] | 67.4736 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-23 | 2 | BL |  | Clean-up / Remediation | 7 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-04 | [32 empty] | KIRBY HARDWARE | 11042020 | SEED/SEED MATERIAL | 58.67 | 4.6936 | 4.11 | 67.4736 | [9 empty] | 67.4736 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Site Access | 8 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-10 | [32 empty] | CENTRAL KY OUTHOUSES | 11102020 | PORT-A-CANS | 59.63 | 4.7704 | 0 | 64.4004 | [9 empty] | 64.4004 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Site Access | 8 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-10 | [32 empty] | CENTRAL KY OUTHOUSES | 11102020 | PORT-A-CANS | 59.63 | 4.7704 |  | 64.4004 | [9 empty] | 64.4004 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Site Access | 8 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-10 | [32 empty] | CENTRAL KY OUTHOUSES | 11102020 | PORT-A-CANS | 59.63 | 4.7704 |  | 64.4004 | [9 empty] | 64.4004 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Site Access | 8 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-10 | [32 empty] | CENTRAL KY OUTHOUSES | 11102020 | PORT-A-CANS | 59.63 | 4.7704 |  | 64.4004 | [9 empty] | 64.4004 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-18 | [32 empty] | LAWRENCE COUNTY LANDFILL | 311900 | DUMP FEE | 58.18 | 4.6544 |  | 62.8344 | [9 empty] | 62.8344 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | [32 empty] | LAWRENCE COUNTY LANDFILL | 311900 | DUMP FEE | 58.18 | 4.6544 |  | 62.8344 | [9 empty] | 62.8344 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-09 | [32 empty] | MORRIS TRUCKING | 1257 | TOP SOIL | 3900 | 312 | 273 | 4485 | [9 empty] | 4485 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-11 | [32 empty] | MORRIS TRUCKING | 1263 | TOP SOIL | 2792.7 | 223.416 |  | 3016.116 | [9 empty] | 3016.116 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-10 | [32 empty] | MORRIS TRUCKING | 1260 | ROCK | 2086.5 | 166.92 |  | 2253.42 | [9 empty] | 2253.42 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-10 | [32 empty] | TRACTOR SUPPLY | 428393 | CATTLE GATE | 157.43 | 12.5944 | 9.45 | 179.4744 | [9 empty] | 179.4744 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | [32 empty] | FLINN FARMS | 106536 | SEED.FERT.STRAW | 252.5 | 20.2 | 17.68 | 290.38 | [9 empty] | 290.38 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | [32 empty] | PREMIER CO | 3755048 | SEED.FERT.STRAW | 222.9 | 17.832 | 15.61 | 256.342 | [9 empty] | 256.342 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-16 | [32 empty] | FLINN FARMS | 11 | STRAW BALES | 74.9 | 5.992 |  | 80.89 | [9 empty] | 80.89 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | [32 empty] | LAWRENCE CO FARM SUPPLY | 47173 | STRAW BALES | 70 | 5.6 | 4.9 | 80.5 | [9 empty] | 80.5 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-17 | [32 empty] | FLINN FARMS | 106556 | FERT. STRAW | 83.5 | 6.68 | 5.85 | 96.03 | [9 empty] | 96.03 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | [32 empty] | LOWES | 11198 | H-BRACE MATERIAL | 92.05 | 7.364 | 8.97 | 108.384 | [9 empty] | 108.384 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | [32 empty] | LAWRENCE CO FARM SUPPLY | 47182 | STRAW BALES | 74.9 | 5.992 |  | 80.892 | [9 empty] | 80.892 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | [32 empty] | LAWRENCE CO LANDFILL | 312205 | DUMP FEE | 30.51 | 2.4408 |  | 32.9508 | [9 empty] | 32.9508 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | [32 empty] | LAWRENCE CO LANDFILL | 312196 | DUMP FEE | 41.01 | 3.2808 |  | 44.2908 | [9 empty] | 44.2908 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | [32 empty] | BURKMANN FEED | 481820 | BARBED STAPLES | 15.5 | 1.24 |  | 16.74 | [9 empty] | 16.74 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-25 | 2 | BL |  | Clean-up / Remediation | 8 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-06 | [32 empty] | STRAW | 481819 | STRAW BALES | 240 | 19.2 |  | 259.2 | [9 empty] | 259.2 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Pipe Preparation | 9 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-18 | [32 empty] | CROSS COUNTRY | 4081846 | SAND FOR BLASTING | 406 | 32.48 | 24.36 | 462.84 | [9 empty] | 462.84 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Clean-up / Remediation | 9 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-17 | [32 empty] | TEMPLE & TEMPLE | 10834 | DIRT/ROCK | 12050 | 964 |  | 13014 | [9 empty] | 13014 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Clean-up / Remediation | 9 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-19 | [32 empty] | BASS TRUCKING | 202092 | DIRT/TOPSOIL | 3407.5 | 272.6 |  | 3680.1 | [9 empty] | 3680.1 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Mobilization | 9 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | [32 empty] | TROPHY LOGISTICS | 2827 | TRUCKING-MATS | 3300 | 264 |  | 3564 | [9 empty] | 3564 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Site Prep | 9 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-22 | [32 empty] | HERC RENTALS | 31761007-001 | FORKLIFT | 530 | 42.4 | 31.8 | 604.2 | [9 empty] | 604.2 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Site Prep | 9 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-22 | [32 empty] | HERC RENTALS | 31761007-001 | FORKLIFT | 530 | 42.4 | 31.8 | 604.2 | [9 empty] | 604.2 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Site Prep | 9 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-11-22 | [32 empty] | HERC RENTALS | 31761007-001 | FORKLIFT | 530 | 42.4 | 31.8 | 604.2 | [9 empty] | 604.2 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-01 | 2 | BL |  | Site Prep | 9 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-22 | [32 empty] | HERC RENTALS | 31761007-001 | FORKLIFT | 530 | 42.4 | 31.8 | 604.2 | [9 empty] | 604.2 | ABC 3500028468-05 | ABC 3500028468-05
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742455001 | LIGHT PLANT | 700 | 56 | 42 | 798 | [8 empty] | 3% | 774.06 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742529001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742529001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742529001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742529001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742529001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742535001 | LIGHT PLANT | 116.67 | 9.3336 | 7 | 133.0036 | [8 empty] | 3% | 129.0135 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742535001 | LIGHT PLANT | 116.67 | 9.3336 | 7 | 133.0036 | [8 empty] | 3% | 129.0135 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742535001 | LIGHT PLANT | 116.67 | 9.3336 | 7 | 133.0036 | [8 empty] | 3% | 129.0135 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742535001 | LIGHT PLANT | 116.67 | 9.3336 | 7 | 133.0036 | [8 empty] | 3% | 129.0135 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742535001 | LIGHT PLANT | 116.67 | 9.3336 | 7 | 133.0036 | [8 empty] | 3% | 129.0135 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742535001 | LIGHT PLANT | 116.67 | 9.3336 | 7 | 133.0036 | [8 empty] | 3% | 129.0135 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742539001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742539001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1465 - MC.400216.032 - 629.925 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742539001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742539001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742539001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721477002 | SKID STEER | 644 | 51.52 | 38.64 | 734.16 | [8 empty] | 3% | 712.1352 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721477002 | SKID STEER | 644 | 51.52 | 38.64 | 734.16 | [8 empty] | 3% | 712.1352 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721477002 | SKID STEER | 644 | 51.52 | 38.64 | 734.16 | [8 empty] | 3% | 712.1352 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721477002 | SKID STEER | 644 | 51.52 | 38.64 | 734.16 | [8 empty] | 3% | 712.1352 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721477002 | SKID STEER | 644 | 51.52 | 38.64 | 734.16 | [8 empty] | 3% | 712.1352 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721530002 | SKID STEER | 425.36 | 34.0288 | 25.52 | 484.9088 | [8 empty] | 3% | 470.3615 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721530002 | SKID STEER | 425.36 | 34.0288 | 25.52 | 484.9088 | [8 empty] | 3% | 470.3615 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721530002 | SKID STEER | 425.36 | 34.0288 | 25.52 | 484.9088 | [8 empty] | 3% | 470.3615 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721530002 | SKID STEER | 425.36 | 34.0288 | 25.52 | 484.9088 | [8 empty] | 3% | 470.3615 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721530002 | SKID STEER | 425.36 | 34.0288 | 25.52 | 484.9088 | [8 empty] | 3% | 470.3615 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721530002 | SKID STEER | 425.36 | 34.0288 | 25.52 | 484.9088 | [8 empty] | 3% | 470.3615 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1466 - MC.400216.032 - 635.962 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721561002 | SKID STEER | 498.21 | 39.8568 | 29.89 | 567.9568 | [8 empty] | 3% | 550.9181 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721561002 | SKID STEER | 498.21 | 39.8568 | 29.89 | 567.9568 | [8 empty] | 3% | 550.9181 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721561002 | SKID STEER | 498.21 | 39.8568 | 29.89 | 567.9568 | [8 empty] | 3% | 550.9181 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721561002 | SKID STEER | 498.21 | 39.8568 | 29.89 | 567.9568 | [8 empty] | 3% | 550.9181 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1476 - MC.400216.032 - 655.884 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721561002 | SKID STEER | 498.21 | 39.8568 | 29.89 | 567.9568 | [8 empty] | 3% | 550.9181 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742429001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742429001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742429001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742429001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742429001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742330001 | LIGHT PLANT | 175 | 14 | 10.5 | 199.5 | [8 empty] | 3% | 193.515 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742330001 | LIGHT PLANT | 175 | 14 | 10.5 | 199.5 | [8 empty] | 3% | 193.515 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742330001 | LIGHT PLANT | 175 | 14 | 10.5 | 199.5 | [8 empty] | 3% | 193.515 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742330001 | LIGHT PLANT | 175 | 14 | 10.5 | 199.5 | [8 empty] | 3% | 193.515 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742334001 | LIGHT PLANT | 175 | 14 | 10.5 | 199.5 | [8 empty] | 3% | 193.515 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742334001 | LIGHT PLANT | 175 | 14 | 10.5 | 199.5 | [8 empty] | 3% | 193.515 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742334001 | LIGHT PLANT | 175 | 14 | 10.5 | 199.5 | [8 empty] | 3% | 193.515 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1778 - MC.400216.085 - 384.804 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742334001 | LIGHT PLANT | 175 | 14 | 10.5 | 199.5 | [8 empty] | 3% | 193.515 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742327001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742327001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742327001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742327001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Site Access | 10 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-23 | [32 empty] | HERC RENTALS | 31742327001 | LIGHT PLANT | 140 | 11.2 | 8.4 | 159.6 | [8 empty] | 3% | 154.812 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721542002 | SKID STEER | 522.43 | 41.7944 | 31.35 | 595.5744 | [8 empty] | 3% | 577.7072 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721542002 | SKID STEER | 522.43 | 41.7944 | 31.35 | 595.5744 | [8 empty] | 3% | 577.7072 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721542002 | SKID STEER | 522.43 | 41.7944 | 31.35 | 595.5744 | [8 empty] | 3% | 577.7072 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721542002 | SKID STEER | 522.43 | 41.7944 | 31.35 | 595.5744 | [8 empty] | 3% | 577.7072 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721542002 | SKID STEER | 522.43 | 41.7944 | 31.35 | 595.5744 | [8 empty] | 3% | 577.7072 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-23 | [32 empty] | HERC RENTALS | 31744398002 | SKID STEER | 359.2 | 28.736 | 21.55 | 409.486 | [8 empty] | 3% | 397.2014 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-23 | [32 empty] | HERC RENTALS | 31744398002 | SKID STEER | 359.2 | 28.736 | 21.55 | 409.486 | [8 empty] | 3% | 397.2014 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-23 | [32 empty] | HERC RENTALS | 31744398002 | SKID STEER | 359.2 | 28.736 | 21.55 | 409.486 | [8 empty] | 3% | 397.2014 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-23 | [32 empty] | HERC RENTALS | 31744398002 | SKID STEER | 359.2 | 28.736 | 21.55 | 409.486 | [8 empty] | 3% | 397.2014 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721453002 | SKID STEER | 508.89 | 40.7112 | 30.53 | 580.1312 | [8 empty] | 3% | 562.7273 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721453002 | SKID STEER | 508.89 | 40.7112 | 30.53 | 580.1312 | [8 empty] | 3% | 562.7273 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721453002 | SKID STEER | 508.89 | 40.7112 | 30.53 | 580.1312 | [8 empty] | 3% | 562.7273 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721453002 | SKID STEER | 508.89 | 40.7112 | 30.53 | 580.1312 | [8 empty] | 3% | 562.7273 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Clean-up / Remediation | 10 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-24 | [32 empty] | HERC RENTALS | 31721453002 | SKID STEER | 508.89 | 40.7112 | 30.53 | 580.1312 | [8 empty] | 3% | 562.7273 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375893 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375893 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375893 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375893 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375893 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411001 | COMPRESSOR | 328.3 | 26.264 | 30.37 | 384.934 | [8 empty] | 3% | 373.386 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411001 | COMPRESSOR | 328.3 | 26.264 | 30.37 | 384.934 | [8 empty] | 3% | 373.386 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411001 | COMPRESSOR | 328.3 | 26.264 | 30.37 | 384.934 | [8 empty] | 3% | 373.386 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411001 | COMPRESSOR | 328.3 | 26.264 | 30.37 | 384.934 | [8 empty] | 3% | 373.386 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411001 | COMPRESSOR | 328.3 | 26.264 | 30.37 | 384.934 | [8 empty] | 3% | 373.386 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-11-24 | [32 empty] | HERC RENTALS | 31740281001 | EXCAVATOR | 2461.63 | 196.9304 | 147.7 | 2806.2604 | [8 empty] | 3% | 2722.0726 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-11-24 | [32 empty] | HERC RENTALS | 31740281001 | EXCAVATOR | 2461.63 | 196.9304 | 147.7 | 2806.2604 | [8 empty] | 3% | 2722.0726 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-11-24 | [32 empty] | HERC RENTALS | 31740281001 | EXCAVATOR | 2461.63 | 196.9304 | 147.7 | 2806.2604 | [8 empty] | 3% | 2722.0726 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-11-24 | [32 empty] | HERC RENTALS | 31740281001 | EXCAVATOR | 2461.63 | 196.9304 | 147.7 | 2806.2604 | [8 empty] | 3% | 2722.0726 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411002 | SANDPOT | 319 | 25.52 | 29.51 | 374.03 | [8 empty] | 3% | 362.8091 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411002 | SANDPOT | 319 | 25.52 | 29.51 | 374.03 | [8 empty] | 3% | 362.8091 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411002 | SANDPOT | 319 | 25.52 | 29.51 | 374.03 | [8 empty] | 3% | 362.8091 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411002 | SANDPOT | 319 | 25.52 | 29.51 | 374.03 | [8 empty] | 3% | 362.8091 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-23 | [32 empty] | HERC RENTALS | 31743411002 | SANDPOT | 319 | 25.52 | 29.51 | 374.03 | [8 empty] | 3% | 362.8091 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1468 - MC.400216.032 - 646.814 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Mobilization | 10 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-12-01 | [32 empty] | TROPHY LOGISTICS | 2828 | TRUCKING | 181.25 | 14.5 |  | 195.75 | [8 empty] | 3% | 189.8775 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375867 | EXCAVATOR | 1504.5 | 120.36 | 88.5 | 1713.36 | [8 empty] | 3% | 1661.9592 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375867 | EXCAVATOR | 1504.5 | 120.36 | 88.5 | 1713.36 | [8 empty] | 3% | 1661.9592 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375867 | EXCAVATOR | 1504.5 | 120.36 | 88.5 | 1713.36 | [8 empty] | 3% | 1661.9592 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375867 | EXCAVATOR | 1504.5 | 120.36 | 88.5 | 1713.36 | [8 empty] | 3% | 1661.9592 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375892 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375892 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375892 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375892 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375892 | EXCAVATOR | 1742.98 | 139.4384 | 102.53 | 1984.9484 | [8 empty] | 3% | 1925.3999 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375866 | EXCAVATOR | 3009 | 240.72 | 177 | 3426.72 | [8 empty] | 3% | 3323.9184 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375866 | EXCAVATOR | 3009 | 240.72 | 177 | 3426.72 | [8 empty] | 3% | 3323.9184 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375865 | EXCAVATOR | 1203.6 | 96.288 | 70.8 | 1370.688 | [8 empty] | 3% | 1329.5674 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375865 | EXCAVATOR | 1203.6 | 96.288 | 70.8 | 1370.688 | [8 empty] | 3% | 1329.5674 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375865 | EXCAVATOR | 1203.6 | 96.288 | 70.8 | 1370.688 | [8 empty] | 3% | 1329.5674 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375865 | EXCAVATOR | 1203.6 | 96.288 | 70.8 | 1370.688 | [8 empty] | 3% | 1329.5674 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375865 | EXCAVATOR | 1203.6 | 96.288 | 70.8 | 1370.688 | [8 empty] | 3% | 1329.5674 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721818002 | COMPRESSOR | 349.55 | 27.964 | 20.97 | 398.484 | [8 empty] | 3% | 386.5295 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721818002 | COMPRESSOR | 349.55 | 27.964 | 20.97 | 398.484 | [8 empty] | 3% | 386.5295 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721818002 | COMPRESSOR | 349.55 | 27.964 | 20.97 | 398.484 | [8 empty] | 3% | 386.5295 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721818002 | COMPRESSOR | 349.55 | 27.964 | 20.97 | 398.484 | [8 empty] | 3% | 386.5295 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-23 | [32 empty] | HERC RENTALS | 31745516001 | COMPRESSOR | 427.52 | 34.2016 | 39.55 | 501.2716 | [8 empty] | 3% | 486.2335 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-23 | [32 empty] | HERC RENTALS | 31745516001 | COMPRESSOR | 427.52 | 34.2016 | 39.55 | 501.2716 | [8 empty] | 3% | 486.2335 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-23 | [32 empty] | HERC RENTALS | 31745516001 | COMPRESSOR | 427.52 | 34.2016 | 39.55 | 501.2716 | [8 empty] | 3% | 486.2335 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-23 | [32 empty] | HERC RENTALS | 31745516001 | COMPRESSOR | 427.52 | 34.2016 | 39.55 | 501.2716 | [8 empty] | 3% | 486.2335 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721791002 | COMPRESSOR | 361.58 | 28.9264 | 21.7 | 412.2064 | [8 empty] | 3% | 399.8402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721791002 | COMPRESSOR | 361.58 | 28.9264 | 21.7 | 412.2064 | [8 empty] | 3% | 399.8402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721791002 | COMPRESSOR | 361.58 | 28.9264 | 21.7 | 412.2064 | [8 empty] | 3% | 399.8402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-23 | [32 empty] | HERC RENTALS | 31721791002 | COMPRESSOR | 361.58 | 28.9264 | 21.7 | 412.2064 | [8 empty] | 3% | 399.8402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-23 | [32 empty] | HERC RENTALS | 31745516002 | SANDPOT | 398.75 | 31.9 | 36.89 | 467.54 | [8 empty] | 3% | 453.5138 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-23 | [32 empty] | HERC RENTALS | 31745516002 | SANDPOT | 398.75 | 31.9 | 36.89 | 467.54 | [8 empty] | 3% | 453.5138 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-23 | [32 empty] | HERC RENTALS | 31745516002 | SANDPOT | 398.75 | 31.9 | 36.89 | 467.54 | [8 empty] | 3% | 453.5138 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Pipe Preparation | 10 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-23 | [32 empty] | HERC RENTALS | 31745516002 | SANDPOT | 398.75 | 31.9 | 36.89 | 467.54 | [8 empty] | 3% | 453.5138 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-23 | [32 empty] | HERC RENTALS | 31741922001 | EXCAVATOR | 1480.76 | 118.4608 | 88.5 | 1687.7208 | [8 empty] | 3% | 1637.0892 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-23 | [32 empty] | HERC RENTALS | 31741922001 | EXCAVATOR | 1480.76 | 118.4608 | 88.5 | 1687.7208 | [8 empty] | 3% | 1637.0892 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-23 | [32 empty] | HERC RENTALS | 31741922001 | EXCAVATOR | 1480.76 | 118.4608 | 88.5 | 1687.7208 | [8 empty] | 3% | 1637.0892 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-07 | 2 | BL |  | Excavation | 10 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-23 | [32 empty] | HERC RENTALS | 31741922001 | EXCAVATOR | 1480.76 | 118.4608 | 88.5 | 1687.7208 | [8 empty] | 3% | 1637.0892 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | TOME | KIRKLAND | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [15 empty] | 3% | 1291.07 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | JASON | JONES | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEW | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [15 empty] | 3% | 910.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Tractor/Semi | 0 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 658 | 151 | 0 |  | 10 | 0 | 809 | [15 empty] | 3% | 784.73 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Lowboy Trailer | 0 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 988 | 151 | 0 |  | 10 | 0 | 1139 | [15 empty] | 3% | 1104.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Tractor/Semi | 0 | HR | 1376 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Lowboy Trailer | 0 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Tractor/Semi | 0 | HR | 1368 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Lowboy Trailer | 0 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | CALEB | HOLTON | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | JORDAN | WIGGINS | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [15 empty] | 3% | 759.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19120 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Tool Trailer | 10 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | [7 empty] | Tool Trailer | 10 | HR | 2178 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1663 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44173-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-08 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH2986 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | TOME | KIRKLAND | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [15 empty] | 3% | 1291.07 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | JASON | JONES | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEW | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [15 empty] | 3% | 910.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Tractor/Semi | 0 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 658 | 151 | 0 |  | 10 | 0 | 809 | [15 empty] | 3% | 784.73 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Lowboy Trailer | 0 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 988 | 151 | 0 |  | 10 | 0 | 1139 | [15 empty] | 3% | 1104.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Tractor/Semi | 0 | HR | 1376 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Lowboy Trailer | 0 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Tractor/Semi | 0 | HR | 1368 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Lowboy Trailer | 0 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | CALEB | HOLTON | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | JORDAN | WIGGINS | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [15 empty] | 3% | 759.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19120 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | [7 empty] | Tool Trailer | 10 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Tool Trailer | 10 | HR | 2178 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1663 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH2986 | [35 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [15 empty] | 3% | 1494.77 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | TOME | KIRKLAND | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [15 empty] | 3% | 1494.77 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [15 empty] | 3% | 1291.07 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [15 empty] | 3% | 970.97 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [15 empty] | 3% | 970.97 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | JASON | JONES | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEW | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [15 empty] | 3% | 970.97 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | SCOTT | MERRY | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [15 empty] | 3% | 1077.67 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | MATTHEW | LINDLEY | Operator II |  | 10 |  | 1 | Tractor/Semi | 0 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 830 | 151 | 0 |  | 10 | 0 | 981 | [15 empty] | 3% | 951.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Lowboy Trailer | 0 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 988 | 151 | 0 |  | 10 | 0 | 1139 | [15 empty] | 3% | 1104.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Tractor/Semi | 0 | HR | 1376 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Lowboy Trailer | 0 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Tractor/Semi | 0 | HR | 1368 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Lowboy Trailer | 0 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | CALEB | HOLTON | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19120 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Tool Trailer | 10 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | JONATHAN | HOLLEY | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | [7 empty] | Tool Trailer | 10 | HR | 2178 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1663 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44170-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-05 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | TOME | KIRKLAND | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [15 empty] | 3% | 1291.07 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | JASON | JONES | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEW | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [15 empty] | 3% | 910.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Tractor/Semi | 0 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 658 | 151 | 0 |  | 10 | 0 | 809 | [15 empty] | 3% | 784.73 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Lowboy Trailer | 0 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 988 | 151 | 0 |  | 10 | 0 | 1139 | [15 empty] | 3% | 1104.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Tractor/Semi | 0 | HR | 1376 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Lowboy Trailer | 0 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Tractor/Semi | 0 | HR | 1368 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Lowboy Trailer | 0 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | CALEB | HOLTON | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19120 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | Tool Trailer | 10 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Tool Trailer | 10 | HR | 2178 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1663 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | TOME | KIRKLAND | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [15 empty] | 3% | 1291.07 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [15 empty] | 3% | 910.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 658 | 151 | 420 |  | 10 | 10 | 1229 | [15 empty] | 3% | 1192.13 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 988 | 151 | 185 |  | 10 | 10 | 1324 | [15 empty] | 3% | 1284.28 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | CALEB | HOLTON | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19120 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | Tool Trailer | 10 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | [7 empty] | Tool Trailer | 10 | HR | 2178 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1663 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | TOME | KIRKLAND | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [15 empty] | 3% | 1291.07 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [15 empty] | 3% | 910.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 658 | 151 | 420 |  | 10 | 10 | 1229 | [15 empty] | 3% | 1192.13 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 988 | 151 | 185 |  | 10 | 10 | 1324 | [15 empty] | 3% | 1284.28 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | CALEB | HOLTON | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19120 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | Tool Trailer | 10 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | [7 empty] | Tool Trailer | 10 | HR | 2178 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1663 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | TOME | KIRKLAND | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [15 empty] | 3% | 1291.07 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15272 | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | SCOTT | MERRY | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [15 empty] | 3% | 910.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 658 | 151 | 420 |  | 10 | 10 | 1229 | [15 empty] | 3% | 1192.13 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 988 | 151 | 185 |  | 10 | 10 | 1324 | [15 empty] | 3% | 1284.28 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | CALEB | HOLTON | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | RCT5164 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19120 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | Tool Trailer | 10 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | 19115 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [15 empty] | 3% | 126.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | [7 empty] | Tool Trailer | 10 | HR | 2178 | [11 empty] | 5 |  |  |  | 50 |  |  | 10 | 50 | [15 empty] | 3% | 48.5 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [15 empty] | 3% | 877.85 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1663 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [15 empty] | 3% | 446.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [15 empty] | 3% | 266.75 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | [7 empty] | Hammer Attachment | 10 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Stand by | [7 empty] | Brush Hog | 10 | HR | RBH2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Clean-up / Remediation | 11 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-17 | [32 empty] | SUNBELT RENTALS | 107134849001 | SWEEPER | 627.61 | 219.6635 | 43.45 | 890.7235 | [8 empty] | 3% | 864.0018 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Clean-up / Remediation | 11 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375896 | PADDING BUCKET | 833.5 | 291.725 | 50.01 | 1175.235 | [8 empty] | 3% | 1139.9779 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375908 | HAMMER ATTCHMENT | 1400 | 490 | 84 | 1974 | [8 empty] | 3% | 1914.78 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375908 | HAMMER ATTCHMENT | 1400 | 490 | 84 | 1974 | [8 empty] | 3% | 1914.78 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375908 | HAMMER ATTCHMENT | 1400 | 490 | 84 | 1974 | [8 empty] | 3% | 1914.78 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375908 | HAMMER ATTCHMENT | 1400 | 490 | 84 | 1974 | [8 empty] | 3% | 1914.78 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375908 | HAMMER ATTCHMENT | 2967.5 | 1038.625 | 178.05 | 4184.175 | [8 empty] | 3% | 4058.6498 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375908 | HAMMER ATTCHMENT | 2967.5 | 1038.625 | 178.05 | 4184.175 | [8 empty] | 3% | 4058.6498 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375902 | HAMMER ATTCHMENT | 1255 | 439.25 | 75.3 | 1769.55 | [8 empty] | 3% | 1716.4635 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375902 | HAMMER ATTCHMENT | 1255 | 439.25 | 75.3 | 1769.55 | [8 empty] | 3% | 1716.4635 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375902 | HAMMER ATTCHMENT | 1255 | 439.25 | 75.3 | 1769.55 | [8 empty] | 3% | 1716.4635 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375902 | HAMMER ATTCHMENT | 1255 | 439.25 | 75.3 | 1769.55 | [8 empty] | 3% | 1716.4635 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 375902 | HAMMER ATTCHMENT | 1255 | 439.25 | 75.3 | 1769.55 | [8 empty] | 3% | 1716.4635 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 31729339003 | HAMMER ATTCHMENT | 415 | 145.25 | 24.9 | 585.15 | [8 empty] | 3% | 567.5955 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 31729339003 | HAMMER ATTCHMENT | 415 | 145.25 | 24.9 | 585.15 | [8 empty] | 3% | 567.5955 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 31729339003 | HAMMER ATTCHMENT | 415 | 145.25 | 24.9 | 585.15 | [8 empty] | 3% | 567.5955 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 31729339003 | HAMMER ATTCHMENT | 415 | 145.25 | 24.9 | 585.15 | [8 empty] | 3% | 567.5955 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-12-02 | [32 empty] | CROSS COUNTRY | 31729339003 | HAMMER ATTCHMENT | 415 | 145.25 | 24.9 | 585.15 | [8 empty] | 3% | 567.5955 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375894 | HAMMER ATTCHMENT | 1141.71 | 399.5985 | 68.5 | 1609.8085 | [8 empty] | 3% | 1561.5142 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375894 | HAMMER ATTCHMENT | 1141.71 | 399.5985 | 68.5 | 1609.8085 | [8 empty] | 3% | 1561.5142 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375894 | HAMMER ATTCHMENT | 1141.71 | 399.5985 | 68.5 | 1609.8085 | [8 empty] | 3% | 1561.5142 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375894 | HAMMER ATTCHMENT | 1141.71 | 399.5985 | 68.5 | 1609.8085 | [8 empty] | 3% | 1561.5142 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375895 | HAMMER ATTCHMENT | 913.37 | 319.6795 | 54.8 | 1287.8495 | [8 empty] | 3% | 1249.214 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375895 | HAMMER ATTCHMENT | 913.37 | 319.6795 | 54.8 | 1287.8495 | [8 empty] | 3% | 1249.214 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375895 | HAMMER ATTCHMENT | 913.37 | 319.6795 | 54.8 | 1287.8495 | [8 empty] | 3% | 1249.214 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375895 | HAMMER ATTCHMENT | 913.37 | 319.6795 | 54.8 | 1287.8495 | [8 empty] | 3% | 1249.214 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375895 | HAMMER ATTCHMENT | 913.37 | 319.6795 | 54.8 | 1287.8495 | [8 empty] | 3% | 1249.214 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Clean-up / Remediation | 11 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375868 | PADDING BUCKET | 1340 | 469 | 80.4 | 1889.4 | [8 empty] | 3% | 1832.718 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Clean-up / Remediation | 11 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375868 | PADDING BUCKET | 1340 | 469 | 80.4 | 1889.4 | [8 empty] | 3% | 1832.718 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Clean-up / Remediation | 11 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375868 | PADDING BUCKET | 1340 | 469 | 80.4 | 1889.4 | [8 empty] | 3% | 1832.718 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Clean-up / Remediation | 11 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375868 | PADDING BUCKET | 1340 | 469 | 80.4 | 1889.4 | [8 empty] | 3% | 1832.718 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Clean-up / Remediation | 11 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-30 | [32 empty] | CROSS COUNTRY | 375868 | PADDING BUCKET | 1340 | 469 | 80.4 | 1889.4 | [8 empty] | 3% | 1832.718 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Site Prep | 11 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-24 | [32 empty] | HERC RENTALS | 31734630002 | BRUSH HOG ATTACHMENT | 300 | 105 | 18 | 423 | [8 empty] | 3% | 410.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Site Prep | 11 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-24 | [32 empty] | HERC RENTALS | 31734630002 | BRUSH HOG ATTACHMENT | 300 | 105 | 18 | 423 | [8 empty] | 3% | 410.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Site Prep | 11 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-24 | [32 empty] | HERC RENTALS | 31734630002 | BRUSH HOG ATTACHMENT | 300 | 105 | 18 | 423 | [8 empty] | 3% | 410.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Site Prep | 11 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-24 | [32 empty] | HERC RENTALS | 31734630002 | BRUSH HOG ATTACHMENT | 300 | 105 | 18 | 423 | [8 empty] | 3% | 410.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Site Prep | 11 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-24 | [32 empty] | HERC RENTALS | 31734630002 | BRUSH HOG ATTACHMENT | 300 | 105 | 18 | 423 | [8 empty] | 3% | 410.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Site Prep | 11 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-11-24 | [32 empty] | HERC RENTALS | 31734630002 | BRUSH HOG ATTACHMENT | 300 | 105 | 18 | 423 | [8 empty] | 3% | 410.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Site Prep | 11 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-24 | [32 empty] | HERC RENTALS | 31734630002 | BRUSH HOG ATTACHMENT | 300 | 105 | 18 | 423 | [8 empty] | 3% | 410.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Site Prep | 11 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-11-24 | [32 empty] | HERC RENTALS | 31734630002 | BRUSH HOG ATTACHMENT | 300 | 105 | 18 | 423 | [8 empty] | 3% | 410.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1778 - MC.400216.085 - 384.804 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Site Prep | 11 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-11-24 | [32 empty] | HERC RENTALS | 31734630002 | BRUSH HOG ATTACHMENT | 300 | 105 | 18 | 423 | [8 empty] | 3% | 410.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-23 | [32 empty] | HERC RENTALS | 31741922001 | HAMMER ATTCHMENT | 1796.25 | 628.6875 | 107.78 | 2532.7175 | [8 empty] | 3% | 2456.736 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-23 | [32 empty] | HERC RENTALS | 31741922001 | HAMMER ATTCHMENT | 1796.25 | 628.6875 | 107.78 | 2532.7175 | [8 empty] | 3% | 2456.736 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-23 | [32 empty] | HERC RENTALS | 31741922001 | HAMMER ATTCHMENT | 1796.25 | 628.6875 | 107.78 | 2532.7175 | [8 empty] | 3% | 2456.736 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-09 | 2 | BL |  | Excavation | 11 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-23 | [32 empty] | HERC RENTALS | 31741922001 | HAMMER ATTCHMENT | 1796.25 | 628.6875 | 107.78 | 2532.7175 | [8 empty] | 3% | 2456.736 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | JASON | JONES | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [15 empty] | 3% | 910.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | 658 | 151 | 420 |  | 10 | 10 | 1229 | [15 empty] | 3% | 1192.13 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 988 | 151 | 185 |  | 10 | 10 | 1324 | [15 empty] | 3% | 1284.28 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [15 empty] | 3% | 407.4 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44174-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-09 | Demob | CALEB | HOLTON | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44174-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-09 | Demob | JORDAN | WIGGINS | Laborer | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 502 | 151 | 160 |  | 10 | 10 | 813 | [15 empty] | 3% | 788.61 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44174-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-09 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [15 empty] | 3% | 856.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | JASON | JONES | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [15 empty] | 3% | 1108.71 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 185 |  | 10 | 10 | 994 | [15 empty] | 3% | 964.18 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [15 empty] | 3% | 1512.23 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-29410-44175-rev0 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-10 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | JONATHAN | HOLLEY | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [15 empty] | 3% | 970.97 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [15 empty] | 3% | 970.97 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | JASON | JONES | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [15 empty] | 3% | 970.97 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | IAIN | ALLRED | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [15 empty] | 3% | 1252.27 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 830 | 151 | 185 |  | 10 | 10 | 1166 | [15 empty] | 3% | 1131.02 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [15 empty] | 3% | 1512.23 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44176-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-11 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | JONATHAN | HOLLEY | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [15 empty] | 3% | 1242.57 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [15 empty] | 3% | 970.97 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [15 empty] | 3% | 970.97 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | JASON | JONES | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [15 empty] | 3% | 970.97 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | IAIN | ALLRED | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [15 empty] | 3% | 1252.27 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 830 | 151 | 185 |  | 10 | 10 | 1166 | [15 empty] | 3% | 1131.02 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [15 empty] | 3% | 1512.23 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-14 | 2 | BL |  | Demobilization | 3500028468-26060-44177-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-12 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 0 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 0 |  | 10 | 0 | 943 | [15 empty] | 3% | 914.71 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 0 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 0 |  | 10 | 0 | 723 | [15 empty] | 3% | 701.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 0 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 0 |  | 10 | 0 | 723 | [15 empty] | 3% | 701.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 0 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 0 |  | 10 | 0 | 723 | [15 empty] | 3% | 701.31 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 0 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 0 |  | 10 | 0 | 809 | [15 empty] | 3% | 784.73 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 0 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 0 |  | 10 | 0 | 1139 | [15 empty] | 3% | 1104.83 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | [7 empty] | Lowboy Trailer | 0 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 0 | HR | 1998 | [11 empty] | 16 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 0 | HR | R19108 | [11 empty] | 16 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | [7 empty] | 40' Flatbed trailer or equal | 0 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-3990-44179-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-14 | Demob | [7 empty] | 40' Flatbed trailer or equal | 0 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [15 empty] | 3% | 1040.81 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [15 empty] | 3% | 827.41 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [15 empty] | 3% | 1108.71 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 185 |  | 10 | 10 | 994 | [15 empty] | 3% | 964.18 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [15 empty] | 3% | 1512.23 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Demobilization | 3500028468-10630-44180-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-15 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-20 | [32 empty] | MEARS | 11162020 | 33 MATS | 10395 | 831.6 |  | 11226.6 | [8 empty] | 3% | 10889.802 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721897002 | COMPRESSOR/SANDPOT | 598.75 | 47.9 | 35.93 | 682.58 | [8 empty] | 3% | 662.1026 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721897002 | COMPRESSOR/SANDPOT | 598.75 | 47.9 | 35.93 | 682.58 | [8 empty] | 3% | 662.1026 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721897002 | COMPRESSOR/SANDPOT | 598.75 | 47.9 | 35.93 | 682.58 | [8 empty] | 3% | 662.1026 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721897002 | COMPRESSOR/SANDPOT | 598.75 | 47.9 | 35.93 | 682.58 | [8 empty] | 3% | 662.1026 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | EXCAVATOR | 430 | 34.4 | 25.8 | 490.2 | [8 empty] | 3% | 475.494 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | EXCAVATOR | 430 | 34.4 | 25.8 | 490.2 | [8 empty] | 3% | 475.494 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | EXCAVATOR | 430 | 34.4 | 25.8 | 490.2 | [8 empty] | 3% | 475.494 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | EXCAVATOR | 430 | 34.4 | 25.8 | 490.2 | [8 empty] | 3% | 475.494 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | EXCAVATOR | 430 | 34.4 | 25.8 | 490.2 | [8 empty] | 3% | 475.494 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Clean-up / Remediation | 12 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721419002 | SKID STEER | 1550 | 124 | 93 | 1767 | [8 empty] | 3% | 1713.99 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Clean-up / Remediation | 12 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721419002 | SKID STEER | 1550 | 124 | 93 | 1767 | [8 empty] | 3% | 1713.99 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Clean-up / Remediation | 12 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-12-10 | [32 empty] | HERC RENTALS | 31721419003 | SKID STEER | 655 | 52.4 | 42.62 | 750.02 | [8 empty] | 3% | 727.5194 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Clean-up / Remediation | 12 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-12-10 | [32 empty] | HERC RENTALS | 31721419003 | SKID STEER | 655 | 52.4 | 42.62 | 750.02 | [8 empty] | 3% | 727.5194 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | [32 empty] | BOTTS PLUMBING | 48486 | PORTA CAN | 76.67 | 6.1336 | 4 | 86.8036 | [8 empty] | 3% | 84.1995 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-09 | [32 empty] | BOTTS PLUMBING | 48486 | PORTA CAN | 76.67 | 6.1336 | 4 | 86.8036 | [8 empty] | 3% | 84.1995 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-09 | [32 empty] | BOTTS PLUMBING | 48486 | PORTA CAN | 76.67 | 6.1336 | 4 | 86.8036 | [8 empty] | 3% | 84.1995 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-10-09 | [32 empty] | BOTTS PLUMBING | 48487 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-09 | [32 empty] | BOTTS PLUMBING | 48487 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 | [32 empty] | BOTTS PLUMBING | 48487 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48655 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48655 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1778 - MC.400216.085 - 384.804 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48655 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48656 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48656 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48656 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48661 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48661 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48661 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48662 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48662 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-24 | [32 empty] | BOTTS PLUMBING | 48662 | PORTA CAN | 51.67 | 4.1336 | 2.5 | 58.3036 | [8 empty] | 3% | 56.5545 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-11-06 | [32 empty] | BOTTS PLUMBING | 48787 | PORTA CAN | 66.67 | 5.3336 | 4 | 76.0036 | [8 empty] | 3% | 73.7235 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-11-06 | [32 empty] | BOTTS PLUMBING | 48787 | PORTA CAN | 66.67 | 5.3336 | 4 | 76.0036 | [8 empty] | 3% | 73.7235 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Access - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Access | 12 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-11-06 | [32 empty] | BOTTS PLUMBING | 48787 | PORTA CAN | 66.67 | 5.3336 | 4 | 76.0036 | [8 empty] | 3% | 73.7235 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721956002 | COMPRESSOR/SANDPOT | 399.17 | 31.9336 | 23.95 | 455.0536 | [8 empty] | 3% | 441.402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721956002 | COMPRESSOR/SANDPOT | 399.17 | 31.9336 | 23.95 | 455.0536 | [8 empty] | 3% | 441.402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721956002 | COMPRESSOR/SANDPOT | 399.17 | 31.9336 | 23.95 | 455.0536 | [8 empty] | 3% | 441.402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721956002 | COMPRESSOR/SANDPOT | 399.17 | 31.9336 | 23.95 | 455.0536 | [8 empty] | 3% | 441.402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721956002 | COMPRESSOR/SANDPOT | 399.17 | 31.9336 | 23.95 | 455.0536 | [8 empty] | 3% | 441.402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721956002 | COMPRESSOR/SANDPOT | 399.17 | 31.9336 | 23.95 | 455.0536 | [8 empty] | 3% | 441.402 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721791003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [8 empty] | 3% | 302.7176 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721791003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [8 empty] | 3% | 302.7176 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721791003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [8 empty] | 3% | 302.7176 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721791003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [8 empty] | 3% | 302.7176 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721818003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [8 empty] | 3% | 302.7176 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721818003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [8 empty] | 3% | 302.7176 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721818003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [8 empty] | 3% | 302.7176 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Pipe Preparation | 12 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-12-04 | [32 empty] | HERC RENTALS | 31721818003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [8 empty] | 3% | 302.7176 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Clean-up / Remediation | 12 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-12-10 | [32 empty] | HERC RENTALS | 31744397002 | SKID STEER | 713.25 | 57.06 | 44.15 | 814.46 | [8 empty] | 3% | 790.0262 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Clean-up / Remediation | 12 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-12-10 | [32 empty] | HERC RENTALS | 31744397002 | SKID STEER | 713.25 | 57.06 | 44.15 | 814.46 | [8 empty] | 3% | 790.0262 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Clean-up / Remediation | 12 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-12-10 | [32 empty] | HERC RENTALS | 31744397002 | SKID STEER | 713.25 | 57.06 | 44.15 | 814.46 | [8 empty] | 3% | 790.0262 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Clean-up / Remediation | 12 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-12-10 | [32 empty] | HERC RENTALS | 31744397002 | SKID STEER | 713.25 | 57.06 | 44.15 | 814.46 | [8 empty] | 3% | 790.0262 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-08 | [32 empty] | BOYD CAT | R47341003 | EXCAVATOR | 811.38 | 64.9104 | 48.68 | 924.9704 | [8 empty] | 3% | 897.2213 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-08 | [32 empty] | BOYD CAT | R47341003 | EXCAVATOR | 811.38 | 64.9104 | 48.68 | 924.9704 | [8 empty] | 3% | 897.2213 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-08 | [32 empty] | BOYD CAT | R47341003 | EXCAVATOR | 811.38 | 64.9104 | 48.68 | 924.9704 | [8 empty] | 3% | 897.2213 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-12-08 | [32 empty] | BOYD CAT | R47341003 | EXCAVATOR | 811.38 | 64.9104 | 48.68 | 924.9704 | [8 empty] | 3% | 897.2213 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 12 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-12-08 | [32 empty] | BOYD CAT | R47341003 | EXCAVATOR | 811.38 | 64.9104 | 48.68 | 924.9704 | [8 empty] | 3% | 897.2213 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-12-11 | [32 empty] | CROSS COUNTRY | 376213 | PADDING BUCKET | 957.14 | 334.999 | 57.43 | 1349.569 | [8 empty] | 3% | 1309.0819 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-12-11 | [32 empty] | CROSS COUNTRY | 376213 | PADDING BUCKET | 957.14 | 334.999 | 57.43 | 1349.569 | [8 empty] | 3% | 1309.0819 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-12-11 | [32 empty] | CROSS COUNTRY | 376213 | PADDING BUCKET | 957.14 | 334.999 | 57.43 | 1349.569 | [8 empty] | 3% | 1309.0819 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-12-11 | [32 empty] | CROSS COUNTRY | 376213 | PADDING BUCKET | 957.14 | 334.999 | 57.43 | 1349.569 | [8 empty] | 3% | 1309.0819 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-12-11 | [32 empty] | CROSS COUNTRY | 376213 | PADDING BUCKET | 957.14 | 334.999 | 57.43 | 1349.569 | [8 empty] | 3% | 1309.0819 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-12-11 | [32 empty] | CROSS COUNTRY | 376213 | PADDING BUCKET | 957.14 | 334.999 | 57.43 | 1349.569 | [8 empty] | 3% | 1309.0819 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-12-11 | [32 empty] | CROSS COUNTRY | 376213 | PADDING BUCKET | 957.14 | 334.999 | 57.43 | 1349.569 | [8 empty] | 3% | 1309.0819 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731068002 | BRUSH CUTTER | 70.71 | 24.7485 | 4.24 | 99.6985 | [8 empty] | 3% | 96.7075 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731068002 | BRUSH CUTTER | 70.71 | 24.7485 | 4.24 | 99.6985 | [8 empty] | 3% | 96.7075 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731068002 | BRUSH CUTTER | 70.71 | 24.7485 | 4.24 | 99.6985 | [8 empty] | 3% | 96.7075 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731068002 | BRUSH CUTTER | 70.71 | 24.7485 | 4.24 | 99.6985 | [8 empty] | 3% | 96.7075 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731068002 | BRUSH CUTTER | 70.71 | 24.7485 | 4.24 | 99.6985 | [8 empty] | 3% | 96.7075 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731068002 | BRUSH CUTTER | 70.71 | 24.75 | 4.24 | 99.7 | [8 empty] | 3% | 96.709 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731068002 | BRUSH CUTTER | 70.71 | 24.7485 | 4.24 | 99.6985 | [8 empty] | 3% | 96.7075 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-08 | [32 empty] | CROSS COUNTRY | 376075 | PADDING BUCKET | 446.67 | 156.3345 | 26.8 | 629.8045 | [8 empty] | 3% | 610.9104 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-12-08 | [32 empty] | CROSS COUNTRY | 376075 | PADDING BUCKET | 446.67 | 156.3345 | 26.8 | 629.8045 | [8 empty] | 3% | 610.9104 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-12-08 | [32 empty] | CROSS COUNTRY | 376075 | PADDING BUCKET | 446.67 | 156.3345 | 26.8 | 629.8045 | [8 empty] | 3% | 610.9104 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-12-08 | [32 empty] | CROSS COUNTRY | 376075 | PADDING BUCKET | 446.67 | 156.3345 | 26.8 | 629.8045 | [8 empty] | 3% | 610.9104 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Backfill | 13 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-08 | [32 empty] | CROSS COUNTRY | 376075 | PADDING BUCKET | 446.67 | 156.3345 | 26.8 | 629.8045 | [8 empty] | 3% | 610.9104 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 13 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-08 | [32 empty] | BOYD CAT | R47341002 | HAMMER ATTACHMENT | 961.88 | 336.658 | 57.71 | 1356.248 | [8 empty] | 3% | 1315.5606 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 13 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-08 | [32 empty] | BOYD CAT | R47341002 | HAMMER ATTACHMENT | 961.88 | 336.658 | 57.71 | 1356.248 | [8 empty] | 3% | 1315.5606 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 13 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-08 | [32 empty] | BOYD CAT | R47341002 | HAMMER ATTACHMENT | 961.88 | 336.658 | 57.71 | 1356.248 | [8 empty] | 3% | 1315.5606 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Excavation | 13 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-12-08 | [32 empty] | BOYD CAT | R47341002 | HAMMER ATTACHMENT | 961.88 | 336.658 | 57.71 | 1356.248 | [8 empty] | 3% | 1315.5606 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731082002 | BRUSH CUTTER | 123.75 | 43.3125 | 7.43 | 174.4925 | [8 empty] | 3% | 169.2577 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731082002 | BRUSH CUTTER | 123.75 | 43.3125 | 7.43 | 174.4925 | [8 empty] | 3% | 169.2577 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731082002 | BRUSH CUTTER | 123.75 | 43.3125 | 7.43 | 174.4925 | [8 empty] | 3% | 169.2577 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-12-16 | 2 | BL |  | Site Prep | 13 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-12-10 | [32 empty] | HERC RENTALS | 31731082002 | BRUSH CUTTER | 123.75 | 43.3125 | 7.43 | 174.4925 | [8 empty] | 3% | 169.2577 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 792 | 151 | 160 |  | 10 | 10 | 1103 | [15 empty] | 3% | 1069.91 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [15 empty] | 3% | 856.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | CARLOS | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [15 empty] | 3% | 856.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | MICHAEL | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [15 empty] | 3% | 856.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | CARLOS | GARCIA | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [15 empty] | 3% | 856.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [15 empty] | 3% | 1108.71 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 185 |  | 10 | 10 | 994 | [15 empty] | 3% | 964.18 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [15 empty] | 3% | 1512.23 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-14960-44181-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-16 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 792 | 151 | 160 |  | 10 | 10 | 1103 | [15 empty] | 3% | 1069.91 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [15 empty] | 3% | 856.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | CARLOS | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [15 empty] | 3% | 856.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | MICHAEL | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [15 empty] | 3% | 856.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | CARLOS | GARCIA | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [15 empty] | 3% | 856.51 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [15 empty] | 3% | 1108.71 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 185 |  | 10 | 10 | 994 | [15 empty] | 3% | 964.18 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [15 empty] | 3% | 1512.23 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [15 empty] | 3% | 155.2 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Demobilization | 3500028468-15400-44182-rev0 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-17 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [15 empty] | 3% | 179.45 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | CALEB | HOLTON | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | 19120 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | RCT5164 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | 19120 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | UTT2182 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for stand by | JODY | BROOM | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for stand by | TOME | KIRKLAND | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for stand by | JAY | MASEY | Quality Assurance Inspector | -5 |  |  |  | Pickup-F150 or F250 or equal | -5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | -525 |  | -65 |  | -5 | -5 | -590 | [15 empty] | 3% | -572.3 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for stand by | STEVE | CLARK | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | R15272 | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for stand by | SCOTT | MERRY | Safety Person | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | DANIEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for stand by | DANIEL | YOUNG | Operator II | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | -350.5 |  | -65 |  | -5 | -5 | -415.5 | [15 empty] | 3% | -403.035 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for stand by | MATTHEW | LINDLEY | Operator II | -3 | -2 |  |  | Tractor/Semi | -5 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | -350.5 |  | -210 |  | -5 | -5 | -560.5 | [15 empty] | 3% | -543.685 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44166-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-01 | Changed to account for credit LEM for stand by | ELIZABETH | PERRY | Project Coordinator | -5 |  |  |  | Lowboy Trailer | -5 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | -494 |  | -92.5 |  | -5 | -5 | -586.5 | [15 empty] | 3% | -568.905 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | JONATHAN | HOLLEY | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | 19115 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | R19108 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | 2178 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS1663 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44166-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-01 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH2986 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | CALEB | HOLTON | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | 19120 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | RCT5164 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | 19120 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | UTT2182 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44167-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | JONATHAN | HOLLEY | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | 19115 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | R19108 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | 2178 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS1663 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH2986 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for stand by | JODY | BROOM | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for stand by | TOME | KIRKLAND | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for stand by | JAY | MASEY | Quality Assurance Inspector | -5 |  |  |  | Pickup-F150 or F250 or equal | -5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | -525 |  | -65 |  | -5 | -5 | -590 | [15 empty] | 3% | -572.3 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for stand by | STEVE | CLARK | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | R15272 | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for stand by | SCOTT | MERRY | Safety Person | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | DANIEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for stand by | DANIEL | YOUNG | Operator II | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | -350.5 |  | -65 |  | -5 | -5 | -415.5 | [15 empty] | 3% | -403.035 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for stand by | MATTHEW | LINDLEY | Operator II | -3 | -2 |  |  | Tractor/Semi | -5 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | -350.5 |  | -210 |  | -5 | -5 | -560.5 | [15 empty] | 3% | -543.685 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44167-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-02 | Changed to account for credit LEM for stand by | ELIZABETH | PERRY | Project Coordinator | -5 |  |  |  | Lowboy Trailer | -5 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | -494 |  | -92.5 |  | -5 | -5 | -586.5 | [15 empty] | 3% | -568.905 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | CALEB | HOLTON | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | 19120 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | RCT5164 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | 19120 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | UTT2182 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev0 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | JODY | BROOM | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | TOME | KIRKLAND | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | JAY | MASEY | Quality Assurance Inspector | -5 |  |  |  | Pickup-F150 or F250 or equal | -5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | -525 |  | -65 |  | -5 | -5 | -590 | [15 empty] | 3% | -572.3 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | STEVE | CLARK | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | R15272 | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | SCOTT | MERRY | Safety Person | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | DANIEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | DANIEL | YOUNG | Operator II | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | -350.5 |  | -65 |  | -5 | -5 | -415.5 | [15 empty] | 3% | -403.035 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | MATTHEW | LINDLEY | Operator II | -3 | -2 |  |  | Tractor/Semi | -5 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | -350.5 |  | -210 |  | -5 | -5 | -560.5 | [15 empty] | 3% | -543.685 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44168-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-03 | Changed to account for credit LEM for standby | ELIZABETH | PERRY | Project Coordinator | -5 |  |  |  | Lowboy Trailer | -5 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | -494 |  | -92.5 |  | -5 | -5 | -586.5 | [15 empty] | 3% | -568.905 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | JONATHAN | HOLLEY | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | 19115 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | R19108 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | 2178 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS1663 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44168-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-03 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH2986 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | CALEB | HOLTON | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | 19120 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | RCT5164 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | 19120 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | UTT2182 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44169-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | JONATHAN | HOLLEY | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | 19115 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | R19108 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | 2178 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS1663 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH2986 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | JODY | BROOM | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | TOME | KIRKLAND | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | JAY | MASEY | Quality Assurance Inspector | -5 |  |  |  | Pickup-F150 or F250 or equal | -5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | -525 |  | -65 |  | -5 | -5 | -590 | [15 empty] | 3% | -572.3 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | STEVE | CLARK | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | JOSHUA | PHILLIPSON | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | JASON | JONES | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | MATTHEW | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | SCOTT | MERRY | Safety Person | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | DANIEL | YOUNG | Operator II | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | -350.5 |  | -65 |  | -5 | -5 | -415.5 | [15 empty] | 3% | -403.035 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | MATTHEW | LINDLEY | Operator II | -3 | -2 |  |  | Tractor/Semi | 0 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | -350.5 |  | 0 |  | -5 | 0 | -350.5 | [15 empty] | 3% | -339.985 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | ELIZABETH | PERRY | Project Coordinator | -5 |  |  |  | Lowboy Trailer | 0 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | -494 |  | 0 |  | -5 | 0 | -494 | [15 empty] | 3% | -479.18 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Tractor/Semi | 0 | HR | 1376 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Lowboy Trailer | 0 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Tractor/Semi | 0 | HR | 1368 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44169-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-04 | Changed to account for credit LEM for standby | [7 empty] | Lowboy Trailer | 0 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | CALEB | HOLTON | Foreman |  | -5 |  |  | Pickup-F150 or F250 or equal | -5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -500 |  | -65 |  | -5 | -5 | -565 | [15 empty] | 3% | -548.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | 19120 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | RCT5164 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | 19120 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | UTT2182 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | JODY | BROOM | Superintendent |  | -5 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -630 |  | -65 |  | -5 | -5 | -695 | [15 empty] | 3% | -674.15 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | TOME | KIRKLAND | Superintendent |  | -5 |  |  | Pickup-F150 or F250 or equal | -5 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -630 |  | -65 |  | -5 | -5 | -695 | [15 empty] | 3% | -674.15 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | JAY | MASEY | Quality Assurance Inspector | -5 |  |  |  | Pickup-F150 or F250 or equal | -5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | -525 |  | -65 |  | -5 | -5 | -590 | [15 empty] | 3% | -572.3 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | STEVE | CLARK | Truck Driver/CDL |  | -5 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -360 |  | -65 |  | -5 | -5 | -425 | [15 empty] | 3% | -412.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | -5 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -360 |  | -65 |  | -5 | -5 | -425 | [15 empty] | 3% | -412.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | JASON | JONES | Truck Driver/CDL |  | -5 |  |  | Pickup-F150 or F250 or equal | -5 | HR | MATTHEW | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -360 |  | -65 |  | -5 | -5 | -425 | [15 empty] | 3% | -412.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | SCOTT | MERRY | Safety Person |  | -5 |  |  | Pickup-F150 or F250 or equal | -5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -500 |  | -65 |  | -5 | -5 | -565 | [15 empty] | 3% | -548.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | DANIEL | YOUNG | Operator II |  | -5 |  |  | Pickup-F150 or F250 or equal | -5 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | -415 |  | -65 |  | -5 | -5 | -480 | [15 empty] | 3% | -465.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | MATTHEW | LINDLEY | Operator II |  | -5 |  |  | Tractor/Semi | 0 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | -415 |  | 0 |  | -5 | 0 | -415 | [15 empty] | 3% | -402.55 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | ELIZABETH | PERRY | Project Coordinator | -5 |  |  |  | Lowboy Trailer | 0 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | -494 |  | 0 |  | -5 | 0 | -494 | [15 empty] | 3% | -479.18 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Tractor/Semi | 0 | HR | 1376 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Lowboy Trailer | 0 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Tractor/Semi | 0 | HR | 1368 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44170-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-05 | Changed to account for credit LEM for standby | [7 empty] | Lowboy Trailer | 0 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | CALEB | HOLTON | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | JORDAN | WIGGINS | Laborer | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | -267 |  | -65 |  | -5 | -5 | -332 | [15 empty] | 3% | -322.04 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | RCT5164 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | 1998 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | UTT2182 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44172-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | JODY | BROOM | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | TOME | KIRKLAND | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | JAY | MASEY | Quality Assurance Inspector | -5 |  |  |  | Pickup-F150 or F250 or equal | -5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | -525 |  | -65 |  | -5 | -5 | -590 | [15 empty] | 3% | -572.3 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | STEVE | CLARK | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | JOSHUA | PHILLIPSON | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | JASON | JONES | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | MATTHEW | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | SCOTT | MERRY | Safety Person | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | DANIEL | YOUNG | Operator II | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | -350.5 |  | -65 |  | -5 | -5 | -415.5 | [15 empty] | 3% | -403.035 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | MATTHEW | LINDLEY | Operator II | -3 | -2 |  |  | Tractor/Semi | 0 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | -350.5 |  | 0 |  | -5 | 0 | -350.5 | [15 empty] | 3% | -339.985 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | ELIZABETH | PERRY | Project Coordinator | -5 |  |  |  | Lowboy Trailer | 0 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | -494 |  | 0 |  | -5 | 0 | -494 | [15 empty] | 3% | -479.18 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Tractor/Semi | 0 | HR | 1376 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Lowboy Trailer | 0 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Tractor/Semi | 0 | HR | 1368 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29410-44172-rev1 | DIG-2095 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2020-12-07 | Changed to account for credit LEM for standby | [7 empty] | Lowboy Trailer | 0 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | CALEB | HOLTON | Foreman | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | JORDAN | WIGGINS | Laborer | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | -267 |  | -65 |  | -5 | -5 | -332 | [15 empty] | 3% | -322.04 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Pickup-F150 or F250 or equal | -5 | HR | RCT5164 | [11 empty] | 13 |  |  |  | -65 |  |  | -5 | -65 | [15 empty] | 3% | -63.05 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | -5 | HR | 19120 | [11 empty] | 16 |  |  |  | -80 |  |  | -5 | -80 | [15 empty] | 3% | -77.6 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Tool Trailer | -5 | HR | UTT2182 | [11 empty] | 5 |  |  |  | -25 |  |  | -5 | -25 | [15 empty] | 3% | -24.25 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | 40' Flatbed trailer or equal | -5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | -92.5 |  |  | -5 | -92.5 | [15 empty] | 3% | -89.725 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | -5 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | -452.5 |  |  | -5 | -452.5 | [15 empty] | 3% | -438.925 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | -5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | -230 |  |  | -5 | -230 | [15 empty] | 3% | -223.1 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | -5 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | -137.5 |  |  | -5 | -137.5 | [15 empty] | 3% | -133.375 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Hammer Attachment | -5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Brush Hog | -5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | -5 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | JODY | BROOM | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | TOME | KIRKLAND | Superintendent | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | -532.5 |  | -65 |  | -5 | -5 | -597.5 | [15 empty] | 3% | -579.575 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | JAY | MASEY | Quality Assurance Inspector | -5 |  |  |  | Pickup-F150 or F250 or equal | -5 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | -525 |  | -65 |  | -5 | -5 | -590 | [15 empty] | 3% | -572.3 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | STEVE | CLARK | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | JOSHUA | PHILLIPSON | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | JASON | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | JASON | JONES | Truck Driver/CDL | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | MATTHEW | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | -304.5 |  | -65 |  | -5 | -5 | -369.5 | [15 empty] | 3% | -358.415 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | SCOTT | MERRY | Safety Person | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | R15272 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | -422 |  | -65 |  | -5 | -5 | -487 | [15 empty] | 3% | -472.39 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | DANIEL | YOUNG | Operator II | -3 | -2 |  |  | Pickup-F150 or F250 or equal | -5 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | -350.5 |  | -65 |  | -5 | -5 | -415.5 | [15 empty] | 3% | -403.035 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | MATTHEW | LINDLEY | Operator II | -3 | -2 |  |  | Tractor/Semi | 0 | HR | R1371 | [7 empty] | 61.5 | 83 | 0 | 151 | 42 |  | -350.5 |  | 0 |  | -5 | 0 | -350.5 | [15 empty] | 3% | -339.985 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | ELIZABETH | PERRY | Project Coordinator | -5 |  |  |  | Lowboy Trailer | 0 | HR | 2455 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | -494 |  | 0 |  | -5 | 0 | -494 | [15 empty] | 3% | -479.18 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Tractor/Semi | 0 | HR | 1376 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Lowboy Trailer | 0 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Tractor/Semi | 0 | HR | 1368 | [11 empty] | 42 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-12-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-26060-44173-rev1 | DIG-2094 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 96267.66 | 26060 | Central | TN | 324.368 | 2020-12-08 | Changed to account for credit LEM for standby | [7 empty] | Lowboy Trailer | 0 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 0 |  |  | 0 | [16 empty] | 3% | 0 | ABC 3500028468-06 | ABC 3500028468-06
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | JONATHAN | HOLLEY | Foreman |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1200 | 151 | 156 |  | 12 | 12 | 1507 | [16 empty] | 1507 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | STEVE | CLARK | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 156 |  | 12 | 12 | 1171 | [16 empty] | 1171 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 156 |  | 12 | 12 | 1171 | [16 empty] | 1171 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | IAIN | ALLRED | Truck Driver/CDL |  | 12 |  | 1 | Tractor/Semi | 12 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 864 | 151 | 504 |  | 12 | 12 | 1519 | [16 empty] | 1519 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | DANIEL | YOUNG | Operator II |  | 12 |  | 1 | Lowboy Trailer | 12 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 996 | 151 | 222 |  | 12 | 12 | 1369 | [16 empty] | 1369 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 12 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 504 |  | 10 | 12 | 1643 | [16 empty] | 1643 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [11 empty] | 16 |  |  |  | 192 |  |  | 12 | 192 | [16 empty] | 192 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | R19108 | [11 empty] | 16 |  |  |  | 192 |  |  | 12 | 192 | [16 empty] | 192 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | [7 empty] | 40' Flatbed trailer or equal | 12 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-3990-44183-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-12-18 | Demob | [7 empty] | 40' Flatbed trailer or equal | 12 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | JONATHAN | HOLLEY | Foreman |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1200 | 151 | 156 |  | 12 | 12 | 1507 | [16 empty] | 1507 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | STEVE | CLARK | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 156 |  | 12 | 12 | 1171 | [16 empty] | 1171 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 864 | 151 | 156 |  | 12 | 12 | 1171 | [16 empty] | 1171 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | IAIN | ALLRED | Truck Driver/CDL |  | 12 |  | 1 | Tractor/Semi | 12 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 864 | 151 | 504 |  | 12 | 12 | 1519 | [16 empty] | 1519 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | DANIEL | YOUNG | Operator II |  | 12 |  | 1 | Lowboy Trailer | 12 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 996 | 151 | 222 |  | 12 | 12 | 1369 | [16 empty] | 1369 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 12 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 504 |  | 10 | 12 | 1643 | [16 empty] | 1643 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | [7 empty] | Lowboy Trailer | 12 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [11 empty] | 16 |  |  |  | 192 |  |  | 12 | 192 | [16 empty] | 192 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | R19108 | [11 empty] | 16 |  |  |  | 192 |  |  | 12 | 192 | [16 empty] | 192 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | [7 empty] | 40' Flatbed trailer or equal | 12 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-10630-44184-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-19 | Demob | [7 empty] | 40' Flatbed trailer or equal | 12 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 792 | 151 | 160 |  | 10 | 10 | 1103 | [16 empty] | 1103 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | CARLOS | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | MICHAEL | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | CARLOS | GARCIA | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 185 |  | 10 | 10 | 994 | [16 empty] | 994 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | ELIZABETH | PERRY | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-12-22 | 2 | BL |  | Demobilization | 3500028468-14960-44186-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-21 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 185 |  | 10 | 10 | 994 | [16 empty] | 994 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-17790-44200-rev1 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-04 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | CARLOS | GARCIA | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 658 | 151 | 160 |  | 10 | 10 | 969 | [16 empty] | 969 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1996 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-16230-44202-rev1 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-06 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | CARLOS | GARCIA | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 658 | 151 | 160 |  | 10 | 10 | 969 | [16 empty] | 969 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1996 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-18890-44203-rev1 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-07 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | CARLOS | GARCIA | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 658 | 151 | 160 |  | 10 | 10 | 969 | [16 empty] | 969 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1996 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-08 | 2 | BL |  | Demobilization | 3500028468-1940-44201-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-05 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | JONATHAN | HOLLEY | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 |  | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 |  | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 |  | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [16 empty] | 1291 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | IAIN | ALLRED | Truck Driver/CDL |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 |  | 151 | 18.5 |  | 720 | 151 | 185 |  | 10 | 10 | 1056 | [16 empty] | 1056 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 |  | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [16 empty] | 1291 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 61.5 | 83 |  | 151 | 18.5 |  | 830 | 151 | 185 |  | 10 | 10 | 1166 | [16 empty] | 1166 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-19030-44204-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | JONATHAN | HOLLEY | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 |  | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 |  | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 |  | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [16 empty] | 1291 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | IAIN | ALLRED | Truck Driver/CDL |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 |  | 151 | 18.5 |  | 720 | 151 | 185 |  | 10 | 10 | 1056 | [16 empty] | 1056 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 |  | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [16 empty] | 1291 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 61.5 | 83 |  | 151 | 18.5 |  | 830 | 151 | 185 |  | 10 | 10 | 1166 | [16 empty] | 1166 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-11 | 2 | BL |  | Demobilization | 3500028468-28110-44205-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-09 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 185 |  | 10 | 10 | 994 | [16 empty] | 994 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-12 | 2 | BL |  | Demobilization | 3500028468-28570-44207-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-11 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 185 |  | 10 | 10 | 994 | [16 empty] | 994 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-13 | 2 | BL |  | Demobilization | 3500028468-29300-44208-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-12 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 572 | 151 | 185 |  | 10 | 10 | 908 | [16 empty] | 908 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 658 | 151 | 185 |  | 10 | 10 | 994 | [16 empty] | 994 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-51610-44209-rev0 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | JONATHAN | HOLLEY | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [16 empty] | 1291 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | IAIN | ALLRED | Truck Driver/CDL |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 720 | 151 | 185 |  | 10 | 10 | 1056 | [16 empty] | 1056 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [16 empty] | 1291 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 830 | 151 | 185 |  | 10 | 10 | 1166 | [16 empty] | 1166 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-10630-44211-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-15 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | JONATHAN | HOLLEY | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | R1371 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [16 empty] | 1291 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | IAIN | ALLRED | Truck Driver/CDL |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2455 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 720 | 151 | 185 |  | 10 | 10 | 1056 | [16 empty] | 1056 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [16 empty] | 1291 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 830 | 151 | 185 |  | 10 | 10 | 1166 | [16 empty] | 1166 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [11 empty] | 16 |  |  |  | 160 |  |  | 10 | 160 | [16 empty] | 160 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Demobilization | 3500028468-14960-44212-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-16 | Demob | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 7130 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Access | 14 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-11-28 | [32 empty] | BETTER SANITATION | 1028MMS | PORTA CANS | 74.2 | 5.936 | 0 | 80.136 | [9 empty] | 80.136 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Access | 14 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-11-28 | [32 empty] | BETTER SANITATION | 1028MMS | PORTA CANS | 74.2 | 5.936 |  | 80.136 | [9 empty] | 80.136 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Access | 14 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-11-28 | [32 empty] | BETTER SANITATION | 1028MMS | PORTA CANS | 74.2 | 5.936 |  | 80.136 | [9 empty] | 80.136 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Access | 14 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2020-11-28 | [32 empty] | BETTER SANITATION | 1028MMS | PORTA CANS | 74.2 | 5.936 |  | 80.136 | [9 empty] | 80.136 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761077-002 | FORKLIFT - YARD | 233.75 | 18.7 | 14.03 | 266.48 | [9 empty] | 266.48 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761077-002 | FORKLIFT - YARD | 233.75 | 18.7 | 14.03 | 266.48 | [9 empty] | 266.48 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761077-002 | FORKLIFT - YARD | 233.75 | 18.7 | 14.03 | 266.48 | [9 empty] | 266.48 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761077-002 | FORKLIFT - YARD | 233.75 | 18.7 | 14.03 | 266.48 | [9 empty] | 266.48 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761077-002 | FORKLIFT - YARD | 233.75 | 18.7 | 14.03 | 266.48 | [9 empty] | 266.48 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761077-002 | FORKLIFT - YARD | 233.75 | 18.7 | 14.03 | 266.48 | [9 empty] | 266.48 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761077-002 | FORKLIFT - YARD | 233.75 | 18.7 | 14.03 | 266.48 | [9 empty] | 266.48 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761077-002 | FORKLIFT - YARD | 233.75 | 18.7 | 14.03 | 266.48 | [9 empty] | 266.48 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-08 | [32 empty] | HERC RENTALS | 31761077-003 | FORKLIFT - YARD | 256.25 | 20.5 | 15.38 | 292.13 | [9 empty] | 292.13 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-08 | [32 empty] | HERC RENTALS | 31761077-003 | FORKLIFT - YARD | 256.25 | 20.5 | 15.38 | 292.13 | [9 empty] | 292.13 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2021-01-08 | [32 empty] | HERC RENTALS | 31761077-003 | FORKLIFT - YARD | 256.25 | 20.5 | 15.38 | 292.13 | [9 empty] | 292.13 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-08 | [32 empty] | HERC RENTALS | 31761077-003 | FORKLIFT - YARD | 256.25 | 20.5 | 15.38 | 292.13 | [9 empty] | 292.13 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2021-01-08 | [32 empty] | HERC RENTALS | 31761077-003 | FORKLIFT - YARD | 256.25 | 20.5 | 15.38 | 292.13 | [9 empty] | 292.13 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-08 | [32 empty] | HERC RENTALS | 31761077-003 | FORKLIFT - YARD | 256.25 | 20.5 | 15.38 | 292.13 | [9 empty] | 292.13 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-08 | [32 empty] | HERC RENTALS | 31761077-003 | FORKLIFT - YARD | 256.25 | 20.5 | 15.38 | 292.13 | [9 empty] | 292.13 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Site Prep | 14 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-08 | [32 empty] | HERC RENTALS | 31761077-003 | FORKLIFT - YARD | 256.25 | 20.5 | 15.38 | 292.13 | [9 empty] | 292.13 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2020-12-27 | [32 empty] | BRAND SAFWAY | 951516633 | ACM REMOVAL | 5900 | 472 |  | 6372 | [9 empty] | 6372 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-12-27 | [32 empty] | BRAND SAFWAY | 951516632 | ACM REMOVAL | 2900 | 232 |  | 3132 | [9 empty] | 3132 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-12-27 | [32 empty] | BRAND SAFWAY | 951516632 | ACM REMOVAL | 2900 | 232 |  | 3132 | [9 empty] | 3132 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-27 | [32 empty] | BRAND SAFWAY | 951516632 | ACM REMOVAL | 2900 | 232 |  | 3132 | [9 empty] | 3132 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-12-27 | [32 empty] | BRAND SAFWAY | 951516632 | ACM REMOVAL | 2900 | 232 |  | 3132 | [9 empty] | 3132 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-12-27 | [32 empty] | BRAND SAFWAY | 951516632 | ACM REMOVAL | 2900 | 232 |  | 3132 | [9 empty] | 3132 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-11-23 | [32 empty] | HERC RENTALS | 31761482-001 | AIR COMPRESSOR | 360 | 28.8 | 21.6 | 410.4 | [9 empty] | 410.4 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-11-23 | [32 empty] | HERC RENTALS | 31761482-001 | AIR COMPRESSOR | 360 | 28.8 | 21.6 | 410.4 | [9 empty] | 410.4 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-23 | [32 empty] | HERC RENTALS | 31761482-001 | AIR COMPRESSOR | 360 | 28.8 | 21.6 | 410.4 | [9 empty] | 410.4 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-23 | [32 empty] | HERC RENTALS | 31761482-001 | AIR COMPRESSOR | 360 | 28.8 | 21.6 | 410.4 | [9 empty] | 410.4 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-23 | [32 empty] | HERC RENTALS | 31761482-001 | AIR COMPRESSOR | 360 | 28.8 | 21.6 | 410.4 | [9 empty] | 410.4 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721791-004 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721791-004 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721791-004 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721791-004 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721818-004 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721818-004 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721818-004 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721818-004 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721956-004 | SANDPOT | 182.5 | 14.6 | 10.95 | 208.05 | [9 empty] | 208.05 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721956-004 | SANDPOT | 182.5 | 14.6 | 10.95 | 208.05 | [9 empty] | 208.05 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721956-004 | SANDPOT | 182.5 | 14.6 | 10.95 | 208.05 | [9 empty] | 208.05 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721956-004 | SANDPOT | 182.5 | 14.6 | 10.95 | 208.05 | [9 empty] | 208.05 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721956-004 | SANDPOT | 182.5 | 14.6 | 10.95 | 208.05 | [9 empty] | 208.05 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-2088 | 3500028468 | MC.400235.133 | 2020 | ABC Group, Inc | ALL | 15 | 77581.7 | 81940 | Central | TN | 301.899 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721956-004 | SANDPOT | 182.5 | 14.6 | 10.95 | 208.05 | [9 empty] | 208.05 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-12-14 | [32 empty] | HERC RENTALS | 31745516-003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-12-14 | [32 empty] | HERC RENTALS | 31745516-003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-12-14 | [32 empty] | HERC RENTALS | 31745516-003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-12-14 | [32 empty] | HERC RENTALS | 31745516-003 | SANDPOT | 273.75 | 21.9 | 16.43 | 312.08 | [9 empty] | 312.08 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721897-004 | SANDPOT | 219 | 17.52 | 13.14 | 249.66 | [9 empty] | 249.66 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721897-004 | SANDPOT | 219 | 17.52 | 13.14 | 249.66 | [9 empty] | 249.66 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721897-004 | SANDPOT | 219 | 17.52 | 13.14 | 249.66 | [9 empty] | 249.66 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721897-004 | SANDPOT | 219 | 17.52 | 13.14 | 249.66 | [9 empty] | 249.66 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-01-19 | 2 | BL |  | Pipe Preparation | 14 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2021-01-03 | [32 empty] | HERC RENTALS | 31721897-004 | SANDPOT | 219 | 17.52 | 13.14 | 249.66 | [9 empty] | 249.66 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Site Access | 15 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-12-23 | [32 empty] | BIG JOHNS | 20886 | PORTA CANS | 72.5 | 5.8 | 0 | 78.3 | [9 empty] | 78.3 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Site Access | 15 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-12-23 | [32 empty] | BIG JOHNS | 20886 | PORTA CANS | 72.5 | 5.8 |  | 78.3 | [9 empty] | 78.3 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Site Access | 15 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-11-25 | [32 empty] | BIG JOHNS | 20815 | PORTA CANS | 72.5 | 5.8 |  | 78.3 | [9 empty] | 78.3 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Site Access | 15 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-11-25 | [32 empty] | BIG JOHNS | 20815 | PORTA CANS | 72.5 | 5.8 |  | 78.3 | [9 empty] | 78.3 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Pipe Preparation | 15 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2021-01-12 | [32 empty] | HERC RENTALS | 31743411004 | SANDPOT | 219 | 17.52 | 20.26 | 256.78 | [9 empty] | 256.78 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Pipe Preparation | 15 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2021-01-12 | [32 empty] | HERC RENTALS | 31743411004 | SANDPOT | 219 | 17.52 | 20.26 | 256.78 | [9 empty] | 256.78 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Pipe Preparation | 15 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2021-01-12 | [32 empty] | HERC RENTALS | 31743411004 | SANDPOT | 219 | 17.52 | 20.26 | 256.78 | [9 empty] | 256.78 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Pipe Preparation | 15 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2021-01-12 | [32 empty] | HERC RENTALS | 31743411004 | SANDPOT | 219 | 17.52 | 20.26 | 256.78 | [9 empty] | 256.78 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Pipe Preparation | 15 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2021-01-12 | [32 empty] | HERC RENTALS | 31743411004 | SANDPOT | 219 | 17.52 | 20.26 | 256.78 | [9 empty] | 256.78 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339002 | EXCAVATOR | 1654.97 | 132.3976 | 31.37 | 1818.7376 | [9 empty] | 1818.7376 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339002 | EXCAVATOR | 1654.97 | 132.3976 | 31.37 | 1818.7376 | [9 empty] | 1818.7376 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339002 | EXCAVATOR | 1654.97 | 132.3976 | 31.37 | 1818.7376 | [9 empty] | 1818.7376 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339002 | EXCAVATOR | 1654.97 | 132.3976 | 31.37 | 1818.7376 | [9 empty] | 1818.7376 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-11-07 | [32 empty] | HERC RENTALS | 31729339002 | EXCAVATOR | 1654.97 | 132.3976 | 31.37 | 1818.7376 | [9 empty] | 1818.7376 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761057003 | PALLET FORKS | 86.25 | 6.9 | 5.18 | 98.33 | [9 empty] | 98.33 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761057003 | PALLET FORKS | 86.25 | 6.9 | 5.18 | 98.33 | [9 empty] | 98.33 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761057003 | PALLET FORKS | 86.25 | 6.9 | 5.18 | 98.33 | [9 empty] | 98.33 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-12-22 | [32 empty] | HERC RENTALS | 31761057003 | PALLET FORKS | 86.25 | 6.9 | 5.18 | 98.33 | [9 empty] | 98.33 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Pipe Preparation | 15 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-01-13 | [32 empty] | HERC RENTALS | 31745516004 | SANDPOT | 273.75 | 21.9 | 25.32 | 320.97 | [9 empty] | 320.97 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Pipe Preparation | 15 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | [32 empty] | HERC RENTALS | 31745516004 | SANDPOT | 273.75 | 21.9 | 25.32 | 320.97 | [9 empty] | 320.97 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Pipe Preparation | 15 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-01-13 | [32 empty] | HERC RENTALS | 31745516004 | SANDPOT | 273.75 | 21.9 | 25.32 | 320.97 | [9 empty] | 320.97 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Pipe Preparation | 15 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2021-01-13 | [32 empty] | HERC RENTALS | 31745516004 | SANDPOT | 273.75 | 21.9 | 25.32 | 320.97 | [9 empty] | 320.97 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-12-08 | [32 empty] | HERC RENTALS | 31783796001 | SKIDSTEER | 228.75 | 18.3 | 13.73 | 260.78 | [9 empty] | 260.78 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-12-08 | [32 empty] | HERC RENTALS | 31783796001 | SKIDSTEER | 228.75 | 18.3 | 13.73 | 260.78 | [9 empty] | 260.78 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-12-08 | [32 empty] | HERC RENTALS | 31783796001 | SKIDSTEER | 228.75 | 18.3 | 13.73 | 260.78 | [9 empty] | 260.78 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-12-08 | [32 empty] | HERC RENTALS | 31783796001 | SKIDSTEER | 228.75 | 18.3 | 13.73 | 260.78 | [9 empty] | 260.78 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-11-24 | [32 empty] | HERC RENTALS | 31761057001 | SKIDSTEER | 781.25 | 62.5 | 46.88 | 890.63 | [9 empty] | 890.63 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-11-24 | [32 empty] | HERC RENTALS | 31761057001 | SKIDSTEER | 781.25 | 62.5 | 46.88 | 890.63 | [9 empty] | 890.63 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-11-24 | [32 empty] | HERC RENTALS | 31761057001 | SKIDSTEER | 781.25 | 62.5 | 46.88 | 890.63 | [9 empty] | 890.63 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Clean-up / Remediation | 15 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-11-24 | [32 empty] | HERC RENTALS | 31761057001 | SKIDSTEER | 781.25 | 62.5 | 46.88 | 890.63 | [9 empty] | 890.63 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Demobilization | 15 | DIG-1556 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 51610 | Central | KY | 381.4525 | 2021-01-13 | [32 empty] | KOMPASS | 10123 | TRUCKING | 3900 | 312 |  | 4212 | [9 empty] | 4212 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Recoat | 15 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2021-01-15 | [32 empty] | PSS | 240490100 | TAPE/PRIMER | 144.07 | 11.5256 | 10.09 | 165.6856 | [9 empty] | 165.6856 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Recoat | 15 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2021-01-15 | [32 empty] | PSS | 240490100 | TAPE/PRIMER | 144.07 | 11.5256 | 10.09 | 165.6856 | [9 empty] | 165.6856 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Recoat | 15 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2021-01-15 | [32 empty] | PSS | 240490100 | TAPE/PRIMER | 144.07 | 11.5256 | 10.09 | 165.6856 | [9 empty] | 165.6856 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Recoat | 15 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2021-01-15 | [32 empty] | PSS | 240490100 | TAPE/PRIMER | 144.07 | 11.5256 | 10.09 | 165.6856 | [9 empty] | 165.6856 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1488 - MC.400216.032 - 666.536 - Recoat - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Recoat | 15 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2021-01-15 | [32 empty] | PSS | 240490100 | TAPE/PRIMER | 144.07 | 11.5256 | 10.09 | 165.6856 | [9 empty] | 165.6856 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377598 | EXCAVATOR | 702.1 | 56.168 | 41.3 | 799.568 | [9 empty] | 799.568 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377598 | EXCAVATOR | 702.1 | 56.168 | 41.3 | 799.568 | [9 empty] | 799.568 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377598 | EXCAVATOR | 702.1 | 56.168 | 41.3 | 799.568 | [9 empty] | 799.568 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377598 | EXCAVATOR | 702.1 | 56.168 | 41.3 | 799.568 | [9 empty] | 799.568 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377611 | EXCAVATOR | 722.16 | 57.7728 | 43.33 | 823.2628 | [9 empty] | 823.2628 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377611 | EXCAVATOR | 722.16 | 57.7728 | 43.33 | 823.2628 | [9 empty] | 823.2628 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377611 | EXCAVATOR | 722.16 | 57.7728 | 43.33 | 823.2628 | [9 empty] | 823.2628 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377611 | EXCAVATOR | 722.16 | 57.7728 | 43.33 | 823.2628 | [9 empty] | 823.2628 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 15 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377611 | EXCAVATOR | 722.16 | 57.7728 | 43.33 | 823.2628 | [9 empty] | 823.2628 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Site Prep | 16 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-12-08 | [32 empty] | HERC RENTALS | 31761057002 | BRUSH CUTTER | 300 | 105 | 18 | 423 | [9 empty] | 423 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Site Prep | 16 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-12-08 | [32 empty] | HERC RENTALS | 31761057002 | BRUSH CUTTER | 300 | 105 | 18 | 423 | [9 empty] | 423 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Site Prep | 16 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2020-12-08 | [32 empty] | HERC RENTALS | 31761057002 | BRUSH CUTTER | 300 | 105 | 18 | 423 | [9 empty] | 423 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Site Prep | 16 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-12-08 | [32 empty] | HERC RENTALS | 31761057002 | BRUSH CUTTER | 300 | 105 | 18 | 423 | [9 empty] | 423 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | HAMMER | 415 | 145.25 |  | 560.25 | [9 empty] | 560.25 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | HAMMER | 415 | 145.25 |  | 560.25 | [9 empty] | 560.25 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | HAMMER | 415 | 145.25 |  | 560.25 | [9 empty] | 560.25 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | HAMMER | 415 | 145.25 |  | 560.25 | [9 empty] | 560.25 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-12-02 | [32 empty] | HERC RENTALS | 31729339003 | HAMMER | 415 | 145.25 |  | 560.25 | [9 empty] | 560.25 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377609 | PADDING BUCKET | 625.33 | 218.8655 | 37.52 | 881.7155 | [9 empty] | 881.7155 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1547 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 45306.12 | 15400 | Central | KY | 360.5932 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377609 | PADDING BUCKET | 625.33 | 218.8655 | 37.52 | 881.7155 | [9 empty] | 881.7155 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377609 | PADDING BUCKET | 625.33 | 218.8655 | 37.52 | 881.7155 | [9 empty] | 881.7155 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377609 | PADDING BUCKET | 625.33 | 218.8655 | 37.52 | 881.7155 | [9 empty] | 881.7155 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377609 | PADDING BUCKET | 625.33 | 218.8655 | 37.52 | 881.7155 | [9 empty] | 881.7155 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377614 | HAMMER | 1400 | 490 | 84 | 1974 | [9 empty] | 1974 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377614 | HAMMER | 1400 | 490 | 84 | 1974 | [9 empty] | 1974 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377614 | HAMMER | 1400 | 490 | 84 | 1974 | [9 empty] | 1974 | ABC 3500028468-07 | ABC 3500028468-07
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Excavation | 16 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2021-02-08 | [32 empty] | CROSS COUNTRY | 377614 | HAMMER | 1400 | 490 | 84 | 1974 | [9 empty] | 1974 | ABC 3500028468-07 | ABC 3500028468-07
CWP - Dig-0219 - MC.400235.071 - 326.751 - Base Price Fixed - 2 - BL - FP Base | CWP | Central | CS | 2021-02-10 | 2 | BL | FP Base | Base Price Fixed | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | <=3ft | 2.1 | FP | 1 | 1 | 0 | 24615 | 24615 |  | 24615
CWP - Dig-0219 - MC.400235.071 - 326.751 - Base Price Variable - 2 - BL - VP Base | CWP | Central | CS | 2021-02-10 | 2 | BL | VP Base | Base Price Variable | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | >3ft | 2.1 | VP | 2.16 | 2.16 | 0 | 218 | 470.88 |  | 470.88
CWP - Dig-0219 - MC.400235.071 - 326.751 - Mobilization - 2 - BL - Labor, Equipment & Supplies Mobilization (After Base Mileage) | CWP | Central | CS | 2021-02-10 | 2 | BL | Labor, Equipment & Supplies Mobilization (After Base Mileage) | Mobilization | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /(site mi) | 2.2.1.1 | UPI | 0 | 0 | 0 | 27 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Mobilization - 2 - BL - Labor, Equipment & Supplies Mobilization Credit | CWP | Central | CS | 2021-02-10 | 2 | BL | Labor, Equipment & Supplies Mobilization Credit | Mobilization | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /site | 2.2.1.2 | UPI | 0 | 0 | 0 | -3500 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Bridge Installation (up to 12') | CWP | Central | CS | 2021-02-10 | 2 | BL | Bridge Installation (up to 12') | Access | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | / bridge | 2.2.2.1 | UPI | 0 | 0 | 0 | 275 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Mat Installation and Removal | CWP | Central | CS | 2021-02-10 | 2 | BL | Mat Installation and Removal | Access | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /mat | 2.2.2.2 | UPI | 150 | 57 | 0 | 52 | 2964 |  | 2964
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Mat Usage | CWP | Central | CS | 2021-02-10 | 2 | BL | Mat Usage | Access | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /(mat day) | 2.2.2.3 | UPI | 1125 | 133 | 0 | 5 | 665 |  | 665
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Additional Trucking Distance (Pickup) | CWP | Central | CS | 2021-02-10 | 2 | BL | Additional Trucking Distance (Pickup) | Access | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /(truck mi) | 2.2.2.4 | UPI | 0 | 0 | 0 | 3 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Additional Trucking Distance (Semi-truck and trailer) | CWP | Central | CS | 2021-02-10 | 2 | BL | Additional Trucking Distance (Semi-truck and trailer) | Access | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /(truck mi) | 2.2.2.5 | UPI | 0 | 0 | 0 | 3.75 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Locates - 2 - BL - Third Party Sweep | CWP | Central | CS | 2021-02-10 | 2 | BL | Third Party Sweep | Locates | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /site | 2.2.3.1 | UPI | 1 | 1 | 0 | 1500 | 1500 |  | 1500
CWP - Dig-0219 - MC.400235.071 - 326.751 - Daylighting - 2 - BL - Hydrovac Material Removed – Temperate | CWP | Central | CS | 2021-02-10 | 2 | BL | Hydrovac Material Removed – Temperate | Daylighting | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft3 removed | 2.2.4.1 | UPI | 0 | 0 | 0 | 61 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Daylighting - 2 - BL - Hydrovac Material Removed – Cold | CWP | Central | CS | 2021-02-10 | 2 | BL | Hydrovac Material Removed – Cold | Daylighting | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft3 removed | 2.2.4.2 | UPI | 0 | 0 | 0 | 63 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Daylighting - 2 - BL - Hand Dug Material Removed – Temperate | CWP | Central | CS | 2021-02-10 | 2 | BL | Hand Dug Material Removed – Temperate | Daylighting | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft3 removed | 2.2.4.1 | UPI | 120 | 27 | 0 | 45 | 1215 |  | 1215
CWP - Dig-0219 - MC.400235.071 - 326.751 - Daylighting - 2 - BL - Hand Dug Material Removed – Cold | CWP | Central | CS | 2021-02-10 | 2 | BL | Hand Dug Material Removed – Cold | Daylighting | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft3 removed | 2.2.4.2 | UPI | 0 | 0 | 0 | 45 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Environmental Controls - 2 - BL - Additional Water Management | CWP | Central | CS | 2021-02-10 | 2 | BL | Additional Water Management | Environmental Controls | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /(pump day) | 2.2.5.1 | UPI | 10 | 0 | 0 | 500 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Environmental Controls - 2 - BL - Equipment Fine Cleaning - Temperate | CWP | Central | CS | 2021-02-10 | 2 | BL | Equipment Fine Cleaning - Temperate | Environmental Controls | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /site | 2.2.5.2 | UPI | 0 | 0 | 0 | 1200 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Environmental Controls - 2 - BL - Equipment Fine Cleaning – Cold | CWP | Central | CS | 2021-02-10 | 2 | BL | Equipment Fine Cleaning – Cold | Environmental Controls | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /site | 2.2.5.3 | UPI | 0 | 0 | 0 | 1800 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Additional Soil Handling | CWP | Central | CS | 2021-02-10 | 2 | BL | Additional Soil Handling | Excavation Activities | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /yd3 | 2.2.6.1 | UPI | 0 | 0 | 0 | 40 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Rock Excavation | CWP | Central | CS | 2021-02-10 | 2 | BL | Rock Excavation | Excavation Activities | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /yd3 | 2.2.6.2 | UPI | 0 | 0 | 0 | 275 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Shoring - Trench Box Assembly | CWP | Central | CS | 2021-02-10 | 2 | BL | Shoring - Trench Box Assembly | Excavation Activities | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /box | 2.2.6.3 | UPI | 1 | 1 | 0 | 500 | 500 |  | 500
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Shoring - Trench Box Installation and Removal | CWP | Central | CS | 2021-02-10 | 2 | BL | Shoring - Trench Box Installation and Removal | Excavation Activities | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /box | 2.2.6.4 | UPI | 2 | 2 | 0 | 1250 | 2500 |  | 2500
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Shoring - Trench Box Usage | CWP | Central | CS | 2021-02-10 | 2 | BL | Shoring - Trench Box Usage | Excavation Activities | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | / (box day) | 2.2.6.5 | UPI | 5 | 4 | 0 | 250 | 1000 |  | 1000
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Extra Depth of Cover | CWP | Central | CS | 2021-02-10 | 2 | BL | Extra Depth of Cover | Excavation Activities | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.6.6 | UPI | 5.16 | 5.16 | 0 | 50 | 258 |  | 258
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - Typical Coating Removal and Blasting | CWP | Central | CS | 2021-02-10 | 2 | BL | Typical Coating Removal and Blasting | Pipe Preparation | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.7.1 | UPI | 0 | 0 | 0 | 27.5 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - FBE Coating Removal and Blasting | CWP | Central | CS | 2021-02-10 | 2 | BL | FBE Coating Removal and Blasting | Pipe Preparation | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.7.2 | UPI | 0 | 0 | 0 | 40 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - Rock Protective Coating Removal and Blasting | CWP | Central | CS | 2021-02-10 | 2 | BL | Rock Protective Coating Removal and Blasting | Pipe Preparation | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.7.3 | UPI | 0 | 0 | 0 | 77 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - Asbestos Containing Coating Removal | CWP | Central | CS | 2021-02-10 | 2 | BL | Asbestos Containing Coating Removal | Pipe Preparation | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.7.4 | UPI | 0 | 0 | 0 | 30 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - Post Asbestos Abatement Blasting | CWP | Central | CS | 2021-02-10 | 2 | BL | Post Asbestos Abatement Blasting | Pipe Preparation | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.7.5 | UPI | 40.53 | 40.53 | 0 | 15 | 607.95 |  | 607.95
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Support - 2 - BL - Site Support – Temperate | CWP | Central | CS | 2021-02-10 | 2 | BL | Site Support – Temperate | Site Support | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /h | 2.2.8.1.1 | UPI | 20 | 20 | 0 | 945 | 18900 |  | 18900
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Support - 2 - BL - Site Support - Winter | CWP | Central | CS | 2021-02-10 | 2 | BL | Site Support - Winter | Site Support | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /h | 2.2.8.1.2 | UPI | 0 | 0 | 0 | 945 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Support - 2 - BL - Hole Watch | CWP | Central | CS | 2021-02-10 | 2 | BL | Hole Watch | Site Support | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /h | 2.2.8.2 | UPI | 0 | 0 | 0 | 135 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - Sleeve Repair (first 394 weld – inches) | CWP | Central | CS | 2021-02-10 | 2 | BL | Sleeve Repair (first 394 weld – inches) | Pipeline Repair | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /weld inches first 394” | 2.2.9.1 | UPI | 0 | 0 | 0 | 65 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - Sleeve Repair (>394 weld – inches) | CWP | Central | CS | 2021-02-10 | 2 | BL | Sleeve Repair (>394 weld – inches) | Pipeline Repair | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /weld inches first >394” | 2.2.9.2 | UPI | 0 | 0 | 0 | 30 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - Clock Spring® Install | CWP | Central | CS | 2021-02-10 | 2 | BL | Clock Spring® Install | Pipeline Repair | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.9.3 | UPI | 0 | 0 | 0 | 221 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - Atlas™ System Install (GTM Only) | CWP | Central | CS | 2021-02-10 | 2 | BL | Atlas™ System Install (GTM Only) | Pipeline Repair | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.9.4 | UPI | 0 | 0 | 0 | 232 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - PetroSleeve® Install (LP Only) | CWP | Central | CS | 2021-02-10 | 2 | BL | PetroSleeve® Install (LP Only) | Pipeline Repair | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.9.5 | UPI | 0 | 0 | 0 | 1030 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Coating - 2 - BL - Coating Application (Epoxy) – Hand Applied | CWP | Central | CS | 2021-02-10 | 2 | BL | Coating Application (Epoxy) – Hand Applied | Coating | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.10.1 | UPI | 0 | 0 | 0 | 150 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Coating - 2 - BL - Coating Application (Epoxy) – Spray Applied | CWP | Central | CS | 2021-02-10 | 2 | BL | Coating Application (Epoxy) – Spray Applied | Coating | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.10.2 | UPI | 48.39 | 0 | 0 | 63 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Coating - 2 - BL - Coating Application (Rock Shield) | CWP | Central | CS | 2021-02-10 | 2 | BL | Coating Application (Rock Shield) | Coating | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.10.3 | UPI | 0 | 40.53 | 0 | 9 | 364.77 |  | 364.77
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Restoration - 2 - BL - Restoration Credit | CWP | Central | CS | 2021-02-10 | 2 | BL | Restoration Credit | Site Restoration | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /site | 2.2.11.1 | UPI | 0 | 0 | 0 | -1500 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Restoration - 2 - BL - Topsoil & Restoration Credit | CWP | Central | CS | 2021-02-10 | 2 | BL | Topsoil & Restoration Credit | Site Restoration | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /site | 2.2.11.2 | UPI | 0 | 0 | 0 | -2000 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Restoration - 2 - BL - Asphalt Resurfacing | CWP | Central | CS | 2021-02-10 | 2 | BL | Asphalt Resurfacing | Site Restoration | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft2 | 2.2.11.3 | UPI | 0 | 0 | 0 | 25 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Restoration - 2 - BL - Access Route Reclamation | CWP | Central | CS | 2021-02-10 | 2 | BL | Access Route Reclamation | Site Restoration | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /ft | 2.2.11.4 | UPI | 0 | 0 | 0 | 1 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Delays - 2 - BL - Weather or Company Controlled Delays | CWP | Central | CS | 2021-02-10 | 2 | BL | Weather or Company Controlled Delays | Delays | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /(site hour) | 2.2.12.1 | UPI | 0 | 0 | 0 | 945 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - De-mobilization - 2 - BL - Labor, Equipment & Supplies Demobilization (After Base Mileage) | CWP | Central | CS | 2021-02-10 | 2 | BL | Labor, Equipment & Supplies Demobilization (After Base Mileage) | De-mobilization | 05-05-2021-Dig-0219-3500031050-0 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [39 empty] | /(site mi) | 2.2.13.1 | UPI | 0 | 0 | 0 | 27 | 0 |  | 0
CWP - Dig-0219 - MC.400235.071 - 326.751 - Mobilization - 2 - BL - | CWP | Central | CS | 2021-02-10 | 2 | BL |  | Mobilization | 123 | Dig-0219 | 3500028468 | MC.400235.071 | 2020 | ABC Group, Inc | ALL | 25 | 108868.59 | 29410 | Central | TN | 326.751 | 2021-02-15 | [31 empty] | 5000 | [16 empty] | 5000
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will create formula to budget tab

## Accrual Entry
Lem ID | Package Type | Package ID | FCA | Date Entered | Issuance | WEA | Cost Item | WBS Activity | LEM # | Dig ID | WO Number | WBS | WBS Year | Vendor Name | Line Segment | Line | Trigger Anomaly WC | GW | Region | State | Mile Post | Date | Comments | Total Costs
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will create formula to budget tab
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Enter Accrual Amount Here