## Dig List
Package Type - ID | Dig_Key | Dig ID | Package Type | Package ID | Parent Package | WBS Year | WBS | Execution Team | Line | Line Segment | Trigger Anomaly WC | Region | State | Mile Post | GW | Chief Inspector | U/S GW Latitude | U/S GW Longitude | General Contractor | Typical/Non Typical
CWP - Contingency - ABC Group, Inc - 3500028468 - 2020 - ALL | CWP - Contingency - ABC Group, Inc - 3500028468 - 2020 - ALL - ALL | Contingency - ABC Group, Inc - 3500028468 | CWP | ALL | ALL | 2020 | ALL | ML | ALL | ALL | ALL | Central/Southeast | ALL | ALL | ALL | ALL |  |  | ABC Group, Inc
CWP - Dig-0545 - 2020 - MC.400216.087 | CWP - Dig-0545 - 2020 - MC.400216.087 - Central | Dig-0545 | CWP | Central | Central | 2020 | MC.400216.087 | ML | 25 | ALL | 63906.27 | Central | KY | 364.114 | 17790 | ALL | 36.9575 | -85.5287 | ABC Group, Inc
CWP - Dig-0547 - 2020 - MC.400216.087 | CWP - Dig-0547 - 2020 - MC.400216.087 - Central | Dig-0547 | CWP | Central | Central | 2020 | MC.400216.087 | ML | 25 | ALL | 113696.86 | Central | KY | 373.552 | 31230 | ALL | 37.0576 | -85.4191 | ABC Group, Inc
CWP - Dig-0872 - 2020 - MC.400235.032 | CWP - Dig-0872 - 2020 - MC.400235.032 - Central | Dig-0872 | CWP | Central | Central | 2020 | MC.400235.032 | ML | 69 | ALL | 129.73 | Central | IN | 0.019 | 110 | ALL | 40.4238 | -85.5742 | ABC Group, Inc
CWP - Dig-0875 - 2020 - MC.400235.032 | CWP - Dig-0875 - 2020 - MC.400235.032 - Central | Dig-0875 | CWP | Central | Central | 2020 | MC.400235.032 | ML | 69 | ALL | 272347 | Central | IN | 51.577 | 71410 | ALL | 40.016 | -84.8264 | ABC Group, Inc
CWP - Dig-1465 - 2020 - MC.400216.032 | CWP - Dig-1465 - 2020 - MC.400216.032 - Central | Dig-1465 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 2010.71 | Central | IN | 629.925 | 650 | ALL | 38.5223 | -86.6641 | ABC Group, Inc
CWP - Dig-1466 - 2020 - MC.400216.032 | CWP - Dig-1466 - 2020 - MC.400216.032 - Central | Dig-1466 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 33938.77 | Central | IN | 635.962 | 9400 | ALL | 38.561 | -86.5701 | ABC Group, Inc
CWP - Dig-1467 - 2020 - MC.400216.032 | CWP - Dig-1467 - 2020 - MC.400216.032 - Central | Dig-1467 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 89163.97 | Central | IN | 646.441 | 23260 | ALL | 38.6369 | -86.4179 | ABC Group, Inc
CWP - Dig-1468 - 2020 - MC.400216.032 | CWP - Dig-1468 - 2020 - MC.400216.032 - Central | Dig-1468 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 91118.47 | Central | IN | 646.814 | 23770 | ALL | 38.6406 | -86.4127 | ABC Group, Inc
CWP - Dig-1472 - 2020 - MC.400216.032 | CWP - Dig-1472 - 2020 - MC.400216.032 - Central | Dig-1472 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 107126.57 | Central | IN | 649.858 | 27760 | ALL | 38.6641 | -86.3655 | ABC Group, Inc
CWP - Dig-1473 - 2020 - MC.400216.032 | CWP - Dig-1473 - 2020 - MC.400216.032 - Central | Dig-1473 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 113235.03 | Central | IN | 651.017 | 29250 | ALL | 38.6722 | -86.3466 | ABC Group, Inc
CWP - Dig-1474 - 2020 - MC.400216.032 | CWP - Dig-1474 - 2020 - MC.400216.032 - Central | Dig-1474 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 123618.27 | Central | IN | 652.986 | 31790 | ALL | 38.6843 | -86.3136 | ABC Group, Inc
CWP - Dig-1475 - 2020 - MC.400216.032 | CWP - Dig-1475 - 2020 - MC.400216.032 - Central | Dig-1475 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 131991.02 | Central | IN | 654.578 | 33820 | ALL | 38.6988 | -86.2911 | ABC Group, Inc
CWP - Dig-1476 - 2020 - MC.400216.032 | CWP - Dig-1476 - 2020 - MC.400216.032 - Central | Dig-1476 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 138951.03 | Central | IN | 655.884 | 35680 | ALL | 38.713 | -86.2762 | ABC Group, Inc
CWP - Dig-1485 - 2020 - MC.400216.032 | CWP - Dig-1485 - 2020 - MC.400216.032 - Central | Dig-1485 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 166964.77 | Central | IN | 661.199 | 43000 | ALL | 38.7672 | -86.2286 | ABC Group, Inc
CWP - Dig-1488 - 2020 - MC.400216.032 | CWP - Dig-1488 - 2020 - MC.400216.032 - Central | Dig-1488 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 195020.56 | Central | IN | 666.536 | 50610 | ALL | 38.8231 | -86.1616 | ABC Group, Inc
CWP - Dig-1489 - 2020 - MC.400216.032 | CWP - Dig-1489 - 2020 - MC.400216.032 - Central | Dig-1489 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 198009.22 | Central | IN | 667.112 | 51460 | ALL | 38.8293 | -86.1549 | ABC Group, Inc
CWP - Dig-1490 - 2020 - MC.400216.032 | CWP - Dig-1490 - 2020 - MC.400216.032 - Central | Dig-1490 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 208943.5 | Central | IN | 669.155 | 54330 | ALL | 38.8535 | -86.1325 | ABC Group, Inc
CWP - Dig-1491 - 2020 - MC.400216.032 | CWP - Dig-1491 - 2020 - MC.400216.032 - Central | Dig-1491 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 223676.86 | Central | IN | 671.952 | 58100 | ALL | 38.8824 | -86.0968 | ABC Group, Inc
CWP - Dig-1492 - 2020 - MC.400216.032 | CWP - Dig-1492 - 2020 - MC.400216.032 - Central | Dig-1492 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 236624.47 | Central | IN | 674.399 | 61420 | ALL | 38.9068 | -86.0638 | ABC Group, Inc
CWP - Dig-1493 - 2020 - MC.400216.032 | CWP - Dig-1493 - 2020 - MC.400216.032 - Central | Dig-1493 | CWP | Central | Central | 2020 | MC.400216.032 | ML | 1 | ALL | 279423.05 | Central | IN | 682.498 | 72330 | ALL | 38.9744 | -85.9416 | ABC Group, Inc
CWP - Dig-1545 - 2020 - MC.400216.085 | CWP - Dig-1545 - 2020 - MC.400216.085 - Central | Dig-1545 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 32027.34 | Central | KY | 358.0856 | 10630 | ALL | 36.8985 | -85.6024 | ABC Group, Inc
CWP - Dig-1546 - 2020 - MC.400216.085 | CWP - Dig-1546 - 2020 - MC.400216.085 - Central | Dig-1546 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 44028.07 | Central | KY | 360.3519 | 14960 | ALL | 36.9219 | -85.5756 | ABC Group, Inc
CWP - Dig-1548 - 2020 - MC.400216.085 | CWP - Dig-1548 - 2020 - MC.400216.085 - Central | Dig-1548 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 47752.86 | Central | KY | 361.0549 | 16230 | ALL | 36.9291 | -85.5668 | ABC Group, Inc
CWP - Dig-1549 - 2020 - MC.400216.085 | CWP - Dig-1549 - 2020 - MC.400216.085 - Central | Dig-1549 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 55217.13 | Central | KY | 362.4633 | 18890 | ALL | 36.9407 | -85.5468 | ABC Group, Inc
CWP - Dig-1551 - 2020 - MC.400216.085 | CWP - Dig-1551 - 2020 - MC.400216.085 - Central | Dig-1551 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 84327.46 | Central | KY | 367.9727 | 28110 | ALL | 36.9986 | -85.4844 | ABC Group, Inc
CWP - Dig-1552 - 2020 - MC.400216.085 | CWP - Dig-1552 - 2020 - MC.400216.085 - Central | Dig-1552 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 85886.46 | Central | KY | 368.2672 | 28570 | ALL | 37.0019 | -85.4814 | ABC Group, Inc
CWP - Dig-1553 - 2020 - MC.400216.085 | CWP - Dig-1553 - 2020 - MC.400216.085 - Central | Dig-1553 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 88526.65 | Central | KY | 368.7653 | 29300 | ALL | 37.0069 | -85.4752 | ABC Group, Inc
CWP - Dig-1560 - 2020 - MC.400216.085 | CWP - Dig-1560 - 2020 - MC.400216.085 - Central | Dig-1560 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 285819.92 | Central | KY | 406.0371 | 86930 | ALL | 37.4039 | -85.0411 | ABC Group, Inc
CWP - Dig-1562 - 2020 - MC.400216.085 | CWP - Dig-1562 - 2020 - MC.400216.085 - Central | Dig-1562 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 322856.96 | Central | KY | 413.0587 | 97640 | ALL | 37.4595 | -84.942 | ABC Group, Inc
CWP - Dig-1564 - 2020 - MC.400216.085 | CWP - Dig-1564 - 2020 - MC.400216.085 - Central | Dig-1564 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 353255.33 | Central | KY | 418.8466 | 108090 | ALL | 37.505 | -84.8704 | ABC Group, Inc
CWP - Dig-1778 - 2020 - MC.400216.085 | CWP - Dig-1778 - 2020 - MC.400216.085 - Central | Dig-1778 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 173507.05 | Central | KY | 384.804 | 10008649 | ALL | 37.1776 | -85.2862 | ABC Group, Inc
CWP - Dig-1544 - 2020 - MC.400216.085 | CWP - Dig-1544 - 2020 - MC.400216.085 - Central | Dig-1544 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 12651.39 | Central | KY | 354.4403 | 3390 | ALL | 36.858 | -85.6423 | ABC Group, Inc
CWP - Dig-0923 - 2020 - MC.400216.085 | CWP - Dig-0923 - 2020 - MC.400216.085 - Central | Dig-0923 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 1 | ALL | 226868.4 | Central | KY | 474.889 | 57880 | ALL | 37.4953 | -89.1059 | ABC Group, Inc
CWP - Dig-0796 - 2020 - MC.400216.084 | CWP - Dig-0796 - 2020 - MC.400216.084 - Central | Dig-0796 | CWP | Central | Central | 2020 | MC.400216.084 | ML | 10 | ALL | 3834.13 | Central | KY | 352.458 | 1940 | ALL | 36.839 | -85.6602 | ABC Group, Inc
CWP - Dig-1550 - 2020 - MC.400216.085 | CWP - Dig-1550 - 2020 - MC.400216.085 - Central | Dig-1550 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 55598.95 | Central | KY | 362.5356 | 19030 | ALL | 36.9414 | -85.5459 | ABC Group, Inc
CWP - Dig-1556 - 2020 - MC.400216.085 | CWP - Dig-1556 - 2020 - MC.400216.085 - Central | Dig-1556 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 55598.95 | Central | KY | 381.4525 | 51610 | ALL | 37.145 | -85.3305 | ABC Group, Inc
CWP - Dig-1547 - 2020 - MC.400216.085 | CWP - Dig-1547 - 2020 - MC.400216.085 - Central | Dig-1547 | CWP | Central | Central | 2020 | MC.400216.085 | ML | 15 | ALL | 45306.12 | Central | KY | 360.5932 | 15400 | ALL | 36.9244 | -85.5726 | ABC Group, Inc
CWP - Dig-2088 - 2020 - MC.400235.133 | CWP - Dig-2088 - 2020 - MC.400235.133 - Central | Dig-2088 | CWP | Central | Central | 2020 | MC.400235.133 | ML | 15 | ALL | 77581.7 | Central | TN | 301.899 | 81940 | ALL |  |  | ABC Group, Inc
CWP - Dig-2094 - 2020 - MC.400235.071 | CWP - Dig-2094 - 2020 - MC.400235.071 - Central | Dig-2094 | CWP | Central | Central | 2020 | MC.400235.071 | ML | 25 | ALL | 96267.66 | Central | TN | 324.368 | 26060 | ALL | 36.5353 | -85.9935 | ABC Group, Inc
CWP - Dig-2095 - 2020 - MC.400235.071 | CWP - Dig-2095 - 2020 - MC.400235.071 - Central | Dig-2095 | CWP | Central | Central | 2020 | MC.400235.071 | ML | 25 | ALL | 108868.59 | Central | TN | 326.751 | 29410 | ALL | 36.56 | -85.9649 | ABC Group, Inc
CWP - Dig-0219 - 2020 - MC.400235.071 | CWP - Dig-0219 - 2020 - MC.400235.071 - Central | Dig-0219 | CWP | Central | Central | 2020 | MC.400235.071 | ML | 25 | ALL | 108868.59 | Central | TN | 326.751 | 29410 | ALL | 36.56 | -85.9649 | ABC Group, Inc

## Contracts
Work Order Number | Vendor Name | Business Unit | Original Budget | Issuance | Rev | Current Budget | Incurred | Package | Closure Status | Difference | Date Initiated | Work Order Year | Adjusted Incurred | Adjusted Budget | Adjusted Earned
3500028468 | ABC Group, Inc | ABC | 4082475.3974 |  |  | 4060560.5974 | 3921565.8389 |  |  | 138994.7586

## Budget
Budget ID | Package ID | Package Type | Dig ID | WBS | WBS Year | Mile Post | Issuance | WEA | Cost Item | WBS Activity | WO Number | Vendor Name | Original Budgeted Cost | Original Budgeted Hours | Current Budgeted Cost | Current Budgeted Hours | Potential Changes | Dig Activity Progress | PL Start Date | PL End Date | ACT Start Date | ACT End Date | FC Start Date | FC End Date | Metric Description | BL QTY | ACT QTY
CWP - Contingency - ABC Group, Inc - 3500028468 - ALL - ALL - Contingency - General Contractor - 2 - BL - | ALL | CWP | Contingency - ABC Group, Inc - 3500028468 | ALL | 2020 | ALL | 2 | BL |  | Contingency - General Contractor | 3500028468 | ABC Group, Inc | 417690.32 |  | 417690.32 |  |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Site Access - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - NDE Assessment - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Recoat - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Demobilization - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-0545 | MC.400216.087 | 2020 | 364.114 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Site Access - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - NDE Assessment - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Recoat - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Backfill - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Demobilization - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0547 - MC.400216.087 - 373.552 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-0547 | MC.400216.087 | 2020 | 373.552 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - NDE Assessment - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Recoat - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Backfill - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Demobilization - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0872 - MC.400235.032 - 0.019 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-0872 | MC.400235.032 | 2020 | 0.019 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - NDE Assessment - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0875 - MC.400235.032 - 51.577 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-0875 | MC.400235.032 | 2020 | 51.577 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Site Access - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Site Prep - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1465 - MC.400216.032 - 629.925 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1465 | MC.400216.032 | 2020 | 629.925 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Site Access - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Recoat - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1466 - MC.400216.032 - 635.962 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1466 | MC.400216.032 | 2020 | 635.962 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Recoat - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Backfill - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Demobilization - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1467 - MC.400216.032 - 646.441 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1467 | MC.400216.032 | 2020 | 646.441 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Mobilization - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Site Access - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Recoat - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Backfill - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Demobilization - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1468 - MC.400216.032 - 646.814 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1468 | MC.400216.032 | 2020 | 646.814 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Site Access - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Recoat - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Backfill - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Demobilization - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1472 - MC.400216.032 - 649.858 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1472 | MC.400216.032 | 2020 | 649.858 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Site Access - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Recoat - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Backfill - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1473 | MC.400216.032 | 2020 | 651.017 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Site Access - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1474 - MC.400216.032 - 652.986 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1474 | MC.400216.032 | 2020 | 652.986 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Site Access - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Backfill - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1475 - MC.400216.032 - 654.578 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1475 | MC.400216.032 | 2020 | 654.578 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Site Access - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Recoat - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Backfill - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Demobilization - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1476 - MC.400216.032 - 655.884 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1476 | MC.400216.032 | 2020 | 655.884 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Backfill - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1485 - MC.400216.032 - 661.199 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1485 | MC.400216.032 | 2020 | 661.199 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Recoat - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1488 - MC.400216.032 - 666.536 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1488 | MC.400216.032 | 2020 | 666.536 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Recoat - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Backfill - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1489 - MC.400216.032 - 667.112 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1489 | MC.400216.032 | 2020 | 667.112 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Backfill - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Demobilization - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1490 | MC.400216.032 | 2020 | 669.155 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Site Access - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Recoat - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Backfill - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1491 - MC.400216.032 - 671.952 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1491 | MC.400216.032 | 2020 | 671.952 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Mobilization - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Site Access - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Site Prep - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Excavation - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Recoat - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Backfill - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Demobilization - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1492 - MC.400216.032 - 674.399 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1492 | MC.400216.032 | 2020 | 674.399 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Mobilization - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Site Access - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Site Prep - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Excavation - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Recoat - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Backfill - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Demobilization - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1493 - MC.400216.032 - 682.498 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1493 | MC.400216.032 | 2020 | 682.498 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Site Access - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Recoat - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Backfill - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Demobilization - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1545 - MC.400216.085 - 358.0856 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1545 | MC.400216.085 | 2020 | 358.0856 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Site Access - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Backfill - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Demobilization - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1546 - MC.400216.085 - 360.3519 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1546 | MC.400216.085 | 2020 | 360.3519 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Site Access - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Recoat - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Backfill - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Demobilization - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1548 - MC.400216.085 - 361.0549 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1548 | MC.400216.085 | 2020 | 361.0549 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Site Access - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1549 - MC.400216.085 - 362.4633 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1549 | MC.400216.085 | 2020 | 362.4633 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Recoat - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Backfill - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Demobilization - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1551 - MC.400216.085 - 367.9727 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1551 | MC.400216.085 | 2020 | 367.9727 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Recoat - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Backfill - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Demobilization - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1552 - MC.400216.085 - 368.2672 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1552 | MC.400216.085 | 2020 | 368.2672 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Recoat - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Backfill - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Demobilization - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1553 - MC.400216.085 - 368.7653 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1553 | MC.400216.085 | 2020 | 368.7653 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1560 | MC.400216.085 | 2020 | 406.0371 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1562 | MC.400216.085 | 2020 | 413.0587 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Demobilization - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1564 | MC.400216.085 | 2020 | 418.8466 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Mobilization - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Site Access - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Site Prep - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Recoat - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Backfill - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1778 | MC.400216.085 | 2020 | 384.804 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Excavation - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1544 - MC.400216.085 - 354.4403 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1544 | MC.400216.085 | 2020 | 354.4403 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - NDE Assessment - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Recoat - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Backfill - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0923 - MC.400216.085 - 474.889 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-0923 | MC.400216.085 | 2020 | 474.889 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Site Access - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - NDE Assessment - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0796 - MC.400216.084 - 352.458 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-0796 | MC.400216.084 | 2020 | 352.458 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Site Access - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Excavation - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1550 - MC.400216.085 - 362.5356 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1550 | MC.400216.085 | 2020 | 362.5356 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Mobilization - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Site Access - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Site Prep - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Excavation - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - NDE Assessment - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Recoat - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Backfill - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Demobilization - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-1556 - MC.400216.085 - 381.4525 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-1556 | MC.400216.085 | 2020 | 381.4525 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Mobilization - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Access - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Site Prep - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Excavation - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Initial Coating Inspection - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Pipe Preparation - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - NDE Assessment - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Repair - Install Sleeve - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Repair - Grind Out - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Post Repair Assessment - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Recoat - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Backfill - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Clean-up / Remediation - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Demobilization - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Stand-by - Weather - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Stand-by - Equipment - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Stand-by - Material - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Stand-by - Incident - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - DIG-1547 - MC.400216.085 - 360.5932 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | DIG-1547 | MC.400216.085 | 2020 | 360.5932 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Mobilization - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Site Access - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Site Prep - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Excavation - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - NDE Assessment - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Recoat - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Backfill - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Demobilization - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2088 - MC.400235.133 - 301.899 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-2088 | MC.400235.133 | 2020 | 301.899 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Mobilization - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Site Access - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Site Prep - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Excavation - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - NDE Assessment - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Recoat - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Backfill - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Demobilization - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2094 - MC.400235.071 - 324.368 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-2094 | MC.400235.071 | 2020 | 324.368 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Mobilization - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Site Access - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Site Access | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Site Prep - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Site Prep | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Excavation - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Excavation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Initial Coating Inspection - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Initial Coating Inspection | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Pipe Preparation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - NDE Assessment - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | NDE Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Repair - Install Clocksprings - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Repair - Install Clocksprings | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Repair - Atlas Wrap - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Repair - Atlas Wrap | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Repair - Install Sleeve - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Repair - Install Sleeve | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Repair - Pipe Replacement - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Repair - Pipe Replacement | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Repair - Grind Out - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Repair - Grind Out | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Post Repair Assessment - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Post Repair Assessment | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Recoat - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Recoat | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Backfill - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Backfill | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Clean-up / Remediation - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Clean-up / Remediation | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Demobilization - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Demobilization | 3500028468 | ABC Group, Inc | 5268.1025 | 526.8102 | 5268.1025 | 526.8102 | 100000 | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Stand-by - Weather - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Stand-by - Weather | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Stand-by - Equipment - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Stand-by - Equipment | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Stand-by - Material - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Stand-by - Material | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Stand-by - Waiting on Repair Decision - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Stand-by - Line Pressure - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Stand-by - Line Pressure | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Stand-by - Incident - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Stand-by - Incident | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-2095 - MC.400235.071 - 326.751 - Stand-by - Other (See Comments) - 2 - BL - | Central | CWP | Dig-2095 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468 | ABC Group, Inc |  | 0 |  | 0 |  | 100%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Base Price Fixed - 2 - BL - FP Base | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | FP Base | Base Price Fixed | 3500028468 | ABC Group, Inc | 24615 | 2461.5 | 24615 | 2461.5 |  | 100% |  |  | 2021-04-21 | 2021-04-21
CWP - Dig-0219 - MC.400235.071 - 326.751 - Base Price Variable - 2 - BL - VP Base | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | VP Base | Base Price Variable | 3500028468 | ABC Group, Inc | 470.88 | 47.088 | 470.88 | 47.088 |  | 100% |  |  | 2021-04-26 | 2021-04-26
CWP - Dig-0219 - MC.400235.071 - 326.751 - Mobilization - 2 - BL - Labor, Equipment & Supplies Mobilization (After Base Mileage) | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Labor, Equipment & Supplies Mobilization (After Base Mileage) | Mobilization | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Mobilization - 2 - BL - Labor, Equipment & Supplies Mobilization Credit | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Labor, Equipment & Supplies Mobilization Credit | Mobilization | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Bridge Installation (up to 12') | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Bridge Installation (up to 12') | Access | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Mat Installation and Removal | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Mat Installation and Removal | Access | 3500028468 | ABC Group, Inc | 7800 | 780 | 2964 | 780 |  | 100% |  |  | 2021-04-24 | 2021-05-01
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Mat Usage | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Mat Usage | Access | 3500028468 | ABC Group, Inc | 5625 | 562.5 | 665 | 562.5 |  | 100% |  |  | 2021-04-26 | 2021-05-01
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Additional Trucking Distance (Pickup) | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Additional Trucking Distance (Pickup) | Access | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Access - 2 - BL - Additional Trucking Distance (Semi-truck and trailer) | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Additional Trucking Distance (Semi-truck and trailer) | Access | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Locates - 2 - BL - Third Party Sweep | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Third Party Sweep | Locates | 3500028468 | ABC Group, Inc | 1500 | 150 | 1500 | 150 |  | 100% |  |  | 2021-04-21 | 2021-04-21
CWP - Dig-0219 - MC.400235.071 - 326.751 - Daylighting - 2 - BL - Hydrovac Material Removed – Temperate | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Hydrovac Material Removed – Temperate | Daylighting | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Daylighting - 2 - BL - Hydrovac Material Removed – Cold | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Hydrovac Material Removed – Cold | Daylighting | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Daylighting - 2 - BL - Hand Dug Material Removed – Temperate | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Hand Dug Material Removed – Temperate | Daylighting | 3500028468 | ABC Group, Inc | 5400 | 540 | 1215 | 540 |  | 100% |  |  | 2021-04-24 | 2021-04-24
CWP - Dig-0219 - MC.400235.071 - 326.751 - Daylighting - 2 - BL - Hand Dug Material Removed – Cold | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Hand Dug Material Removed – Cold | Daylighting | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Environmental Controls - 2 - BL - Additional Water Management | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Additional Water Management | Environmental Controls | 3500028468 | ABC Group, Inc | 5000 | 500 | 0 | 500 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Environmental Controls - 2 - BL - Equipment Fine Cleaning - Temperate | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Equipment Fine Cleaning - Temperate | Environmental Controls | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Environmental Controls - 2 - BL - Equipment Fine Cleaning – Cold | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Equipment Fine Cleaning – Cold | Environmental Controls | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Additional Soil Handling | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Additional Soil Handling | Excavation Activities | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Rock Excavation | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Rock Excavation | Excavation Activities | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Shoring - Trench Box Assembly | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Shoring - Trench Box Assembly | Excavation Activities | 3500028468 | ABC Group, Inc | 500 | 50 | 500 | 50 |  | 100% |  |  | 2021-04-23 | 2021-04-23
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Shoring - Trench Box Installation and Removal | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Shoring - Trench Box Installation and Removal | Excavation Activities | 3500028468 | ABC Group, Inc | 2500 | 250 | 2500 | 250 |  | 100% |  |  | 2021-04-24 | 2021-05-01
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Shoring - Trench Box Usage | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Shoring - Trench Box Usage | Excavation Activities | 3500028468 | ABC Group, Inc | 1250 | 125 | 1000 | 125 |  | 100% |  |  | 2021-04-26 | 2021-05-01
CWP - Dig-0219 - MC.400235.071 - 326.751 - Excavation Activities - 2 - BL - Extra Depth of Cover | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Extra Depth of Cover | Excavation Activities | 3500028468 | ABC Group, Inc | 258 | 25.8 | 258 | 25.8 |  | 100% |  |  | 2021-04-24 | 2021-04-24
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - Typical Coating Removal and Blasting | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Typical Coating Removal and Blasting | Pipe Preparation | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - FBE Coating Removal and Blasting | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | FBE Coating Removal and Blasting | Pipe Preparation | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - Rock Protective Coating Removal and Blasting | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Rock Protective Coating Removal and Blasting | Pipe Preparation | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - Asbestos Containing Coating Removal | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Asbestos Containing Coating Removal | Pipe Preparation | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipe Preparation - 2 - BL - Post Asbestos Abatement Blasting | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Post Asbestos Abatement Blasting | Pipe Preparation | 3500028468 | ABC Group, Inc | 607.95 | 60.795 | 607.95 | 60.795 |  | 100% |  |  | 2021-04-26 | 2021-04-26
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Support - 2 - BL - Site Support – Temperate | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Site Support – Temperate | Site Support | 3500028468 | ABC Group, Inc | 18900 | 1890 | 18900 | 1890 |  | 100% |  |  | 2021-04-27 | 2021-05-01
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Support - 2 - BL - Site Support - Winter | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Site Support - Winter | Site Support | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Support - 2 - BL - Hole Watch | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Hole Watch | Site Support | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - Sleeve Repair (first 394 weld – inches) | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Sleeve Repair (first 394 weld – inches) | Pipeline Repair | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - Sleeve Repair (>394 weld – inches) | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Sleeve Repair (>394 weld – inches) | Pipeline Repair | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - Clock Spring® Install | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Clock Spring® Install | Pipeline Repair | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - Atlas™ System Install (GTM Only) | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Atlas™ System Install (GTM Only) | Pipeline Repair | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Pipeline Repair - 2 - BL - PetroSleeve® Install (LP Only) | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | PetroSleeve® Install (LP Only) | Pipeline Repair | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Coating - 2 - BL - Coating Application (Epoxy) – Hand Applied | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Coating Application (Epoxy) – Hand Applied | Coating | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Coating - 2 - BL - Coating Application (Epoxy) – Spray Applied | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Coating Application (Epoxy) – Spray Applied | Coating | 3500028468 | ABC Group, Inc | 3048.57 | 304.857 | 0 | 304.857 |  | 100%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Coating - 2 - BL - Coating Application (Rock Shield) | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Coating Application (Rock Shield) | Coating | 3500028468 | ABC Group, Inc | 0 | 0 | 364.77 | 0 |  | 0% |  |  | 2021-05-01 | 2021-05-01
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Restoration - 2 - BL - Restoration Credit | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Restoration Credit | Site Restoration | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Restoration - 2 - BL - Topsoil & Restoration Credit | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Topsoil & Restoration Credit | Site Restoration | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Restoration - 2 - BL - Asphalt Resurfacing | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Asphalt Resurfacing | Site Restoration | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Site Restoration - 2 - BL - Access Route Reclamation | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Access Route Reclamation | Site Restoration | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Delays - 2 - BL - Weather or Company Controlled Delays | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Weather or Company Controlled Delays | Delays | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - De-mobilization - 2 - BL - Labor, Equipment & Supplies Demobilization (After Base Mileage) | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL | Labor, Equipment & Supplies Demobilization (After Base Mileage) | De-mobilization | 3500028468 | ABC Group, Inc | 0 | 0 | 0 | 0 |  | 0%
CWP - Dig-0219 - MC.400235.071 - 326.751 - Mobilization - 2 - BL - | Central | CWP | Dig-0219 | MC.400235.071 | 2020 | 326.751 | 2 | BL |  | Mobilization | 3500028468 | ABC Group, Inc | 5000 | 500 | 5000 | 500 |  | 100%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can't be a duplicate.

## LEM Entry
Lem ID | Package Type | Package ID | FCA | Date Entered | Issuance | WEA | Cost Item | WBS Activity | LEM # | Dig ID | WO Number | WBS | WBS Year | Vendor Name | Line Segment | Line | Trigger Anomaly WC | GW | Region | State | Mile Post | Date | Comments | First Name | Last Name | Position | ST Hrs | OT Hrs | DT Hrs | Per Diem | Equip Code | Unit Count | Unit | Equip. Number | Description | Qty | Units | 3rd Party Vendor Name | 3rd Party Description | Qty3 | Unit4 | ST Rate | OT Rate | DT Rate | Per Diem Rate | Equip. Rate | Mat'l Unit Cost | Labor Costs | Per Diem Costs | Equip. Costs | Materials Cost | Man Hours | Equip Unit Count | Total Cost (Before 3rd Party) | GC 3rd Party Vendor Name With Cost | GC 3rd Party Invoice Number | Work Description | Third Party Costs | Mark Up | Taxes | Total 3rd Party | Scorecard Unit | Scope of Work Id | FP/VP/UPI | Baseline Units | Total Units | Scorecard Comments | Rate | Cost | Discount % | Total Costs | Invoice Number | Payment Certificate Number
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | BARKLEY | BROWN | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | WAYLON | GREEN | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | JOSE | VALLES | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | LUTHER | LINDLEY | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | JONATHAN (BLAKE) | HOLLEY | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | RYAN | FARINELLI | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | DAVID | KNOTTS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | JEREMAINE | EVANS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | DEMETRIUS | MCDONALD | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | KYLE | BONNEAU | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | MICHEAL | RATLIFF | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | RAYMOND | RATLIFF | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | MICHAEL | ELLIOTT | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | SETH | RATLIFF | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | DAVID (BLAKE) | RATLIFF | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | TOME | KIRKLAND | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | CALEB | HOLTON | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 |  | ABC 3500028468-07
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | MICHAEL | ANISZEWSKI | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | BOLDBAATAR | ZORIGT | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | JORDAN | WIGGINS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | GERALD (WAYNE) | SMITH | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | RICHARD | SHOEMAKE | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | GREG | MCMILLIAN | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | OJ | SEALS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | JAMES | KERVIN | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | BRIAN | RANDLE | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | TYLER | BIGG | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | ALDO | REYNA | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-09-30 |  | RICHARD | THOMAS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | BARKLEY | BROWN | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | WAYLON | GREEN | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | JOSE | VALLES | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | LUTHER | LINDLEY | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | JONATHAN (BLAKE) | HOLLEY | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | RYAN | FARINELLI | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | DAVID | KNOTTS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | JEREMAINE | EVANS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | DEMETRIUS | MCDONALD | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | KYLE | BONNEAU | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | MICHEAL | RATLIFF | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | RAYMOND | RATLIFF | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | MICHAEL | ELLIOTT | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | SETH | RATLIFF | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | DAVID (BLAKE) | RATLIFF | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | TOME | KIRKLAND | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | CALEB | HOLTON | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | MICHAEL | ANISZEWSKI | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | BOLDBAATAR | ZORIGT | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | JORDAN | WIGGINS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | GERALD (WAYNE) | SMITH | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | RICHARD | SHOEMAKE | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | GREG | MCMILLIAN | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | OJ | SEALS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | JAMES | KERVIN | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | BRIAN | RANDLE | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | TYLER | BIGG | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | ALDO | REYNA | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-01 |  | RICHARD | THOMAS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | BARKLEY | BROWN | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | WAYLON | GREEN | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | JOSE | VALLES | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | LUTHER | LINDLEY | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | JONATHAN (BLAKE) | HOLLEY | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | RYAN | FARINELLI | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | DAVID | KNOTTS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | JEREMAINE | EVANS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | DEMETRIUS | MCDONALD | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | KYLE | BONNEAU | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 130 |  | 12 | 10 | 1273 | [16 empty] | 1273 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | Mob-1 | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-02 |  | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-01 | ABC 3500028468-01
CWP - Dig-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 1 - 3rd party | Dig-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-03 | [32 empty] | ATLAS WRAP | 11312 | TRAINING | 8145.91 | 651.67 |  | 8797.58 | [9 empty] | 8797.58 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44109-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-05 | MATCHES DIG SITE FOR CREW 2. 6 MATS WERE USED ON CREW 2 FOR WE 10/10/20 AND THEY WERE NOT CAPTURED ON THE SIT SPECIFIC TIMESHEET THAT WAS ALREADY APPROVED. | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | Mats | 6 | Ea |  |  |  |  | 93.5 | 126 | 0 | 151 | 13 | 325 | 1000 | 151 | 130 | 1950 | 10 | 10 | 3231 | [16 empty] | 3231 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44109-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-05 | MATCHES DIG SITE FOR CREW 2. 6 MATS WERE USED ON CREW 2 FOR WE 10/10/20 AND THEY WERE NOT CAPTURED ON THE SIT SPECIFIC TIMESHEET THAT WAS ALREADY APPROVED. | JAY | MASEY | Quality Assurance Inspector | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 105 | 0 | 0 | 151 | 42 |  | 840 | 151 | 420 |  | 10 | 10 | 1411 | [16 empty] | 1411 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44109-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-05 | MATCHES DIG SITE FOR CREW 2. 6 MATS WERE USED ON CREW 2 FOR WE 10/10/20 AND THEY WERE NOT CAPTURED ON THE SIT SPECIFIC TIMESHEET THAT WAS ALREADY APPROVED. | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 74 | 100 | 0 | 151 | 42 |  | 792 | 151 | 420 |  | 10 | 10 | 1363 | [16 empty] | 1363 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44109-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-05 | MATCHES DIG SITE FOR CREW 2. 6 MATS WERE USED ON CREW 2 FOR WE 10/10/20 AND THEY WERE NOT CAPTURED ON THE SIT SPECIFIC TIMESHEET THAT WAS ALREADY APPROVED. | KIM | FORNALL | Project Coordinator | 8 | 2 |  | 1 | Lowboy Trailer | 10 | HR | 2449 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 790.4 | 151 | 185 |  | 10 | 10 | 1126.4 | [16 empty] | 1126.4 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44109-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-05 | MATCHES DIG SITE FOR CREW 2. 6 MATS WERE USED ON CREW 2 FOR WE 10/10/20 AND THEY WERE NOT CAPTURED ON THE SIT SPECIFIC TIMESHEET THAT WAS ALREADY APPROVED. | MICHAEL | GOSS | Truck Driver/CDL | 8 | 4 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 716 | 151 | 185 |  | 12 | 10 | 1052 | [16 empty] | 1052 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44109-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-05 | MATCHES DIG SITE FOR CREW 2. 6 MATS WERE USED ON CREW 2 FOR WE 10/10/20 AND THEY WERE NOT CAPTURED ON THE SIT SPECIFIC TIMESHEET THAT WAS ALREADY APPROVED. | RICHARD | THOMAS | Truck Driver/CDL | 8 | 4 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 716 | 151 |  |  | 12 |  | 867 | [16 empty] | 867 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44110-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | MATCHES DIG SITE FOR CREW 3 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44110-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | MATCHES DIG SITE FOR CREW 4 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 105 | 0 | 0 | 151 | 42 |  | 1050 | 151 | 420 |  | 10 | 10 | 1621 | [16 empty] | 1621 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44110-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | MATCHES DIG SITE FOR CREW 5 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 74 | 100 | 0 | 151 | 42 |  | 792 | 151 | 420 |  | 10 | 10 | 1363 | [16 empty] | 1363 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44110-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | MATCHES DIG SITE FOR CREW 6 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Lowboy Trailer | 10 | HR | 2449 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 988 | 151 | 185 |  | 10 | 10 | 1324 | [16 empty] | 1324 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44110-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | MATCHES DIG SITE FOR CREW 7 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 4 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 716 | 151 | 185 |  | 12 | 10 | 1052 | [16 empty] | 1052 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44110-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | MATCHES DIG SITE FOR CREW 8 | RICHARD | THOMAS | Truck Driver/CDL | 8 | 4 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 716 | 151 |  |  | 12 |  | 867 | [16 empty] | 867 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | JONATHAN | HOLLY | Foreman | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15334 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 518 | 151 | 130 |  | 7 | 10 | 799 | [16 empty] | 799 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | JONATHAN | HOLLY | Foreman | 1 | 2 | [13 empty] | 74 | 100 | 0 | 151 |  |  | 274 | 0 |  |  | 3 |  | 274 | [16 empty] | 274 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | RYAN | FARINELLI | Operator II | 7 |  |  | 1 | [11 empty] | 61.5 | 83 | 0 | 151 |  |  | 430.5 | 151 |  |  | 7 |  | 581.5 | [16 empty] | 581.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | RYAN | FARINELLI | Operator II | 1 | 2 | [13 empty] | 61.5 | 83 | 0 | 151 |  |  | 227.5 | 0 |  |  | 3 |  | 227.5 | [16 empty] | 227.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | DAVID | KNOTTS | Laborer | 7 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 329 | 151 |  |  | 7 |  | 480 | [16 empty] | 480 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | DAVID | KNOTTS | Laborer | 1 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 173 | 0 |  |  | 3 |  | 173 | [16 empty] | 173 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | JEREMAINE | EVANS | Laborer | 7 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 329 | 151 |  |  | 7 |  | 480 | [16 empty] | 480 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | JEREMAINE | EVANS | Laborer | 1 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 173 | 0 |  |  | 3 |  | 173 | [16 empty] | 173 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | DEMETRIUS | MCDONALD | Laborer | 7 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 329 | 151 |  |  | 7 |  | 480 | [16 empty] | 480 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | DEMETRIUS | MCDONALD | Laborer | 1 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 173 | 0 |  |  | 3 |  | 173 | [16 empty] | 173 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | BRIAN | RANDLE | Truck Driver/CDL | 7 |  |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 374.5 | 151 |  |  | 7 |  | 525.5 | [16 empty] | 525.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44110-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-06 |  | BRIAN | RANDLE | Truck Driver/CDL | 1 | 2 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 197.5 | 0 |  |  | 3 |  | 197.5 | [16 empty] | 197.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44110-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-06 | MET AT STATION AND GOT EQUIPMENT ORGANIZED. THEN DROVE TO THE ROW AND ASSESSED THE DIG SITE AND GOT FAMILIAR WITH INSPECTION TEAM | KYLE | BONNEAU | Foreman | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 15335 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 792 | 151 | 160 |  | 10 | 10 | 1103 | [16 empty] | 1103 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44110-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-06 | MET AT STATION AND GOT EQUIPMENT ORGANIZED. THEN DROVE TO THE ROW AND ASSESSED THE DIG SITE AND GOT FAMILIAR WITH INSPECTION TEAM | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 658 | 151 | 160 |  | 10 | 10 | 969 | [16 empty] | 969 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44110-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-06 | MET AT STATION AND GOT EQUIPMENT ORGANIZED. THEN DROVE TO THE ROW AND ASSESSED THE DIG SITE AND GOT FAMILIAR WITH INSPECTION TEAM | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44110-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-06 | MET AT STATION AND GOT EQUIPMENT ORGANIZED. THEN DROVE TO THE ROW AND ASSESSED THE DIG SITE AND GOT FAMILIAR WITH INSPECTION TEAM | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44110-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-06 | MET AT STATION AND GOT EQUIPMENT ORGANIZED. THEN DROVE TO THE ROW AND ASSESSED THE DIG SITE AND GOT FAMILIAR WITH INSPECTION TEAM | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44110-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-06 | MET AT STATION AND GOT EQUIPMENT ORGANIZED. THEN DROVE TO THE ROW AND ASSESSED THE DIG SITE AND GOT FAMILIAR WITH INSPECTION TEAM | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44110-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-06 | MET AT STATION AND GOT EQUIPMENT ORGANIZED. THEN DROVE TO THE ROW AND ASSESSED THE DIG SITE AND GOT FAMILIAR WITH INSPECTION TEAM | MATTHEW | SCHMITT | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44110-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-06 | MET AT STATION AND GOT EQUIPMENT ORGANIZED. THEN DROVE TO THE ROW AND ASSESSED THE DIG SITE AND GOT FAMILIAR WITH INSPECTION TEAM | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | RATLIFF | Foreman | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19111 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 148 | 0 | 32 |  | 2 | 2 | 180 | [16 empty] | 180 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | RATLIFF | Foreman | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 19111 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 222 | 0 | 48 |  | 3 | 3 | 270 | [16 empty] | 270 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | RATLIFF | Foreman | 3 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 19111 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 522 | 151 | 80 |  | 6 | 5 | 753 | [16 empty] | 753 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SHAWN | ROSE | Operator II | 5 |  |  | 1 | [11 empty] | 61.5 | 83 | 0 | 151 |  |  | 307.5 | 151 |  |  | 5 |  | 458.5 | [16 empty] | 458.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SHAWN | ROSE | Operator II | 3 | 2 | [13 empty] | 61.5 | 83 | 0 | 151 |  |  | 350.5 | 0 |  |  | 5 |  | 350.5 | [16 empty] | 350.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | ELLIOTT | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | 2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 0 | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | ELLIOTT | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | 2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 0 | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | ELLIOTT | Laborer | 3 | 3 |  | 1 | Tool Trailer | 5 | HR | 2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 330 | 151 | 25 |  | 6 | 5 | 506 | [16 empty] | 506 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SETH | RATLIFF | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 | 0 | 112 |  | 2 | 7 | 206 | [16 empty] | 206 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SETH | RATLIFF | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 | 0 | 48 |  | 3 | 3 | 189 | [16 empty] | 189 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SETH | RATLIFF | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | DAVID | RATLIFF | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 7 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 0 | 129.5 |  | 2 | 7 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | DAVID | RATLIFF | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 0 | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | DAVID | RATLIFF | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | ERNESTO | TREJO | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 0 | 230 |  | 2 | 5 | 324 | [16 empty] | 324 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | ERNESTO | TREJO | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | ERNESTO | TREJO | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | CHRISTOPHER | URBAN | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | CHRISTOPHER | URBAN | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | CHRISTOPHER | URBAN | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | TYLER | BIGG | Truck Driver/CDL | 7 |  |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 374.5 | 151 |  |  | 7 |  | 525.5 | [16 empty] | 525.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | TYLER | BIGG | Truck Driver/CDL | 1 | 3 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 269.5 | 0 |  |  | 4 |  | 269.5 | [16 empty] | 269.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-06 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | TYLER | BIGG | Truck Driver/CDL |  | 1 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 72 | 0 |  |  | 1 |  | 72 | [16 empty] | 72 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44110-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-06 | MOB IN ON DIG WITH SKIDSTEER | WAYNE | SMITH | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15336 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 130 |  | 11 | 10 | 1173 | [16 empty] | 1173 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44110-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-06 | MOB IN ON DIG WITH SKIDSTEER | RICHARD | SHOEMAKE | Operator II | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | 2180 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 658 | 151 | 50 |  | 10 | 10 | 859 | [16 empty] | 859 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44110-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-06 | MOB IN ON DIG WITH SKIDSTEER | OJ | SEALS | Laborer | 8 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 565 | 151 | 160 |  | 11 | 10 | 876 | [16 empty] | 876 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44110-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-06 | MOB IN ON DIG WITH SKIDSTEER | JAMES | KERVIN | Laborer | 8 | 3 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT2605 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 565 | 151 | 74 |  | 11 | 4 | 790 | [16 empty] | 790 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44110-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-06 | MOB IN ON DIG WITH SKIDSTEER | STEVE | CLARK | Truck Driver/CDL | 8 | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1620 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 644 | 151 | 184 |  | 11 | 4 | 979 | [16 empty] | 979 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44110-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-06 | PREPARED TOOL TRAILER AND UNLOADED EQUIPMENT THAT WAS BEING RECEIVED AT THOMPKINSVILLE STATION. | BARKLEY | BROWN | Foreman | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19115 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 792 | 151 | 160 |  | 10 | 10 | 1103 | [16 empty] | 1103 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44110-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-06 | PREPARED TOOL TRAILER AND UNLOADED EQUIPMENT THAT WAS BEING RECEIVED AT THOMPKINSVILLE STATION. | MATTHEW | LINDLEY | Operator II | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF0380 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 658 | 151 | 160 |  | 10 | 10 | 969 | [16 empty] | 969 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44110-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-06 | PREPARED TOOL TRAILER AND UNLOADED EQUIPMENT THAT WAS BEING RECEIVED AT THOMPKINSVILLE STATION. | WAYLON | GREEN | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | 2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44110-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-06 | PREPARED TOOL TRAILER AND UNLOADED EQUIPMENT THAT WAS BEING RECEIVED AT THOMPKINSVILLE STATION. | JOSE | VALLES | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44110-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-06 | PREPARED TOOL TRAILER AND UNLOADED EQUIPMENT THAT WAS BEING RECEIVED AT THOMPKINSVILLE STATION. | LUTHER | LINDLEY | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44110-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-06 | PREPARED TOOL TRAILER AND UNLOADED EQUIPMENT THAT WAS BEING RECEIVED AT THOMPKINSVILLE STATION. | MARCELO | GOMEZ | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44110-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-06 | PREPARED TOOL TRAILER AND UNLOADED EQUIPMENT THAT WAS BEING RECEIVED AT THOMPKINSVILLE STATION. | ANTHONY | MORENO | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44110-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-06 | PREPARED TOOL TRAILER AND UNLOADED EQUIPMENT THAT WAS BEING RECEIVED AT THOMPKINSVILLE STATION. | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | JODY | BROOM | Superintendent | 2 |  |  |  | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 93.5 | 126 | 0 | 151 | 42 |  | 187 | 0 | 420 |  | 2 | 10 | 607 | [16 empty] | 607 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | JODY | BROOM | Superintendent | 2 | [14 empty] | 93.5 | 126 | 0 | 151 |  |  | 187 | 0 |  |  | 2 |  | 187 | [16 empty] | 187 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | JODY | BROOM | Superintendent | 3 | [14 empty] | 93.5 | 126 | 0 | 151 |  |  | 280.5 | 0 |  |  | 3 |  | 280.5 | [16 empty] | 280.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | JODY | BROOM | Superintendent | 1 | 2 |  | 1 | [11 empty] | 93.5 | 126 | 0 | 151 |  |  | 345.5 | 151 |  |  | 3 |  | 496.5 | [16 empty] | 496.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 105 | 0 | 0 | 151 | 42 |  | 210 | 0 | 420 |  | 2 | 10 | 630 | [16 empty] | 630 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | JAY | MASEY | Quality Assurance Inspector | 2 | [14 empty] | 105 | 0 | 0 | 151 |  |  | 210 | 0 |  |  | 2 |  | 210 | [16 empty] | 210 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | JAY | MASEY | Quality Assurance Inspector | 3 | [14 empty] | 105 | 0 | 0 | 151 |  |  | 315 | 0 |  |  | 3 |  | 315 | [16 empty] | 315 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | JAY | MASEY | Quality Assurance Inspector | 3 |  |  | 1 | [11 empty] | 105 | 0 | 0 | 151 |  |  | 315 | 151 |  |  | 3 |  | 466 | [16 empty] | 466 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Lowboy Trailer | 10 | HR | 2449 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 197.6 | 0 | 185 |  | 2 | 10 | 382.6 | [16 empty] | 382.6 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | KIM | FORNALL | Project Coordinator | 2 | [14 empty] | 98.8 | 0 | 0 | 151 |  |  | 197.6 | 0 |  |  | 2 |  | 197.6 | [16 empty] | 197.6 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | KIM | FORNALL | Project Coordinator | 3 | [14 empty] | 98.8 | 0 | 0 | 151 |  |  | 296.4 | 0 |  |  | 3 |  | 296.4 | [16 empty] | 296.4 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | KIM | FORNALL | Project Coordinator | 3 |  |  | 1 | [11 empty] | 98.8 | 0 | 0 | 151 |  |  | 296.4 | 151 |  |  | 3 |  | 447.4 | [16 empty] | 447.4 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 4 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 716 | 151 | 185 |  | 12 | 10 | 1052 | [16 empty] | 1052 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | MATCHES DIG SITE FOR CREW 4 | RICHARD | THOMAS | Truck Driver/CDL | 8 | 4 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 716 | 151 |  |  | 12 |  | 867 | [16 empty] | 867 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | JONATHAN | HOLLY | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15334 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 | 0 | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | JONATHAN | HOLLY | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15334 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 | 0 | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | JONATHAN | HOLLY | Foreman | 2 | 3 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15334 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 448 | 151 | 65 |  | 5 | 5 | 664 | [16 empty] | 664 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | RYAN | FARINELLI | Operator II | 8 | 3 |  | 1 | [11 empty] | 61.5 | 83 | 0 | 151 |  |  | 741 | 151 |  |  | 11 |  | 892 | [16 empty] | 892 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | GREG | MCMILLIAN | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | 2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 0 | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | GREG | MCMILLIAN | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | 2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 0 | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | GREG | MCMILLIAN | Laborer | 2 | 3 |  | 1 | Tool Trailer | 5 | HR | 2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 283 | 151 | 25 |  | 5 | 5 | 459 | [16 empty] | 459 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | JEREMAINE | EVANS | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 0 | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | JEREMAINE | EVANS | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 0 | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | JEREMAINE | EVANS | Laborer | 2 | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 283 | 151 | 92 |  | 5 | 2 | 526 | [16 empty] | 526 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | DEMETRIUS | MCDONALD | Laborer | 8 | 3 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 565 | 151 |  |  | 11 |  | 716 | [16 empty] | 716 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | BRIAN | RANDLE | Truck Driver/CDL | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0563 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 160.5 | 0 | 271.5 |  | 3 | 3 | 432 | [16 empty] | 432 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | BRIAN | RANDLE | Truck Driver/CDL | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0563 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 160.5 | 0 | 271.5 |  | 3 | 3 | 432 | [16 empty] | 432 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 |  | BRIAN | RANDLE | Truck Driver/CDL | 2 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 323 | 151 | 181 |  | 5 | 2 | 655 | [16 empty] | 655 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 | [8 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 | [8 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44111-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-07 | [8 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44111-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-07 | WENT TO STATION TO GET SUPPLIES TO START POTHOLE, SET UP GOAL POSTS, AT 7:30AM GOT TEXT FROM INSPECTOR ABOUT ACCESS PROBLEMS, AT 1:00PM GOT A CALL TO GO TO ANOTHER DIG SITE AND THEN IT CHANGED AGAIN TO STAY AND LOG TIME AS STANDBY | KYLE | BONNEAU | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44111-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-07 | WENT TO STATION TO GET SUPPLIES TO START POTHOLE, SET UP GOAL POSTS, AT 7:30AM GOT TEXT FROM INSPECTOR ABOUT ACCESS PROBLEMS, AT 1:00PM GOT A CALL TO GO TO ANOTHER DIG SITE AND THEN IT CHANGED AGAIN TO STAY AND LOG TIME AS STANDBY | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 658 | 151 | 160 |  | 10 | 10 | 969 | [16 empty] | 969 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44111-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-07 | WENT TO STATION TO GET SUPPLIES TO START POTHOLE, SET UP GOAL POSTS, AT 7:30AM GOT TEXT FROM INSPECTOR ABOUT ACCESS PROBLEMS, AT 1:00PM GOT A CALL TO GO TO ANOTHER DIG SITE AND THEN IT CHANGED AGAIN TO STAY AND LOG TIME AS STANDBY | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44111-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-07 | WENT TO STATION TO GET SUPPLIES TO START POTHOLE, SET UP GOAL POSTS, AT 7:30AM GOT TEXT FROM INSPECTOR ABOUT ACCESS PROBLEMS, AT 1:00PM GOT A CALL TO GO TO ANOTHER DIG SITE AND THEN IT CHANGED AGAIN TO STAY AND LOG TIME AS STANDBY | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44111-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-07 | WENT TO STATION TO GET SUPPLIES TO START POTHOLE, SET UP GOAL POSTS, AT 7:30AM GOT TEXT FROM INSPECTOR ABOUT ACCESS PROBLEMS, AT 1:00PM GOT A CALL TO GO TO ANOTHER DIG SITE AND THEN IT CHANGED AGAIN TO STAY AND LOG TIME AS STANDBY | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44111-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-07 | WENT TO STATION TO GET SUPPLIES TO START POTHOLE, SET UP GOAL POSTS, AT 7:30AM GOT TEXT FROM INSPECTOR ABOUT ACCESS PROBLEMS, AT 1:00PM GOT A CALL TO GO TO ANOTHER DIG SITE AND THEN IT CHANGED AGAIN TO STAY AND LOG TIME AS STANDBY | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44111-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-07 | WENT TO STATION TO GET SUPPLIES TO START POTHOLE, SET UP GOAL POSTS, AT 7:30AM GOT TEXT FROM INSPECTOR ABOUT ACCESS PROBLEMS, AT 1:00PM GOT A CALL TO GO TO ANOTHER DIG SITE AND THEN IT CHANGED AGAIN TO STAY AND LOG TIME AS STANDBY | MATTHEW | SCHMITT | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44111-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-07 | WENT TO STATION TO GET SUPPLIES TO START POTHOLE, SET UP GOAL POSTS, AT 7:30AM GOT TEXT FROM INSPECTOR ABOUT ACCESS PROBLEMS, AT 1:00PM GOT A CALL TO GO TO ANOTHER DIG SITE AND THEN IT CHANGED AGAIN TO STAY AND LOG TIME AS STANDBY | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | MICHAEL | RATLIFF | Foreman | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 19111 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 296 | 0 | 80 |  | 4 | 5 | 376 | [16 empty] | 376 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | MICHAEL | RATLIFF | Foreman | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 19111 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 222 | 0 | 80 |  | 3 | 5 | 302 | [16 empty] | 302 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | MICHAEL | RATLIFF | Foreman | 1 | 4 |  | 1 | [11 empty] | 74 | 100 | 0 | 151 |  |  | 474 | 151 |  |  | 5 |  | 625 | [16 empty] | 625 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | SHAWN | ROSE | Operator II | 11 |  |  | 1 | [11 empty] | 61.5 | 83 | 0 | 151 |  |  | 676.5 | 151 |  |  | 11 |  | 827.5 | [16 empty] | 827.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | MICHAEL | ELLIOTT | Laborer | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 | 0 | 80 |  | 4 | 5 | 268 | [16 empty] | 268 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | MICHAEL | ELLIOTT | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 | 0 | 80 |  | 3 | 5 | 221 | [16 empty] | 221 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | MICHAEL | ELLIOTT | Laborer | 1 | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 299 | 151 |  |  | 5 |  | 450 | [16 empty] | 450 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | SETH | RATLIFF | Laborer | 4 |  |  |  | Tool Trailer | 5 | HR | 2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 0 | 25 |  | 4 | 5 | 213 | [16 empty] | 213 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | SETH | RATLIFF | Laborer | 3 |  |  |  | Tool Trailer | 5 | HR | 2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 0 | 25 |  | 3 | 5 | 166 | [16 empty] | 166 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | SETH | RATLIFF | Laborer | 1 | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 299 | 151 |  |  | 5 |  | 450 | [16 empty] | 450 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | DAVID | RATLIFF | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 | 0 |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | DAVID | RATLIFF | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | DAVID | RATLIFF | Laborer | 1 | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 299 | 151 |  |  | 5 |  | 450 | [16 empty] | 450 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | ERNESTO | TREJO | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 | 0 |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | ERNESTO | TREJO | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | ERNESTO | TREJO | Laborer | 1 | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 299 | 151 |  |  | 5 |  | 450 | [16 empty] | 450 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | CHRISTOPHER | URBAN | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 | 0 |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | CHRISTOPHER | URBAN | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | CHRISTOPHER | URBAN | Laborer | 1 | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 299 | 151 |  |  | 5 |  | 450 | [16 empty] | 450 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | TYLER | BIGG | Truck Driver/CDL | 4 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 214 | 0 |  |  | 4 |  | 214 | [16 empty] | 214 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | TYLER | BIGG | Truck Driver/CDL | 3 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 160.5 | 0 |  |  | 3 |  | 160.5 | [16 empty] | 160.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44111-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-07 | STAGED/LOADED EQUIPMENT AND MATERIALS. SITE ACCESS AND SITE PREP | TYLER | BIGG | Truck Driver/CDL | 1 | 4 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 341.5 | 151 |  |  | 5 |  | 492.5 | [16 empty] | 492.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | GERALD | SMITH | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | 2888 Coating | 4 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 22.35 | 148 | 0 | 26 | 89.4 | 2 | 2 | 263.4 | [16 empty] | 263.4 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | GERALD | SMITH | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 0 | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | GERALD | SMITH | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 0 | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - NDE Assessment - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | NDE Assessment | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | GERALD | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 | 0 | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | GERALD | SMITH | Foreman | 1 | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 374 | 151 | 39 |  | 4 | 3 | 564 | [16 empty] | 564 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | RICHARD | SHOEMAKE | Operator II | 2 |  |  |  | Tool Trailer | 2 | HR | 2180 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 123 | 0 | 10 |  | 2 | 2 | 133 | [16 empty] | 133 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | RICHARD | SHOEMAKE | Operator II | 2 |  |  |  | Tool Trailer | 2 | HR | 2180 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 123 | 0 | 10 |  | 2 | 2 | 133 | [16 empty] | 133 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | RICHARD | SHOEMAKE | Operator II | 2 |  |  |  | Tool Trailer | 2 | HR | 2180 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 123 | 0 | 10 |  | 2 | 2 | 133 | [16 empty] | 133 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - NDE Assessment - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | NDE Assessment | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | RICHARD | SHOEMAKE | Operator II | 1 |  |  |  | Tool Trailer | 1 | HR | 2180 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 61.5 | 0 | 5 |  | 1 | 1 | 66.5 | [16 empty] | 66.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | RICHARD | SHOEMAKE | Operator II | 1 | 2 |  | 1 | Tool Trailer | 3 | HR | 2180 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 227.5 | 151 | 15 |  | 3 | 3 | 393.5 | [16 empty] | 393.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | OJ | SEALS | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 0 | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | OJ | SEALS | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 0 | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | OJ | SEALS | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 0 | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - NDE Assessment - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | NDE Assessment | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | OJ | SEALS | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 | 0 | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | OJ | SEALS | Laborer | 1 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 173 | 151 | 138 |  | 3 | 3 | 462 | [16 empty] | 462 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | JAMES | KERVIN | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 0 | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | JAMES | KERVIN | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 0 | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | JAMES | KERVIN | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 0 | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - NDE Assessment - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | NDE Assessment | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | JAMES | KERVIN | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 0 | 90.5 |  | 2 | 1 | 184.5 | [16 empty] | 184.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | JAMES | KERVIN | Laborer |  | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 | 151 | 271.5 |  | 3 | 3 | 611.5 | [16 empty] | 611.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RT439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44111-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-07 | PUT UP GOAL POST UNDER POWER LINE AT ENTRANCE TO WORK SITE. MOB IN TRACK HOE AND TOOL TRAILER. DID DHE ASSESSMENT ON STRIKE COATING. JEEP PIPE AND FOUND 50+ JEEPS ON PIPE. PATCHED WITH 2888 COATING. | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44111-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-07 | CREW MOBILIZED FROM TOMPKINSVILLE KY TO DIG SITE. F550 BROUGHT GOOSENECK TRAILER, 1 PALLET OF SAND AND SKIDSTEER TO DIG SITE. F550 WENT BACK TO BRING TOOL TRAILER TO DIG SITE TOMORROW. | TOME | KIRKLAND | Foreman | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF9120 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 792 | 151 | 160 |  | 10 | 10 | 1103 | [16 empty] | 1103 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44111-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-07 | CREW MOBILIZED FROM TOMPKINSVILLE KY TO DIG SITE. F550 BROUGHT GOOSENECK TRAILER, 1 PALLET OF SAND AND SKIDSTEER TO DIG SITE. F550 WENT BACK TO BRING TOOL TRAILER TO DIG SITE TOMORROW. | CALEB | HOLTON | Operator II | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 13 | HR | 1998 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 658 | 151 | 208 |  | 10 | 13 | 1017 | [16 empty] | 1017 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44111-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-07 | CREW MOBILIZED FROM TOMPKINSVILLE KY TO DIG SITE. F550 BROUGHT GOOSENECK TRAILER, 1 PALLET OF SAND AND SKIDSTEER TO DIG SITE. F550 WENT BACK TO BRING TOOL TRAILER TO DIG SITE TOMORROW. | MICHAEL | ANISZEWKSI | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 13 | HR | GNT8992 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 240.5 |  | 10 | 13 | 893.5 | [16 empty] | 893.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44111-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-07 | CREW MOBILIZED FROM TOMPKINSVILLE KY TO DIG SITE. F550 BROUGHT GOOSENECK TRAILER, 1 PALLET OF SAND AND SKIDSTEER TO DIG SITE. F550 WENT BACK TO BRING TOOL TRAILER TO DIG SITE TOMORROW. | BOLDBAATAR | ZORIGT | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 13 | HR | RSS3492 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 598 |  | 10 | 13 | 1251 | [16 empty] | 1251 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44111-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-07 | CREW MOBILIZED FROM TOMPKINSVILLE KY TO DIG SITE. F550 BROUGHT GOOSENECK TRAILER, 1 PALLET OF SAND AND SKIDSTEER TO DIG SITE. F550 WENT BACK TO BRING TOOL TRAILER TO DIG SITE TOMORROW. | JORDAN | WIGGINS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44111-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-07 | CREW MOBILIZED FROM TOMPKINSVILLE KY TO DIG SITE. F550 BROUGHT GOOSENECK TRAILER, 1 PALLET OF SAND AND SKIDSTEER TO DIG SITE. F550 WENT BACK TO BRING TOOL TRAILER TO DIG SITE TOMORROW. | DAIVD | KNOTTS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44111-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-07 | CREW MOBILIZED FROM TOMPKINSVILLE KY TO DIG SITE. F550 BROUGHT GOOSENECK TRAILER, 1 PALLET OF SAND AND SKIDSTEER TO DIG SITE. F550 WENT BACK TO BRING TOOL TRAILER TO DIG SITE TOMORROW. | TANNER | BRITT | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44111-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-07 | CREW MOBILIZED FROM TOMPKINSVILLE KY TO DIG SITE. F550 BROUGHT GOOSENECK TRAILER, 1 PALLET OF SAND AND SKIDSTEER TO DIG SITE. F550 WENT BACK TO BRING TOOL TRAILER TO DIG SITE TOMORROW. | ALDO | REYNA | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44111-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-07 | PREPARE TO MOBILIZE, STOCKING UTILITY TRAILER, LOADING AND UNLOADING TRUCKS | BARKLEY | BROWN | Foreman | 8 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 11 | HR | 19115 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 892 | 151 | 176 |  | 11 | 11 | 1219 | [16 empty] | 1219 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44111-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-07 | PREPARE TO MOBILIZE, STOCKING UTILITY TRAILER, LOADING AND UNLOADING TRUCKS | MATTHEW | LINDLEY | Operator II | 8 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 11 | HR | RF0380 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 741 | 151 | 176 |  | 11 | 11 | 1068 | [16 empty] | 1068 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44111-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-07 | PREPARE TO MOBILIZE, STOCKING UTILITY TRAILER, LOADING AND UNLOADING TRUCKS | WAYLON | GREEN | Laborer | 8 | 3 |  | 1 | Tool Trailer | 4 | HR | 2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 565 | 151 | 20 |  | 11 | 4 | 736 | [16 empty] | 736 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44111-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-07 | PREPARE TO MOBILIZE, STOCKING UTILITY TRAILER, LOADING AND UNLOADING TRUCKS | JOSE | VALLES | Laborer | 8 | 3 |  | 1 | 40' Flatbed trailer or equal | 11 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 565 | 151 | 203.5 |  | 11 | 11 | 919.5 | [16 empty] | 919.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44111-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-07 | PREPARE TO MOBILIZE, STOCKING UTILITY TRAILER, LOADING AND UNLOADING TRUCKS | LUTHER | LINDLEY | Laborer | 8 | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 565 | 151 | 184 |  | 11 | 4 | 900 | [16 empty] | 900 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44111-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-07 | PREPARE TO MOBILIZE, STOCKING UTILITY TRAILER, LOADING AND UNLOADING TRUCKS | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 644 | 151 | 362 |  | 11 | 4 | 1157 | [16 empty] | 1157 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44111-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-07 | PREPARE TO MOBILIZE, STOCKING UTILITY TRAILER, LOADING AND UNLOADING TRUCKS | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | JODY | BROOM | Superintendent | 2 | [14 empty] | 93.5 | 126 | 0 | 151 |  |  | 187 | 0 |  |  | 2 |  | 187 | [16 empty] | 187 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | JODY | BROOM | Superintendent | 2 | [14 empty] | 93.5 | 126 | 0 | 151 |  |  | 187 | 0 |  |  | 2 |  | 187 | [16 empty] | 187 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | JODY | BROOM | Superintendent | 4 | 2 |  | 1 | [11 empty] | 93.5 | 126 | 0 | 151 |  |  | 626 | 151 |  |  | 6 |  | 777 | [16 empty] | 777 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | JAY | MASEY | Quality Assurance Inspector | 2 | [14 empty] | 105 | 0 | 0 | 151 |  |  | 210 | 0 |  |  | 2 |  | 210 | [16 empty] | 210 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | JAY | MASEY | Quality Assurance Inspector | 2 | [14 empty] | 105 | 0 | 0 | 151 |  |  | 210 | 0 |  |  | 2 |  | 210 | [16 empty] | 210 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | JAY | MASEY | Quality Assurance Inspector | 6 |  |  | 1 | [11 empty] | 105 | 0 | 0 | 151 |  |  | 630 | 151 |  |  | 6 |  | 781 | [16 empty] | 781 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | JUANITO | RODRIGUEZ | Safety Person | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 0 | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | JUANITO | RODRIGUEZ | Safety Person | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 0 | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | JUANITO | RODRIGUEZ | Safety Person | 4 | 2 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 496 | 151 | 78 |  | 6 | 6 | 725 | [16 empty] | 725 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | KIM | FORNALL | Project Coordinator | 2 | [14 empty] | 98.8 | 0 | 0 | 151 |  |  | 197.6 | 0 |  |  | 2 |  | 197.6 | [16 empty] | 197.6 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | KIM | FORNALL | Project Coordinator | 2 | [14 empty] | 98.8 | 0 | 0 | 151 |  |  | 197.6 | 0 |  |  | 2 |  | 197.6 | [16 empty] | 197.6 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | KIM | FORNALL | Project Coordinator | 6 |  |  | 1 | [11 empty] | 98.8 | 0 | 0 | 151 |  |  | 592.8 | 151 |  |  | 6 |  | 743.8 | [16 empty] | 743.8 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | RICHARD | THOMAS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | MATCHES DIG SITE FOR CREW 5. | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | JONATHAN | HOLLEY | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15334 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 | 0 | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | JONATHAN | HOLLEY | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15334 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 | 0 | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | JONATHAN | HOLLEY | Foreman | 2 | 2 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15334 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 348 | 151 | 52 |  | 4 | 4 | 551 | [16 empty] | 551 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | RYAN | FARINELLI | Operator II | 3 |  |  |  | Tool Trailer | 3 | HR | 2183 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 184.5 | 0 | 15 |  | 3 | 3 | 199.5 | [16 empty] | 199.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | RYAN | FARINELLI | Operator II | 3 |  |  |  | Tool Trailer | 3 | HR | 2183 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 184.5 | 0 | 15 |  | 3 | 3 | 199.5 | [16 empty] | 199.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | RYAN | FARINELLI | Operator II | 2 | 2 |  | 1 | Tool Trailer | 4 | HR | 2183 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 289 | 151 | 20 |  | 4 | 4 | 460 | [16 empty] | 460 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | GREG | MCMILLIAN | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 0 | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | GREG | MCMILLIAN | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 0 | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | GREG | MCMILLIAN | Laborer | 2 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 220 | 151 | 362 |  | 4 | 4 | 733 | [16 empty] | 733 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | JEREMAINE | EVANS | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | JEREMAINE | EVANS | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | JEREMAINE | EVANS | Laborer | 2 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 220 | 151 |  |  | 4 |  | 371 | [16 empty] | 371 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | DEMETRIUS | MCDONALD | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | DEMETRIUS | MCDONALD | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | DEMETRIUS | MCDONALD | Laborer | 2 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 220 | 151 |  |  | 4 |  | 371 | [16 empty] | 371 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | JOSE | ORTIZ | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | JOSE | ORTIZ | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | JOSE | ORTIZ | Laborer | 2 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 220 | 151 |  |  | 4 |  | 371 | [16 empty] | 371 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | ROBERT | FOSTER | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | ROBERT | FOSTER | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | ROBERT | FOSTER | Laborer | 2 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 220 | 151 |  |  | 4 |  | 371 | [16 empty] | 371 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | BRIAN | RANDLE | Truck Driver/CDL | 3 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 160.5 | 0 |  |  | 3 |  | 160.5 | [16 empty] | 160.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | BRIAN | RANDLE | Truck Driver/CDL | 3 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 160.5 | 0 |  |  | 3 |  | 160.5 | [16 empty] | 160.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44112-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-08 | BRUSH HOGGED THE ROW, FINISHED POTHOLING THE OTHER TWO LINES, 4-WAY SWEEP OF JOBSITE AND DIDN'T FIND ANYTHING, STARTED EXCAVATION ON LINE 10 TRYING TO FIND GIRTH WELD AND ANOMALY BUT IT WAS NOT WHERE SURVEY MARKED IT | BRIAN | RANDLE | Truck Driver/CDL | 2 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 251 | 151 |  |  | 4 |  | 402 | [16 empty] | 402 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44112-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-08 | MET WITH INSPECTOR AND EI. WENT OVER ACCESS AND CREEKS, BEGAN PLANNING (ORDERING MATERIAL), TRIMMED A LOT OF TREES AND SET GOAL POSTS. AT 11AM ACCESS WAS CHANGED, HAD TO TAKE DOWN GOAL POSTS AND MOVE TO ANOTHER LOCATION. STARTED TRIMMING TREES ON NEW ACCESS. POTHOLED 30" LINE IN CREEK, MADE PREPERATION TO BRUSH HOG ROW TOMORROW (ACCESS IS ABOUT 1 MILE LONG WITH (2) STREAM CROSSINGS. ANOMALY IS IN THE BOTTOM OF THE CREEK | KYLE | BONNEAU | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44112-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-08 | MET WITH INSPECTOR AND EI. WENT OVER ACCESS AND CREEKS, BEGAN PLANNING (ORDERING MATERIAL), TRIMMED A LOT OF TREES AND SET GOAL POSTS. AT 11AM ACCESS WAS CHANGED, HAD TO TAKE DOWN GOAL POSTS AND MOVE TO ANOTHER LOCATION. STARTED TRIMMING TREES ON NEW ACCESS. POTHOLED 30" LINE IN CREEK, MADE PREPERATION TO BRUSH HOG ROW TOMORROW (ACCESS IS ABOUT 1 MILE LONG WITH (2) STREAM CROSSINGS. ANOMALY IS IN THE BOTTOM OF THE CREEK | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 658 | 151 | 160 |  | 10 | 10 | 969 | [16 empty] | 969 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44112-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-08 | MET WITH INSPECTOR AND EI. WENT OVER ACCESS AND CREEKS, BEGAN PLANNING (ORDERING MATERIAL), TRIMMED A LOT OF TREES AND SET GOAL POSTS. AT 11AM ACCESS WAS CHANGED, HAD TO TAKE DOWN GOAL POSTS AND MOVE TO ANOTHER LOCATION. STARTED TRIMMING TREES ON NEW ACCESS. POTHOLED 30" LINE IN CREEK, MADE PREPERATION TO BRUSH HOG ROW TOMORROW (ACCESS IS ABOUT 1 MILE LONG WITH (2) STREAM CROSSINGS. ANOMALY IS IN THE BOTTOM OF THE CREEK | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44112-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-08 | MET WITH INSPECTOR AND EI. WENT OVER ACCESS AND CREEKS, BEGAN PLANNING (ORDERING MATERIAL), TRIMMED A LOT OF TREES AND SET GOAL POSTS. AT 11AM ACCESS WAS CHANGED, HAD TO TAKE DOWN GOAL POSTS AND MOVE TO ANOTHER LOCATION. STARTED TRIMMING TREES ON NEW ACCESS. POTHOLED 30" LINE IN CREEK, MADE PREPERATION TO BRUSH HOG ROW TOMORROW (ACCESS IS ABOUT 1 MILE LONG WITH (2) STREAM CROSSINGS. ANOMALY IS IN THE BOTTOM OF THE CREEK | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44112-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-08 | MET WITH INSPECTOR AND EI. WENT OVER ACCESS AND CREEKS, BEGAN PLANNING (ORDERING MATERIAL), TRIMMED A LOT OF TREES AND SET GOAL POSTS. AT 11AM ACCESS WAS CHANGED, HAD TO TAKE DOWN GOAL POSTS AND MOVE TO ANOTHER LOCATION. STARTED TRIMMING TREES ON NEW ACCESS. POTHOLED 30" LINE IN CREEK, MADE PREPERATION TO BRUSH HOG ROW TOMORROW (ACCESS IS ABOUT 1 MILE LONG WITH (2) STREAM CROSSINGS. ANOMALY IS IN THE BOTTOM OF THE CREEK | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44112-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-08 | MET WITH INSPECTOR AND EI. WENT OVER ACCESS AND CREEKS, BEGAN PLANNING (ORDERING MATERIAL), TRIMMED A LOT OF TREES AND SET GOAL POSTS. AT 11AM ACCESS WAS CHANGED, HAD TO TAKE DOWN GOAL POSTS AND MOVE TO ANOTHER LOCATION. STARTED TRIMMING TREES ON NEW ACCESS. POTHOLED 30" LINE IN CREEK, MADE PREPERATION TO BRUSH HOG ROW TOMORROW (ACCESS IS ABOUT 1 MILE LONG WITH (2) STREAM CROSSINGS. ANOMALY IS IN THE BOTTOM OF THE CREEK | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44112-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-08 | MET WITH INSPECTOR AND EI. WENT OVER ACCESS AND CREEKS, BEGAN PLANNING (ORDERING MATERIAL), TRIMMED A LOT OF TREES AND SET GOAL POSTS. AT 11AM ACCESS WAS CHANGED, HAD TO TAKE DOWN GOAL POSTS AND MOVE TO ANOTHER LOCATION. STARTED TRIMMING TREES ON NEW ACCESS. POTHOLED 30" LINE IN CREEK, MADE PREPERATION TO BRUSH HOG ROW TOMORROW (ACCESS IS ABOUT 1 MILE LONG WITH (2) STREAM CROSSINGS. ANOMALY IS IN THE BOTTOM OF THE CREEK | MATTHEW | SCHMITT | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44112-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-08 | MET WITH INSPECTOR AND EI. WENT OVER ACCESS AND CREEKS, BEGAN PLANNING (ORDERING MATERIAL), TRIMMED A LOT OF TREES AND SET GOAL POSTS. AT 11AM ACCESS WAS CHANGED, HAD TO TAKE DOWN GOAL POSTS AND MOVE TO ANOTHER LOCATION. STARTED TRIMMING TREES ON NEW ACCESS. POTHOLED 30" LINE IN CREEK, MADE PREPERATION TO BRUSH HOG ROW TOMORROW (ACCESS IS ABOUT 1 MILE LONG WITH (2) STREAM CROSSINGS. ANOMALY IS IN THE BOTTOM OF THE CREEK | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | RATLIFF | Foreman | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19111 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 148 | 0 | 32 |  | 2 | 2 | 180 | [16 empty] | 180 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | RATLIFF | Foreman | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 19111 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 222 | 0 | 48 |  | 3 | 3 | 270 | [16 empty] | 270 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | RATLIFF | Foreman | 3 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 19111 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 522 | 151 | 80 |  | 6 | 5 | 753 | [16 empty] | 753 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SHAWN | ROSE | Operator II | 5 |  |  | 1 | [11 empty] | 61.5 | 83 | 0 | 151 |  |  | 307.5 | 151 |  |  | 5 |  | 458.5 | [16 empty] | 458.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SHAWN | ROSE | Operator II | 3 | 2 | [13 empty] | 61.5 | 83 | 0 | 151 |  |  | 350.5 | 0 |  |  | 5 |  | 350.5 | [16 empty] | 350.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | ELLIOTT | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | 2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 0 | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | ELLIOTT | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | 2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 0 | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | MICHAEL | ELLIOTT | Laborer | 3 | 3 |  | 1 | Tool Trailer | 5 | HR | 2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 330 | 151 | 25 |  | 6 | 5 | 506 | [16 empty] | 506 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SETH | RATLIFF | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 | 0 | 112 |  | 2 | 7 | 206 | [16 empty] | 206 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SETH | RATLIFF | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 | 0 | 48 |  | 3 | 3 | 189 | [16 empty] | 189 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | SETH | RATLIFF | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | DAVID | RATLIFF | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 7 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 0 | 129.5 |  | 2 | 7 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | DAVID | RATLIFF | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 0 | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | DAVID | RATLIFF | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | ERNESTO | TREJO | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 0 | 230 |  | 2 | 5 | 324 | [16 empty] | 324 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | ERNESTO | TREJO | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | ERNESTO | TREJO | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | CHRISTOPHER | URBAN | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | CHRISTOPHER | URBAN | Laborer | 3 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 0 |  |  | 3 |  | 141 | [16 empty] | 141 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | CHRISTOPHER | URBAN | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | TYLER | BIGG | Truck Driver/CDL | 7 |  |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 374.5 | 151 |  |  | 7 |  | 525.5 | [16 empty] | 525.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | TYLER | BIGG | Truck Driver/CDL | 1 | 3 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 269.5 | 0 |  |  | 4 |  | 269.5 | [16 empty] | 269.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44112-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-08 | STAGING/MOBILIZATION OF SKIDSTEER VIA GOOSENECK TRAILER, COVID SANITARY STATION, LINE LOCATION, PROBING AND START DAYLIGHTING | TYLER | BIGG | Truck Driver/CDL |  | 1 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 72 | 0 |  |  | 1 |  | 72 | [16 empty] | 72 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | WAYNE | SMITH | Foreman | 1 | [14 empty] | 74 | 100 | 0 | 151 |  |  | 74 | 0 |  |  | 1 |  | 74 | [16 empty] | 74 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | WAYNE | SMITH | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15336 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 0 | 65 |  | 4 | 5 | 361 | [16 empty] | 361 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | WAYNE | SMITH | Foreman | 3 | 3 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15336 | Mats | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 325 | 522 | 151 | 65 | 1300 | 6 | 5 | 2038 | [16 empty] | 2038 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | RICHARD | SHOEMAKE | Operator II | 4 |  |  |  | Tool Trailer | 5 | HR | 2180 | 2888 Coating | 6 | L |  |  |  |  | 61.5 | 83 | 0 | 151 | 5 | 22.35 | 246 | 0 | 25 | 134.1 | 4 | 5 | 405.1 | [16 empty] | 405.1 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | RICHARD | SHOEMAKE | Operator II | 4 | 2 |  | 1 | Tool Trailer | 5 | HR | 2180 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 412 | 151 | 25 |  | 6 | 5 | 588 | [16 empty] | 588 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | OJ | SEALS | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 0 | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | OJ | SEALS | Laborer | 4 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 314 | 151 | 276 |  | 6 | 6 | 741 | [16 empty] | 741 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | JAMES | KERVIN | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 0 | 452.5 |  | 4 | 5 | 640.5 | [16 empty] | 640.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | JAMES | KERVIN | Laborer | 4 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 314 | 151 | 452.5 |  | 6 | 5 | 917.5 | [16 empty] | 917.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | RICHARD | ADKINS | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 | 0 |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | RICHARD | ADKINS | Laborer | 4 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 314 | 151 |  |  | 6 |  | 465 | [16 empty] | 465 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | NICHOLAS | BLANCO | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 | 0 |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | NICHOLAS | BLANCO | Laborer | 4 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 314 | 151 |  |  | 6 |  | 465 | [16 empty] | 465 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | BARRETT | WISE | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 | 0 |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | BARRETT | WISE | Laborer | 4 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 314 | 151 |  |  | 6 |  | 465 | [16 empty] | 465 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44112-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-08 | HAULED IN 4 MATS FOR SITE PREP. JEEPED PIPE AND REPAIRED 70+ SPOTS. GETTING TRACK HOE HOOKED UP WITH PADDING BUCKET | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | TOME | KIRKLAND | Foreman | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS3492 | [7 empty] | 74 | 100 | 0 | 151 | 46 |  | 148 | 0 | 92 |  | 2 | 2 | 240 | [16 empty] | 240 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | TOME | KIRKLAND | Foreman | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF9120 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 148 | 0 | 32 |  | 2 | 2 | 180 | [16 empty] | 180 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | TOME | KIRKLAND | Foreman | 4 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF9120 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 496 | 151 | 96 |  | 6 | 6 | 743 | [16 empty] | 743 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | CALEB | HOLTON | Operator II | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF9120 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 123 | 0 | 32 |  | 2 | 2 | 155 | [16 empty] | 155 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | CALEB | HOLTON | Operator II | 2 | [14 empty] | 61.5 | 83 | 0 | 151 |  |  | 123 | 0 |  |  | 2 |  | 123 | [16 empty] | 123 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | CALEB | HOLTON | Operator II | 4 | 2 |  | 1 | [11 empty] | 61.5 | 83 | 0 | 151 |  |  | 412 | 151 |  |  | 6 |  | 563 | [16 empty] | 563 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | MICHAEL | ANISZEWSKI | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | MICHAEL | ANISZEWSKI | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | MICHAEL | ANISZEWSKI | Laborer | 4 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 314 | 151 |  |  | 6 |  | 465 | [16 empty] | 465 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | BOLDBAATAR | ZORIGT | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | BOLDBAATAR | ZORIGT | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | BOLDBAATAR | ZORIGT | Laborer | 4 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 314 | 151 |  |  | 6 |  | 465 | [16 empty] | 465 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | JORDAN | WIGGINS | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | JORDAN | WIGGINS | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | JORDAN | WIGGINS | Laborer | 4 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 314 | 151 |  |  | 6 |  | 465 | [16 empty] | 465 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | DAIVD | KNOTTS | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | DAIVD | KNOTTS | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | DAIVD | KNOTTS | Laborer | 4 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 314 | 151 |  |  | 6 |  | 465 | [16 empty] | 465 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | TANNER | BRITT | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 0 |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | TANNER | BRITT | Laborer | 2 |  |  |  | Tool Trailer | 5 | HR | 2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 0 | 25 |  | 2 | 5 | 119 | [16 empty] | 119 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | TANNER | BRITT | Laborer | 4 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 314 | 151 | 362 |  | 6 | 4 | 827 | [16 empty] | 827 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | ALDO | REYNA | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 192 |  | 12 | 12 | 1059 | [16 empty] | 1059 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | [7 empty] | 40' Flatbed trailer or equal | 6 | HR | GNT8992 | [11 empty] | 18.5 |  |  |  | 111 |  |  | 6 | 111 | [16 empty] | 111 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | [7 empty] | Tool Trailer | 5 | HR | 2182 | [11 empty] | 5 |  |  |  | 25 |  |  | 5 | 25 | [16 empty] | 25 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44112-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-08 | ALL ENTERPRISE LINES WERE LOCATED AND MARKED. SETUP ALL NECESSARY ROAD SIGNAGE. UNLOADED EXCAVATOR AND (2) TRENCH BOXES. LOCATED AND MARKED 24" ENBRIDGE LINE. POTHOLED AT ANOMALY LOCATION AND 30' IN BOTH DIRECTIONS. COORDINATED WITH ENTERPRISE TO POTHOLE 16" ENBRIDGE DUE TO LINE BEING WITHIN 16' OF PROPOSED EXCAVATION AREA. T-POST AND SAFETY FENCE INSTALLED AROUND ALL POTHOLES THAT WEREN'T BACKFILLED. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44112-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-08 | MOBILIIZED TO DIG SITE | BARKLEY | BROWN | Foreman | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 19115 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 992 | 151 | 192 |  | 12 | 12 | 1335 | [16 empty] | 1335 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44112-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-08 | MOBILIIZED TO DIG SITE | MATTHEW | LINDLEY | Operator II | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | RF0380 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 824 | 151 | 192 |  | 12 | 12 | 1167 | [16 empty] | 1167 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44112-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-08 | MOBILIIZED TO DIG SITE | WAYLON | GREEN | Laborer | 8 | 4 |  | 1 | Tool Trailer | 12 | HR | 2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 60 |  | 12 | 12 | 839 | [16 empty] | 839 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44112-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-08 | MOBILIIZED TO DIG SITE | JOSE | VALLES | Laborer | 8 | 4 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 628 | 151 | 222 |  | 12 | 12 | 1001 | [16 empty] | 1001 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44112-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-08 | MOBILIIZED TO DIG SITE | LUTHER | LINDLEY | Laborer | 8 | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 628 | 151 | 552 |  | 12 | 12 | 1331 | [16 empty] | 1331 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44112-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-08 | MOBILIIZED TO DIG SITE | MARCELO | GOMEZ | Laborer | 8 | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 12 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 628 | 151 | 1086 |  | 12 | 12 | 1865 | [16 empty] | 1865 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44112-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-08 | MOBILIIZED TO DIG SITE | ANTHONY | MORENO | Laborer | 8 | 4 |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 12 | HR | RAC8545 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 628 | 151 | 342 |  | 12 | 12 | 1121 | [16 empty] | 1121 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44112-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-08 | MOBILIIZED TO DIG SITE | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 4 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 716 | 151 |  |  | 12 |  | 867 | [16 empty] | 867 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1488). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | JODY | BROOM | Superintendent | 4 | 1 |  | 1 | [11 empty] | 93.5 | 126 | 0 | 151 |  |  | 500 | 151 |  |  | 5 |  | 651 | [16 empty] | 651 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1488). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | JAY | MASEY | Quality Assurance Inspector | 5 |  |  | 1 | [11 empty] | 105 | 0 | 0 | 151 |  |  | 525 | 151 |  |  | 5 |  | 676 | [16 empty] | 676 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1488). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | JUANITO | RODRIGUEZ | Safety Person | 4 | 1 |  | 1 | [11 empty] | 74 | 100 | 0 | 151 |  |  | 396 | 151 |  |  | 5 |  | 547 | [16 empty] | 547 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1488). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | KIM | FORNALL | Project Coordinator | 5 | [14 empty] | 98.8 | 0 | 0 | 151 |  |  | 494 | 0 |  |  | 5 |  | 494 | [16 empty] | 494 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1488). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | MICHAEL | GOSS | Truck Driver/CDL | 4 | 1 |  |  | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 286 | 0 | 420 |  | 5 | 10 | 706 | [16 empty] | 706 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1488). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | RICHARD | THOMAS | Truck Driver/CDL | 4 | 1 |  |  | Lowboy Trailer | 10 | HR | 2449 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 286 | 0 | 185 |  | 5 | 10 | 471 | [16 empty] | 471 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1485). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | JODY | BROOM | Superintendent | 4 | 1 | [13 empty] | 93.5 | 126 | 0 | 151 |  |  | 500 | 0 |  |  | 5 |  | 500 | [16 empty] | 500 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1485). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | JAY | MASEY | Quality Assurance Inspector | 5 | [14 empty] | 105 | 0 | 0 | 151 |  |  | 525 | 0 |  |  | 5 |  | 525 | [16 empty] | 525 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1485). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | JUANITO | RODRIGUEZ | Safety Person | 4 | 1 | [13 empty] | 74 | 100 | 0 | 151 |  |  | 396 | 0 |  |  | 5 |  | 396 | [16 empty] | 396 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1485). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | KIM | FORNALL | Project Coordinator | 5 |  |  | 1 | [11 empty] | 98.8 | 0 | 0 | 151 |  |  | 494 | 151 |  |  | 5 |  | 645 | [16 empty] | 645 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1485). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | MICHAEL | GOSS | Truck Driver/CDL | 4 | 1 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 286 | 151 | 420 |  | 5 | 10 | 857 | [16 empty] | 857 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | MATCHES DIG SITE FOR CREW 6 FOR HALF THE DAY. SPLIT PER DIEM EQUALLY TO EACH DIG SITE (OTHER SITE IS 1485). THERE WERE TWO SEMI'S AND TWO LOWBOYS, SO SPLIT AND ONLY CHARGE FOR ONE ON EACH SITE. | RICHARD | THOMAS | Truck Driver/CDL | 4 | 1 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 286 | 151 | 185 |  | 5 | 10 | 622 | [16 empty] | 622 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | JONATHAN | HOLLEY | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15334 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | JONATHAN | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15334 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 | 0 | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | RYAN | FARINELLI | Operator II | 8 |  |  | 1 | Tool Trailer | 8 | HR | 2183 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 492 | 151 | 40 |  | 8 | 8 | 683 | [16 empty] | 683 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | RYAN | FARINELLI | Operator II |  | 2 |  |  | Tool Trailer | 2 | HR | 2183 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 166 | 0 | 10 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | GREG | MCMILLIAN | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | [16 empty] | 895 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | GREG | MCMILLIAN | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 0 | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | JEREMAINE | EVANS | Laborer | 8 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 376 | 151 | 724 |  | 8 | 8 | 1251 | [16 empty] | 1251 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | JEREMAINE | EVANS | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 | 0 | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | DEMETRIUS | MCDONALD | Laborer | 8 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 376 | 151 |  |  | 8 |  | 527 | [16 empty] | 527 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | DEMETRIUS | MCDONALD | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | JOSE | ORTIZ | Laborer | 8 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 376 | 151 |  |  | 8 |  | 527 | [16 empty] | 527 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | JOSE | ORTIZ | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | ROBERT | FOSTER | Laborer | 8 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 376 | 151 |  |  | 8 |  | 527 | [16 empty] | 527 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | ROBERT | FOSTER | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | BRIAN | RANDLE | Truck Driver/CDL | 8 |  |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 428 | 151 |  |  | 8 |  | 579 | [16 empty] | 579 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44113-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-09 | DUG DITCH UNTIL WE FOUND ANOMALY THAT WAS 18FT OFF SURVERY'S MARK. BEAT OUT 4CY OF ROCK, NDE CAME AND GOT PRIMARY ASSESSMENT | BRIAN | RANDLE | Truck Driver/CDL |  | 2 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 144 | 0 |  |  | 2 |  | 144 | [16 empty] | 144 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | KYLE | BONNEAU | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15335 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 0 | 52 |  | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | JESSE | BERTHIAUME | Operator II | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF1040 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 246 | 0 | 64 |  | 4 | 4 | 310 | [16 empty] | 310 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | CADEN | THOMPSON | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | 2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 0 | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | JACOB | CAPITANO | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 0 | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | BROC | CALIGER | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 0 | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | CODY | GAXIOLA | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 0 | 362 |  | 4 | 4 | 550 | [16 empty] | 550 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | MATTHEW | SCHMITT | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 | 0 |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 4 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 214 | 0 |  |  | 4 |  | 214 | [16 empty] | 214 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | KYLE | BONNEAU | Foreman | 4 | 3 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15335 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 596 | 151 | 78 |  | 7 | 6 | 825 | [16 empty] | 825 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | JESSE | BERTHIAUME | Operator II | 4 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF1040 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 412 | 151 | 96 |  | 6 | 6 | 659 | [16 empty] | 659 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | CADEN | THOMPSON | Laborer | 4 | 2 |  | 1 | Tool Trailer | 6 | HR | 2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 314 | 151 | 30 |  | 6 | 6 | 495 | [16 empty] | 495 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | JACOB | CAPITANO | Laborer | 4 | 2 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 314 | 151 | 111 |  | 6 | 6 | 576 | [16 empty] | 576 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | BROC | CALIGER | Laborer | 4 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 314 | 151 | 276 |  | 6 | 6 | 741 | [16 empty] | 741 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | CODY | GAXIOLA | Laborer | 4 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 314 | 151 | 543 |  | 6 | 6 | 1008 | [16 empty] | 1008 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | MATTHEW | SCHMITT | Laborer | 4 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 314 | 151 |  |  | 6 |  | 465 | [16 empty] | 465 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-97640-44113-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-09 |  | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 4 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 358 | 151 |  |  | 6 |  | 509 | [16 empty] | 509 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44113-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-09 | MOVE TRACK HOE IN. POT HOLED LINE. INSTALLED GOAL POST | MICHAEL | RATLIFF | Foreman | 8 | 2 |  | 1 | [11 empty] | 74 | 100 | 0 | 151 |  |  | 792 | 151 |  |  | 10 |  | 943 | [16 empty] | 943 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44113-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-09 | MOVE TRACK HOE IN. POT HOLED LINE. INSTALLED GOAL POST | SHAWN | ROSE | Operator II | 8 | 2 |  | 1 | [11 empty] | 61.5 | 83 | 0 | 151 |  |  | 658 | 151 |  |  | 10 |  | 809 | [16 empty] | 809 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44113-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-09 | MOVE TRACK HOE IN. POT HOLED LINE. INSTALLED GOAL POST | MICHAEL | ELLIOTT | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44113-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-09 | MOVE TRACK HOE IN. POT HOLED LINE. INSTALLED GOAL POST | SETH | RATLIFF | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44113-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-09 | MOVE TRACK HOE IN. POT HOLED LINE. INSTALLED GOAL POST | DAVID | RATLIFF | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44113-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-09 | MOVE TRACK HOE IN. POT HOLED LINE. INSTALLED GOAL POST | ERNESTO | TREJO | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44113-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-09 | MOVE TRACK HOE IN. POT HOLED LINE. INSTALLED GOAL POST | CHRISTOPHER | URBAN | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-108090-44113-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-09 | MOVE TRACK HOE IN. POT HOLED LINE. INSTALLED GOAL POST | TYLER | TIGG | Truck Driver/CDL | 8 | 2 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 572 | 151 |  |  | 10 |  | 723 | [16 empty] | 723 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-108090-44113-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-09 | MOVE TRACK HOE IN. POT HOLED LINE. INSTALLED GOAL POST | [23 empty] | 6.28 | [23 empty] | 0 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | WAYNE | SMITH | Foreman | 5 |  |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15336 | Sand | 10 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 22.35 | 370 | 0 | 65 | 223.5 | 5 | 5 | 658.5 | [16 empty] | 658.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | WAYNE | SMITH | Foreman | 3 | 3 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15336 | 2888 Coating | 4 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0.99 | 522 | 151 | 65 | 3.96 | 6 | 5 | 741.96 | [16 empty] | 741.96 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | RICHARD | SHOEMAKE | Operator II | 5 |  |  |  | Tool Trailer | 5 | HR | 2180 | Brushes | 30 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 5 |  | 307.5 | 0 | 25 |  | 5 | 5 | 332.5 | [16 empty] | 332.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | RICHARD | SHOEMAKE | Operator II | 3 | 2 |  | 1 | Tool Trailer | 5 | HR | 2180 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 350.5 | 151 | 25 |  | 5 | 5 | 526.5 | [16 empty] | 526.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | OJ | SEALS | Laborer | 5 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 0 | 230 |  | 5 | 5 | 465 | [16 empty] | 465 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | OJ | SEALS | Laborer | 3 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 | 151 | 230 |  | 5 | 5 | 648 | [16 empty] | 648 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | JAMES | KERVIN | Laborer | 5 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 235 | 0 | 452.5 |  | 5 | 5 | 687.5 | [16 empty] | 687.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | JAMES | KERVIN | Laborer | 3 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 267 | 151 | 452.5 |  | 5 | 5 | 870.5 | [16 empty] | 870.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | RICHARD | ADKINS | Laborer | 5 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 235 | 0 |  |  | 5 |  | 235 | [16 empty] | 235 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | RICHARD | ADKINS | Laborer | 3 | 2 |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | RAC8545 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 267 | 151 | 285 |  | 5 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | NICHOLAS | BLANCO | Laborer | 5 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 235 | 0 |  |  | 5 |  | 235 | [16 empty] | 235 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | NICHOLAS | BLANCO | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | BARRETT | WISE | Laborer | 5 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 235 | 0 |  |  | 5 |  | 235 | [16 empty] | 235 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Recoat | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | BARRETT | WISE | Laborer | 3 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 151 |  |  | 5 |  | 418 | [16 empty] | 418 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | STEVE | CLARK | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 160 |  | 12 | 10 | 1027 | [16 empty] | 1027 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44113-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-09 | JEEPED PIPE AND FOUND 30+ JEEPS. REPAIRED AND JEEPED AGAIN, FOUND MORE JEEPS. INSPECTION TOLD US TO SANDBLAST AND RECOAT WHOLE DIG. STARTED SANDBLASTING. | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | TOME | KIRKLAND | Foreman | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 792 | 151 | 64 |  | 10 | 4 | 1007 | [16 empty] | 1007 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | TOME | KIRKLAND | Foreman |  | 1 | [13 empty] | 74 | 100 | 0 | 151 |  |  | 100 | 0 |  |  | 1 |  | 100 | [16 empty] | 100 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | CALEB | HOLTON | Operator II | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF9120 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 61.5 | 0 | 16 |  | 1 | 1 | 77.5 | [16 empty] | 77.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | CALEB | HOLTON | Operator II | 7 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF9120 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 596.5 | 151 | 160 |  | 9 | 10 | 907.5 | [16 empty] | 907.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | CALEB | HOLTON | Operator II |  | 1 | [13 empty] | 61.5 | 83 | 0 | 151 |  |  | 83 | 0 |  |  | 1 |  | 83 | [16 empty] | 83 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 | 0 | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | MICHAEL | ANISZEWSKI | Laborer | 7 | 2 |  | 1 | Tool Trailer | 10 | HR | 2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 455 | 151 | 50 |  | 9 | 10 | 656 | [16 empty] | 656 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | MICHAEL | ANISZEWSKI | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | BOLDBAATAR | ZORIGT | Laborer | 8 | 2 |  | 1 | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB | [7 empty] | 47 | 63 | 0 | 151 | 24.5 |  | 502 | 151 | 245 |  | 10 | 10 | 898 | [16 empty] | 898 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | BOLDBAATAR | ZORIGT | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | JORDAN | WIGGINS | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 | 0 | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | JORDAN | WIGGINS | Laborer | 7 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 455 | 151 | 905 |  | 9 | 10 | 1511 | [16 empty] | 1511 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | JORDAN | WIGGINS | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | DAVID | KNOTTS | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | DAVID | KNOTTS | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | TANNER | BRITT | Laborer | 1 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 47 | 0 |  |  | 1 |  | 47 | [16 empty] | 47 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | TANNER | BRITT | Laborer | 7 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 455 | 151 |  |  | 9 |  | 606 | [16 empty] | 606 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Initial Coating Inspection | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | TANNER | BRITT | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | ALDO | REYNA | Truck Driver/CDL | 4 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 214 | 0 |  |  | 4 |  | 214 | [16 empty] | 214 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | ALDO | REYNA | Truck Driver/CDL | 4 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 502 | 151 | 128 |  | 8 | 8 | 781 | [16 empty] | 781 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | [7 empty] | 40' Flatbed trailer or equal | 8 | HR | GNT8992 | [11 empty] | 18.5 |  |  |  | 148 |  |  | 8 | 148 | [16 empty] | 148 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 8 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 228 |  |  | 8 | 228 | [16 empty] | 228 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-57880-44113-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-09 | ASSEMBLED TRENCHBOX. COORDINATED WITH ELECTRIC COMPANY TO HOLD POWER POLE WHILE DIGGING NEAR IT. ENTERPRISE REP NOT ON SITE UNTIL 8:30 BECAUSE OF AN ENTERPRISE SAFETY STANDDOWN. BEGAN EXCAVATION AND FOUND ANOMALY 7.2' DOWNSTREAM OF GIRTH WELD. HAND DUG 3' BELOW PIPE FOR NDE AND FUTURE REPAIRS. SET TRENCHBOX. EXCAVATION 100% COMPLETE AND READY FOR COATING REMOVAL SUBCONTRACTOR. INSTALLED SILT FENCE AROUND TOP AND SUB SOIL. INSTALLED SAFETY FENCE AROUND OPEN EXCAVATION. MOBILIZED AIR COMPRESSOR/SANDBLASTER, 1 PALLET ROCKSHIELD, 1 BUNDLE SKIDS. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS3492 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON THIS DIG SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON DIG SITE 1488 | BARKLEY | BROWN | Foreman | 6 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 19115 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 444 | 0 | 80 |  | 6 | 5 | 524 | [16 empty] | 524 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON THIS DIG SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON DIG SITE 1488 | MATTHEW | LINDLEY | Operator II | 5 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 307.5 | 0 | 80 |  | 5 | 5 | 387.5 | [16 empty] | 387.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON THIS DIG SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON DIG SITE 1488 | WAYLON | GREEN | Laborer | 6 |  |  |  | Tool Trailer | 5 | HR | 2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 0 | 25 |  | 6 | 5 | 307 | [16 empty] | 307 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON THIS DIG SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON DIG SITE 1488 | JOSE | VALLES | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON THIS DIG SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON DIG SITE 1488 | LUTHER | LINDLEY | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 184 |  | 5 | 4 | 570 | [16 empty] | 570 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON THIS DIG SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON DIG SITE 1488 | MARCELO | GOMEZ | Laborer | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 235 | 151 | 724 |  | 5 | 8 | 1110 | [16 empty] | 1110 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON THIS DIG SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON DIG SITE 1488 | ANTHONY | MORENO | Laborer | 5 |  |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 8 | HR | RAC8545 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 235 | 151 | 228 |  | 5 | 8 | 614 | [16 empty] | 614 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44113-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON THIS DIG SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON DIG SITE 1488 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 5 |  |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 267.5 | 151 |  |  | 5 |  | 418.5 | [16 empty] | 418.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON THIS DIG SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON DIG SITE 1485. | BARKLEY | BROWN | Foreman | 2 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 19115 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 448 | 151 | 80 |  | 5 | 5 | 679 | [16 empty] | 679 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON THIS DIG SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON DIG SITE 1485. | MATTHEW | LINDLEY | Operator II | 3 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF0380 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 350.5 | 151 | 80 |  | 5 | 5 | 581.5 | [16 empty] | 581.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON THIS DIG SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON DIG SITE 1485. | WAYLON | GREEN | Laborer | 2 | 3 |  | 1 | Tool Trailer | 5 | HR | 2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 283 | 151 | 25 |  | 5 | 5 | 459 | [16 empty] | 459 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON THIS DIG SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON DIG SITE 1485. | LUTHER | LINDLEY | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 | 0 | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON THIS DIG SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON DIG SITE 1485. | MARCELO | GOMEZ | Laborer | 3 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 0 |  |  | 5 |  | 267 | [16 empty] | 267 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-50610-44113-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-09 | SITE PREP. THERE WERE NO SURVEY MARKERS AT DIG SITE. ENTERPRISE REP SHOWED UP EXPECTING US TO BE READY TO DIG BUT BECAUSE THERE WERE NO SURVEY MARKERS WE WERE UNABLE TO DO SO. WAITING ON ENBRIDGE OPERATIONS TO GET SURVERY ON SITE. 3 DAYS OF PER DIEM AND OVERTIME CAPTURED ON THIS DIG SITE. 5 DAYS OF PER DIEM AND NO OVERTIME CAPTURED ON DIG SITE 1485. | ANTHONY | MORENO | Laborer | 3 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 267 | 0 |  |  | 5 |  | 267 | [16 empty] | 267 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | MATCHED DIG SITE FOR CREW 1 | JODY | BROOM | Superintendent |  | 8 |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 93.5 | 126 | 0 | 151 | 42 |  | 1008 | 151 | 420 |  | 8 | 10 | 1579 | [16 empty] | 1579 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | MATCHED DIG SITE FOR CREW 1 | JODY | BROOM | Superintendent |  | 2 | [13 empty] | 93.5 | 126 | 0 | 151 |  |  | 252 | 0 |  |  | 2 |  | 252 | [16 empty] | 252 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | MATCHED DIG SITE FOR CREW 1 | JAY | MASEY | Quality Assurance Inspector | 8 |  |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 105 | 0 | 0 | 151 | 42 |  | 840 | 151 | 420 |  | 8 | 10 | 1411 | [16 empty] | 1411 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | MATCHED DIG SITE FOR CREW 1 | JAY | MASEY | Quality Assurance Inspector | 2 | [14 empty] | 105 | 0 | 0 | 151 |  |  | 210 | 0 |  |  | 2 |  | 210 | [16 empty] | 210 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | MATCHED DIG SITE FOR CREW 1 | KIM | FORNALL | Project Coordinator | 8 |  |  | 1 | Lowboy Trailer | 10 | HR | 2449 | [7 empty] | 98.8 | 0 | 0 | 151 | 18.5 |  | 790.4 | 151 | 185 |  | 8 | 10 | 1126.4 | [16 empty] | 1126.4 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | MATCHED DIG SITE FOR CREW 1 | KIM | FORNALL | Project Coordinator | 2 | [14 empty] | 98.8 | 0 | 0 | 151 |  |  | 197.6 | 0 |  |  | 2 |  | 197.6 | [16 empty] | 197.6 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | MATCHED DIG SITE FOR CREW 1 | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Lowboy Trailer | 10 | HR | 2450 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 720 | 151 | 185 |  | 10 | 10 | 1056 | [16 empty] | 1056 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | MATCHED DIG SITE FOR CREW 1 | RICHARD | THOMAS | Truck Driver/CDL |  | 10 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 720 | 151 |  |  | 10 |  | 871 | [16 empty] | 871 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | BRAND SAFWAY CAME OUT TO START REMOVING COATING. 8FT IN TOTAL REMOVED. RAINY CONDITIONS, HAD EXCAVATOR CLEAN BELL HOLE TO REDUCE SLICKNESS OF GROUND. | JONATHAN | HOLLEY | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15334 |  |  |  | BRAND SAFWAY | ASBESTOS ABATEMENT |  |  | 74 | 100 | 0 | 151 | 13 |  | 600 | 151 | 52 |  | 6 | 4 | 803 | [16 empty] | 803 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | BRAND SAFWAY CAME OUT TO START REMOVING COATING. 8FT IN TOTAL REMOVED. RAINY CONDITIONS, HAD EXCAVATOR CLEAN BELL HOLE TO REDUCE SLICKNESS OF GROUND. | RYAN | FARINELLI | Operator II |  | 4 |  | 1 | Tool Trailer | 4 | HR | 2183 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 332 | 151 | 20 |  | 4 | 4 | 503 | [16 empty] | 503 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | BRAND SAFWAY CAME OUT TO START REMOVING COATING. 8FT IN TOTAL REMOVED. RAINY CONDITIONS, HAD EXCAVATOR CLEAN BELL HOLE TO REDUCE SLICKNESS OF GROUND. | GREG | MCMILLIAN | Laborer |  | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 252 | 151 | 64 |  | 4 | 4 | 467 | [16 empty] | 467 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | BRAND SAFWAY CAME OUT TO START REMOVING COATING. 8FT IN TOTAL REMOVED. RAINY CONDITIONS, HAD EXCAVATOR CLEAN BELL HOLE TO REDUCE SLICKNESS OF GROUND. | JEREMAINE | EVANS | Laborer |  | 4 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | [8 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 | 151 | 74 |  | 4 | 4 | 477 | [16 empty] | 477 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | BRAND SAFWAY CAME OUT TO START REMOVING COATING. 8FT IN TOTAL REMOVED. RAINY CONDITIONS, HAD EXCAVATOR CLEAN BELL HOLE TO REDUCE SLICKNESS OF GROUND. | DEMETRIUS | MCDONALD | Laborer |  | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 | 151 | 184 |  | 4 | 4 | 587 | [16 empty] | 587 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | BRAND SAFWAY CAME OUT TO START REMOVING COATING. 8FT IN TOTAL REMOVED. RAINY CONDITIONS, HAD EXCAVATOR CLEAN BELL HOLE TO REDUCE SLICKNESS OF GROUND. | JOSE | ORITZ | Laborer |  | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 | 151 | 362 |  | 4 | 4 | 765 | [16 empty] | 765 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | BRAND SAFWAY CAME OUT TO START REMOVING COATING. 8FT IN TOTAL REMOVED. RAINY CONDITIONS, HAD EXCAVATOR CLEAN BELL HOLE TO REDUCE SLICKNESS OF GROUND. | ROBERT | FOSTER | Laborer |  | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 252 | 151 |  |  | 4 |  | 403 | [16 empty] | 403 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44114-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-10 | BRAND SAFWAY CAME OUT TO START REMOVING COATING. 8FT IN TOTAL REMOVED. RAINY CONDITIONS, HAD EXCAVATOR CLEAN BELL HOLE TO REDUCE SLICKNESS OF GROUND. | BRIAN | RANDLE | Truck Driver/CDL |  | 4 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 288 | 151 |  |  | 4 |  | 439 | [16 empty] | 439 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | KYLE | BONNEAU | Foreman |  | 7 |  | 1 | Pickup-F150 or F250 or equal |  | HR | [8 empty] | 74 | 100 | 0 | 151 | 13 |  | 700 | 151 | 0 |  | 7 | 0 | 851 | [16 empty] | 851 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | KYLE | BONNEAU | Foreman |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) |  | HR | [8 empty] | 74 | 100 | 0 | 151 | 16 |  | 400 | 0 | 0 |  | 4 | 0 | 400 | [16 empty] | 400 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | JESSE | BERTHIAUME | Operator II |  | 7 |  | 1 | Tool Trailer |  | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 581 | 151 | 0 |  | 7 | 0 | 732 | [16 empty] | 732 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | JESSE | BERTHIAUME | Operator II |  | 3 |  |  | 40' Flatbed trailer or equal |  | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 249 | 0 | 0 |  | 3 | 0 | 249 | [16 empty] | 249 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | CADEN | THOMPSON | Laborer |  | 7 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 46 |  | 441 | 151 | 0 |  | 7 | 0 | 592 | [16 empty] | 592 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | CADEN | THOMPSON | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 | 0 | 0 |  | 3 | 0 | 189 | [16 empty] | 189 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | JACOB | CAPITANO | Laborer |  | 7 |  | 1 | Brush Hog |  | HR | [8 empty] | 47 | 63 | 0 | 151 |  |  | 441 | 151 |  |  | 7 | 0 | 592 | [16 empty] | 592 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | JACOB | CAPITANO | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 | 0 |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | BROC | CALIGER | Laborer |  | 7 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 441 | 151 |  |  | 7 |  | 592 | [16 empty] | 592 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | BROC | CALIGER | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 | 0 |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | CODY | GAXIOLA | Laborer |  | 7 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 441 | 151 |  |  | 7 |  | 592 | [16 empty] | 592 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | CODY | GAXIOLA | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 | 0 |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | MATTHEW | SCHMITT | Laborer |  | 10 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 630 | 151 |  |  | 10 |  | 781 | [16 empty] | 781 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 7 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 504 | 151 |  |  | 7 |  | 655 | [16 empty] | 655 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 3 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 216 | 0 |  |  | 3 |  | 216 | [16 empty] | 216 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-97640-44114-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-10 | EXCAVATOR TOOK MATS; BUILT (2) TEMPORARY BRIDGES, TRACKED BACK INTO ANOMALY, UP AND DOWN STEEP INCLINES. LABORERS M SCOPED AND POTHOLED FOR TOPSOIL, EXCAVATOR TOPSOILED FOR THE DIG. BEGAN DIG (IN CREEK), EXPOSED PIPE. PIPE IS IN SOLID ROCK, WILL NEED TO HAMMER MONDAY. EXPOSED ABOUT 12' OF PIPE, INSTALLED ECD'S PUT UP SAFETY FENCE. | ZACHARY | POWDERS | Laborer |  | 10 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 630 | 151 |  |  | 10 |  | 781 | [16 empty] | 781 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-108090-44114-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-10 | RAIN OUT | MICHAEL | RATLIFF | Foreman |  | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 19111 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 600 | 151 | 96 |  | 6 | 6 | 847 | [16 empty] | 847 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-108090-44114-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-10 | RAIN OUT | SHAWN | ROSE | Operator II |  | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1996 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 332 | 151 | 64 |  | 4 | 4 | 547 | [16 empty] | 547 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-108090-44114-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-10 | RAIN OUT | MICHAEL | ELLIOTT | Laborer |  | 4 |  | 1 | Tool Trailer | 4 | HR | 2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 | 151 | 20 |  | 4 | 4 | 423 | [16 empty] | 423 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-108090-44114-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-10 | RAIN OUT | SETH | RATLIFF | Laborer |  | 4 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 | 151 | 74 |  | 4 | 4 | 477 | [16 empty] | 477 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-108090-44114-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-10 | RAIN OUT | DAVID | RATLIFF | Laborer |  | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 | 151 | 184 |  | 4 | 4 | 587 | [16 empty] | 587 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-108090-44114-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-10 | RAIN OUT | TYLER | BIGG | Truck Driver/CDL |  | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 288 | 151 | 362 |  | 4 | 4 | 801 | [16 empty] | 801 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | GERALD | SMITH | Foreman |  | 4 |  | 1 | Tool Trailer |  | HR | [8 empty] | 74 | 100 | 0 | 151 | 5 |  | 400 | 151 | 0 |  | 4 | 0 | 551 | [16 empty] | 551 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | GERALD | SMITH | Foreman |  | 4 |  |  | Tool Trailer |  | HR | [8 empty] | 74 | 100 | 0 | 151 | 5 |  | 400 | 0 | 0 |  | 4 | 0 | 400 | [16 empty] | 400 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | RICHARD | SHOEMAKE | Operator II |  | 2 |  | 1 | 40' Flatbed trailer or equal |  | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 166 | 151 | 0 |  | 2 | 0 | 317 | [16 empty] | 317 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | RICHARD | SHOEMAKE | Operator II |  | 2 |  |  | 40' Flatbed trailer or equal |  | HR | [8 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 166 | 0 | 0 |  | 2 | 0 | 166 | [16 empty] | 166 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | OJ | SEALS | Laborer |  | 2 |  | 1 | Pickup-F150 or F250 or equal |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 | 151 | 0 |  | 2 | 0 | 277 | [16 empty] | 277 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | OJ | SEALS | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 | 0 | 0 |  | 2 | 0 | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | OJ | SEALS | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 | 0 | 0 |  | 2 | 0 | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | JAMES | KERVIN | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 0 | 0 |  | 2 | 0 | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | JAMES | KERVIN | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 0 |  | 2 | 0 | 277 | [16 empty] | 277 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | RICHARD | ADKINS | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 | 0 | 0 |  | 2 | 0 | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | RICHARD | ADKINS | Laborer |  | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 | 151 | 0 |  | 2 | 0 | 277 | [16 empty] | 277 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | NICHOLAS | BLANCO | Laborer |  | 2 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 126 | 0 | 0 |  | 2 | 0 | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | NICHOLAS | BLANCO | Laborer |  | 2 |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** |  | HR | [8 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 126 | 151 | 0 |  | 2 | 0 | 277 | [16 empty] | 277 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | BARRETT | WISE | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | BARRETT | WISE | Laborer |  | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 151 |  |  | 2 |  | 277 | [16 empty] | 277 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | STEVE | CLARK | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) |  | HR | [8 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 0 | 0 |  | 2 | 0 | 144 | [16 empty] | 144 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Weather | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | STEVE | CLARK | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) |  | HR | [8 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 0 | 0 |  | 2 | 0 | 144 | [16 empty] | 144 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-3990-44114-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-10 | DID JHS AND COMPETENT PERSON REPORT TO GET IN DIG. GOT SET UP TO SANDBLAST AND IT STARTED TO RAIN. WAITED UNTIL IT WAS CALLED A RAIN OUT. | STEVE | CLARK | Truck Driver/CDL |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) |  | HR | [8 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 151 | 0 |  | 2 | 0 | 295 | [16 empty] | 295 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-650-44114-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-10 | MOB'D TO DIG SITE. WAS INSTRUCTED PER INSPECTOR TO CALL LOWBOY OUT OF INDIANA TO DIG-0923 TO MOVE TRACKHOE TO DIG-1465 BEFORE ANYONE HAD SEEN SITE. CALLED THE LOWBOY OFF AT 1PM DUE TO NOT BEING ABLE TO GET HOE MOB'D ON TO DIG SITE. LOWBOY PREPARED TO HAUL TO DIG-1465 MONDAY. POT-HOLED 24" ENBRIDGE LINE IN 3 SPOTS | TOME | KIRKLAND | Foreman |  | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 1998 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 400 | 151 | 96 |  | 4 | 6 | 647 | [16 empty] | 647 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1465 - MC.400216.032 - 629.925 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-650-44114-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-10 | MOB'D TO DIG SITE. WAS INSTRUCTED PER INSPECTOR TO CALL LOWBOY OUT OF INDIANA TO DIG-0923 TO MOVE TRACKHOE TO DIG-1465 BEFORE ANYONE HAD SEEN SITE. CALLED THE LOWBOY OFF AT 1PM DUE TO NOT BEING ABLE TO GET HOE MOB'D ON TO DIG SITE. LOWBOY PREPARED TO HAUL TO DIG-1465 MONDAY. POT-HOLED 24" ENBRIDGE LINE IN 3 SPOTS | TOME | KIRKLAND | Foreman |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 200 | 0 | 32 |  | 2 | 2 | 232 | [16 empty] | 232 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1465 - MC.400216.032 - 629.925 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-650-44114-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-10 | MOB'D TO DIG SITE. WAS INSTRUCTED PER INSPECTOR TO CALL LOWBOY OUT OF INDIANA TO DIG-0923 TO MOVE TRACKHOE TO DIG-1465 BEFORE ANYONE HAD SEEN SITE. CALLED THE LOWBOY OFF AT 1PM DUE TO NOT BEING ABLE TO GET HOE MOB'D ON TO DIG SITE. LOWBOY PREPARED TO HAUL TO DIG-1465 MONDAY. POT-HOLED 24" ENBRIDGE LINE IN 3 SPOTS | TOME | KIRKLAND | Foreman |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 74 | 100 | 0 | 151 | 16 |  | 200 | 0 | 32 |  | 2 | 2 | 232 | [16 empty] | 232 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-650-44114-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-10 | MOB'D TO DIG SITE. WAS INSTRUCTED PER INSPECTOR TO CALL LOWBOY OUT OF INDIANA TO DIG-0923 TO MOVE TRACKHOE TO DIG-1465 BEFORE ANYONE HAD SEEN SITE. CALLED THE LOWBOY OFF AT 1PM DUE TO NOT BEING ABLE TO GET HOE MOB'D ON TO DIG SITE. LOWBOY PREPARED TO HAUL TO DIG-1465 MONDAY. POT-HOLED 24" ENBRIDGE LINE IN 3 SPOTS | TANNER | BRITT | Laborer |  | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 252 | 151 |  |  | 4 |  | 403 | [16 empty] | 403 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1465 - MC.400216.032 - 629.925 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-650-44114-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-10 | MOB'D TO DIG SITE. WAS INSTRUCTED PER INSPECTOR TO CALL LOWBOY OUT OF INDIANA TO DIG-0923 TO MOVE TRACKHOE TO DIG-1465 BEFORE ANYONE HAD SEEN SITE. CALLED THE LOWBOY OFF AT 1PM DUE TO NOT BEING ABLE TO GET HOE MOB'D ON TO DIG SITE. LOWBOY PREPARED TO HAUL TO DIG-1465 MONDAY. POT-HOLED 24" ENBRIDGE LINE IN 3 SPOTS | TANNER | BRITT | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1465 - MC.400216.032 - 629.925 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-650-44114-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-10 | MOB'D TO DIG SITE. WAS INSTRUCTED PER INSPECTOR TO CALL LOWBOY OUT OF INDIANA TO DIG-0923 TO MOVE TRACKHOE TO DIG-1465 BEFORE ANYONE HAD SEEN SITE. CALLED THE LOWBOY OFF AT 1PM DUE TO NOT BEING ABLE TO GET HOE MOB'D ON TO DIG SITE. LOWBOY PREPARED TO HAUL TO DIG-1465 MONDAY. POT-HOLED 24" ENBRIDGE LINE IN 3 SPOTS | TANNER | BRITT | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Mobilization | 3500028468-650-44114-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-10 | MOB'D TO DIG SITE. WAS INSTRUCTED PER INSPECTOR TO CALL LOWBOY OUT OF INDIANA TO DIG-0923 TO MOVE TRACKHOE TO DIG-1465 BEFORE ANYONE HAD SEEN SITE. CALLED THE LOWBOY OFF AT 1PM DUE TO NOT BEING ABLE TO GET HOE MOB'D ON TO DIG SITE. LOWBOY PREPARED TO HAUL TO DIG-1465 MONDAY. POT-HOLED 24" ENBRIDGE LINE IN 3 SPOTS | ALDO | REYNA | Truck Driver/CDL |  | 6 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 432 | 151 |  |  | 6 |  | 583 | [16 empty] | 583 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1465 - MC.400216.032 - 629.925 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-650-44114-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-10 | MOB'D TO DIG SITE. WAS INSTRUCTED PER INSPECTOR TO CALL LOWBOY OUT OF INDIANA TO DIG-0923 TO MOVE TRACKHOE TO DIG-1465 BEFORE ANYONE HAD SEEN SITE. CALLED THE LOWBOY OFF AT 1PM DUE TO NOT BEING ABLE TO GET HOE MOB'D ON TO DIG SITE. LOWBOY PREPARED TO HAUL TO DIG-1465 MONDAY. POT-HOLED 24" ENBRIDGE LINE IN 3 SPOTS | ALDO | REYNA | Truck Driver/CDL |  | 2 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 144 | 0 |  |  | 2 |  | 144 | [16 empty] | 144 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1465 - MC.400216.032 - 629.925 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-650-44114-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-10 | MOB'D TO DIG SITE. WAS INSTRUCTED PER INSPECTOR TO CALL LOWBOY OUT OF INDIANA TO DIG-0923 TO MOVE TRACKHOE TO DIG-1465 BEFORE ANYONE HAD SEEN SITE. CALLED THE LOWBOY OFF AT 1PM DUE TO NOT BEING ABLE TO GET HOE MOB'D ON TO DIG SITE. LOWBOY PREPARED TO HAUL TO DIG-1465 MONDAY. POT-HOLED 24" ENBRIDGE LINE IN 3 SPOTS | ALDO | REYNA | Truck Driver/CDL |  | 2 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 144 | 0 |  |  | 2 |  | 144 | [16 empty] | 144 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44114-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-10 | BRAND SAFWAY STARTED COATING REMOVAL AT 8AM AND FINISHED AT 1PM. CREW BEGAN SANDBLASTING AREA MARKED OUT BY THE NDE TECHS. FINISHED BLASTING AT 3:30PM. USED 13 BAGS OF SAND. NDE TECHS TOOK (2) HOURS TO ASSESS THE ANOMALY. | TOME | KIRKLAND | Foreman |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19120 | Sand | 13 | Bag | BRAND SAFWAY | COATING REMOVAL |  |  | 74 | 100 | 0 | 151 | 16 | 6.28 | 200 | 0 | 160 | 81.64 | 2 | 10 | 441.64 | [16 empty] | 441.64 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44114-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-10 | BRAND SAFWAY STARTED COATING REMOVAL AT 8AM AND FINISHED AT 1PM. CREW BEGAN SANDBLASTING AREA MARKED OUT BY THE NDE TECHS. FINISHED BLASTING AT 3:30PM. USED 13 BAGS OF SAND. NDE TECHS TOOK (2) HOURS TO ASSESS THE ANOMALY. | CALEB | HORTON | Operator II |  | 10 |  | 1 | Tool Trailer | 10 | HR | 2182 | [7 empty] | 61.5 | 83 | 0 | 151 | 5 |  | 830 | 151 | 50 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44114-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-10 | BRAND SAFWAY STARTED COATING REMOVAL AT 8AM AND FINISHED AT 1PM. CREW BEGAN SANDBLASTING AREA MARKED OUT BY THE NDE TECHS. FINISHED BLASTING AT 3:30PM. USED 13 BAGS OF SAND. NDE TECHS TOOK (2) HOURS TO ASSESS THE ANOMALY. | MICHAEL | ANISZEWSKI | Laborer |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 630 | 151 | 32 |  | 10 | 2 | 813 | [16 empty] | 813 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44114-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-10 | BRAND SAFWAY STARTED COATING REMOVAL AT 8AM AND FINISHED AT 1PM. CREW BEGAN SANDBLASTING AREA MARKED OUT BY THE NDE TECHS. FINISHED BLASTING AT 3:30PM. USED 13 BAGS OF SAND. NDE TECHS TOOK (2) HOURS TO ASSESS THE ANOMALY. | BOLDBAATAR | ZORIGT | Laborer |  | 10 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT8992 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 630 | 151 | 185 |  | 10 | 10 | 966 | [16 empty] | 966 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44114-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-10 | BRAND SAFWAY STARTED COATING REMOVAL AT 8AM AND FINISHED AT 1PM. CREW BEGAN SANDBLASTING AREA MARKED OUT BY THE NDE TECHS. FINISHED BLASTING AT 3:30PM. USED 13 BAGS OF SAND. NDE TECHS TOOK (2) HOURS TO ASSESS THE ANOMALY. | JORDAN | WIGGINS | Laborer |  | 10 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS3492 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 630 | 151 | 460 |  | 10 | 10 | 1241 | [16 empty] | 1241 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44114-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-10 | BRAND SAFWAY STARTED COATING REMOVAL AT 8AM AND FINISHED AT 1PM. CREW BEGAN SANDBLASTING AREA MARKED OUT BY THE NDE TECHS. FINISHED BLASTING AT 3:30PM. USED 13 BAGS OF SAND. NDE TECHS TOOK (2) HOURS TO ASSESS THE ANOMALY. | DAVID | KNOTTS | Laborer |  | 10 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 630 | 151 | 905 |  | 10 | 10 | 1686 | [16 empty] | 1686 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44114-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-10 | BRAND SAFWAY STARTED COATING REMOVAL AT 8AM AND FINISHED AT 1PM. CREW BEGAN SANDBLASTING AREA MARKED OUT BY THE NDE TECHS. FINISHED BLASTING AT 3:30PM. USED 13 BAGS OF SAND. NDE TECHS TOOK (2) HOURS TO ASSESS THE ANOMALY. | TANNER | BRITT | Laborer |  | 2 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 126 | 0 | 285 |  | 2 | 10 | 411 | [16 empty] | 411 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-0923 - MC.400216.085 - 474.889 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-57880-44114-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-10 | BRAND SAFWAY STARTED COATING REMOVAL AT 8AM AND FINISHED AT 1PM. CREW BEGAN SANDBLASTING AREA MARKED OUT BY THE NDE TECHS. FINISHED BLASTING AT 3:30PM. USED 13 BAGS OF SAND. NDE TECHS TOOK (2) HOURS TO ASSESS THE ANOMALY. | ALDO | REYNA | Truck Driver/CDL |  | 2 |  |  | Hammer Attachment | 10 | HR | RHA6A06 | [7 empty] | 53.5 | 72 | 0 | 151 |  |  | 144 | 0 |  |  | 2 | 10 | 144 | [16 empty] | 144 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 10 | HR | RF0380 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 | 0 | 130 |  | 2 | 10 | 330 | [16 empty] | 330 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | BARKLEY | BROWN | Foreman |  | 2 | [13 empty] | 74 | 100 | 0 | 151 |  |  | 200 | 0 |  |  | 2 |  | 200 | [16 empty] | 200 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | BARKLEY | BROWN | Foreman |  | 5 |  | 1 | [11 empty] | 74 | 100 | 0 | 151 |  |  | 500 | 151 |  |  | 5 |  | 651 | [16 empty] | 651 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | BARKLEY | BROWN | Foreman |  | 1 | [6 empty] | Mats | 6 | Ea |  |  |  |  | 74 | 100 | 0 | 151 |  | 325 | 100 | 0 |  | 1950 | 1 |  | 2050 | [16 empty] | 2050 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | MATTHEW | LINDLEY | Operator II |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RT9829 | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 166 | 0 | 160 |  | 2 | 10 | 326 | [16 empty] | 326 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | MATTHEW | LINDLEY | Operator II |  | 2 | [13 empty] | 61.5 | 83 | 0 | 151 |  |  | 166 | 0 |  |  | 2 |  | 166 | [16 empty] | 166 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | MATTHEW | LINDLEY | Operator II |  | 5 |  | 1 | [11 empty] | 61.5 | 83 | 0 | 151 |  |  | 415 | 151 |  |  | 5 |  | 566 | [16 empty] | 566 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | MATTHEW | LINDLEY | Operator II |  | 1 | [13 empty] | 61.5 | 83 | 0 | 151 |  |  | 83 | 0 |  |  | 1 |  | 83 | [16 empty] | 83 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | WAYLON | GREEN | Laborer |  | 2 |  |  | Tool Trailer | 10 | HR | 2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 0 | 50 |  | 2 | 10 | 176 | [16 empty] | 176 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | WAYLON | GREEN | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | WAYLON | GREEN | Laborer |  | 5 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 315 | 151 |  |  | 5 |  | 466 | [16 empty] | 466 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | WAYLON | GREEN | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | JOSE | VALLES | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 0 | 185 |  | 2 | 10 | 311 | [16 empty] | 311 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | JOSE | VALLES | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | JOSE | VALLES | Laborer |  | 5 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 315 | 151 |  |  | 5 |  | 466 | [16 empty] | 466 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | JOSE | VALLES | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | LUTHER | LINDLEY | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 0 | 230 |  | 2 | 5 | 356 | [16 empty] | 356 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | LUTHER | LINDLEY | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 0 | 230 |  | 2 | 5 | 356 | [16 empty] | 356 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | LUTHER | LINDLEY | Laborer |  | 5 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 315 | 151 |  |  | 5 |  | 466 | [16 empty] | 466 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | LUTHER | LINDLEY | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 | 0 | 452.5 |  | 2 | 5 | 578.5 | [16 empty] | 578.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | MARCELO | GOMEZ | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | MARCELO | GOMEZ | Laborer |  | 5 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 | 151 | 452.5 |  | 5 | 5 | 918.5 | [16 empty] | 918.5 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | MARCELO | GOMEZ | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | ANTHONY | MORENO | Laborer |  | 2 |  |  | Brush Hog | 5 | HR | R2986 | [7 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 | 5 | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | ANTHONY | MORENO | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 | 0 |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | ANTHONY | MORENO | Laborer |  | 5 |  | 1 | Brush Hog | 5 | HR | R2986 | [7 empty] | 47 | 63 | 0 | 151 |  |  | 315 | 151 |  |  | 5 | 5 | 466 | [16 empty] | 466 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | ANTHONY | MORENO | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 | 0 |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Access | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 144 | 0 |  |  | 2 |  | 144 | [16 empty] | 144 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Site Prep | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 144 | 0 |  |  | 2 |  | 144 | [16 empty] | 144 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Excavation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 5 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 360 | 151 |  |  | 5 |  | 511 | [16 empty] | 511 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 1 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 72 | 0 |  |  | 1 |  | 72 | [16 empty] | 72 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Equipment | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1485 - MC.400216.032 - 661.199 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-21 | 2 | BL |  | Stand-by - Equipment | 3500028468-43000-44114-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-10 | BRUSHHOGGED DIG SITE, INSTALLED MATS, MARKED DIG SITE, POTHOLED EXPOSED PIPE. INSTALLED SAFETY FENCE, SILT FENCE, AND COVERED SPOIL AND TOP SOIL. | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [18 empty] | 4 | [17 empty] | 0 | ABC 3500028468-01 | ABC 3500028468-01
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | JODY | BROOM | Superintendent | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15161 | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 561 | 151 | 78 |  | 6 | 6 | 790 | [16 empty] | 790 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | JODY | BROOM | Superintendent | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15161 | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 439 |  | 52 |  | 4 | 4 | 491 | [16 empty] | 491 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | JAY | MASEY | Quality Assurance Inspector | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JODY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 630 | 151 | 78 |  | 6 | 6 | 859 | [16 empty] | 859 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | JAY | MASEY | Quality Assurance Inspector | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | JODY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 420 |  | 52 |  | 4 | 4 | 472 | [16 empty] | 472 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | KIM | FORNALL | Project Coordinator | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JAY | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 592.8 | 151 | 78 |  | 6 | 6 | 821.8 | [16 empty] | 821.8 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | KIM | FORNALL | Project Coordinator | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | JAY | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 395.2 |  | 52 |  | 4 | 4 | 447.2 | [16 empty] | 447.2 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | RICHARD | THOMAS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | TOME | KIRKLAND | Superintendent | 6 |  |  |  | Pickup-F150 or F250 or equal | 6 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 561 |  | 78 |  | 6 | 6 | 639 | [16 empty] | 639 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | TOME | KIRKLAND | Superintendent | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 439 |  | 52 |  | 4 | 4 | 491 | [16 empty] | 491 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | MICHAEL | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | RICHARD | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 6 | HR | 0 | [11 empty] | 24.5 |  |  |  | 147 |  |  | 6 | 147 | [16 empty] | 147 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | 0 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 6 | HR | 0 | [11 empty] | 24.5 |  |  |  | 147 |  |  | 6 | 147 | [16 empty] | 147 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | MATCHES CREW 1 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | 0 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | JONATHAN | HOLLEY | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | Sand | 10 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | JONATHAN | HOLLEY | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 444 | 151 | 78 |  | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | JONATHAN | HOLLEY | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | RYAN | FARINELLI | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | RYAN | FARINELLI | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 369 | 151 | 78 |  | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | RYAN | FARINELLI | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | GREG | MCMILLIAN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | GREG | MCMILLIAN | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | GREG | MCMILLIAN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | JEREMAINE | EVANS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | JEREMAINE | EVANS | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | JEREMAINE | EVANS | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | DEMETRIUS | MCDONALD | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | DEMETRIUS | MCDONALD | Laborer | 6 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 282 | 151 | 276 |  | 6 | 6 | 709 | [16 empty] | 709 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | DEMETRIUS | MCDONALD | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | JOSE | ORTIZ | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | JOSE | ORTIZ | Laborer | 6 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 282 | 151 | 543 |  | 6 | 6 | 976 | [16 empty] | 976 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | JOSE | ORTIZ | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | ROBERT | FOSTER | Laborer | 2 |  |  |  | Hammer Attachment | 2 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 94 |  | 0 |  | 2 | 2 | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | ROBERT | FOSTER | Laborer | 6 |  |  | 1 | Hammer Attachment | 6 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 282 | 151 | 0 |  | 6 | 6 | 433 | [16 empty] | 433 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | ROBERT | FOSTER | Laborer |  | 4 |  |  | Hammer Attachment | 4 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 252 |  | 0 |  | 4 | 4 | 252 | [16 empty] | 252 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | BRIAN | RANDLE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R42809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | BRIAN | RANDLE | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | R42809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | [16 empty] | 568 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | BRIAN | RANDLE | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R42809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-86930-44116-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-12 | Sand blasted 8ft of the dig 1560, NDE assessed the dent and waiting on further information. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP922 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 502 | 151 | 905 |  | 10 | 10 | 1558 | [16 empty] | 1558 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [16 empty] | 460 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | [7 empty] | Hammer Attachment | 10 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | [7 empty] | Brush Hog | 10 | HR | RBH | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44116-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-12 | Started with JSA. Ditch was full of water, pumped it with 2' pump, didn't have hoses for 3". Began excavation, dug 25' because the weld that was marked was not where stakes were. NDE showed up and gave footage, got hammer attachment to the bottom of the hill, attached to hoe to be ready to hammer 1st thing in the morning. | [7 empty] | Water Pump ( up to 2") | 10 | HR | 2INP | [11 empty] | 6 |  |  |  | 60 |  |  | 10 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | MICHAEL | RATLIFF | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | MICHAEL | T-Posts | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | MICHAEL | RATLIFF | Foreman | 5 | 2 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | MICHAEL | Safety Fence | 140 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 570 | 151 | 91 | 0 | 7 | 7 | 812 | [16 empty] | 812 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | SHAWN | ROSE | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWN | Silt Fence | 120 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 184.5 |  | 39 | 0 | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | SHAWN | ROSE | Operator II | 5 | 2 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 473.5 | 151 | 91 |  | 7 | 7 | 715.5 | [16 empty] | 715.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | MICHAEL | ELLIOTT | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 19111 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 |  | 48 |  | 3 | 3 | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | MICHAEL | ELLIOTT | Laborer | 5 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | 19111 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 361 | 151 | 112 |  | 7 | 7 | 624 | [16 empty] | 624 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | SETH | RATLIFF | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 |  | 48 |  | 3 | 3 | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | SETH | RATLIFF | Laborer | 5 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 361 | 151 | 112 |  | 7 | 7 | 624 | [16 empty] | 624 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | DAVID | RATLIFF | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | DAVID | RATLIFF | Laborer | 5 | 2 |  | 1 | Tool Trailer | 7 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 361 | 151 | 35 |  | 7 | 7 | 547 | [16 empty] | 547 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | TYLER | BIGG | Truck Driver/CDL | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 160.5 |  | 55.5 |  | 3 | 3 | 216 | [16 empty] | 216 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | TYLER | BIGG | Truck Driver/CDL | 5 | 2 |  | 1 | 40' Flatbed trailer or equal | 7 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 411.5 | 151 | 129.5 |  | 7 | 7 | 692 | [16 empty] | 692 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 322 |  |  | 7 | 322 | [16 empty] | 322 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44116-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-12 | SET UP SITE. PUT UP FENCE. EXPOSED 20' PIPE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 633.5 |  |  | 7 | 633.5 | [16 empty] | 633.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | WAYNE | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | WAYNE | Sand | 60 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | WAYNE | SMITH | Foreman | 7 | 5 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | WAYNE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1018 | 151 | 156 |  | 12 | 12 | 1325 | [16 empty] | 1325 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | RICHARD | SHOEMAKE | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 824 | 151 | 156 |  | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | OJ | SEALS | Laborer | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 628 | 151 | 130 |  | 12 | 10 | 909 | [16 empty] | 909 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | JAMES | KERVIN | Laborer | 8 | 4 |  | 1 | Tool Trailer | 10 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 50 |  | 12 | 10 | 829 | [16 empty] | 829 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | RICHARD | ADKINS | Laborer | 8 | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 628 | 151 | 460 |  | 12 | 10 | 1239 | [16 empty] | 1239 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | NICHOLAS | BLANCO | Laborer | 8 | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 628 | 151 | 905 |  | 12 | 10 | 1684 | [16 empty] | 1684 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | BARRETT | WISE | Laborer | 8 | 4 |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | RAC8545 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 628 | 151 | 285 |  | 12 | 10 | 1064 | [16 empty] | 1064 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44116-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-12 | SANDBLASTED PIPE TO ROCOAL. DIDN'T FINISH BLASTING | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 10 | HR | 0 | [11 empty] | 23.5 |  |  |  | 235 |  |  | 10 | 235 | [16 empty] | 235 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-57880-44116-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-12 | CREW DEMOB'D FROM DIG WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY DEMOB'D WITH TRACK HOE. TRUCK DRIVER AND ONE LABOR CAME BACK TO DEMOB MATERIAL. ONE COMPETENT PERSON CAME BACK FOR NDE CREW TO ENTER EXCAVATION FIRST THING 10/13. NDE CREW WAS AWARE ON SATURDAY THAT THEY WOULD HAVE TO GO BACK IN THE EXCAVATION MONDAY BUT DIDN'T COMMUNICATE THAT WITH ANYONE UNTIL THIS MORNING AT 9AM, WHEN CREW WAS ALREADY DEMOB'ING. | CALEB | HOLTON | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-57880-44116-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-12 | CREW DEMOB'D FROM DIG WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY DEMOB'D WITH TRACK HOE. TRUCK DRIVER AND ONE LABOR CAME BACK TO DEMOB MATERIAL. ONE COMPETENT PERSON CAME BACK FOR NDE CREW TO ENTER EXCAVATION FIRST THING 10/13. NDE CREW WAS AWARE ON SATURDAY THAT THEY WOULD HAVE TO GO BACK IN THE EXCAVATION MONDAY BUT DIDN'T COMMUNICATE THAT WITH ANYONE UNTIL THIS MORNING AT 9AM, WHEN CREW WAS ALREADY DEMOB'ING. | MICHAEL | ANISZEWSKI | Laborer | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 | 151 | 64 |  | 4 | 4 | 403 | [16 empty] | 403 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-57880-44116-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-12 | CREW DEMOB'D FROM DIG WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY DEMOB'D WITH TRACK HOE. TRUCK DRIVER AND ONE LABOR CAME BACK TO DEMOB MATERIAL. ONE COMPETENT PERSON CAME BACK FOR NDE CREW TO ENTER EXCAVATION FIRST THING 10/13. NDE CREW WAS AWARE ON SATURDAY THAT THEY WOULD HAVE TO GO BACK IN THE EXCAVATION MONDAY BUT DIDN'T COMMUNICATE THAT WITH ANYONE UNTIL THIS MORNING AT 9AM, WHEN CREW WAS ALREADY DEMOB'ING. | BOLDBAATAR | ZORIGT | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-57880-44116-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-12 | CREW DEMOB'D FROM DIG WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY DEMOB'D WITH TRACK HOE. TRUCK DRIVER AND ONE LABOR CAME BACK TO DEMOB MATERIAL. ONE COMPETENT PERSON CAME BACK FOR NDE CREW TO ENTER EXCAVATION FIRST THING 10/13. NDE CREW WAS AWARE ON SATURDAY THAT THEY WOULD HAVE TO GO BACK IN THE EXCAVATION MONDAY BUT DIDN'T COMMUNICATE THAT WITH ANYONE UNTIL THIS MORNING AT 9AM, WHEN CREW WAS ALREADY DEMOB'ING. | JORDAN | WIGGINS | Laborer | 6 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 282 |  | 96 |  | 6 | 6 | 378 | [16 empty] | 378 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-57880-44116-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-12 | CREW DEMOB'D FROM DIG WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY DEMOB'D WITH TRACK HOE. TRUCK DRIVER AND ONE LABOR CAME BACK TO DEMOB MATERIAL. ONE COMPETENT PERSON CAME BACK FOR NDE CREW TO ENTER EXCAVATION FIRST THING 10/13. NDE CREW WAS AWARE ON SATURDAY THAT THEY WOULD HAVE TO GO BACK IN THE EXCAVATION MONDAY BUT DIDN'T COMMUNICATE THAT WITH ANYONE UNTIL THIS MORNING AT 9AM, WHEN CREW WAS ALREADY DEMOB'ING. | DAVID | KNOTTS | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT8992 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 111 |  | 4 | 6 | 450 | [16 empty] | 450 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-57880-44116-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-12 | CREW DEMOB'D FROM DIG WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY DEMOB'D WITH TRACK HOE. TRUCK DRIVER AND ONE LABOR CAME BACK TO DEMOB MATERIAL. ONE COMPETENT PERSON CAME BACK FOR NDE CREW TO ENTER EXCAVATION FIRST THING 10/13. NDE CREW WAS AWARE ON SATURDAY THAT THEY WOULD HAVE TO GO BACK IN THE EXCAVATION MONDAY BUT DIDN'T COMMUNICATE THAT WITH ANYONE UNTIL THIS MORNING AT 9AM, WHEN CREW WAS ALREADY DEMOB'ING. | TANNER | BRITT | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS3492 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 460 |  | 4 | 10 | 799 | [16 empty] | 799 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-57880-44116-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-12 | CREW DEMOB'D FROM DIG WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY DEMOB'D WITH TRACK HOE. TRUCK DRIVER AND ONE LABOR CAME BACK TO DEMOB MATERIAL. ONE COMPETENT PERSON CAME BACK FOR NDE CREW TO ENTER EXCAVATION FIRST THING 10/13. NDE CREW WAS AWARE ON SATURDAY THAT THEY WOULD HAVE TO GO BACK IN THE EXCAVATION MONDAY BUT DIDN'T COMMUNICATE THAT WITH ANYONE UNTIL THIS MORNING AT 9AM, WHEN CREW WAS ALREADY DEMOB'ING. | ALDO | REYNA | Truck Driver/CDL | 6 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 321 |  | 362 |  | 6 | 4 | 683 | [16 empty] | 683 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-57880-44116-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-12 | CREW DEMOB'D FROM DIG WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY DEMOB'D WITH TRACK HOE. TRUCK DRIVER AND ONE LABOR CAME BACK TO DEMOB MATERIAL. ONE COMPETENT PERSON CAME BACK FOR NDE CREW TO ENTER EXCAVATION FIRST THING 10/13. NDE CREW WAS AWARE ON SATURDAY THAT THEY WOULD HAVE TO GO BACK IN THE EXCAVATION MONDAY BUT DIDN'T COMMUNICATE THAT WITH ANYONE UNTIL THIS MORNING AT 9AM, WHEN CREW WAS ALREADY DEMOB'ING. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 285 |  |  | 10 | 285 | [16 empty] | 285 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | CALEB | HOLTON | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | CALEB | T-Posts | 6 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 52 | 0 | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | CALEB | HOLTON | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | CALEB | Safety Fence | 45 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 400 |  | 52 | 0 | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | MICHAEL | ANISZEWSKI | Laborer | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 |  | 64 |  | 4 | 4 | 252 | [16 empty] | 252 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | MICHAEL | ANISZEWSKI | Laborer |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 252 |  | 64 |  | 4 | 4 | 316 | [16 empty] | 316 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | BOLDBAATAR | ZORIGT | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | BOLDBAATAR | ZORIGT | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | JORDAN | WIGGINS | Laborer | 2 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 346 | 151 | 96 |  | 6 | 6 | 593 | [16 empty] | 593 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | DAVID | KNOTTS | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 362 |  | 4 | 4 | 550 | [16 empty] | 550 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | DAVID | KNOTTS | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | TANNER | BRITT | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 |  |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | TANNER | BRITT | Laborer |  | 4 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 252 |  |  |  | 4 |  | 252 | [16 empty] | 252 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-650-44116-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-12 | MOB'D WITH TOOL TRAILER AND AIR COMPRESSOR. LOWBOY MOB'D WITH TRACK HOE. PROBED 24" ENBRIDGE LINE AT PROPOSED ANOLMALY, FOUND EACH SIDE MARKED 2' FROM EDGE OF PIPE ON EACH SIDE PER ENBRIDGE GROUND DISTURBANCE POLICY. MARKED ENTERPRISE LINE 2' OFF OF EDGE OF PIPE BEFORE ANY MECHANICAL EXCAVATION. TOP SOILED AND BEGAN EXCAVATION. 50% DONE AND WILL FINISH TOMORROW MORNING. SENT ONE LABOR AND ONE TRUCK DRIVER BACK TO DIG 0923 TO MOBE REST OF MATERIAL TO DIG 1465. ALSO SENT BACK A COMPETENT PERSON FOR NDE. | ALDO | REYNA | Truck Driver/CDL | 2 | 4 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT8992 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 395 | 151 | 111 |  | 6 | 6 | 657 | [16 empty] | 657 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | BARKLEY | BROWN | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | BARKLEY | Sand | 12 | Bag | BRAND SAFWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 592 | 151 | 104 | 0 | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | MATTHEW | LINDLEY | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | MATTHEW | Safety Fence | 36 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 492 | 151 | 104 | 0 | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | WAYLON | GREEN | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | RT9829 | T-Posts | 8 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 376 | 151 | 104 | 0 | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | JOSE | VALLES | Laborer | 8 |  |  | 1 | Tool Trailer | 10 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 50 |  | 8 | 10 | 577 | [16 empty] | 577 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | LUTHER | LINDLEY | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 185 |  | 8 | 10 | 712 | [16 empty] | 712 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | MARCELO | GOMEZ | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 460 |  | 8 | 10 | 987 | [16 empty] | 987 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | ANTHONY | MORENO | Laborer | 8 |  |  | 1 | Brush Hog | 10 | HR | RCA2986 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 376 | 151 | 0 |  | 8 | 10 | 527 | [16 empty] | 527 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 160 |  | 12 | 10 | 1027 | [16 empty] | 1027 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | [7 empty] | Hammer Attachment | 10 | HR | RAH1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 285 |  |  | 10 | 285 | [16 empty] | 285 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44116-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-12 | BRAND SAFWAY REMOVED COATING, SAND BLASTED. NDE INSPECTED PIPE. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 8 | HR | RSP | [11 empty] | 23.5 |  |  |  | 188 |  |  | 8 | 188 | [16 empty] | 188 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44116-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-12 | POT HOLED AND INSTALLED MARKER POLES FOR POWER LINES | BARKLEY | BROWN | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44116-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-12 | POT HOLED AND INSTALLED MARKER POLES FOR POWER LINES | MATTHEW | LINDLEY | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44116-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-12 | POT HOLED AND INSTALLED MARKER POLES FOR POWER LINES | WAYLON | GREEN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44116-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-12 | POT HOLED AND INSTALLED MARKER POLES FOR POWER LINES | JOSE | VALLES | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44116-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-12 | POT HOLED AND INSTALLED MARKER POLES FOR POWER LINES | LUTHER | LINDLEY | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44116-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-12 | POT HOLED AND INSTALLED MARKER POLES FOR POWER LINES | MARCELO | GOMEZ | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44116-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-12 | POT HOLED AND INSTALLED MARKER POLES FOR POWER LINES | ANTHONY | MORENO | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | JODY | BROOM | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | [16 empty] | 1003 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | JODY | BROOM | Superintendent |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 126 |  | 13 |  | 1 | 1 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | JODY | BROOM | Superintendent |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 126 |  | 13 |  | 1 | 1 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | JAY | MASEY | Quality Assurance Inspector | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 840 | 151 | 104 |  | 8 | 8 | 1095 | [16 empty] | 1095 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | JAY | MASEY | Quality Assurance Inspector | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 105 |  | 13 |  | 1 | 1 | 118 | [16 empty] | 118 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | JAY | MASEY | Quality Assurance Inspector | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 105 |  | 13 |  | 1 | 1 | 118 | [16 empty] | 118 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | TOME | KIRKLAND | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | [16 empty] | 1003 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | TOME | KIRKLAND | Superintendent |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 126 |  | 13 |  | 1 | 1 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | TOME | KIRKLAND | Superintendent |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 126 |  | 13 |  | 1 | 1 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | KIM | FORNALL | Project Coordinator | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 790.4 | 151 | 104 |  | 8 | 8 | 1045.4 | [16 empty] | 1045.4 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | KIM | FORNALL | Project Coordinator | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 98.8 |  | 13 |  | 1 | 1 | 111.8 | [16 empty] | 111.8 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | KIM | FORNALL | Project Coordinator | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 98.8 |  | 13 |  | 1 | 1 | 111.8 | [16 empty] | 111.8 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | RICHARD | THOMAS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | MICHAEL | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | RICHARD | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | 0 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | 0 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | 0 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | 0 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | 0 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | MATCHES CREW 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | 0 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | JONATHAN | HOLLEY | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | 2888 Coating | 7 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 52 | 0 | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | JONATHAN | HOLLEY | Foreman | 4 | 3 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | JONATHAN | Sand | 10 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 596 | 151 | 91 | 0 | 7 | 7 | 838 | [16 empty] | 838 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | RYAN | FARINELLI | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | RYAN | FARINELLI | Operator II | 5 | 2 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 473.5 | 151 | 91 |  | 7 | 7 | 715.5 | [16 empty] | 715.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | GREG | MCMILLIAN | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | GREG | MCMILLIAN | Laborer | 5 | 2 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 361 | 151 | 91 |  | 7 | 7 | 603 | [16 empty] | 603 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | JEREMAINE | EVANS | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | JEREMAINE | EVANS | Laborer | 5 | 2 |  | 1 | Tool Trailer | 7 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 361 | 151 | 35 |  | 7 | 7 | 547 | [16 empty] | 547 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | DEMETRIUS | MCDONALD | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | DEMETRIUS | MCDONALD | Laborer | 5 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 361 | 151 | 322 |  | 7 | 7 | 834 | [16 empty] | 834 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | JOSE | ORTIZ | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | JOSE | ORTIZ | Laborer | 5 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 361 | 151 | 633.5 |  | 7 | 7 | 1145.5 | [16 empty] | 1145.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | ROBERT | FOSTER | Laborer | 3 |  |  |  | Hammer Attachment | 3 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 141 |  | 0 |  | 3 | 3 | 141 | [16 empty] | 141 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | ROBERT | FOSTER | Laborer | 5 | 2 |  | 1 | Hammer Attachment | 7 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 361 | 151 | 0 |  | 7 | 7 | 512 | [16 empty] | 512 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | BRIAN | RANDLE | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R42809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | BRIAN | RANDLE | Truck Driver/CDL | 5 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | R42809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 411.5 | 151 | 112 |  | 7 | 7 | 674.5 | [16 empty] | 674.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | [7 empty] | 40' Flatbed trailer or equal | 3 | HR | T0000204 | [11 empty] | 18.5 |  |  |  | 55.5 |  |  | 3 | 55.5 | [16 empty] | 55.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | [7 empty] | 40' Flatbed trailer or equal | 7 | HR | T0000204 | [11 empty] | 18.5 |  |  |  | 129.5 |  |  | 7 | 129.5 | [16 empty] | 129.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 7 | HR | RSP922 | [11 empty] | 23.5 |  |  |  | 164.5 |  |  | 7 | 164.5 | [16 empty] | 164.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44117-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-13 | Waited on NDE to give work scope. Blasted and coated the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 192.5 |  |  | 7 | 192.5 | [16 empty] | 192.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | KYLE | BONNEAU | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | KYLE | Rockshield | 40 | LnFt |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 592 | 151 | 104 | 0 | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | KYLE | BONNEAU | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | KYLE | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | JESSE | BERTHIAUME | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | CADEN | THOMPSON | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | CADEN | THOMPSON | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | CADEN | THOMPSON | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | JACOB | CAPITANO | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | [16 empty] | 567 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | JACOB | CAPITANO | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | JACOB | CAPITANO | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | BROC | CALIGER | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | [16 empty] | 675 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | CODY | GAXIOLA | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | [16 empty] | 895 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | CODY | GAXIOLA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | CODY | GAXIOLA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 724 |  |  | 8 | 724 | [16 empty] | 724 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Hammer Attachment | 8 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Hammer Attachment | 1 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Hammer Attachment | 1 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | [16 empty] | 707 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | [16 empty] | 220 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Brush Hog | 8 | HR | RBH | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Brush Hog | 1 | HR | RBH | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Brush Hog | 1 | HR | RBH | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-97640-44117-rev1 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-13 | Started with JSA. Could not use foot ROW due to hunter.. Took longer to get tools and supplies in. pumped water, began to hammer. Got sides hammered out. Hooked up air compressor and jack hammer to knock out the rock under the pipe. NDE came and marked out and had old coating removed. Ready to sandblast in the morning. Put creek back at end of the day. | [7 empty] | Water Pump ( up to 2") | 8 | HR | 2INP | [11 empty] | 6 |  |  |  | 48 |  |  | 8 | 48 | [16 empty] | 48 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | MICHAEL | RATLIFF | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAEL | T-Posts | 15 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | MICHAEL | RATLIFF | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MICHAEL | Safety Fence | 50 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | MICHAEL | RATLIFF | Foreman | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MICHAEL | T-Post Caps | 15 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 274 |  | 39 | 0 | 3 | 3 | 313 | [16 empty] | 313 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | SHAWN | ROSE | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | SHAWN | ROSE | Operator II | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 289 |  | 52 |  | 4 | 4 | 341 | [16 empty] | 341 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | MICHAEL | ELLIOTT | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 13 |  | 2 | 1 | 107 | [16 empty] | 107 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | MICHAEL | ELLIOTT | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | MICHAEL | ELLIOTT | Laborer | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 173 |  | 52 |  | 3 | 4 | 225 | [16 empty] | 225 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | SETH | RATLIFF | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 32 |  | 1 | 2 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | SETH | RATLIFF | Laborer | 5 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 235 |  | 80 |  | 5 | 5 | 315 | [16 empty] | 315 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | SETH | RATLIFF | Laborer | 2 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 220 | 151 | 48 |  | 4 | 3 | 419 | [16 empty] | 419 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | DAVID | RATLIFF | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | DAVID | RATLIFF | Laborer | 5 |  |  |  | Tool Trailer | 5 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 |  | 25 |  | 5 | 5 | 260 | [16 empty] | 260 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | DAVID | RATLIFF | Laborer | 2 | 2 |  | 1 | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 220 | 151 | 20 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | TYLER | BIGG | Truck Driver/CDL | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 107 |  | 37 |  | 2 | 2 | 144 | [16 empty] | 144 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | TYLER | BIGG | Truck Driver/CDL | 5 |  |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 267.5 |  | 92.5 |  | 5 | 5 | 360 | [16 empty] | 360 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | TYLER | BIGG | Truck Driver/CDL | 1 | 2 |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 197.5 | 151 | 55.5 |  | 3 | 3 | 404 | [16 empty] | 404 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | [16 empty] | 46 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | [16 empty] | 184 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-108090-44117-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-13 | PREPPED, CLEANED PIPE/G.WELD SECTION, MOVED SAND BLASTER ON SITE. EXCAVATION/BACKFILL OF SIDES AND POTHOLE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | WAYNE | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | WAYNE | Sand | 50 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | WAYNE | SMITH | Foreman | 7 | 1 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | WAYNE | 2888 Coating | 40 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 618 | 151 | 104 | 0 | 8 | 8 | 873 | [16 empty] | 873 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | WAYNE | SMITH | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | WAYNE | Brushes | 30 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 400 |  | 52 | 0 | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | RICHARD | SHOEMAKE | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | RICHARD | SHOEMAKE | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | OJ | SEALS | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | OJ | SEALS | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | JAMES | KERVIN | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | [16 empty] | 567 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | JAMES | KERVIN | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | RICHARD | ADKINS | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | [16 empty] | 895 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | RICHARD | ADKINS | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1620 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | NICHOLAS | BLANCO | Laborer | 8 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 376 | 151 | 724 |  | 8 | 8 | 1251 | [16 empty] | 1251 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | NICHOLAS | BLANCO | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | BARRETT | WISE | Laborer | 8 |  |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 8 | HR | RAC8545 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 376 | 151 | 228 |  | 8 | 8 | 755 | [16 empty] | 755 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | BARRETT | WISE | Laborer |  | 4 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC8545 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 252 |  | 114 |  | 4 | 4 | 366 | [16 empty] | 366 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | FINISHED SANDBLASTING PIPE. NDE DID INSPECTION. COATED PIPE WITH 2888 | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 8 | HR | 0 | [11 empty] | 23.5 |  |  |  | 188 |  |  | 8 | 188 | [16 empty] | 188 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-57880-44117-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-13 | ASSISTED NDE WHILE NDE WAS GRINDING ANOMALY FLUSH. | JORDAN | WIGGINS | Laborer | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 0 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 |  | 0 |  | 4 | 0 | 188 | [16 empty] | 188 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-57880-44117-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-13 | ASSISTED NDE WHILE NDE WAS GRINDING ANOMALY FLUSH. | JORDAN | WIGGINS | Laborer | 4 | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 0 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 503 | 151 | 0 |  | 9 | 0 | 654 | [16 empty] | 654 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-57880-44117-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-13 | ASSISTED NDE WHILE NDE WAS GRINDING ANOMALY FLUSH. | ALDO | REYNA | Truck Driver/CDL | 4 |  |  |  | 40' Flatbed trailer or equal | 0 | HR | 0 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 214 |  | 0 |  | 4 | 0 | 214 | [16 empty] | 214 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0923 - MC.400216.085 - 474.889 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-57880-44117-rev0 | DIG-0923 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 1 | 226868.4 | 57880 | Central | KY | 474.889 | 2020-10-13 | ASSISTED NDE WHILE NDE WAS GRINDING ANOMALY FLUSH. | ALDO | REYNA | Truck Driver/CDL | 4 | 5 |  | 1 | 40' Flatbed trailer or equal | 0 | HR | 0 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 574 | 151 | 0 |  | 9 | 0 | 725 | [16 empty] | 725 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | CALEB | HOLTON | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | CALEB | Silt Fence | 310 | Ft | BRAND SAFWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | BRAND SAFWAY | [15 empty] | 325 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | CALEB | HOLTON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | T-Posts | 20 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | CALEB | HOLTON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | Safety Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | CALEB | HOLTON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | Sand | 8 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | ZACH | FRANKLIN | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | ZACH | FRANKLIN | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | ZACH | FRANKLIN | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | ZACH | FRANKLIN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | BOLDBAATAR | ZORIGT | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS3492 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | BOLDBAATAR | ZORIGT | Laborer | 2 |  |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 94 | 151 | 114 |  | 2 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | BOLDBAATAR | ZORIGT | Laborer | 2 |  |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 94 |  | 57 |  | 2 | 2 | 151 | [16 empty] | 151 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | BOLDBAATAR | ZORIGT | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS3492 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | DAVID | KNOTTS | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | DAVID | KNOTTS | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | DAVID | KNOTTS | Laborer | 2 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 151 |  |  | 2 |  | 245 | [16 empty] | 245 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | DAVID | KNOTTS | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 181 |  | 1 | 2 | 228 | [16 empty] | 228 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | TANNER | BRITT | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | TANNER | BRITT | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | TANNER | BRITT | Laborer | 2 |  |  | 1 | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 23.5 |  | 94 | 151 | 47 |  | 2 | 2 | 292 | [16 empty] | 292 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | TANNER | BRITT | Laborer | 1 |  |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 47 |  | 57 |  | 1 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-650-44117-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-13 | FINISHED DIGGING. COATING REMOVAL COMPANY BEAT COATING OFF OF PIPE THAT WAS EXPOSED. SANDBLASTED THE ANOMALY AREA. NDE MADE ASSESSMENT. INSTALLED SILT FENCE AROUND SUBSOIL AND TOPSOIL. POT HOLED 24" ENBRIDGE LINE. | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19120 | [11 empty] | 16 |  |  |  | 64 |  |  | 4 | 64 | [16 empty] | 64 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | CALEB | HOLTON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | ZACH | FRANKLIN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | ZACH | FRANKLIN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | ZACH | FRANKLIN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | BOLDBAATAR | ZORIGT | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS3492 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | BOLDBAATAR | ZORIGT | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS3492 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | BOLDBAATAR | ZORIGT | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS3492 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | DAVID | KNOTTS | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 181 |  | 1 | 2 | 228 | [16 empty] | 228 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | DAVID | KNOTTS | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 181 |  | 1 | 2 | 244 | [16 empty] | 244 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | DAVID | KNOTTS | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 181 |  | 1 | 2 | 244 | [16 empty] | 244 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | TANNER | BRITT | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 64 |  | 1 | 4 | 111 | [16 empty] | 111 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | TANNER | BRITT | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 32 |  | 1 | 2 | 95 | [16 empty] | 95 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | TANNER | BRITT | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44117-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-13 | MOB'D WITH TRACK HOE. PUT UP GOAL POSTS AND STREAMERS AND ACCESS SIGNS. ENTERPRISE REP MARKED AND PROBED BOTH LINES OF THEIRS. UNABLE TO TOPSOIL OR BEGIN DIGGING DUE TO BUTTER BAR BREAKING OFF TRACK HOE. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 13 |  | 2 | 1 | 161 | [16 empty] | 161 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 13 |  | 2 | 1 | 107 | [16 empty] | 107 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | MARCELO | GOMEZ | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  |  | Brush Hog | 1 | HR | RRC | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 107 |  | 0 |  | 2 | 1 | 107 | [16 empty] | 107 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-43000-44117-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-13 | DEMOB'D | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Silt Fence | 200 | FT | BRAND SAFWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | BRAND SAFWAY | [15 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Safety Fence | 150 | FT |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | BARKLEY | BROWN | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | T-Posts | 8 | FT |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Mats | 4 | EA |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MATTHEW | LINDLEY | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MATTHEW | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | WAYLON | GREEN | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSE | VALLES | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | LUTHER | LINDLEY | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | LUTHER | LINDLEY | Laborer | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 | 151 | 32 |  | 2 | 2 | 277 | [16 empty] | 277 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MARCELO | GOMEZ | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MARCELO | GOMEZ | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MARCELO | GOMEZ | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MARCELO | GOMEZ | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | MARCELO | GOMEZ | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | ANTHONY | MORENO | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 53.5 |  | 90.5 |  | 1 | 1 | 144 | [16 empty] | 144 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 53.5 |  | 90.5 |  | 1 | 1 | 144 | [16 empty] | 144 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 107 |  | 181 |  | 2 | 2 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 107 | 151 | 181 |  | 2 | 2 | 439 | [16 empty] | 439 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 72 |  | 90.5 |  | 1 | 1 | 162.5 | [16 empty] | 162.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44117-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (4) MATS. EXPOSED LINE. NDE EXAMINED PIPE. BRAND SAFWAY REMOVED COATING. NO ROOM BELOW TO ADD THE BRUSH HOG ON THIS SHEET. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Mats | 2 | EA |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | MATTHEW | LINDLEY | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | LUTHER | LINDLEY | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 32 |  | 2 | 2 | 158 | [16 empty] | 158 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | MARCELO | GOMEZ | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | MARCELO | GOMEZ | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | MARCELO | GOMEZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | ANTHONY | MORENO | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 1 |  |  | Brush Hog | 1 | HR | RRC | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 72 |  | 0 |  | 1 | 1 | 72 | [16 empty] | 72 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 1 |  |  | Brush Hog | 1 | HR | RRC | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 72 |  | 0 |  | 1 | 1 | 72 | [16 empty] | 72 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  |  | Brush Hog | 2 | HR | RRC | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 144 |  | 0 |  | 2 | 2 | 144 | [16 empty] | 144 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44117-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-13 | MOB'D TO DIG SITE. INSTALLED (2) MATS. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44117-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-13 | PREPARED TOOL TRAILER FOR MOB. | JAVIER | VALDEZ | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JAVIER | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 369 | 151 | 78 |  | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44117-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-13 | PREPARED TOOL TRAILER FOR MOB. | ALEJANDRO | CRUZ | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44117-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-13 | PREPARED TOOL TRAILER FOR MOB. | IVAN | MADRID | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 10 | HR | 15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 130 |  | 2 | 10 | 224 | [16 empty] | 224 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44117-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-13 | PREPARED TOOL TRAILER FOR MOB. | ROBERTO | RODRIGUEZ | Laborer | 2 |  |  |  | Tool Trailer | 10 | HR | UTT2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 50 |  | 2 | 10 | 144 | [16 empty] | 144 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44117-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-13 | PREPARED TOOL TRAILER FOR MOB. | JOEL | VALDEZ | Laborer | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19130 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 282 | 151 | 160 |  | 6 | 10 | 593 | [16 empty] | 593 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44117-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-13 | PREPARED TOOL TRAILER FOR MOB. | HECTOR | QUINTANA | Laborer | 2 |  |  |  | Sullair Air Compressor (161 to 185 CFM) or equal ** | 10 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 160 |  | 2 | 10 | 254 | [16 empty] | 254 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44117-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-13 | PREPARED TOOL TRAILER FOR MOB. | MATTHEW | SCHMITT | Truck Driver/CDL | 2 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 107 |  |  |  | 2 |  | 107 | [16 empty] | 107 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | HELPED CREW 4 FINISH SANDBLASTING AND COATING. | JAVIER | VALDEZ | Operator II | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | JAVIER | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 289 |  | 39 |  | 4 | 3 | 328 | [16 empty] | 328 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | HELPED CREW 4 FINISH SANDBLASTING AND COATING. | JAVIER | VALDEZ | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | JAVIER | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 39 |  | 2 | 3 | 205 | [16 empty] | 205 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | HELPED CREW 4 FINISH SANDBLASTING AND COATING. | ALEJANDRO | CRUZ | Laborer | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 220 |  | 39 |  | 4 | 3 | 259 | [16 empty] | 259 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | HELPED CREW 4 FINISH SANDBLASTING AND COATING. | ALEJANDRO | CRUZ | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 39 |  | 2 | 3 | 165 | [16 empty] | 165 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | HELPED CREW 4 FINISH SANDBLASTING AND COATING. | JOEL | VALDEZ | Laborer | 2 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 220 |  |  |  | 4 |  | 220 | [16 empty] | 220 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44117-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-13 | HELPED CREW 4 FINISH SANDBLASTING AND COATING. | JOEL | VALDEZ | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | JODY | BROOM | Superintendent | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 | 151 | 26 |  | 2 | 2 | 364 | [16 empty] | 364 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | JODY | BROOM | Superintendent | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 280.5 |  | 39 |  | 3 | 3 | 319.5 | [16 empty] | 319.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | JODY | BROOM | Superintendent | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 |  | 26 |  | 2 | 2 | 213 | [16 empty] | 213 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | JODY | BROOM | Superintendent | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 345.5 |  | 39 |  | 3 | 3 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | JAY | MASEY | Quality Assurance Inspector | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 315 | 151 | 39 |  | 3 | 3 | 505 | [16 empty] | 505 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | JAY | MASEY | Quality Assurance Inspector | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 315 |  | 39 |  | 3 | 3 | 354 | [16 empty] | 354 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | TOME | KIRKLAND | Superintendent | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 |  | 26 |  | 2 | 2 | 213 | [16 empty] | 213 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | TOME | KIRKLAND | Superintendent | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 280.5 |  | 39 |  | 3 | 3 | 319.5 | [16 empty] | 319.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | TOME | KIRKLAND | Superintendent | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 | 151 | 26 |  | 2 | 2 | 364 | [16 empty] | 364 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | TOME | KIRKLAND | Superintendent | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 345.5 |  | 39 |  | 3 | 3 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 197.6 |  | 26 |  | 2 | 2 | 223.6 | [16 empty] | 223.6 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | KIM | FORNALL | Project Coordinator | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 296.4 |  | 39 |  | 3 | 3 | 335.4 | [16 empty] | 335.4 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 197.6 |  | 26 |  | 2 | 2 | 223.6 | [16 empty] | 223.6 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | KIM | FORNALL | Project Coordinator | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 296.4 | 151 | 39 |  | 3 | 3 | 486.4 | [16 empty] | 486.4 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | RICHARD | THOMAS | Truck Driver/CDL | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RICHARD | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 214 | 151 | 130 |  | 4 | 10 | 495 | [16 empty] | 495 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Tractor/Semi | 10 | HR | 1368 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 3 | HR | 0 | [11 empty] | 24.5 |  |  |  | 73.5 |  |  | 3 | 73.5 | [16 empty] | 73.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 3 | HR | 0 | [11 empty] | 24.5 |  |  |  | 73.5 |  |  | 3 | 73.5 | [16 empty] | 73.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 3 | HR | 0 | [11 empty] | 24.5 |  |  |  | 73.5 |  |  | 3 | 73.5 | [16 empty] | 73.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | MATCHES CREW 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 3 | HR | 0 | [11 empty] | 24.5 |  |  |  | 73.5 |  |  | 3 | 73.5 | [16 empty] | 73.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44118-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | Jeeped pipe, sanded 8ft of pipe to add more coating. Jeeped and found 5 repairs. | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | 2888 Coating | 7 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 792 | 151 | 130 | 0 | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44118-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | Jeeped pipe, sanded 8ft of pipe to add more coating. Jeeped and found 5 repairs. | RYAN | FARINELLI | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44118-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | Jeeped pipe, sanded 8ft of pipe to add more coating. Jeeped and found 5 repairs. | GREG | MCMILLIAN | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44118-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | Jeeped pipe, sanded 8ft of pipe to add more coating. Jeeped and found 5 repairs. | JERMAINE | EVANS | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44118-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | Jeeped pipe, sanded 8ft of pipe to add more coating. Jeeped and found 5 repairs. | DEMETRIUS | MCDONALD | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 368 |  | 10 | 8 | 1021 | [16 empty] | 1021 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44118-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | Jeeped pipe, sanded 8ft of pipe to add more coating. Jeeped and found 5 repairs. | JOSE | ORTIZ | Laborer | 8 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 502 | 151 | 724 |  | 10 | 8 | 1377 | [16 empty] | 1377 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44118-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | Jeeped pipe, sanded 8ft of pipe to add more coating. Jeeped and found 5 repairs. | ROBERT | FOSTER | Laborer | 8 | 2 |  | 1 | Hammer Attachment | 8 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 502 | 151 | 0 |  | 10 | 8 | 653 | [16 empty] | 653 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44118-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | Jeeped pipe, sanded 8ft of pipe to add more coating. Jeeped and found 5 repairs. | BRIAN | RANDLE | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R42809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-86930-44118-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-14 | Jeeped pipe, sanded 8ft of pipe to add more coating. Jeeped and found 5 repairs. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | [16 empty] | 220 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | KYLE | BONNEAU | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | KYLE | Filter Bag | 1 | ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | KYLE | BONNEAU | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | KYLE | Sand | 6 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | JESSE | BERTHIAUME | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | CADEN | THOMPSON | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | CADEN | THOMPSON | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | CADEN | THOMPSON | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | JACOB | CAPITANO | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | [16 empty] | 567 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | JACOB | CAPITANO | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | JACOB | CAPITANO | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | BROC | CALIGER | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | [16 empty] | 675 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | CODY | GAXIOLA | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | [16 empty] | 895 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | CODY | GAXIOLA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | CODY | GAXIOLA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | [16 empty] | 707 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 724 |  |  | 8 | 724 | [16 empty] | 724 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Hammer Attachment | 8 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Hammer Attachment | 1 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Hammer Attachment | 1 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | [16 empty] | 220 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Brush Hog | 8 | HR | RBH | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Brush Hog | 1 | HR | RBH | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Brush Hog | 1 | HR | RBH | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44118-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-14 | Started with JSA. Pumped ditch water, completed backfilling the creek. Sandblasted the pipe, NDE came and assessed anomaly. Tomorrow repair. | [7 empty] | Water Pump ( up to 2") | 8 | HR | 2INP | [11 empty] | 6 |  |  |  | 48 |  |  | 8 | 48 | [16 empty] | 48 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | MICHAEL | RATLIFF | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAEL | Sand | 12 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | MICHAEL | RATLIFF | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | MICHAEL | T-Posts | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | MICHAEL | RATLIFF | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAEL | T-Post Caps | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | MICHAEL | RATLIFF | Foreman | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MICHAEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 248 |  | 39 |  | 3 | 3 | 287 | [16 empty] | 287 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | SHAWN | ROSE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | SHAWN | ROSE | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | SHAWN | ROSE | Operator II | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 206 |  | 39 |  | 3 | 3 | 245 | [16 empty] | 245 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | MICHAEL | ELLIOTT | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | MICHAEL | ELLIOTT | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 | 151 | 39 |  | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | MICHAEL | ELLIOTT | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | MICHAEL | ELLIOTT | Laborer | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 157 |  | 39 |  | 3 | 3 | 196 | [16 empty] | 196 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | SETH | RATLIFF | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | SETH | RATLIFF | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 |  | 48 |  | 3 | 3 | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | SETH | RATLIFF | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | SETH | RATLIFF | Laborer | 2 | 1 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 157 | 151 | 48 |  | 3 | 3 | 356 | [16 empty] | 356 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | DAVID | RATLIFF | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | DAVID | RATLIFF | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | DAVID | RATLIFF | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | DAVID | RATLIFF | Laborer | 2 | 1 |  | 1 | Tool Trailer | 3 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 157 | 151 | 15 |  | 3 | 3 | 323 | [16 empty] | 323 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | TYLER | BIGG | Truck Driver/CDL | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 107 |  | 37 |  | 2 | 2 | 144 | [16 empty] | 144 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | TYLER | BIGG | Truck Driver/CDL | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 160.5 |  | 55.5 |  | 3 | 3 | 216 | [16 empty] | 216 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | TYLER | BIGG | Truck Driver/CDL | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 53.5 |  | 18.5 |  | 1 | 1 | 72 | [16 empty] | 72 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | TYLER | BIGG | Truck Driver/CDL | 2 | 1 |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 179 | 151 | 55.5 |  | 3 | 3 | 385.5 | [16 empty] | 385.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | [16 empty] | 46 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44118-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-14 | SANDBLASTED REPAIR SECTION. INSPECTED AND NDE SUBMITTED FOR RESULTS. SET EXTRA GOAL POSTS AND SIGNAGE. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | 0 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | WAYNE | SMITH | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 0 | Sand | 10 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | WAYNE | SMITH | Foreman | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 0 | 2888 Coating | 20 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 422 |  | 65 | 0 | 5 | 5 | 487 | [16 empty] | 487 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | RICHARD | SHOEMAKE | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 0 | Brushes | 30 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 307.5 | 151 | 65 | 0 | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | RICHARD | SHOEMAKE | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 0 | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | OJ | SEALS | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | OJ | SEALS | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | JAMES | KERVIN | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | JAMES | KERVIN | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | RICHARD | ADKINS | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 230 |  | 5 | 5 | 616 | [16 empty] | 616 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | RICHARD | ADKINS | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 230 |  | 5 | 5 | 497 | [16 empty] | 497 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | NICHOLAS | BLANCO | Laborer | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 235 | 151 | 452.5 |  | 5 | 5 | 838.5 | [16 empty] | 838.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | NICHOLAS | BLANCO | Laborer | 3 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 267 |  | 452.5 |  | 5 | 5 | 719.5 | [16 empty] | 719.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | BARRETT | WISE | Laborer | 5 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 235 | 151 |  |  | 5 |  | 386 | [16 empty] | 386 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | BARRETT | WISE | Laborer | 3 | 2 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 267 |  | 285 |  | 5 | 10 | 552 | [16 empty] | 552 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 0 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | 0 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-3990-44118-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-14 | FINISHED SANDBLASTING PIPE AND RECOAT. JEEP AND DID REPAIR OF COATING | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 5 | HR | 0 | [11 empty] | 23.5 |  |  |  | 117.5 |  |  | 5 | 117.5 | [16 empty] | 117.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-650-44118-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-14 | ASSISTED NDE TECH. | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | CALEB | HOLTON | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | CALEB | Silt Fence | 285 | Ft | BRAND SAFWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 444 | 151 | 78 | 0 | 6 | 6 | 673 | BRAND SAFWAY | [15 empty] | 673 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | CALEB | HOLTON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | ZACH | FRANKLIN | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | MICHAEL | ANISZEWSKI | Laborer | 7 | 1 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 392 | 151 | 128 |  | 8 | 8 | 671 | [16 empty] | 671 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 126 |  | 57 |  | 2 | 2 | 183 | [16 empty] | 183 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | BOLDBAATAR | ZORIGT | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | [16 empty] | 567 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | BOLDBAATAR | ZORIGT | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | JODRAN | WIGGINS | Laborer | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 235 | 151 | 80 |  | 5 | 5 | 466 | [16 empty] | 466 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | JODRAN | WIGGINS | Laborer | 3 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 204 |  | 64 |  | 4 | 4 | 268 | [16 empty] | 268 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | DAVID | KNOTTS | Laborer | 8 |  |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 8 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 376 | 151 | 228 |  | 8 | 8 | 755 | [16 empty] | 755 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | DAVID | KNOTTS | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | TANNER | BRITT | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS3492 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 184 |  | 8 | 4 | 711 | [16 empty] | 711 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | ALDO | REYNA | Truck Driver/CDL | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT8992 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 267.5 | 151 | 92.5 |  | 5 | 5 | 511 | [16 empty] | 511 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | ALDO | REYNA | Truck Driver/CDL | 3 | 1 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT8992 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 232.5 |  | 74 |  | 4 | 4 | 306.5 | [16 empty] | 306.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS3492 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 724 |  |  | 8 | 724 | [16 empty] | 724 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-9400-44118-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-14 | WELDED DIGGING BAR ON TRACK HOE. BEGAN TOPSOILING. BEGAN EXCAVATING - 100% COMPLETE. COATING REMOVAL COMPANY BEAT COATING OFF OF PROPOSED ANOMALY. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | CALEB | HOLTON | Foreman | 1 | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 374 |  | 39 |  | 4 | 3 | 413 | [16 empty] | 413 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | ZACH | FRANKLIN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | ZACH | FRANKLIN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | BOLDBAATAR | ZORIGT | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 32 |  | 1 | 2 | 95 | [16 empty] | 95 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | BOLDBAATAR | ZORIGT | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | JODRAN | WIGGINS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | JODRAN | WIGGINS | Laborer |  | 1 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 10 |  | 1 | 2 | 73 | [16 empty] | 73 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | DAVID | KNOTTS | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 32 |  | 1 | 2 | 95 | [16 empty] | 95 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | DAVID | KNOTTS | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | TANNER | BRITT | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8992 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | TANNER | BRITT | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8992 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 18.5 |  | 2 | 1 | 144.5 | [16 empty] | 144.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | ALDO | REYNA | Truck Driver/CDL |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS3492 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 144 |  | 92 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | ALDO | REYNA | Truck Driver/CDL |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS3492 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 72 |  | 46 |  | 1 | 1 | 118 | [16 empty] | 118 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-23260-44118-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-14 | BEGAN SITE ACCESS. POT HOLED ENBRIDGE LINE AT PROPOSED ANOMALY AREA. | MICHAEL | ANISZEWSKI | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Sand | 8 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Silt Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | BARKLEY | BROWN | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | T-Posts | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | Safety Fence | 150 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 61.5 |  | 13 | 0 | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | MATTHEW | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | MATTHEW | LINDLEY | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | WAYLON | GREEN | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 | 151 | 39 |  | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | JOSE | VALLES | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | LUTHER | LINDLEY | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | LUTHER | LINDLEY | Laborer | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 | 151 | 48 |  | 3 | 3 | 340 | [16 empty] | 340 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | MARCELO | GOMEZ | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | MARCELO | GOMEZ | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | MARCELO | GOMEZ | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | ANTHONY | MORENO | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 92 |  | 3 | 2 | 384 | [16 empty] | 384 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  |  | Brush Hog | 1 | HR | RRC | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 53.5 |  | 0 |  | 1 | 1 | 53.5 | [16 empty] | 53.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  |  | Brush Hog | 2 | HR | RRC | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 107 |  | 0 |  | 2 | 2 | 107 | [16 empty] | 107 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | JOSHUA | PHILLIPSON | Truck Driver/CDL | 3 |  |  | 1 | Brush Hog | 2 | HR | RRC | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 160.5 | 151 | 0 |  | 3 | 2 | 311.5 | [16 empty] | 311.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44118-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-14 | PUMPED WATER OUT OF BELL HOLE. CLEANED OUT BELL HOLE WITH EXCAVATOR. SANDBLASTED. NDE EXAMINED PIPE. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | RSP | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Silt Fence | 50 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 39 | 0 | 1 | 3 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | BARKLEY | BROWN | Foreman | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | T-Posts | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 274 |  | 39 | 0 | 3 | 3 | 313 | [16 empty] | 313 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | Safety Fence | 50 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 61.5 |  | 39 | 0 | 1 | 3 | 100.5 | [16 empty] | 100.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | MATTHEW | LINDLEY | Operator II | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 227.5 |  | 39 |  | 3 | 3 | 266.5 | [16 empty] | 266.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 39 |  | 1 | 3 | 86 | [16 empty] | 86 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | WAYLON | GREEN | Laborer | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | RT9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 173 |  | 39 |  | 3 | 3 | 212 | [16 empty] | 212 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 15 |  | 1 | 3 | 62 | [16 empty] | 62 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | JOSE | VALLES | Laborer | 1 | 2 |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 173 |  | 15 |  | 3 | 3 | 188 | [16 empty] | 188 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 48 |  | 1 | 3 | 95 | [16 empty] | 95 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | LUTHER | LINDLEY | Laborer | 1 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 173 |  | 48 |  | 3 | 3 | 221 | [16 empty] | 221 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | MARCELO | GOMEZ | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 55.5 |  | 1 | 3 | 102.5 | [16 empty] | 102.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | MARCELO | GOMEZ | Laborer | 1 | 2 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 173 |  | 55.5 |  | 3 | 3 | 228.5 | [16 empty] | 228.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 138 |  | 1 | 3 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | ANTHONY | MORENO | Laborer | 1 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 173 |  | 92 |  | 3 | 2 | 265 | [16 empty] | 265 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  |  | Brush Hog | 3 | HR | RRC | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 53.5 |  | 0 |  | 1 | 3 | 53.5 | [16 empty] | 53.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 | 2 |  |  | Brush Hog | 2 | HR | RRC | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 197.5 |  | 0 |  | 3 | 2 | 197.5 | [16 empty] | 197.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-51460-44118-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-14 | EXPOSED PIPE. NDE EXAMINED THE COATING | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44118-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-14 | CUT ACCESS INTO DIG | BARKLEY | BROWN | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44118-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-14 | CUT ACCESS INTO DIG | MATTHEW | LINDLEY | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44118-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-14 | CUT ACCESS INTO DIG | WAYLON | GREEN | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1907 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 92 |  | 3 | 2 | 281 | [16 empty] | 281 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44118-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-14 | CUT ACCESS INTO DIG | JOSE | VALLES | Laborer |  | 2 |  |  | Brush Hog | 2 | HR | RRC | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 126 |  | 0 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44118-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-14 | CUT ACCESS INTO DIG | LUTHER | LINDLEY | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44118-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-14 | CUT ACCESS INTO DIG | MARCELO | GOMEZ | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44118-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-14 | CUT ACCESS INTO DIG | ANTHONY | MORENO | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44118-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-14 | CUT ACCESS INTO DIG | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 144 |  |  |  | 2 |  | 144 | [16 empty] | 144 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | FRANKIE | VALENCIA | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 6 | HR | 15349 | Safety Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 78 | 0 | 2 | 6 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | FRANKIE | VALENCIA | Foreman | 6 | 4 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15349 | T-Posts | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 844 | 151 | 78 | 0 | 10 | 6 | 1073 | [16 empty] | 1073 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | JAVIER | VALDEZ | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 6 | HR | JAVIER | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 78 |  | 2 | 6 | 201 | [16 empty] | 201 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | JAVIER | VALDEZ | Operator II | 6 | 4 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JAVIER | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 701 | 151 | 78 |  | 10 | 6 | 930 | [16 empty] | 930 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | ALEJANDRO | CRUZ | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 6 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 78 |  | 2 | 6 | 172 | [16 empty] | 172 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | ALEJANDRO | CRUZ | Laborer | 6 | 4 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 534 | 151 | 78 |  | 10 | 6 | 763 | [16 empty] | 763 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | ASTOLFO | FLORES | Laborer | 2 |  |  |  | Tool Trailer | 6 | HR | UTT2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 30 |  | 2 | 6 | 124 | [16 empty] | 124 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | ASTOLFO | FLORES | Laborer | 6 | 4 |  | 1 | Tool Trailer | 6 | HR | UTT2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 534 | 151 | 30 |  | 10 | 6 | 715 | [16 empty] | 715 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | IVAN | MADRID | Laborer | 2 |  |  |  | Sullair Air Compressor (161 to 185 CFM) or equal ** | 6 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 96 |  | 2 | 6 | 190 | [16 empty] | 190 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | IVAN | MADRID | Laborer | 6 | 4 |  | 1 | Sullair Air Compressor (161 to 185 CFM) or equal ** | 6 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 534 | 151 | 96 |  | 10 | 6 | 781 | [16 empty] | 781 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | ROBERTO | RODRIGUEZ | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | ROBERTO | RODRIGUEZ | Laborer | 6 | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 534 | 151 |  |  | 10 |  | 685 | [16 empty] | 685 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | JOEL | VALDEZ | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | JOEL | VALDEZ | Laborer | 6 | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 534 | 151 |  |  | 10 |  | 685 | [16 empty] | 685 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | HECTOR | QUINTANA | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | HECTOR | QUINTANA | Laborer | 6 | 4 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 534 | 151 |  |  | 10 |  | 685 | [16 empty] | 685 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | MATTHEW | SCHMITT | Truck Driver/CDL | 6 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 |  | 96 |  | 6 | 6 | 417 | [16 empty] | 417 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44118-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-14 | ROW SWEEP AT DIGGING AREA. SETUP GOAL POSTS AND SIGNS FOR WORK SITE. STARTED POTHOLING 30" ENBRIDGE LINE. PUT UP SAFETY FENCE AND CLEANED UP WORKING AREA. | MATTHEW | SCHMITT | Truck Driver/CDL | 2 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 395 | 151 | 96 |  | 6 | 6 | 642 | [16 empty] | 642 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | GARRETT | DICKSON | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 |  | 52 |  | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | GARRETT | DICKSON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | GARRETT | DICKSON | Foreman | 2 | 3 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 448 | 151 | 65 |  | 5 | 5 | 664 | [16 empty] | 664 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | RYAN | COLEMAN | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | RYAN | COLEMAN | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | RYAN | COLEMAN | Operator II | 2 | 3 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 372 | 151 | 65 |  | 5 | 5 | 588 | [16 empty] | 588 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | JACOB | GORDON | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | JACOB | GORDON | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | JACOB | GORDON | Laborer | 2 | 3 |  | 1 | Tool Trailer | 5 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 283 | 151 | 25 |  | 5 | 5 | 459 | [16 empty] | 459 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | ZACHARY | POWDERS | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 |  |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | ZACHARY | POWDERS | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | ZACHARY | POWDERS | Laborer | 2 | 3 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 283 | 151 |  |  | 5 |  | 434 | [16 empty] | 434 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | COLTON | ROBERTS | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 |  |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | COLTON | ROBERTS | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | COLTON | ROBERTS | Laborer | 2 | 3 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 283 | 151 |  |  | 5 |  | 434 | [16 empty] | 434 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | JUAN | DURAN | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 |  |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | JUAN | DURAN | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | JUAN | DURAN | Laborer | 2 | 3 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 283 | 151 |  |  | 5 |  | 434 | [16 empty] | 434 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | TANNER | BRUMMETT | Laborer | 4 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 188 |  |  |  | 4 |  | 188 | [16 empty] | 188 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | TANNER | BRUMMETT | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | TANNER | BRUMMETT | Laborer | 2 | 3 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 283 | 151 |  |  | 5 |  | 434 | [16 empty] | 434 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | IAIN | ALLRED | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | IAIN | ALLRED | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44118-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-14 | MOB'D TO DIG. SET TRAILER IN PLACE AND ORGANIZED IT. SET ROAD SIGNS OUT. STANDBY FOR (5) HOURS WAITING FOR SURVEY CREW TO SET STAKES. | IAIN | ALLRED | Truck Driver/CDL | 2 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 323 | 151 | 80 |  | 5 | 5 | 554 | [16 empty] | 554 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | JODY | BROOM | Superintendent | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 |  | 26 |  | 2 | 2 | 213 | [16 empty] | 213 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | JODY | BROOM | Superintendent | 6 | 2 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 0 | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 813 | 151 | 104 |  | 8 | 8 | 1068 | [16 empty] | 1068 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | TOME | KIRKLAND | Superintendent | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 |  | 26 |  | 2 | 2 | 213 | [16 empty] | 213 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | TOME | KIRKLAND | Superintendent | 6 | 2 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 0 | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 813 | 151 | 104 |  | 8 | 8 | 1068 | [16 empty] | 1068 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | JAY | MASEY | Quality Assurance Inspector | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 0 | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 840 | 151 | 104 |  | 8 | 8 | 1095 | [16 empty] | 1095 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | JUANITO | RODRIGUEZ | Safety Person | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | JUANITO | RODRIGUEZ | Safety Person | 6 | 2 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 0 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 644 | 151 | 104 |  | 8 | 8 | 899 | [16 empty] | 899 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | DANIEL | YOUNG | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | DANIEL | YOUNG | Operator II | 6 | 2 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 0 | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 535 | 151 | 104 |  | 8 | 8 | 790 | [16 empty] | 790 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAEL | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 197.6 |  | 26 |  | 2 | 2 | 223.6 | [16 empty] | 223.6 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | KIM | FORNALL | Project Coordinator | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 0 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 790.4 | 151 | 104 |  | 8 | 8 | 1045.4 | [16 empty] | 1045.4 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | 0 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | 0 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 8 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 8 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-18890-44119-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-15 | MOB'D | BLAKE | HOLLEY | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BLAKE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-18890-44119-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-15 | MOB'D | RYAN | FARINELLI | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-18890-44119-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-15 | MOB'D | GREG | MCMILLIAN | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-18890-44119-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-15 | MOB'D | JEREMAINE | EVANS | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-18890-44119-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-15 | MOB'D | DEMETRIUS | MCDONALD | Laborer |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 189 |  | 48 |  | 3 | 3 | 237 | [16 empty] | 237 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-18890-44119-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-15 | MOB'D | JOSE | ORTIZ | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-18890-44119-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-15 | MOB'D | ROBERT | FOSTER | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-18890-44119-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-15 | MOB'D | BRIAN | RANDLE | Truck Driver/CDL |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0563 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 216 |  | 271.5 |  | 3 | 3 | 487.5 | [16 empty] | 487.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-18890-44119-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-15 | MOB'D | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | Straw Bales | 10 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 892 | 151 | 143 | 0 | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 502 | 151 | 160 |  | 10 | 10 | 813 | [16 empty] | 813 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 572 | 151 | 460 |  | 10 | 10 | 1183 | [16 empty] | 1183 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 285 |  |  | 10 | 285 | [16 empty] | 285 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-97640-44119-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-15 | WAITED ON ASSESSMENT OF DAMAGE. PREPARED FOR A RECOAT AND CLOCK SPRING | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | WAYNE | SMITH | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | WAYNE | Rockshield | 32 | LnFt |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | WAYNE | SMITH | Foreman | 6 | 4 |  |  | Pickup-F150 or F250 or equal | 10 | HR | WAYNE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 844 |  | 130 |  | 10 | 10 | 974 | [16 empty] | 974 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | RICHARD | SHOEMAKE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | RICHARD | SHOEMAKE | Operator II | 6 | 4 |  |  | Pickup-F150 or F250 or equal | 10 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 701 |  | 130 |  | 10 | 10 | 831 | [16 empty] | 831 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | OJ | SEALS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | OJ | SEALS | Laborer | 6 | 4 |  |  | Pickup-F150 or F250 or equal | 10 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 534 |  | 130 |  | 10 | 10 | 664 | [16 empty] | 664 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | JAMES | KERVIN | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | JAMES | KERVIN | Laborer | 6 | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 534 |  | 460 |  | 10 | 10 | 994 | [16 empty] | 994 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | RICHARD | ADKINS | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | RICHARD | ADKINS | Laborer | 6 | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 534 |  | 905 |  | 10 | 10 | 1439 | [16 empty] | 1439 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | NICHOLAS | BLANCO | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | NICHOLAS | BLANCO | Laborer | 6 | 4 |  |  | Padding Bucket | 10 | HR | RPB2004 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 534 |  | 0 |  | 10 | 10 | 534 | [16 empty] | 534 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | BARRETT | WISE | Laborer | 2 |  |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 94 |  | 57 |  | 2 | 2 | 151 | [16 empty] | 151 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | BARRETT | WISE | Laborer | 6 | 4 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | RAC0858 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 534 |  | 285 |  | 10 | 10 | 819 | [16 empty] | 819 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | STEVE | CLARK | Truck Driver/CDL | 8 | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 |  | 192 |  | 12 | 12 | 908 | [16 empty] | 908 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | [7 empty] | 40' Flatbed trailer or equal | 12 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLT | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | [7 empty] | Tool Trailer | 2 | HR | UTT2180 | [11 empty] | 5 |  |  |  | 10 |  |  | 2 | 10 | [16 empty] | 10 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44119-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-15 | JEEPED PIPE WITH NO REPAIRS. PUT ON ROCKSHEILD, PADDED PIPE AND COMPACTED WITH POGO. GOT ABOUT 50% BACKFILLED | [7 empty] | Tool Trailer | 8 | HR | UTT2180 | [11 empty] | 5 |  |  |  | 40 |  |  | 8 | 40 | [16 empty] | 40 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | CALEB | HOLTON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | Sand | 5 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | CALEB | HOLTON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | ZACH | FRANKLIN | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | ZACH | FRANKLIN | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | MICHAEL | ANISZEWSKI | Laborer | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 | 151 | 64 |  | 4 | 4 | 403 | [16 empty] | 403 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | BOLDBAATAR | ZORIGT | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | BOLDBAATAR | ZORIGT | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | JORDAN | WIGGINS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | JORDAN | WIGGINS | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | DAVID | KNOTTS | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | DAVID | KNOTTS | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | TANNER | BRITT | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | TANNER | BRITT | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | ALDO | REYNA | Truck Driver/CDL | 2 |  |  |  | Hammer Attachment | 2 | HR | RHA6A06 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 107 |  | 0 |  | 2 | 2 | 107 | [16 empty] | 107 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | ALDO | REYNA | Truck Driver/CDL | 4 |  |  | 1 | Hammer Attachment | 4 | HR | RHA6A06 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 214 | 151 | 0 |  | 4 | 4 | 365 | [16 empty] | 365 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLT | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLT | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [11 empty] | 16 |  |  |  | 32 |  |  | 2 | 32 | [16 empty] | 32 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [11 empty] | 16 |  |  |  | 64 |  |  | 4 | 64 | [16 empty] | 64 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44119-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-15 | SANDBLASTED. NDE TOOK AN HOUR TO DO THEIR ASSESSMENT ON ANOMALY. WAITED ON LOWBOY UNTIL 12:30PM. DEMOB'D | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | CALEB | HOLTON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | T-Posts | 8 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | CALEB | HOLTON | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | CALEB | HOLTON | Foreman |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 | 151 | 52 |  | 4 | 4 | 603 | [16 empty] | 603 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | ZACH | FRANKLIN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | ZACH | FRANKLIN | Operator II | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 144.5 |  | 26 |  | 2 | 2 | 170.5 | [16 empty] | 170.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | ZACH | FRANKLIN | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | MICHAEL | ANISZEWSKI | Laborer | 1 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 110 |  | 32 |  | 2 | 2 | 142 | [16 empty] | 142 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | MICHAEL | ANISZEWSKI | Laborer |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 189 |  | 48 |  | 3 | 3 | 237 | [16 empty] | 237 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | BOLDBAATAR | ZORIGT | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | BOLDBAATAR | ZORIGT | Laborer | 1 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 110 |  | 32 |  | 2 | 2 | 142 | [16 empty] | 142 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | BOLDBAATAR | ZORIGT | Laborer |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 189 |  | 48 |  | 3 | 3 | 237 | [16 empty] | 237 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | JORDAN | WIGGINS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | JORDAN | WIGGINS | Laborer | 1 | 1 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 110 |  | 10 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | JORDAN | WIGGINS | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | DAIVD | KNOTTS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | DAIVD | KNOTTS | Laborer | 1 | 1 |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 110 |  | 37 |  | 2 | 2 | 147 | [16 empty] | 147 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | DAIVD | KNOTTS | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | TANNER | BRITT | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | TANNER | BRITT | Laborer | 1 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 110 |  | 92 |  | 2 | 2 | 202 | [16 empty] | 202 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | TANNER | BRITT | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | ALDO | REYNA | Truck Driver/CDL | 2 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 251 |  | 90.5 |  | 4 | 1 | 341.5 | [16 empty] | 341.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | ALDO | REYNA | Truck Driver/CDL |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 144 |  | 181 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44119-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-15 | MOB'D. TOP SOILED. PUT TOP SOIL TO ONE SIDE AND COVERED WITH SILT FENCE. WAITING THE REST OF THE DAY ON ENBRIDGE OPERATIONS SO WE COULD START DIGGING AT THE PROPOSED ANOMALY. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Water Pump ( up to 2") | 1 | HR | 2INP | [11 empty] | 6 |  |  |  | 6 |  |  | 1 | 6 | [16 empty] | 6 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44119-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-15 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | BARKLEY | BROWN | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Sand | 9 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | BARKLEY | BROWN | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | T-Posts | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 52 | 0 | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Safety Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | MATTHEW | LINDLEY | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | MATTHEW | LINDLEY | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | WAYLON | GREEN | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | WAYLON | GREEN | Laborer | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 52 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | JOSE | VALLES | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | JOSE | VALLES | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | LUTHER | LINDLEY | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | LUTHER | LINDLEY | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | MARCELO | GOMEZ | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | MARCELO | GOMEZ | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | ANTHONY | MORENO | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | ANTHONY | MORENO | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 362 |  | 4 | 4 | 550 | [16 empty] | 550 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Padding Bucket | 4 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44119-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-15 | No Comments | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 4 | HR | SBP | [11 empty] | 23.5 |  |  |  | 94 |  |  | 4 | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-54330-44119-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-15 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | GARRETT | DICKSON | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | GARRETT | DICKSON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | GARRETT | DICKSON | Foreman | 3 | 3 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 522 | 151 | 78 |  | 6 | 6 | 751 | [16 empty] | 751 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 13 |  | 2 | 1 | 213 | [16 empty] | 213 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | RYAN | COLEMAN | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | RYAN | COLEMAN | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | RYAN | COLEMAN | Operator II | 3 | 3 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 433.5 | 151 | 78 |  | 6 | 6 | 662.5 | [16 empty] | 662.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | RYAN | COLEMAN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | JACOB | GORDON | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | JACOB | GORDON | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | JACOB | GORDON | Laborer | 3 | 3 |  | 1 | Tool Trailer | 6 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 330 | 151 | 30 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | JACOB | GORDON | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | ZACHARY | POWDERS | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 |  | 48 |  | 3 | 3 | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | ZACHARY | POWDERS | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | ZACHARY | POWDERS | Laborer | 3 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 330 | 151 | 96 |  | 6 | 6 | 577 | [16 empty] | 577 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | ZACHARY | POWDERS | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | COLTON | ROBERTS | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | COLTON | ROBERTS | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | COLTON | ROBERTS | Laborer | 3 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 330 | 151 | 543 |  | 6 | 6 | 1024 | [16 empty] | 1024 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | JUAN | DURAN | Laborer | 3 |  |  |  | Hammer Attachment | 3 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 141 |  | 0 |  | 3 | 3 | 141 | [16 empty] | 141 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | JUAN | DURAN | Laborer | 2 |  |  |  | Hammer Attachment | 2 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 94 |  | 0 |  | 2 | 2 | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | JUAN | DURAN | Laborer | 3 | 3 |  | 1 | Hammer Attachment | 6 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 330 | 151 | 0 |  | 6 | 6 | 481 | [16 empty] | 481 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | JUAN | DURAN | Laborer |  | 1 |  |  | Hammer Attachment | 1 | HR | RHA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 63 |  | 0 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | TANNER | BRUMMETT | Laborer | 3 |  |  |  | Padding Bucket | 3 | HR | RPB | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 141 |  | 0 |  | 3 | 3 | 141 | [16 empty] | 141 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | TANNER | BRUMMETT | Laborer | 2 |  |  |  | Padding Bucket | 2 | HR | RPB | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 94 |  | 0 |  | 2 | 2 | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | TANNER | BRUMMETT | Laborer | 3 | 3 |  | 1 | Padding Bucket | 6 | HR | RPB | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 330 | 151 | 0 |  | 6 | 6 | 481 | [16 empty] | 481 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | TANNER | BRUMMETT | Laborer |  | 1 |  |  | Padding Bucket | 1 | HR | RPB | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 63 |  | 0 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | IAIN | ALLRED | Truck Driver/CDL | 3 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 160.5 |  |  |  | 3 |  | 160.5 | [16 empty] | 160.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | IAIN | ALLRED | Truck Driver/CDL | 2 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 107 |  |  |  | 2 |  | 107 | [16 empty] | 107 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | IAIN | ALLRED | Truck Driver/CDL | 3 | 3 |  | 1 | [11 empty] | 53.5 | 72 | 0 | 151 |  |  | 376.5 | 151 |  |  | 6 |  | 527.5 | [16 empty] | 527.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44119-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-15 | DAYLIGHTED THE PIPE IN 5 LOCATIONS AROUND THE BEND OF THE PIPE. THEN ON STANDBY WAITING FOR EQUIPMENT TO ARRIVE. WHILE WAITING THE CREW ORGANIZED THE TOOL TRAILER AND PREPARED FOR DIGGING. ONCE EQUIPMENT ARRIVED, BELLHOLE WAS COMPLETED. THEN PUT UP SAFETY FENCE AROUND THE DIG AND CLEANED UP THE SITE. TALKED TO SURVEY AROUND 6PM AND THEY WERE NOT ABLE TO STAKE OFF OUR NEXT DIG TODAY | IAIN | ALLRED | Truck Driver/CDL |  | 1 | [13 empty] | 53.5 | 72 | 0 | 151 |  |  | 72 |  |  |  | 1 |  | 72 | [16 empty] | 72 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | URIEL | VALENCIA | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | URIEL | Mats | 6 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | 0 | [15 empty] | 586 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | URIEL | VALENCIA | Foreman | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | URIEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 322 |  | 52 |  | 4 | 4 | 374 | 0 | [15 empty] | 374 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | HECTOR | VALDEZ NEVAREZ | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | 0 | [15 empty] | 523.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | HECTOR | VALDEZ NEVAREZ | Operator II | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 267.5 |  | 52 |  | 4 | 4 | 319.5 | 0 | [15 empty] | 319.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | 0 | [15 empty] | 451 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 204 |  | 52 |  | 4 | 4 | 256 | 0 | [15 empty] | 256 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | ASTOLFO | FLORES | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | 0 | [15 empty] | 451 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | ASTOLFO | FLORES | Laborer | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 204 |  | 52 |  | 4 | 4 | 256 | 0 | [15 empty] | 256 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | IVAN | MADRID | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | IVAN | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | 0 | [15 empty] | 451 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | IVAN | MADRID | Laborer | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | IVAN | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 204 |  | 52 |  | 4 | 4 | 256 | 0 | [15 empty] | 256 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | ROBERTO | RODRIGUEZ | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | 0 | [15 empty] | 411 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | ROBERTO | RODRIGUEZ | Laborer | 3 | 1 |  |  | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 204 |  | 20 |  | 4 | 4 | 224 | 0 | [15 empty] | 224 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | JOEL | VALDEZ NEVAREZ | Laborer | 5 |  |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 5 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 235 | 151 | 142.5 |  | 5 | 5 | 528.5 | 0 | [15 empty] | 528.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | JOEL | VALDEZ NEVAREZ | Laborer | 3 | 1 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 204 |  | 114 |  | 4 | 4 | 318 | 0 | [15 empty] | 318 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | HECTOR | QUINTANA VALDEZ | Laborer | 5 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 235 | 151 |  |  | 5 |  | 386 | 0 | [15 empty] | 386 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | HECTOR | QUINTANA VALDEZ | Laborer | 3 | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 204 |  |  |  | 4 |  | 204 | 0 | [15 empty] | 204 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | MATTHEW | SCHMITT | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | 0 | [15 empty] | 498.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44119-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-15 | WAITED FOR SEMI TRUCK TO DELIVER EXCAVATOR. RECEIVED 6 MATS FOR SITE. 2 WERE PLACED ON ROW ENTRANCE. 4 USED FOR DIGGING WHEN STRADDLING OVER 30". FINISHED SITE PREP, READY TO COMMENCE EXCAVATION. | MATTHEW | SCHMITT | Truck Driver/CDL | 3 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 232.5 |  | 64 |  | 4 | 4 | 296.5 | 0 | [15 empty] | 296.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | BLAKE | HOLLEY | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | BLAKE | Rockshield | 8 | LnFt |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | 0 | [15 empty] | 261 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | BLAKE | HOLLEY | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | BLAKE | Straw Bales | 28 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | 0 | [15 empty] | 499 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | BLAKE | HOLLEY | Foreman | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BLAKE | Seed Mix | 25 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 174 |  | 26 | 0 | 2 | 2 | 200 | 0 | [15 empty] | 200 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | RYAN | FARINELLI | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | 0 | [15 empty] | 223.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | RYAN | FARINELLI | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | RYAN | FARINELLI | Operator II | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 144.5 |  | 26 |  | 2 | 2 | 170.5 | 0 | [15 empty] | 170.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | GREG | MCMILLIAN | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | 0 | [15 empty] | 180 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | GREG | MCMILLIAN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | 0 | [15 empty] | 391 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | GREG | MCMILLIAN | Laborer | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 110 |  | 26 |  | 2 | 2 | 136 | 0 | [15 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | JEREMIANE | EVANS | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | 0 | [15 empty] | 156 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | JEREMIANE | EVANS | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | 0 | [15 empty] | 359 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | JEREMIANE | EVANS | Laborer | 1 | 1 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 110 |  | 10 |  | 2 | 2 | 120 | 0 | [15 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | DEMETRIUS | MCDONALD | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 |  | 48 |  | 3 | 3 | 189 | 0 | [15 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | DEMETRIUS | MCDONALD | Laborer | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 | 151 | 64 |  | 4 | 4 | 403 | 0 | [15 empty] | 403 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | DEMETRIUS | MCDONALD | Laborer | 1 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 110 |  | 32 |  | 2 | 2 | 142 | 0 | [15 empty] | 142 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | JOSE | ORTIZ | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | 0 | [15 empty] | 196.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | JOSE | ORTIZ | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | 0 | [15 empty] | 413 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | JOSE | ORTIZ | Laborer | 1 | 1 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 110 |  | 37 |  | 2 | 2 | 147 | 0 | [15 empty] | 147 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | ROBERT | FOSTER | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | 0 | [15 empty] | 279 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | ROBERT | FOSTER | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | 0 | [15 empty] | 523 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | ROBERT | FOSTER | Laborer | 1 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 110 |  | 92 |  | 2 | 2 | 202 | 0 | [15 empty] | 202 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | BRIAN | RANDLE | Truck Driver/CDL | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0563 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 160.5 |  | 271.5 |  | 3 | 3 | 432 | 0 | [15 empty] | 432 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | BRIAN | RANDLE | Truck Driver/CDL | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 214 | 151 | 362 |  | 4 | 4 | 727 | 0 | [15 empty] | 727 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | BRIAN | RANDLE | Truck Driver/CDL | 1 | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 125.5 |  | 181 |  | 2 | 2 | 306.5 | 0 | [15 empty] | 306.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | 0 | [15 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | 0 | [15 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44119-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-15 | JEEP PIPE. ROCK SHIELDED PIPE. BACKFILLED EXCAVATION. CLEANED UP SITE AND DEMOB'D | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | 0 | [15 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | MICHAEL | RATLIFF | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | 0 | [15 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | MICHAEL | RATLIFF | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | MICHAEL | RATLIFF | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MICHAEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | 0 | [15 empty] | 586 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | MICHAEL | RATLIFF | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | 0 | [15 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | 0 | [15 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | SHAWN | ROSE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | SHAWN | ROSE | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | 0 | [15 empty] | 523.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | SHAWN | ROSE | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | 0 | [15 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | MICHAEL | ELLIOTT | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | 0 | [15 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | MICHAEL | ELLIOTT | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | 0 | [15 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | MICHAEL | ELLIOTT | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | 0 | [15 empty] | 451 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | MICHAEL | ELLIOTT | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | 0 | [15 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | SETH | RATLIFF | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | SETH | RATLIFF | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | SETH | RATLIFF | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | 0 | [15 empty] | 411 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | SETH | RATLIFF | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | 0 | [15 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | DAVID | RATLIFF | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | 0 | [15 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | DAVID | RATLIFF | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | 0 | [15 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | DAVID | RATLIFF | Laborer | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 235 | 151 | 80 |  | 5 | 5 | 466 | 0 | [15 empty] | 466 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | DAVID | RATLIFF | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 32 |  | 2 | 2 | 158 | 0 | [15 empty] | 158 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | TYLER | BIGG | Truck Driver/CDL | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 53.5 |  | 18.5 |  | 1 | 1 | 72 | 0 | [15 empty] | 72 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | TYLER | BIGG | Truck Driver/CDL | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 107 |  | 37 |  | 2 | 2 | 144 | 0 | [15 empty] | 144 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | TYLER | BIGG | Truck Driver/CDL | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 267.5 | 151 | 92.5 |  | 5 | 5 | 511 | 0 | [15 empty] | 511 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | TYLER | BIGG | Truck Driver/CDL |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 144 |  | 37 |  | 2 | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | 0 | [15 empty] | 46 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | 0 | [15 empty] | 92 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | 0 | [15 empty] | 230 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | 0 | [15 empty] | 92 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | 0 | [15 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | 0 | [15 empty] | 452.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Hammer Attachment | 1 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Hammer Attachment | 5 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Padding Bucket | 5 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLT | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLT | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLT | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | 0 | [15 empty] | 65 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLT | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | 0 | [15 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | 0 | [15 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 5 | HR | RAC | [11 empty] | 28.5 |  |  |  | 142.5 |  |  | 5 | 142.5 | 0 | [15 empty] | 142.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | 0 | [15 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-108090-44119-rev1 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-15 | SAND BLASTED, COATED AND WAITED ON PIPE TO DRY | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | 0 | [15 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | JODY | BROOM | Superintendent | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 |  | 26 |  | 2 | 2 | 213 | [16 empty] | 213 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | JODY | BROOM | Superintendent | 6 | 2 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 813 | 151 | 104 |  | 8 | 8 | 1068 | [16 empty] | 1068 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | TOME | KIRKLAND | Superintendent | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 187 |  | 26 |  | 2 | 2 | 213 | [16 empty] | 213 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | TOME | KIRKLAND | Superintendent | 6 | 2 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 813 | 151 | 104 |  | 8 | 8 | 1068 | [16 empty] | 1068 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | JAY | MASEY | Quality Assurance Inspector | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 840 | 151 | 104 |  | 8 | 8 | 1095 | [16 empty] | 1095 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | JUANITO | RODRIGUEZ | Safety Person | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | JUANITO | RODRIGUEZ | Safety Person | 6 | 2 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 644 | 151 | 104 |  | 8 | 8 | 899 | [16 empty] | 899 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | DANIEL | YOUNG | Truck Driver/CDL | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 107 |  | 26 |  | 2 | 2 | 133 | [16 empty] | 133 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | DANIEL | YOUNG | Truck Driver/CDL | 6 | 2 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 465 | 151 | 104 |  | 8 | 8 | 720 | [16 empty] | 720 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | KIM | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 197.6 |  | 26 |  | 2 | 2 | 223.6 | [16 empty] | 223.6 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | KIM | FORNALL | Project Coordinator | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | KIM | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 790.4 | 151 | 104 |  | 8 | 8 | 1045.4 | [16 empty] | 1045.4 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 572 | 151 | 420 |  | 10 | 10 | 1143 | [16 empty] | 1143 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | 0 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | 0 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Kubota UTV | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Kubota UTV | 8 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Kubota UTV | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | MATCHES CREW 7 | [7 empty] | Kubota UTV | 8 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44120-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-16 | WAITING ON EXCAVATOR TO BE MOB'D FROM DIG 1560 | BLAKE | HOLLEY | Foreman | 5 | 3 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | BLAKE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 670 | 151 | 104 |  | 8 | 8 | 925 | [16 empty] | 925 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44120-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-16 | WAITING ON EXCAVATOR TO BE MOB'D FROM DIG 1560 | RYAN | FARINELLI | Operator II | 4 | 3 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 495 | 151 | 91 |  | 7 | 7 | 737 | [16 empty] | 737 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44120-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-16 | WAITING ON EXCAVATOR TO BE MOB'D FROM DIG 1560 | GREG | MCMILLIAN | Laborer | 4 | 3 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | 15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 377 | 151 | 91 |  | 7 | 7 | 619 | [16 empty] | 619 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44120-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-16 | WAITING ON EXCAVATOR TO BE MOB'D FROM DIG 1560 | JEREMAINE | EVANS | Laborer | 4 | 3 |  | 1 | Tool Trailer | 7 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 377 | 151 | 35 |  | 7 | 7 | 563 | [16 empty] | 563 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44120-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-16 | WAITING ON EXCAVATOR TO BE MOB'D FROM DIG 1560 | DEMETRIUS | MCDONALD | Laborer | 4 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 377 | 151 | 112 |  | 7 | 7 | 640 | [16 empty] | 640 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44120-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-16 | WAITING ON EXCAVATOR TO BE MOB'D FROM DIG 1560 | JOSE | ORTIZ | Laborer | 4 | 3 |  | 1 | 40' Flatbed trailer or equal | 7 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 377 | 151 | 129.5 |  | 7 | 7 | 657.5 | [16 empty] | 657.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44120-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-16 | WAITING ON EXCAVATOR TO BE MOB'D FROM DIG 1560 | ROBERT | FOSTER | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 322 |  | 2 | 7 | 567 | [16 empty] | 567 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44120-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-16 | WAITING ON EXCAVATOR TO BE MOB'D FROM DIG 1560 | BRIAN | RANDLE | Truck Driver/CDL | 4 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX0563 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 430 | 151 | 633.5 |  | 7 | 7 | 1214.5 | [16 empty] | 1214.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44120-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-16 | WAITING ON EXCAVATOR TO BE MOB'D FROM DIG 1560 | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 7 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 199.5 |  |  | 7 | 199.5 | [16 empty] | 199.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44120-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-16 | DEMOB'D EXCAVATOR TO DIG 1549 | BLAKE | HOLLEY | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | BLAKE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44120-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-16 | DEMOB'D EXCAVATOR TO DIG 1549 | RYAN | FARINELLI | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44120-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-16 | DEMOB'D EXCAVATOR TO DIG 1549 | GREG | MCMILLIAN | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44120-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-16 | DEMOB'D EXCAVATOR TO DIG 1549 | JEREMAINE | EVANS | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44120-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-16 | DEMOB'D EXCAVATOR TO DIG 1549 | DEMETRIUS | MCDONALD | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 |  | 48 |  | 3 | 3 | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44120-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-16 | DEMOB'D EXCAVATOR TO DIG 1549 | JOSE | ORTIZ | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44120-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-16 | DEMOB'D EXCAVATOR TO DIG 1549 | ROBERT | FOSTER | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44120-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-16 | DEMOB'D EXCAVATOR TO DIG 1549 | BRIAN | RANDLE | Truck Driver/CDL | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0563 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 160.5 |  | 271.5 |  | 3 | 3 | 432 | [16 empty] | 432 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1560 - MC.400216.085 - 406.0371 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-86930-44120-rev0 | DIG-1560 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 285819.92 | 86930 | Central | KY | 406.0371 | 2020-10-16 | DEMOB'D EXCAVATOR TO DIG 1549 | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | KYLE | BONNEAU | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | KYLE | BONNEAU | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | CODY | GAXIOLA | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | CODY | GAXIOLA | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | GNT0705 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | [7 empty] | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [11 empty] | 18.5 |  |  |  | 18.5 |  |  | 1 | 18.5 | [16 empty] | 18.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RS9350 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RS9350 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | [16 empty] | 46 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | [7 empty] | Brush Hog | 2 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | [7 empty] | Brush Hog | 1 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | [7 empty] | Hammer Attachment | 2 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-28570-44120-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-16 | MOB'D SKIDSTEER, HAMMER, ETC TO DIG SITE. UNLOADED FLOAT AND MOWED PARKING LOT AT NEW SITE. | [7 empty] | Hammer Attachment | 1 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | KYLE | BONNEAU | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | KYLE | Rockshield | 16 | LnFt |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | KYLE | BONNEAU | Foreman | 6 | 1 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | KYLE | 2888 Coating | 12 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 544 | 151 | 91 | 0 | 7 | 7 | 786 | [16 empty] | 786 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | JESSE | BERTHIAUME | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JESSE | Sand | 5 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 123 |  | 26 | 0 | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | JESSE | BERTHIAUME | Operator II | 6 | 1 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 452 | 151 | 91 |  | 7 | 7 | 694 | [16 empty] | 694 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | JESSE | BERTHIAUME | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | CADEN | THOMPSON | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | CADEN | THOMPSON | Laborer | 6 | 2 |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 408 | 151 | 91 |  | 8 | 7 | 650 | [16 empty] | 650 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | JACOB | CAPITANO | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | JACOB | CAPITANO | Laborer | 6 | 1 |  | 1 | Tool Trailer | 7 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 345 | 151 | 35 |  | 7 | 7 | 531 | [16 empty] | 531 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | JACOB | CAPITANO | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | BROC | CALIGER | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | BROC | CALIGER | Laborer | 6 | 1 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 345 | 151 | 633.5 |  | 7 | 7 | 1129.5 | [16 empty] | 1129.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | BROC | CALIGER | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | CODY | GAXIOLA | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | CODY | GAXIOLA | Laborer | 6 | 1 |  | 1 | 40' Flatbed trailer or equal | 7 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 345 | 151 | 129.5 |  | 7 | 7 | 625.5 | [16 empty] | 625.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 2 | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 539 | 151 | 32 |  | 8 | 2 | 722 | [16 empty] | 722 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 112 |  | 1 | 7 | 184 | [16 empty] | 184 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Brush Hog | 2 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Brush Hog | 7 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9350 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS9350 | [11 empty] | 46 |  |  |  | 322 |  |  | 7 | 322 | [16 empty] | 322 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Hammer Attachment | 2 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Hammer Attachment | 7 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Padding Bucket | 5 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Padding Bucket | 3 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 7 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 199.5 |  |  | 7 | 199.5 | [16 empty] | 199.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLT | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLT | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-97640-44120-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-16 | HAD DETAILED JHA MEETING. PUMPED WATER AND WAITED FOR NDE UNTIL 9:45AM. BLASTED AND COATED ANOMALY. WAITED (6) HOURS FOR IT TO DRY. ONCE DRY, WE JEEPED PIPE AND BACKFILLED. | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLT | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | MICHAEL | RATLIFF | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAEL | 2888 Coating | 18 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | MICHAEL | RATLIFF | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MICHAEL | Brushes | 20 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | MICHAEL | RATLIFF | Foreman | 1 | 3 |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAEL | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 374 |  | 52 |  | 4 | 4 | 426 | [16 empty] | 426 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | SHAWN | ROSE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | SHAWN | ROSE | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | SHAWN | ROSE | Operator II | 1 | 3 |  |  | Pickup-F150 or F250 or equal | 4 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 310.5 |  | 52 |  | 4 | 4 | 362.5 | [16 empty] | 362.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | MICHAEL | ELLIOTT | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | MICHAEL | ELLIOTT | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | MICHAEL | ELLIOTT | Laborer | 1 | 3 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 236 |  | 52 |  | 4 | 4 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | SETH | RATLIFF | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | SETH | RATLIFF | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | SETH | RATLIFF | Laborer | 1 | 3 |  |  | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 236 |  | 20 |  | 4 | 4 | 256 | [16 empty] | 256 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | DAVID | RATLIFF | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | DAVID | RATLIFF | Laborer | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 235 | 151 | 80 |  | 5 | 5 | 466 | [16 empty] | 466 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | DAVID | RATLIFF | Laborer | 1 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 236 |  | 64 |  | 4 | 4 | 300 | [16 empty] | 300 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | TYLER | BIGG | Truck Driver/CDL | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 107 |  | 37 |  | 2 | 2 | 144 | [16 empty] | 144 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | TYLER | BIGG | Truck Driver/CDL | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 267.5 | 151 | 92.5 |  | 5 | 5 | 511 | [16 empty] | 511 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | TYLER | BIGG | Truck Driver/CDL | 1 | 3 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 269.5 |  | 74 |  | 4 | 4 | 343.5 | [16 empty] | 343.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | [16 empty] | 184 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Hammer Attachment | 5 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Hammer Attachment | 4 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Padding Bucket | 5 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Padding Bucket | 4 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLT | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLT | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLT | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Recoat - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Recoat | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 5 | HR | RAC | [11 empty] | 28.5 |  |  |  | 142.5 |  |  | 5 | 142.5 | [16 empty] | 142.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-108090-44120-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-16 | PIPE JEEPED AND FIXED. THEN BACKFILLED | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | WAYNE | SMITH | Foreman | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | WAYNE | Mats | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 174 |  | 26 | 0 | 2 | 2 | 200 | [16 empty] | 200 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | WAYNE | SMITH | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | WAYNE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | RICHARD | SHOEMAKE | Operator II | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 144.5 |  | 26 |  | 2 | 2 | 170.5 | [16 empty] | 170.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | RICHARD | SHOEMAKE | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | OJ | SEALS | Laborer | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 110 |  | 26 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | OJ | SEALS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | JAMES | KERVIN | Laborer | 1 | 1 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 110 |  | 5 |  | 2 | 1 | 115 | [16 empty] | 115 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | JAMES | KERVIN | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | RICHARD | ADKINS | Laborer | 1 | 1 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 110 |  | 28.5 |  | 2 | 1 | 138.5 | [16 empty] | 138.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | RICHARD | ADKINS | Laborer |  | 1 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 63 |  | 28.5 |  | 1 | 1 | 91.5 | [16 empty] | 91.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | NICHOLAS | BLANCO | Laborer | 1 | 1 |  |  | Hammer Attachment | 3 | HR | RAHA0141 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 110 |  | 0 |  | 2 | 3 | 110 | [16 empty] | 110 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | NICHOLAS | BLANCO | Laborer |  | 1 |  |  | Hammer Attachment | 2 | HR | RAHA0141 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 63 |  | 0 |  | 1 | 2 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | BARRETT | WISE | Laborer | 1 | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 110 |  | 90.5 |  | 2 | 1 | 200.5 | [16 empty] | 200.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | BARRETT | WISE | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | STEVE | CLARK | Truck Driver/CDL | 3 | 2 |  | 1 | Padding Bucket | 1 | HR | RPB2004 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 304.5 | 151 | 0 |  | 5 | 1 | 455.5 | [16 empty] | 455.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [11 empty] | 16 |  |  |  | 80 |  |  | 5 | 80 | [16 empty] | 80 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44120-rev1 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-16 | MOB'D IN ON SITE. HAULED IN 4 MATS. | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | WAYNE | SMITH | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | WAYNE | Fertilizer | 240 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | WAYNE | SMITH | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | WAYNE | Lime | 6 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | WAYNE | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | WAYNE | Seed Mix | 20 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | RICHARD | SHOEMAKE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RICHARD | Straw Bales | 25 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 123 |  | 26 | 0 | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | RICHARD | SHOEMAKE | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | RICHARD | SHOEMAKE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | OJ | SEALS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | OJ | SEALS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 39 |  | 4 | 3 | 378 | [16 empty] | 378 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | JAMES | KERVIN | Laborer | 2 |  |  |  | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 20 |  | 2 | 4 | 114 | [16 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | JAMES | KERVIN | Laborer | 4 |  |  | 1 | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 15 |  | 4 | 3 | 354 | [16 empty] | 354 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | JAMES | KERVIN | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | RICHARD | ADKINS | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 230 |  | 2 | 5 | 324 | [16 empty] | 324 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | RICHARD | ADKINS | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | RICHARD | ADKINS | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | NICHOLAS | BLANCO | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 271.5 |  | 2 | 3 | 365.5 | [16 empty] | 365.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | NICHOLAS | BLANCO | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | NICHOLAS | BLANCO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | BARRETT | WISE | Laborer | 2 |  |  |  | Padding Bucket | 4 | HR | RPB2004 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 94 |  | 0 |  | 2 | 4 | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | BARRETT | WISE | Laborer | 4 |  |  | 1 | Padding Bucket | 4 | HR | RPB2004 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 188 | 151 | 0 |  | 4 | 4 | 339 | [16 empty] | 339 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | BARRETT | WISE | Laborer | 1 |  |  |  | Padding Bucket | 1 | HR | RPB2004 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 47 |  | 0 |  | 1 | 1 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | STEVE | CLARK | Truck Driver/CDL | 5 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 |  | 80 |  | 5 | 5 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | Hammer Attachment | 2 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Backfill - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Backfill | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLT9317 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLT9317 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1544 - MC.400216.085 - 354.4403 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-3990-44120-rev0 | DIG-1544 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 12651.39 | 3390 | Central | KY | 354.4403 | 2020-10-16 | FINISHED BACKFILL, LIME, FERTILIZED, SEEDED AND MULCHED. DEMOB'D. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLT9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | CALEB | HOLTON | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | CALEB | Silt Fence | 250 | Ft | BRAND SAFWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | BRAND SAFWAY | [15 empty] | 499 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | CALEB | HOLTON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | Safety Fence | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | CALEB | HOLTON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | Sand | 4 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | ZACH | FRANKLIN | Operator II | 5 |  |  |  | Pickup-F150 or F250 or equal | 5 | HR | ZACH | T-Posts | 8 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 307.5 |  | 65 | 0 | 5 | 5 | 372.5 | [16 empty] | 372.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | MICHAEL | ANISZEWSKI | Laborer | 5 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4155 | T-Post Caps | 8 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 90.5 | 0 | 235 |  | 452.5 | 0 | 5 | 5 | 687.5 | [16 empty] | 687.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | BOLDBAATAR | ZORIGT | Laborer | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 235 | 151 | 80 |  | 5 | 5 | 466 | [16 empty] | 466 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | BOLDBAATAR | ZORIGT | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | JORDAN | WIGGINS | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | JORDAN | WIGGINS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | DAVID | KNOTTS | Laborer | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 235 | 151 | 80 |  | 5 | 5 | 466 | [16 empty] | 466 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | DAVID | KNOTTS | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | TANNER | BRITT | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | TANNER | BRITT | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | ALDO | REYNA | Truck Driver/CDL | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8664 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 267.5 | 151 | 230 |  | 5 | 5 | 648.5 | [16 empty] | 648.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | ALDO | REYNA | Truck Driver/CDL | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 107 |  | 92 |  | 2 | 2 | 199 | [16 empty] | 199 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Hammer Attachment | 5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Padding Bucket | 5 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 5 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 142.5 |  |  | 5 | 142.5 | [16 empty] | 142.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLT | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLT | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23260-44120-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-16 | TOP SOILED DIG. PROBED BOTH SIDES OF PIPE AND MARKED 2' OFF. STARTED EXCAVATION. DUG DOWN 3' AND HIT ROCK. JACK HAMMERED ROCK AWAY FROM PIPE. DUG DOWN 2' UNDER PIPE, CLEANED HOLE OUT. SAFWAY CAME OUT AND KNOCKED COATING OFF PIPE. NDE MADE ASSESSMENTS. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 5 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 122.5 |  |  | 5 | 122.5 | [16 empty] | 122.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | CALEB | HOLTON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | Silt Fence | 250 | Ft | BRAND SAFWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | BRAND SAFWAY | [15 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | CALEB | HOLTON | Foreman | 1 | 4 |  |  | Pickup-F150 or F250 or equal | 5 | HR | CALEB | Safety Fence | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 474 |  | 65 | 0 | 5 | 5 | 539 | [16 empty] | 539 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | Sand | 4 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | ZACH | FRANKLIN | Operator II | 3 | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | ZACH | T-Posts | 8 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 433.5 | 151 | 39 | 0 | 6 | 3 | 623.5 | [16 empty] | 623.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | ZACH | FRANKLIN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | ZACH | T-Post Caps | 8 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 83 |  | 13 | 0 | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | MICHAEL | ANISZEWSKI | Laborer | 3 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 330 | 151 | 64 |  | 6 | 4 | 545 | [16 empty] | 545 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | BOLDBAATAR | ZORIGT | Laborer | 1 | 3 |  |  | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 236 |  | 20 |  | 4 | 4 | 256 | [16 empty] | 256 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | BOLDBAATAR | ZORIGT | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | JORDAN | WIGGINS | Laborer | 1 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 236 |  | 64 |  | 4 | 4 | 300 | [16 empty] | 300 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | JORDAN | WIGGINS | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | DAVID | KNOTTS | Laborer | 1 | 3 |  |  | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 236 |  | 74 |  | 4 | 4 | 310 | [16 empty] | 310 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | DAVID | KNOTTS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | TANNER | BRITT | Laborer | 1 | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 236 |  | 184 |  | 4 | 4 | 420 | [16 empty] | 420 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | TANNER | BRITT | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | ALDO | REYNA | Truck Driver/CDL | 1 | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4155 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 269.5 |  | 543 |  | 4 | 6 | 812.5 | [16 empty] | 812.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | ALDO | REYNA | Truck Driver/CDL |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 72 |  | 90.5 |  | 1 | 1 | 162.5 | [16 empty] | 162.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Hammer Attachment | 6 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Padding Bucket | 6 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 5 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 142.5 |  |  | 5 | 142.5 | [16 empty] | 142.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLT | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLT | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-23770-44120-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-16 | TOP SOILED DIG. MARKED SIDES OF PIPE. PROBED EACH SIDE AND MARKED 2' AWAY. STARTED EXCAVATING. DUG DOWN 2 FEET BELOW PIPE. AFTER EXCAVATION, SAFWAY KNOCKED COATING OFF PIPE. NDE ASSESSED ANOMALY AS WELL. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 5 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 122.5 |  |  | 5 | 122.5 | [16 empty] | 122.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | BARKLEY | BROWN | Foreman | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 | 151 | 13 |  | 1 | 1 | 238 | [16 empty] | 238 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | MATTHEW | LINDLEY | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 | 151 | 13 |  | 1 | 1 | 225.5 | [16 empty] | 225.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | WAYLON | GREEN | Laborer | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 | 151 | 13 |  | 1 | 1 | 211 | [16 empty] | 211 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | JOSE | VALLES | Laborer | 1 |  |  | 1 | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 | 151 | 5 |  | 1 | 1 | 203 | [16 empty] | 203 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | LUTHER | LINDLEY | Laborer | 1 |  |  | 1 | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 | 151 | 18.5 |  | 1 | 1 | 216.5 | [16 empty] | 216.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | MARCELO | GOMEZ | Laborer | 1 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 | 151 | 46 |  | 1 | 1 | 244 | [16 empty] | 244 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | ANTHONY | MORENO | Laborer | 1 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 | 151 | 90.5 |  | 1 | 1 | 288.5 | [16 empty] | 288.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 | 151 | 16 |  | 1 | 1 | 220.5 | [16 empty] | 220.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-50610-44120-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-16 | No Comments | [7 empty] | Water Pump ( up to 2") | 1 | HR | 2INP | [11 empty] | 6 |  |  |  | 6 |  |  | 1 | 6 | [16 empty] | 6 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Sand | 1 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | MATTHEW | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | MATTHEW | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | LUTHER | LINDLEY | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | LUTHER | LINDLEY | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | MARCELO | GOMEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | MARCELO | GOMEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373B | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373B | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373B | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44120-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-16 | No Comments | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | SBP | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Sand | 9 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | T-Posts | 6 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | MATTHEW | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | Safety Fence | 175 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 61.5 |  | 13 | 0 | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | Silt Fence | 150 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 83 |  | 13 | 0 | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 2829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 2829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373C | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373C | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44120-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-16 | No Comments | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | SBP | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | T-Posts | 6 | EA |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | BARKLEY | BROWN | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Safety Fence | 175 | FT |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | Silt Fence | 150 | FT |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 83 |  | 13 | 0 | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | MATTHEW | LINDLEY | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | WAYLON | GREEN | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | LUTHER | LINDLEY | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373D | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | ANTHONY | MORENO | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373D | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-58100-44120-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-16 | No Comments | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | URIEL | VALENCIA | Foreman | 2 |  |  | 1 |  |  |  |  | Safety Fence | 400 | Ft |  |  |  |  | 74 | 100 | 0 | 151 |  | 0 | 148 | 151 |  | 0 | 2 |  | 299 | [16 empty] | 299 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | URIEL | VALENCIA | Foreman | 6 | 4 | [6 empty] | Silt Fence | 400 | Ft |  |  |  |  | 74 | 100 | 0 | 151 |  | 0 | 844 |  |  | 0 | 10 |  | 844 | [16 empty] | 844 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | HECTOR | VALDEZ NEVAREZ | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | T-Posts | 20 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 123 | 151 | 26 | 0 | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | HECTOR | VALDEZ NEVAREZ | Operator II | 6 | 4 |  |  | Pickup-F150 or F250 or equal | 10 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 701 |  | 130 |  | 10 | 10 | 831 | [16 empty] | 831 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 6 | 4 |  |  | Pickup-F150 or F250 or equal | 10 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 534 |  | 130 |  | 10 | 10 | 664 | [16 empty] | 664 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | ASTOLFO | FLORES | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | ASTOLFO | FLORES | Laborer | 6 | 4 |  |  | Pickup-F150 or F250 or equal | 10 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 534 |  | 130 |  | 10 | 10 | 664 | [16 empty] | 664 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | IVAN | MADRID | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | IVAN | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | IVAN | MADRID | Laborer | 6 | 4 |  |  | Pickup-F150 or F250 or equal | 10 | HR | IVAN | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 534 |  | 130 |  | 10 | 10 | 664 | [16 empty] | 664 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | ROBERTO | RODRIGUEZ | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | ROBERTO | RODRIGUEZ | Laborer | 6 | 4 |  |  | Tool Trailer | 10 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 534 |  | 50 |  | 10 | 10 | 584 | [16 empty] | 584 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | JOEL | VALDEZ NEVAREZ | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | JOEL | VALDEZ NEVAREZ | Laborer | 6 | 4 |  |  | 40' Flatbed trailer or equal | 10 | HR | GNT | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 534 |  | 185 |  | 10 | 10 | 719 | [16 empty] | 719 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | HECTOR | QUINTANA VALDEZ | Laborer | 2 |  |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 94 | 151 | 57 |  | 2 | 2 | 302 | [16 empty] | 302 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | HECTOR | QUINTANA VALDEZ | Laborer | 6 | 4 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 534 |  | 285 |  | 10 | 10 | 819 | [16 empty] | 819 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 192 |  | 12 | 12 | 1059 | [16 empty] | 1059 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44120-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-16 | INSTALLED 400' SILT FENCE AROUND EXCAVATION SITE. PULLED A FOOT OF TOP SOIL AND BEGAN EXCAVATING. TOUCH UP WORK TO BE COMPLETED IN THE MORNING TO FINISH EXCAVATION. EXCAVATION WAS FENCED OFF FOR THE NIGHT. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | GARRETT | DICKSON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 13 |  | 2 | 1 | 161 | [16 empty] | 161 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | GARRETT | DICKSON | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 13 |  | 3 | 1 | 235 | [16 empty] | 235 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | GARRETT | DICKSON | Foreman | 3 | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 422 | 151 | 26 |  | 5 | 2 | 599 | [16 empty] | 599 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 13 |  | 2 | 1 | 213 | [16 empty] | 213 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | RYAN | COLEMAN | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | RYAN | COLEMAN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | JACOB | GORDON | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 16 |  | 2 | 1 | 110 | [16 empty] | 110 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | JACOB | GORDON | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 |  | 16 |  | 3 | 1 | 157 | [16 empty] | 157 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | JACOB | GORDON | Laborer | 3 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 267 | 151 | 32 |  | 5 | 2 | 450 | [16 empty] | 450 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | JACOB | GORDON | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | ZACH | POWDERS | Laborer | 2 |  |  |  | Hammer Attachment | 1 | HR | RHAA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 94 |  | 0 |  | 2 | 1 | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | ZACH | POWDERS | Laborer | 1 |  |  |  | Hammer Attachment | 1 | HR | RHAA | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 47 |  | 0 |  | 1 | 1 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | COLTON | ROBERTS | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 90.5 |  | 2 | 1 | 184.5 | [16 empty] | 184.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | COLTON | ROBERTS | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 90.5 |  | 3 | 1 | 231.5 | [16 empty] | 231.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | COLTON | ROBERTS | Laborer | 3 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 267 | 151 | 181 |  | 5 | 2 | 599 | [16 empty] | 599 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | JUAN | DURAN | Laborer | 2 |  |  |  | Padding Bucket | 1 | HR | RPB | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 94 |  | 0 |  | 2 | 1 | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | JUAN | DURAN | Laborer | 1 |  |  |  | Padding Bucket | 1 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 47 |  | 0 |  | 1 | 1 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | TANNER | BRUMMETT | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | [16 empty] | 94 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | TANNER | BRUMMETT | Laborer | 1 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 47 |  |  |  | 1 |  | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | IAIN | ALLRED | Truck Driver/CDL | 2 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 107 |  |  |  | 2 |  | 107 | [16 empty] | 107 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | IAIN | ALLRED | Truck Driver/CDL | 1 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 53.5 |  |  |  | 1 |  | 53.5 | [16 empty] | 53.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | [7 empty] | Hammer Attachment | 1 | HR | RHAA | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | [7 empty] | Hammer Attachment | 2 | HR | RHAA | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | [7 empty] | Tool Trailer | 1 | HR | UTT2179 | [11 empty] | 5 |  |  |  | 5 |  |  | 1 | 5 | [16 empty] | 5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | [7 empty] | Tool Trailer | 1 | HR | UTT2179 | [11 empty] | 5 |  |  |  | 5 |  |  | 1 | 5 | [16 empty] | 5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | [7 empty] | Tool Trailer | 2 | HR | UTT2179 | [11 empty] | 5 |  |  |  | 10 |  |  | 2 | 10 | [16 empty] | 10 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44120-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-16 | WAITED FOR DAYLIGHT TO LOAD EQUIPMENT. DEMOB'D EQUIPMENT TO 1474. COATING CREW WAITING FOR NDE TO ARRIVE. ONCE NDE ARRIVED HE NEEDED ANOTHER 1.5' OF DIRT REMOVED. THEN NEEDED ANOTHER 5-10 INCHES REMOVED TO LOOK AT COATING. THEN CREW ON STANBY FOR WAITING ON EQUIPMENT. ONCE EQUIPMENT WAS BACK ON SITE. CLEANED UP SITE AND PUT UP SAFETY FENCE | [7 empty] | Tool Trailer | 1 | HR | UTT2179 | [11 empty] | 5 |  |  |  | 5 |  |  | 1 | 5 | [16 empty] | 5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | RYAN | COLEMAN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | RYAN | COLEMAN | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | RYAN | COLEMAN | Operator II | 1 | 3 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 310.5 | 151 | 52 |  | 4 | 4 | 513.5 | [16 empty] | 513.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | RYAN | COLEMAN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | JACOB | GORDON | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | ZACH | POWDERS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | ZACH | POWDERS | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | ZACH | POWDERS | Laborer | 1 | 3 |  | 1 | Tool Trailer | 4 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 236 | 151 | 20 |  | 4 | 4 | 407 | [16 empty] | 407 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | ZACH | POWDERS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | COLTON | ROBERTS | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | JUAN | DURAN | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | JUAN | DURAN | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 |  | 48 |  | 3 | 3 | 189 | [16 empty] | 189 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | JUAN | DURAN | Laborer | 1 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 236 | 151 | 64 |  | 4 | 4 | 451 | [16 empty] | 451 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | JUAN | DURAN | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | TANNER | BRUMMETT | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | TANNER | BRUMMETT | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | TANNER | BRUMMETT | Laborer | 1 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 236 | 151 | 362 |  | 4 | 4 | 749 | [16 empty] | 749 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | TANNER | BRUMMETT | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | Hammer Attachment | 1 | HR | RHAB | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 53.5 |  | 0 |  | 1 | 1 | 53.5 | [16 empty] | 53.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | IAIN | ALLRED | Truck Driver/CDL | 3 |  |  |  | Hammer Attachment | 3 | HR | RHAB | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 160.5 |  | 0 |  | 3 | 3 | 160.5 | [16 empty] | 160.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | IAIN | ALLRED | Truck Driver/CDL | 1 | 3 |  | 1 | Hammer Attachment | 4 | HR | RHAB | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 269.5 | 151 | 0 |  | 4 | 4 | 420.5 | [16 empty] | 420.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | Hammer Attachment | 1 | HR | RHAB | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 72 |  | 0 |  | 1 | 1 | 72 | [16 empty] | 72 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | [7 empty] | Padding Bucket | 3 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | [7 empty] | Padding Bucket | 4 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-31790-44120-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-16 | MOB'D EQUIPMENT FROM DIG 1473. DAYLIGHTING PIPE IN THREE SEPARATE PLACES ON THE LINE. ON STANDBY WAITING FOR EQUIPMENT. | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JODY | BROOM | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JODY | BROOM | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JODY | BROOM | Superintendent |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 378 | 151 | 39 |  | 3 | 3 | 568 | [16 empty] | 568 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JODY | BROOM | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JODY | BROOM | Superintendent |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 126 |  | 13 |  | 1 | 1 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | TOME | KIRKLAND | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | TOME | KIRKLAND | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | TOME | KIRKLAND | Superintendent |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 378 | 151 | 39 |  | 3 | 3 | 568 | [16 empty] | 568 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | TOME | KIRKLAND | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | TOME | KIRKLAND | Superintendent |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 126 |  | 13 |  | 1 | 1 | 139 | [16 empty] | 139 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 | 151 | 26 |  | 2 | 2 | 387 | [16 empty] | 387 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JAY | MASEY | Quality Assurance Inspector | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 315 |  | 39 |  | 3 | 3 | 354 | [16 empty] | 354 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JAY | MASEY | Quality Assurance Inspector | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 105 |  | 13 |  | 1 | 1 | 118 | [16 empty] | 118 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JUANITO | RODRIGUEZ | Safety Person |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 | 151 | 26 |  | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JUANITO | RODRIGUEZ | Safety Person |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JUANITO | RODRIGUEZ | Safety Person |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JUANITO | RODRIGUEZ | Safety Person |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JUANITO | RODRIGUEZ | Safety Person |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | DANIEL | YOUNG | Truck Driver/CDL |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 |  | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | DANIEL | YOUNG | Truck Driver/CDL |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 | 151 | 26 |  | 2 | 2 | 321 | [16 empty] | 321 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | DANIEL | YOUNG | Truck Driver/CDL |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 216 |  | 39 |  | 3 | 3 | 255 | [16 empty] | 255 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | DANIEL | YOUNG | Truck Driver/CDL |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 |  | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | DANIEL | YOUNG | Truck Driver/CDL |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | DANIEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 72 |  | 13 |  | 1 | 1 | 85 | [16 empty] | 85 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [7 empty] | 98.8 | 0 | 0 | 151 | 24.5 |  | 197.6 |  | 49 |  | 2 | 2 | 246.6 | [16 empty] | 246.6 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | KIM | FORNALL | Project Coordinator | 2 |  |  | 1 | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [7 empty] | 98.8 | 0 | 0 | 151 | 24.5 |  | 197.6 | 151 | 49 |  | 2 | 2 | 397.6 | [16 empty] | 397.6 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | KIM | FORNALL | Project Coordinator | 3 |  |  |  | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 3 | HR | 0 | [7 empty] | 98.8 | 0 | 0 | 151 | 24.5 |  | 296.4 |  | 73.5 |  | 3 | 3 | 369.9 | [16 empty] | 369.9 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [7 empty] | 98.8 | 0 | 0 | 151 | 24.5 |  | 197.6 |  | 49 |  | 2 | 2 | 246.6 | [16 empty] | 246.6 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | KIM | FORNALL | Project Coordinator | 1 |  |  |  | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | 0 | [7 empty] | 98.8 | 0 | 0 | 151 | 24.5 |  | 98.8 |  | 24.5 |  | 1 | 1 | 123.3 | [16 empty] | 123.3 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | MICHAEL | GOSS | Truck Driver/CDL |  | 12 |  | 1 | Tractor/Semi | 12 | HR | 1368 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 864 | 151 | 504 |  | 12 | 12 | 1519 | [16 empty] | 1519 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Tractor/Semi | 10 | HR | 1376 | [7 empty] | 53.5 | 72 | 0 | 151 | 42 |  | 720 | 151 | 420 |  | 10 | 10 | 1291 | [16 empty] | 1291 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Lowboy Trailer | 12 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 222 |  |  | 12 | 222 | [16 empty] | 222 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Pickup-F150 or F250 or equal | 12 | HR | KIM | [11 empty] | 13 |  |  |  | 156 |  |  | 12 | 156 | [16 empty] | 156 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 3 | HR | 0 | [11 empty] | 24.5 |  |  |  | 73.5 |  |  | 3 | 73.5 | [16 empty] | 73.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | 0 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | 0 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Kubota UTV | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Kubota UTV | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Kubota UTV | 3 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Kubota UTV | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Kubota UTV | 1 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Kubota UTV | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Kubota UTV | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Kubota UTV | 3 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | MATCHES CREW 8 | [7 empty] | Kubota UTV | 3 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | BLAKE | HOLLEY | Foreman |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | BLAKE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 | 151 | 52 |  | 4 | 4 | 603 | [16 empty] | 603 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | BLAKE | HOLLEY | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BLAKE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | BLAKE | HOLLEY | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BLAKE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | RYAN | FARINELLI | Operator II |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 | 151 | 52 |  | 4 | 4 | 535 | [16 empty] | 535 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | RYAN | FARINELLI | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | RYAN | FARINELLI | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | GREG | MCMILLIAN | Laborer |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 | 151 | 52 |  | 4 | 4 | 455 | [16 empty] | 455 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | GREG | MCMILLIAN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | GREG | MCMILLIAN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | JEREMAINE | EVANS | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | JEREMAINE | EVANS | Laborer |  | 4 |  | 1 | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 | 151 | 20 |  | 4 | 4 | 423 | [16 empty] | 423 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | JEREMAINE | EVANS | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | DEMETRIUS | MCDONALD | Laborer |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 252 |  | 64 |  | 4 | 4 | 316 | [16 empty] | 316 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | DEMETRIUS | MCDONALD | Laborer |  | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 252 | 151 | 64 |  | 4 | 4 | 467 | [16 empty] | 467 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | DEMETRIUS | MCDONALD | Laborer |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 252 |  | 64 |  | 4 | 4 | 316 | [16 empty] | 316 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | JOSE | ORTIZ | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | JOSE | ORTIZ | Laborer |  | 4 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 | 151 | 74 |  | 4 | 4 | 477 | [16 empty] | 477 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | JOSE | ORTIZ | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | ROBERT | FOSTER | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | ROBERT | FOSTER | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | ROBERT | FOSTER | Laborer |  | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 | 151 | 184 |  | 4 | 4 | 587 | [16 empty] | 587 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | BRIAN | RANDLE | Truck Driver/CDL |  | 4 |  |  | Brush Hog | 4 | HR | RBH | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 288 |  | 0 |  | 4 | 4 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | BRIAN | RANDLE | Truck Driver/CDL |  | 4 |  |  | Brush Hog | 4 | HR | RBH | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 288 |  | 0 |  | 4 | 4 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | BRIAN | RANDLE | Truck Driver/CDL |  | 4 |  | 1 | Brush Hog | 4 | HR | RBH | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 288 | 151 | 0 |  | 4 | 4 | 439 | [16 empty] | 439 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Hammer Attachment | 4 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Hammer Attachment | 4 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Hammer Attachment | 4 | HR | RHA | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Padding Bucket | 4 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Padding Bucket | 4 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Padding Bucket | 4 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-18890-44121-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-17 | WAITING ON EXCAVATOR. POT HOLED AND THEN STARTED EXCAVATION. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | Silt Fence | 50 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | Straw Bales | 8 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | KYLE | BONNEAU | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | KYLE | Safety Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 600 | 151 | 65 | 0 | 6 | 5 | 816 | [16 empty] | 816 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | JESSE | BERTHIAUME | Operator II |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 498 | 151 | 65 |  | 6 | 5 | 714 | [16 empty] | 714 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | CADEN | THOMPSON | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | CADEN | THOMPSON | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 65 |  | 6 | 5 | 594 | [16 empty] | 594 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | JACOB | CAPITANO | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | JACOB | CAPITANO | Laborer |  | 6 |  | 1 | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 | 151 | 25 |  | 6 | 5 | 554 | [16 empty] | 554 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | BROC | CALIGER | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | BROC | CALIGER | Laborer |  | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF1040 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 378 | 151 | 80 |  | 6 | 5 | 609 | [16 empty] | 609 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | CODY | GAXIOLA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | CODY | GAXIOLA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | CODY | GAXIOLA | Laborer |  | 6 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 378 | 151 | 184 |  | 6 | 4 | 713 | [16 empty] | 713 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 72 |  | 18.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 6 |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0705 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 432 | 151 | 92.5 |  | 6 | 5 | 675.5 | [16 empty] | 675.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Brush Hog | 1 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Prep | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Brush Hog | 1 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Brush Hog | 5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Hammer Attachment | 1 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Hammer Attachment | 5 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Padding Bucket | 5 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 5 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 142.5 |  |  | 5 | 142.5 | [16 empty] | 142.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLT | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-28570-44121-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-17 | MOB'D TO SITE. MOED ROW AND M SCOPED. MOVED TOPSOIL, POTHOLED AND STARTED EXCAVATING | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLT | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | KYLE | BONNEAU | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | KYLE | Straw Bales | 16 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | Fertilizer | 100 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | JESSE | BERTHIAUME | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | JESSE | Seed Mix | 50 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 249 |  | 39 | 0 | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | Silt Fence | 50 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 83 |  | 13 | 0 | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | CADEN | THOMPSON | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | CADEN | THOMPSON | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | JACOB | CAPITANO | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | JACOB | CAPITANO | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | BROC | CALIGER | Laborer |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF1040 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 189 |  | 48 |  | 3 | 3 | 237 | [16 empty] | 237 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | BROC | CALIGER | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | CODY | GAXIOLA | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 55.5 |  | 2 | 3 | 181.5 | [16 empty] | 181.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | CODY | GAXIOLA | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9350 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 216 |  | 138 |  | 3 | 3 | 354 | [16 empty] | 354 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 72 |  | 46 |  | 1 | 1 | 118 | [16 empty] | 118 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Brush Hog | 3 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Brush Hog | 1 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Hammer Attachment | 3 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Hammer Attachment | 1 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Padding Bucket | 3 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Padding Bucket | 1 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLT | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1562 - MC.400216.085 - 413.0587 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-97640-44121-rev0 | DIG-1562 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 322856.96 | 97640 | Central | KY | 413.0587 | 2020-10-17 | SPREAD TOPSOIL AND SEEDED AND MULCHED. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLT | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | MICHAEL | RATLIFF | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RATLIFF | Seed Mix | 150 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 1000 | 151 | 130 | 0 | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | SHAWN | ROSE | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | SHAWN | Fertilizer | 100 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 830 | 151 | 130 | 0 | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | MICHAEL | ELLIOTT | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15363 | Rockshield | 40 | LnFt |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 630 | 151 | 130 | 0 | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | SETH | RATLIFF | Laborer |  | 10 |  | 1 | Tool Trailer | 10 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 630 | 151 | 50 |  | 10 | 10 | 831 | [16 empty] | 831 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | DAVID | RATLIFF | Laborer |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1996 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 630 | 151 | 160 |  | 10 | 10 | 941 | [16 empty] | 941 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | TYLER | BIGG | Truck Driver/CDL |  | 14 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT447 | [7 empty] | 53.5 | 72 | 0 | 151 | 18.5 |  | 1008 | 151 | 185 |  | 14 | 10 | 1344 | [16 empty] | 1344 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [16 empty] | 460 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | [7 empty] | Hammer Attachment | 10 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | [7 empty] | Padding Bucket | 10 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | RAC | [11 empty] | 28.5 |  |  |  | 285 |  |  | 10 | 285 | [16 empty] | 285 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-108090-44121-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-17 | FINISH DIRT WORK. SEEDED, MULCHED. GOT EVERYTHING READY TO MOVE TOMORROW. | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | WAYNE | SMITH | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | WAYNE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | RICHARD | SHOEMAKE | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RICHARD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | OJ | SEALS | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | JAMES | KERVIN | Laborer |  | 10 |  | 1 | Tool Trailer | 10 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 630 | 151 | 50 |  | 10 | 10 | 831 | [16 empty] | 831 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | RICHARD | ADKINS | Laborer |  | 10 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 630 | 151 | 460 |  | 10 | 10 | 1241 | [16 empty] | 1241 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | NICHOLAS | BLANCO | Laborer |  | 10 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 630 | 151 | 905 |  | 10 | 10 | 1686 | [16 empty] | 1686 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | BARRETT | WISE | Laborer |  | 10 |  | 1 | Hammer Attachment | 10 | HR | RHA0141 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 630 | 151 | 0 |  | 10 | 10 | 781 | [16 empty] | 781 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | [7 empty] | Padding Bucket | 10 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 10 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 285 |  |  | 10 | 285 | [16 empty] | 285 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-1940-44121-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-17 | DUG BACK, DIG ANOTHER 15'. HAD TO HAMMER ROCK WITH HOE AND JACK HAMMER AND BY HAND | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT9317 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | Sand | 5 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 32 |  | 2 | 2 | 158 | [16 empty] | 158 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | BOLDBAATAR | ZORIGT | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | JORDAN | WIGGINS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | DAIVD | KNOTTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLT | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44121-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-17 | PUMPED WATER FROM BELLHOLE AND DUG BACK A LITTLE BIT MORE ON EACH SIDE. SANDBLASTED FLASH RUST FROM PROPOSED ANOMALY. PUT CLOCKSPRINGS OVER PIPE | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | 0 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 32 |  | 2 | 2 | 158 | [16 empty] | 158 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | BOLDBAATAR | ZORIGT | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | JORDAN | WIGGINS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | DAIVD | KNOTTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLT | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1467 - MC.400216.032 - 646.441 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23260-44121-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-17 | AFTER JSA AND WHILE NDE WAS DOING ASSESSMENT. MOB'D TRACK HOE TO DIG 1472 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | CALEB | HOLTON | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | MICHAEL | ANISZEWSKI | Laborer |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 252 |  | 64 |  | 4 | 4 | 316 | [16 empty] | 316 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | BOLDBAATAR | ZORIGT | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | JORDAN | WIGGINS | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | DAIVD | KNOTTS | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | [7 empty] | Padding Bucket | 4 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | RAC4049 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLT | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1468 - MC.400216.032 - 646.814 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-23770-44121-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-17 | NDE CONDUCTED ASSESSMENT | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | CALEB | HOLTON | Foreman |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 | 151 | 39 |  | 3 | 3 | 490 | [16 empty] | 490 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | ZACH | FRANKLIN | Operator II |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | ZACH | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 996 | 151 | 156 |  | 12 | 12 | 1303 | [16 empty] | 1303 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 32 |  | 2 | 2 | 158 | [16 empty] | 158 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 | 151 | 32 |  | 2 | 2 | 309 | [16 empty] | 309 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | BOLDBAATAR | ZORIGT | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | BOLDBAATAR | ZORIGT | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | JORDAN | WIGGINS | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 160 |  | 2 | 10 | 286 | [16 empty] | 286 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | JORDAN | WIGGINS | Laborer |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 | 151 | 32 |  | 2 | 2 | 309 | [16 empty] | 309 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | DAVID | KNOTTS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Access - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Site Access | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | DAVID | KNOTTS | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | TANNER | BRITT | Laborer |  | 12 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 756 | 151 | 92 |  | 12 | 2 | 999 | [16 empty] | 999 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1472 - MC.400216.032 - 649.858 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-27760-44121-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-17 | MOB'D AND SITE ACCESS WORK. | ALDO | REYNA | Truck Driver/CDL |  | 12 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 53.5 | 72 | 0 | 151 | 46 |  | 864 | 151 | 92 |  | 12 | 2 | 1107 | [16 empty] | 1107 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | URIEL | VALENCIA | Foreman |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | URIEL | Sand | 2 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 400 | 151 | 52 | 0 | 4 | 4 | 603 | [16 empty] | 603 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | URIEL | VALENCIA | Foreman |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | URIEL | Silt Fence | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 600 |  | 78 | 0 | 6 | 6 | 678 | [16 empty] | 678 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | URIEL | VALENCIA | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | URIEL | Safety Fence | 400 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | HECTOR | VALDEZ NEVAREZ | Operator II |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 | 151 | 52 |  | 4 | 4 | 535 | [16 empty] | 535 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | HECTOR | VALDEZ NEVAREZ | Operator II |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 498 |  | 78 |  | 6 | 6 | 576 | [16 empty] | 576 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | HECTOR | VALDEZ NEVAREZ | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 | 151 | 52 |  | 4 | 4 | 455 | [16 empty] | 455 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 |  | 78 |  | 6 | 6 | 456 | [16 empty] | 456 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | ASTOLFO | FLORES | Laborer |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 | 151 | 52 |  | 4 | 4 | 455 | [16 empty] | 455 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | ASTOLFO | FLORES | Laborer |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 |  | 78 |  | 6 | 6 | 456 | [16 empty] | 456 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | ASTOLFO | FLORES | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15349 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | IVAN | MADRID | Laborer |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | IVAN | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 | 151 | 52 |  | 4 | 4 | 455 | [16 empty] | 455 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | IVAN | MADRID | Laborer |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | IVAN | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 |  | 78 |  | 6 | 6 | 456 | [16 empty] | 456 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | IVAN | MADRID | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | IVAN | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | ROBERTO | RODRIGUEZ | Laborer |  | 4 |  | 1 | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 | 151 | 20 |  | 4 | 4 | 423 | [16 empty] | 423 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | ROBERTO | RODRIGUEZ | Laborer |  | 6 |  |  | Tool Trailer | 6 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 |  | 30 |  | 6 | 6 | 408 | [16 empty] | 408 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | ROBERTO | RODRIGUEZ | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | JOEL | VALDEZ NEVAREZ | Laborer |  | 4 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 | 151 | 74 |  | 4 | 4 | 477 | [16 empty] | 477 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | JOEL | VALDEZ NEVAREZ | Laborer |  | 6 |  |  | 40' Flatbed trailer or equal | 6 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 |  | 111 |  | 6 | 6 | 489 | [16 empty] | 489 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | JOEL | VALDEZ NEVAREZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | HECTOR | QUINTANA VALDEZ | Laborer |  | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 | 151 | 362 |  | 4 | 4 | 765 | [16 empty] | 765 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | HECTOR | QUINTANA VALDEZ | Laborer |  | 6 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 378 |  | 543 |  | 6 | 6 | 921 | [16 empty] | 921 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | HECTOR | QUINTANA VALDEZ | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 | 151 | 64 |  | 4 | 4 | 503 | [16 empty] | 503 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 6 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 |  | 96 |  | 6 | 6 | 528 | [16 empty] | 528 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 4 | HR | 7160 | [11 empty] | 28.5 |  |  |  | 114 |  |  | 4 | 114 | [16 empty] | 114 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 6 | HR | 7160 | [11 empty] | 28.5 |  |  |  | 171 |  |  | 6 | 171 | [16 empty] | 171 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | 7160 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Light Tower 6000 Watt | 6 | HR | RLP | [11 empty] | 13 |  |  |  | 78 |  |  | 6 | 78 | [16 empty] | 78 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Hammer Attachment | 6 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44121-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-17 | FINISH EXCAVATION AND HAND DIGGING 2' UNDERNEATH THE PIPE. 200' OF SILT FENCE INSTALLED AROUND TOP SOIL AND SPOIL PILE. PIPE INSPECTED AND SANDBLASTED ON DAMAGED SPOTS. ALL HOSES INSTALLED ON AIR COMPRESSOR BEFORE SANDBLASTING. WAITING ON NDE ASSESSMENT TO BE COMPLETED. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | SBP | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | GARRETT | DICKSON | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | Sand | 16 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 | 151 | 26 | 0 | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Silt Fence | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | Safety Fence | 300 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | GARRETT | DICKSON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | T-Posts | 11 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | RYAN | COLEMAN | Operator II |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 | 151 | 26 |  | 2 | 2 | 343 | [16 empty] | 343 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | RYAN | COLEMAN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | RYAN | COLEMAN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | RYAN | COLEMAN | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | RYAN | COLEMAN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | RYAN | COLEMAN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JACOB | GORDON | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JACOB | GORDON | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JACOB | GORDON | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JACOB | GORDON | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JACOB | GORDON | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JACOB | GORDON | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | ZACH | POWDERS | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 32 |  | 2 | 2 | 158 | [16 empty] | 158 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | ZACH | POWDERS | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | ZACH | POWDERS | Laborer |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 | 151 | 32 |  | 2 | 2 | 309 | [16 empty] | 309 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | ZACH | POWDERS | Laborer |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 189 |  | 48 |  | 3 | 3 | 237 | [16 empty] | 237 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | ZACH | POWDERS | Laborer |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 |  | 32 |  | 2 | 2 | 158 | [16 empty] | 158 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | ZACH | POWDERS | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | COLTON | ROBERTS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | COLTON | ROBERTS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | COLTON | ROBERTS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | COLTON | ROBERTS | Laborer |  | 3 |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 | 151 | 55.5 |  | 3 | 3 | 395.5 | [16 empty] | 395.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | COLTON | ROBERTS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | COLTON | ROBERTS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JUAN | DURAN | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JUAN | DURAN | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JUAN | DURAN | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JUAN | DURAN | Laborer |  | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 | 151 | 271.5 |  | 3 | 3 | 611.5 | [16 empty] | 611.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JUAN | DURAN | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | JUAN | DURAN | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | TANNER | BRUMMETT | Laborer |  | 2 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 126 |  | 57 |  | 2 | 2 | 183 | [16 empty] | 183 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | TANNER | BRUMMETT | Laborer |  | 1 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 63 |  | 28.5 |  | 1 | 1 | 91.5 | [16 empty] | 91.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | TANNER | BRUMMETT | Laborer |  | 2 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 126 |  | 57 |  | 2 | 2 | 183 | [16 empty] | 183 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | TANNER | BRUMMETT | Laborer |  | 3 |  | 1 | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 189 | 151 | 85.5 |  | 3 | 3 | 425.5 | [16 empty] | 425.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | TANNER | BRUMMETT | Laborer |  | 2 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 126 |  | 57 |  | 2 | 2 | 183 | [16 empty] | 183 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | TANNER | BRUMMETT | Laborer |  | 1 |  |  | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | RAC | [7 empty] | 47 | 63 | 0 | 151 | 28.5 |  | 63 |  | 28.5 |  | 1 | 1 | 91.5 | [16 empty] | 91.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  |  | Light Tower 6000 Watt | 2 | HR | RLT | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 |  | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | Light Tower 6000 Watt | 1 | HR | RLT | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 72 |  | 13 |  | 1 | 1 | 85 | [16 empty] | 85 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  |  | Light Tower 6000 Watt | 2 | HR | RLT | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 |  | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Stand-by - Equipment | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | IAIN | ALLRED | Truck Driver/CDL |  | 3 |  | 1 | Light Tower 6000 Watt | 3 | HR | RLT | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 216 | 151 | 39 |  | 3 | 3 | 406 | [16 empty] | 406 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  |  | Light Tower 6000 Watt | 2 | HR | RLT | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 |  | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Clean-up / Remediation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | Light Tower 6000 Watt | 1 | HR | RLT | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 72 |  | 13 |  | 1 | 1 | 85 | [16 empty] | 85 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44121-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-17 | PREPPED EXCAVATION FOR DAILY TASK. ON STANDBY WAITING ON LINE REP. UPON ARRIVAL OF REP, BEGAN EXCAVATING FURTHER, INVESTIGATED CORROSION PAST INITIAL ANOMALY. WAITED ON NDE TO ARRIVE AND ASSESS CORROSION. UPON ARRIVAL OF BLASTING EQUIPMENT, SANDBLASTED PIPE. NDE INSPECTED JOB AND THEN BORROWED EQUIPMENT WAS SENT BACK TO OTHER CREW. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | 0 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | BARKLEY | BROWN | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Sand | 4 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 | 151 | 26 | 0 | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | MATTHEW | LINDLEY | Operator II |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 | 151 | 26 |  | 2 | 2 | 343 | [16 empty] | 343 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | MATTHEW | LINDLEY | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | MATTHEW | LINDLEY | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | WAYLON | GREEN | Laborer |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 | 151 | 26 |  | 2 | 2 | 303 | [16 empty] | 303 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | JOSE | VALLES | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | LUTHER | LINDLEY | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | LUTHER | LINDLEY | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | LUTHER | LINDLEY | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | MARCELO | GOMEZ | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | ANTHONY | MORENO | Laborer |  | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 | 151 | 181 |  | 2 | 2 | 458 | [16 empty] | 458 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | ANTHONY | MORENO | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | ANTHONY | MORENO | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 151 | 32 |  | 2 | 2 | 327 | [16 empty] | 327 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Mobilization | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Padding Bucket | 2 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Excavation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Excavation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Water Pump ( up to 2") | 2 | HR | 2INP | [11 empty] | 6 |  |  |  | 12 |  |  | 2 | 12 | [16 empty] | 12 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44121-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-17 | No Comments | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | SBP | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | BARKLEY | BROWN | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | MATTHEW | LINDLEY | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | WAYLON | GREEN | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | JOSE | VALLES | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | LUTHER | LINDLEY | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 55.5 |  | 5 | 3 | 370.5 | [16 empty] | 370.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | MARCELO | GOMEZ | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | ANTHONY | MORENO | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 28.5 |  |  |  | 85.5 |  |  | 3 | 85.5 | [16 empty] | 85.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | [7 empty] | Brush Hog | 3 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44121-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-17 | No Comments | [7 empty] | Padding Bucket | 3 | HR | RPB | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 0 |  |  |  | BRAND SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | BRAND SAFEWAY | [15 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 0 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | MATTHEW | LINDLEY | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 0 | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 0 | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | LUTHER | LINDLEY | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | MARCELO | GOMEZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | MARCELO | GOMEZ | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 3 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 55.5 |  | 1 | 3 | 118.5 | [16 empty] | 118.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | ANTHONY | MORENO | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 92 |  | 4 | 2 | 344 | [16 empty] | 344 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | 0 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 0 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 0 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | 0 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | 0 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 2 | HR | 0 | [11 empty] | 28.5 |  |  |  | 57 |  |  | 2 | 57 | [16 empty] | 57 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Sullair Air Compressor (376 to 425 CFM) or equal ** | 1 | HR | 0 | [11 empty] | 28.5 |  |  |  | 28.5 |  |  | 1 | 28.5 | [16 empty] | 28.5 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Light Tower 6000 Watt | 2 | HR | 0 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Light Tower 6000 Watt | 1 | HR | 0 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Hammer Attachment | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Hammer Attachment | 1 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Brush Hog | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Brush Hog | 1 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Padding Bucket | 2 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-1491 - MC.400216.032 - 671.952 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-10-22 | 2 | BL |  | Demobilization | 3500028468-58100-44121-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-17 | No Comments | [7 empty] | Padding Bucket | 1 | HR | 0 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-02 | ABC 3500028468-02
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JODY | BROOM | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | [16 empty] | 1003 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JODY | BROOM | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | TOME | KIRKLAND | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | [16 empty] | 1003 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | TOME | KIRKLAND | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JAY | MASEY | Quality Assurance Inspector | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 840 | 151 | 104 |  | 8 | 8 | 1095 | [16 empty] | 1095 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | MICHAEL | GOSS | Truck Driver/CDL | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 428 | 151 | 104 |  | 8 | 8 | 683 | [16 empty] | 683 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | MICHAEL | GOSS | Truck Driver/CDL |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 | 0 | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 428 | 151 | 104 |  | 8 | 8 | 683 | [16 empty] | 683 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 |  | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | DANIEL | YOUNG | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | DANIEL | YOUNG | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | KIM | FORNALL | Project Coordinator | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 790.4 | 151 | 104 |  | 8 | 8 | 1045.4 | [16 empty] | 1045.4 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 197.6 |  | 26 |  | 2 | 2 | 223.6 | [16 empty] | 223.6 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Tractor/Semi | 8 | HR | 1368 | [11 empty] | 42 |  |  |  | 336 |  |  | 8 | 336 | [16 empty] | 336 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Tractor/Semi | 2 | HR | 1368 | [11 empty] | 42 |  |  |  | 84 |  |  | 2 | 84 | [16 empty] | 84 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Tractor/Semi | 8 | HR | 1376 | [11 empty] | 42 |  |  |  | 336 |  |  | 8 | 336 | [16 empty] | 336 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Tractor/Semi | 2 | HR | 1376 | [11 empty] | 42 |  |  |  | 84 |  |  | 2 | 84 | [16 empty] | 84 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 8 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 148 |  |  | 8 | 148 | [16 empty] | 148 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 2 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 8 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 148 |  |  | 8 | 148 | [16 empty] | 148 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 2 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 8 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 2 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 8 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 2 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT1 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT2 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT3 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT4 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT5 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT6 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JONATHAN | HOLLEY | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JONATHAN | Silt Fence | 166 | Ft | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 592 | 151 | 104 | 0 | 8 | 8 | 847 | SAFEWAY | [15 empty] | 847 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JONATHAN | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | Safety Fence | 60 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | RYAN | FARINELLI | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | RYANF | T-Posts | 7 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 492 | 151 | 104 | 0 | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | RYAN | FARINELLI | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | GREG | MCMILLIAN | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | GREG | MCMILLIAN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JERMAINE | EVANS | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | [16 empty] | 567 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JERMAINE | EVANS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | DEMETRIUS | MCDONALD | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | [16 empty] | 675 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | DEMETRIUS | MCDONALD | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JOSE | ORTIZ | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | [16 empty] | 895 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JOSE | ORTIZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | ROBERT | FOSTER | Laborer | 8 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 376 | 151 | 724 |  | 8 | 8 | 1251 | [16 empty] | 1251 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | ROBERT | FOSTER | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | BRIAN | RANDLE | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | [16 empty] | 707 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | [16 empty] | 220 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Hammer Attachment | 8 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Brush Hog | 8 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Brush Hog | 2 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Padding Bucket | 8 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Hammer Attachment | 10 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Brush Hog | 10 | HR | RBH4491 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Padding Bucket | 10 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | RATLIFF | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | RATLIFF | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 |  | 52 |  | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | RATLIFF | Foreman | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 274 |  | 39 |  | 3 | 3 | 313 | [16 empty] | 313 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | SHAWN | ROSE | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | SHAWN | ROSE | Operator II | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 144.5 |  | 26 |  | 2 | 2 | 170.5 | [16 empty] | 170.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | ELLIOTT | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | ELLIOTT | Laborer | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 52 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | ELLIOTT | Laborer | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 110 |  | 26 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | DAVID | RATLIFF | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | DAVID | RATLIFF | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | DAVID | RATLIFF | Laborer | 1 | 1 |  |  | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 110 |  | 10 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | TYLER | BIGG | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | TYLER | BIGG | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | TYLER | BIGG | Truck Driver/CDL | 1 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 125.5 |  | 32 |  | 2 | 2 | 157.5 | [16 empty] | 157.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | 40' Flatbed trailer or equal | 1 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 18.5 |  |  | 1 | 18.5 | [16 empty] | 18.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | 40' Flatbed trailer or equal | 4 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 74 |  |  | 4 | 74 | [16 empty] | 74 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | [16 empty] | 46 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | [16 empty] | 184 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Hammer Attachment | 4 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Padding Bucket | 1 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Padding Bucket | 4 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Brush Hog | 1 | HR | RBH3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Brush Hog | 4 | HR | RBH3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Brush Hog | 2 | HR | RBH3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | MICHAEL | RATLIFF | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | SHAWN | ROSE | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | MICHAEL | ELLIOT | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | DAVID | RATLIFF | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | TYLER | BIGG | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | GERALD | SMITH | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | GERALD | Sand | 10 | Bag | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | SAFEWAY | [15 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | GERALD | SMITH | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | RICHARD | SHOEMAKE | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | RICHARD | SHOEMAKE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | OJ | SEALS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | OJ | SEALS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | JAMES | KERVIN | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | JAMES | KERVIN | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | RICHARD | ADKINS | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | RICHARD | ADKINS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | NICHOLAS | BLANCO | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | NICHOLAS | BLANCO | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | BARRETT | WISE | Laborer | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF439 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 | 151 | 64 |  | 4 | 4 | 403 | [16 empty] | 403 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | BARRETT | WISE | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF439 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Hammer Attachment | 4 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Hammer Attachment | 2 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP4 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP4 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Padding Bucket | 4 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Padding Bucket | 2 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSBP4 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | Sand | 6 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | 2888 Coating | 11 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAEL | T-Posts | 6 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 63 |  | 13 | 0 | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAEL | T-Post Caps | 6 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 126 |  | 26 | 0 | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | JORDAN | WIGGINS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | Safety Fence | 100 | Ft |  |  |  |  | 47 | 63 | 0 | 151 | 5 | 0 | 63 |  | 5 | 0 | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | JORDAN | WIGGINS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | Brushes | 36 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 5 | 0 | 63 |  | 5 | 0 | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | DAVID | KNOTTS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | Clocksprings | 3 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | DAVID | KNOTTS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | TANNER | BRITT | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | TANNER | BRITT | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Hammer Attachment | 1 | HR | RHA606 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Hammer Attachment | 1 | HR | RHA606 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSBP5 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | CALEB | HOLTON | Foreman | 8 | 1 |  | 1 | Pickup-F150 or F250 or equal | 9 | HR | CALEB |  |  |  | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 692 | 151 | 117 |  | 9 | 9 | 960 | SAFEWAY | [15 empty] | 960 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | THOMAS | FRANKLIN | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 824 | 151 | 156 |  | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | MICHAEL | ANISZEWSKI | Laborer | 8 | 1 |  | 1 | Pickup-F150 or F250 or equal | 9 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 439 | 151 | 117 |  | 9 | 9 | 707 | [16 empty] | 707 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | BOLDBAUTOR | ZORIGT | Laborer | 8 | 4 |  | 1 | Tool Trailer | 12 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 60 |  | 12 | 12 | 839 | [16 empty] | 839 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | JORDAN | WIGGINS | Laborer | 8 | 1 |  | 1 | 40' Flatbed trailer or equal | 9 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 439 | 151 | 166.5 |  | 9 | 9 | 756.5 | [16 empty] | 756.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | JORDAN | WIGGINS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | DAVID | KNOTTS | Laborer | 8 | 1 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 9 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 439 | 151 | 414 |  | 9 | 9 | 1004 | [16 empty] | 1004 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | DAVID | KNOTTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | TANNER | BRITT | Laborer | 8 | 1 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 9 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 439 | 151 | 814.5 |  | 9 | 9 | 1404.5 | [16 empty] | 1404.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | TANNER | BRITT | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | ALDO | RENYA | Truck Driver/CDL | 8 | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 13 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 788 | 151 | 208 |  | 13 | 13 | 1147 | [16 empty] | 1147 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 9 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 247.5 |  |  | 9 | 247.5 | [16 empty] | 247.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Hammer Attachment | 9 | HR | RAC4049 | [11 empty] | 0 |  |  |  | 0 |  |  | 9 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Hammer Attachment | 1 | HR | RAC4049 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Padding Bucket | 9 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 9 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 9 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 220.5 |  |  | 9 | 220.5 | [16 empty] | 220.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | BARKLEY | BROWN | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Sand | 3 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | BARKLEY | BROWN | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | 2888 Coating | 9 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | BARKLEY | BROWN | Foreman | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Clocksprings | 3 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 248 |  | 39 |  | 3 | 3 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | BARKLEY | BROWN | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MATTHEW | LINDLEY | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MATTHEW | LINDLEY | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MATTHEW | LINDLEY | Operator II | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 206 |  | 39 |  | 3 | 3 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MATTHEW | LINDLEY | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | WAYLON | GREEN | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 | 151 | 39 |  | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | WAYLON | GREEN | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | WAYLON | GREEN | Laborer | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 157 |  | 39 |  | 3 | 3 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | WAYLON | GREEN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSE | VALLES | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSE | VALLES | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSE | VALLES | Laborer | 2 | 1 |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 157 |  | 15 |  | 3 | 3 | 172 | [16 empty] | 172 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSE | VALLES | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | LUTHER | LINDLEY | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | LUTHER | LINDLEY | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | LUTHER | LINDLEY | Laborer | 2 | 1 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 157 |  | 55.5 |  | 3 | 3 | 212.5 | [16 empty] | 212.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | LUTHER | LINDLEY | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MARCELO | GOMEZ | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 138 |  | 3 | 3 | 430 | [16 empty] | 430 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MARCELO | GOMEZ | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MARCELO | GOMEZ | Laborer | 2 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 157 |  | 138 |  | 3 | 3 | 295 | [16 empty] | 295 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MARCELO | GOMEZ | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | ANTHONY | MORENO | Laborer | 3 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 | 151 | 271.5 |  | 3 | 3 | 563.5 | [16 empty] | 563.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | ANTHONY | MORENO | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | ANTHONY | MORENO | Laborer | 2 | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 157 |  | 271.5 |  | 3 | 3 | 428.5 | [16 empty] | 428.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | ANTHONY | MORENO | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSHUA | PHILLIPSON | Truck Driver/CDL | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 | 151 | 48 |  | 3 | 3 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSHUA | PHILLIPSON | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 179 |  | 48 |  | 3 | 3 | 227 | [16 empty] | 227 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Padding Bucket | 3 | HR | RBP6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Padding Bucket | 3 | HR | RBP6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Padding Bucket | 3 | HR | RBP6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Padding Bucket | 3 | HR | RBP6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Water Pump ( up to 2") | 3 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 18 |  |  | 3 | 18 | [16 empty] | 18 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | SBP6 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | URIEL | VALENCIA | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | R15349 | Sand | 3 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | URIEL | VALENCIA | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | R15349 | 2888 Coating | 3 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | URIEL | VALENCIA | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15349 | Brushes | 24 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | URIEL | VALENCIA | Foreman | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 274 |  | 39 |  | 3 | 3 | 313 | [16 empty] | 313 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | VALDEZ NEVAREZ | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | VALDEZ NEVAREZ | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | VALDEZ NEVAREZ | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | VALDEZ NEVAREZ | Operator II | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 227.5 |  | 39 |  | 3 | 3 | 266.5 | [16 empty] | 266.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 173 |  | 39 |  | 3 | 3 | 212 | [16 empty] | 212 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ASTOLFO | FLORES | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ASTOLFO | FLORES | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ASTOLFO | FLORES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ASTOLFO | FLORES | Laborer | 1 | 2 |  |  | Tool Trailer | 3 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 173 |  | 15 |  | 3 | 3 | 188 | [16 empty] | 188 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | IVAN | MADRID | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | IVAN | MADRID | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | IVAN | MADRID | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | IVAN | MADRID | Laborer | 1 | 2 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 173 |  | 55.5 |  | 3 | 3 | 228.5 | [16 empty] | 228.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ROBERTO | RODRIGUEZ | Laborer | 2 |  |  | 1 | Light Tower 6000 Watt | 2 | HR | RLP7 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ROBERTO | RODRIGUEZ | Laborer | 3 |  |  |  | Light Tower 6000 Watt | 3 | HR | RLP7 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ROBERTO | RODRIGUEZ | Laborer | 2 |  |  |  | Light Tower 6000 Watt | 2 | HR | RLP7 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ROBERTO | RODRIGUEZ | Laborer | 1 | 2 |  |  | Light Tower 6000 Watt | 3 | HR | RLP7 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 173 |  | 39 |  | 3 | 3 | 212 | [16 empty] | 212 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | JOEL | VALDEZ NEVAREZ | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | JOEL | VALDEZ NEVAREZ | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | JOEL | VALDEZ NEVAREZ | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | JOEL | VALDEZ NEVAREZ | Laborer | 1 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 173 |  | 271.5 |  | 3 | 3 | 444.5 | [16 empty] | 444.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | QUINTANA VALDEZ | Laborer | 2 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 | 151 | 55 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | QUINTANA VALDEZ | Laborer | 3 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 141 |  | 82.5 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | QUINTANA VALDEZ | Laborer | 2 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 |  | 55 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | QUINTANA VALDEZ | Laborer | 1 | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 173 |  | 82.5 |  | 3 | 3 | 255.5 | [16 empty] | 255.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | MATTHEW | SCHMITT | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | MATTHEW | SCHMITT | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | MATTHEW | SCHMITT | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | MATTHEW | SCHMITT | Truck Driver/CDL | 1 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 197.5 |  | 48 |  | 3 | 3 | 245.5 | [16 empty] | 245.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Hammer Attachment | 2 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Hammer Attachment | 3 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Hammer Attachment | 2 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Hammer Attachment | 3 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSBP7 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | GARRETT | DICKSON | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | RYAN | COLEMAN | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | RYAN | COLEMAN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | JACOB | GORDAN | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | JACOB | GORDAN | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | ZACHARY | POWDERS | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | ZACHARY | POWDERS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | TOME | KIRKLAND | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Kubota UTV | 10 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT1 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT2 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT3 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT4 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT5 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | MATCHES CREW 2 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT6 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | JONATHAN | HOLLEY | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | RYAN | FARINELLI | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | GREG | MCMILLIAN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | JERMAINE | EVANS | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | DEMETRIUS | MCDONALD | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | JOSE | ORTIZ | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | ROBERT | FOSTER | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | BRIAN | RANDLE | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | [7 empty] | Hammer Attachment | 4 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | [7 empty] | Brush Hog | 4 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44123-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-19 | Prepped site | [7 empty] | Padding Bucket | 4 | HR | RBP1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | JONATHAN | HOLLEY | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | Sand | 15 | Bag | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | SAFEWAY | [15 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | JONATHAN | HOLLEY | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 |  | 52 |  | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | JONATHAN | HOLLEY | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | RYAN | FARINELLI | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | RYAN | FARINELLI | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | RYAN | FARINELLI | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | GREG | MCMILLIAN | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | GREG | MCMILLIAN | Laborer | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 52 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | GREG | MCMILLIAN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | JERMAINE | EVANS | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | JERMAINE | EVANS | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | JERMAINE | EVANS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | DEMETRIUS | MCDONALD | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | DEMETRIUS | MCDONALD | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | DEMETRIUS | MCDONALD | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | JOSE | ORTIZ | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | JOSE | ORTIZ | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | JOSE | ORTIZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | ROBERT | FOSTER | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | ROBERT | FOSTER | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 362 |  | 4 | 4 | 550 | [16 empty] | 550 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | ROBERT | FOSTER | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | BRIAN | RANDLE | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | BRIAN | RANDLE | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | BRIAN | RANDLE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Hammer Attachment | 4 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Brush Hog | 2 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Brush Hog | 4 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Brush Hog | 2 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Padding Bucket | 4 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44123-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-19 | Cleaned up bellhole for NDE and Safeway. Safeway beat off 8ft of coating. Sandblasted (2) spots for NDE to inspect. | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | Straw Bales | 16 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 892 | 151 | 143 | 0 | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | HEATHER | ENGEL | Laborer | 8 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 502 | 151 | 905 |  | 10 | 10 | 1558 | [16 empty] | 1558 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | [7 empty] | Hammer Attachment | 10 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | [7 empty] | Padding Bucket | 10 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44123-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-19 | Pumped water, hammered rock all day. Dig about 75% complete | [7 empty] | Water Pump ( up to 2") | 10 | HR | 2INP2 | [11 empty] | 6 |  |  |  | 60 |  |  | 10 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | MICHAEL | RATLIFF | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MICHAELR | Silt Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | MICHAEL | RATLIFF | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | MICHAELR | T-Posts | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | MICHAEL | RATLIFF | Foreman | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 322 |  | 52 |  | 4 | 4 | 374 | [16 empty] | 374 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | SHAWN | ROSE | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | SHAWN | ROSE | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | SHAWN | ROSE | Operator II | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 267.5 |  | 52 |  | 4 | 4 | 319.5 | [16 empty] | 319.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | MICHAEL | ELLIOTT | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | MICHAEL | ELLIOTT | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | MICHAEL | ELLIOTT | Laborer | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 204 |  | 52 |  | 4 | 4 | 256 | [16 empty] | 256 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | DAVID | RATLIFF | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | DAVID | RATLIFF | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | DAVID | RATLIFF | Laborer | 3 | 1 |  |  | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 204 |  | 20 |  | 4 | 4 | 224 | [16 empty] | 224 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | TYLER | BIGG | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | TYLER | BIGG | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | TYLER | BIGG | Truck Driver/CDL | 3 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 232.5 |  | 64 |  | 4 | 4 | 296.5 | [16 empty] | 296.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 55.5 |  |  | 3 | 55.5 | [16 empty] | 55.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | 40' Flatbed trailer or equal | 4 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 74 |  |  | 4 | 74 | [16 empty] | 74 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | [16 empty] | 184 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Hammer Attachment | 3 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Hammer Attachment | 4 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Brush Hog | 2 | HR | RBH3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Brush Hog | 3 | HR | RBH3 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Brush Hog | 4 | HR | RBH3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Padding Bucket | 3 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44123-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-19 | Brush hogged site. Pot holed and located line with line locator then dug and found line. | [7 empty] | Padding Bucket | 4 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | GERALD | SMITH | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | GERALD | Sand | 20 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | GERALD | SMITH | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | RICHARD | SHOEMAKE | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | RICHARD | SHOEMAKE | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | OJ | SEALS | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 | 151 | 39 |  | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | OJ | SEALS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | JAMES | KERVIN | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | JAMES | KERVIN | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | RICHARD | ADKINS | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | RICHARD | ADKINS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | NICHOLAS | BLANCO | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 138 |  | 3 | 3 | 430 | [16 empty] | 430 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | NICHOLAS | BLANCO | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | BARRETT | WISE | Laborer | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF439 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 | 151 | 48 |  | 3 | 3 | 340 | [16 empty] | 340 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | BARRETT | WISE | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF439 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 32 |  | 1 | 2 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Hammer Attachment | 3 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Hammer Attachment | 2 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Padding Bucket | 3 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Padding Bucket | 2 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44123-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-19 | Sandblasted pipe to expose anomalies. Assisted NDE crew with inspection of pipe. Waiting on results | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | RSBP4 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | GERALD | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | GERALD | Sand | 25 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | GERALD | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | GERALD | SMITH | Foreman | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 274 |  | 39 |  | 3 | 3 | 313 | [16 empty] | 313 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | RICHARD | SHOEMAKE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | RICHARD | SHOEMAKE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | JAMES | KERVIN | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | JAMES | KERVIN | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | RICHARD | ADKINS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | RICHARD | ADKINS | Laborer | 1 |  |  |  | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSBP4 | [7 empty] | 47 | 63 | 0 | 151 | 23.5 |  | 47 |  | 23.5 |  | 1 | 1 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | RICHARD | ADKINS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 185 |  | 1 | 10 | 232 | [16 empty] | 232 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | NICHOLAS | BLANCO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | NICHOLAS | BLANCO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | NICHOLAS | BLANCO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | BARRETT | WISE | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | BARRETT | WISE | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | BARRETT | WISE | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 |  | 160 |  | 10 | 10 | 732 | [16 empty] | 732 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44123-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-19 | MOB into site and did site prep. Started sandblasting | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | CALEB | HOLTON | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | THOMAS | FRANKLIN | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | MICHAEL | ANISZEWSKI | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | BOLDBAUTOR | ZORIGT | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | JORDAN | WIGGINS | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | DAVID | KNOTTS | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | TANNER | BRITT | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | ALDO | RENYA | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | [16 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-27760-44123-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-19 | Bad weather hit and had to call rainout on site | [7 empty] | Padding Bucket | 4 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | BARKLEY | BROWN | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | BARKLEY | BROWN | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 |  | 52 |  | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | MATTHEW | LINDLEY | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | WAYLON | GREEN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | JOSE | VALLES | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | LUTHER | LINDLEY | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | MARCELO | GOMEZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | ANTHONY | MORENO | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-50610-44123-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-19 | Rain Out from site. Foreman picked up repair kits for coating | [7 empty] | Hammer Attachment | 4 | HR | RGA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | URIEL | VALENCIA | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | HECTOR | VALDEZ NEVAREZ | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | ALEJANDRO | CRUZ CONTRERAS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | ASTOLFO | FLORES | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | IVAN | MADRID | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | ROBERTO | RODRIGUEZ | Laborer | 4 |  |  | 1 | Hammer Attachment | 4 | HR | RHA7 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 188 | 151 | 0 |  | 4 | 4 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | JOEL | VALDEZ NEVAREZ | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | HECTOR | QUINTANA VALDEZ | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-71410-44123-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-19 | Rained out | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP7 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | GARRETT | DICKSON | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | GARRETT | DICKSON | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 |  | 52 |  | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | RYAN | COLEMAN | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | JACOB | GORDON | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | ZACHARY | POWDERS | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | ZACHARY | POWDERS | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 362 |  | 4 | 4 | 550 | [16 empty] | 550 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | COLTON | ROBERTS | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | JUAN | DURAN | Laborer | 4 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 188 | 151 | 110 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | TANNER | BRUMMETT | Laborer | 4 |  |  | 1 | Hammer Attachment | 4 | HR | RHA8 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 188 | 151 | 0 |  | 4 | 4 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | IAIN | ALLRED | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-31790-44123-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-19 | Rained out on jobsite. Foreman and labor went back to location to unload equipment | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP8 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | JODY | BROOM | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | [16 empty] | 1003 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | JODY | BROOM | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | TOME | KIRKLAND | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | [16 empty] | 1003 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | TOME | KIRKLAND | Superintendent |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 504 |  | 52 |  | 4 | 4 | 556 | [16 empty] | 556 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | JAY | MASEY | Quality Assurance Inspector | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 840 | 151 | 104 |  | 8 | 8 | 1095 | [16 empty] | 1095 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | MICHAEL | GOSS | Truck Driver/CDL | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 428 | 151 | 104 |  | 8 | 8 | 683 | [16 empty] | 683 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | MICHAEL | GOSS | Truck Driver/CDL |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 |  | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 428 | 151 | 104 |  | 8 | 8 | 683 | [16 empty] | 683 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 |  | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | JUANITO | RODRIGUEZ | Safety Person | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | JUANITO | RODRIGUEZ | Safety Person |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | DANIEL | YOUNG | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | DANIEL | YOUNG | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | KIM | FORNALL | Project Coordinator | 8 |  |  | 1 | Tractor/Semi | 8 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 790.4 | 151 | 336 |  | 8 | 8 | 1277.4 | [16 empty] | 1277.4 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Tractor/Semi | 2 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 197.6 |  | 84 |  | 2 | 2 | 281.6 | [16 empty] | 281.6 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Tractor/Semi | 8 | HR | 1376 | [11 empty] | 42 |  |  |  | 336 |  |  | 8 | 336 | [16 empty] | 336 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Tractor/Semi | 2 | HR | 1376 | [11 empty] | 42 |  |  |  | 84 |  |  | 2 | 84 | [16 empty] | 84 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Lowboy Trailer | 8 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 148 |  |  | 8 | 148 | [16 empty] | 148 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Lowboy Trailer | 2 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Lowboy Trailer | 8 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 148 |  |  | 8 | 148 | [16 empty] | 148 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Lowboy Trailer | 2 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Kubota UTV | 8 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Kubota UTV | 2 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Kubota UTV | 8 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Kubota UTV | 2 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP1 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP1 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP2 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP2 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP3 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP3 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP5 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP5 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP6 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Match to crew 7 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP6 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | JONATHAN | HOLLEY | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 0 | HR | JONATHAN | Silt Fence | 35 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 0 | 0 | 4 | 0 | 296 | [16 empty] | 296 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | JONATHAN | HOLLEY | Foreman | 2 | 4 |  |  | Pickup-F150 or F250 or equal | 0 | HR | JONATHAN | Safety Fence | 98 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 548 |  | 0 | 0 | 6 | 0 | 548 | [16 empty] | 548 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | RYAN | FARINELLI | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 0 | HR | RYANF | T-Posts | 7 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 246 |  | 0 | 0 | 4 | 0 | 246 | [16 empty] | 246 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | RYAN | FARINELLI | Operator II | 2 | 4 |  |  | Pickup-F150 or F250 or equal | 0 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 455 |  | 0 |  | 6 | 0 | 455 | [16 empty] | 455 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | GREG | MCMILLIAN | Laborer | 4 |  |  |  | Pickup-F150 or F250 or equal | 0 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 0 |  | 4 | 0 | 188 | [16 empty] | 188 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | GREG | MCMILLIAN | Laborer | 2 | 4 |  |  | Pickup-F150 or F250 or equal | 0 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 346 |  | 0 |  | 6 | 0 | 346 | [16 empty] | 346 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | JERMAINE | EVANS | Laborer | 4 |  |  |  | Tool Trailer | 0 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 0 |  | 4 | 0 | 188 | [16 empty] | 188 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | JERMAINE | EVANS | Laborer | 2 | 4 |  |  | Tool Trailer | 0 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 346 |  | 0 |  | 6 | 0 | 346 | [16 empty] | 346 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | DEMETRIUS | MCDONALD | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 0 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 0 |  | 4 | 0 | 188 | [16 empty] | 188 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | DEMETRIUS | MCDONALD | Laborer | 2 | 4 |  |  | 40' Flatbed trailer or equal | 0 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 346 |  | 0 |  | 6 | 0 | 346 | [16 empty] | 346 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | JOSE | ORTIZ | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 0 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 0 |  | 4 | 0 | 188 | [16 empty] | 188 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | JOSE | ORTIZ | Laborer | 2 | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 0 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 346 |  | 0 |  | 6 | 0 | 346 | [16 empty] | 346 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | ROBERT | FOSTER | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 0 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 0 |  | 4 | 0 | 188 | [16 empty] | 188 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | ROBERT | FOSTER | Laborer | 2 | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 0 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 346 |  | 0 |  | 6 | 0 | 346 | [16 empty] | 346 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | BRIAN | RANDLE | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 0 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 0 |  | 4 | 0 | 214 | [16 empty] | 214 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | BRIAN | RANDLE | Truck Driver/CDL | 2 | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 0 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 395 |  | 0 |  | 6 | 0 | 395 | [16 empty] | 395 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 0 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 0 |  |  | 0 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 0 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 0 |  |  | 0 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | [7 empty] | Hammer Attachment | 0 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 0 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | [7 empty] | Hammer Attachment | 0 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 0 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | [7 empty] | Brush Hog | 0 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 0 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | [7 empty] | Brush Hog | 0 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 0 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | [7 empty] | Padding Bucket | 0 | HR | RBP1 | [11 empty] | 0 |  |  |  | 0 |  |  | 0 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44124-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-20 | Potholed line 15 and then potholed line 10 that was 10ft deep. Started digging line 15 to locate anomally. | [7 empty] | Padding Bucket | 0 | HR | RBP1 | [11 empty] | 0 |  |  |  | 0 |  |  | 0 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | JONATHAN | HOLLEY | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | RYAN | FARINELLI | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | GREG | MCMILLIAN | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | JERMAINE | EVANS | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | DEMETRIUS | MCDONALD | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | JOSE | ORTIZ | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | ROBERT | FOSTER | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | BRIAN | RANDLE | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | [7 empty] | Brush Hog | 2 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-18890-44124-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-20 | MOVED FROM 1549 TO 1546 | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44124-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-20 | Moved equipment to start clearing ROW for 0545, trimmed trees and brushhogged | KYLE | BONNEAU | Foreman | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 448 |  | 65 |  | 5 | 5 | 513 | [16 empty] | 513 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44124-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-20 | Moved equipment to start clearing ROW for 0545, trimmed trees and brushhogged | CODY | GAXIOLA | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44124-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-20 | Moved equipment to start clearing ROW for 0545, trimmed trees and brushhogged | ALTANOCHIR | JANSTAN | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44124-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-20 | Moved equipment to start clearing ROW for 0545, trimmed trees and brushhogged | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9350 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44124-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-20 | Moved equipment to start clearing ROW for 0545, trimmed trees and brushhogged | [7 empty] | Brush Hog | 5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | KYLE | BONNEAU | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | KYLE |  |  |  | ABATE | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | ABATE | [15 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | KYLE | BONNEAU | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | JESSE | BERTHIAUME | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | JESSE | BERTHIAUME | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | CADEN | THOMPSON | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | CADEN | THOMPSON | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | JACOB | CAPITANO | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | JACOB | CAPITANO | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | BROC | CALIGER | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 74 |  | 5 | 4 | 460 | [16 empty] | 460 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | BROC | CALIGER | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 18.5 |  | 5 | 1 | 285.5 | [16 empty] | 285.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | CODY | GAXIOLA | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 230 |  | 4 | 5 | 569 | [16 empty] | 569 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | CODY | GAXIOLA | Laborer | 1 |  |  |  | Brush Hog | 5 | HR | RBH4991 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 47 |  | 0 |  | 1 | 5 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | HEATHER | ENGLE | Laborer | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 235 | 151 | 452.5 |  | 5 | 5 | 838.5 | [16 empty] | 838.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | HEATHER | ENGLE | Laborer | 3 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 267 |  | 452.5 |  | 5 | 5 | 719.5 | [16 empty] | 719.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | ALTANOCHIR | JANSTAN | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | ALTANOCHIR | JANSTAN | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | [7 empty] | Hammer Attachment | 5 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | [7 empty] | Hammer Attachment | 5 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44124-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-20 | Had detailed JSA, pumped water from ditch, proceeded to hammer and excavate. Finished excavation, NDE came to inspect. Abate came and took off coating. | [7 empty] | Water Pump (3") | 10 | HR | 3INP2 | [11 empty] | 12 |  |  |  | 120 |  |  | 10 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | MICHAEL | RATLIFF | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | MICHAELR | Silt Fence | 75 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | MICHAEL | RATLIFF | Foreman | 5 | 2 |  |  | Pickup-F150 or F250 or equal | 7 | HR | MICHAELR | Safety Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 570 |  | 91 | 0 | 7 | 7 | 661 | [16 empty] | 661 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | SHAWN | ROSE | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | SHAWN | T-Posts | 10 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 184.5 | 151 | 39 | 0 | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | SHAWN | ROSE | Operator II | 5 | 2 |  |  | Pickup-F150 or F250 or equal | 7 | HR | SHAWN | T-Post Caps | 10 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 473.5 |  | 91 | 0 | 7 | 7 | 564.5 | [16 empty] | 564.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | MICHAEL | ELLIOTT | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15363 | 2888 Coating | 2 | L |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 141 | 151 | 39 | 0 | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | MICHAEL | ELLIOTT | Laborer | 5 | 2 |  |  | Pickup-F150 or F250 or equal | 7 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 361 |  | 91 |  | 7 | 7 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | DAVID | RATLIFF | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | DAVID | RATLIFF | Laborer | 5 | 2 |  |  | Tool Trailer | 7 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 361 |  | 35 |  | 7 | 7 | 396 | [16 empty] | 396 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | TYLER | BIGG | Truck Driver/CDL | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 | 151 | 48 |  | 3 | 3 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | TYLER | BIGG | Truck Driver/CDL | 5 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 |  | 80 |  | 5 | 5 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | 40' Flatbed trailer or equal | 3 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 55.5 |  |  | 3 | 55.5 | [16 empty] | 55.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | 40' Flatbed trailer or equal | 7 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 129.5 |  |  | 7 | 129.5 | [16 empty] | 129.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 322 |  |  | 7 | 322 | [16 empty] | 322 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 633.5 |  |  | 7 | 633.5 | [16 empty] | 633.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 192.5 |  |  | 7 | 192.5 | [16 empty] | 192.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Hammer Attachment | 3 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Hammer Attachment | 7 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Padding Bucket | 3 | HR | RBP3 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44124-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-20 | Replaced (2) hydrolic lines on excavator. Reverified line location. Began excavation and exposed G.W. Repaired/coated. Cleaned roads of mud and pulled additional top soil. | [7 empty] | Padding Bucket | 7 | HR | RBP3 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | GERALD | SMITH | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | GERALD | Sand | 35 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 444 | 151 | 78 | 0 | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | GERALD | SMITH | Foreman | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | GERALD | 2888 Coating | 40 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 448 |  | 65 | 0 | 5 | 5 | 513 | [16 empty] | 513 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | RICHARD | SHOEMAKE | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | RICHARDS | Brushes | 48 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 369 | 151 | 78 | 0 | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | RICHARD | SHOEMAKE | Operator II | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 289 |  | 52 |  | 4 | 4 | 341 | [16 empty] | 341 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | OJ | SEALS | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | OJ | SEALS | Laborer | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 220 |  | 52 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | JAMES | KERVIN | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | JAMES | KERVIN | Laborer | 2 | 2 |  |  | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 220 |  | 20 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | RICHARD | ADKINS | Laborer | 6 |  |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 282 | 151 | 111 |  | 6 | 6 | 544 | [16 empty] | 544 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | RICHARD | ADKINS | Laborer | 2 | 2 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 220 |  | 74 |  | 4 | 4 | 294 | [16 empty] | 294 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | NICHOLAS | BLANCO | Laborer | 6 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 282 | 151 | 276 |  | 6 | 6 | 709 | [16 empty] | 709 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | NICHOLAS | BLANCO | Laborer | 2 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 220 |  | 184 |  | 4 | 4 | 404 | [16 empty] | 404 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | BARRETT | WISE | Laborer | 6 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 282 | 151 | 543 |  | 6 | 6 | 976 | [16 empty] | 976 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | BARRETT | WISE | Laborer | 2 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 220 |  | 362 |  | 4 | 4 | 582 | [16 empty] | 582 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | STEVE | CLARK | Truck Driver/CDL | 6 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 321 | 151 | 96 |  | 6 | 6 | 568 | [16 empty] | 568 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | STEVE | CLARK | Truck Driver/CDL | 2 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 251 |  | 64 |  | 4 | 4 | 315 | [16 empty] | 315 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | [7 empty] | Hammer Attachment | 6 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | [7 empty] | Hammer Attachment | 4 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | [7 empty] | Padding Bucket | 6 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | [7 empty] | Padding Bucket | 4 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 6 | HR | RSP4 | [11 empty] | 23.5 |  |  |  | 141 |  |  | 6 | 141 | [16 empty] | 141 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | [7 empty] | Light Tower 6000 Watt | 6 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 78 |  |  | 6 | 78 | [16 empty] | 78 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-19030-44124-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-20 | Sandblasted pipe and recoated pipe. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44124-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-20 | Sandblasted proposed anomaly and NDE did assessment | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | Sand | 8 | Bag |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 94 |  | 26 | 0 | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-27760-44124-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-20 | Sandblasted proposed anomaly and NDE did assessment | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44124-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-20 | Sandblasted proposed anomaly and NDE did assessment | TANNER | BRITT | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-27760-44124-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-20 | Sandblasted proposed anomaly and NDE did assessment | TANNER | BRITT | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44124-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-20 | Sandblasted proposed anomaly and NDE did assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-27760-44124-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-20 | Sandblasted proposed anomaly and NDE did assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44124-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-20 | Sandblasted proposed anomaly and NDE did assessment | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP5 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | CALEB | HOLTON | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | CALEB | Safety Fence | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 592 | 151 | 104 | 0 | 8 | 8 | 847 | [16 empty] | 847 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | Silt Fence | 225 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | T-Posts | 8 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | THOMAS | FRANKLIN | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | THOMAS | T-Post Caps | 8 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 492 | 151 | 104 | 0 | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | THOMAS | FRANKLIN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | THOMAS | FRANKLIN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | MICHAEL | ANISZEWSKI | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | BOLDBAUTOR | ZORIGT | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | [16 empty] | 675 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | BOLDBAUTOR | ZORIGT | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | BOLDBAUTOR | ZORIGT | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | JORDAN | WIGGINS | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | [16 empty] | 895 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | JORDAN | WIGGINS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | JORDAN | WIGGINS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | DAVID | KNOTTS | Laborer | 8 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 376 | 151 | 724 |  | 8 | 8 | 1251 | [16 empty] | 1251 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | DAVID | KNOTTS | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | DAVID | KNOTTS | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | TANNER | BRITT | Laborer | 8 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 376 | 151 | 220 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | ALDO | RENYA | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | [16 empty] | 707 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | ALDO | RENYA | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | ALDO | RENYA | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Hammer Attachment | 8 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Padding Bucket | 8 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-35680-44124-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-20 | MOB into site. Prepped site by putting up goal posts and marking lines. Started top soiling and excavation of proposed anomaly. | [7 empty] | Tool Trailer | 8 | HR | UTT2182 | [11 empty] | 5 |  |  |  | 40 |  |  | 8 | 40 | [16 empty] | 40 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | BARKLEY | BROWN | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | BARKLEY | BROWN | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | MATTHEW | LINDLEY | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | MATTHEW | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | WAYLON | GREEN | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | WAYLON | GREEN | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | JOSE | VALLES | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | LUTHER | LINDLEY | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | LUTHER | LINDLEY | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | MARCELO | GOMEZ | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | MARCELO | GOMEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | ANTHONY | MORENO | Laborer | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 | 151 | 32 |  | 2 | 2 | 277 | [16 empty] | 277 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | ANTHONY | MORENO | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44124-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-20 | Cleaned up site. Hauled trash and hazmat drums to Enbridge station in Seymore, IN | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | BARKLEY | BROWN | Foreman | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 322 |  | 52 |  | 4 | 4 | 374 | [16 empty] | 374 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | MATTHEW | LINDLEY | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | WAYLON | GREEN | Laborer | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 204 |  | 52 |  | 4 | 4 | 256 | [16 empty] | 256 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | JOSE | VALLES | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | LUTHER | LINDLEY | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | MARCELO | GOMEZ | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | ANTHONY | MORENO | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373B | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | [7 empty] | Water Pump ( up to 2") | 4 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 24 |  |  | 4 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44124-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-20 | Pumped water. Posted fire watch for NDE assessment | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | BARKLEY | BROWN | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | MATTHEW | LINDLEY | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | WAYLON | GREEN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | JOSE | VALLES | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | LUTHER | LINDLEY | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | MARCELO | GOMEZ | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | ANTHONY | MORENO | Laborer |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 252 |  | 64 |  | 4 | 4 | 316 | [16 empty] | 316 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373B | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858B | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44124-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-20 | Pumped water and posted fire watch for NDE | [7 empty] | Water Pump ( up to 2") | 4 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 24 |  |  | 4 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | URIEL | VALENCIA | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | R15349 | Filter Bags | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | 0 | [15 empty] | 847 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | URIEL | VALENCIA | Foreman | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 248 |  | 39 |  | 3 | 3 | 287 | 0 | [15 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | HECTOR | VALDEZ NEVAREZ | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | 0 | [15 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | HECTOR | VALDEZ NEVAREZ | Operator II | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 206 |  | 39 |  | 3 | 3 | 245 | 0 | [15 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | ALEJANDRO | CRUZ CONTRERAS | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | 0 | [15 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | ALEJANDRO | CRUZ CONTRERAS | Laborer | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 157 |  | 39 |  | 3 | 3 | 196 | 0 | [15 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | ASTOLFO | FLORES | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | [16 empty] | 567 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | ASTOLFO | FLORES | Laborer | 2 | 1 |  |  | Tool Trailer | 3 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 157 |  | 15 |  | 3 | 3 | 172 | [16 empty] | 172 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | IVAN | MADRID | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | 0 | [15 empty] | 675 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | IVAN | MADRID | Laborer | 2 | 1 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 157 |  | 55.5 |  | 3 | 3 | 212.5 | 0 | [15 empty] | 212.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | ROBERTO | RODRIGUEZ | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | 0 | [15 empty] | 895 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | ROBERTO | RODRIGUEZ | Laborer | 2 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 157 |  | 138 |  | 3 | 3 | 295 | 0 | [15 empty] | 295 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | JOEL | VALDEZ NEVAREZ | Laborer | 8 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 376 | 151 | 724 |  | 8 | 8 | 1251 | 0 | [15 empty] | 1251 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | JOEL | VALDEZ NEVAREZ | Laborer | 2 | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 157 |  | 271.5 |  | 3 | 3 | 428.5 | 0 | [15 empty] | 428.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | HECTOR | QUINTANA VALDEZ | Laborer | 8 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 376 | 151 | 220 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | HECTOR | QUINTANA VALDEZ | Laborer | 2 | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 157 |  | 82.5 |  | 3 | 3 | 239.5 | [16 empty] | 239.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | MATTHEW | SCHMITT | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | 0 | [15 empty] | 707 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | MATTHEW | SCHMITT | Truck Driver/CDL | 2 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 179 |  | 48 |  | 3 | 3 | 227 | 0 | [15 empty] | 227 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | [7 empty] | Hammer Attachment | 8 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | [7 empty] | Hammer Attachment | 3 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP7 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP7 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | 0 | [15 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | [7 empty] | Water Pump (3") | 8 | HR | 3INP7 | [11 empty] | 12 |  |  |  | 96 |  |  | 8 | 96 | 0 | [15 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44124-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-20 | Completed safety meeting. Dewatered and had constant flow of water in bellhole due to ranchers clay line. NDE tech completed their final measurements and we proceeded to cover soil pile and topsoil pile as weather shows more rain in forecast. Put up safety fence and cleaned up site | [7 empty] | Water Pump (3") | 3 | HR | 3INP7 | [11 empty] | 12 |  |  |  | 36 |  |  | 3 | 36 | 0 | [15 empty] | 36 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | GARRETT | DICKSON | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | Sand | 8 | Bag | ABATE | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | ABATE | [15 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | GARRETT | DICKSON | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15318 | Rockshield | 2 | LnFt |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 52 | 0 | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | T-Posts | 3 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | GARRETT | DICKSON | Foreman | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 174 |  | 26 |  | 2 | 2 | 200 | [16 empty] | 200 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | RYAN | COLEMAN | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | RYAN | COLEMAN | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | RYAN | COLEMAN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | RYAN | COLEMAN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | JACOB | GORDON | Laborer | 2 |  |  | 1 | Light Tower 6000 Watt | 2 | HR | RLP8 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | JACOB | GORDON | Laborer | 4 |  |  |  | Light Tower 6000 Watt | 4 | HR | RLP8 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 52 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | JACOB | GORDON | Laborer | 1 |  |  |  | Light Tower 6000 Watt | 1 | HR | RLP8 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | JACOB | GORDON | Laborer | 1 |  |  |  | Light Tower 6000 Watt | 1 | HR | RLP8 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | ZACHARY | POWDERS | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | ZACHARY | POWDERS | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | ZACHARY | POWDERS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | ZACHARY | POWDERS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | COLTON | ROBERTS | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | COLTON | ROBERTS | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | COLTON | ROBERTS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | COLTON | ROBERTS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | JUAN | DURAN | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | JUAN | DURAN | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | JUAN | DURAN | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | JUAN | DURAN | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | TANNER | BRUMMETT | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | TANNER | BRUMMETT | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 362 |  | 4 | 4 | 550 | [16 empty] | 550 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | TANNER | BRUMMETT | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | TANNER | BRUMMETT | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | IAIN | ALLRED | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | IAIN | ALLRED | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Water Pump ( up to 2") | 2 | HR | 2INP8 | [11 empty] | 6 |  |  |  | 12 |  |  | 2 | 12 | [16 empty] | 12 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44124-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-20 | Pumped water out of bellhole.Did maintence on silt fence Sloped sides of bellhole, crew began to move dirt from under pipe for NDE assessment and coating removal. Coating removal company came and NDE started assessment | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RBP8 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | GARRETT | DICKSON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | RYAN | COLEMAN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | RYAN | COLEMAN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | JACOB | GORDON | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | JACOB | GORDON | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | ZACHARY | POWDERS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | ZACHARY | POWDERS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | ZACHARY | POWDERS | Laborer |  | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 126 |  | 27.5 |  | 2 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | COLTON | ROBERTS | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 55 |  | 1 | 2 | 118 | [16 empty] | 118 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | COLTON | ROBERTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 46 |  | 2 | 1 | 172 | [16 empty] | 172 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | JUAN | DURAN | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 92 |  | 1 | 2 | 155 | [16 empty] | 155 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | JUAN | DURAN | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 90.5 |  | 2 | 1 | 216.5 | [16 empty] | 216.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | TANNER | BRUMMETT | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 181 |  | 1 | 2 | 244 | [16 empty] | 244 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | TANNER | BRUMMETT | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44124-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-20 | Lowboy driver moved equipment in. Staged equipment. NDE assessed pipe. 2 hands stayed to firewatch. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Matches crew 5 | TOME | KIRKLAND | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | 0 | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Matches crew 5 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | 0 | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Matches crew 5 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | [11 empty] | 98.8 | 0 | 0 | 151 |  |  | 988 | 151 |  |  | 10 |  | 1139 | [16 empty] | 1139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | CALEB | HOLTON | Foreman | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | CALEB | 4888 Coating | 5 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 | 151 | 13 | 0 | 1 | 1 | 238 | [16 empty] | 238 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | CALEB | HOLTON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | Brushes | 9 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | THOMAS | FRANKLIN | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 | 151 | 13 |  | 1 | 1 | 225.5 | [16 empty] | 225.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | THOMAS | FRANKLIN | Operator II | 7 | 2 |  |  | Pickup-F150 or F250 or equal | 9 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 596.5 |  | 117 |  | 9 | 9 | 713.5 | [16 empty] | 713.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 | 151 | 13 |  | 1 | 1 | 211 | [16 empty] | 211 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | MICHAEL | ANISZEWSKI | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | BOLDBAUTOR | ZORIGT | Laborer | 1 |  |  | 1 | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 | 151 | 5 |  | 1 | 1 | 203 | [16 empty] | 203 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | BOLDBAUTOR | ZORIGT | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | JORDAN | WIGGINS | Laborer | 1 |  |  | 1 | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 | 151 | 18.5 |  | 1 | 1 | 216.5 | [16 empty] | 216.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | JORDAN | WIGGINS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | DAVID | KNOTTS | Laborer | 1 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 | 151 | 46 |  | 1 | 1 | 244 | [16 empty] | 244 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | DAVID | KNOTTS | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | TANNER | BRITT | Laborer | 1 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 | 151 | 90.5 |  | 1 | 1 | 288.5 | [16 empty] | 288.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | TANNER | BRITT | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | ALDO | RENYA | Truck Driver/CDL | 1 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 | 151 | 16 |  | 1 | 1 | 220.5 | [16 empty] | 220.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | ALDO | RENYA | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP5 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-650-44129-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-25 | Blasted pipe for recoat, recoated pipe, jeeped pipe, put skids under exposed pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | CALEB | HOLTON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | THOMAS | FRANKLIN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | JORDAN | WIGGINS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | DAVID | KNOTTS | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | TANNER | BRITT | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | ALDO | RENYA | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-9400-44129-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | CALEB | HOLTON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | JORDAN | WIGGINS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | DAVID | KNOTTS | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | TANNER | BRITT | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | ALDO | RENYA | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1467 - MC.400216.032 - 646.441 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23260-44129-rev0 | DIG-1467 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 89163.97 | 23260 | Central | IN | 646.441 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | CALEB | HOLTON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | MICHAEL | ANISZEWSKI | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | JORDAN | WIGGINS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | DAVID | KNOTTS | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | TANNER | BRITT | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | ALDO | RENYA | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1468 - MC.400216.032 - 646.814 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-23770-44129-rev0 | DIG-1468 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 91118.47 | 23770 | Central | IN | 646.814 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | THOMAS | FRANKLIN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | BOLDBAUTOR | ZORIGT | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | JORDAN | WIGGINS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | DAVID | KNOTTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | TANNER | BRITT | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | ALDO | RENYA | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-27760-44129-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | CALEB | HOLTON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | THOMAS | FRANKLIN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | MICHAEL | ANISZEWSKI | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | BOLDBAUTOR | ZORIGT | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | JORDAN | WIGGINS | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 2 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 37 |  | 3 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | DAVID | KNOTTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | TANNER | BRITT | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | ALDO | RENYA | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-35680-44129-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-25 | Put skids under exposed pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | BARKLEY | BROWN | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Sand | 11 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | 2888 Coating | 13 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Brushes | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | JOSHUA | MENDARIES | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | Filter Bag | 2 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 | 0 | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | JOSHUA | MENDARIES | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JOSHUAM | Skids | 20 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 | 0 | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | JOSHUA | MENDARIES | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | WAYLON | GREEN | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | JOSE | VALLES | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | REYMUNDO | REYES | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | REYMUNDO | REYES | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | REYMUNDO | REYES | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | MARCELO | GOMEZ | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | MARCELO | GOMEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | ANTHONY | MORENO | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | EFREM | LEE | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | EFREM | LEE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | EFREM | LEE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Water Pump (3") | 2 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 24 |  |  | 2 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Water Pump (3") | 2 | HR | 3INP6-2 | [11 empty] | 12 |  |  |  | 24 |  |  | 2 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44129-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-25 | Dewatered dig, NDE inspection. Sandblasted and recoated | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | JOSHUA | MENDARIES | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | REYMUNDO | REYES | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | ANTHONY | MORENO | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | EFREM | LEE | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44129-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-25 | Helped with NDE assessment | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Filter Bag | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | BARKLEY | BROWN | Foreman | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Skids | 20 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 174 |  | 26 | 0 | 2 | 2 | 200 | [16 empty] | 200 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | JOSHUA | MENDARIES | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | JOSHUA | MENDARIES | Operator II | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 144.5 |  | 26 |  | 2 | 2 | 170.5 | [16 empty] | 170.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | WAYLON | GREEN | Laborer | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 110 |  | 26 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | JOSE | VALLES | Laborer | 1 | 1 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 110 |  | 10 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | REYMUNDO | REYES | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | REYMUNDO | REYES | Laborer | 1 | 1 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 110 |  | 37 |  | 2 | 2 | 147 | [16 empty] | 147 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | MARCELO | GOMEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | MARCELO | GOMEZ | Laborer | 1 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 110 |  | 92 |  | 2 | 2 | 202 | [16 empty] | 202 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | ANTHONY | MORENO | Laborer | 1 | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 110 |  | 181 |  | 2 | 2 | 291 | [16 empty] | 291 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | EFREM | LEE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | EFREM | LEE | Truck Driver/CDL | 1 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 125.5 |  | 32 |  | 2 | 2 | 157.5 | [16 empty] | 157.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Water Pump (3") | 2 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 24 |  |  | 2 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44129-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-25 | Dewatered hole, NDE did assessment. Jeeped pipe. Placed skids | [7 empty] | Water Pump (3") | 2 | HR | 3INP6-2 | [11 empty] | 12 |  |  |  | 24 |  |  | 2 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | URIEL | VALENCIA | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 | 151 | 65 |  | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | URIEL | VALENCIA | Foreman | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 422 |  | 65 |  | 5 | 5 | 487 | [16 empty] | 487 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | HECTOR | VALDEZ NEVAREZ | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | HECTOR | VALDEZ NEVAREZ | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | ALEJANDRO | CRUZ CONTRERAS | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | ALEJANDRO | CRUZ CONTRERAS | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | ASTOLFO | FLORES | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | ASTOLFO | FLORES | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | IVAN | MADRID | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | IVAN | MADRID | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | ROBERTO | RODRIGUEZ | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 230 |  | 5 | 5 | 616 | [16 empty] | 616 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | ROBERTO | RODRIGUEZ | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 230 |  | 5 | 5 | 497 | [16 empty] | 497 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | JOEL | VALDEZ NEVAREZ | Laborer | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 235 | 151 | 452.5 |  | 5 | 5 | 838.5 | [16 empty] | 838.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | JOEL | VALDEZ NEVAREZ | Laborer | 3 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 267 |  | 452.5 |  | 5 | 5 | 719.5 | [16 empty] | 719.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | HECTOR | QUINITANA VALDEZ | Laborer | 5 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 235 | 151 | 137.5 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | HECTOR | QUINITANA VALDEZ | Laborer | 3 | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 267 |  | 137.5 |  | 5 | 5 | 404.5 | [16 empty] | 404.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | MATTHEW | SCHMITT | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | MATTHEW | SCHMITT | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | [7 empty] | Hammer Attachment | 5 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | [7 empty] | Hammer Attachment | 5 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44129-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-25 | Had JSA meeting. Operator signed off on dig sheet for inspection. Backfilled. Once complete, compacted the sub soil. Top soil was pulled and restoration began. All trash and debris was removed from jobsite. Mats were taken off the road for De-MOB | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | GARRETT | DICKSON | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15318 | 2888 Coating | 1 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 52 | 0 | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Brushes | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | ZACHARY | POWDERS | Laborer | 4 |  |  |  | Tool Trailer | 3 | HR | 2178 | Silt Fence | 100 | Ft |  |  |  |  | 47 | 63 | 0 | 151 | 5 | 0 | 188 |  | 15 | 0 | 4 | 3 | 203 | [16 empty] | 203 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | ZACHARY | POWDERS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | COLTON | ROBERTS | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | COLTON | ROBERTS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | IAIN | ALLRED | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | [16 empty] | 46 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Hammer Attachment | 3 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP8 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-31790-44129-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-25 | Jeeped pipe and added coating to low mill spots. Ready for backfill in the morning | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | GARRETT | DICKSON | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 15318 | Silt Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | GARRETT | DICKSON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | RYAN | COLEMAN | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | RYANC | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | RYAN | COLEMAN | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYANC | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | RYAN | COLEMAN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYANC | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | JACOB | GORDON | Laborer | 1 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 47 | 151 |  |  | 1 |  | 198 | [16 empty] | 198 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | ZACHARY | POWDERS | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | ZACHARY | POWDERS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | ZACHARY | POWDERS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | COLTON | ROBERTS | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | COLTON | ROBERTS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | COLTON | ROBERTS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | JUAN | DURAN | Laborer | 1 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 47 | 151 |  |  | 1 |  | 198 | [16 empty] | 198 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | TANNER | BRUMMETT | Laborer | 1 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 47 | 151 |  |  | 1 |  | 198 | [16 empty] | 198 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | IAIN | ALLRED | Truck Driver/CDL | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 | 151 | 48 |  | 3 | 3 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | IAIN | ALLRED | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | [16 empty] | 46 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Hammer Attachment | 3 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP8 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44129-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-25 | Moved excavator to 1474 for backfill. Prepped bellhole for NDE assessment | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | JODY | BROOM | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | 0 | [15 empty] | 1003 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | JODY | BROOM | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | 0 | [15 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | TOME | KIRKLAND | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | 0 | [15 empty] | 1003 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | TOME | KIRKLAND | Superintendent |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 504 |  | 52 |  | 4 | 4 | 556 | 0 | [15 empty] | 556 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | JAY | MASEY | Quality Assurance Inspector | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 840 | 151 | 104 |  | 8 | 8 | 1095 | 0 | [15 empty] | 1095 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | JAY | MASEY | Quality Assurance Inspector |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 0 |  | 26 |  | 2 | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | MICHAEL | GOSS | Truck Driver/CDL | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 428 | 151 | 104 |  | 8 | 8 | 683 | 0 | [15 empty] | 683 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | MICHAEL | GOSS | Truck Driver/CDL |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 |  | 26 |  | 2 | 2 | 170 | 0 | [15 empty] | 170 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 107 | 151 | 26 |  | 2 | 2 | 284 | 0 | [15 empty] | 284 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 107 |  | 26 |  | 2 | 2 | 133 | 0 | [15 empty] | 133 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | JUANITO | RODRIGUEZ | Safety Person | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 104 |  | 8 | 8 | 847 | 0 | [15 empty] | 847 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | JUANITO | RODRIGUEZ | Safety Person |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | 0 | [15 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | DANIEL | YOUNG | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | 0 | [15 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | DANIEL | YOUNG | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | 0 | [15 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | KIM | FORNALL | Project Coordinator | 8 |  |  | 1 | Tractor/Semi | 8 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 790.4 | 151 | 336 |  | 8 | 8 | 1277.4 | 0 | [15 empty] | 1277.4 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | KIM | FORNALL | Project Coordinator |  | 2 |  |  | Tractor/Semi | 2 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 0 |  | 84 |  | 2 | 2 | 84 | 0 | [15 empty] | 84 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Tractor/Semi | 8 | HR | 1376 | [11 empty] | 42 |  |  |  | 336 |  |  | 8 | 336 | 0 | [15 empty] | 336 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Tractor/Semi | 2 | HR | 1376 | [11 empty] | 42 |  |  |  | 84 |  |  | 2 | 84 | 0 | [15 empty] | 84 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Lowboy Trailer | 8 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 148 |  |  | 8 | 148 | 0 | [15 empty] | 148 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Lowboy Trailer | 2 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | 0 | [15 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Lowboy Trailer | 8 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 148 |  |  | 8 | 148 | 0 | [15 empty] | 148 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Lowboy Trailer | 2 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | 0 | [15 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | RTB1 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | 0 | [15 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB1 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | 0 | [15 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | RTB2 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | 0 | [15 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | 0 | [15 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Kubota UTV | 8 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Kubota UTV | 2 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Kubota UTV | 8 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Matches crew 4 | [7 empty] | Kubota UTV | 2 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JONATHAN | HOLLEY | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JONATHAN | Clocksprings | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 | 0 | 1 | 1 | 87 | 0 | [15 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JONATHAN | HOLLEY | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | Sand | 7 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JONATHAN | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | 0 | [15 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | RYAN | FARINELLI | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | 0 | [15 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | RYAN | FARINELLI | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | RYAN | FARINELLI | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | 0 | [15 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | GREG | MCMILLIAN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | 0 | [15 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | GREG | MCMILLIAN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | 0 | [15 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | GREG | MCMILLIAN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | 0 | [15 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JERMAINE | EVANS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JERMAINE | EVANS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JERMAINE | EVANS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | 0 | [15 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | DEMETRIUS | MCDONALD | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | 0 | [15 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | DEMETRIUS | MCDONALD | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | 0 | [15 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | DEMETRIUS | MCDONALD | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | 0 | [15 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JOSE | ORTIZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | 0 | [15 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JOSE | ORTIZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | 0 | [15 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JOSE | ORTIZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | 0 | [15 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | ROBERT | FOSTER | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | 0 | [15 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | ROBERT | FOSTER | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | 0 | [15 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | ROBERT | FOSTER | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | 0 | [15 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | BRIAN | RANDLE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | 0 | [15 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | BRIAN | RANDLE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | 0 | [15 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | 0 | [15 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Padding Bucket | 1 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP1 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP1 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP1 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP1 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | 0 | [15 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JONATHAN | HOLLEY | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JONATHAN | Clocksprings | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 | 0 | 1 | 1 | 87 | 0 | [15 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JONATHAN | HOLLEY | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | Sand | 7 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JONATHAN | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | 0 | [15 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | RYAN | FARINELLI | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | 0 | [15 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | RYAN | FARINELLI | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | RYAN | FARINELLI | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | 0 | [15 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | GREG | MCMILLIAN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | 0 | [15 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | GREG | MCMILLIAN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | 0 | [15 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | GREG | MCMILLIAN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | 0 | [15 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JERMAINE | EVANS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JERMAINE | EVANS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JERMAINE | EVANS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | 0 | [15 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | DEMETRIUS | MCDONALD | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | 0 | [15 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | DEMETRIUS | MCDONALD | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | 0 | [15 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | DEMETRIUS | MCDONALD | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | 0 | [15 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JOSE | ORTIZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | 0 | [15 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JOSE | ORTIZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | 0 | [15 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | JOSE | ORTIZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | 0 | [15 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | ROBERT | FOSTER | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | 0 | [15 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | ROBERT | FOSTER | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | 0 | [15 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | ROBERT | FOSTER | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | 0 | [15 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | BRIAN | RANDLE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | 0 | [15 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | BRIAN | RANDLE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | 0 | [15 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | 0 | [15 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Padding Bucket | 1 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP1 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP1 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP1 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44131-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-27 | Tracked from 1548. Sandblasted and laced (2) clocksprings on pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP1 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | 0 | [15 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | Sand | 5 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | 0 | [15 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | T-Posts | 15 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | 0 | [15 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | 2888 Coating | 4 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | 0 | [15 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | Brushes | 10 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 83 |  | 13 | 0 | 1 | 1 | 96 | 0 | [15 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | 0 | [15 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | 0 | [15 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | JACOB | CAPITANO | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | 0 | [15 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | JACOB | CAPITANO | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | 0 | [15 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | JACOB | CAPITANO | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | 0 | [15 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | 0 | [15 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | 0 | [15 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | 0 | [15 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44131-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-27 | Had rock approach installed. Had a recoat so sandblasted and recoated. Ready to jeep and rockshield in AM | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP2 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | 0 | [15 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | KYLE | BONNEAU | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | KYLE | Sand | 40 | Bag | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | SAFEWAY | [15 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | KYLE | BONNEAU | Foreman | 6 |  |  |  | Pickup-F150 or F250 or equal | 6 | HR | KYLE | T-Posts | 20 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 444 |  | 78 | 0 | 6 | 6 | 522 | [16 empty] | 522 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | JESSE | BERTHIAUME | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | JESSE | BERTHIAUME | Operator II | 6 |  |  |  | Pickup-F150 or F250 or equal | 6 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 369 |  | 78 |  | 6 | 6 | 447 | [16 empty] | 447 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | JACOB | CAPITANO | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | JACOB | CAPITANO | Laborer | 6 |  |  |  | Pickup-F150 or F250 or equal | 6 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 |  | 78 |  | 6 | 6 | 360 | [16 empty] | 360 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | BROC | CALIGER | Laborer | 2 |  |  | 1 | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 25 |  | 2 | 5 | 270 | [16 empty] | 270 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | BROC | CALIGER | Laborer | 6 |  |  |  | Tool Trailer | 6 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 |  | 30 |  | 6 | 6 | 312 | [16 empty] | 312 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | CODY | GAXIOLA | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 37 |  | 5 | 2 | 423 | [16 empty] | 423 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | CODY | GAXIOLA | Laborer | 3 | 3 |  |  | 40' Flatbed trailer or equal | 6 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 330 |  | 111 |  | 6 | 6 | 441 | [16 empty] | 441 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | HEATHER | ENGLE | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 92 |  | 5 | 2 | 478 | [16 empty] | 478 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | HEATHER | ENGLE | Laborer | 3 | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 330 |  | 276 |  | 6 | 6 | 606 | [16 empty] | 606 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 3 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 376.5 |  | 96 |  | 6 | 6 | 472.5 | [16 empty] | 472.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Hammer Attachment | 5 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Hammer Attachment | 6 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Brush Hog | 5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Brush Hog | 6 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Light Tower 6000 Watt | 5 | HR | RLP2 | [11 empty] | 13 |  |  |  | 65 |  |  | 5 | 65 | [16 empty] | 65 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Light Tower 6000 Watt | 6 | HR | RLP2 | [11 empty] | 13 |  |  |  | 78 |  |  | 6 | 78 | [16 empty] | 78 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-10008649-44131-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-27 | NDE inspected 40ft joint. Coating removal arrived and removed coating. Sandblasted and NDE inspected again. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 6 | HR | RSP2 | [11 empty] | 23.5 |  |  |  | 141 |  |  | 6 | 141 | [16 empty] | 141 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | MATTHEW | LINDLEY | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 | 151 | 39 |  | 3 | 3 | 412 | 0 | [15 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | MATTHEW | LINDLEY | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 39 |  | 3 | 3 | 261 | 0 | [15 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | W. MONROE | LINDLEY | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | 0 | [15 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | W. MONROE | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | LUTHER | LINDLEY | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | 0 | [15 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | LUTHER | LINDLEY | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | 0 | [15 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | DEMETRIUS | DOBY | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | 0 | [15 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | DEMETRIUS | DOBY | Laborer | 2 |  |  |  | Tool Trailer | 8 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 40 |  | 2 | 8 | 134 | 0 | [15 empty] | 134 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | NICHOLAS | BLANCO | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 37 |  | 8 | 2 | 564 | 0 | [15 empty] | 564 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | NICHOLAS | BLANCO | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 8 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 148 |  | 2 | 8 | 242 | 0 | [15 empty] | 242 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | DANIEL | MENDOZA | Laborer | 8 | 1 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 439 | 151 | 92 |  | 9 | 2 | 682 | 0 | [15 empty] | 682 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | DANIEL | MENDOZA | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 368 |  | 2 | 8 | 462 | 0 | [15 empty] | 462 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | JESUS | MENDOZA | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | 0 | [15 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | JESUS | MENDOZA | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | 0 | [15 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | TYLER | BIGG | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 32 |  | 8 | 2 | 611 | 0 | [15 empty] | 611 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | TYLER | BIGG | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 128 |  | 2 | 8 | 235 | 0 | [15 empty] | 235 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | 0 | [15 empty] | 220 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP3 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP3 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-29300-44131-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-27 | Finished bellhole, mob excavtor to 0547, Began excavating pipe with jackhammer | [7 empty] | Padding Bucket | 8 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | MATTHEW | LINDLEY | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | Silt Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | MATTHEW | LINDLEY | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | Safety Fence | 160 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | 0 | [15 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | MATTHEW | LINDLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | T-Posts | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | 0 | [15 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | W, MONORE | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | W, MONORE | LINDLEY | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | 0 | [15 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | W, MONORE | LINDLEY | Operator II | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 227.5 |  | 39 |  | 3 | 3 | 266.5 | 0 | [15 empty] | 266.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | LUTHER | LINDLEY | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | 0 | [15 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | LUTHER | LINDLEY | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | 0 | [15 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | LUTHER | LINDLEY | Laborer | 1 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 173 |  | 181 |  | 3 | 2 | 354 | 0 | [15 empty] | 354 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | DEMETRIUS | DOBY | Laborer | 2 |  |  |  | Hammer Attachment | 2 | HR | RHA1066 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 94 |  | 0 |  | 2 | 2 | 94 | 0 | [15 empty] | 94 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | DEMETRIUS | DOBY | Laborer | 1 |  |  |  | Hammer Attachment | 1 | HR | RHA1066 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 47 |  | 0 |  | 1 | 1 | 47 | 0 | [15 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | DEMETRIUS | DOBY | Laborer | 1 | 2 |  |  | Hammer Attachment | 2 | HR | RHA1066 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 173 |  | 0 |  | 3 | 2 | 173 | 0 | [15 empty] | 173 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | JESUS | MENDOZA | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | 0 | [15 empty] | 94 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | JESUS | MENDOZA | Laborer | 1 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 47 |  |  |  | 1 |  | 47 | 0 | [15 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31230-44131-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-27 | Potholed, brought in 329 excavator to take compressor uphill. Began excavating, part of butter bar detached and shut down mechanical excavation. Continued potholing adjacent line and installed silted fence on down hill side of excavation. | JESUS | MENDOZA | Laborer | 1 | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 173 |  |  |  | 3 |  | 173 | 0 | [15 empty] | 173 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | GERALD | SMITH | Foreman | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 518 | 151 | 91 |  | 7 | 7 | 760 | 0 | [15 empty] | 760 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | GERALD | SMITH | Foreman | 1 | 3 |  |  | Pickup-F150 or F250 or equal | 4 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 374 |  | 52 |  | 4 | 4 | 426 | 0 | [15 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | MICHAEL | RATLIFF | Operator II | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 430.5 | 151 | 91 |  | 7 | 7 | 672.5 | 0 | [15 empty] | 672.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | MICHAEL | RATLIFF | Operator II | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 227.5 |  | 39 |  | 3 | 3 | 266.5 | 0 | [15 empty] | 266.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | OJ | SEALS | Laborer | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 329 | 151 | 91 |  | 7 | 7 | 571 | 0 | [15 empty] | 571 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | OJ | SEALS | Laborer | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 173 |  | 39 |  | 3 | 3 | 212 | 0 | [15 empty] | 212 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | RICHARD | ADKINS | Laborer | 7 |  |  | 1 | Tool Trailer | 7 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 329 | 151 | 35 |  | 7 | 7 | 515 | 0 | [15 empty] | 515 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | RICHARD | ADKINS | Laborer | 1 | 2 |  |  | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 173 |  | 15 |  | 3 | 3 | 188 | 0 | [15 empty] | 188 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | BARRETT | WISE | Laborer | 7 |  |  | 1 | 40' Flatbed trailer or equal | 7 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 329 | 151 | 129.5 |  | 7 | 7 | 609.5 | 0 | [15 empty] | 609.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | BARRETT | WISE | Laborer | 1 | 2 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 173 |  | 55.5 |  | 3 | 3 | 228.5 | 0 | [15 empty] | 228.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | DAVID | RATLIFF | Laborer | 7 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 329 | 151 | 322 |  | 7 | 7 | 802 | 0 | [15 empty] | 802 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | DAVID | RATLIFF | Laborer | 1 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 173 |  | 138 |  | 3 | 3 | 311 | 0 | [15 empty] | 311 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | 0 | [15 empty] | 883 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 633.5 |  |  | 7 | 633.5 | 0 | [15 empty] | 633.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | 0 | [15 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 192.5 |  |  | 7 | 192.5 | 0 | [15 empty] | 192.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | 0 | [15 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Light Tower 6000 Watt | 7 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 91 |  |  | 7 | 91 | 0 | [15 empty] | 91 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | 0 | [15 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Hammer Attachment | 7 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Hammer Attachment | 3 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Padding Bucket | 7 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44131-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-27 | Finished getting sand out of hole. Padded pipe with padding bucket, compacted under pipe w/ air pogo. Backfilled, placed topsoil back dressed up grass. | [7 empty] | Padding Bucket | 3 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | CALEB | HOLTON | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 592 | 151 | 52 |  | 8 | 4 | 795 | 0 | [15 empty] | 795 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | THOMAS | FRANKLIN | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | MICHAEL | ANISZEWSKI | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | 0 | [15 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | BOLDBAUTOR | ZORIGT | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | 0 | [15 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | JORDAN | WIGGINS | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | 0 | [15 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | DAVID | KNOTTS | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | 0 | [15 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | TANNER | BRITT | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | 0 | [15 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | ALDO | REYNA | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 192 |  | 12 | 12 | 1059 | 0 | [15 empty] | 1059 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | 0 | [15 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 4 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 98 |  |  | 4 | 98 | 0 | [15 empty] | 98 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | [7 empty] | Hammer Attachment | 4 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-9400-44131-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-27 | Rained out on ROW. Foreman picked up material for tomorrow. Truck driver went to Arkansas for material | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | BARKLEY | BROWN | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 |  | 4 | 4 | 499 | 0 | [15 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | JOSHUA | MENDARIES | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | JOSHUA | MENDARIES | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | WAYLON | GREEN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | 0 | [15 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | 0 | [15 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | JOSE | VALLES | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | 0 | [15 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | REYMUNDO | REYES | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | 0 | [15 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | REYMUNDO | REYES | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | 0 | [15 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | MARCELO | GOMEZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | 0 | [15 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | MARCELO | GOMEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | 0 | [15 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | ANTHONY | MORENO | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | 0 | [15 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | 0 | [15 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | EFREM | LEE | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | 0 | [15 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | EFREM | LEE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | 0 | [15 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | 0 | [15 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP6 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP6 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Hammer Attachment | 2 | HR | RAC0858A | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-50610-44131-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-27 | Completely cleaned up site and demob to 1489 | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | BRAKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Skids | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 | 0 | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | JOSHUA | MENDARIES | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | 0 | [15 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | REYMUNDO | REYES | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | 0 | [15 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | MARCELO | GOMEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | 0 | [15 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | 0 | [15 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | EFREM | LEE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | 0 | [15 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP6 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44131-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-27 | Set up all equipment. Welders to put sleeve on Wednesday morning. | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44131-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | Set up for welders to come in | BARKLEY | BROWN | Foreman | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Skids | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 248 |  | 39 | 0 | 3 | 3 | 287 | 0 | [15 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44131-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | Set up for welders to come in | JOSHUA | MENDARIES | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44131-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | Set up for welders to come in | WAYLON | GREEN | Laborer | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 157 |  | 39 |  | 3 | 3 | 196 | 0 | [15 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44131-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | Set up for welders to come in | JOSE | VALLES | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | 0 | [15 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44131-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | Set up for welders to come in | REYMUNDO | REYES | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | 0 | [15 empty] | 94 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44131-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | Set up for welders to come in | MARCELO | GOMEZ | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | 0 | [15 empty] | 94 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44131-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | Set up for welders to come in | ANTHONY | MORENO | Laborer | 2 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 94 |  |  |  | 2 |  | 94 | 0 | [15 empty] | 94 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44131-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-27 | Set up for welders to come in | EFREM | LEE | Truck Driver/CDL | 2 | [14 empty] | 53.5 | 72 | 0 | 151 |  |  | 107 |  |  |  | 2 |  | 107 | 0 | [15 empty] | 107 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | URIEL | VALENCIA | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | R15349 | Mats | 16 | Ea | BADGER1 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | BADGER1 | [15 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | URIEL | VALENCIA | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15349 | Silt Fence | 100 | Ft | BADGER2 | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | BADGER2 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | URIEL | VALENCIA | Foreman | 4 | 3 |  |  | Pickup-F150 or F250 or equal | 7 | HR | R15349 | Safety Fence | 250 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 596 |  | 91 | 0 | 7 | 7 | 687 | [16 empty] | 687 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | HECTOR | VALDEZ NEVAREZ | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | T-Posts | 17 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 123 | 151 | 26 | 0 | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | HECTOR | VALDEZ NEVAREZ | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | HECTOR | VALDEZ NEVAREZ | Operator II | 4 | 3 |  |  | Pickup-F150 or F250 or equal | 7 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 495 |  | 91 |  | 7 | 7 | 586 | [16 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | ALEJANDRO | CRUZ CONTRERAS | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | ALEJANDRO | CRUZ CONTRERAS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | ALEJANDRO | CRUZ CONTRERAS | Laborer | 4 | 3 |  |  | Pickup-F150 or F250 or equal | 7 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 377 |  | 91 |  | 7 | 7 | 468 | [16 empty] | 468 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | ASTOLFO | FLORES | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | ASTOLFO | FLORES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | ASTOLFO | FLORES | Laborer | 4 | 3 |  |  | Tool Trailer | 7 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 377 |  | 35 |  | 7 | 7 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | IVAN | MADRID | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | IVAN | MADRID | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | IVAN | MADRID | Laborer | 4 | 3 |  |  | 40' Flatbed trailer or equal | 7 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 377 |  | 129.5 |  | 7 | 7 | 506.5 | [16 empty] | 506.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | ROBERTO | RODRIGUEZ | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | ROBERTO | RODRIGUEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | ROBERTO | RODRIGUEZ | Laborer | 4 | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS0072 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 377 |  | 322 |  | 7 | 7 | 699 | [16 empty] | 699 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | JOEL | VALDEZ NEVAREZ | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | JOEL | VALDEZ NEVAREZ | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | JOEL | VALDEZ NEVAREZ | Laborer | 4 | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 377 |  | 633.5 |  | 7 | 7 | 1010.5 | [16 empty] | 1010.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | HECTOR | QUINTANA VALDEZ | Laborer | 2 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 | 151 | 55 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | HECTOR | QUINTANA VALDEZ | Laborer | 2 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 |  | 55 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | HECTOR | QUINTANA VALDEZ | Laborer | 4 | 3 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 377 |  | 192.5 |  | 7 | 7 | 569.5 | [16 empty] | 569.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | MATTHEW | SCHMITT | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | MATTHEW | SCHMITT | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | MATTHEW | SCHMITT | Truck Driver/CDL | 4 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 430 |  | 112 |  | 7 | 7 | 542 | [16 empty] | 542 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | [7 empty] | Light Tower 6000 Watt | 7 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 91 |  |  | 7 | 91 | [16 empty] | 91 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | [7 empty] | Hammer Attachment | 7 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | [7 empty] | Padding Bucket | 2 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | [7 empty] | Padding Bucket | 2 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-110-44131-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-27 | Had JSA meeting. All permits signed. (2) hydrovac trucks slot trenching. (12) mats used for trucks to access dump site, (2) mats over drainage ditch. Put up goal posts. Silt fence was installed around mat bridge to retain all mud coming off trucks. Waiting on slot trenching to be completed to continue with mechianical excavation | [7 empty] | Padding Bucket | 7 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | GARRETT | DICKSON | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | 4888 Coating | 4 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | 0 | [15 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | GARRETT | DICKSON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | Silt Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | GARRETT | DICKSON | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15318 | Brushes | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 52 | 0 | 4 | 4 | 348 | 0 | [15 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | GARRETT | DICKSON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | 0 | [15 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | SHAWN | ROSE | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | 0 | [15 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | SHAWN | ROSE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | SHAWN | ROSE | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | 0 | [15 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | SHAWN | ROSE | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | 0 | [15 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | COLTON | ROBERTS | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | 0 | [15 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | COLTON | ROBERTS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | COLTON | ROBERTS | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | 0 | [15 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | COLTON | ROBERTS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | 0 | [15 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | ZACHARY | POWDERS | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | 0 | [15 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | ZACHARY | POWDERS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | 0 | [15 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | ZACHARY | POWDERS | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | 0 | [15 empty] | 262 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | ZACHARY | POWDERS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | 0 | [15 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | IAIN | ALLRED | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | 0 | [15 empty] | 883 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | 0 | [15 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | 0 | [15 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | 0 | [15 empty] | 184 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | 0 | [15 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | 0 | [15 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | 0 | [15 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Padding Bucket | 2 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Padding Bucket | 2 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Padding Bucket | 4 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Padding Bucket | 2 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP8 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44131-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-27 | Held JSA. NDE inspected pipe. Not enough mills on coating. Crew prepped the pipe and recoated. Placed more silt fence and fenced off site and cleaned up. Driver went to kentucky for materials for (4) crews. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44131-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-27 | Held Jsa. Marker was not correct, had to move 28ft up hill. Hit rock. Had to install couplers for hammer. Hand dug and found pipe laying on top of thick slab of rock. Used jackhammer while mechanic was working on excavator. Hydraulic line was leaking after we began to hammer. Went back to jackhammering and hand digging to get pipe fully exposed. | RENE | CASAREZ | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | RENE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 156 |  | 12 | 12 | 1299 | 0 | [15 empty] | 1299 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44131-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-27 | Held Jsa. Marker was not correct, had to move 28ft up hill. Hit rock. Had to install couplers for hammer. Hand dug and found pipe laying on top of thick slab of rock. Used jackhammer while mechanic was working on excavator. Hydraulic line was leaking after we began to hammer. Went back to jackhammering and hand digging to get pipe fully exposed. | DONALD | TIGUE | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 824 | 151 | 156 |  | 12 | 12 | 1131 | 0 | [15 empty] | 1131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44131-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-27 | Held Jsa. Marker was not correct, had to move 28ft up hill. Hit rock. Had to install couplers for hammer. Hand dug and found pipe laying on top of thick slab of rock. Used jackhammer while mechanic was working on excavator. Hydraulic line was leaking after we began to hammer. Went back to jackhammering and hand digging to get pipe fully exposed. | DAVID | LOPEZ | Laborer | 8 | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 12 | HR | REX0278 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 628 | 151 | 1086 |  | 12 | 12 | 1865 | 0 | [15 empty] | 1865 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44131-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-27 | Held Jsa. Marker was not correct, had to move 28ft up hill. Hit rock. Had to install couplers for hammer. Hand dug and found pipe laying on top of thick slab of rock. Used jackhammer while mechanic was working on excavator. Hydraulic line was leaking after we began to hammer. Went back to jackhammering and hand digging to get pipe fully exposed. | FERNANDO | GARCIA | Laborer | 8 | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 628 | 151 | 552 |  | 12 | 12 | 1331 | 0 | [15 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44131-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-27 | Held Jsa. Marker was not correct, had to move 28ft up hill. Hit rock. Had to install couplers for hammer. Hand dug and found pipe laying on top of thick slab of rock. Used jackhammer while mechanic was working on excavator. Hydraulic line was leaking after we began to hammer. Went back to jackhammering and hand digging to get pipe fully exposed. | ADDEY | BENNETT | Laborer | 8 | 4 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 12 | HR | RAC78982 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 628 | 151 | 330 |  | 12 | 12 | 1109 | 0 | [15 empty] | 1109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44131-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-27 | Held Jsa. Marker was not correct, had to move 28ft up hill. Hit rock. Had to install couplers for hammer. Hand dug and found pipe laying on top of thick slab of rock. Used jackhammer while mechanic was working on excavator. Hydraulic line was leaking after we began to hammer. Went back to jackhammering and hand digging to get pipe fully exposed. | MARGIL | GARZA | Laborer | 8 | 4 |  | 1 | Hammer Attachment | 12 | HR | RHA0141A | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 628 | 151 | 0 |  | 12 | 12 | 779 | 0 | [15 empty] | 779 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44131-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-27 | Held Jsa. Marker was not correct, had to move 28ft up hill. Hit rock. Had to install couplers for hammer. Hand dug and found pipe laying on top of thick slab of rock. Used jackhammer while mechanic was working on excavator. Hydraulic line was leaking after we began to hammer. Went back to jackhammering and hand digging to get pipe fully exposed. | JODY | HASTON | Truck Driver/CDL | 8 | 4 |  | 1 | Padding Bucket | 12 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 716 | 151 | 0 |  | 12 | 12 | 867 | 0 | [15 empty] | 867 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [16 empty] | 1541 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | TOME | KIRKLAND | Superintendent |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1512 | 151 | 156 |  | 12 | 12 | 1819 | [16 empty] | 1819 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | JUANITO | RODRIGUEZ | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Kubota UTV | 10 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP1 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP2 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP3 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP5 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP6 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44126-rev1 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-22 | Matches crew 8 | [7 empty] | Padding Bucket | 10 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | JONATHAN | HOLLEY | Foreman |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | Sand | 11 | Bag | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 400 | 151 | 52 | 0 | 4 | 4 | 603 | SAFEWAY | [15 empty] | 603 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | RYAN | FARINELLI | Operator II |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 | 151 | 52 |  | 4 | 4 | 535 | [16 empty] | 535 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | GREG | MCMILLIAN | Laborer |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 | 151 | 52 |  | 4 | 4 | 455 | [16 empty] | 455 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | JERMAINE | EVANS | Laborer |  | 4 |  | 1 | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 | 151 | 20 |  | 4 | 4 | 423 | [16 empty] | 423 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | DEMETRIUS | MCDONALD | Laborer |  | 4 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 | 151 | 74 |  | 4 | 4 | 477 | [16 empty] | 477 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | JOSE | ORTIZ | Laborer |  | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 | 151 | 184 |  | 4 | 4 | 587 | [16 empty] | 587 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | ROBERT | FOSTER | Laborer |  | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 | 151 | 362 |  | 4 | 4 | 765 | [16 empty] | 765 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | ROBERT | FOSTER | Laborer |  | 5 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8430 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 315 |  | 110 |  | 5 | 4 | 425 | [16 empty] | 425 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | BRIAN | RANDLE | Truck Driver/CDL |  | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 | 151 | 64 |  | 4 | 4 | 503 | [16 empty] | 503 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [7 empty] | Hammer Attachment | 4 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [7 empty] | Padding Bucket | 4 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 4 | HR | RSP1 | [11 empty] | 23.5 |  |  |  | 94 |  |  | 4 | 94 | [16 empty] | 94 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-14960-44126-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-22 | Safeway removed 10FT of coating, sandblasted so NDE could do assessment. | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | JONATHAN | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | JONATHAN | HOLLEY | Foreman |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 600 |  | 78 |  | 6 | 6 | 678 | [16 empty] | 678 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | RYAN | FARNIELLI | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | RYAN | FARNIELLI | Operator II |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 498 |  | 78 |  | 6 | 6 | 576 | [16 empty] | 576 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | GREG | MCMILLIAN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | GREG | MCMILLIAN | Laborer |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 |  | 78 |  | 6 | 6 | 456 | [16 empty] | 456 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | JERMAINE | EVANS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | JERMAINE | EVANS | Laborer |  | 6 |  |  | Tool Trailer | 6 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 |  | 30 |  | 6 | 6 | 408 | [16 empty] | 408 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | DEMETRIUS | MCDONALD | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | DEMETRIUS | MCDONALD | Laborer |  | 6 |  |  | 40' Flatbed trailer or equal | 6 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 |  | 111 |  | 6 | 6 | 489 | [16 empty] | 489 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | JOSE | ORTIZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | JOSE | ORTIZ | Laborer |  | 6 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 378 |  | 276 |  | 6 | 6 | 654 | [16 empty] | 654 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | ROBERT | FOSTER | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | BRIAN | RANDLE | Truck Driver/CDL |  | 6 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 |  | 96 |  | 6 | 6 | 528 | [16 empty] | 528 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [7 empty] | Hammer Attachment | 6 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [7 empty] | Padding Bucket | 6 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-16230-44126-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-22 | MOB into site, started to locate line | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | KYLE | BONNEAU | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 600 | 151 | 78 |  | 6 | 6 | 829 | [16 empty] | 829 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | KYLE | BONNEAU | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | [16 empty] | 565 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | JESSE | BERTHIAUME | Operator II |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 498 | 151 | 78 |  | 6 | 6 | 727 | [16 empty] | 727 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | JESSE | BERTHIAUME | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | CADEN | THOMPSON | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | CADEN | THOMPSON | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | JACOB | CAPITANO | Laborer |  | 6 |  | 1 | Tool Trailer | 6 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 378 | 151 | 30 |  | 6 | 6 | 559 | [16 empty] | 559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | JACOB | CAPITANO | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | BROC | CALIGER | Laborer |  | 6 |  | 1 | 40' Flatbed trailer or equal | 6 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 378 | 151 | 111 |  | 6 | 6 | 640 | [16 empty] | 640 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | BROC | CALIGER | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | CODY | GAXIOLA | Laborer |  | 6 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 378 | 151 | 276 |  | 6 | 6 | 805 | [16 empty] | 805 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | CODY | GAXIOLA | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | HEATHER | ENGEL | Laborer |  | 6 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 378 | 151 | 543 |  | 6 | 6 | 1072 | [16 empty] | 1072 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | HEATHER | ENGEL | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 6 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 432 | 151 | 96 |  | 6 | 6 | 679 | [16 empty] | 679 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | [7 empty] | Hammer Attachment | 6 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | [7 empty] | Hammer Attachment | 4 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | [7 empty] | Brush Hog | 6 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | [7 empty] | Brush Hog | 4 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | [7 empty] | Padding Bucket | 6 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44126-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-22 | Started with JSA, began excavating, chased pipe to find weld for reference point. Began to dig down and get ready for hammer. We were shut down due to a positive COVID test from labor hand. | [7 empty] | Padding Bucket | 4 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | MICHAEL | RATLIFF | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MICHAELR | Sand | 10 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 | 151 | 26 | 0 | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | MICHAEL | RATLIFF | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | Rockshield | 6 | LnFt |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 400 |  | 52 | 0 | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | MICHAEL | RATLIFF | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | SHAWN | ROSE | Operator II | 1 | 1 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 144.5 | 151 | 26 |  | 2 | 2 | 321.5 | [16 empty] | 321.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | SHAWN | ROSE | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | SHAWN | ROSE | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | MICHAEL | ELLIOTT | Laborer | 1 | 1 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 110 | 151 | 26 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | MICHAEL | ELLIOTT | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | MICHAEL | ELLIOTT | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | DAVID | RATLIFF | Laborer | 1 | 1 |  | 1 | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 110 | 151 | 10 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | DAVID | RATLIFF | Laborer |  | 5 |  |  | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 |  | 20 |  | 5 | 4 | 335 | [16 empty] | 335 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | DAVID | RATLIFF | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | TYLER | BIGG | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | TYLER | BIGG | Truck Driver/CDL | 2 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 251 |  | 64 |  | 4 | 4 | 315 | [16 empty] | 315 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | TYLER | BIGG | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | [16 empty] | 184 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Hammer Attachment | 4 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Hammer Attachment | 3 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Padding Bucket | 4 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Padding Bucket | 3 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28110-44126-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-22 | Hammered/excavated appx 50 yards of rock. Pipe and coating was inspected and prepped. Sandblasted for NDE inspection | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | RSP3 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44126-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-22 | Went to 1553 to start staging | MICHAEL | RATLIFF | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44126-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-22 | Went to 1553 to start staging | MICHAEL | ELLIOTT | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44126-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-22 | Went to 1553 to start staging | TYLER | BIGG | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | GERALD | SMITH | Foreman |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | GERALD | Sand | 10 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 | 151 | 39 | 0 | 3 | 3 | 490 | [16 empty] | 490 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | GERALD | SMITH | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | GERALD | 4888 Coating | 30 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | RICHARD | SHOEMAKE | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | RICHARDS | Brushes | 36 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 307.5 | 151 | 65 | 0 | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | RICHARD | SHOEMAKE | Operator II | 1 | 4 |  |  | Pickup-F150 or F250 or equal | 5 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 393.5 |  | 65 |  | 5 | 5 | 458.5 | [16 empty] | 458.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | OJ | SEALS | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | OJ | SEALS | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | JAMES | KERVIN | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | JAMES | KERVIN | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | RICHARD | ADKINS | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 0 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 0 |  | 2 | 0 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | RICHARD | ADKINS | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 0 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 0 |  | 3 | 0 | 141 | [16 empty] | 141 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | NICHOLAS | BLANCO | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 452.5 |  | 2 | 5 | 697.5 | [16 empty] | 697.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | NICHOLAS | BLANCO | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 452.5 |  | 3 | 5 | 593.5 | [16 empty] | 593.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | BARRETT | WISE | Laborer | 2 |  |  | 1 | Light Tower 6000 Watt | 5 | HR | RLP9317 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 65 |  | 2 | 5 | 310 | [16 empty] | 310 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | BARRETT | WISE | Laborer | 3 |  |  |  | Light Tower 6000 Watt | 5 | HR | RLP9317 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 65 |  | 3 | 5 | 206 | [16 empty] | 206 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | [7 empty] | Padding Bucket | 5 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | [7 empty] | Padding Bucket | 5 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | [7 empty] | Hammer Attachment | 5 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | [7 empty] | Hammer Attachment | 5 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44126-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-22 | Swept pipe sandblasted and applied second coat of 4888 | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP4 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | GERALD | SMITH | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | GERALD | 2888 Coating | 5 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | GERALD | SMITH | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | GERALD | Brushes | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | OJ | SEALS | Laborer | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | Rockshield | 420 | LnFt |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 110 |  | 26 | 0 | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | OJ | SEALS | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | JAMES | KERVIN | Laborer | 1 | 1 |  |  | Tool Trailer | 2 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 110 |  | 10 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | JAMES | KERVIN | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | RICHARD | ADKINS | Laborer | 1 | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 110 |  |  |  | 2 |  | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | RICHARD | ADKINS | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | NICHOLAS | BLANCO | Laborer | 1 | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 110 |  |  |  | 2 |  | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | NICHOLAS | BLANCO | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | BARRETT | WISE | Laborer | 1 | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 110 |  |  |  | 2 |  | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | BARRETT | WISE | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44126-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-22 | Jeeped pipe and made repairs to coating. Installed rockshield for backfilling | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44126-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-22 | MOB excavator to dig. Safeway knocked off coating from proposed anomaly. | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB |  |  |  | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | SAFEWAY | [15 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44126-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-22 | MOB excavator to dig. Safeway knocked off coating from proposed anomaly. | THOMAS | FRANKLIN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44126-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-22 | MOB excavator to dig. Safeway knocked off coating from proposed anomaly. | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44126-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-22 | MOB excavator to dig. Safeway knocked off coating from proposed anomaly. | BOLDBAUTOR | ZORIGT | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44126-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-22 | MOB excavator to dig. Safeway knocked off coating from proposed anomaly. | JORDAN | WIGGINS | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44126-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-22 | MOB excavator to dig. Safeway knocked off coating from proposed anomaly. | DAVID | KNOTTS | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44126-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-22 | MOB excavator to dig. Safeway knocked off coating from proposed anomaly. | TANNER | BRITT | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44126-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-22 | MOB excavator to dig. Safeway knocked off coating from proposed anomaly. | ALDO | REYNA | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | CALEB | HOLTON | Foreman |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | CALEB | Sand | 18 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 1000 | 151 | 130 | 0 | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | T-Posts | 10 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | THOMAS | FRANKLIN | Operator II | 1 | 9 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | THOMAS | T-Post Caps | 10 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 808.5 | 151 | 130 | 0 | 10 | 10 | 1089.5 | [16 empty] | 1089.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | THOMAS | FRANKLIN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | MICHAEL | ANISZEWSKI | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | BOLDBAUTOR | ZORIGT | Laborer | 1 | 9 |  | 1 | Tool Trailer | 10 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 614 | 151 | 50 |  | 10 | 10 | 815 | [16 empty] | 815 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | BOLDBAUTOR | ZORIGT | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | JORDAN | WIGGINS | Laborer | 1 | 9 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 614 | 151 | 185 |  | 10 | 10 | 950 | [16 empty] | 950 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | JORDAN | WIGGINS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | DAVID | KNOTTS | Laborer |  | 10 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 630 | 151 | 460 |  | 10 | 10 | 1241 | [16 empty] | 1241 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | DAVID | KNOTTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | TANNER | BRITT | Laborer |  | 10 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 630 | 151 | 905 |  | 10 | 10 | 1686 | [16 empty] | 1686 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | TANNER | BRITT | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | ALDO | RENYA | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | ALDO | RENYA | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | [7 empty] | Hammer Attachment | 10 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | [7 empty] | Padding Bucket | 10 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44126-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-22 | Finished excavation at proposed anomaly, NDE assessed pipe and we sandblasted pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP5 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | BARKLEY | BROWN | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 200 | 151 | 26 | 0 | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | MATTHEW | LINDLEY | Operator II |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 | 151 | 26 |  | 2 | 2 | 343 | [16 empty] | 343 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | WAYLON | GREEN | Laborer |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 | 151 | 26 |  | 2 | 2 | 303 | [16 empty] | 303 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | JOSE | VALLES | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | LUTHER | LINDLEY | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | MARCELO | GOMEZ | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | ANTHONY | MORENO | Laborer |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 | 151 | 32 |  | 2 | 2 | 309 | [16 empty] | 309 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44126-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-22 | Dewatered, cleaned out bellhole in prep to sandblast tomorrow | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | 2888 Coating | 9 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Brushes | 30 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | BARKLEY | BROWN | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Safety Fence | 60 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | Sand | 7 | Bag |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 83 |  | 13 | 0 | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | MATTHEW | LINDLEY | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | WAYLON | GREEN | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | LUTHER | LINDLEY | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | ANTHONY | MORENO | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | ANTHONY | MORENO | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | ANTHONY | MORENO | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | ANTHONY | MORENO | Laborer |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 189 |  | 32 |  | 3 | 2 | 221 | [16 empty] | 221 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Water Pump ( up to 2") | 1 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 6 |  |  | 1 | 6 | [16 empty] | 6 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44126-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-22 | Dewatered, sandblasted and coated with 2888. Due to pipe sweating because of pressure, will have to remove the 2888 and coat with 4888 tomorrow. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Sand | 7 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | ANTHONY | MORENO | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | ANTHONY | MORENO | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | ANTHONY | MORENO | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44126-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-22 | Sandblasted for NDE to inspect and X-Ray | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | URIEL | VALENCIA | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15349 | Sand | 47 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | URIEL | VALENCIA | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15349 | Filter Bag | 3 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 | 0 | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | URIEL | VALENCIA | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | HECTOR | VALDEZ NEVAREZ | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | HECTOR | VALDEZ NEVAREZ | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | HECTOR | VALDEZ NEVAREZ | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | ASTOLFO | FLORES | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | ASTOLFO | FLORES | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | ASTOLFO | FLORES | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | IVAN | MADRID | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | IVAN | MADRID | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | IVAN | MADRID | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | ROBERTO | RODRIGUEZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | ROBERTO | RODRIGUEZ | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | ROBERTO | RODRIGUEZ | Laborer |  | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 |  | 184 |  | 4 | 4 | 436 | [16 empty] | 436 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | JOEL | VALDEZ NEVAREZ | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | JOEL | VALDEZ NEVAREZ | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | JOEL | VALDEZ NEVAREZ | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | HECTOR | QUINTANA VALDEZ | Laborer | 4 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 188 | 151 | 110 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | HECTOR | QUINTANA VALDEZ | Laborer |  | 4 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 252 |  | 110 |  | 4 | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | HECTOR | QUINTANA VALDEZ | Laborer |  | 4 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 252 |  | 110 |  | 4 | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | MATTHEW | SCHMITT | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | MATTHEW | SCHMITT | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | [7 empty] | Water Pump (3") | 12 | HR | 3INP7 | [11 empty] | 12 |  |  |  | 144 |  |  | 12 | 144 | [16 empty] | 144 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44126-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-22 | Started with JSA. Dewatered bellhole from 7:30-10:30. Started sandblasting pipe at 10:30 and finished at 2:45. NDE got into bellhole to assess at 2:48 and done at 6:30. Cleaned up site and fenced off. | [7 empty] | Water Pump (3") | 12 | HR | 3INP7-2 | [11 empty] | 12 |  |  |  | 144 |  |  | 12 | 144 | [16 empty] | 144 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [16 empty] | 1541 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | TOME | KIRKLAND | Superintendent |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1512 | 151 | 130 |  | 12 | 10 | 1793 | [16 empty] | 1793 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | JUANITO | RODRIGUEZ | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Kubota UTV | 10 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP1 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP2 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP3 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP5 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP6 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev1 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | Match crew 6 | [7 empty] | Padding Bucket | 10 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | JONATHAN | HOLLEY | Foreman |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | JONATHAN | Sand | 12 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 16 | 0 | 200 | 151 | 32 | 0 | 2 | 2 | 383 | [16 empty] | 383 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | JONATHAN | HOLLEY | Foreman |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | JONATHAN | 2888 Coating | 13 | L |  |  |  |  | 74 | 100 | 0 | 151 | 16 | 0 | 300 |  | 48 | 0 | 3 | 3 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | JONATHAN | HOLLEY | Foreman |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | JONATHAN | Clocksprings | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 16 |  | 500 |  | 80 | 0 | 5 | 5 | 580 | [16 empty] | 580 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | RYAN | FARINELLI | Operator II |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 166 | 151 | 32 |  | 2 | 2 | 349 | [16 empty] | 349 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | RYAN | FARINELLI | Operator II |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 249 |  | 48 |  | 3 | 3 | 297 | [16 empty] | 297 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | RYAN | FARINELLI | Operator II |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 16 |  | 415 |  | 80 |  | 5 | 5 | 495 | [16 empty] | 495 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | GREG | MCMILLIAN | Laborer |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 126 | 151 | 32 |  | 2 | 2 | 309 | [16 empty] | 309 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | GREG | MCMILLIAN | Laborer |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 189 |  | 48 |  | 3 | 3 | 237 | [16 empty] | 237 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | GREG | MCMILLIAN | Laborer |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 315 |  | 80 |  | 5 | 5 | 395 | [16 empty] | 395 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | JERMAINE | EVANS | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | JERMAINE | EVANS | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | JERMAINE | EVANS | Laborer |  | 5 |  |  | Tool Trailer | 5 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 |  | 25 |  | 5 | 5 | 340 | [16 empty] | 340 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | DEMETRIUS | MCDONALD | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | DEMETRIUS | MCDONALD | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | DEMETRIUS | MCDONALD | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 92.5 |  | 5 | 5 | 407.5 | [16 empty] | 407.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | JOSE | ORTIZ | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | JOSE | ORTIZ | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | JOSE | ORTIZ | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | ROBERT | FOSTER | Laborer |  | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 | 151 | 181 |  | 2 | 2 | 458 | [16 empty] | 458 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | ROBERT | FOSTER | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | ROBERT | FOSTER | Laborer |  | 5 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 |  | 452.5 |  | 5 | 5 | 767.5 | [16 empty] | 767.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 151 | 32 |  | 2 | 2 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | BRIAN | RANDLE | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | BRIAN | RANDLE | Truck Driver/CDL |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 |  | 80 |  | 5 | 5 | 440 | [16 empty] | 440 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Hammer Attachment | 3 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Hammer Attachment | 5 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Padding Bucket | 3 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Padding Bucket | 5 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44127-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-23 | Sandblasted both spots on 1549, installed clockspring and used 2888 coating on spots. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP1 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | KYLE | BONNEAU | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | KYLE | Straw Bales | 3 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 600 | 151 | 78 | 0 | 6 | 6 | 829 | [16 empty] | 829 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | Safety Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | KYLE | BONNEAU | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | KYLE | 2888 Coating | 1 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | KYLE | BONNEAU | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | KYLE | Sand | 1 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | JESSE | BERTHIAUME | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 | 151 | 65 |  | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | JESSE | BERTHIAUME | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | CADEN | THOMPSON | Laborer |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 | 151 | 65 |  | 5 | 5 | 531 | [16 empty] | 531 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | CADEN | THOMPSON | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | CADEN | THOMPSON | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | CADEN | THOMPSON | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | JACOB | CAPITANO | Laborer |  | 5 |  | 1 | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 | 151 | 25 |  | 5 | 5 | 491 | [16 empty] | 491 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | JACOB | CAPITANO | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | JACOB | CAPITANO | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | JACOB | CAPITANO | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | BROC | CALIGER | Laborer |  | 5 |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 | 151 | 92.5 |  | 5 | 5 | 558.5 | [16 empty] | 558.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | BROC | CALIGER | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | CODY | GAXIOLA | Laborer |  | 5 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 | 151 | 230 |  | 5 | 5 | 696 | [16 empty] | 696 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | CODY | GAXIOLA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | CODY | GAXIOLA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | CODY | GAXIOLA | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | HEATHER | ENGLE | Laborer |  | 5 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 | 151 | 452.5 |  | 5 | 5 | 918.5 | [16 empty] | 918.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | HEATHER | ENGLE | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | HEATHER | ENGLE | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | HEATHER | ENGLE | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | ALTANOCHIR | JANSTAN | Truck Driver/CDL |  | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 | 151 | 80 |  | 5 | 5 | 591 | [16 empty] | 591 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | ALTANOCHIR | JANSTAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | ALTANOCHIR | JANSTAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | ALTANOCHIR | JANSTAN | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Hammer Attachment | 5 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Hammer Attachment | 1 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Hammer Attachment | 1 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Hammer Attachment | 3 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Brush Hog | 5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Brush Hog | 1 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Brush Hog | 1 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Brush Hog | 3 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Padding Bucket | 5 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Padding Bucket | 1 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Padding Bucket | 1 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-17790-44127-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-23 | Had JSA meeting, hammered rock and finished excavation. NDE examined and had coating removed. Waited on NDE to inspect before blasting. They did not show. | [7 empty] | Padding Bucket | 3 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | MICHAEL | RATLIFF | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | MICHAELR | Silt Fence | 50 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | MICHAEL | RATLIFF | Foreman | 3 | 3 |  |  | Pickup-F150 or F250 or equal | 6 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 522 |  | 78 |  | 6 | 6 | 600 | [16 empty] | 600 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | SHAWN | ROSE | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | SHAWN | ROSE | Operator II | 3 | 3 |  |  | Pickup-F150 or F250 or equal | 6 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 433.5 |  | 78 |  | 6 | 6 | 511.5 | [16 empty] | 511.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | MICHAEL | ELLIOTT | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | MICHAEL | ELLIOTT | Laborer | 3 | 3 |  |  | Pickup-F150 or F250 or equal | 6 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 330 |  | 78 |  | 6 | 6 | 408 | [16 empty] | 408 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | DAVID | RATLIFF | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | DAVID | RATLIFF | Laborer | 3 | 3 |  |  | Tool Trailer | 6 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 330 |  | 30 |  | 6 | 6 | 360 | [16 empty] | 360 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | TYLER | BIGG | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | TYLER | BIGG | Truck Driver/CDL | 3 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 376.5 |  | 96 |  | 6 | 6 | 472.5 | [16 empty] | 472.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | 40' Flatbed trailer or equal | 6 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 111 |  |  | 6 | 111 | [16 empty] | 111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 276 |  |  | 6 | 276 | [16 empty] | 276 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Hammer Attachment | 5 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Hammer Attachment | 6 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Padding Bucket | 5 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44127-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-23 | Potholed and found seam. Seam was downstream, started digging upstream | [7 empty] | Padding Bucket | 6 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-1940-44127-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-23 | Jeeped pipe and made repairs. Put on rockshield, cleaned up blasting sand from hole to start backfilling | GERALD | SMITH | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | GERALD | 4888 Coating | 1 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 600 | 151 | 78 | 0 | 6 | 6 | 829 | [16 empty] | 829 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-1940-44127-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-23 | Jeeped pipe and made repairs. Put on rockshield, cleaned up blasting sand from hole to start backfilling | RICHARD | SHOEMAKE | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RICHARDS | Brushes | 4 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 830 | 151 | 130 | 0 | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-1940-44127-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-23 | Jeeped pipe and made repairs. Put on rockshield, cleaned up blasting sand from hole to start backfilling | OJ | SEALS | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15336 | Rockshield | 36 | LnFt |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 378 | 151 | 78 | 0 | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-1940-44127-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-23 | Jeeped pipe and made repairs. Put on rockshield, cleaned up blasting sand from hole to start backfilling | JAMES | KERVIN | Laborer |  | 6 |  | 1 | Light Tower 6000 Watt | 6 | HR | RLP9317 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-1940-44127-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-23 | Jeeped pipe and made repairs. Put on rockshield, cleaned up blasting sand from hole to start backfilling | RICHARD | ADKINS | Laborer |  | 6 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 378 | 151 | 276 |  | 6 | 6 | 805 | [16 empty] | 805 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-1940-44127-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-23 | Jeeped pipe and made repairs. Put on rockshield, cleaned up blasting sand from hole to start backfilling | NICHOLAS | BLANCO | Laborer |  | 6 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 378 | 151 | 543 |  | 6 | 6 | 1072 | [16 empty] | 1072 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-1940-44127-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-23 | Jeeped pipe and made repairs. Put on rockshield, cleaned up blasting sand from hole to start backfilling | BARRETT | WISE | Laborer |  | 6 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC0858A | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 378 | 151 | 165 |  | 6 | 6 | 694 | [16 empty] | 694 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-1940-44127-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-23 | Jeeped pipe and made repairs. Put on rockshield, cleaned up blasting sand from hole to start backfilling | [7 empty] | Hammer Attachment | 6 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-1940-44127-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-23 | Jeeped pipe and made repairs. Put on rockshield, cleaned up blasting sand from hole to start backfilling | [7 empty] | Padding Bucket | 6 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | GERALD | SMITH | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | GERALD | SMITH | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | OJ | SEALS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | OJ | SEALS | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | JAMES | KERVIN | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | JAMES | KERVIN | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | RICHARD | ADKINS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | RICHARD | ADKINS | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | NICHOLAS | BLANCO | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | NICHOLAS | BLANCO | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | BARRETT | WISE | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858B | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | BARRETT | WISE | Laborer |  | 3 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858B | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 189 |  | 82.5 |  | 3 | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | [7 empty] | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | [7 empty] | Hammer Attachment | 3 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-19030-44127-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-23 | MOB to site. Started picking up blasting sand and putting in containment bags | [7 empty] | Padding Bucket | 3 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | CALEB | HOLTON | Foreman |  | 9 |  | 1 | Pickup-F150 or F250 or equal | 9 | HR | CALEB | Sand | 13 | Bag | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 900 | 151 | 117 | 0 | 9 | 9 | 1168 | SAFEWAY | [15 empty] | 1168 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | THOMAS | FRANKLIN | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | MICHAEL | ANISZEWSKI | Laborer |  | 9 |  | 1 | Pickup-F150 or F250 or equal | 9 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 567 | 151 | 117 |  | 9 | 9 | 835 | [16 empty] | 835 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | BOLDBAUTOR | ZORIGT | Laborer |  | 8 |  | 1 | Tool Trailer | 8 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 504 | 151 | 40 |  | 8 | 8 | 695 | [16 empty] | 695 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | BOLDBAUTOR | ZORIGT | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | BOLDBAUTOR | ZORIGT | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | JORDAN | WIGGINS | Laborer |  | 8 |  | 1 | 40' Flatbed trailer or equal | 8 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 504 | 151 | 148 |  | 8 | 8 | 803 | [16 empty] | 803 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | JORDAN | WIGGINS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | JORDAN | WIGGINS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | DAVID | KNOTTS | Laborer |  | 8 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 504 | 151 | 368 |  | 8 | 8 | 1023 | [16 empty] | 1023 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | DAVID | KNOTTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | DAVID | KNOTTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | TANNER | BRITT | Laborer |  | 8 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 504 | 151 | 724 |  | 8 | 8 | 1379 | [16 empty] | 1379 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | TANNER | BRITT | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | TANNER | BRITT | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | ALDO | RENYA | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | [16 empty] | 220 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Hammer Attachment | 8 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Hammer Attachment | 1 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Padding Bucket | 8 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44127-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-23 | Dug back 5ft for corosion on pipe. Safeway went into bellhole and kncoked off coating. Sandblasted the section. It was X-Rayed the 2 welds. Loaded excavator on lowboy and took to 1465 | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | SANDBLASTED. STARTED RAINING, CABBED UP AND THEN WENT BACK TO WORK. STARTED RAINING AGAIN, SO WE MOVED TO 1489. | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Sand | 8 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | SANDBLASTED. STARTED RAINING, CABBED UP AND THEN WENT BACK TO WORK. STARTED RAINING AGAIN, SO WE MOVED TO 1489. | MATTHEW | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | SANDBLASTED. STARTED RAINING, CABBED UP AND THEN WENT BACK TO WORK. STARTED RAINING AGAIN, SO WE MOVED TO 1489. | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | SANDBLASTED. STARTED RAINING, CABBED UP AND THEN WENT BACK TO WORK. STARTED RAINING AGAIN, SO WE MOVED TO 1489. | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | SANDBLASTED. STARTED RAINING, CABBED UP AND THEN WENT BACK TO WORK. STARTED RAINING AGAIN, SO WE MOVED TO 1489. | LUTHER | LINDLEY | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | SANDBLASTED. STARTED RAINING, CABBED UP AND THEN WENT BACK TO WORK. STARTED RAINING AGAIN, SO WE MOVED TO 1489. | MARCELO | GOMEZ | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44127-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-23 | SANDBLASTED. STARTED RAINING, CABBED UP AND THEN WENT BACK TO WORK. STARTED RAINING AGAIN, SO WE MOVED TO 1489. | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | BARKLEY | BROWN | Foreman | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 174 |  | 26 |  | 2 | 2 | 200 | [16 empty] | 200 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | MATTHEW | LINDLEY | Operator II | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 144.5 |  | 26 |  | 2 | 2 | 170.5 | [16 empty] | 170.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | WAYLON | GREEN | Laborer | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 110 |  | 26 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | JOSE | VALLES | Laborer | 1 | 1 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 110 |  | 10 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 5 |  | 2 | 1 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | LUTHER | LINDLEY | Laborer | 1 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 110 |  | 32 |  | 2 | 2 | 142 | [16 empty] | 142 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | MARCELO | GOMEZ | Laborer | 1 | 1 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 110 |  | 37 |  | 2 | 2 | 147 | [16 empty] | 147 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | MARCELO | GOMEZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 18.5 |  | 2 | 1 | 144.5 | [16 empty] | 144.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | ANTHONY | MORENO | Laborer | 1 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 110 |  | 92 |  | 2 | 2 | 202 | [16 empty] | 202 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | ANTHONY | MORENO | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 46 |  | 2 | 1 | 172 | [16 empty] | 172 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858C | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858C | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP6A | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44127-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-23 | SET UP TENT AND GET WATER PUMPED OUT FOR NDE TO DO ANOTHER ASSESSMENT. FIRE WATCH WAS PRESENT. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP6A | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | BARKLEY | BROWN | Foreman | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Sand | 4 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 | 151 | 13 | 0 | 1 | 1 | 238 | [16 empty] | 238 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Brushes | 6 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Paint Roller Handles | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | MATTHEW | LINDLEY | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | Paint Rollers | 12 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 | 151 | 13 | 0 | 1 | 1 | 225.5 | [16 empty] | 225.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | MATTHEW | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | 4888 Coating | 6 | L |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 123 |  | 26 | 0 | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | MATTHEW | LINDLEY | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | WAYLON | GREEN | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | JOSE | VALLES | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | LUTHER | LINDLEY | Laborer | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 47 |  | 16 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | LUTHER | LINDLEY | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | LUTHER | LINDLEY | Laborer | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 | 151 | 32 |  | 2 | 2 | 277 | [16 empty] | 277 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | MARCELO | GOMEZ | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | MARCELO | GOMEZ | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | MARCELO | GOMEZ | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | ANTHONY | MORENO | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Brush Hog | 1 | HR | RCC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Brush Hog | 2 | HR | RCC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Brush Hog | 2 | HR | RCC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP6B | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP6B | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-54330-44127-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-23 | SANDBLASTED. NDE DID ASSESSMENT. COATED PIPE. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP6B | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Stand-by - Equipment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Equipment | 3500028468-110-44127-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-23 | EQUIPMENT WAITING ON PERMIT. WAS ORIGINALLY PLANNED TO BE A HAND DIG AND EQUIPMENT IS NEEDED. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS7 | [11 empty] | 46 |  |  |  | 460 |  |  | 10 | 460 | [16 empty] | 460 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | URIEL | VALENCIA | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | JAVIER | VALDEZ | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAVIER | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | ALEJANDRO | CRUZ | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | ASTOLFO | FLORES | Laborer | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | 19130 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 502 | 151 | 160 |  | 10 | 10 | 813 | [16 empty] | 813 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | IVAN | MADRID | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | ROBERTO | RODRIGUEZ | Laborer | 8 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 502 | 151 | 905 |  | 10 | 10 | 1558 | [16 empty] | 1558 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | JOEL | VALDEZ | Laborer | 8 | 2 |  | 1 | Hammer Attachment | 10 | HR | RHA3070 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 502 | 151 | 0 |  | 10 | 10 | 653 | [16 empty] | 653 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | HECTOR | QUINTANA | Laborer | 8 | 2 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 502 | 151 |  |  | 10 |  | 653 | [16 empty] | 653 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | MATTHEW | SCHMITT | Truck Driver/CDL | 8 | 2 |  | 1 | Light Tower 6000 Watt | 10 | HR | RLP5311 | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | [7 empty] | Water Pump (3") | 10 | HR | WP71 | [11 empty] | 12 |  |  |  | 120 |  |  | 10 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44127-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-23 | STARTED DAY WITH TAILGATE MEETING, COVID PLANE AND SAFETY TOPIC FOR THE DAY. STAND-BY WAITING ON ENGINEERS DECISION TO PROCEED. | [7 empty] | Water Pump (3") | 10 | HR | WP72 | [11 empty] | 12 |  |  |  | 120 |  |  | 10 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | GARRETT | DICKSON | Foreman | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | 15318 |  |  |  | BRAND SAFWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 992 | 151 | 143 |  | 12 | 11 | 1286 | BRAND SAFWAY | [15 empty] | 1286 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | RYAN | COLEMAN | Operator II | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 741 | 151 | 143 |  | 11 | 11 | 1035 | [16 empty] | 1035 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | JACOB | GORDON | Laborer | 8 | 3 |  | 1 | Tool Trailer | 11 | HR | UTT2179 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 565 | 151 | 55 |  | 11 | 11 | 771 | [16 empty] | 771 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | ZACHARY | POWDERS | Laborer | 8 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 11 | HR | 19108 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 565 | 151 | 176 |  | 11 | 11 | 892 | [16 empty] | 892 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | COLTON | ROBERTS | Laborer | 8 | 3 |  | 1 | 40' Flatbed trailer or equal | 11 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 565 | 151 | 203.5 |  | 11 | 11 | 919.5 | [16 empty] | 919.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | JUAN | DURAN | Laborer | 8 | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 11 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 565 | 151 | 506 |  | 11 | 11 | 1222 | [16 empty] | 1222 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | TANNER | BRUMMETT | Laborer | 8 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 11 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 565 | 151 | 995.5 |  | 11 | 11 | 1711.5 | [16 empty] | 1711.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | IAIN | ALLRED | Truck Driver/CDL | 8 | 3 |  | 1 | Hammer Attachment | 11 | HR | RHA8 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 644 | 151 | 0 |  | 11 | 11 | 795 | [16 empty] | 795 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 11 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 302.5 |  |  | 11 | 302.5 | [16 empty] | 302.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44127-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-23 | KICKED OFF JSA, THEN THE CREW PROCEEDED TO EXCAVATE AND BREAK THE ROCK FROM THE PIPE. THERE IS A LOT OF ROCK AND IT IS VERY TIME CONSUMING. WE ARE ALMOST COMPLETED ON OUR 360, WE HAVE SIX MORE INCHES TO BE COMPLETED. THE WEATHER GOT BAD AND RAIN MOVED IN. THERE WERE LIGHTENING STRIKES SO THE CREW CABBED UP AND WE ENDED UP CALLING IT A RAIN OUT. | [7 empty] | Light Tower 6000 Watt | 11 | HR | RLP8 | [11 empty] | 13 |  |  |  | 143 |  |  | 11 | 143 | [16 empty] | 143 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | JODY | BROOM | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [16 empty] | 1541 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | TOME | KIRKLAND | Superintendent |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1260 | 151 | 130 |  | 10 | 10 | 1541 | [16 empty] | 1541 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | MICHAEL | GOSS | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAEL | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 720 | 151 | 130 |  | 10 | 10 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | JUANITO | RODRIGUEZ | Safety Person |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | DANIEL | YOUNG | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Kubota UTV | 10 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP1 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP2 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP3 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP5 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP6 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Matches crew 3 | [7 empty] | Padding Bucket | 10 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | JONATHAN | HOLLEY | Foreman |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 | 151 | 52 |  | 4 | 4 | 603 | [16 empty] | 603 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | RYAN | FARINELLI | Operator II |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 | 151 | 52 |  | 4 | 4 | 535 | [16 empty] | 535 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | GREG | MCMILLIAN | Laborer |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 | 151 | 52 |  | 4 | 4 | 455 | [16 empty] | 455 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | JERMAINE | EVANS | Laborer |  | 4 |  | 1 | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 | 151 | 20 |  | 4 | 4 | 423 | [16 empty] | 423 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | DEMETRIUS | MCDONALD | Laborer |  | 4 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 | 151 | 74 |  | 4 | 4 | 477 | [16 empty] | 477 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | JOSE | ORTIZ | Laborer |  | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 | 151 | 184 |  | 4 | 4 | 587 | [16 empty] | 587 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | ROBERT | FOSTER | Laborer |  | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 | 151 | 362 |  | 4 | 4 | 765 | [16 empty] | 765 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | BRIAN | RANDLE | Truck Driver/CDL |  | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 | 151 | 64 |  | 4 | 4 | 503 | [16 empty] | 503 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | [7 empty] | Hammer Attachment | 4 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-18890-44128-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-24 | Jeeped but could not repair due to weather | [7 empty] | Padding Bucket | 4 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | KYLE | BONNEAU | Foreman |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1100 | 151 | 143 |  | 11 | 11 | 1394 | [16 empty] | 1394 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | JESSE | BERTHIAUME | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | JACOB | CAPITANO | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | BROC | CALIGER | Laborer |  | 10 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 630 | 151 | 50 |  | 10 | 10 | 831 | [16 empty] | 831 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | CODY | GAXIOLA | Laborer |  | 10 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 630 | 151 | 185 |  | 10 | 10 | 966 | [16 empty] | 966 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | HEATHER | ENGLE | Laborer |  | 10 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 630 | 151 | 460 |  | 10 | 10 | 1241 | [16 empty] | 1241 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | ALTANOCHIR | JANTSAN | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | [7 empty] | Hammer Attachment | 10 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | [7 empty] | Brush Hog | 10 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-10008649-44128-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-24 | Had JSA meeting. NDE was tied up on 1552. MOB to dig 1778, prepared for site access, set up goal posts. Waited for work authorization | [7 empty] | Padding Bucket | 10 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | MATTHEW | LINDLEY | Foreman |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1200 | 151 | 156 |  | 12 | 12 | 1507 | [16 empty] | 1507 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | W. MONROE | LINDLEY | Operator II |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 913 | 151 | 143 |  | 11 | 11 | 1207 | [16 empty] | 1207 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | LUTHER | LINDLEY | Laborer |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 693 | 151 | 143 |  | 11 | 11 | 987 | [16 empty] | 987 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | DEMETRIUS | DOBY | Laborer |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | MICHAELR | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 693 | 151 | 104 |  | 11 | 8 | 948 | [16 empty] | 948 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | DANIEL | MENDOZA | Laborer |  | 12 |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | SHAWN | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 756 | 151 | 104 |  | 12 | 8 | 1011 | [16 empty] | 1011 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | JESUS | MENDOZA | Laborer |  | 11 |  | 1 | Tool Trailer | 11 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 693 | 151 | 55 |  | 11 | 11 | 899 | [16 empty] | 899 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | TYLER | BIGG | Truck Driver/CDL |  | 11 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 11 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 792 | 151 | 176 |  | 11 | 11 | 1119 | [16 empty] | 1119 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | MICHAEL | RATLIFF | Operator II |  | 8 |  | 1 | 40' Flatbed trailer or equal | 11 | HR | GNT447 | [7 empty] | 61.5 | 83 | 0 | 151 | 18.5 |  | 664 | 151 | 203.5 |  | 8 | 11 | 1018.5 | [16 empty] | 1018.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | SHAWN | ROSE | Operator II |  | 8 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 11 | HR | RSS1413 | [7 empty] | 61.5 | 83 | 0 | 151 | 46 |  | 664 | 151 | 506 |  | 8 | 11 | 1321 | [16 empty] | 1321 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | MICHAEL | ELLIOTT | Laborer |  | 8 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 11 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 504 | 151 | 995.5 |  | 8 | 11 | 1650.5 | [16 empty] | 1650.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | DAVID | RATLIFF | Laborer |  | 8 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 11 | HR | RAC3 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 504 | 151 | 302.5 |  | 8 | 11 | 957.5 | [16 empty] | 957.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | [7 empty] | Hammer Attachment | 11 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44128-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-24 | Excavated and hammered rock, potholed additional area 60ft from the original. Started digging where inspector determined GW to be. Found they had a false reading and decided it was wrong direction to excavate so we moved in other direction to excavate further upstream | [7 empty] | Padding Bucket | 11 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | GERALD | SMITH | Foreman |  | 11 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1100 | 151 | 143 |  | 11 | 11 | 1394 | [16 empty] | 1394 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | RICHARD | SHOEMAKE | Operator II |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 830 | 151 | 130 |  | 10 | 10 | 1111 | [16 empty] | 1111 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | OJ | SEALS | Laborer |  | 10 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 630 | 151 | 130 |  | 10 | 10 | 911 | [16 empty] | 911 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | JAMES | KERVIN | Laborer |  | 10 |  | 1 | Tool Trailer | 10 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 630 | 151 | 50 |  | 10 | 10 | 831 | [16 empty] | 831 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | RICHARD | ADKINS | Laborer |  | 10 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 630 | 151 | 185 |  | 10 | 10 | 966 | [16 empty] | 966 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | NICHOLAS | BLANCO | Laborer |  | 10 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 630 | 151 | 460 |  | 10 | 10 | 1241 | [16 empty] | 1241 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | BARRETT | WISE | Laborer |  | 10 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 630 | 151 | 905 |  | 10 | 10 | 1686 | [16 empty] | 1686 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | STEVE | CLARK | Truck Driver/CDL |  | 10 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 720 | 151 | 160 |  | 10 | 10 | 1031 | [16 empty] | 1031 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | [7 empty] | Hammer Attachment | 10 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | [7 empty] | Padding Bucket | 10 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-1940-44128-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-24 | Padded pipe and compacted with airpogo. Started backfilling pipe. Slow going with a lot of big rock and wet conditions | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | CALEB | HOLTON | Foreman |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 600 | 151 | 78 |  | 6 | 6 | 829 | [16 empty] | 829 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | CALEB | HOLTON | Foreman |  | 6 |  |  | Pickup-F150 or F250 or equal | 6 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 600 |  | 78 |  | 6 | 6 | 678 | [16 empty] | 678 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | THOMAS | FRANKLIN | Operator II |  | 5 |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 | 151 | 65 |  | 5 | 5 | 631 | [16 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | THOMAS | FRANKLIN | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | [16 empty] | 480 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | MICHAEL | ANISZEWSKI | Laborer |  | 6 |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 378 | 151 | 78 |  | 6 | 6 | 607 | [16 empty] | 607 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | MICHAEL | ANISZEWSKI | Laborer |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 315 |  | 65 |  | 5 | 5 | 380 | [16 empty] | 380 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | BOLDBAUTOR | ZORIGT | Laborer |  | 5 |  | 1 | Tool Trailer | 5 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 | 151 | 25 |  | 5 | 5 | 491 | [16 empty] | 491 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | BOLDBAUTOR | ZORIGT | Laborer |  | 5 |  |  | Tool Trailer | 5 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 |  | 25 |  | 5 | 5 | 340 | [16 empty] | 340 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | JORDON | WIGGINS | Laborer |  | 5 |  | 1 | 40' Flatbed trailer or equal | 5 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 | 151 | 92.5 |  | 5 | 5 | 558.5 | [16 empty] | 558.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | JORDON | WIGGINS | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 5 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 92.5 |  | 5 | 5 | 407.5 | [16 empty] | 407.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | DAVID | KNOTTS | Laborer |  | 5 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 | 151 | 230 |  | 5 | 5 | 696 | [16 empty] | 696 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | DAVID | KNOTTS | Laborer |  | 5 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 315 |  | 230 |  | 5 | 5 | 545 | [16 empty] | 545 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | TANNER | BRITT | Laborer |  | 5 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 | 151 | 452.5 |  | 5 | 5 | 918.5 | [16 empty] | 918.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | TANNER | BRITT | Laborer |  | 5 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 315 |  | 452.5 |  | 5 | 5 | 767.5 | [16 empty] | 767.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | ALDO | RENYA | Truck Driver/CDL |  | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 | 151 | 80 |  | 5 | 5 | 591 | [16 empty] | 591 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | ALDO | RENYA | Truck Driver/CDL |  | 5 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 360 |  | 80 |  | 5 | 5 | 440 | [16 empty] | 440 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 5 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 122.5 |  |  | 5 | 122.5 | [16 empty] | 122.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 5 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 122.5 |  |  | 5 | 122.5 | [16 empty] | 122.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | [7 empty] | Hammer Attachment | 5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | [7 empty] | Hammer Attachment | 5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | [7 empty] | Padding Bucket | 5 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-35680-44128-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-24 | Sandblasted proposed anomaly, NDE went down and did assessments | [7 empty] | Padding Bucket | 5 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44128-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-24 | Dewatered site. Moved in skids for PIG run Monday. Cleaned up site | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-43000-44128-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-24 | Dewatered site. Moved in skids for PIG run Monday. Cleaned up site | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | Skids | 10 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Skids | 10 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | JOSHUA | MENDARIES | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | REMUNDO | REYES | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | REMUNDO | REYES | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 92 |  | 1 | 2 | 155 | [16 empty] | 155 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373B | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 55 |  | 1 | 2 | 118 | [16 empty] | 118 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | ANTHONY | MORENO | Laborer |  | 2 |  |  | Hammer Attachment | 2 | HR | RHA1055 | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 126 |  | 0 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | [7 empty] | Brush Hog | 2 | HR | RRC1663 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-51460-44128-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-24 | Dewatered. Firewatched for NDE. Moved skids for PIG run Monday. Cleaned up site | [7 empty] | Water Pump (3") | 2 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 24 |  |  | 2 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Skids | 10 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | JOSHUA | MENDARIES | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | JOSHUA | MENDARIES | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | REYMUNDO | REYES | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | REYMUNDO | REYES | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | ANTHONY | MORENO | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373B | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | ANTHONY | MORENO | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373B | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44128-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Water Pump (3") | 4 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 48 |  |  | 4 | 48 | [16 empty] | 48 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | BARKLEY | BROWN | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 200 | 151 | 26 |  | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Skids | 10 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | JOSHUA | MENDARIES | Operator II |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | Safety Fence | 100 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 166 | 151 | 26 | 0 | 2 | 2 | 343 | [16 empty] | 343 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | JOSHUA | MENDARIES | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | WAYLON | GREEN | Laborer |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 | 151 | 26 |  | 2 | 2 | 303 | [16 empty] | 303 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | JOSE | VALLES | Laborer |  | 2 |  | 1 | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 | 151 | 10 |  | 2 | 2 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | REYMUNDO | REYES | Laborer |  | 2 |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 | 151 | 37 |  | 2 | 2 | 314 | [16 empty] | 314 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | REYMUNDO | REYES | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | MARCELO | GOMEZ | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | MARCELO | GOMEZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | ANTHONY | MORENO | Laborer |  | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373B | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 | 151 | 181 |  | 2 | 2 | 458 | [16 empty] | 458 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | ANTHONY | MORENO | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373B | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | EFREM | LEE | Truck Driver/CDL |  | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 | 151 | 32 |  | 2 | 2 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44128-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-24 | Dewatered and site prep. Fire watched for NDE. Moved skids to each dig to put under pipe for PIG run Monday. Cleaned up sites | [7 empty] | Water Pump (3") | 4 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 48 |  |  | 4 | 48 | [16 empty] | 48 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | URIEL | VALENCIA | Foreman |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 | 151 | 39 |  | 3 | 3 | 490 | [16 empty] | 490 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | URIEL | VALENCIA | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | URIEL | VALENCIA | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | URIEL | VALENCIA | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | URIEL | VALENCIA | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | VALDEZ NEVAREZ | Operator II |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 | 151 | 39 |  | 3 | 3 | 439 | [16 empty] | 439 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | VALDEZ NEVAREZ | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | VALDEZ NEVAREZ | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | VALDEZ NEVAREZ | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | VALDEZ NEVAREZ | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 3 |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 | 151 | 39 |  | 3 | 3 | 379 | [16 empty] | 379 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | IVAN | MADRID | Laborer |  | 3 |  | 1 | Tool Trailer | 3 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 | 151 | 15 |  | 3 | 3 | 355 | [16 empty] | 355 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | IVAN | MADRID | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | IVAN | MADRID | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | IVAN | MADRID | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | IVAN | MADRID | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ROBERTO | RODRIGUEZ | Laborer |  | 3 |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 | 151 | 55.5 |  | 3 | 3 | 395.5 | [16 empty] | 395.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ROBERTO | RODRIGUEZ | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ROBERTO | RODRIGUEZ | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ROBERTO | RODRIGUEZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | ROBERTO | RODRIGUEZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS7 | [11 empty] | 46 |  |  |  | 138 |  |  | 3 | 138 | [16 empty] | 138 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS7 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | [16 empty] | 184 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS7 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | [16 empty] | 46 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS7 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS7 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Hammer Attachment | 3 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 4 | HR | RSP7 | [11 empty] | 23.5 |  |  |  | 94 |  |  | 4 | 94 | [16 empty] | 94 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | JOEL | VALDEZ NEVAREZ | Laborer |  | 3 |  | 1 | Light Tower 6000 Watt | 3 | HR | RLP5311 | Filter Bag | 3 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 |  | 189 | 151 | 39 |  | 3 | 3 | 379 | [16 empty] | 379 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | JOEL | VALDEZ NEVAREZ | Laborer |  | 4 |  |  | Light Tower 6000 Watt | 4 | HR | RLP5311 | 2888 Coating | 5 | L |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 252 |  | 52 | 0 | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | JOEL | VALDEZ NEVAREZ | Laborer |  | 1 |  |  | Light Tower 6000 Watt | 1 | HR | RLP5311 | Brushes | 12 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 63 |  | 13 | 0 | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | JOEL | VALDEZ NEVAREZ | Laborer |  | 2 |  |  | Light Tower 6000 Watt | 2 | HR | RLP5311 | Sand | 10 | Bag |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 126 |  | 26 | 0 | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | JOEL | VALDEZ NEVAREZ | Laborer |  | 2 |  |  | Light Tower 6000 Watt | 2 | HR | RLP5311 | Rockshield | 12 | LnFt |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 126 |  | 26 | 0 | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | QUINTANA VALDEZ | Laborer |  | 3 |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 189 | 151 |  |  | 3 |  | 340 | [16 empty] | 340 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | QUINTANA VALDEZ | Laborer |  | 4 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 252 |  |  |  | 4 |  | 252 | [16 empty] | 252 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | QUINTANA VALDEZ | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | QUINTANA VALDEZ | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | HECTOR | QUINTANA VALDEZ | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | MATTHEW | SCHMITT | Truck Driver/CDL |  | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 | 151 | 48 |  | 3 | 3 | 415 | [16 empty] | 415 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | MATTHEW | SCHMITT | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | MATTHEW | SCHMITT | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | MATTHEW | SCHMITT | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | MATTHEW | SCHMITT | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Water Pump (3") | 3 | HR | 3INP7 | [11 empty] | 12 |  |  |  | 36 |  |  | 3 | 36 | [16 empty] | 36 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Water Pump (3") | 3 | HR | 3INP72 | [11 empty] | 12 |  |  |  | 36 |  |  | 3 | 36 | [16 empty] | 36 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44128-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-24 | Started with JSA. Dewatered and sanblasted. Started re-coat and let pipe cure. Started initial inspection at 3:15. 5 holidays were found, repaired holidays and wrapped the pipe with rockshield. Began backfill. Repaired clay tile line for land owner and shaded the rest of the pipe | [7 empty] | Water Pump ( up to 2") | 3 | HR | 2INP7 | [11 empty] | 6 |  |  |  | 18 |  |  | 3 | 18 | [16 empty] | 18 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Sand | 13 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | GARRETT | DICKSON | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15318 | 2888 Coating | 4 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 400 |  | 52 | 0 | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | RYAN | COLEMAN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYANC | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | RYAN | COLEMAN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYANC | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | RYAN | COLEMAN | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 4 | HR | RYANC | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 52 |  | 3 | 4 | 301 | [16 empty] | 301 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | JACOB | GORDON | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | JACOB | GORDON | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | JACOB | GORDON | Laborer |  | 3 |  |  | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 20 |  | 3 | 4 | 209 | [16 empty] | 209 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | ZACHARY | POWDERS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | ZACHARY | POWDERS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | ZACHARY | POWDERS | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 74 |  | 3 | 4 | 263 | [16 empty] | 263 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | COLTON | ROBERTS | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 184 |  | 3 | 4 | 373 | [16 empty] | 373 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | JUAN | DURAN | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | JUAN | DURAN | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | JUAN | DURAN | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 362 |  | 3 | 4 | 551 | [16 empty] | 551 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | TANNER | BRUMMETT | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | TANNER | BRUMMETT | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | TANNER | BRUMMETT | Laborer |  | 3 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 189 |  | 110 |  | 3 | 4 | 299 | [16 empty] | 299 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | IAIN | ALLRED | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 64 |  | 3 | 4 | 280 | [16 empty] | 280 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Padding Bucket | 1 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Padding Bucket | 1 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Padding Bucket | 4 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP8 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Water Pump (3") | 1 | HR | 3INP8 | [11 empty] | 12 |  |  |  | 12 |  |  | 1 | 12 | [16 empty] | 12 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP8 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-31790-44128-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-24 | Sandblasted and recoated | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | GARRETT | DICKSON | Foreman |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15318 | Sand | 13 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 400 | 151 | 52 | 0 | 4 | 4 | 603 | [16 empty] | 603 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | GARRETT | DICKSON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Filter Bag | 2 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | Skids | 20 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | RYAN | COLEMAN | Operator II |  | 4 |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYANC | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 | 151 | 52 |  | 4 | 4 | 535 | [16 empty] | 535 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | RYAN | COLEMAN | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYANC | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | RYAN | COLEMAN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYANC | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | JACOB | GORDON | Laborer |  | 4 |  | 1 | Tool Trailer | 4 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 | 151 | 20 |  | 4 | 4 | 423 | [16 empty] | 423 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | JACOB | GORDON | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | JACOB | GORDON | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | ZACHARY | POWDERS | Laborer |  | 4 |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 | 151 | 74 |  | 4 | 4 | 477 | [16 empty] | 477 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | ZACHARY | POWDERS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | ZACHARY | POWDERS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | COLTON | ROBERTS | Laborer |  | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 252 | 151 | 184 |  | 4 | 4 | 587 | [16 empty] | 587 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | COLTON | ROBERTS | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | COLTON | ROBERTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | JUAN | DURAN | Laborer |  | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 | 151 | 362 |  | 4 | 4 | 765 | [16 empty] | 765 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | JUAN | DURAN | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | JUAN | DURAN | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | TANNER | BRUMMETT | Laborer |  | 4 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 252 | 151 | 110 |  | 4 | 4 | 513 | [16 empty] | 513 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | TANNER | BRUMMETT | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | TANNER | BRUMMETT | Laborer |  | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 126 |  | 55 |  | 2 | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | IAIN | ALLRED | Truck Driver/CDL |  | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 | 151 | 64 |  | 4 | 4 | 503 | [16 empty] | 503 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | IAIN | ALLRED | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Hammer Attachment | 4 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Padding Bucket | 4 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Padding Bucket | 1 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Padding Bucket | 2 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP8 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Water Pump (3") | 4 | HR | 3INP8 | [11 empty] | 12 |  |  |  | 48 |  |  | 4 | 48 | [16 empty] | 48 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44128-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-24 | Kicked off JSA. Finished jackhammering and hand digging under pipe. Sandblasted for NDE assessment Skidded up 1473 for NDE reassessment | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSP8 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | RENE | CASAREZ | Foreman |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RENE | Safety Fence | 130 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 | 151 | 26 | 0 | 2 | 2 | 377 | [16 empty] | 377 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | RENE | CASAREZ | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RENE | Barbed wire fence | 130 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | RENE | CASAREZ | Foreman |  | 7 |  |  | Pickup-F150 or F250 or equal | 7 | HR | RENE | Silt Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 700 |  | 91 | 0 | 7 | 7 | 791 | [16 empty] | 791 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | DONALD | TIGUE | Operator II |  | 2 |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 | 151 | 26 |  | 2 | 2 | 343 | [16 empty] | 343 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | DONALD | TIGUE | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | DONALD | TIGUE | Operator II |  | 7 |  |  | Pickup-F150 or F250 or equal | 7 | HR | DONALD | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 581 |  | 91 |  | 7 | 7 | 672 | [16 empty] | 672 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | DAVID | LOPEZ | Laborer |  | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 | 151 | 92 |  | 2 | 2 | 369 | [16 empty] | 369 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | DAVID | LOPEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | DAVID | LOPEZ | Laborer |  | 7 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 441 |  | 322 |  | 7 | 7 | 763 | [16 empty] | 763 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | FERNANDO | GARCIA | Laborer |  | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX9 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 | 151 | 181 |  | 2 | 2 | 458 | [16 empty] | 458 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | FERNANDO | GARCIA | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX9 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | FERNANDO | GARCIA | Laborer |  | 7 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX9 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 441 |  | 633.5 |  | 7 | 7 | 1074.5 | [16 empty] | 1074.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | ADDEY | BENNETT | Laborer |  | 2 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC7892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 126 | 151 | 55 |  | 2 | 2 | 332 | [16 empty] | 332 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | ADDEY | BENNETT | Laborer |  | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC7892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 63 |  | 27.5 |  | 1 | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | ADDEY | BENNETT | Laborer |  | 7 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | RAC7892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 441 |  | 192.5 |  | 7 | 7 | 633.5 | [16 empty] | 633.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | MARGIL | GARZA | Laborer |  | 2 |  | 1 | Hammer Attachment | 2 | HR | RHA0141A | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 126 | 151 | 0 |  | 2 | 2 | 277 | [16 empty] | 277 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | MARGIL | GARZA | Laborer |  | 1 |  |  | Hammer Attachment | 1 | HR | RHA0141A | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 63 |  | 0 |  | 1 | 1 | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | MARGIL | GARZA | Laborer |  | 7 |  |  | Hammer Attachment | 7 | HR | RHA0141A | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 441 |  | 0 |  | 7 | 7 | 441 | [16 empty] | 441 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | JODY | HASTON | Truck Driver/CDL |  | 2 |  | 1 | Padding Bucket | 2 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 144 | 151 | 0 |  | 2 | 2 | 295 | [16 empty] | 295 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | JODY | HASTON | Truck Driver/CDL |  | 1 |  |  | Padding Bucket | 1 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 72 |  | 0 |  | 1 | 1 | 72 | [16 empty] | 72 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-10630-44128-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-24 | MOB into dig site. Had to track excavator into 2 miles to dig site. Topsoiled, started excavating, hand dug to exposed pipe. Installed safety fence, silt fence and barbed wire fence | JODY | HASTON | Truck Driver/CDL |  | 7 |  |  | Padding Bucket | 7 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 504 |  | 0 |  | 7 | 7 | 504 | [16 empty] | 504 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | [16 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 7 | 3 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 590.5 | 151 | 130 |  | 10 | 10 | 871.5 | [16 empty] | 871.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Kubota UTV | 10 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP1 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP2 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP3 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP5 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP6 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev1 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Matches crew 5 | [7 empty] | Padding Bucket | 10 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | JONATHAN | HOLLEY | Foreman | 6 | 4 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 844 | 151 | 130 |  | 10 | 10 | 1125 | [16 empty] | 1125 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | JONATHAN | HOLLEY | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JONATHAN | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | RYAN | FARINELLI | Operator II | 6 | 3 |  | 1 | Pickup-F150 or F250 or equal | 9 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 618 | 151 | 117 |  | 9 | 9 | 886 | [16 empty] | 886 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | RYAN | FARINELLI | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | GREG | MCMILLIAN | Laborer | 6 | 3 |  | 1 | Pickup-F150 or F250 or equal | 9 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 471 | 151 | 117 |  | 9 | 9 | 739 | [16 empty] | 739 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | GREG | MCMILLIAN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | JERMAINE | EVANS | Laborer | 6 | 3 |  | 1 | Tool Trailer | 9 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 471 | 151 | 45 |  | 9 | 9 | 667 | [16 empty] | 667 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | JERMAINE | EVANS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | DEMETRIUS | MCDONALD | Laborer | 6 | 3 |  | 1 | 40' Flatbed trailer or equal | 9 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 471 | 151 | 166.5 |  | 9 | 9 | 788.5 | [16 empty] | 788.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | DEMETRIUS | MCDONALD | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | JOSE | ORTIZ | Laborer | 6 | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 9 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 471 | 151 | 414 |  | 9 | 9 | 1036 | [16 empty] | 1036 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | JOSE | ORTIZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | ROBERT | FOSTER | Laborer | 3 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 141 | 151 |  |  | 3 |  | 292 | [16 empty] | 292 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | BRIAN | RANDLE | Truck Driver/CDL | 6 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 9 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 537 | 151 | 144 |  | 9 | 9 | 832 | [16 empty] | 832 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | BRIAN | RANDLE | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 9 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 814.5 |  |  | 9 | 814.5 | [16 empty] | 814.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0563 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 9 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 247.5 |  |  | 9 | 247.5 | [16 empty] | 247.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | [7 empty] | Hammer Attachment | 9 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 9 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | [7 empty] | Hammer Attachment | 1 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | [7 empty] | Padding Bucket | 9 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 9 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-14960-44125-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-21 | Finished excavation on 1546. NDE did intial coating inspection | [7 empty] | Padding Bucket | 1 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | KYLE | BONNEAU | Foreman | 2 | 3 |  |  | Pickup-F150 or F250 or equal | 5 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 448 |  | 65 |  | 5 | 5 | 513 | [16 empty] | 513 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | KYLE | BONNEAU | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | JESSE | BERTHIAUME | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | JESSE | BERTHIAUME | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | CADEN | THOMPSON | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | CADEN | THOMPSON | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | JACOB | CAPITANO | Laborer | 3 | 2 |  |  | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 267 |  | 25 |  | 5 | 5 | 292 | [16 empty] | 292 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | JACOB | CAPITANO | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | BROC | CALIGER | Laborer | 3 | 2 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 267 |  | 92.5 |  | 5 | 5 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | BROC | CALIGER | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | CODY | GAXIOLA | Laborer | 3 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 267 |  | 230 |  | 5 | 5 | 497 | [16 empty] | 497 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | CODY | GAXIOLA | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | ALTANOCHIR | JANSTAN | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | ALTANOCHIR | JANSTAN | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Hammer Attachment | 5 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Brush Hog | 5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Brush Hog | 1 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Padding Bucket | 5 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-17790-44125-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-21 | MOB in from 1552 pot holed and began excavating. Exposed pipe | [7 empty] | Padding Bucket | 1 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | KYLE | BONNEAU | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | KYLE | Sand | 51 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | JESSE | BERTHIAUME | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | JESSE | Silt Fence | 200 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 307.5 | 151 | 65 | 0 | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | CADEN | THOMPSON | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 15335 | Safety Fence | 100 | Ft |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 235 | 151 | 65 | 0 | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | JACOB | CAPITANO | Laborer | 5 |  |  | 1 | Tool Trailer | 5 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 | 151 | 25 |  | 5 | 5 | 411 | [16 empty] | 411 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | BROC | CALIGER | Laborer | 5 |  |  | 1 | 40' Flatbed trailer or equal | 5 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 235 | 151 | 92.5 |  | 5 | 5 | 478.5 | [16 empty] | 478.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | CODY | GAXIOLA | Laborer | 5 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 | 151 | 230 |  | 5 | 5 | 616 | [16 empty] | 616 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | HEATHER | ENGLE | Laborer | 8 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX0369 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 502 | 151 | 452.5 |  | 10 | 5 | 1105.5 | [16 empty] | 1105.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 5 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 137.5 |  |  | 5 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 5 | HR | RSP2 | [11 empty] | 23.5 |  |  |  | 117.5 |  |  | 5 | 117.5 | [16 empty] | 117.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | [7 empty] | Water Pump (3") | 5 | HR | 3INP2 | [11 empty] | 12 |  |  |  | 60 |  |  | 5 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | [7 empty] | Brush Hog | 5 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | [7 empty] | Hammer Attachment | 5 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-28570-44125-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-21 | Had JSA and pumped water. Blasted 40FT of pipe for NDE | [7 empty] | Padding Bucket | 5 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | MICHAEL | RATLIFF | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | SHAWN | ROSE | Operator II | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 741 | 151 | 143 |  | 11 | 11 | 1035 | [16 empty] | 1035 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | MICHAEL | ELLIOTT | Laborer | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 565 | 151 | 143 |  | 11 | 11 | 859 | [16 empty] | 859 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | DAVID | RATLIFF | Laborer | 8 | 3 |  | 1 | Tool Trailer | 11 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 565 | 151 | 55 |  | 11 | 11 | 771 | [16 empty] | 771 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | TYLER | BIGG | Truck Driver/CDL | 8 | 3 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 11 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 644 | 151 | 176 |  | 11 | 11 | 971 | [16 empty] | 971 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | [7 empty] | 40' Flatbed trailer or equal | 11 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 203.5 |  |  | 11 | 203.5 | [16 empty] | 203.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 11 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 506 |  |  | 11 | 506 | [16 empty] | 506 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 11 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 995.5 |  |  | 11 | 995.5 | [16 empty] | 995.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 11 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 302.5 |  |  | 11 | 302.5 | [16 empty] | 302.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | [7 empty] | Hammer Attachment | 11 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28110-44125-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-21 | Found GW and dug 20FT up stream | [7 empty] | Padding Bucket | 11 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 11 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | GERALD | SMITH | Foreman | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | GERALD | 4888 Coating | 1 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 | 151 | 13 | 0 | 1 | 1 | 238 | [16 empty] | 238 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | GERALD | SMITH | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | GERALD | Sand | 25 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | GERALD | SMITH | Foreman | 1 | 3 |  |  | Pickup-F150 or F250 or equal | 4 | HR | GERALD | Brushes | 40 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 374 |  | 52 | 0 | 4 | 4 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | RICHARD | SHOEMAKE | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 | 151 | 13 |  | 1 | 1 | 225.5 | [16 empty] | 225.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | RICHARD | SHOEMAKE | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | RICHARD | SHOEMAKE | Operator II | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 227.5 |  | 39 |  | 3 | 3 | 266.5 | [16 empty] | 266.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | OJ | SEALS | Laborer | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 | 151 | 13 |  | 1 | 1 | 211 | [16 empty] | 211 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | OJ | SEALS | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | OJ | SEALS | Laborer | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 173 |  | 39 |  | 3 | 3 | 212 | [16 empty] | 212 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | JAMES | KERVIN | Laborer | 1 |  |  | 1 | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 | 151 | 5 |  | 1 | 1 | 203 | [16 empty] | 203 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | JAMES | KERVIN | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | JAMES | KERVIN | Laborer | 1 | 2 |  |  | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 173 |  | 15 |  | 3 | 3 | 188 | [16 empty] | 188 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | RICHARD | ADKINS | Laborer | 1 |  |  | 1 | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 | 151 | 18.5 |  | 1 | 1 | 216.5 | [16 empty] | 216.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | RICHARD | ADKINS | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | RICHARD | ADKINS | Laborer | 1 | 2 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 173 |  | 55.5 |  | 3 | 3 | 228.5 | [16 empty] | 228.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | NICHOLAS | BLANCO | Laborer | 1 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 | 151 | 46 |  | 1 | 1 | 244 | [16 empty] | 244 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | NICHOLAS | BLANCO | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | NICHOLAS | BLANCO | Laborer | 1 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 173 |  | 138 |  | 3 | 3 | 311 | [16 empty] | 311 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | BARRETT | WISE | Laborer | 1 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 | 151 | 90.5 |  | 1 | 1 | 288.5 | [16 empty] | 288.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | BARRETT | WISE | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | BARRETT | WISE | Laborer | 1 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 173 |  | 271.5 |  | 3 | 3 | 444.5 | [16 empty] | 444.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | STEVE | CLARK | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Hammer Attachment | 3 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Hammer Attachment | 3 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Padding Bucket | 3 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Padding Bucket | 3 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44125-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-21 | MOB to dig. Sandblasted pipe to recoat recoated pipe with 4888 coating | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | RSP4 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | GERALD | SMITH | Foreman | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | GERALD | 2888 Coating | 4 | L |  |  |  |  | 74 | 100 | 0 | 151 | 16 | 0 | 222 |  | 48 | 0 | 3 | 3 | 270 | [16 empty] | 270 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | RICHARD | SHOEMAKE | Operator II | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RICHARDS | Brushes | 12 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 16 | 0 | 184.5 |  | 48 | 0 | 3 | 3 | 232.5 | [16 empty] | 232.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | OJ | SEALS | Laborer | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 141 |  | 48 |  | 3 | 3 | 189 | [16 empty] | 189 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | JAMES | KERVIN | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | RICHARD | ADKINS | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | NICHOLAS | BLANCO | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | BARRETT | WISE | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | [7 empty] | Hammer Attachment | 3 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | [7 empty] | Padding Bucket | 3 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-19030-44125-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-21 | Jeeped pipe and did repairs. | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | CALEB | HOLTON | Foreman | 7 | 6 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | CALEB | T-Posts | 11 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 1118 | 151 | 169 | 0 | 13 | 13 | 1438 | [16 empty] | 1438 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | THOMAS | FRANKLIN | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | THOMAS | T-Post Caps | 11 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 824 | 151 | 156 | 0 | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | MICHAEL | ANISZEWSKI | Laborer | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | 19120 | Silt Fence | 100 | Ft |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 691 | 151 | 169 | 0 | 13 | 13 | 1011 | [16 empty] | 1011 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | BOLDBAUTOR | ZORIGT | Laborer | 8 | 4 |  | 1 | Tool Trailer | 12 | HR | UTT2182 | Safety Fence | 100 | Ft |  |  |  |  | 47 | 63 | 0 | 151 | 5 | 0 | 628 | 151 | 60 | 0 | 12 | 12 | 839 | [16 empty] | 839 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | JORDAN | WIGGINS | Laborer | 8 | 4 |  | 1 | 40' Flatbed trailer or equal | 12 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 628 | 151 | 222 |  | 12 | 12 | 1001 | [16 empty] | 1001 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | DAVID | KNOTTS | Laborer | 8 | 4 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 628 | 151 | 552 |  | 12 | 12 | 1331 | [16 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | TANNER | BRITT | Laborer | 8 | 4 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 12 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 628 | 151 | 1086 |  | 12 | 12 | 1865 | [16 empty] | 1865 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | ALDO | RENYA | Truck Driver/CDL | 8 | 4 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 12 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 716 | 151 | 192 |  | 12 | 12 | 1059 | [16 empty] | 1059 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 12 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 330 |  |  | 12 | 330 | [16 empty] | 330 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | [7 empty] | Hammer Attachment | 12 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | [7 empty] | Padding Bucket | 12 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1476 - MC.400216.032 - 655.884 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-35680-44125-rev0 | DIG-1476 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 138951.03 | 35680 | Central | IN | 655.884 | 2020-10-21 | Began digging on proposed anomaly. Hit rock and had to switch abck and forth between hammer and bucket | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 12 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 294 |  |  | 12 | 294 | [16 empty] | 294 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | BARKLEY | BROWN | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | Clocksprings | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 296 | 151 | 52 | 0 | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | BARKLEY | BROWN | Foreman | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | Sand | 10 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 348 |  | 52 | 0 | 4 | 4 | 400 | [16 empty] | 400 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | MATTHEW | LINDLEY | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | MATTHEW | Filter Bag | 1 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 | 0 | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | MATTHEW | LINDLEY | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | WAYLON | GREEN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | WAYLON | GREEN | Laborer | 2 | 2 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 220 |  | 52 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | JOSE | VALLES | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | JOSE | VALLES | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | LUTHER | LINDLEY | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | LUTHER | LINDLEY | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | MARCELO | GOMEZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | MARCELO | GOMEZ | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | ANTHONY | MORENO | Laborer | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 | 151 | 64 |  | 4 | 4 | 403 | [16 empty] | 403 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | ANTHONY | MORENO | Laborer | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 |  | 64 |  | 4 | 4 | 252 | [16 empty] | 252 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373A | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44125-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-21 | Installed heaters to keep moisture off pipe to get an accurate dewpoint reading. Installed clockspring | [7 empty] | Water Pump ( up to 2") | 4 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 24 |  |  | 4 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | BARKLEY | BROWN | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | BARKLEY | BROWN | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | MATTHEW | LINDLEY | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | MATTHEW | LINDLEY | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | WAYLON | GREEN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | WAYLON | GREEN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | JOSE | VALLES | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | JOSE | VALLES | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | LUTHER | LINDLEY | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | LUTHER | LINDLEY | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | MARCELO | GOMEZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | MARCELO | GOMEZ | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | ANTHONY | MORENO | Laborer |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 63 |  | 16 |  | 1 | 1 | 79 | [16 empty] | 79 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | ANTHONY | MORENO | Laborer |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 189 |  | 48 |  | 3 | 3 | 237 | [16 empty] | 237 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373B | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373B | [11 empty] | 90.5 |  |  |  | 271.5 |  |  | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Brush Hog | 3 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44125-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-21 | MOB to site. Staged equipment to sand blast pipe for NDE in the morning | [7 empty] | Padding Bucket | 3 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | URIEL | VALENCIA | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15349 | Sand | 1 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | [16 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | URIEL | VALENCIA | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15349 | Filter Bag | 3 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 296 |  | 52 | 0 | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | URIEL | VALENCIA | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | URIEL | VALENCIA | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | HECTOR | VALDEZ NEVAREZ | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | HECTOR | VALDEZ NEVAREZ | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | HECTOR | VALDEZ NEVAREZ | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | HECTOR | VALDEZ NEVAREZ | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | ALEJANDRO | CRUZ CONTRERAS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | ALEJANDRO | CRUZ CONTRERAS | Laborer | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 52 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | IVAN | MADRID | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | IVAN | MADRID | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | IVAN | MADRID | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | IVAN | MADRID | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | ROBERTO | RODRIGUEZ | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | ROBERTO | RODRIGUEZ | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | ROBERTO | RODRIGUEZ | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | ROBERTO | RODRIGUEZ | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | JOEL | VALDEZ NEVAREZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | JOEL | VALDEZ NEVAREZ | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | JOEL | VALDEZ NEVAREZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | JOEL | VALDEZ NEVAREZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS7 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | HECTOR | QUINTANA VALDEZ | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | HECTOR | QUINTANA VALDEZ | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 362 |  | 4 | 4 | 550 | [16 empty] | 550 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | HECTOR | QUINTANA VALDEZ | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | HECTOR | QUINTANA VALDEZ | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | MATTHEW | SCHMITT | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | MATTHEW | SCHMITT | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | MATTHEW | SCHMITT | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | MATTHEW | SCHMITT | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP5311 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Hammer Attachment | 1 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Water Pump (3") | 11 | HR | 3INP7 | [11 empty] | 12 |  |  |  | 132 |  |  | 11 | 132 | [16 empty] | 132 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44125-rev1 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-21 | Waited on decision and set up water pumps to dewater bellhole. Waited on NDE assessment. Sandblasted, cleaned up site to prepare for next day | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP7 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | GARRETT | DICKSON | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | Silt Fence | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | GARRETT | DICKSON | Foreman | 4 | 7 |  |  | Pickup-F150 or F250 or equal | 11 | HR | 15318 | Safety Fence | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 996 |  | 143 | 0 | 11 | 11 | 1139 | [16 empty] | 1139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | RYAN | COLEMAN | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RYAN | T-Posts | 8 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 123 | 151 | 26 | 0 | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | RYAN | COLEMAN | Operator II | 6 | 4 |  |  | Pickup-F150 or F250 or equal | 10 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 701 |  | 130 |  | 10 | 10 | 831 | [16 empty] | 831 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | JACOB | GORDON | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | JACOB | GORDON | Laborer | 6 | 4 |  |  | Tool Trailer | 10 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 534 |  | 50 |  | 10 | 10 | 584 | [16 empty] | 584 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | ZACHARY | POWDERS | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | ZACHARY | POWDERS | Laborer | 5 | 5 |  |  | 40' Flatbed trailer or equal | 10 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 550 |  | 185 |  | 10 | 10 | 735 | [16 empty] | 735 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | COLTON | ROBERTS | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | COLTON | ROBERTS | Laborer | 6 | 4 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 534 |  | 460 |  | 10 | 10 | 994 | [16 empty] | 994 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | JUAN | DURAN | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | JUAN | DURAN | Laborer | 6 | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 534 |  | 905 |  | 10 | 10 | 1439 | [16 empty] | 1439 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | TANNER | BRUMMETT | Laborer | 2 |  |  | 1 | Light Tower 6000 Watt | 2 | HR | RLP8 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | TANNER | BRUMMETT | Laborer | 6 | 4 |  |  | Light Tower 6000 Watt | 10 | HR | RLP8 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 534 |  | 130 |  | 10 | 10 | 664 | [16 empty] | 664 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | IAIN | ALLRED | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | IAIN | ALLRED | Truck Driver/CDL | 6 | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 609 |  | 160 |  | 10 | 10 | 769 | [16 empty] | 769 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-33820-44125-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-21 | Had JSA meeting. Driver went to KY to pick up materials. Prepped site for excavation, put up silt fence. Daylighted pipe, started excavation. Had to order trench box, will arrive 10/22. Cleaned up site and placed safety fence. | [7 empty] | Hammer Attachment | 10 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JODY | BROOM | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | [16 empty] | 1003 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JODY | BROOM | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | TOME | KIRKLAND | Superintendent | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 748 | 151 | 104 |  | 8 | 8 | 1003 | [16 empty] | 1003 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | TOME | KIRKLAND | Superintendent |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 252 |  | 26 |  | 2 | 2 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JAY | MASEY | Quality Assurance Inspector | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 840 | 151 | 104 |  | 8 | 8 | 1095 | [16 empty] | 1095 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | JAY | MASEY | Quality Assurance Inspector | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 210 |  | 26 |  | 2 | 2 | 236 | [16 empty] | 236 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | MICHAEL | GOSS | Truck Driver/CDL | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 428 | 151 | 104 |  | 8 | 8 | 683 | [16 empty] | 683 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | MICHAEL | GOSS | Truck Driver/CDL |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 144 | 0 | 26 |  | 2 | 2 | 170 | [16 empty] | 170 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | DANIEL | YOUNG | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | DANIEL | YOUNG | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | KIM | FORNALL | Project Coordinator | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 790.4 | 151 | 104 |  | 8 | 8 | 1045.4 | [16 empty] | 1045.4 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | KIM | FORNALL | Project Coordinator | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15161 | [7 empty] | 98.8 | 0 | 0 | 151 | 13 |  | 197.6 |  | 26 |  | 2 | 2 | 223.6 | [16 empty] | 223.6 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Tractor/Semi | 8 | HR | 1368 | [11 empty] | 42 |  |  |  | 336 |  |  | 8 | 336 | [16 empty] | 336 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Tractor/Semi | 2 | HR | 1368 | [11 empty] | 42 |  |  |  | 84 |  |  | 2 | 84 | [16 empty] | 84 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Tractor/Semi | 8 | HR | 1376 | [11 empty] | 42 |  |  |  | 336 |  |  | 8 | 336 | [16 empty] | 336 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Tractor/Semi | 2 | HR | 1376 | [11 empty] | 42 |  |  |  | 84 |  |  | 2 | 84 | [16 empty] | 84 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 8 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 148 |  |  | 8 | 148 | [16 empty] | 148 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 2 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 8 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 148 |  |  | 8 | 148 | [16 empty] | 148 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Lowboy Trailer | 2 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | TB1 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | TB2 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 8 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 2 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 8 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Kubota UTV | 2 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT1 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT2 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT3 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT4 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT5 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | MATCHES CREW 4 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLT6 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JONATHAN | HOLLEY | Foreman | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | JONATHAN | Silt Fence | 166 | Ft | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 592 | 151 | 104 | 0 | 8 | 8 | 847 | SAFEWAY | [15 empty] | 847 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JONATHAN | HOLLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JONATHAN | Safety Fence | 60 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | RYAN | FARINELLI | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | RYANF | T-Posts | 7 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 492 | 151 | 104 | 0 | 8 | 8 | 747 | [16 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | RYAN | FARINELLI | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | GREG | MCMILLIAN | Laborer | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 376 | 151 | 104 |  | 8 | 8 | 631 | [16 empty] | 631 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | GREG | MCMILLIAN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JERMAINE | EVANS | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | [16 empty] | 567 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JERMAINE | EVANS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | DEMETRIUS | MCDONALD | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | [16 empty] | 675 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | DEMETRIUS | MCDONALD | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JOSE | ORTIZ | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | [16 empty] | 895 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | JOSE | ORTIZ | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | ROBERT | FOSTER | Laborer | 8 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 376 | 151 | 724 |  | 8 | 8 | 1251 | [16 empty] | 1251 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | ROBERT | FOSTER | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | BRIAN | RANDLE | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | [16 empty] | 707 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | BRIAN | RANDLE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | [16 empty] | 220 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Hammer Attachment | 8 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Hammer Attachment | 2 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Brush Hog | 8 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Brush Hog | 2 | HR | RBH1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Padding Bucket | 8 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-18890-44122-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-18 | Dug 1549 to weld. Had embankment crew take off 8ft of coating to realize it was wrong spot. Started digging back the other way and found anomaly. | [7 empty] | Padding Bucket | 2 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | KYLE | BONNEAU | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 892 | 151 | 143 |  | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | JESSE | BERTHIAUME | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | CADEN | THOMPSON | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | JACOB | CAPITANO | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | BROC | CALIGER | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | CODY | GAXIOLA | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 905 |  |  | 10 | 905 | [16 empty] | 905 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Hammer Attachment | 10 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Brush Hog | 10 | HR | RBH4491 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1552 - MC.400216.085 - 368.2672 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-28570-44122-rev0 | DIG-1552 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 85886.46 | 28570 | Central | KY | 368.2672 | 2020-10-18 | Had JSA meeting, headed up the hill and exposed 30' of pipe and hammered all day. Helped Michaels crew unload materials | [7 empty] | Padding Bucket | 10 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | RATLIFF | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | RATLIFF | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 |  | 52 |  | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | RATLIFF | Foreman | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 274 |  | 39 |  | 3 | 3 | 313 | [16 empty] | 313 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | SHAWN | ROSE | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | SHAWN | ROSE | Operator II | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 144.5 |  | 26 |  | 2 | 2 | 170.5 | [16 empty] | 170.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | ELLIOTT | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | ELLIOTT | Laborer | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 52 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | MICHAEL | ELLIOTT | Laborer | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 110 |  | 26 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | DAVID | RATLIFF | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | DAVID | RATLIFF | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | DAVID | RATLIFF | Laborer | 1 | 1 |  |  | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 110 |  | 10 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | TYLER | BIGG | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | TYLER | BIGG | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | TYLER | BIGG | Truck Driver/CDL | 1 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 125.5 |  | 32 |  | 2 | 2 | 157.5 | [16 empty] | 157.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | 40' Flatbed trailer or equal | 1 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 18.5 |  |  | 1 | 18.5 | [16 empty] | 18.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | 40' Flatbed trailer or equal | 4 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 74 |  |  | 4 | 74 | [16 empty] | 74 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | [16 empty] | 46 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | [16 empty] | 184 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Hammer Attachment | 1 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Hammer Attachment | 4 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Padding Bucket | 1 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Padding Bucket | 4 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Brush Hog | 1 | HR | RBH3 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Brush Hog | 4 | HR | RBH3 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1551 - MC.400216.085 - 367.9727 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-28110-44122-rev0 | DIG-1551 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 84327.46 | 28110 | Central | KY | 367.9727 | 2020-10-18 | Brushhogged and set up access signs. Located the pipe | [7 empty] | Brush Hog | 2 | HR | RBH3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | MICHAEL | RATLIFF | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | MICHAELR | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | SHAWN | ROSE | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | MICHAEL | ELLIOT | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | DAVID | RATLIFF | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | TYLER | BIGG | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC3 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1564 - MC.400216.085 - 418.8466 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-108090-44122-rev0 | DIG-1564 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 353255.33 | 108090 | Central | KY | 418.8466 | 2020-10-18 | Moved equipment and staged | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | GERALD | SMITH | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | GERALD | Sand | 10 | Bag | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | SAFEWAY | [15 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | GERALD | SMITH | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | RICHARD | SHOEMAKE | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | RICHARD | SHOEMAKE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | RICHARDS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | OJ | SEALS | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | OJ | SEALS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | JAMES | KERVIN | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | JAMES | KERVIN | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | RICHARD | ADKINS | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | RICHARD | ADKINS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | NICHOLAS | BLANCO | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | NICHOLAS | BLANCO | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | BARRETT | WISE | Laborer | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF439 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 188 | 151 | 64 |  | 4 | 4 | 403 | [16 empty] | 403 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | BARRETT | WISE | Laborer | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF439 | [7 empty] | 47 | 63 | 0 | 151 | 16 |  | 94 |  | 32 |  | 2 | 2 | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Hammer Attachment | 4 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Hammer Attachment | 2 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP4 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP4 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Padding Bucket | 4 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Padding Bucket | 2 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-1940-44122-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-18 | Helped NDT inspect and measure coating on pipe. Waited on coating to be removed and started sandblasting pipe behind removable coating. Got rained out early | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSBP4 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | Sand | 6 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | 2888 Coating | 11 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAEL | T-Posts | 6 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 63 |  | 13 | 0 | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAEL | T-Post Caps | 6 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 126 |  | 26 | 0 | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | JORDAN | WIGGINS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | Safety Fence | 100 | Ft |  |  |  |  | 47 | 63 | 0 | 151 | 5 | 0 | 63 |  | 5 | 0 | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | JORDAN | WIGGINS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2182 | Brushes | 36 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 5 | 0 | 63 |  | 5 | 0 | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | DAVID | KNOTTS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | Clocksprings | 3 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 | 0 | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | DAVID | KNOTTS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | TANNER | BRITT | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | TANNER | BRITT | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [47 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Hammer Attachment | 1 | HR | RHA606 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Hammer Attachment | 1 | HR | RHA606 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-650-44122-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-18 | Sandblasted pipe, Installed (3) clocksprings. Once clocksprings dried, coated anomaly | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 1 | HR | RSBP5 | [11 empty] | 23.5 |  |  |  | 23.5 |  |  | 1 | 23.5 | [16 empty] | 23.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | CALEB | HOLTON | Foreman | 8 | 1 |  | 1 | Pickup-F150 or F250 or equal | 9 | HR | CALEB |  |  |  | SAFEWAY | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 |  | 692 | 151 | 117 |  | 9 | 9 | 960 | SAFEWAY | [15 empty] | 960 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | THOMAS | FRANKLIN | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 824 | 151 | 156 |  | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | MICHAEL | ANISZEWSKI | Laborer | 8 | 1 |  | 1 | Pickup-F150 or F250 or equal | 9 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 439 | 151 | 117 |  | 9 | 9 | 707 | [16 empty] | 707 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | BOLDBAUTOR | ZORIGT | Laborer | 8 | 4 |  | 1 | Tool Trailer | 12 | HR | UTT2182A | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 60 |  | 12 | 12 | 839 | [16 empty] | 839 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | JORDAN | WIGGINS | Laborer | 8 | 1 |  | 1 | 40' Flatbed trailer or equal | 9 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 439 | 151 | 166.5 |  | 9 | 9 | 756.5 | [16 empty] | 756.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | JORDAN | WIGGINS | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | DAVID | KNOTTS | Laborer | 8 | 1 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 9 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 439 | 151 | 414 |  | 9 | 9 | 1004 | [16 empty] | 1004 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | DAVID | KNOTTS | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | TANNER | BRITT | Laborer | 8 | 1 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 9 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 439 | 151 | 814.5 |  | 9 | 9 | 1404.5 | [16 empty] | 1404.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | TANNER | BRITT | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | ALDO | RENYA | Truck Driver/CDL | 8 | 5 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 13 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 788 | 151 | 208 |  | 13 | 13 | 1147 | [16 empty] | 1147 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 9 | HR | RAC4049A | [11 empty] | 27.5 |  |  |  | 247.5 |  |  | 9 | 247.5 | [16 empty] | 247.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC4049A | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Hammer Attachment | 9 | HR | [12 empty] | 0 |  |  |  | 0 |  |  | 9 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Hammer Attachment | 1 | HR | [12 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Padding Bucket | 9 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 9 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Padding Bucket | 1 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 9 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 220.5 |  |  | 9 | 220.5 | [16 empty] | 220.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1472 - MC.400216.032 - 649.858 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-27760-44122-rev0 | DIG-1472 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 107126.57 | 27760 | Central | IN | 649.858 | 2020-10-18 | Top soiled dig site, excavated to anomaly. Safeway knocked off coating at dig site. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 1 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 24.5 |  |  | 1 | 24.5 | [16 empty] | 24.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | BARKLEY | BROWN | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Sand | 3 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | BARKLEY | BROWN | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | 2888 Coating | 9 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | BARKLEY | BROWN | Foreman | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Clocksprings | 3 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 248 |  | 39 | 0 | 3 | 3 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | BARKLEY | BROWN | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MATTHEW | LINDLEY | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MATTHEW | LINDLEY | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MATTHEW | LINDLEY | Operator II | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 206 |  | 39 |  | 3 | 3 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MATTHEW | LINDLEY | Operator II |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 249 |  | 39 |  | 3 | 3 | 288 | [16 empty] | 288 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | WAYLON | GREEN | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 | 151 | 39 |  | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | WAYLON | GREEN | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | WAYLON | GREEN | Laborer | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 157 |  | 39 |  | 3 | 3 | 196 | [16 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | WAYLON | GREEN | Laborer |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 9829 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 252 |  | 52 |  | 4 | 4 | 304 | [16 empty] | 304 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSE | VALLES | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSE | VALLES | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSE | VALLES | Laborer | 2 | 1 |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 157 |  | 15 |  | 3 | 3 | 172 | [16 empty] | 172 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSE | VALLES | Laborer |  | 3 |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 189 |  | 15 |  | 3 | 3 | 204 | [16 empty] | 204 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | LUTHER | LINDLEY | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | LUTHER | LINDLEY | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | LUTHER | LINDLEY | Laborer | 2 | 1 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 157 |  | 55.5 |  | 3 | 3 | 212.5 | [16 empty] | 212.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | LUTHER | LINDLEY | Laborer |  | 3 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 189 |  | 55.5 |  | 3 | 3 | 244.5 | [16 empty] | 244.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MARCELO | GOMEZ | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 138 |  | 3 | 3 | 430 | [16 empty] | 430 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MARCELO | GOMEZ | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MARCELO | GOMEZ | Laborer | 2 | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 157 |  | 138 |  | 3 | 3 | 295 | [16 empty] | 295 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | MARCELO | GOMEZ | Laborer |  | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 189 |  | 138 |  | 3 | 3 | 327 | [16 empty] | 327 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | ANTHONY | MORENO | Laborer | 3 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 | 151 | 271.5 |  | 3 | 3 | 563.5 | [16 empty] | 563.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | ANTHONY | MORENO | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | ANTHONY | MORENO | Laborer | 2 | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 157 |  | 271.5 |  | 3 | 3 | 428.5 | [16 empty] | 428.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | ANTHONY | MORENO | Laborer |  | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 189 |  | 271.5 |  | 3 | 3 | 460.5 | [16 empty] | 460.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSHUA | PHILLIPSON | Truck Driver/CDL | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 | 151 | 48 |  | 3 | 3 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSHUA | PHILLIPSON | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSHUA | PHILLIPSON | Truck Driver/CDL | 2 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 179 |  | 48 |  | 3 | 3 | 227 | [16 empty] | 227 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | JOSHUA | PHILLIPSON | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | [16 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858A | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Padding Bucket | 3 | HR | RBP6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Padding Bucket | 3 | HR | RBP6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Padding Bucket | 3 | HR | RBP6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Padding Bucket | 3 | HR | RBP6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Water Pump ( up to 2") | 3 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 18 |  |  | 3 | 18 | [16 empty] | 18 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Pumped water, sandblasted pipe. NDE inspected pipe, installed (3) 30" clocksprings, sandblasted and coated pipe. Jeeped pipe, no repairs needed. NDE did final assessment of pipe. Backfilled | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | SBP6 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | URIEL | VALENCIA | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | R15349 | Sand | 3 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | URIEL | VALENCIA | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | R15349 | 2888 Coating | 3 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | URIEL | VALENCIA | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | R15349 | Brushes | 24 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | URIEL | VALENCIA | Foreman | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 274 |  | 39 |  | 3 | 3 | 313 | [16 empty] | 313 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | VALDEZ NEVAREZ | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | VALDEZ NEVAREZ | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | VALDEZ NEVAREZ | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | VALDEZ NEVAREZ | Operator II | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 227.5 |  | 39 |  | 3 | 3 | 266.5 | [16 empty] | 266.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 1 | 2 |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 173 |  | 39 |  | 3 | 3 | 212 | [16 empty] | 212 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ASTOLFO | FLORES | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ASTOLFO | FLORES | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ASTOLFO | FLORES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ASTOLFO | FLORES | Laborer | 1 | 2 |  |  | Tool Trailer | 3 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 173 |  | 15 |  | 3 | 3 | 188 | [16 empty] | 188 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | IVAN | MADRID | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | IVAN | MADRID | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | IVAN | MADRID | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | IVAN | MADRID | Laborer | 1 | 2 |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 173 |  | 55.5 |  | 3 | 3 | 228.5 | [16 empty] | 228.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ROBERTO | RODRIGUEZ | Laborer | 2 |  |  | 1 | Light Tower 6000 Watt | 2 | HR | RLP7 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ROBERTO | RODRIGUEZ | Laborer | 3 |  |  |  | Light Tower 6000 Watt | 3 | HR | RLP7 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ROBERTO | RODRIGUEZ | Laborer | 2 |  |  |  | Light Tower 6000 Watt | 2 | HR | RLP7 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | ROBERTO | RODRIGUEZ | Laborer | 1 | 2 |  |  | Light Tower 6000 Watt | 3 | HR | RLP7 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 173 |  | 39 |  | 3 | 3 | 212 | [16 empty] | 212 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | JOEL | VALDEZ NEVAREZ | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | JOEL | VALDEZ NEVAREZ | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | JOEL | VALDEZ NEVAREZ | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | JOEL | VALDEZ NEVAREZ | Laborer | 1 | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX7 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 173 |  | 271.5 |  | 3 | 3 | 444.5 | [16 empty] | 444.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | QUINTANA VALDEZ | Laborer | 2 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 | 151 | 55 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | QUINTANA VALDEZ | Laborer | 3 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 141 |  | 82.5 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | QUINTANA VALDEZ | Laborer | 2 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 |  | 55 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | HECTOR | QUINTANA VALDEZ | Laborer | 1 | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 173 |  | 82.5 |  | 3 | 3 | 255.5 | [16 empty] | 255.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | MATTHEW | SCHMITT | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | MATTHEW | SCHMITT | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | MATTHEW | SCHMITT | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | MATTHEW | SCHMITT | Truck Driver/CDL | 1 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 197.5 |  | 48 |  | 3 | 3 | 245.5 | [16 empty] | 245.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Hammer Attachment | 2 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Hammer Attachment | 3 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Post Repair Assessment - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Post Repair Assessment | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Hammer Attachment | 2 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Stand-by - Waiting on Repair Decision - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Waiting on Repair Decision | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Hammer Attachment | 3 | HR | RHA7 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-71410-44122-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-18 | Started with tailgate meeting. Used Jeep to inspect any jeeps on pipe and sandblasted the affected areas. Repaired all holidays on the pipe. Re-jeeped to make sure there were no more hoildays and coating was properly applied. Cleaned up work area and waited on NDE for instruction on repairing anomaly. | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSBP7 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | GARRETT | DICKSON | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | RYAN | COLEMAN | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | RYAN | COLEMAN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | JACOB | GORDAN | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | JACOB | GORDAN | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | ZACHARY | POWDERS | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | ZACHARY | POWDERS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | COLTON | ROBERTS | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | COLTON | ROBERTS | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | JUAN | DURAN | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | JUAN | DURAN | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | TANNER | BRUMMETT | Laborer | 2 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 | 151 | 55 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | TANNER | BRUMMETT | Laborer | 1 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 |  | 27.5 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | IAIN | ALLRED | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP8 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP8 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-29250-44122-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-18 | Started with JSA. Prepped bellhole for NDE. Loaded equipment to move to dig 1474 | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Safety Fence | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | GARRETT | DICKSON | Foreman | 2 | 1 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | Silt Fence | 200 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 248 |  | 39 | 0 | 3 | 3 | 287 | [16 empty] | 287 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | GARRETT | DICKSON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | T-Posts | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 200 |  | 26 | 0 | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | RYAN | COLEMAN | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | RYAN | COLEMAN | Operator II | 4 | 2 |  |  | Pickup-F150 or F250 or equal | 6 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 412 |  | 78 |  | 6 | 6 | 490 | [16 empty] | 490 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | RYAN | COLEMAN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | RYAN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | JACOB | GORDAN | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | JACOB | GORDAN | Laborer | 4 | 2 |  |  | Tool Trailer | 6 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 314 |  | 30 |  | 6 | 6 | 344 | [16 empty] | 344 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | JACOB | GORDAN | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | ZACHARY | POWDERS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | ZACHARY | POWDERS | Laborer | 4 | 2 |  |  | 40' Flatbed trailer or equal | 6 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 314 |  | 111 |  | 6 | 6 | 425 | [16 empty] | 425 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | ZACHARY | POWDERS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | [16 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | TANNER | BRUMMETT | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | TANNER | BRUMMETT | Laborer | 4 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 314 |  | 276 |  | 6 | 6 | 590 | [16 empty] | 590 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | TANNER | BRUMMETT | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | IAIN | ALLRED | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | IAIN | ALLRED | Truck Driver/CDL | 4 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 6 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 358 |  | 96 |  | 6 | 6 | 454 | [16 empty] | 454 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | IAIN | ALLRED | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | [16 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 543 |  |  | 6 | 543 | [16 empty] | 543 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 165 |  |  | 6 | 165 | [16 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | [7 empty] | Hammer Attachment | 1 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | [7 empty] | Hammer Attachment | 6 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-31790-44122-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-18 | Had JSA meeting. Unloaded equipment and performed excavation. Put silt fence up around soil piles and placed safety fence around bellhole. | [7 empty] | Hammer Attachment | 2 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-33820-44122-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-18 | Had (2) crew members start clearing ROW and daylight pipe | GARRETT | DICKSON | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 400 |  | 52 |  | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Had (2) crew members handle coating. | COLTON | ROBERTS | Laborer |  | 9 |  |  | Light Tower 6000 Watt | 9 | RLP8 | 0 | 2888 Coating | 9 | L |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 567 |  | 117 | 0 | 9 | 9 | 684 | [16 empty] | 684 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1488 - MC.400216.032 - 666.536 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-50610-44122-rev0 | DIG-1488 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 195020.56 | 50610 | Central | IN | 666.536 | 2020-10-18 | Had (2) crew members handle coating. | JUAN | DURAN | Laborer |  | 9 | [6 empty] | Brushes | 12 | Ea |  |  |  |  | 47 | 63 | 0 | 151 |  | 0 | 567 |  |  | 0 | 9 |  | 567 | [16 empty] | 567 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | [16 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | [16 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | [16 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUAP | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | [16 empty] | 853 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | [16 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | [16 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | [16 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Kubota UTV | 10 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP1 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP2 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP3 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP5 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Light Tower 6000 Watt | 10 | HR | RLP6 | [11 empty] | 13 |  |  |  | 130 |  |  | 10 | 130 | [16 empty] | 130 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Matches crew 9 | [7 empty] | Padding Bucket | 10 | HR | RPB7 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | JONATHAN | HOLLEY | Foreman | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JONATHAN | Silt Fence | 263 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 792 | 151 | 130 | 0 | 10 | 10 | 1073 | [16 empty] | 1073 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | JONATHAN | HOLLEY | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JONATHAN | Safety Fence | 50 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | RYAN | FARINELLI | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | RYANF | T-Posts | 6 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 658 | 151 | 130 | 0 | 10 | 10 | 939 | [16 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | RYAN | FARINELLI | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | GREG | MCMILLIAN | Laborer | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 502 | 151 | 130 |  | 10 | 10 | 783 | [16 empty] | 783 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | GREG | MCMILLIAN | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | JERMAINE | EVANS | Laborer | 8 | 2 |  | 1 | Tool Trailer | 10 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 502 | 151 | 50 |  | 10 | 10 | 703 | [16 empty] | 703 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | JERMAINE | EVANS | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | [16 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | DEMETRIUS | MCDONALD | Laborer | 8 | 2 |  | 1 | 40' Flatbed trailer or equal | 10 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 502 | 151 | 185 |  | 10 | 10 | 838 | [16 empty] | 838 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | DEMETRIUS | MCDONALD | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | [16 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | JOSE | ORTIZ | Laborer | 8 | 2 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 10 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 502 | 151 | 460 |  | 10 | 10 | 1113 | [16 empty] | 1113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | JOSE | ORTIZ | Laborer |  | 1 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 63 |  | 46 |  | 1 | 1 | 109 | [16 empty] | 109 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | ROBERT | FOSTER | Laborer | 8 | 2 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 10 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 502 | 151 | 905 |  | 10 | 10 | 1558 | [16 empty] | 1558 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | ROBERT | FOSTER | Laborer |  | 1 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 63 |  | 90.5 |  | 1 | 1 | 153.5 | [16 empty] | 153.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | BRIAN | RANDLE | Truck Driver/CDL | 8 | 2 |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 10 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 572 | 151 | 160 |  | 10 | 10 | 883 | [16 empty] | 883 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | BRIAN | RANDLE | Truck Driver/CDL |  | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 72 |  | 16 |  | 1 | 1 | 88 | [16 empty] | 88 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 10 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 275 |  |  | 10 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | [7 empty] | Hammer Attachment | 10 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1548 - MC.400216.085 - 361.0549 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-16230-44130-rev0 | DIG-1548 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 47752.86 | 16230 | Central | KY | 361.0549 | 2020-10-26 | Excavated and was 15ft off survey mark, nde did initial inspection | [7 empty] | Hammer Attachment | 1 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | KYLE | BONNEAU | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | KYLE | Sand | 5 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | KYLE | BONNEAU | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 |  | 26 |  | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | JESSE | BERTHIAUME | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | JESSE | BERTHIAUME | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | JACOB | CAPITANO | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | JACOB | CAPITANO | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | BROC | CALIGER | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | BROC | CALIGER | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | CODY | GAXIOLA | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | CODY | GAXIOLA | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | HEATHER | ENGLE | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | [16 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | HEATHER | ENGLE | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Hammer Attachment | 2 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Hammer Attachment | 2 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Brush Hog | 2 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Brush Hog | 2 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Padding Bucket | 2 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-17790-44130-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-26 | Had JHA, sandblasted and NDE came and assessed | [7 empty] | Padding Bucket | 2 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | KYLE | BONNEAU | Foreman | 4 | 4 |  |  | Pickup-F150 or F250 or equal | 8 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 696 |  | 104 |  | 8 | 8 | 800 | [16 empty] | 800 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | JESSE | BERTHIAUME | Operator II | 4 | 3 |  |  | Pickup-F150 or F250 or equal | 7 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 495 |  | 91 |  | 7 | 7 | 586 | [16 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | JACOB | CAPITANO | Laborer | 4 | 3 |  |  | Pickup-F150 or F250 or equal | 7 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 377 |  | 91 |  | 7 | 7 | 468 | [16 empty] | 468 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | BROC | CALIGER | Laborer | 4 | 3 |  |  | Tool Trailer | 7 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 377 |  | 35 |  | 7 | 7 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | CODY | GAXIOLA | Laborer | 4 | 3 |  |  | 40' Flatbed trailer or equal | 7 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 377 |  | 129.5 |  | 7 | 7 | 506.5 | [16 empty] | 506.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | HEATHER | ENGLE | Laborer | 4 | 3 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 7 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 377 |  | 322 |  | 7 | 7 | 699 | [16 empty] | 699 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 4 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 430 |  | 112 |  | 7 | 7 | 542 | [16 empty] | 542 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 7 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 633.5 |  |  | 7 | 633.5 | [16 empty] | 633.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 192.5 |  |  | 7 | 192.5 | [16 empty] | 192.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | [7 empty] | Hammer Attachment | 7 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | [7 empty] | Padding Bucket | 7 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10008649-44130-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-26 | Got work authorization, did line sweep with m-scope, offset stakes, potholed and topsoiled began excavation. Lined up NDE and coating removal for tomorrow AM | [7 empty] | Brush Hog | 7 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 7 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | GERALD | SMITH | Foreman | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | GERALD | Lime | 30 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 444 | 151 | 78 | 0 | 6 | 6 | 673 | [16 empty] | 673 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | GERALD | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | GERALD | Fertilizer | 300 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | MICHAEL | RATLIFF | Operator II | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | MICHAELR | Seed Mix | 20 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 369 | 151 | 78 | 0 | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | MICHAEL | RATLIFF | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | Straw Bales | 25 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 61.5 |  | 13 | 0 | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | OJ | SEALS | Laborer | 6 |  |  | 1 | Pickup-F150 or F250 or equal | 6 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 282 | 151 | 78 |  | 6 | 6 | 511 | [16 empty] | 511 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | RICHARD | ADKINS | Laborer | 6 |  |  | 1 | Tool Trailer | 6 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 282 | 151 | 30 |  | 6 | 6 | 463 | [16 empty] | 463 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | RICHARD | ADKINS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | BARRETT | WISE | Laborer | 6 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 282 | 151 | 276 |  | 6 | 6 | 709 | [16 empty] | 709 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | BARRETT | WISE | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | MICHAEL | ELLIOTT | Laborer | 6 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 6 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 282 | 151 | 543 |  | 6 | 6 | 976 | [16 empty] | 976 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | MICHAEL | ELLIOTT | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | DAVID | RATLIFF | Laborer | 6 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 6 | HR | RAC0858 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 282 | 151 | 165 |  | 6 | 6 | 598 | [16 empty] | 598 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | DAVID | RATLIFF | Laborer | 1 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 |  | 27.5 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | STEVE | CLARK | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | RF439 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | [7 empty] | Light Tower 6000 Watt | 6 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 78 |  |  | 6 | 78 | [16 empty] | 78 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | [7 empty] | Hammer Attachment | 6 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | [7 empty] | Padding Bucket | 6 | HR | RPB9317 | [11 empty] | 0 |  |  |  | 0 |  |  | 6 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0796 - MC.400216.084 - 352.458 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-1940-44130-rev0 | DIG-0796 | 3500028468 | MC.400216.084 | 2020 | ABC Group, Inc | ALL | 10 | 3834.13 | 1940 | Central | KY | 352.458 | 2020-10-26 | Put topsoil back on dig site. Graded site, fertilized, lime and seeded site De-MOB to dig 1550 | [7 empty] | Padding Bucket | 1 | HR | RPB9317 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | GERALD | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | GERALD | Mats | 4 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | GERALD | SMITH | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | MICHAEL | RATLIFF | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | MICHAEL | RATLIFF | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | OJ | SEALS | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | RICHARD | ADKINS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | RICHARD | ADKINS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | BARRETT | WISE | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | BARRETT | WISE | Laborer |  | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 126 |  | 92 |  | 2 | 2 | 218 | [16 empty] | 218 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | MICHAEL | ELLIOTT | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | MICHAEL | ELLIOTT | Laborer |  | 2 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 126 |  | 181 |  | 2 | 2 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | DAVID | RATLIFF | Laborer | 1 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 47 |  | 27.5 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | DAVID | RATLIFF | Laborer |  | 2 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 126 |  | 55 |  | 2 | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | STEVE | CLARK | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439A | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | RF439A | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | [16 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | [16 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | [7 empty] | Hammer Attachment | 2 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | [7 empty] | Padding Bucket | 1 | HR | RPB9317 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-19030-44130-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-26 | MOB into site. Started getting blasting sand out of hole. | [7 empty] | Padding Bucket | 2 | HR | RPB9317 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | CALEB | HOLTON | Foreman | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | CALEB | Seed Mix | 50 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 370 | 151 | 65 | 0 | 5 | 5 | 586 | [16 empty] | 586 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | CALEB | HOLTON | Foreman | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 422 |  | 65 |  | 5 | 5 | 487 | [16 empty] | 487 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | CALEB | HOLTON | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | THOMAS | FRANKLIN | Operator II | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 307.5 | 151 | 65 |  | 5 | 5 | 523.5 | [16 empty] | 523.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | THOMAS | FRANKLIN | Operator II | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 350.5 |  | 65 |  | 5 | 5 | 415.5 | [16 empty] | 415.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | THOMAS | FRANKLIN | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | MICHAEL | ANISZEWSKI | Laborer | 5 |  |  | 1 | Pickup-F150 or F250 or equal | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 | 151 | 65 |  | 5 | 5 | 451 | [16 empty] | 451 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | MICHAEL | ANISZEWSKI | Laborer | 3 | 2 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 267 |  | 65 |  | 5 | 5 | 332 | [16 empty] | 332 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | MICHAEL | ANISZEWSKI | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | BOLDBAUTOR | ZORIGT | Laborer | 2 |  |  | 1 | Tool Trailer | 5 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 25 |  | 2 | 5 | 270 | [16 empty] | 270 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | JORDAN | WIGGINS | Laborer | 2 |  |  | 1 | Tool Trailer | 5 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 25 |  | 2 | 5 | 270 | [16 empty] | 270 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | DAVID | KNOTTS | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | TANNER | BRITT | Laborer | 2 |  |  | 1 | [11 empty] | 47 | 63 | 0 | 151 |  |  | 94 | 151 |  |  | 2 |  | 245 | [16 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | ALDO | RENYA | Truck Driver/CDL | 5 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 267.5 | 151 | 80 |  | 5 | 5 | 498.5 | [16 empty] | 498.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | ALDO | RENYA | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | [16 empty] | 384.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | ALDO | RENYA | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | 40' Flatbed trailer or equal | 5 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 92.5 |  |  | 5 | 92.5 | [16 empty] | 92.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | 22115 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 5 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 122.5 |  |  | 5 | 122.5 | [16 empty] | 122.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 5 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 122.5 |  |  | 5 | 122.5 | [16 empty] | 122.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 2 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 49 |  |  | 2 | 49 | [16 empty] | 49 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 5 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 230 |  |  | 5 | 230 | [16 empty] | 230 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS8664 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 5 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 452.5 |  |  | 5 | 452.5 | [16 empty] | 452.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Hammer Attachment | 5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Hammer Attachment | 5 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Hammer Attachment | 2 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Padding Bucket | 5 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Padding Bucket | 5 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 5 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1465 - MC.400216.032 - 629.925 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-650-44130-rev0 | DIG-1465 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 2010.71 | 650 | Central | IN | 629.925 | 2020-10-26 | Jeeped pipe, backfilled anomaly hole. Pulled topsoil and cleaned up area. Seeded topsoil, loaded excavator and cleaned up site. | [7 empty] | Padding Bucket | 2 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | CALEB | HOLTON | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | CALEB | 2888 Coating | 5 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 100 |  | 13 | 0 | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | MICHAEL | ANISZEWSKI | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19120 | Brushes | 9 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 13 | 0 | 63 |  | 13 | 0 | 1 | 1 | 76 | [16 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | BOLDBAUTOR | ZORIGT | Laborer | 5 | [7 empty] | Sand | 4 | Bag |  |  |  |  | 47 | 63 | 0 | 151 |  | 0 | 235 |  |  | 0 | 5 |  | 235 | [16 empty] | 235 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | BOLDBAUTOR | ZORIGT | Laborer | 1 | 4 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 299 |  |  |  | 5 |  | 299 | [16 empty] | 299 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | JORDAN | WIGGINS | Laborer | 5 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 235 |  |  |  | 5 |  | 235 | [16 empty] | 235 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | JORDAN | WIGGINS | Laborer | 1 | 4 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 299 |  |  |  | 5 |  | 299 | [16 empty] | 299 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | DAVID | KNOTTS | Laborer | 5 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 235 |  |  |  | 5 |  | 235 | [16 empty] | 235 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | DAVID | KNOTTS | Laborer | 1 | 4 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 299 |  |  |  | 5 |  | 299 | [16 empty] | 299 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | TANNER | BRITT | Laborer | 5 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 235 |  |  |  | 5 |  | 235 | [16 empty] | 235 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-9400-44130-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-26 | MOB into site. Sandblasted proposed anomaly then coated pipe | TANNER | BRITT | Laborer | 1 | 4 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 299 |  |  |  | 5 |  | 299 | [16 empty] | 299 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | BARKLEY | BROWN | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | 4888 Coating | 1 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | BARKLEY | BROWN | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | [16 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | JOSHUA | MENDARIES | Operator II | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 | 151 | 39 |  | 3 | 3 | 374.5 | [16 empty] | 374.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | JOSHUA | MENDARIES | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | [16 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | WAYLON | GREEN | Laborer | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 | 151 | 39 |  | 3 | 3 | 331 | [16 empty] | 331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | WAYLON | GREEN | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | [16 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | JOSE | VALLES | Laborer | 3 |  |  | 1 | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 | 151 | 15 |  | 3 | 3 | 307 | [16 empty] | 307 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | JOSE | VALLES | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | [16 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | REYMUNDO | REYES | Laborer | 3 |  |  | 1 | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 | 151 | 55.5 |  | 3 | 3 | 347.5 | [16 empty] | 347.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | REYMUNDO | REYES | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | [16 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | MARCELO | GOMEZ | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 138 |  | 3 | 3 | 430 | [16 empty] | 430 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | MARCELO | GOMEZ | Laborer | 2 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 |  | 92 |  | 2 | 2 | 186 | [16 empty] | 186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | ANTHONY | MORENO | Laborer | 3 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 | 151 | 271.5 |  | 3 | 3 | 563.5 | [16 empty] | 563.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | ANTHONY | MORENO | Laborer | 2 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 |  | 181 |  | 2 | 2 | 275 | [16 empty] | 275 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | EFREM | LEE | Truck Driver/CDL | 3 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 | 151 | 48 |  | 3 | 3 | 359.5 | [16 empty] | 359.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | EFREM | LEE | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | [16 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Brush Hog | 3 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Padding Bucket | 3 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 3 | HR | RSP6 | [11 empty] | 23.5 |  |  |  | 70.5 |  |  | 3 | 70.5 | [16 empty] | 70.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1485 - MC.400216.032 - 661.199 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-43000-44130-rev0 | DIG-1485 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 166964.77 | 43000 | Central | IN | 661.199 | 2020-10-26 | Dewatered bellhole. Jeeped and repaired, demob equipment to 1489 | [7 empty] | Water Pump (3") | 3 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 36 |  |  | 3 | 36 | [16 empty] | 36 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | BARKLEY | BROWN | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | JOSHUA | MENDARIES | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | [16 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | WAYLON | GREEN | Laborer |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 126 |  | 26 |  | 2 | 2 | 152 | [16 empty] | 152 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | REYMUNDO | REYES | Laborer |  | 1 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 10 |  | 1 | 2 | 73 | [16 empty] | 73 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | [7 empty] | 40' Flatbed trailer or equal | 2 | HR | GNT7130 | [11 empty] | 18.5 |  |  |  | 37 |  |  | 2 | 37 | [16 empty] | 37 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1663 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | [16 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | [16 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | [16 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | [7 empty] | Hammer Attachment | 2 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | [7 empty] | Padding Bucket | 2 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-51460-44130-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-26 | MOB equipment | [7 empty] | Brush Hog | 2 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 74 |  | 13 |  | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | JOSHUA | MENDARIES | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | JOSHUA | MENDARIES | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | REYMUNDO | REYES | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | REYMUNDO | REYES | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | [16 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | MARCELO | GOMEZ | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | [16 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | ANTHONY | MORENO | Laborer | 1 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 47 |  | 90.5 |  | 1 | 1 | 137.5 | [16 empty] | 137.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | EFREM | LEE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | EFREM | LEE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | [16 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | [7 empty] | Hammer Attachment | 1 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | [7 empty] | Brush Hog | 1 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | [7 empty] | Padding Bucket | 1 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1490 - MC.400216.032 - 669.155 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-54330-44130-rev0 | DIG-1490 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 208943.5 | 54330 | Central | IN | 669.155 | 2020-10-26 | Dewatered and jeeped. Ready for backfill | [7 empty] | Water Pump (3") | 2 | HR | 3INP6 | [11 empty] | 12 |  |  |  | 24 |  |  | 2 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | BARKLEY | BROWN | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | BARKLEY | Filter Bag | 1 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | [16 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | BARKLEY | BROWN | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | JOSHUA | MENDARIES | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | [16 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | JOSHUA | MENDARIES | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | [16 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | WAYLON | GREEN | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | [16 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | WAYLON | GREEN | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | JOSE | VALLES | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | JOSE | VALLES | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | [16 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | REYMUNDO | REYES | Laborer | 1 |  |  |  | Water Pump (3") | 1 | HR | 3INP6 | [7 empty] | 47 | 63 | 0 | 151 | 12 |  | 47 |  | 12 |  | 1 | 1 | 59 | [16 empty] | 59 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | REYMUNDO | REYES | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | MARCELO | GOMEZ | Laborer | 1 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 47 |  |  |  | 1 |  | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | MARCELO | GOMEZ | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | ANTHONY | MORENO | Laborer | 1 | [14 empty] | 47 | 63 | 0 | 151 |  |  | 47 |  |  |  | 1 |  | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | ANTHONY | MORENO | Laborer |  | 2 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 126 |  |  |  | 2 |  | 126 | [16 empty] | 126 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | EFREM | LEE | Truck Driver/CDL | 1 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 53.5 |  | 16 |  | 1 | 1 | 69.5 | [16 empty] | 69.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-58100-44130-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-26 | Dewatered and did firewatch for NDE and X-Ray | EFREM | LEE | Truck Driver/CDL |  | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 144 |  | 32 |  | 2 | 2 | 176 | [16 empty] | 176 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | URIEL | VALENCIA | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | R15349 | Silt Fence | 400 | Ft | BADGER | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | BADGER | [15 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | URIEL | VALENCIA | Foreman |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15349 | T-Posts | 22 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 400 |  | 52 | 0 | 4 | 4 | 452 | [16 empty] | 452 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | HECTOR | VALDEZ NEVAREZ | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | HECTOR | VALDEZ NEVAREZ | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | ALEJANDRO | CRUZ CONTRERAS | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | ALEJANDRO | CRUZ CONTRERAS | Laborer |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 39 |  | 3 | 3 | 228 | [16 empty] | 228 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | ASTOLFO | FLORES | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | ASTOLFO | FLORES | Laborer |  | 4 |  |  | Tool Trailer | 4 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 252 |  | 20 |  | 4 | 4 | 272 | [16 empty] | 272 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | IVAN | MADRID | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | IVAN | MADRID | Laborer |  | 4 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 252 |  | 74 |  | 4 | 4 | 326 | [16 empty] | 326 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | ROBERTO | RODRIGUEZ | Laborer | 3 |  |  |  | Light Tower 6000 Watt | 3 | HR | RLP5311 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | ROBERTO | RODRIGUEZ | Laborer |  | 3 |  |  | Light Tower 6000 Watt | 4 | HR | RLP5311 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 189 |  | 52 |  | 3 | 4 | 241 | [16 empty] | 241 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | JOEL | VALDEZ NEVAREZ | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | JOEL | VALDEZ NEVAREZ | Laborer |  | 4 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 252 |  | 362 |  | 4 | 4 | 614 | [16 empty] | 614 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | HECTOR | QUINTANA VALDEZ | Laborer | 3 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 141 |  | 82.5 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | HECTOR | QUINTANA VALDEZ | Laborer |  | 4 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 252 |  | 110 |  | 4 | 4 | 362 | [16 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | MATTHEW | SCHMITT | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | MATTHEW | SCHMITT | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 64 |  | 3 | 4 | 280 | [16 empty] | 280 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | [7 empty] | Hammer Attachment | 3 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | [7 empty] | Hammer Attachment | 4 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS7 | [11 empty] | 46 |  |  |  | 276 |  |  | 6 | 276 | [16 empty] | 276 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0872 - MC.400235.032 - 0.019 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-110-44130-rev0 | DIG-0872 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 129.73 | 110 | Central | IN | 0.019 | 2020-10-26 | Mobilizaed to dig site. Built dump site for hydrovac slurry. Area to be excavated was m-scoped and marked for Badger truck. Slot trenching started. Fencing was put up around excavation | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 6 | HR | RSS7 | [11 empty] | 46 |  |  |  | 276 |  |  | 6 | 276 | [16 empty] | 276 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | URIEL | VALENCIA | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | URIEL | VALENCIA | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | R15349 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 222 |  | 39 |  | 3 | 3 | 261 | [16 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | HECTOR | VALDEZ NEVAREZ | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | HECTOR | VALDEZ NEVAREZ | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | HECTOR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | ALEJANDRO | CRUZ CONTRERAS | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | ALEJANDRO | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | ASTOLFO | FLORES | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | ASTOLFO | FLORES | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | 2169 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | IVAN | MADRID | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | IVAN | MADRID | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT0829 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | ROBERTO | RODRIGUEZ | Laborer | 2 |  |  | 1 | Light Tower 6000 Watt | 2 | HR | RLP5311 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | ROBERTO | RODRIGUEZ | Laborer | 3 |  |  |  | Light Tower 6000 Watt | 3 | HR | RLP5311 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | JOEL | VALDEZ NEVAREZ | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | JOEL | VALDEZ NEVAREZ | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX4074 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | HECTOR | QUINTANA VALDEZ | Laborer | 2 |  |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 94 | 151 | 55 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | HECTOR | QUINTANA VALDEZ | Laborer | 3 |  |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | 7160 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 141 |  | 82.5 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | MATTHEW | SCHMITT | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | MATTHEW | SCHMITT | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19130 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | [7 empty] | Hammer Attachment | 2 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0875 - MC.400235.032 - 51.577 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-71410-44130-rev0 | DIG-0875 | 3500028468 | MC.400235.032 | 2020 | ABC Group, Inc | ALL | 69 | 272347 | 71410 | Central | IN | 51.577 | 2020-10-26 | Pre-job meeting at Gas City with Enbridge reps. Did JSA meeting finished cleaning and demob. | [7 empty] | Hammer Attachment | 3 | HR | RHA3070 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | GARRETT | DICKSON | Foreman | 7 |  |  | 1 | Pickup-F150 or F250 or equal | 7 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 518 | 151 | 91 |  | 7 | 7 | 760 | [16 empty] | 760 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | SHAWN | ROSE | Operator II | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 824 | 151 | 156 |  | 12 | 12 | 1131 | [16 empty] | 1131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | COLTON | ROBERTS | Laborer | 8 | 4 |  | 1 | Tool Trailer | 12 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 628 | 151 | 60 |  | 12 | 12 | 839 | [16 empty] | 839 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | ZACHARY | POWDERS | Laborer | 7 |  |  | 1 | 40' Flatbed trailer or equal | 12 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 329 | 151 | 222 |  | 7 | 12 | 702 | [16 empty] | 702 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | IAIN | ALLRED | Truck Driver/CDL | 7 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 7 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 374.5 |  | 112 |  | 7 | 7 | 486.5 | [16 empty] | 486.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 12 | HR | REX8 | [11 empty] | 90.5 |  |  |  | 1086 |  |  | 12 | 1086 | [16 empty] | 1086 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 12 | HR | RSS8 | [11 empty] | 46 |  |  |  | 552 |  |  | 12 | 552 | [16 empty] | 552 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 7 | HR | RAC8 | [11 empty] | 27.5 |  |  |  | 192.5 |  |  | 7 | 192.5 | [16 empty] | 192.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | [7 empty] | Light Tower 6000 Watt | 12 | HR | RLP8 | [11 empty] | 13 |  |  |  | 156 |  |  | 12 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | [7 empty] | Hammer Attachment | 12 | HR | RHA8 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1474 - MC.400216.032 - 652.986 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-31790-44130-rev0 | DIG-1474 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 123618.27 | 31790 | Central | IN | 652.986 | 2020-10-26 | Had JSA meeting. Started backfilling and completed | [7 empty] | Padding Bucket | 12 | HR | RPB8 | [11 empty] | 0 |  |  |  | 0 |  |  | 12 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44130-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-26 | Sandblasted and recoated pipe | GARRETT | DICKSON | Foreman | 1 | 1 |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | Sand | 11 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 174 |  | 26 | 0 | 2 | 2 | 200 | [16 empty] | 200 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44130-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-26 | Sandblasted and recoated pipe | GARRETT | DICKSON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | 4888 Coating | 7 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 300 |  | 39 | 0 | 3 | 3 | 339 | [16 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44130-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-26 | Sandblasted and recoated pipe | ZACHARY | POWDERS | Laborer | 1 | 1 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8 | Brushes | 12 | Ea |  |  |  |  | 47 | 63 | 0 | 151 | 27.5 | 0 | 110 |  | 55 | 0 | 2 | 2 | 165 | [16 empty] | 165 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44130-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-26 | Sandblasted and recoated pipe | ZACHARY | POWDERS | Laborer |  | 3 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC8 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 189 |  | 82.5 |  | 3 | 3 | 271.5 | [16 empty] | 271.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44130-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-26 | Sandblasted and recoated pipe | IAIN | ALLRED | Truck Driver/CDL | 1 | 1 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 125.5 |  | 32 |  | 2 | 2 | 157.5 | [16 empty] | 157.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-33820-44130-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-26 | Sandblasted and recoated pipe | IAIN | ALLRED | Truck Driver/CDL |  | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 216 |  | 48 |  | 3 | 3 | 264 | [16 empty] | 264 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1475 - MC.400216.032 - 654.578 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-33820-44130-rev0 | DIG-1475 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 131991.02 | 33820 | Central | IN | 654.578 | 2020-10-26 | Sandblasted and recoated pipe | [7 empty] | Sandblaster & Safety Equipment (Single Nozzle) | 2 | HR | RSP8 | [11 empty] | 23.5 |  |  |  | 47 |  |  | 2 | 47 | [16 empty] | 47 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Had JSA and started Excavating | RENE | CASAREZ | Foreman | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | RENE | Barbed Wire Fence | 60 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 892 | 151 | 143 | 0 | 11 | 11 | 1186 | [16 empty] | 1186 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Had JSA and started Excavating | DONALD | TIGUE | Operator II | 8 | 3 |  | 1 | Pickup-F150 or F250 or equal | 11 | HR | DONALD | Safety Fence | 60 | Ft |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 741 | 151 | 143 | 0 | 11 | 11 | 1035 | [16 empty] | 1035 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Had JSA and started Excavating | DAVID | LOPEZ | Laborer | 8 | 3 |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 11 | HR | RSS1304 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 565 | 151 | 506 |  | 11 | 11 | 1222 | [16 empty] | 1222 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Had JSA and started Excavating | FERNANDO | GARCIA | Laborer | 8 | 3 |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 11 | HR | REX9 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 565 | 151 | 995.5 |  | 11 | 11 | 1711.5 | [16 empty] | 1711.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Had JSA and started Excavating | ADDEY | BENNETT | Laborer | 8 | 3 |  | 1 | Sullair Air Compressor (251 to 375 CFM) or equal ** | 11 | HR | RAC7892 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 565 | 151 | 302.5 |  | 11 | 11 | 1018.5 | [16 empty] | 1018.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Had JSA and started Excavating | MARGIL | GARZA | Laborer | 8 | 3 |  | 1 | Hammer Attachment | 11 | HR | RHA0141A | [7 empty] | 47 | 63 | 0 | 151 | 0 |  | 565 | 151 | 0 |  | 11 | 11 | 716 | [16 empty] | 716 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1545 - MC.400216.085 - 358.0856 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-10630-44130-rev0 | DIG-1545 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 32027.34 | 10630 | Central | KY | 358.0856 | 2020-10-26 | Had JSA and started Excavating | JODY | HASTON | Truck Driver/CDL | 8 | 3 |  | 1 | Padding Bucket | 11 | HR | RPB7093 | [7 empty] | 53.5 | 72 | 0 | 151 | 0 |  | 644 | 151 | 0 |  | 11 | 11 | 795 | [16 empty] | 795 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | MATTHEW | LINDLEY | Foreman | 3 |  |  | 1 | Pickup-F150 or F250 or equal | 3 | HR | MATTHEW | Silt Fence | 100 | Ft |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 222 | 151 | 39 | 0 | 3 | 3 | 412 | [16 empty] | 412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | MATTHEW | LINDLEY | Foreman | 5 | 1 |  |  | Pickup-F150 or F250 or equal | 6 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 470 |  | 78 |  | 6 | 6 | 548 | [16 empty] | 548 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | W. MONROE | LINDLEY | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | W. MONROE | LINDLEY | Operator II | 6 | 3 |  |  | Pickup-F150 or F250 or equal | 9 | HR | W. MONROE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 618 |  | 117 |  | 9 | 9 | 735 | [16 empty] | 735 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | LUTHER | LINDLEY | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | [16 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | LUTHER | LINDLEY | Laborer | 6 | 3 |  |  | Pickup-F150 or F250 or equal | 9 | HR | 15363 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 471 |  | 117 |  | 9 | 9 | 588 | [16 empty] | 588 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | DEMETRIUS | DOBY | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | [16 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | DEMETRIUS | DOBY | Laborer | 5 |  |  |  | Tool Trailer | 9 | HR | UTT2177 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 235 |  | 45 |  | 5 | 9 | 280 | [16 empty] | 280 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | NICHOLAS | BLANCO | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | [16 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | NICHOLAS | BLANCO | Laborer | 6 | 3 |  |  | 40' Flatbed trailer or equal | 9 | HR | GNT447 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 471 |  | 166.5 |  | 9 | 9 | 637.5 | [16 empty] | 637.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | DANIEL | MENDOZA | Laborer | 3 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 | 151 | 92 |  | 3 | 2 | 384 | [16 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | DANIEL | MENDOZA | Laborer | 5 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 9 | HR | RSS1413 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 235 |  | 414 |  | 5 | 9 | 649 | [16 empty] | 649 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | JESUS | MENDOZA | Laborer | 2 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 94 | 151 | 181 |  | 2 | 2 | 426 | [16 empty] | 426 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | JESUS | MENDOZA | Laborer | 6 | 3 |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 9 | HR | REX1373A | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 471 |  | 814.5 |  | 9 | 9 | 1285.5 | [16 empty] | 1285.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | TYLER | BIGG | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | [16 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | TYLER | BIGG | Truck Driver/CDL | 6 | 3 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 9 | HR | 1996 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 537 |  | 144 |  | 9 | 9 | 681 | [16 empty] | 681 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | [7 empty] | Hammer Attachment | 2 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | [7 empty] | Hammer Attachment | 9 | HR | RHA1066 | [11 empty] | 0 |  |  |  | 0 |  |  | 9 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Excavation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Excavation | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | [7 empty] | Padding Bucket | 2 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1553 - MC.400216.085 - 368.7653 - Site Access - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Access | 3500028468-29300-44130-rev0 | DIG-1553 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 88526.65 | 29300 | Central | KY | 368.7653 | 2020-10-26 | Had butter bar welded on. Backfilled where hole was overdug, cleaned up bellhole to make safer access. Repaired coating. Broke up rock with hammer and dug. Had to assess the ROW to get compressor up the hill. Have plan of action for the morning | [7 empty] | Padding Bucket | 9 | HR | RPB3 | [11 empty] | 0 |  |  |  | 0 |  |  | 9 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31230-44130-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-26 | Mobilized laborers and began to pothole | MATTHEW | LINDLEY | Foreman |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 100 |  | 13 |  | 1 | 1 | 113 | [16 empty] | 113 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31230-44130-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-26 | Mobilized laborers and began to pothole | MATTHEW | LINDLEY | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | MATTHEW | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | [16 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31230-44130-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-26 | Mobilized laborers and began to pothole | DEMETRIUS | DOBY | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31230-44130-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-26 | Mobilized laborers and began to pothole | DEMETRIUS | DOBY | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-31230-44130-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-26 | Mobilized laborers and began to pothole | DANIEL | MENDOZA | Laborer |  | 1 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 63 |  |  |  | 1 |  | 63 | [16 empty] | 63 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0547 - MC.400216.087 - 373.552 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-31230-44130-rev0 | DIG-0547 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 113696.86 | 31230 | Central | KY | 373.552 | 2020-10-26 | Mobilized laborers and began to pothole | DANIEL | MENDOZA | Laborer |  | 3 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 189 |  |  |  | 3 |  | 189 | [16 empty] | 189 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | JODY | BROOM | Superintendent | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JODY | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1000 | 151 | 130 |  | 10 | 10 | 1281 | 0 | [15 empty] | 1281 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | TOME | KIRKLAND | Superintendent | 8 | 4 |  | 1 | Pickup-F150 or F250 or equal | 12 | HR | TOME | [7 empty] | 93.5 | 126 | 0 | 151 | 13 |  | 1252 | 151 | 156 |  | 12 | 12 | 1559 | 0 | [15 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | JAY | MASEY | Quality Assurance Inspector | 10 |  |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JAY | [7 empty] | 105 | 0 | 0 | 151 | 13 |  | 1050 | 151 | 130 |  | 10 | 10 | 1331 | 0 | [15 empty] | 1331 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | MICHAEL | GOSS | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | MICHAELG | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | 0 | [15 empty] | 853 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | JOSHUA | PHILLIPSON | Truck Driver/CDL | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | JOSHUA | [7 empty] | 53.5 | 72 | 0 | 151 | 13 |  | 572 | 151 | 130 |  | 10 | 10 | 853 | 0 | [15 empty] | 853 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | JUANITO | RODRIGUEZ | Safety Person | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | 15161 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 792 | 151 | 130 |  | 10 | 10 | 1073 | 0 | [15 empty] | 1073 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | DANIEL | YOUNG | Operator II | 8 | 2 |  | 1 | Pickup-F150 or F250 or equal | 10 | HR | DANIEL | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 658 | 151 | 130 |  | 10 | 10 | 939 | 0 | [15 empty] | 939 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | KIM | FORNALL | Project Coordinator | 10 |  |  | 1 | Tractor/Semi | 10 | HR | 1368 | [7 empty] | 98.8 | 0 | 0 | 151 | 42 |  | 988 | 151 | 420 |  | 10 | 10 | 1559 | 0 | [15 empty] | 1559 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | [7 empty] | Tractor/Semi | 10 | HR | 1376 | [11 empty] | 42 |  |  |  | 420 |  |  | 10 | 420 | 0 | [15 empty] | 420 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | [7 empty] | Lowboy Trailer | 10 | HR | 2449 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | 0 | [15 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | [7 empty] | Lowboy Trailer | 10 | HR | 2450 | [11 empty] | 18.5 |  |  |  | 185 |  |  | 10 | 185 | 0 | [15 empty] | 185 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB1 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | 0 | [15 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 10 | HR | RTB2 | [11 empty] | 24.5 |  |  |  | 245 |  |  | 10 | 245 | 0 | [15 empty] | 245 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | [7 empty] | Kubota UTV | 10 | HR | UTV7861 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Matches crew 2 | [7 empty] | Kubota UTV | 10 | HR | UTV2003 | [11 empty] | 0 |  |  |  | 0 |  |  | 10 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | JONATHAN | HOLLEY | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | 2888 Coating | 13 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | 0 | [15 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | JONATHAN | HOLLEY | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | JONATHAN | Brushes | 15 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 296 |  | 52 | 0 | 4 | 4 | 348 | 0 | [15 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | RYAN | FARINELLI | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | 0 | [15 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | RYAN | FARINELLI | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | RYANF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | 0 | [15 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | GREG | MCMILLIAN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | 0 | [15 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | GREG | MCMILLIAN | Laborer | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | R15334 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 52 |  | 4 | 4 | 240 | 0 | [15 empty] | 240 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | JERMAINE | EVANS | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | 0 | [15 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | JERMAINE | EVANS | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2183 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | 0 | [15 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | DEMETRIUS | MCDONALD | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | 0 | [15 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | DEMETRIUS | MCDONALD | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0204 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | 0 | [15 empty] | 262 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | JOSE | ORTIZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | 0 | [15 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | JOSE | ORTIZ | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS8762 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | 0 | [15 empty] | 372 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | ROBERT | FOSTER | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | 0 | [15 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | ROBERT | FOSTER | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0563 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 362 |  | 4 | 4 | 550 | 0 | [15 empty] | 550 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | BRIAN | RANDLE | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | 0 | [15 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | BRIAN | RANDLE | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF2809 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | 0 | [15 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | 0 | [15 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC8430 | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | 0 | [15 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP1 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP1 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | [7 empty] | Hammer Attachment | 4 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | [7 empty] | Hammer Attachment | 4 | HR | RHA1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | [7 empty] | Padding Bucket | 4 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1546 - MC.400216.085 - 360.3519 - Stand-by - Weather - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Weather | 3500028468-14960-44132-rev0 | DIG-1546 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 44028.07 | 14960 | Central | KY | 360.3519 | 2020-10-28 | Coated pipe. Tried to wait the rain out but weather conditions got worse | [7 empty] | Padding Bucket | 4 | HR | RPB1 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | KYLE | BONNEAU | Foreman | 6 | 3 |  |  | Pickup-F150 or F250 or equal | 9 | HR | KYLE | Rockshield | 16 | LnFt |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 744 |  | 117 | 0 | 9 | 9 | 861 | 0 | [15 empty] | 861 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | JESSE | BERTHIAUME | Operator II | 6 | 2 |  |  | Pickup-F150 or F250 or equal | 8 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 535 |  | 104 |  | 8 | 8 | 639 | 0 | [15 empty] | 639 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | JACOB | CAPITANO | Laborer | 6 | 2 |  |  | Pickup-F150 or F250 or equal | 8 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 408 |  | 104 |  | 8 | 8 | 512 | 0 | [15 empty] | 512 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | BROC | CALIGER | Laborer | 6 | 2 |  |  | Tool Trailer | 8 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 408 |  | 40 |  | 8 | 8 | 448 | 0 | [15 empty] | 448 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | CODY | GAXIOLA | Laborer | 6 | 2 |  |  | 40' Flatbed trailer or equal | 8 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 408 |  | 148 |  | 8 | 8 | 556 | 0 | [15 empty] | 556 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | HEATHER | ENGLE | Laborer | 6 | 2 |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 408 |  | 368 |  | 8 | 8 | 776 | 0 | [15 empty] | 776 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 6 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 465 |  | 128 |  | 8 | 8 | 593 | 0 | [15 empty] | 593 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 724 |  |  | 8 | 724 | 0 | [15 empty] | 724 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | 0 | [15 empty] | 220 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP2 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | [7 empty] | Hammer Attachment | 8 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | [7 empty] | Brush Hog | 8 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-0545 - MC.400216.087 - 364.114 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-17790-44132-rev0 | DIG-0545 | 3500028468 | MC.400216.087 | 2020 | ABC Group, Inc | ALL | 25 | 63906.27 | 17790 | Central | KY | 364.114 | 2020-10-28 | Jeeped pipe and rockshield. Began backfill in rain | [7 empty] | Padding Bucket | 8 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | KYLE | BONNEAU | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | KYLE | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 |  | 2 | 2 | 325 | 0 | [15 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | JESSE | BERTHIAUME | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | JESSE | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | 0 | [15 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | JACOB | CAPITANO | Laborer | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15335 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 | 151 | 26 |  | 2 | 2 | 271 | 0 | [15 empty] | 271 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | BROC | CALIGER | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | UTT2181 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | 0 | [15 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | CODY | GAXIOLA | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT0705 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | 0 | [15 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | HEATHER | ENGLE | Laborer | 2 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9350 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 94 | 151 | 92 |  | 2 | 2 | 337 | 0 | [15 empty] | 337 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | ALTANOCHIR | JANTSAN | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | RF1040 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | 0 | [15 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0369 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 2 | HR | RAC8545 | [11 empty] | 27.5 |  |  |  | 55 |  |  | 2 | 55 | 0 | [15 empty] | 55 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP2 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | [7 empty] | Hammer Attachment | 2 | HR | RHA0706 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | [7 empty] | Brush Hog | 2 | HR | RBH4991 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1778 - MC.400216.085 - 384.804 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-10008649-44132-rev0 | DIG-1778 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 173507.05 | 10008649 | Central | KY | 384.804 | 2020-10-28 | set up traffic control and loaded out excavator and trailer to 0545 | [7 empty] | Padding Bucket | 2 | HR | RPB2 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | GERALD | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | GERALD | 2888 Coating | 6 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | 0 | [15 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | GERALD | SMITH | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | GERALD | Brushes | 12 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | GERALD | SMITH | Foreman | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | GERALD | Rockshield | 40 | LnFt |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 322 |  | 52 | 0 | 4 | 4 | 374 | 0 | [15 empty] | 374 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | GERALD | SMITH | Foreman |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | GERALD | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 200 |  | 26 |  | 2 | 2 | 226 | 0 | [15 empty] | 226 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | MICHAEL | RATLIFF | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | 0 | [15 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | MICHAEL | RATLIFF | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | MICHAEL | RATLIFF | Operator II | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 267.5 |  | 52 |  | 4 | 4 | 319.5 | 0 | [15 empty] | 319.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | MICHAEL | RATLIFF | Operator II |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 83 |  | 13 |  | 1 | 1 | 96 | 0 | [15 empty] | 96 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | 0 | [15 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | OJ | SEALS | Laborer | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 94 |  | 26 |  | 2 | 2 | 120 | 0 | [15 empty] | 120 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | OJ | SEALS | Laborer | 3 | 1 |  |  | Pickup-F150 or F250 or equal | 4 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 204 |  | 52 |  | 4 | 4 | 256 | 0 | [15 empty] | 256 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | OJ | SEALS | Laborer |  | 1 |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 63 |  | 13 |  | 1 | 1 | 76 | 0 | [15 empty] | 76 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | BARRETT | WISE | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | BARRETT | WISE | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | BARRETT | WISE | Laborer | 3 | 1 |  |  | Tool Trailer | 4 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 204 |  | 20 |  | 4 | 4 | 224 | 0 | [15 empty] | 224 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | BARRETT | WISE | Laborer |  | 1 |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 63 |  | 5 |  | 1 | 1 | 68 | 0 | [15 empty] | 68 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | DAVID | RATLIFF | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | 0 | [15 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | DAVID | RATLIFF | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | 0 | [15 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | DAVID | RATLIFF | Laborer | 3 | 1 |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 204 |  | 74 |  | 4 | 4 | 278 | 0 | [15 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | DAVID | RATLIFF | Laborer |  | 1 |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 63 |  | 18.5 |  | 1 | 1 | 81.5 | 0 | [15 empty] | 81.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | STEVE | CLARK | Truck Driver/CDL | 3 | 2 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 5 | HR | RF439 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 304.5 |  | 80 |  | 5 | 5 | 384.5 | 0 | [15 empty] | 384.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | 0 | [15 empty] | 46 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 2 | HR | RSS9336 | [11 empty] | 46 |  |  |  | 92 |  |  | 2 | 92 | 0 | [15 empty] | 92 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS9336 | [11 empty] | 46 |  |  |  | 184 |  |  | 4 | 184 | 0 | [15 empty] | 184 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [11 empty] | 46 |  |  |  | 46 |  |  | 1 | 46 | 0 | [15 empty] | 46 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | 0 | [15 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 2 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 181 |  |  | 2 | 181 | 0 | [15 empty] | 181 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 362 |  |  | 4 | 362 | 0 | [15 empty] | 362 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | 0 | [15 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Light Tower 6000 Watt | 2 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 26 |  |  | 2 | 26 | 0 | [15 empty] | 26 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Hammer Attachment | 2 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Hammer Attachment | 4 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Mobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Mobilization | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Recoat - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Recoat | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Padding Bucket | 2 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 2 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Padding Bucket | 4 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1549 - MC.400216.085 - 362.4633 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-18890-44132-rev0 | DIG-1549 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55217.13 | 18890 | Central | KY | 362.4633 | 2020-10-28 | MOB in. Jeep and recoated pipe. Put 40ft rockshield on, padded pipe, compacted with air pogo next to pipe. Finished backfilling and started seeding and clean up | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | GERALD | SMITH | Foreman | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | GERALD | Fertilizer | 200 | lbs |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 | 151 | 13 | 0 | 1 | 1 | 238 | 0 | [15 empty] | 238 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | GERALD | SMITH | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | GERALD | Lime | 16 | Bag |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | 0 | [15 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | MICHAEL | RATLIFF | Operator II | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | Seed Mix | 20 | lbs |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 61.5 | 151 | 13 | 0 | 1 | 1 | 225.5 | 0 | [15 empty] | 225.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | MICHAEL | RATLIFF | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | MICHAELR | Straw Bales | 30 | Ea |  |  |  |  | 61.5 | 83 | 0 | 151 | 13 | 0 | 61.5 |  | 13 | 0 | 1 | 1 | 74.5 | 0 | [15 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | OJ | SEALS | Laborer | 1 |  |  | 1 | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 | 151 | 13 |  | 1 | 1 | 211 | 0 | [15 empty] | 211 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | OJ | SEALS | Laborer | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15336 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 47 |  | 13 |  | 1 | 1 | 60 | 0 | [15 empty] | 60 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | RICHARD | ADKINS | Laborer | 1 |  |  | 1 | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 | 151 | 5 |  | 1 | 1 | 203 | 0 | [15 empty] | 203 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | RICHARD | ADKINS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | UTT2180 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | BARRETT | WISE | Laborer | 1 |  |  | 1 | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 | 151 | 18.5 |  | 1 | 1 | 216.5 | 0 | [15 empty] | 216.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | BARRETT | WISE | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT0229 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | 0 | [15 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | DAVID | RATLIFF | Laborer | 1 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 | 151 | 46 |  | 1 | 1 | 244 | 0 | [15 empty] | 244 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | DAVID | RATLIFF | Laborer | 1 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 1 | HR | RSS9336 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 47 |  | 46 |  | 1 | 1 | 93 | 0 | [15 empty] | 93 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | STEVE | CLARK | Truck Driver/CDL | 5 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [7 empty] | 53.5 | 72 | 0 | 151 | 90.5 |  | 267.5 | 151 | 90.5 |  | 5 | 1 | 509 | 0 | [15 empty] | 509 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 1 | HR | REX0842 | [11 empty] | 90.5 |  |  |  | 90.5 |  |  | 1 | 90.5 | 0 | [15 empty] | 90.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | 1-ton Truck (F350/F450/F550 or equal) | 1 | HR | RF439 | [11 empty] | 16 |  |  |  | 16 |  |  | 1 | 16 | 0 | [15 empty] | 16 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 1 | HR | RAC0858 | [11 empty] | 27.5 |  |  |  | 27.5 |  |  | 1 | 27.5 | 0 | [15 empty] | 27.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | Light Tower 6000 Watt | 1 | HR | RLP9317 | [11 empty] | 13 |  |  |  | 13 |  |  | 1 | 13 | 0 | [15 empty] | 13 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | Hammer Attachment | 1 | HR | RHA0141 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Clean-up / Remediation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Clean-up / Remediation | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1550 - MC.400216.085 - 362.5356 - Demobilization - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Demobilization | 3500028468-19030-44132-rev0 | DIG-1550 | 3500028468 | MC.400216.085 | 2020 | ABC Group, Inc | ALL | 15 | 55598.95 | 19030 | Central | KY | 362.5356 | 2020-10-28 | Finished grassing site. Demob | [7 empty] | Padding Bucket | 1 | HR | RPB2004 | [11 empty] | 0 |  |  |  | 0 |  |  | 1 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | THOMAS | FRANKLIN | Operator II | 8 |  |  | 1 | Pickup-F150 or F250 or equal | 8 | HR | THOMAS | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 492 | 151 | 104 |  | 8 | 8 | 747 | 0 | [15 empty] | 747 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | BOLDBAUTOR | ZORIGT | Laborer | 8 |  |  | 1 | Tool Trailer | 8 | HR | UTT2182 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 376 | 151 | 40 |  | 8 | 8 | 567 | 0 | [15 empty] | 567 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | DAVID | KNOTTS | Laborer | 8 |  |  | 1 | 40' Flatbed trailer or equal | 8 | HR | 22115 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 376 | 151 | 148 |  | 8 | 8 | 675 | 0 | [15 empty] | 675 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | TANNER | BRITT | Laborer | 8 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 8 | HR | RSS8664 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 376 | 151 | 368 |  | 8 | 8 | 895 | 0 | [15 empty] | 895 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | ALDO | RENYA | Truck Driver/CDL | 8 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 8 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 428 | 151 | 128 |  | 8 | 8 | 707 | 0 | [15 empty] | 707 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | [7 empty] | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 8 | HR | REX4155 | [11 empty] | 90.5 |  |  |  | 724 |  |  | 8 | 724 | 0 | [15 empty] | 724 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 8 | HR | RAC4049 | [11 empty] | 27.5 |  |  |  | 220 |  |  | 8 | 220 | 0 | [15 empty] | 220 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | [7 empty] | Light Tower 6000 Watt | 8 | HR | RLP5 | [11 empty] | 13 |  |  |  | 104 |  |  | 8 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | [7 empty] | Hammer Attachment | 8 | HR | RHA6A06 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | [7 empty] | Padding Bucket | 8 | HR | RPB5 | [11 empty] | 0 |  |  |  | 0 |  |  | 8 |  | 0 | [15 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1466 - MC.400216.032 - 635.962 - Backfill - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Backfill | 3500028468-9400-44132-rev0 | DIG-1466 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 33938.77 | 9400 | Central | IN | 635.962 | 2020-10-28 | Had JSA. 1/2 crew stayed for backfill | [7 empty] | Aluminum Shield/Trench Box - (6' x 10' to 8' x 10' - approx 1251 to 1686 lbs) | 8 | HR | RTB2482 | [11 empty] | 24.5 |  |  |  | 196 |  |  | 8 | 196 | 0 | [15 empty] | 196 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | Assisted another crew installing Atlas wrap. | CALEB | HOLTON | Foreman | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | CALEB | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 1092 | 151 | 169 |  | 13 | 13 | 1412 | 0 | [15 empty] | 1412 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | Assisted another crew installing Atlas wrap. | THOMAS | FRANKLIN | Operator II |  | 4 |  |  | Pickup-F150 or F250 or equal | 4 | HR | THOMASF | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 332 |  | 52 |  | 4 | 4 | 384 | 0 | [15 empty] | 384 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | Assisted another crew installing Atlas wrap. | MICHAEL | ANISZEWSKI | Laborer | 8 | 5 |  | 1 | Pickup-F150 or F250 or equal | 13 | HR | 19120 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 691 | 151 | 169 |  | 13 | 13 | 1011 | 0 | [15 empty] | 1011 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | Assisted another crew installing Atlas wrap. | BOLDBAUTOR | ZORIGT | Laborer |  | 4 |  |  | Sullair Air Compressor (251 to 375 CFM) or equal ** | 12 | HR | RAC4049 | [7 empty] | 47 | 63 | 0 | 151 | 27.5 |  | 252 |  | 330 |  | 4 | 12 | 582 | 0 | [15 empty] | 582 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | Assisted another crew installing Atlas wrap. | JORDAN | WIGGINS | Laborer | 8 | 4 |  | 1 | Sandblaster & Safety Equipment (Single Nozzle) | 12 | HR | RSP5 | [7 empty] | 47 | 63 | 0 | 151 | 23.5 |  | 628 | 151 | 282 |  | 12 | 12 | 1061 | 0 | [15 empty] | 1061 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | Assisted another crew installing Atlas wrap. | DAVID | KNOTTS | Laborer |  | 4 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 252 |  |  |  | 4 |  | 252 | 0 | [15 empty] | 252 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | Assisted another crew installing Atlas wrap. | TANNER | BRITT | Laborer |  | 4 | [13 empty] | 47 | 63 | 0 | 151 |  |  | 252 |  |  |  | 4 |  | 252 | 0 | [15 empty] | 252 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | Assisted another crew installing Atlas wrap. | ALDO | RENYA | Truck Driver/CDL |  | 4 |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | 1998 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 288 |  | 64 |  | 4 | 4 | 352 | 0 | [15 empty] | 352 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | BARKLEY | BROWN | Foreman | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | Filter Bag | 1 | Ea | State Line Service | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 296 | 151 | 52 | 0 | 4 | 4 | 499 | State Line Service | [15 empty] | 499 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | BARKLEY | BROWN | Foreman | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 296 |  | 52 |  | 4 | 4 | 348 | [16 empty] | 348 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | JOSHUA | MENDARIES | Operator II | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 | 151 | 52 |  | 4 | 4 | 449 | [16 empty] | 449 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | JOSHUA | MENDARIES | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | WAYLON | GREEN | Laborer | 4 |  |  | 1 | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 | 151 | 52 |  | 4 | 4 | 391 | [16 empty] | 391 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | WAYLON | GREEN | Laborer | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 188 |  | 52 |  | 4 | 4 | 240 | [16 empty] | 240 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | JOSE | VALLES | Laborer | 4 |  |  | 1 | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 | 151 | 20 |  | 4 | 4 | 359 | [16 empty] | 359 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | JOSE | VALLES | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | REYMUNDO | REYES | Laborer | 4 |  |  | 1 | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 | 151 | 74 |  | 4 | 4 | 413 | [16 empty] | 413 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | REYMUNDO | REYES | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | MARCELO | GOMEZ | Laborer | 4 |  |  | 1 | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 | 151 | 184 |  | 4 | 4 | 523 | [16 empty] | 523 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | MARCELO | GOMEZ | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | ANTHONY | MORENO | Laborer | 4 |  |  | 1 | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 | 151 | 362 |  | 4 | 4 | 701 | [16 empty] | 701 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | ANTHONY | MORENO | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 362 |  | 4 | 4 | 550 | [16 empty] | 550 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | EFREM | LEE | Truck Driver/CDL | 4 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 | 151 | 64 |  | 4 | 4 | 429 | [16 empty] | 429 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | EFREM | LEE | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858a | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858a | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP6 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP6 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Water Pump ( up to 2") | 4 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 24 |  |  | 4 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - Dig-1489 - MC.400216.032 - 667.112 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-51460-44132-rev0 | Dig-1489 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 198009.22 | 51460 | Central | IN | 667.112 | 2020-10-28 | Welders arrived, had JSA meeting. Prepped pipe for sleeve and transistioned 4' pipe. Started welding at 11am. Completed at 3pm | [7 empty] | Water Pump ( up to 2") | 4 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 24 |  |  | 4 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | BARKLEY | BROWN | Foreman | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | BARKLEY | Filter Bag | 1 | Ea | State Line Service | 0 | 0 | 0 | 74 | 100 | 0 | 151 | 13 | 0 | 222 |  | 39 | 0 | 3 | 3 | 261 | State Line Service | [15 empty] | 261 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | BARKLEY | BROWN | Foreman | 5 |  |  |  | Pickup-F150 or F250 or equal | 5 | HR | BARKLEY | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 370 |  | 65 |  | 5 | 5 | 435 | [16 empty] | 435 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | JOSHUA | MENDARIES | Operator II | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 184.5 |  | 39 |  | 3 | 3 | 223.5 | [16 empty] | 223.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | JOSHUA | MENDARIES | Operator II | 4 |  |  |  | Pickup-F150 or F250 or equal | 4 | HR | JOSHUAM | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 246 |  | 52 |  | 4 | 4 | 298 | [16 empty] | 298 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | WAYLON | GREEN | Laborer | 3 |  |  |  | Pickup-F150 or F250 or equal | 3 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 141 |  | 39 |  | 3 | 3 | 180 | [16 empty] | 180 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | WAYLON | GREEN | Laborer | 5 |  |  |  | Pickup-F150 or F250 or equal | 5 | HR | 19115 | [7 empty] | 47 | 63 | 0 | 151 | 13 |  | 235 |  | 65 |  | 5 | 5 | 300 | [16 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | JOSE | VALLES | Laborer | 3 |  |  |  | Tool Trailer | 3 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 141 |  | 15 |  | 3 | 3 | 156 | [16 empty] | 156 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | JOSE | VALLES | Laborer | 4 |  |  |  | Tool Trailer | 4 | HR | UTT2184 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 188 |  | 20 |  | 4 | 4 | 208 | [16 empty] | 208 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | REYMUNDO | REYES | Laborer | 3 |  |  |  | 40' Flatbed trailer or equal | 3 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 141 |  | 55.5 |  | 3 | 3 | 196.5 | [16 empty] | 196.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | REYMUNDO | REYES | Laborer | 4 |  |  |  | 40' Flatbed trailer or equal | 4 | HR | GNT7130 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 188 |  | 74 |  | 4 | 4 | 262 | [16 empty] | 262 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | MARCELO | GOMEZ | Laborer | 3 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 3 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 141 |  | 138 |  | 3 | 3 | 279 | [16 empty] | 279 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | MARCELO | GOMEZ | Laborer | 4 |  |  |  | Cat 272C Skid Steer/ASV (cap 2701 to 3250 lbs) or equal* | 4 | HR | RSS1663 | [7 empty] | 47 | 63 | 0 | 151 | 46 |  | 188 |  | 184 |  | 4 | 4 | 372 | [16 empty] | 372 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | ANTHONY | MORENO | Laborer | 3 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 3 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 141 |  | 271.5 |  | 3 | 3 | 412.5 | [16 empty] | 412.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | ANTHONY | MORENO | Laborer | 4 |  |  |  | Cat 320/321 LCR Excavator or equal* (39,001 to 53,000 lbs) | 4 | HR | REX1373 | [7 empty] | 47 | 63 | 0 | 151 | 90.5 |  | 188 |  | 362 |  | 4 | 4 | 550 | [16 empty] | 550 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | EFREM | LEE | Truck Driver/CDL | 3 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 3 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 160.5 |  | 48 |  | 3 | 3 | 208.5 | [16 empty] | 208.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | EFREM | LEE | Truck Driver/CDL | 4 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 4 | HR | RF0380 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 214 |  | 64 |  | 4 | 4 | 278 | [16 empty] | 278 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 3 | HR | RAC0858a | [11 empty] | 27.5 |  |  |  | 82.5 |  |  | 3 | 82.5 | [16 empty] | 82.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Sullair Air Compressor (251 to 375 CFM) or equal ** | 4 | HR | RAC0858a | [11 empty] | 27.5 |  |  |  | 110 |  |  | 4 | 110 | [16 empty] | 110 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Hammer Attachment | 3 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Hammer Attachment | 4 | HR | RHA1055 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Light Tower 6000 Watt | 3 | HR | RLP6 | [11 empty] | 13 |  |  |  | 39 |  |  | 3 | 39 | [16 empty] | 39 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Light Tower 6000 Watt | 4 | HR | RLP6 | [11 empty] | 13 |  |  |  | 52 |  |  | 4 | 52 | [16 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Brush Hog | 3 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Brush Hog | 4 | HR | RRC2986 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Padding Bucket | 3 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Padding Bucket | 4 | HR | RPB6 | [11 empty] | 0 |  |  |  | 0 |  |  | 4 | [17 empty] | 0 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Water Pump ( up to 2") | 3 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 18 |  |  | 3 | 18 | [16 empty] | 18 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1491 - MC.400216.032 - 671.952 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-58100-44132-rev0 | DIG-1491 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 223676.86 | 58100 | Central | IN | 671.952 | 2020-10-28 | Moved to site. Prepped pipe for sleeve and transitioned 4in sleeve to 2in sleeve. Started welding at 6pm. Completed at 10pm. Was sure to maintain welding procedures during welds | [7 empty] | Water Pump ( up to 2") | 4 | HR | 2INP6 | [11 empty] | 6 |  |  |  | 24 |  |  | 4 | 24 | [16 empty] | 24 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | GARRETT | DICKSON | Foreman | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | 15318 | Clocksprings | 14 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 |  | 148 | 151 | 26 | 0 | 2 | 2 | 325 | [16 empty] | 325 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | GARRETT | DICKSON | Foreman | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | 15318 | 2888 Coating | 2 | L |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 148 |  | 26 | 0 | 2 | 2 | 174 | 0 | [15 empty] | 174 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | GARRETT | DICKSON | Foreman | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | 15318 | Brushes | 18 | Ea |  |  |  |  | 74 | 100 | 0 | 151 | 13 | 0 | 74 |  | 13 | 0 | 1 | 1 | 87 | 0 | [15 empty] | 87 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | GARRETT | DICKSON | Foreman |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 500 |  | 65 |  | 5 | 5 | 565 | 0 | [15 empty] | 565 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | GARRETT | DICKSON | Foreman |  | 3 |  |  | Pickup-F150 or F250 or equal | 3 | HR | 15318 | [7 empty] | 74 | 100 | 0 | 151 | 13 |  | 300 |  | 39 |  | 3 | 3 | 339 | 0 | [15 empty] | 339 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | SHAWN | ROSE | Operator II | 2 |  |  | 1 | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 | 151 | 26 |  | 2 | 2 | 300 | 0 | [15 empty] | 300 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | SHAWN | ROSE | Operator II | 2 |  |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 123 |  | 26 |  | 2 | 2 | 149 | 0 | [15 empty] | 149 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | SHAWN | ROSE | Operator II | 1 |  |  |  | Pickup-F150 or F250 or equal | 1 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 61.5 |  | 13 |  | 1 | 1 | 74.5 | 0 | [15 empty] | 74.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | SHAWN | ROSE | Operator II |  | 5 |  |  | Pickup-F150 or F250 or equal | 5 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 415 |  | 65 |  | 5 | 5 | 480 | 0 | [15 empty] | 480 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | SHAWN | ROSE | Operator II |  | 2 |  |  | Pickup-F150 or F250 or equal | 2 | HR | SHAWN | [7 empty] | 61.5 | 83 | 0 | 151 | 13 |  | 166 |  | 26 |  | 2 | 2 | 192 | 0 | [15 empty] | 192 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | COLTON | ROBERTS | Laborer | 2 |  |  | 1 | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 | 151 | 10 |  | 2 | 2 | 255 | 0 | [15 empty] | 255 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | COLTON | ROBERTS | Laborer | 2 |  |  |  | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 94 |  | 10 |  | 2 | 2 | 104 | 0 | [15 empty] | 104 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | COLTON | ROBERTS | Laborer | 1 |  |  |  | Tool Trailer | 1 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 47 |  | 5 |  | 1 | 1 | 52 | 0 | [15 empty] | 52 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | COLTON | ROBERTS | Laborer |  | 5 |  |  | Tool Trailer | 5 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 315 |  | 25 |  | 5 | 5 | 340 | 0 | [15 empty] | 340 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | COLTON | ROBERTS | Laborer |  | 2 |  |  | Tool Trailer | 2 | HR | 2178 | [7 empty] | 47 | 63 | 0 | 151 | 5 |  | 126 |  | 10 |  | 2 | 2 | 136 | 0 | [15 empty] | 136 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | ZACHARY | POWDERS | Laborer | 2 |  |  | 1 | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 | 151 | 37 |  | 2 | 2 | 282 | 0 | [15 empty] | 282 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | ZACHARY | POWDERS | Laborer | 2 |  |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 94 |  | 37 |  | 2 | 2 | 131 | 0 | [15 empty] | 131 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Initial Coating Inspection - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Initial Coating Inspection | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | ZACHARY | POWDERS | Laborer | 1 |  |  |  | 40' Flatbed trailer or equal | 1 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 47 |  | 18.5 |  | 1 | 1 | 65.5 | 0 | [15 empty] | 65.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Repair - Install Clocksprings - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Repair - Install Clocksprings | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | ZACHARY | POWDERS | Laborer |  | 5 |  |  | 40' Flatbed trailer or equal | 5 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 315 |  | 92.5 |  | 5 | 5 | 407.5 | 0 | [15 empty] | 407.5 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Stand-by - Other (See Comments) - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Stand-by - Other (See Comments) | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | ZACHARY | POWDERS | Laborer |  | 2 |  |  | 40' Flatbed trailer or equal | 2 | HR | GNT8 | [7 empty] | 47 | 63 | 0 | 151 | 18.5 |  | 126 |  | 37 |  | 2 | 2 | 163 | 0 | [15 empty] | 163 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Site Prep - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Site Prep | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | IAIN | ALLRED | Truck Driver/CDL | 2 |  |  | 1 | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 | 151 | 32 |  | 2 | 2 | 290 | 0 | [15 empty] | 290 | ABC 3500028468-03 | ABC 3500028468-03
CWP - DIG-1473 - MC.400216.032 - 651.017 - Pipe Preparation - 2 - BL - | CWP | Central | CS | 2020-11-03 | 2 | BL |  | Pipe Preparation | 3500028468-29250-44132-rev0 | DIG-1473 | 3500028468 | MC.400216.032 | 2020 | ABC Group, Inc | ALL | 1 | 113235.03 | 29250 | Central | IN | 651.017 | 2020-10-28 | JSA meeting. Prepped site for tasks of the day. Blasted pipe. NDE did assessment and crew started applying atlas wraps. Crew began cleaning site. Had to stay in hole and watch due to hazardous weather moving in. | IAIN | ALLRED | Truck Driver/CDL | 2 |  |  |  | 1-ton Truck (F350/F450/F550 or equal) | 2 | HR | R19108 | [7 empty] | 53.5 | 72 | 0 | 151 | 16 |  | 107 |  | 32 |  | 2 | 2 | 139 | 0 | [15 empty] | 139 | ABC 3500028468-03 | ABC 3500028468-03