## Sheet1
LEVEL | WBS Code | WBS Name
0 | PROJECT | SCHEDULE OR WORK
2 | PROJECT.1 | GENERAL
4 | PROJECT.1.1 | MILESTONES
6 | PROJECT.1.1.1 | KEY DATES
6 | PROJECT.1.1.2 | CONTRACTUAL MILESTONES
8 | PROJECT.1.1.2.1 | MILESTONE (#1)-(COMMENCEMENT OF THE WORKS)
8 | PROJECT.1.1.2.2 | MILESTONE (#2)-(CONTRACTOR MOBILIZATION)
8 | PROJECT.1.1.2.3 | MILESTONE (#3)-(EMPLOYERS SITE OFFICES)
8 | PROJECT.1.1.2.4 | MILESTONE (#4)-(LONG LEAD MEP PLANT & EQUIPMENT)
8 | PROJECT.1.1.2.5 | MILESTONE (#5)-(ALL FULL SCALE MOCK UP'S COMPLETE)
8 | PROJECT.1.1.2.6 | MILESTONE (#6)-(CIVIL WORKS COMPLETE FOR MEP WORKS)
8 | PROJECT.1.1.2.7 | MILESTONE (#7)-(BUILDING WEATHER TIGHT)
8 | PROJECT.1.1.2.8 | MILESTONE (#8)-(SUBSTATIONS)
8 | PROJECT.1.1.2.9 | MILESTONE (#9)-(POWER AND WATER ON)
8 | PROJECT.1.1.2.10 | MILESTONE (#10)-(CHILLED WATER)
8 | PROJECT.1.1.2.11 | MILESTONE (#11)-(WILD AIR)
8 | PROJECT.1.1.2.12 | MILESTONE (#12)-(MEP SYSTEMS COMPLETE)
8 | PROJECT.1.1.2.13 | MILESTONE (#13)-(SPECIALIST SYSTEMS ROOMS)
8 | PROJECT.1.1.2.14 | MILESTONE (#14)-(VERTICAL TRANSPORTATION)
8 | PROJECT.1.1.2.15 | MILESTONE (#15)-(COMMISSIONING)
8 | PROJECT.1.1.2.16 | MILESTONE (#16)-(MALL MANAGEMENT OFFICE, FM OFFICE, SECURITY ROOM & STORES)
8 | PROJECT.1.1.2.17 | MILESTONE (#17)-(MALL FLOOR FINISHES)
8 | PROJECT.1.1.2.18 | MILESTONE (#18)-(EXTERNAL WORKS/LANDSCAPING)
8 | PROJECT.1.1.2.19 | MILESTONE (#19)-(SERVICE LEVEL & CAR PARKS)
8 | PROJECT.1.1.2.20 | MILESTONE (#20)-(CIVIL DEFENSE INSPECTION)
8 | PROJECT.1.1.2.21 | MILESTONE (#21)-(BUILDING COMPLETION CERTIFICATE)
8 | PROJECT.1.1.2.22 | MILESTONE (#22)-(ADDC FINAL INSPECTION & POWER ON)
8 | PROJECT.1.1.2.23 | MILESTONE (#23)-(SNOW PLAY/SNOW PARK)
6 | PROJECT.1.1.3 | TENANT ACCESS MILESTONES-(TAM'S)
8 | PROJECT.1.1.3.1 | TENANT ACCESS MILESTONE (#1)-(SNOW PLAY/SNOW PARK)
8 | PROJECT.1.1.3.2 | TENANT ACCESS MILESTONE (#2)-(HYPERMARKET)
8 | PROJECT.1.1.3.3 | TENANT ACCESS MILESTONE (#3)-(CINEMA & FAMILY ENTERTAINMENT CENTRE)
8 | PROJECT.1.1.3.4 | TENANT ACCESS MILESTONE (#4)-(ANCHOR UNITS)
8 | PROJECT.1.1.3.5 | TENANT ACCESS MILESTONE (#5)-(MAJOR UNITS AND MINI MAJOR UNITS)
8 | PROJECT.1.1.3.6 | TENANT ACCESS MILESTONE (#6)-(FOOD COURT OUTLETS-(MANGROVE & CRYSTAL))
8 | PROJECT.1.1.3.7 | TENANT ACCESS MILESTONE (#7)-(FLAGSHIP UNITS)
8 | PROJECT.1.1.3.8 | TENANT ACCESS MILESTONE (#8)-(FOOD & BEVERAGE UNITS WITH COOKING)
8 | PROJECT.1.1.3.9 | TENANT ACCESS MILESTONE (#9)-(FOOD & BEVERAGE UNITS WITHOUT COOKING)
8 | PROJECT.1.1.3.10 | TENANT ACCESS MILESTONE (#10)-(LINE UNITS/LINE SHOPS)
8 | PROJECT.1.1.3.11 | TENANT ACCESS MILESTONE (#11)-(KIOSKS REQUIRING MEP SERVICES)
4 | PROJECT.1.2 | PRELIMINARIES
4 | PROJECT.1.6 | VARIATION COST
4 | PROJECT.1.3 | CONTRACTOR MOBILIZATION
4 | PROJECT.1.4 | EMPLOYERS OFFICE
6 | PROJECT.1.4.1 | PROCUREMENT
8 | PROJECT.1.4.1.1 | SUBCONTRACTING
10 | PROJECT.1.4.1.1.1 | PREPARATION
10 | PROJECT.1.4.1.1.2 | APPROVAL
8 | PROJECT.1.4.1.2 | MATERIAL SELECTION
10 | PROJECT.1.4.1.2.1 | PREPARATION
10 | PROJECT.1.4.1.2.2 | APPROVAL
8 | PROJECT.1.4.1.3 | MATERIAL DELIVERY
6 | PROJECT.1.4.2 | ENGINEERING
8 | PROJECT.1.4.2.1 | PREPARATION
8 | PROJECT.1.4.2.2 | APPROVAL
6 | PROJECT.1.4.3 | CONSTRUCTION
8 | PROJECT.1.4.3.1 | STRUCTURE
8 | PROJECT.1.4.3.2 | INSTALLATION OF OFFICES
8 | PROJECT.1.4.3.3 | MEP
8 | PROJECT.1.4.3.4 | INTERNAL WORKS
8 | PROJECT.1.4.3.5 | EXTERNAL WORKS
8 | PROJECT.1.4.3.6 | TIE-INS
4 | PROJECT.1.5 | CARINA VIEWS
6 | PROJECT.1.5.1 | PROCUREMENT
8 | PROJECT.1.5.1.1 | SUBCONTRACTING
10 | PROJECT.1.5.1.1.1 | PREPARATION
10 | PROJECT.1.5.1.1.2 | APPROVAL
8 | PROJECT.1.5.1.2 | MATERIAL SELECTION
10 | PROJECT.1.5.1.2.1 | PREPARATION
10 | PROJECT.1.5.1.2.2 | APPROVAL
8 | PROJECT.1.5.1.3 | MATERIAL DELIVERY
6 | PROJECT.1.5.2 | ENGINEERING
8 | PROJECT.1.5.2.1 | PREPARATION
8 | PROJECT.1.5.2.2 | APPROVAL
6 | PROJECT.1.5.3 | CONSTRUCTION
8 | PROJECT.1.5.3.1 | SUBCONTRACTOR OFFICES
8 | PROJECT.1.5.3.2 | REST AREA
8 | PROJECT.1.5.3.3 | ROAD CROSSING BRIDGE
8 | PROJECT.1.5.3.4 | TOILETS
8 | PROJECT.1.5.3.5 | FIRST AID AND MOSQUE
8 | PROJECT.1.5.3.6 | YARDS, WORKSHOPS AND STORES
8 | PROJECT.1.5.3.7 | TESTING
2 | PROJECT.2 | MOCK UP BUILDING
4 | PROJECT.2.1 | PROCUREMENT
6 | PROJECT.2.1.1 | SUBCONTRACTING
8 | PROJECT.2.1.1.PREP | PREPARATION AND SUBMISSION
8 | PROJECT.2.1.1.APROV | REVIEW AND APPROVAL
6 | PROJECT.2.1.2 | MATERIAL SELECTION
8 | PROJECT.2.1.2.PREP | PREPARATION AND SUBMISSION
8 | PROJECT.2.1.2.APROV | REVIEW AND APPROVAL
6 | PROJECT.2.1.3 | ORDER, FABRICATION AND DELIVERY
4 | PROJECT.2.2 | SHOP DRAWINGS
6 | PROJECT.2.2.1 | PREPARATION AND SUBMISSION
6 | PROJECT.2.2.2 | REVIEW AND APPROVAL
4 | PROJECT.2.3 | CONSTRUCTION
6 | PROJECT.2.3.1 | STRUCTURE
8 | PROJECT.2.3.1.1 | SUB-STRUCTURE
8 | PROJECT.2.3.1.2 | SUPPER STRUCTURE
6 | PROJECT.2.3.2 | BLOCK WORKS AND PARTITIONS
6 | PROJECT.2.3.3 | MEP
6 | PROJECT.2.3.4 | INTERNAL FITOUT WORKS
8 | PROJECT.2.3.4.1 | FOH TOILET ZONE
10 | PROJECT.2.3.4.1.1 | DYNAMIC TYPE TOILET
12 | PROJECT.2.3.4.1.1.1 | FLOOR FINISHES
12 | PROJECT.2.3.4.1.1.2 | WALL FINISHES
12 | PROJECT.2.3.4.1.1.3 | CEILING FINISHES
12 | PROJECT.2.3.4.1.1.4 | JOINERY FINISHES
12 | PROJECT.2.3.4.1.1.5 | FF&E
10 | PROJECT.2.3.4.1.2 | URBAN TYPE TOILET
12 | PROJECT.2.3.4.1.2.1 | FLOOR FINISHES
12 | PROJECT.2.3.4.1.2.2 | WALL FINISHES
12 | PROJECT.2.3.4.1.2.3 | CEILING FINISHES
12 | PROJECT.2.3.4.1.2.4 | JOINERY FINISHES
12 | PROJECT.2.3.4.1.2.5 | FF&E
10 | PROJECT.2.3.4.1.3 | TOILET LOBBY
12 | PROJECT.2.3.4.1.3.1 | FLOOR FINISHES
12 | PROJECT.2.3.4.1.3.2 | WALL FINISHES
12 | PROJECT.2.3.4.1.3.3 | CEILING FINISHES
12 | PROJECT.2.3.4.1.3.4 | JOINERY FINISHES
8 | PROJECT.2.3.4.2 | FOH THEMED ACCESS
10 | PROJECT.2.3.4.2.1 | MANGROVE AREA
12 | PROJECT.2.3.4.2.1.1 | FLOOR FINISHES
12 | PROJECT.2.3.4.2.1.2 | WALL FINISHES
12 | PROJECT.2.3.4.2.1.3 | CEILING FINISHES
12 | PROJECT.2.3.4.2.1.4 | JOINERY & GLASS FINISHES
10 | PROJECT.2.3.4.2.2 | URBAN AREA
12 | PROJECT.2.3.4.2.2.1 | FLOOR FINISHES
12 | PROJECT.2.3.4.2.2.2 | WALL FINISHES
12 | PROJECT.2.3.4.2.2.3 | CEILING FINISHES
12 | PROJECT.2.3.4.2.2.4 | JOINERY & GLASS FINISHES
10 | PROJECT.2.3.4.2.3 | DYNAMIC AREA
12 | PROJECT.2.3.4.2.3.1 | FLOOR FINISHES
12 | PROJECT.2.3.4.2.3.2 | WALL FINISHES
12 | PROJECT.2.3.4.2.3.3 | CEILING FINISHES
12 | PROJECT.2.3.4.2.3.4 | JOINERY & GLASS FINISHES
10 | PROJECT.2.3.4.2.4 | TYPICAL LOBBY
12 | PROJECT.2.3.4.2.4.1 | FLOOR FINISHES
12 | PROJECT.2.3.4.2.4.2 | WALL FINISHES
12 | PROJECT.2.3.4.2.4.3 | CEILING FINISHES
12 | PROJECT.2.3.4.2.4.4 | GLASS FINISHES
8 | PROJECT.2.3.4.3 | BOH AREA
10 | PROJECT.2.3.4.3.1 | STAIRCASES (GF to FF)
12 | PROJECT.2.3.4.3.1.1 | FLOOR FINISHES
12 | PROJECT.2.3.4.3.1.2 | WALL FINISHES
12 | PROJECT.2.3.4.3.1.3 | CEILING FINISHES
12 | PROJECT.2.3.4.3.1.4 | JOINERY & METAL FINISHES
10 | PROJECT.2.3.4.3.2 | LOBBIED AT FIRST FLOOR
12 | PROJECT.2.3.4.3.2.1 | FLOOR FINISHES
12 | PROJECT.2.3.4.3.2.2 | WALL FINISHES
12 | PROJECT.2.3.4.3.2.3 | CEILING FINISHES
6 | PROJECT.2.3.5 | FACADE
6 | PROJECT.2.3.6 | ROOF
6 | PROJECT.2.3.7 | TIE-INS
2 | PROJECT.3 | THE MALL
4 | PROJECT.3.1 | STRUCTURE
6 | PROJECT.3.1.1 | PROCUREMENT
8 | PROJECT.3.1.1.1 | SUBCONTRACTING
10 | PROJECT.3.1.1.1.1 | PREPARATION AND SUBMISSION
10 | PROJECT.3.1.1.1.2 | REVIEW AND APPROVAL
8 | PROJECT.3.1.1.2 | MATERIAL SELECTION
10 | PROJECT.3.1.1.2.1 | PREPARATION AND SUBMISSION
10 | PROJECT.3.1.1.2.2 | REVIEW AND APPROVAL
8 | PROJECT.3.1.1.3 | ORDER AND DELIVERY
8 | PROJECT.3.1.1.4 | FACTORY ACCEPTANCE TEST (FAT's)
6 | PROJECT.3.1.2 | ENGINEERING
8 | PROJECT.3.1.2.1 | SHOP DRAWINGS
10 | PROJECT.3.1.2.1.1 | PREPARATION AND SUBMISSION
12 | PROJECT.3.1.2.1.1.1 | GENERAL
12 | PROJECT.3.1.2.1.1.2 | AREA A
12 | PROJECT.3.1.2.1.1.3 | AREA B
12 | PROJECT.3.1.2.1.1.4 | AREA C
10 | PROJECT.3.1.2.1.2 | REVIEW AND APPROVAL
12 | PROJECT.3.1.2.1.2.1 | GENERAL
12 | PROJECT.3.1.2.1.2.2 | AREA A
12 | PROJECT.3.1.2.1.2.3 | AREA B
12 | PROJECT.3.1.2.1.2.4 | AREA C
8 | PROJECT.3.1.2.2 | METHOD STATEMENTS
10 | PROJECT.3.1.2.2.1 | SUBMITTAL
10 | PROJECT.3.1.2.2.2 | APPROVAL
6 | PROJECT.3.1.3 | CONSTRUCTION
8 | PROJECT.3.1.3.1 | CONCRETE STRUCTURE
10 | PROJECT.3.1.3.1.1 | EARTH WORKS
10 | PROJECT.3.1.3.1.2 | RAFT INCLUDING MEP EMBEDMENTS
12 | PROJECT.3.1.3.1.2.1 | AREA A
14 | PROJECT.3.1.3.1.2.1.1 | POUR A2
14 | PROJECT.3.1.3.1.2.1.2 | POUR A5
14 | PROJECT.3.1.3.1.2.1.3 | POUR A1
14 | PROJECT.3.1.3.1.2.1.4 | POUR A7
14 | PROJECT.3.1.3.1.2.1.5 | POUR A3
14 | PROJECT.3.1.3.1.2.1.6 | POUR A4
14 | PROJECT.3.1.3.1.2.1.7 | POUR A6
14 | PROJECT.3.1.3.1.2.1.8 | POUR A'5
14 | PROJECT.3.1.3.1.2.1.9 | POUR A'2
14 | PROJECT.3.1.3.1.2.1.10 | POUR A'1
14 | PROJECT.3.1.3.1.2.1.11 | POUR A'3
14 | PROJECT.3.1.3.1.2.1.12 | POUR A'7
14 | PROJECT.3.1.3.1.2.1.13 | POUR A'6
14 | PROJECT.3.1.3.1.2.1.14 | POUR A'4
14 | PROJECT.3.1.3.1.2.1.15 | POUR A11
14 | PROJECT.3.1.3.1.2.1.16 | POUR A9
14 | PROJECT.3.1.3.1.2.1.17 | POUR A10
14 | PROJECT.3.1.3.1.2.1.18 | POUR A12
14 | PROJECT.3.1.3.1.2.1.19 | POUR A'8
14 | PROJECT.3.1.3.1.2.1.20 | POUR A8
12 | PROJECT.3.1.3.1.2.2 | AREA B
14 | PROJECT.3.1.3.1.2.2.1 | POUR B'9
14 | PROJECT.3.1.3.1.2.2.2 | POUR B'11
14 | PROJECT.3.1.3.1.2.2.3 | POUR B'10
14 | PROJECT.3.1.3.1.2.2.4 | POUR B'8
14 | PROJECT.3.1.3.1.2.2.5 | POUR B1
14 | PROJECT.3.1.3.1.2.2.6 | POUR B2
14 | PROJECT.3.1.3.1.2.2.7 | POUR B'1
14 | PROJECT.3.1.3.1.2.2.8 | POUR B3
14 | PROJECT.3.1.3.1.2.2.9 | POUR B'13
14 | PROJECT.3.1.3.1.2.2.10 | POUR B13
14 | PROJECT.3.1.3.1.2.2.11 | POUR B'2
14 | PROJECT.3.1.3.1.2.2.12 | POUR B'3
14 | PROJECT.3.1.3.1.2.2.13 | POUR B'14
14 | PROJECT.3.1.3.1.2.2.14 | POUR B14
14 | PROJECT.3.1.3.1.2.2.15 | POUR B9
14 | PROJECT.3.1.3.1.2.2.16 | POUR B10
14 | PROJECT.3.1.3.1.2.2.17 | POUR B8
14 | PROJECT.3.1.3.1.2.2.18 | POUR B4
14 | PROJECT.3.1.3.1.2.2.19 | POUR B5
14 | PROJECT.3.1.3.1.2.2.20 | POUR B6
14 | PROJECT.3.1.3.1.2.2.21 | POUR B7
14 | PROJECT.3.1.3.1.2.2.22 | POUR B11
14 | PROJECT.3.1.3.1.2.2.23 | POUR B'12
14 | PROJECT.3.1.3.1.2.2.24 | POUR B12
12 | PROJECT.3.1.3.1.2.3 | AREA C
14 | PROJECT.3.1.3.1.2.3.1 | POUR C5
14 | PROJECT.3.1.3.1.2.3.2 | POUR C1
14 | PROJECT.3.1.3.1.2.3.3 | POUR C6
14 | PROJECT.3.1.3.1.2.3.4 | POUR C'1
14 | PROJECT.3.1.3.1.2.3.5 | POUR C7
14 | PROJECT.3.1.3.1.2.3.6 | POUR C2
14 | PROJECT.3.1.3.1.2.3.7 | POUR C8
14 | PROJECT.3.1.3.1.2.3.8 | POUR C'2
14 | PROJECT.3.1.3.1.2.3.9 | POUR C3
14 | PROJECT.3.1.3.1.2.3.10 | POUR C'3
14 | PROJECT.3.1.3.1.2.3.11 | POUR C'4
14 | PROJECT.3.1.3.1.2.3.12 | POUR C4
10 | PROJECT.3.1.3.1.3 | VERTICALS AND SLABS INCLUDING MEP EMBEDMENTS
12 | PROJECT.3.1.3.1.3.1 | BASEMENT 2
14 | PROJECT.3.1.3.1.3.1.1 | AREA B (BOH SLAB)
12 | PROJECT.3.1.3.1.3.2 | BASEMENT 1
14 | PROJECT.3.1.3.1.3.2.1 | AREA A
14 | PROJECT.3.1.3.1.3.2.2 | AREA B
14 | PROJECT.3.1.3.1.3.2.3 | AREA C
12 | PROJECT.3.1.3.1.3.3 | GROUND FLOOR
14 | PROJECT.3.1.3.1.3.3.1 | AREA A
14 | PROJECT.3.1.3.1.3.3.2 | AREA B
14 | PROJECT.3.1.3.1.3.3.3 | AREA C
12 | PROJECT.3.1.3.1.3.4 | LEVEL1
14 | PROJECT.3.1.3.1.3.4.1 | AREA A
16 | PROJECT.3.1.3.1.3.4.1.1 | Construction Joints (Interface with Steel Structure) including base plate installations
14 | PROJECT.3.1.3.1.3.4.2 | AREA B
16 | PROJECT.3.1.3.1.3.4.2.1 | Construction Joints (Interface with Steel Structure) including base plate installations
14 | PROJECT.3.1.3.1.3.4.3 | AREA C
16 | PROJECT.3.1.3.1.3.4.3.1 | Construction Joints (Interface with Steel Structure)
12 | PROJECT.3.1.3.1.3.5 | LEVEL 2 PODIUM PARKING 1
14 | PROJECT.3.1.3.1.3.5.1 | AREA A
16 | PROJECT.3.1.3.1.3.5.1.1 | Construction Joints (Interface with Steel Structure) including base plate installations
14 | PROJECT.3.1.3.1.3.5.2 | AREA B
16 | PROJECT.3.1.3.1.3.5.2.1 | Construction Joints (Interface with Steel Structure) including base plate installations
14 | PROJECT.3.1.3.1.3.5.3 | AREA C
16 | PROJECT.3.1.3.1.3.5.3.1 | Construction Joints (Interface with Steel Structure)
12 | PROJECT.3.1.3.1.3.6 | LEVEL 3 PODIUM PARKING 2
14 | PROJECT.3.1.3.1.3.6.1 | VERTICALS ONLY
16 | PROJECT.3.1.3.1.3.6.1.1 | AREA A
16 | PROJECT.3.1.3.1.3.6.1.2 | AREA B
14 | PROJECT.3.1.3.1.3.6.2 | AREA B
16 | PROJECT.3.1.3.1.3.6.2.1 | Construction Joints (Interface with Steel Structure)
14 | PROJECT.3.1.3.1.3.6.3 | AREA C
16 | PROJECT.3.1.3.1.3.6.3.1 | Construction Joints (Interface with Steel Structure)
12 | PROJECT.3.1.3.1.3.7 | PODIUM PARKING 3 (ROOF/PP3)
14 | PROJECT.3.1.3.1.3.7.1 | AREA A
16 | PROJECT.3.1.3.1.3.7.1.1 | Construction Joints (Interface with Steel Structure) including Encased Beam Installations
14 | PROJECT.3.1.3.1.3.7.2 | AREA B
16 | PROJECT.3.1.3.1.3.7.2.1 | Construction Joints (Interface with Steel Structure)
14 | PROJECT.3.1.3.1.3.7.3 | AREA C
16 | PROJECT.3.1.3.1.3.7.3.1 | Construction Joints (Interface with Steel Structure)
12 | PROJECT.3.1.3.1.3.8 | PODIUM PARKING 4
14 | PROJECT.3.1.3.1.3.8.1 | AREA B
16 | PROJECT.3.1.3.1.3.8.1.1 | Construction Joints (Interface with Steel Structure)
14 | PROJECT.3.1.3.1.3.8.2 | AREA C
16 | PROJECT.3.1.3.1.3.8.2.1 | Construction Joints (Interface with Steel Structure)
14 | PROJECT.3.1.3.1.3.8.3 | PARAPET
10 | PROJECT.3.1.3.1.4 | PERIMETER WATERPROOFING (WP) AND BACKFILLING
12 | PROJECT.3.1.3.1.4.1 | NORTH SIDE
12 | PROJECT.3.1.3.1.4.2 | EAST SIDE
12 | PROJECT.3.1.3.1.4.3 | SOUTH SIDE
12 | PROJECT.3.1.3.1.4.4 | WEST SIDE
8 | PROJECT.3.1.3.2 | STEEL STRUCTURE (Including Decking, FF, Screed, Sheeting & Glazing)
10 | PROJECT.3.1.3.2.1 | BASE PLATES
12 | PROJECT.3.1.3.2.1.1 | RAFT
12 | PROJECT.3.1.3.2.1.2 | BP2 (BOH AREA)
12 | PROJECT.3.1.3.2.1.3 | BP1
12 | PROJECT.3.1.3.2.1.4 | GF
10 | PROJECT.3.1.3.2.2 | ENCASED COLUMNS
12 | PROJECT.3.1.3.2.2.1 | FROM SERVICE LEVEL
12 | PROJECT.3.1.3.2.2.2 | FROM BP2 LEVEL
12 | PROJECT.3.1.3.2.2.3 | FROM BP1 LEVEL
12 | PROJECT.3.1.3.2.2.4 | FROM GF LEVEL
10 | PROJECT.3.1.3.2.3 | LINK BRIDGE
12 | PROJECT.3.1.3.2.3.1 | L1
14 | PROJECT.3.1.3.2.3.1.1 | STEEL STRUCTURE
14 | PROJECT.3.1.3.2.3.1.2 | METAL DECKING
16 | PROJECT.3.1.3.2.3.1.2.1 | FABRICATION AND DELIVERY
16 | PROJECT.3.1.3.2.3.1.2.2 | INSTALLATION
14 | PROJECT.3.1.3.2.3.1.4 | SCREED
14 | PROJECT.3.1.3.2.3.1.8 | FIRE PROOFING (Cement.)
12 | PROJECT.3.1.3.2.3.8 | L2
14 | PROJECT.3.1.3.2.3.8.1 | ENGINEERING
16 | PROJECT.3.1.3.2.3.8.1.4 | PREPARATION AND SUBMISSION
16 | PROJECT.3.1.3.2.3.8.1.1 | REVIEW AND APPROVAL
14 | PROJECT.3.1.3.2.3.8.2 | FABRICATION AND DELIVERY
14 | PROJECT.3.1.3.2.3.8.6 | STEEL STRUCTURE INSTALLATION
14 | PROJECT.3.1.3.2.3.8.7 | METAL DECKING
16 | PROJECT.3.1.3.2.3.8.7.1 | FABRICATION AND DELIVERY
16 | PROJECT.3.1.3.2.3.8.7.2 | INSTALLATION
14 | PROJECT.3.1.3.2.3.8.4 | SCREED
14 | PROJECT.3.1.3.2.3.8.8 | FIRE PROOFING (Intumes.)
10 | PROJECT.3.1.3.2.9 | TRANSFER FRAME
12 | PROJECT.3.1.3.2.9.10 | L1
14 | PROJECT.3.1.3.2.9.10.1 | ENCASED BEAMS (FOR L1 TRANSFER FRAME)
14 | PROJECT.3.1.3.2.9.10.2 | SECONDARY BEAMS AND DECKING
16 | PROJECT.3.1.3.2.9.10.2.1 | C1 & C4 & B13 (Right)
16 | PROJECT.3.1.3.2.9.10.2.2 | B5 & B13 (Top)
16 | PROJECT.3.1.3.2.9.10.2.3 | C7 & C9 & C10 & B22 (Right)
16 | PROJECT.3.1.3.2.9.10.2.4 | B22 (Bottom) & B23
12 | PROJECT.3.1.3.2.9.1 | L2/PP1
14 | PROJECT.3.1.3.2.9.1.1 | STEEL STRUCTURE
16 | PROJECT.3.1.3.2.9.1.1.1 | INSTALLATION OF TEMPORARY SUPPORTS
16 | PROJECT.3.1.3.2.9.1.1.2 | INSTALLATION OF TRANSFER FRAMES
16 | PROJECT.3.1.3.2.9.1.1.3 | REMOVAL OF TEMPORARY SUPPORTS
14 | PROJECT.3.1.3.2.9.1.2 | METAL DECKING
14 | PROJECT.3.1.3.2.9.1.3 | SCREED
14 | PROJECT.3.1.3.2.9.1.4 | FIRE PROOFING (Intumes.)
14 | PROJECT.3.1.3.2.9.1.5 | SKYLIGHTS
12 | PROJECT.3.1.3.2.9.3 | PP2
14 | PROJECT.3.1.3.2.9.3.1 | STEEL STRUCTURE
16 | PROJECT.3.1.3.2.9.3.1.1 | ENGINEERING
18 | PROJECT.3.1.3.2.9.3.1.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.9.3.1.1.2 | REVIEW AND APPROVAL
16 | PROJECT.3.1.3.2.9.3.1.3 | FABRICATION AND DELIVERY
16 | PROJECT.3.1.3.2.9.3.1.2 | INSTALLATION
18 | PROJECT.3.1.3.2.9.3.1.2.2 | INSTALLATION OF TRANSFER FRAMES
18 | PROJECT.3.1.3.2.9.3.1.2.1 | INSTALLATION OF TEMPORARY SUPPORTS
18 | PROJECT.3.1.3.2.9.3.1.2.3 | REMOVAL OF TEMPORARY SUPPORTS
14 | PROJECT.3.1.3.2.9.3.2 | METAL DECKING
14 | PROJECT.3.1.3.2.9.3.3 | SCREED
14 | PROJECT.3.1.3.2.9.3.4 | FIRE PROOFING (Intumes.)
12 | PROJECT.3.1.3.2.9.4 | PP3
14 | PROJECT.3.1.3.2.9.4.5 | ENGINEERING
16 | PROJECT.3.1.3.2.9.4.5.2 | PREPARATION AND SUBMISSION
16 | PROJECT.3.1.3.2.9.4.5.1 | REVIEW AND APPROVAL
14 | PROJECT.3.1.3.2.9.4.6 | FABRICATION AND DELIVERY
14 | PROJECT.3.1.3.2.9.4.1 | STEEL STRUCTURE
16 | PROJECT.3.1.3.2.9.4.1.2 | INSTALLATION OF TRANSFER FRAMES
16 | PROJECT.3.1.3.2.9.4.1.1 | INSTALLATION OF TEMPORARY SUPPORTS
16 | PROJECT.3.1.3.2.9.4.1.3 | REMOVAL OF TEMPORARY SUPPORTS
14 | PROJECT.3.1.3.2.9.4.2 | METAL DECKING
14 | PROJECT.3.1.3.2.9.4.3 | SCREED
14 | PROJECT.3.1.3.2.9.4.4 | FIRE PROOFING (Cement.)
12 | PROJECT.3.1.3.2.9.5 | PP4
14 | PROJECT.3.1.3.2.9.5.6 | ENGINEERING
16 | PROJECT.3.1.3.2.9.5.6.2 | PREPARATION AND SUBMISSION
16 | PROJECT.3.1.3.2.9.5.6.1 | REVIEW AND APPROVAL
14 | PROJECT.3.1.3.2.9.5.7 | FABRICATION AND DELIVERY
14 | PROJECT.3.1.3.2.9.5.1 | STEEL STRUCTURE
16 | PROJECT.3.1.3.2.9.5.1.2 | INSTALLATION OF TRANSFER FRAMES
16 | PROJECT.3.1.3.2.9.5.1.1 | INSTALLATION OF TEMPORARY SUPPORTS
16 | PROJECT.3.1.3.2.9.5.1.3 | REMOVAL OF TEMPORARY SUPPORTS
14 | PROJECT.3.1.3.2.9.5.2 | METAL DECKING
14 | PROJECT.3.1.3.2.9.5.3 | SCREED
14 | PROJECT.3.1.3.2.9.5.4 | FIRE PROOFING (Cement.)
14 | PROJECT.3.1.3.2.9.5.5 | SKY LIGHTS
12 | PROJECT.3.1.3.2.9.2 | ROOF
14 | PROJECT.3.1.3.2.9.2.7 | ENGINEERING
16 | PROJECT.3.1.3.2.9.2.7.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.1.3.2.9.2.7.2 | REVIEW AND APPROVAL
14 | PROJECT.3.1.3.2.9.2.8 | FABRICATION AND DELIVERY
14 | PROJECT.3.1.3.2.9.2.1 | STEEL STRUCTURE INSTALLATION
14 | PROJECT.3.1.3.2.9.2.2 | METAL DECKING
14 | PROJECT.3.1.3.2.9.2.3 | SCREED
14 | PROJECT.3.1.3.2.9.2.5 | PURLINS
14 | PROJECT.3.1.3.2.9.2.6 | ROOF SANDWICH PANELS
14 | PROJECT.3.1.3.2.9.2.9 | SKYLIGHTS AT ROOF
14 | PROJECT.3.1.3.2.9.2.4 | FIRE PROOFING (Cement.)
12 | PROJECT.3.1.3.2.9.6 | Zone C1
14 | PROJECT.3.1.3.2.9.6.5 | FABRICATION AND DELIVERY
14 | PROJECT.3.1.3.2.9.6.3 | STEEL STRUCTURE
14 | PROJECT.3.1.3.2.9.6.2 | METAL DECKING
14 | PROJECT.3.1.3.2.9.6.1 | SCREED
14 | PROJECT.3.1.3.2.9.6.4 | FIRE PROOFING
10 | PROJECT.3.1.3.2.10 | FRONT CANOPY
12 | PROJECT.3.1.3.2.10.1 | FABRICATION & DELIVERY
12 | PROJECT.3.1.3.2.10.2 | STEEL STRUCTURE INSTALLATION
12 | PROJECT.3.1.3.2.10.3 | METAL DECKING
12 | PROJECT.3.1.3.2.10.4 | SCREED
10 | PROJECT.3.1.3.2.5 | CINEMA
12 | PROJECT.3.1.3.2.5.4 | STEEL STRUCTURE INSTALLATION
12 | PROJECT.3.1.3.2.5.8 | PURLINS
14 | PROJECT.3.1.3.2.5.8.1 | ENGINEERING
14 | PROJECT.3.1.3.2.5.8.2 | FABRICATION AND DELIVERY
14 | PROJECT.3.1.3.2.5.8.3 | INSTALLATION
12 | PROJECT.3.1.3.2.5.6 | METAL DECKING AND SCREED
12 | PROJECT.3.1.3.2.5.5 | SANDWICH PANEL
14 | PROJECT.3.1.3.2.5.5.2 | FABRICATION AND DELIVERY
14 | PROJECT.3.1.3.2.5.5.3 | INSTALLATION
12 | PROJECT.3.1.3.2.5.7 | FIRE PROOFING
12 | PROJECT.3.1.3.2.5.1 | WIND BEAMS
14 | PROJECT.3.1.3.2.5.1.1 | ENGINEERING
16 | PROJECT.3.1.3.2.5.1.1.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.1.3.2.5.1.1.2 | REVIEW AND APPROVAL
14 | PROJECT.3.1.3.2.5.1.3 | FABRICATION AND DELIVERY
14 | PROJECT.3.1.3.2.5.1.4 | INSTALLATION
14 | PROJECT.3.1.3.2.5.1.5 | FIRE PROOFING
10 | PROJECT.3.1.3.2.6 | SNOWPARK AND SNOW CENTER
12 | PROJECT.3.1.3.2.6.2 | SNOW CENTER
14 | PROJECT.3.1.3.2.6.2.1 | STEEL STRUCTURE
16 | PROJECT.3.1.3.2.6.2.1.1 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.6.2.1.2 | INSTALLATION
14 | PROJECT.3.1.3.2.6.2.3 | METAL DECKING
16 | PROJECT.3.1.3.2.6.2.3.1 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.6.2.3.2 | INSTALLATION
14 | PROJECT.3.1.3.2.6.2.2 | SCREED
14 | PROJECT.3.1.3.2.6.2.4 | PURLINS
16 | PROJECT.3.1.3.2.6.2.4.1 | ENGINEERING
18 | PROJECT.3.1.3.2.6.2.4.1.1 | PREPARATION & SUBMISSION
18 | PROJECT.3.1.3.2.6.2.4.1.2 | REVIEW & APPROVAL
16 | PROJECT.3.1.3.2.6.2.4.3 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.6.2.4.2 | INSTALLATION
14 | PROJECT.3.1.3.2.6.2.6 | SANDWICH PANELS
16 | PROJECT.3.1.3.2.6.2.6.1 | ENGINEERING
18 | PROJECT.3.1.3.2.6.2.6.1.1 | PREPARATION & SUBMISSION
18 | PROJECT.3.1.3.2.6.2.6.1.2 | REVIEW & APPROVAL
16 | PROJECT.3.1.3.2.6.2.6.3 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.6.2.6.2 | INSTALLATION
14 | PROJECT.3.1.3.2.6.2.5 | FIRE PROOFING
12 | PROJECT.3.1.3.2.6.5 | SNOW PARK
14 | PROJECT.3.1.3.2.6.5.1 | COLUMNS
16 | PROJECT.3.1.3.2.6.5.1.1 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.6.5.1.2 | INSTALLATION
14 | PROJECT.3.1.3.2.6.5.2 | RAMPS
16 | PROJECT.3.1.3.2.6.5.2.4 | STEEL STRUCTURE
18 | PROJECT.3.1.3.2.6.5.2.4.3 | ENGINEERING
20 | PROJECT.3.1.3.2.6.5.2.4.3.1 | PREPARATION & SUBMISSION
20 | PROJECT.3.1.3.2.6.5.2.4.3.2 | REVIEW & APPROVAL
18 | PROJECT.3.1.3.2.6.5.2.4.1 | FABRICATION & DELIVERY
18 | PROJECT.3.1.3.2.6.5.2.4.2 | INSTALLATION
16 | PROJECT.3.1.3.2.6.5.2.1 | METAL DECKING
18 | PROJECT.3.1.3.2.6.5.2.1.1 | FABRICATION & DELIVERY
18 | PROJECT.3.1.3.2.6.5.2.1.2 | INSTALLATION
16 | PROJECT.3.1.3.2.6.5.2.6 | MEP PROVISIONS AND BUILDERS WORKS
16 | PROJECT.3.1.3.2.6.5.2.3 | SCREED
16 | PROJECT.3.1.3.2.6.5.2.2 | FIRE PROOFING
14 | PROJECT.3.1.3.2.6.5.3 | TRUSSES & INFILLS
16 | PROJECT.3.1.3.2.6.5.3.1 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.6.5.3.2 | INSTALLATION
14 | PROJECT.3.1.3.2.6.5.4 | PURLINS
16 | PROJECT.3.1.3.2.6.5.4.3 | ENGINEERING
18 | PROJECT.3.1.3.2.6.5.4.3.1 | PREPARATION & SUBMISSION
18 | PROJECT.3.1.3.2.6.5.4.3.2 | REVIEW & APPROVAL
16 | PROJECT.3.1.3.2.6.5.4.1 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.6.5.4.2 | INSTALLATION
18 | PROJECT.3.1.3.2.6.5.4.2.1 | ROOF PURLINS
18 | PROJECT.3.1.3.2.6.5.4.2.2 | WALL PURLINS
14 | PROJECT.3.1.3.2.6.5.5 | WALL & ROOF SHEETING
16 | PROJECT.3.1.3.2.6.5.5.3 | ENGINEERING
18 | PROJECT.3.1.3.2.6.5.5.3.1 | PREPARATION & SUBMISSION
18 | PROJECT.3.1.3.2.6.5.5.3.2 | REVIEW & APPROVAL
16 | PROJECT.3.1.3.2.6.5.5.1 | FABRICATION & DELIVERY
18 | PROJECT.3.1.3.2.6.5.5.1.1 | WALL SHEETING
18 | PROJECT.3.1.3.2.6.5.5.1.2 | ROOF SHEETING
16 | PROJECT.3.1.3.2.6.5.5.2 | INSTALLATION
18 | PROJECT.3.1.3.2.6.5.5.2.1 | WALL SHEETING
18 | PROJECT.3.1.3.2.6.5.5.2.2 | ROOF SHEETING
20 | PROJECT.3.1.3.2.6.5.5.2.2.LINER | LINER SHEET
20 | PROJECT.3.1.3.2.6.5.5.2.2.1 | VAPOUR BARRIER & TOP MAT
20 | PROJECT.3.1.3.2.6.5.5.2.2.2 | BRACKETS & INSULATION
20 | PROJECT.3.1.3.2.6.5.5.2.2.3 | TOP SHEET
14 | PROJECT.3.1.3.2.6.5.6 | GLAZING
16 | PROJECT.3.1.3.2.6.5.6.3 | ENGINEERING
18 | PROJECT.3.1.3.2.6.5.6.3.1 | PREPARATION & SUBMISSION
18 | PROJECT.3.1.3.2.6.5.6.3.2 | REVIEW & APPROVAL
16 | PROJECT.3.1.3.2.6.5.6.1 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.6.5.6.2 | INSTALLATION
10 | PROJECT.3.1.3.2.7 | SKYLIGHTS
12 | PROJECT.3.1.3.2.7.2 | SKYLIGHT AT EL +31.200 (West Mall, Dynamic West & Urban West)
14 | PROJECT.3.1.3.2.7.2.8 | STEEL STRUCTURE
16 | PROJECT.3.1.3.2.7.2.8.4 | ENGINEERING
18 | PROJECT.3.1.3.2.7.2.8.4.2 | SHOP DRAWINGS
20 | PROJECT.3.1.3.2.7.2.8.4.2.1 | PREPARATION AND SUBMISSION
20 | PROJECT.3.1.3.2.7.2.8.4.2.2 | REVIEW AND APPROVAL
16 | PROJECT.3.1.3.2.7.2.8.3 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.7.2.8.1 | INSTALLATION OF TEMPARORY SUPPORTS
16 | PROJECT.3.1.3.2.7.2.8.2 | INSTALLATION OF STEEL STRUCTURE
14 | PROJECT.3.1.3.2.7.2.1 | PURLINS
16 | PROJECT.3.1.3.2.7.2.1.1 | ENGINEERING
18 | PROJECT.3.1.3.2.7.2.1.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.7.2.1.1.2 | REVIEW AND APPROVAL
16 | PROJECT.3.1.3.2.7.2.1.2 | FABRICATION AND DELIVERY
16 | PROJECT.3.1.3.2.7.2.1.4 | INSTALLATION
14 | PROJECT.3.1.3.2.7.2.2 | SANDWICH PANELS / STANDING SEAM
16 | PROJECT.3.1.3.2.7.2.2.3 | ENGINEERING
18 | PROJECT.3.1.3.2.7.2.2.3.2 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.7.2.2.3.1 | REVIEW AND APPROVAL
16 | PROJECT.3.1.3.2.7.2.2.2 | FABRICATION AND DELIVERY
16 | PROJECT.3.1.3.2.7.2.2.1 | INSTALLATION OF SANDWICH PANELS
16 | PROJECT.3.1.3.2.7.2.2.5 | INSTALLATION OF STANDING SEAM
18 | PROJECT.3.1.3.2.7.2.2.5.4 | INSTALLATION OF LINER SHEET
18 | PROJECT.3.1.3.2.7.2.2.5.1 | INSTALLATION OF VAPOUR BARRIER
18 | PROJECT.3.1.3.2.7.2.2.5.2 | INSTALLATION OF INSULATION & TOP HAT
18 | PROJECT.3.1.3.2.7.2.2.5.3 | INSTALLATION OF TOP SHEET
14 | PROJECT.3.1.3.2.7.2.4 | FIREPROOFING (INT)
14 | PROJECT.3.1.3.2.7.2.6 | GLAZING AND CLADDINGS
16 | PROJECT.3.1.3.2.7.2.6.1 | GLAZING - CLERESTORY
16 | PROJECT.3.1.3.2.7.2.6.2 | GLAZING - TOP PORTION
12 | PROJECT.3.1.3.2.7.1 | SKYLIGHT AT EL +36.600
14 | PROJECT.3.1.3.2.7.1.1 | ACCESS PLATFORMS
16 | PROJECT.3.1.3.2.7.1.1.3 | ENGINEERING
18 | PROJECT.3.1.3.2.7.1.1.3.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.7.1.1.3.2 | REVIEW AND APPROVAL
16 | PROJECT.3.1.3.2.7.1.1.4 | PROCUREMENT AND DELIVERY
16 | PROJECT.3.1.3.2.7.1.1.1 | ERECTION
16 | PROJECT.3.1.3.2.7.1.1.2 | DISMANTLING
14 | PROJECT.3.1.3.2.7.1.2 | STEEL STRUCTURE
16 | PROJECT.3.1.3.2.7.1.2.3 | ENGINEERING
18 | PROJECT.3.1.3.2.7.1.2.3.1 | CALCULATIONS
20 | PROJECT.3.1.3.2.7.1.2.3.1.1 | PREPARATION AND SUBMISSION
20 | PROJECT.3.1.3.2.7.1.2.3.1.2 | REVIEW AND APPROVAL
18 | PROJECT.3.1.3.2.7.1.2.3.2 | SHOP DRAWINGS
20 | PROJECT.3.1.3.2.7.1.2.3.2.1 | PREPARATION AND SUBMISSION
20 | PROJECT.3.1.3.2.7.1.2.3.2.2 | REVIEW AND APPROVAL
16 | PROJECT.3.1.3.2.7.1.2.4 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.7.1.2.5 | INSTALLATION
14 | PROJECT.3.1.3.2.7.1.3 | PURLINS
16 | PROJECT.3.1.3.2.7.1.3.2 | SHOP DRAWINGS
18 | PROJECT.3.1.3.2.7.1.3.2.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.7.1.3.2.2 | REVIEW AND APPROVAL
16 | PROJECT.3.1.3.2.7.1.3.1 | FABRICATION AND DELIVERY
16 | PROJECT.3.1.3.2.7.1.3.7 | INSTALLATION
18 | PROJECT.3.1.3.2.7.1.3.7.1 | INSTALLATION AT LOWER LEVEL
18 | PROJECT.3.1.3.2.7.1.3.7.2 | INSTALLATION AT HIGHER LEVEL
14 | PROJECT.3.1.3.2.7.1.4 | SANDWICH PANELS / STANDING SEAM
16 | PROJECT.3.1.3.2.7.1.4.3 | ENGINEERING
18 | PROJECT.3.1.3.2.7.1.4.3.2 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.7.1.4.3.1 | REVIEW AND APPROVAL
16 | PROJECT.3.1.3.2.7.1.4.2 | FABRICATION AND DELIVERY
16 | PROJECT.3.1.3.2.7.1.4.1 | INSTALLATION
18 | PROJECT.3.1.3.2.7.1.4.1.1 | SANDWICH PANELS
18 | PROJECT.3.1.3.2.7.1.4.1.2 | ROOF STANDING SEAM
20 | PROJECT.3.1.3.2.7.1.4.1.2.1 | LINER SHEET
20 | PROJECT.3.1.3.2.7.1.4.1.2.2 | VAPOUR BARRIER & TOP HAT
20 | PROJECT.3.1.3.2.7.1.4.1.2.3 | INSULATION & BRACKETS
20 | PROJECT.3.1.3.2.7.1.4.1.2.4 | TOP SHEET
18 | PROJECT.3.1.3.2.7.1.4.1.3 | METAL DECKING & SCREED
14 | PROJECT.3.1.3.2.7.1.6 | FIREPROOFING (INT)
14 | PROJECT.3.1.3.2.7.1.7 | SECONDARY STEEL
16 | PROJECT.3.1.3.2.7.1.7.1 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.7.1.7.2 | INSTALLATION
14 | PROJECT.3.1.3.2.7.1.5 | GLAZING AND CLADDINGS
12 | PROJECT.3.1.3.2.7.3 | ISOLATED SKYLIGHTS
14 | PROJECT.3.1.3.2.7.3.1 | STRUCTURAL STEEL COMPLETION
14 | PROJECT.3.1.3.2.7.3.2 | FRAMING & GLAZING COMPLETION
10 | PROJECT.3.1.3.2.8 | PLANT ROOMS
12 | PROJECT.3.1.3.2.8.1 | PLANT ROOMS SUPPORTED ON PP3 (EXCLUDING SNOW PARK)
14 | PROJECT.3.1.3.2.8.1.3 | STEEL STRUCTURE
16 | PROJECT.3.1.3.2.8.1.3.3 | ENGINEERING
18 | PROJECT.3.1.3.2.8.1.3.3.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.8.1.3.3.2 | REVIEW AND APPROVAL
16 | PROJECT.3.1.3.2.8.1.3.1 | FABRICATION AND DELIVERY
16 | PROJECT.3.1.3.2.8.1.3.2 | INSTALLATION
14 | PROJECT.3.1.3.2.8.1.10 | FIRE PROOFING WORKS
14 | PROJECT.3.1.3.2.8.1.4 | PURLINS
16 | PROJECT.3.1.3.2.8.1.4.1 | ENGINEERING
18 | PROJECT.3.1.3.2.8.1.4.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.8.1.4.1.2 | REVIEW AND APPROVALS
16 | PROJECT.3.1.3.2.8.1.4.2 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.8.1.4.3 | INSTALLATION
14 | PROJECT.3.1.3.2.8.1.14 | SANDWICH PANELS
16 | PROJECT.3.1.3.2.8.1.14.1 | ENGINEERING
18 | PROJECT.3.1.3.2.8.1.14.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.8.1.14.1.2 | REVIEW AND APPROVALS
16 | PROJECT.3.1.3.2.8.1.14.2 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.8.1.14.3 | INSTALLATION
12 | PROJECT.3.1.3.2.8.2 | PLANT ROOMS SUPPORTED ON PP4 (EXCLUDING CINEMA)
14 | PROJECT.3.1.3.2.8.2.6 | STEEL STRUCTURE
16 | PROJECT.3.1.3.2.8.2.6.1 | ENGINEERING
18 | PROJECT.3.1.3.2.8.2.6.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.8.2.6.1.2 | REVIEW AND APPROVALS
16 | PROJECT.3.1.3.2.8.2.6.3 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.8.2.6.2 | INSTALLATION
14 | PROJECT.3.1.3.2.8.2.9 | FIRE PROOFING WORKS
14 | PROJECT.3.1.3.2.8.2.7 | PURLINS
16 | PROJECT.3.1.3.2.8.2.7.1 | ENGINEERING
18 | PROJECT.3.1.3.2.8.2.7.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.8.2.7.1.2 | REVIEW AND APPROVALS
16 | PROJECT.3.1.3.2.8.2.7.3 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.8.2.7.2 | INSTALLATION
14 | PROJECT.3.1.3.2.8.2.8 | SANDWICH PANELS
16 | PROJECT.3.1.3.2.8.2.8.1 | ENGINEERING
18 | PROJECT.3.1.3.2.8.2.8.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.1.3.2.8.2.8.1.2 | REVIEW AND APPROVALS
16 | PROJECT.3.1.3.2.8.2.8.3 | FABRICATION & DELIVERY
16 | PROJECT.3.1.3.2.8.2.8.2 | INSTALLATION
8 | PROJECT.3.1.3.3 | TOWER CRANES (TC)
10 | PROJECT.3.1.3.3.1 | TOWER CRANE FOUNDATION
10 | PROJECT.3.1.3.3.2 | TOWER CRANE ERECTION
10 | PROJECT.3.1.3.3.3 | TOWER CRANE DISMANTLING
10 | PROJECT.3.1.3.3.4 | TOWER CRANE AREA INFILL
12 | PROJECT.3.1.3.3.4.1 | INFILL FOR TC-01
12 | PROJECT.3.1.3.3.4.2 | INFILL FOR TC-02
12 | PROJECT.3.1.3.3.4.3 | INFILL FOR TC-03
12 | PROJECT.3.1.3.3.4.4 | INFILL FOR TC-04
12 | PROJECT.3.1.3.3.4.5 | INFILL FOR TC-05
12 | PROJECT.3.1.3.3.4.6 | INFILL FOR TC-06
12 | PROJECT.3.1.3.3.4.7 | INFILL FOR TC-07
12 | PROJECT.3.1.3.3.4.9 | INFILL FOR TC-08
12 | PROJECT.3.1.3.3.4.10 | INFILL FOR TC-09
12 | PROJECT.3.1.3.3.4.11 | INFILL FOR TC-10
12 | PROJECT.3.1.3.3.4.12 | INFILL FOR TC-11
12 | PROJECT.3.1.3.3.4.13 | INFILL FOR TC-12
12 | PROJECT.3.1.3.3.4.14 | INFILL FOR TC-13
12 | PROJECT.3.1.3.3.4.15 | INFILL FOR TC-14
12 | PROJECT.3.1.3.3.4.16 | INFILL FOR TC-15
12 | PROJECT.3.1.3.3.4.17 | INFILL FOR TC-16
4 | PROJECT.3.2 | FINISHING
6 | PROJECT.3.2.1 | PROCUREMENT
8 | PROJECT.3.2.1.1 | SUBCONTRACTING
10 | PROJECT.3.2.1.1.1 | PREPARATION AND SUBMISSION
10 | PROJECT.3.2.1.1.2 | REVIEW AND APPROVAL
8 | PROJECT.3.2.1.2 | MATERIAL SELECTION
10 | PROJECT.3.2.1.2.1 | PREPARATION AND SUBMISSION
10 | PROJECT.3.2.1.2.2 | REVIEW AND APPROVALS
8 | PROJECT.3.2.1.3 | ORDER, FABRICATION AND DELIVERY
8 | PROJECT.3.2.1.4 | FACTORY ACCEPTANCE TEST (FAT's)
6 | PROJECT.3.2.2 | SHOP DRAWINGS
8 | PROJECT.3.2.2.1 | PREPARATION AND SUBMISSION
8 | PROJECT.3.2.2.2 | REVIEW AND APPROVAL
6 | PROJECT.3.2.3 | CONSTRUCTION
8 | PROJECT.3.2.3.1 | BOH LEVEL
10 | PROJECT.3.2.3.1.3 | GENERAL
10 | PROJECT.3.2.3.1.1 | DRY AREAS
12 | PROJECT.3.2.3.1.1.1 | LB-05 A, LB-05B, LB-05C/ GARBAGE ROOM SL 203
12 | PROJECT.3.2.3.1.1.2 | MACHINE CHARGING YARD SL-410 & CLEANER OFFICE SL-409
12 | PROJECT.3.2.3.1.1.3 | ELECTRICAL STORE/CIVIL STORE/SUBCONTRACTOR STORE SL 449
12 | PROJECT.3.2.3.1.1.4 | PAINT STORE/DISPOSAL STORE SL 452
12 | PROJECT.3.2.3.1.1.5 | CHEMICAL STORE & CLEANING CONSUMABLE STORE SL-407
12 | PROJECT.3.2.3.1.1.6 | FILTER WASHING ROOM SL448/ FILTER STORE ROOM SL-447
12 | PROJECT.3.2.3.1.1.7 | DATA CENTER SL 446/TETRA ROOM SL-454
12 | PROJECT.3.2.3.1.1.8 | LB-04 A, LB-04B
12 | PROJECT.3.2.3.1.1.9 | CORRIDOR SL-413
12 | PROJECT.3.2.3.1.1.10 | CORRIDOR SL-402
12 | PROJECT.3.2.3.1.1.11 | CORRIDOR SL-401
12 | PROJECT.3.2.3.1.1.12 | CORRIDOR SL-456
12 | PROJECT.3.2.3.1.1.13 | SUBSTATION NO-6
10 | PROJECT.3.2.3.1.2 | TOILETS 431, 432, 241, 229 & ABLUTION AND KITCHEN 429
8 | PROJECT.3.2.3.2 | SL
10 | PROJECT.3.2.3.2.12 | GENERAL
10 | PROJECT.3.2.3.2.1 | ZONE 1
12 | PROJECT.3.2.3.2.1.3 | GENERAL
12 | PROJECT.3.2.3.2.1.1 | DRY AREAS INCLUDING SUBSTATION NO-1
12 | PROJECT.3.2.3.2.1.2 | WET AREAS INCLUDING TOILET 165
10 | PROJECT.3.2.3.2.2 | ZONE 2
12 | PROJECT.3.2.3.2.2.3 | GENERAL
12 | PROJECT.3.2.3.2.2.1 | DRY AREAS INCLUDING SUBSTATION NO-5
12 | PROJECT.3.2.3.2.2.2 | WET AREAS INCLUDING TOILET 179
10 | PROJECT.3.2.3.2.3 | ZONE 3
12 | PROJECT.3.2.3.2.3.3 | GENERAL
12 | PROJECT.3.2.3.2.3.1 | DRY AREAS INCLUDING ETS No-3
12 | PROJECT.3.2.3.2.3.2 | WET AREAS INCLUDING TOILET 199
10 | PROJECT.3.2.3.2.4 | ZONE 4
12 | PROJECT.3.2.3.2.4.3 | GENERAL
12 | PROJECT.3.2.3.2.4.1 | DRY AREAS INCLUDING SUBSTATION NO-2
12 | PROJECT.3.2.3.2.4.2 | WET AREAS INCLUDING TOILET 146
10 | PROJECT.3.2.3.2.5 | ZONE 6
12 | PROJECT.3.2.3.2.5.3 | GENERAL
12 | PROJECT.3.2.3.2.5.1 | DRY AREAS
12 | PROJECT.3.2.3.2.5.2 | WET AREAS INCLUDING TOILETS 214, 225, 223
10 | PROJECT.3.2.3.2.6 | ZONE 7
12 | PROJECT.3.2.3.2.6.3 | GENERAL
12 | PROJECT.3.2.3.2.6.1 | DRY AREAS
12 | PROJECT.3.2.3.2.6.2 | WET AREAS INCLUDING TOILET 120
10 | PROJECT.3.2.3.2.7 | ZONE 9
12 | PROJECT.3.2.3.2.7.3 | GENERAL
12 | PROJECT.3.2.3.2.7.1 | DRY AREAS INCLUDING SUBSTATION NO-3
12 | PROJECT.3.2.3.2.7.2 | WET AREAS
10 | PROJECT.3.2.3.2.8 | ZONE 11
12 | PROJECT.3.2.3.2.8.3 | GENERAL
12 | PROJECT.3.2.3.2.8.1 | DRY AREAS INCLUDING ETS NO-2
12 | PROJECT.3.2.3.2.8.2 | WET AREAS INCLUDING TOILETS 241, 225
10 | PROJECT.3.2.3.2.9 | ZONE 12
12 | PROJECT.3.2.3.2.9.2 | GENERAL
12 | PROJECT.3.2.3.2.9.1 | DRY AREAS INCLUDING SUBSTATION NO-4
12 | PROJECT.3.2.3.2.9.3 | WET AREAS INCLUDING TOILET 300
10 | PROJECT.3.2.3.2.10 | ZONE 13
12 | PROJECT.3.2.3.2.10.3 | GENERAL
12 | PROJECT.3.2.3.2.10.1 | DRY AREAS
12 | PROJECT.3.2.3.2.10.2 | WET AREAS INCLUDING TOILETS 285, 276
10 | PROJECT.3.2.3.2.11 | ZONE 14
12 | PROJECT.3.2.3.2.11.3 | GENERAL
12 | PROJECT.3.2.3.2.11.1 | DRY AREAS INCLUDING SUBSTATION NO-7 AND ETS NO-1
12 | PROJECT.3.2.3.2.11.2 | WET AREAS
8 | PROJECT.3.2.3.3 | BP2
10 | PROJECT.3.2.3.3.1 | SECTION A
12 | PROJECT.3.2.3.3.1.5 | GENERAL
12 | PROJECT.3.2.3.3.1.1 | FOH - LOBBY 06 - Zone 02
12 | PROJECT.3.2.3.3.1.2 | BOH (BP2-LIFTS AND STAIRCASE ROOMS/LOBBY/ELECTRICAL ROOMS)
12 | PROJECT.3.2.3.3.1.3 | CARPARK AND RAMPS
12 | PROJECT.3.2.3.3.1.6 | STAIRCASES SL/BP2-BP1
14 | PROJECT.3.2.3.3.1.6.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.3.1.6.1 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.3.2 | SECTION B
12 | PROJECT.3.2.3.3.2.5 | GENERAL
12 | PROJECT.3.2.3.3.2.4 | FOH LOBBIES
14 | PROJECT.3.2.3.3.2.4.1 | LOBBY 01 Zone 04
14 | PROJECT.3.2.3.3.2.4.7 | LOBBY 02 Zone 07&09
14 | PROJECT.3.2.3.3.2.4.8 | LOBBY 04 Zone 11
14 | PROJECT.3.2.3.3.2.4.6 | LOBBY 05 Zone 06
12 | PROJECT.3.2.3.3.2.2 | BOH (BP2-LIFTS AND STAIRCASE ROOMS/LOBBY/ELECTRICAL ROOMS)
12 | PROJECT.3.2.3.3.2.3 | CARPARK AND RAMPS
12 | PROJECT.3.2.3.3.2.9 | STAIRCASES SL/BP2-BP1
14 | PROJECT.3.2.3.3.2.9.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.3.2.9.1 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.3.3 | SECTION C
12 | PROJECT.3.2.3.3.3.5 | GENERAL
12 | PROJECT.3.2.3.3.3.6 | FOH LOBBY 03 Zone 10
12 | PROJECT.3.2.3.3.3.2 | BOH (BP2-LIFTS AND STAIRCASE ROOMS/LOBBY/ELECTRICAL ROOMS)
12 | PROJECT.3.2.3.3.3.3 | CARPARK AND RAMPS
12 | PROJECT.3.2.3.3.3.8 | STAIRCASES SL/BP2-BP1
14 | PROJECT.3.2.3.3.3.8.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.3.3.8.1 | ACCESS STAIRCASES
8 | PROJECT.3.2.3.4 | BP1
10 | PROJECT.3.2.3.4.1 | SECTION A
12 | PROJECT.3.2.3.4.1.5 | GENERAL
12 | PROJECT.3.2.3.4.1.4 | FOH: LOBBIES
14 | PROJECT.3.2.3.4.1.4.1 | LOBBY 6 - Zone 02
14 | PROJECT.3.2.3.4.1.4.6 | LOBBY 7 (Entrance West) Zone 01
12 | PROJECT.3.2.3.4.1.2 | BOH
14 | PROJECT.3.2.3.4.1.2.1 | BP1-CPF RM-114
14 | PROJECT.3.2.3.4.1.2.2 | BP1-CPF RM-111
14 | PROJECT.3.2.3.4.1.2.3 | BP1-CPF RM-109
14 | PROJECT.3.2.3.4.1.2.4 | BP1-CPF RM-126 & 123
14 | PROJECT.3.2.3.4.1.2.5 | ELECTRICAL ROOM-BP1 131/UTT RM/BMS RM/BATRM/LOBBY/STAIRCASE/LIF ROOM BP1/Corridor-129
14 | PROJECT.3.2.3.4.1.2.6 | UTT RM BP 207/BMS RM/LOBBY/STAIRCASE/LIFT ROOM BP1 207
12 | PROJECT.3.2.3.4.1.3 | CARPARK
12 | PROJECT.3.2.3.4.1.7 | STAIRCASES BP1-GF
14 | PROJECT.3.2.3.4.1.7.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.4.1.7.1 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.4.2 | SECTION B
12 | PROJECT.3.2.3.4.2.5 | GENERAL
12 | PROJECT.3.2.3.4.2.4 | FOH: LOBBIES
14 | PROJECT.3.2.3.4.2.4.1 | LOBBY 01 Zone 04
14 | PROJECT.3.2.3.4.2.4.6 | LOBBY 02 Zone 09
14 | PROJECT.3.2.3.4.2.4.7 | LOBBY 04 Zone 11
14 | PROJECT.3.2.3.4.2.4.8 | LOBBY 05 Zone 06
14 | PROJECT.3.2.3.4.2.4.9 | LOBBY 08 (Mangrove North Entrance) Zone 07
14 | PROJECT.3.2.3.4.2.4.10 | LOBBY 09 (Main Entrance Mangrove South) Zone 06
12 | PROJECT.3.2.3.4.2.2 | BOH
14 | PROJECT.3.2.3.4.2.2.1 | BP1-CPF RM-101 & 102
14 | PROJECT.3.2.3.4.2.2.2 | BP1-CPF RM-172 & 228
14 | PROJECT.3.2.3.4.2.2.3 | BP1-CPF RM-170 & 169
14 | PROJECT.3.2.3.4.2.2.4 | BP1-CPF RM-134, 144 & 137
14 | PROJECT.3.2.3.4.2.2.5 | ELECTRICAL ROOM-BP1 106/UTT RM/BMS RM/LED RM/STAIRCASE & LIFT ROOM BP1
14 | PROJECT.3.2.3.4.2.2.6 | ELECTRICAL ROOM-BP1 174/UTT RM/BMS RM/LED RM/STAIRCASE & LIFT ROOM BP1
14 | PROJECT.3.2.3.4.2.2.7 | ELECTRICAL ROOM-BP1 213/UTT RM/BMS RM/LED RM/STAIRCASE & LIFT ROOM BP1
14 | PROJECT.3.2.3.4.2.2.8 | ELECTRICAL ROOM-BP1 216/UTT RM/BMS RM/LED RM/STAIRCASE & LIFT ROOM BP1
14 | PROJECT.3.2.3.4.2.2.9 | ELECTRICAL ROOM-BP1 141/UTT RM/BMS RM/BATRM/LOBBY/STAIRCASE/LIFT ROOM BP1
14 | PROJECT.3.2.3.4.2.2.10 | UTT RM BP 221, 203/BMS RM/LOBBY/STAIRCASE/LIFT ROOM BP1 221, 203
14 | PROJECT.3.2.3.4.2.2.11 | BP1-WATER FEATURE PUMP ROOM-229
14 | PROJECT.3.2.3.4.2.2.12 | BP1-WATER FEATURE PUMP ROOM-230
12 | PROJECT.3.2.3.4.2.3 | CARPARK
12 | PROJECT.3.2.3.4.2.11 | STAIRCASES BP-GF
14 | PROJECT.3.2.3.4.2.11.1 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.4.2.11.4 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.4.3 | SECTION C
12 | PROJECT.3.2.3.4.3.5 | GENERAL
12 | PROJECT.3.2.3.4.3.1 | FOH: LOBBY 03 Zone 09&13
12 | PROJECT.3.2.3.4.3.2 | BOH
14 | PROJECT.3.2.3.4.3.2.1 | BP1-CPF RM-152 & 146
14 | PROJECT.3.2.3.4.3.2.2 | ELECTRICAL ROOM-BP1 233/UTT RM/BMS RM/LED RM/ STAIRCASE & LIFT ROOM BP1
14 | PROJECT.3.2.3.4.3.2.3 | BP1-POP ROOM-163A
12 | PROJECT.3.2.3.4.3.3 | CARPARK AND RAMPS
12 | PROJECT.3.2.3.4.3.6 | STAIRCASES BP1-GF
14 | PROJECT.3.2.3.4.3.6.1 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.4.3.6.4 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.4.4 | SOFFITT INSULATION WORKS-BP1
10 | PROJECT.3.2.3.4.5 | EGRESS CORRIDORS
12 | PROJECT.3.2.3.4.5.1 | ZONE 01 (CORRIDOR 115)
12 | PROJECT.3.2.3.4.5.3 | ZONE 03 (CORRIDOR 119)
8 | PROJECT.3.2.3.5 | GF
10 | PROJECT.3.2.3.5.2 | WEST SIDE
12 | PROJECT.3.2.3.5.2.5 | GENERAL
12 | PROJECT.3.2.3.5.2.1 | BOH
14 | PROJECT.3.2.3.5.2.1.1 | GL-Electrical Room-104/UTT RM/BMS RM/BATRM
14 | PROJECT.3.2.3.5.2.1.2 | GL-Electrical Room-206/UTT RM/BMS RM/BATRM
14 | PROJECT.3.2.3.5.2.1.3 | GL-Electrical Room-711/UTT RM/BMS RM/BATRM
14 | PROJECT.3.2.3.5.2.1.4 | GL-Electrical Room-305/UTT RM/BMS RM/BATRM
14 | PROJECT.3.2.3.5.2.1.5 | GL-UTT RM-706/BMS RM/Lift room (BESIDE LIFT LOBBY)
12 | PROJECT.3.2.3.5.2.3 | WET AREAS
14 | PROJECT.3.2.3.5.2.3.3 | T-Z01
14 | PROJECT.3.2.3.5.2.3.4 | T-Z03
14 | PROJECT.3.2.3.5.2.3.2 | T-Z05N
14 | PROJECT.3.2.3.5.2.3.1 | T-Z05S
12 | PROJECT.3.2.3.5.2.6 | STAIRCASES GF-L1 SECTION A
14 | PROJECT.3.2.3.5.2.6.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.5.2.6.2 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.5.1 | EAST SIDE
12 | PROJECT.3.2.3.5.1.5 | GENERAL
12 | PROJECT.3.2.3.5.1.2 | BOH
14 | PROJECT.3.2.3.5.1.2.1 | GL-ELECTRICAL ROOM-606/UTT RM/BMS RM/BATRM
14 | PROJECT.3.2.3.5.1.2.2 | GL-ELECTRICAL ROOM-504/UTT RM/BMS RM/BATRM
14 | PROJECT.3.2.3.5.1.2.3 | GL-ELECTRICAL ROOM-407/UTT RM/BMS RM/BATRM
14 | PROJECT.3.2.3.5.1.2.4 | GL-ELECTRICAL ROOM-804/UTT RM/BMS RM/BATRM
14 | PROJECT.3.2.3.5.1.2.5 | GL-UTT RM-814/BMS RM/Lift room (BESIDE LIFT LOBBY)
12 | PROJECT.3.2.3.5.1.3 | WET AREAS
14 | PROJECT.3.2.3.5.1.3.2 | TZ08N
14 | PROJECT.3.2.3.5.1.3.1 | TZ08S
14 | PROJECT.3.2.3.5.1.3.4 | TZ09
14 | PROJECT.3.2.3.5.1.3.3 | TZ14
12 | PROJECT.3.2.3.5.1.4 | STAIRCASES GF-L1 SECTION B
14 | PROJECT.3.2.3.5.1.4.1 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.5.1.4.4 | ACCESS STAIRCASES
12 | PROJECT.3.2.3.5.1.1 | STAIRCASES GF-L1 SECTION C
14 | PROJECT.3.2.3.5.1.1.1 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.5.1.1.4 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.5.3 | MALL CONCOURSE INCLUDING FOH CORRIDORS
12 | PROJECT.3.2.3.5.3.8 | GENERAL
12 | PROJECT.3.2.3.5.3.1 | EAST MALL
12 | PROJECT.3.2.3.5.3.2 | DYNAMIC EAST
12 | PROJECT.3.2.3.5.3.3 | URBAN EAST
12 | PROJECT.3.2.3.5.3.4 | MANGROVE AND ENTRANCE LOBBY
12 | PROJECT.3.2.3.5.3.5 | DYNAMIC WEST
12 | PROJECT.3.2.3.5.3.6 | URBAN WEST
12 | PROJECT.3.2.3.5.3.7 | WEST MALL
10 | PROJECT.3.2.3.5.4 | EGRESS CORRIDORS
12 | PROJECT.3.2.3.5.4.2 | ZONE 02 (CORRIDOR 214)
12 | PROJECT.3.2.3.5.4.4 | ZONE 04 (CORRIDORS 101, 109)
12 | PROJECT.3.2.3.5.4.5 | ZONE 05 (CORRIDOR 708)
12 | PROJECT.3.2.3.5.4.6 | ZONE 06 (CORRIDORS 301, 303)
12 | PROJECT.3.2.3.5.4.7 | ZONE 07 (CORRIDORS 601, 602)
12 | PROJECT.3.2.3.5.4.8 | ZONE 08 (CORRIDORS 816, 817)
12 | PROJECT.3.2.3.5.4.10 | ZONE 10 (CORRIDOR 801)
12 | PROJECT.3.2.3.5.4.11 | ZONE 11 (CORRIDORS 401, 403)
8 | PROJECT.3.2.3.6 | L1
10 | PROJECT.3.2.3.6.2 | WEST SIDE
12 | PROJECT.3.2.3.6.2.6 | GENERAL
12 | PROJECT.3.2.3.6.2.2 | BOH
14 | PROJECT.3.2.3.6.2.2.1 | L1-ELECTRICAL ROOM-104/UTT RM/BMS RM/LEDRM
14 | PROJECT.3.2.3.6.2.2.2 | L1-ELECTRICAL ROOM-205/UTT RM/BMS RM/LEDRM
14 | PROJECT.3.2.3.6.2.2.3 | L1-ELECTRICAL ROOM-305/UTT RM/BMS RM/LEDRM
14 | PROJECT.3.2.3.6.2.2.4 | L1-ELECTRICAL ROOM-710/UTT RM/BMS RM/LEDRM
14 | PROJECT.3.2.3.6.2.2.5 | L1-UTT RM-705/BMS RM/LIFT ROOM (BESIDE LIFT LOBBY)
12 | PROJECT.3.2.3.6.2.3 | WET AREAS
14 | PROJECT.3.2.3.6.2.3.3 | T-Z01
14 | PROJECT.3.2.3.6.2.3.4 | T-Z03
14 | PROJECT.3.2.3.6.2.3.2 | TZ05N
14 | PROJECT.3.2.3.6.2.3.1 | TZ05S
12 | PROJECT.3.2.3.6.2.5 | STAIRCASES L1-L2 SECTION A
14 | PROJECT.3.2.3.6.2.5.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.6.2.5.2 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.6.1 | EAST SIDE
12 | PROJECT.3.2.3.6.1.6 | GENERAL
12 | PROJECT.3.2.3.6.1.2 | BOH
14 | PROJECT.3.2.3.6.1.2.1 | L1-ELECTRICAL ROOM-604/UTT RM/BMS RM/LEDRM
14 | PROJECT.3.2.3.6.1.2.2 | L1-ELECTRICAL ROOM-803/UTT RM/BMS RM/LEDRM
14 | PROJECT.3.2.3.6.1.2.3 | L1-ELECTRICAL ROOM-405/UTT RM/BMS RM/LEDRM
14 | PROJECT.3.2.3.6.1.2.4 | L1-ELECTRICAL ROOM-502/UTT RM/BMS RM/LEDRM
14 | PROJECT.3.2.3.6.1.2.5 | L1-UTT RM-813/BMS RM/LIFT ROOM (BESIDE LIFT LOBBY)
12 | PROJECT.3.2.3.6.1.3 | WET AREAS
14 | PROJECT.3.2.3.6.1.3.4 | T-Z08N
14 | PROJECT.3.2.3.6.1.3.2 | T-Z08S
14 | PROJECT.3.2.3.6.1.3.3 | T-Z09
14 | PROJECT.3.2.3.6.1.3.1 | T-Z14 (FOOD COURT)
12 | PROJECT.3.2.3.6.1.4 | FOOD COURT
12 | PROJECT.3.2.3.6.1.5 | STAIRCASES L1-L2/PP1 SECTION B
14 | PROJECT.3.2.3.6.1.5.5 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.6.1.5.4 | ACCESS STAIRCASES
12 | PROJECT.3.2.3.6.1.1 | STAIRCASES L1-L2/PP1 SECTION C
14 | PROJECT.3.2.3.6.1.1.5 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.2.3.6.1.1.4 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.6.3 | THE MALL CONCOURSE INCLUDING FOH CORRIDORS
12 | PROJECT.3.2.3.6.3.8 | GENERAL
12 | PROJECT.3.2.3.6.3.1 | EAST MALL
12 | PROJECT.3.2.3.6.3.2 | DYNAMIC EAST
12 | PROJECT.3.2.3.6.3.3 | URBAN EAST
12 | PROJECT.3.2.3.6.3.4 | MANGROVE
12 | PROJECT.3.2.3.6.3.5 | DYNAMIC WEST
12 | PROJECT.3.2.3.6.3.6 | URBAN WEST
12 | PROJECT.3.2.3.6.3.7 | WEST MALL
10 | PROJECT.3.2.3.6.4 | SOFFITT INSULATION WORKS-L1
10 | PROJECT.3.2.3.6.5 | EGRESS CORRIDORS
12 | PROJECT.3.2.3.6.5.2 | ZONE 02 (CORRIDO 209)
12 | PROJECT.3.2.3.6.5.4 | ZONE 04 (CORRIDOR 101)
12 | PROJECT.3.2.3.6.5.5 | ZONE 05 (CORRIDORS 707, 708)
12 | PROJECT.3.2.3.6.5.6 | ZONE 06 (CORRIDORS 301, 303)
12 | PROJECT.3.2.3.6.5.7 | ZONE 07 (CORRIDORS 601, 602)
12 | PROJECT.3.2.3.6.5.8 | ZONE 08 (CORRIDORS 801, 807)
12 | PROJECT.3.2.3.6.5.11 | ZONE 11 (CORRIDORS 401, 402)
12 | PROJECT.3.2.3.6.5.14 | ZONE 14 (CORRIDORS 511)
8 | PROJECT.3.2.3.7 | L2/PP1
10 | PROJECT.3.2.3.7.10 | GENERAL
10 | PROJECT.3.2.3.7.1 | FOH: LOBBY 03 Zone 10&13
10 | PROJECT.3.2.3.7.2 | BOH
12 | PROJECT.3.2.3.7.2.1 | L2-PP-1-ELECTRICAL ROOM-104/UTT RM/BMS RM/LEDRM
12 | PROJECT.3.2.3.7.2.2 | L2-PP-1-ELECTRICAL ROOM-205/UTT RM/BMS RM/LEDRM
12 | PROJECT.3.2.3.7.2.3 | L2-PP-1-ELECTRICAL ROOM-305/UTT RM/BMS RM/LEDRM
12 | PROJECT.3.2.3.7.2.4 | L2-PP-1-ELECTRICAL ROOM-604/UTT RM/BMS RM/LEDRM
12 | PROJECT.3.2.3.7.2.5 | L2-PP-1-ELECTRICAL ROOM-712/UTT RM/BMS RM/LEDRM
12 | PROJECT.3.2.3.7.2.6 | L2-PP-1-ELECTRICAL ROOM-904/UTT RM/BMS RM/LEDRM
12 | PROJECT.3.2.3.7.2.7 | L2-PP-1-ELECTRICAL ROOM-917/UTT RM/BMS RM/LEDRM
12 | PROJECT.3.2.3.7.2.8 | L2-PP-1-UTT RM 705/ BMS RM/LOBBY/STAIRCASE/LIF ROOM
12 | PROJECT.3.2.3.7.2.9 | L2-PP-1-UTT RM 816, ELECTRICAL ROOM-802/BMS RM/LOBBY/STAIRCASE/LIFT ROOM
12 | PROJECT.3.2.3.7.2.10 | L2-PP-1-PLANT ROOM 907,913 & 919
10 | PROJECT.3.2.3.7.3 | PRAYER ROOM
10 | PROJECT.3.2.3.7.4 | WET AREAS
12 | PROJECT.3.2.3.7.4.2 | T-Z01
12 | PROJECT.3.2.3.7.4.4 | T-Z03 (FOOD COURT)
12 | PROJECT.3.2.3.7.4.1 | T-08N
12 | PROJECT.3.2.3.7.4.3 | T-08S
10 | PROJECT.3.2.3.7.5 | FOOD COURT
10 | PROJECT.3.2.3.7.6 | OFFICES
10 | PROJECT.3.2.3.7.13 | CINEMA
10 | PROJECT.3.2.3.7.7 | THE MALL CONCOURSE INCLUDING FOH CORRIDORS
12 | PROJECT.3.2.3.7.7.5 | GENERAL
12 | PROJECT.3.2.3.7.7.1 | DYNAMIC
12 | PROJECT.3.2.3.7.7.2 | URBAN
12 | PROJECT.3.2.3.7.7.3 | MANGROVE
14 | PROJECT.3.2.3.7.7.3.8 | FLOOR FINISHES
14 | PROJECT.3.2.3.7.7.3.9 | WALL FINISHES
14 | PROJECT.3.2.3.7.7.3.7 | CEILING FINISHES
16 | PROJECT.3.2.3.7.7.3.7.1 | CEILING FINISHES - ABOVE ENTRANCE
16 | PROJECT.3.2.3.7.7.3.7.2 | CEILING FINISHES - BW SK-2/11
16 | PROJECT.3.2.3.7.7.3.7.3 | CEILING FINISHES -SK- 3c
16 | PROJECT.3.2.3.7.7.3.7.6 | CEILING FINISHES -SK- 3b
16 | PROJECT.3.2.3.7.7.3.7.4 | CEILING FINISHES -SK- 3a
16 | PROJECT.3.2.3.7.7.3.7.5 | CEILING FINISHES -Bw SK 3/5
12 | PROJECT.3.2.3.7.7.4 | WEST MALL
10 | PROJECT.3.2.3.7.8 | CARPARK AND RAMPS
10 | PROJECT.3.2.3.7.12 | STAIRCASES L2/PP1 TO L3/PP2 SECTION A
12 | PROJECT.3.2.3.7.12.9 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.2.3.7.12.4 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.7.9 | STAIRCASES L2/PP1 TO L3/PP2 SECTION B
12 | PROJECT.3.2.3.7.9.9 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.2.3.7.9.4 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.7.11 | STAIRCASES L2/PP1 TO L3/PP2 SECTION C
12 | PROJECT.3.2.3.7.11.9 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.2.3.7.11.4 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.7.14 | EGRESS CORRIDORS
12 | PROJECT.3.2.3.7.14.3 | ZONE 03 (CORRIDOR 822)
12 | PROJECT.3.2.3.7.14.4 | ZONE 04 (CORRIDORS 101, 107)
12 | PROJECT.3.2.3.7.14.11 | ZONE 04 (CORRIDOR 701)
12 | PROJECT.3.2.3.7.14.5 | ZONE 05 (CORRIDORS 707, 710)
12 | PROJECT.3.2.3.7.14.6 | ZONE 06 (CORRIDORS 301, 303)
12 | PROJECT.3.2.3.7.14.7 | ZONE 07 (CORRIDORS 602)
12 | PROJECT.3.2.3.7.14.8 | ZONE 08 (CORRIDORS 806, 807)
8 | PROJECT.3.2.3.8 | L3/PP2
10 | PROJECT.3.2.3.8.7 | GENERAL
10 | PROJECT.3.2.3.8.8 | FOH LOBBIES
12 | PROJECT.3.2.3.8.8.11 | LOBBY 02 Zone 07&09
12 | PROJECT.3.2.3.8.8.1 | LOBBY 03 Zone 10&13
12 | PROJECT.3.2.3.8.8.2 | LOBBY 04 Zone 11
10 | PROJECT.3.2.3.8.2 | PRAYER ROOM
10 | PROJECT.3.2.3.8.3 | WET AREA BESIDE PRAYER ROOM
10 | PROJECT.3.2.3.8.4 | BOH
12 | PROJECT.3.2.3.8.4.1 | L-3 PP-02-ELECTRICAL ROOM-904,913/UTT RM/BMS RM/LED RM
12 | PROJECT.3.2.3.8.4.2 | L-3 PP-02-ELECTRICAL ROOM-802/UTT RM/BMS RM/LED RM
12 | PROJECT.3.2.3.8.4.3 | L3-PP-2-PLANT ROOMS-914 & 907
12 | PROJECT.3.2.3.8.4.4 | L-3 PP-02-UTT RM-705/BMS RM/LOBBY/STAIRCASE/LIFT ROOM L3 706
12 | PROJECT.3.2.3.8.4.5 | L-3 PP-02-UTT RM-814/BMS RM/LOBBY/STAIRCASE/LIFT ROOM L3 811
10 | PROJECT.3.2.3.8.5 | CAR PARK AND RAMPS
10 | PROJECT.3.2.3.8.9 | STAIRCASES PP3 TO PP4 SECTION A
12 | PROJECT.3.2.3.8.9.6 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.2.3.8.9.1 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.8.6 | STAIRCASES PP3 TO PP4 SECTION B
12 | PROJECT.3.2.3.8.6.6 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.2.3.8.6.1 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.8.1 | STAIRCASES PP3 TO PP4 SECTION C
12 | PROJECT.3.2.3.8.1.6 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.2.3.8.1.1 | ACCESS STAIRCASES
8 | PROJECT.3.2.3.9 | ROOF/PP3
10 | PROJECT.3.2.3.9.6 | GENERAL
10 | PROJECT.3.2.3.9.7 | FOH LOBBIES
12 | PROJECT.3.2.3.9.7.11 | LOBBY 02 Zone 07&09
12 | PROJECT.3.2.3.9.7.1 | LOBBY 03 Zone 10&13
12 | PROJECT.3.2.3.9.7.2 | LOBBY 04 Zone 11
10 | PROJECT.3.2.3.9.2 | BOH
12 | PROJECT.3.2.3.9.2.1 | PP-03-PLANT ROOM-124 (B20) Zone 06
12 | PROJECT.3.2.3.9.2.15 | PP-03-PLANT ROOM-126 (B21) Zone 11
12 | PROJECT.3.2.3.9.2.2 | PP-03-PLANT ROOM-121 (A17) Zone 06
12 | PROJECT.3.2.3.9.2.18 | PP-03-MCC ROOM- ATTACHED TO 121 (A17B) Zone 06
12 | PROJECT.3.2.3.9.2.3 | PP-03-PLANT ROOM-118 (A9) Zone 03
12 | PROJECT.3.2.3.9.2.16 | PP-03-PLANT ROOM-136 (A6) Zone 02
12 | PROJECT.3.2.3.9.2.17 | PP-03-MCC ROOM- ATTACHED TO 136 (A6) Zone 02
12 | PROJECT.3.2.3.9.2.4 | PP-03-PLANT ROOM-137 (A13 - Beside Snow Park) Zone 02
12 | PROJECT.3.2.3.9.2.5 | PP-03-PLANT ROOM-140 (B14 beside Snow Park - stage 5) Zone 06
12 | PROJECT.3.2.3.9.2.21 | PP-03-PLANT ROOM-142 (B15 beside Snow Park - stage 5) Zone 06
12 | PROJECT.3.2.3.9.2.6 | PP-03-PLANT ROOM-107 (A12) Zone 01 & Zone 04
12 | PROJECT.3.2.3.9.2.25 | PP-03-MCC ROOM- ATTACHED TO 107 (A12) Zone 04
12 | PROJECT.3.2.3.9.2.34 | PP-03-MCC ROOM- ATTACHED TO 120 (A9) Zone 03
12 | PROJECT.3.2.3.9.2.22 | PP-03-PLANT ROOM-108 (A12) Zone 01
12 | PROJECT.3.2.3.9.2.7 | PP-03-PLANT ROOM-106 (B01) Zone 04
12 | PROJECT.3.2.3.9.2.23 | PP-03-PLANT ROOM-109 (B01) Zone 04
12 | PROJECT.3.2.3.9.2.24 | PP-03-PLANT ROOM- 919 (B02) Zone 04
12 | PROJECT.3.2.3.9.2.8 | PP-03-PLANT ROOM-101 (B3) Zone 07
12 | PROJECT.3.2.3.9.2.27 | PP-03-PLANT ROOM-102 (B3) Zone 07
12 | PROJECT.3.2.3.9.2.28 | PP-03-PLANT ROOM-104 (B3) Zone 07
12 | PROJECT.3.2.3.9.2.29 | PP-03-MCC ROOM- ATTACHED TO 101 (B3) Zone 07
12 | PROJECT.3.2.3.9.2.30 | PP-03-MCC ROOM- ATTACHED TO 102 (B3) Zone 07
12 | PROJECT.3.2.3.9.2.31 | PP-03-MCC ROOM- North east of 101 (B3) Zone 07
12 | PROJECT.3.2.3.9.2.9 | PP-03-PLANT ROOM-139 (B14 beside Snow Park - stage 4) Zone 06
12 | PROJECT.3.2.3.9.2.26 | PP-03-PLANT ROOM-152 (A16 beside Snow Park - stage 1) Zone 03 & Zone 06
12 | PROJECT.3.2.3.9.2.10 | PP-03-PLANT ROOM-119 (A9) Zone 03
12 | PROJECT.3.2.3.9.2.19 | PP-03-PLANT ROOM-120 (A9) Zone 03
12 | PROJECT.3.2.3.9.2.20 | PP-03-PLANT ROOM-129 (B11) Zone 08
12 | PROJECT.3.2.3.9.2.32 | PP-03-PLANT ROOM-134 (B11) Zone 08
12 | PROJECT.3.2.3.9.2.35 | PP-03-PLANT ROOM-131 (B11) Zone 08
12 | PROJECT.3.2.3.9.2.11 | PP-03-PLANT ROOM-128 (Zones 8, 11)
12 | PROJECT.3.2.3.9.2.12 | PP-03-ELECTRICAL ROOM-904/UTT RM/BMS RM/LED RM (ZONE 11)
12 | PROJECT.3.2.3.9.2.13 | PP-03-UTT RM-914 & 925 UTT RM/ BMS RM/LOBBY/STAIRCASE/LIFT ROOM (Zones 10 & 13)
12 | PROJECT.3.2.3.9.2.14 | PP-03-PUMP ROOM-143 (Zone 03)
12 | PROJECT.3.2.3.9.2.33 | PP-03-WATER TANKS-144 (Zone 03), 145 (Zone 06)
10 | PROJECT.3.2.3.9.3 | CARPARK AND RAMPS
10 | PROJECT.3.2.3.9.4 | STAIRCASES PP3 TO PP4 SECTION B
12 | PROJECT.3.2.3.9.4.4 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.2.3.9.4.1 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.9.1 | STAIRCASES PP3 TO PP4 SECTION C
12 | PROJECT.3.2.3.9.1.4 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.2.3.9.1.1 | ACCESS STAIRCASES
10 | PROJECT.3.2.3.9.5 | ROOF
8 | PROJECT.3.2.3.10 | PP4
10 | PROJECT.3.2.3.10.4 | GENERAL
10 | PROJECT.3.2.3.10.5 | FOH LOBBIES
12 | PROJECT.3.2.3.10.5.2 | LOBBY 02 Zone 07&09
12 | PROJECT.3.2.3.10.5.3 | FOH: LOBBY 03 Zone 10&13
12 | PROJECT.3.2.3.10.5.1 | LOBBY 04 Zone 11
10 | PROJECT.3.2.3.10.2 | BOH
12 | PROJECT.3.2.3.10.2.2 | PLANT ROOMS-934, 936, 937, 938, 939, 940, 941, 942, 947 (CINEMA & FEC)
14 | PROJECT.3.2.3.10.2.2.2 | PLANT ROOMS-934 (CINEMA & FEC) (Zone 1)
14 | PROJECT.3.2.3.10.2.2.1 | PLANT ROOMS-936 (CINEMA & FEC) (Zone 1)
14 | PROJECT.3.2.3.10.2.2.3 | PLANT ROOMS-937 (CINEMA & FEC) (Zone 1)
14 | PROJECT.3.2.3.10.2.2.9 | PLANT ROOMS-947 (CINEMA & FEC) (Zone 1)
14 | PROJECT.3.2.3.10.2.2.4 | PLANT ROOMS-938 (CINEMA & FEC) (Zone 1)
14 | PROJECT.3.2.3.10.2.2.5 | PLANT ROOMS-939 (CINEMA & FEC) (Zone 1)
14 | PROJECT.3.2.3.10.2.2.6 | PLANT ROOMS-940 (CINEMA & FEC) (Zone 2)
14 | PROJECT.3.2.3.10.2.2.7 | PLANT ROOMS-941 (CINEMA & FEC) (Zone 2)
14 | PROJECT.3.2.3.10.2.2.8 | PLANT ROOMS-942 (CINEMA & FEC) (Zone 2)
12 | PROJECT.3.2.3.10.2.3 | PP-04-PLANT ROOM-922 (B5) (Zone 9)
12 | PROJECT.3.2.3.10.2.5 | PP-04-PLANT ROOM-918 (B18) (Zone 10)
12 | PROJECT.3.2.3.10.2.6 | PP-04-PLANT ROOM-952, 953 (B23) (Zone 11)
12 | PROJECT.3.2.3.10.2.1 | PP-04-PLANT ROOM-932 (B09 Snow Center) (Zone 5)
12 | PROJECT.3.2.3.10.2.7 | PP-04-PLANT ROOM-946 (B08 Snow Center) (Zone 5)
12 | PROJECT.3.2.3.10.2.4 | PLANT ROOMS-SECTION C
14 | PROJECT.3.2.3.10.2.4.1 | PP-04-PLANT ROOM-921 (C2 & C3) (Zone 12)
14 | PROJECT.3.2.3.10.2.4.2 | PP-04-PLANT ROOM-919 (C4) (Zone 9 & 12)
14 | PROJECT.3.2.3.10.2.4.5 | PP-04-PLANT ROOM-949, 950, 912, 914 (C7) (Zones 10 & 13)
14 | PROJECT.3.2.3.10.2.4.3 | PP-04-PLANT ROOM-911 (C6 & C8) (Zone 13)
14 | PROJECT.3.2.3.10.2.4.4 | PP-04-PLANT ROOM-907 (C11) (Zone 14)
14 | PROJECT.3.2.3.10.2.4.6 | PP-04-PLANT ROOM-908, 951 (C9) (Zone 14)
14 | PROJECT.3.2.3.10.2.4.7 | PP-04-PLANT ROOM-948 (TRF) (Zone 9)
14 | PROJECT.3.2.3.10.2.4.8 | PP-04-PLANT ROOM-909 (TRF) (Zone 11)
10 | PROJECT.3.2.3.10.3 | CAR PARK
8 | PROJECT.3.2.3.11 | MEP SHAFTS
10 | PROJECT.3.2.3.11.1 | ZONE 01
10 | PROJECT.3.2.3.11.2 | ZONE 02
10 | PROJECT.3.2.3.11.3 | ZONE 03
10 | PROJECT.3.2.3.11.4 | ZONE 04
10 | PROJECT.3.2.3.11.5 | ZONE 05
10 | PROJECT.3.2.3.11.6 | ZONE 06
10 | PROJECT.3.2.3.11.7 | ZONE 07
10 | PROJECT.3.2.3.11.8 | ZONE 08
10 | PROJECT.3.2.3.11.9 | ZONE 09
10 | PROJECT.3.2.3.11.10 | ZONE 10
10 | PROJECT.3.2.3.11.11 | ZONE 11
10 | PROJECT.3.2.3.11.12 | ZONE 12
10 | PROJECT.3.2.3.11.13 | ZONE 13
10 | PROJECT.3.2.3.11.14 | ZONE 14
8 | PROJECT.3.2.3.12 | FACADE
10 | PROJECT.3.2.3.12.1 | ENGINEERING
12 | PROJECT.3.2.3.12.1.1 | ENGINEERING BY FACADE PARTS
14 | PROJECT.3.2.3.12.1.1.1 | WEST
16 | PROJECT.3.2.3.12.1.1.1.1 | WEST SOUTH
18 | PROJECT.3.2.3.12.1.1.1.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.1.1.2 | REVIEW AND APPROVAL
16 | PROJECT.3.2.3.12.1.1.1.3 | WEST NORTH
18 | PROJECT.3.2.3.12.1.1.1.3.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.1.3.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.1.2 | EAST
16 | PROJECT.3.2.3.12.1.1.2.1 | EAST SOUTH
18 | PROJECT.3.2.3.12.1.1.2.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.2.1.2 | REVIEW AND APPROVAL
16 | PROJECT.3.2.3.12.1.1.2.2 | EAST NORTH
18 | PROJECT.3.2.3.12.1.1.2.2.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.2.2.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.1.3 | NORTH
16 | PROJECT.3.2.3.12.1.1.3.1 | NORTH WEST
18 | PROJECT.3.2.3.12.1.1.3.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.3.1.2 | REVIEW AND APPROVAL
16 | PROJECT.3.2.3.12.1.1.3.2 | NORTH CENTER
18 | PROJECT.3.2.3.12.1.1.3.2.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.3.2.2 | REVIEW AND APPROVAL
16 | PROJECT.3.2.3.12.1.1.3.3 | NORTH EAST
18 | PROJECT.3.2.3.12.1.1.3.3.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.3.3.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.1.4 | SOUTH
16 | PROJECT.3.2.3.12.1.1.4.1 | SOUTH WEST
18 | PROJECT.3.2.3.12.1.1.4.1.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.4.1.2 | REVIEW AND APPROVAL
16 | PROJECT.3.2.3.12.1.1.4.3 | SOUTH CENTER
18 | PROJECT.3.2.3.12.1.1.4.3.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.4.3.2 | REVIEW AND APPROVAL
16 | PROJECT.3.2.3.12.1.1.4.2 | SOUTH EAST
18 | PROJECT.3.2.3.12.1.1.4.2.1 | PREPARATION AND SUBMISSION
18 | PROJECT.3.2.3.12.1.1.4.2.2 | REVIEW AND APPROVAL
12 | PROJECT.3.2.3.12.1.2 | ENGINEERING BY ZONES
14 | PROJECT.3.2.3.12.1.2.2 | ZONE 01
16 | PROJECT.3.2.3.12.1.2.2.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.2.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.1 | ZONE 02
16 | PROJECT.3.2.3.12.1.2.1.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.1.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.3 | ZONE 03
16 | PROJECT.3.2.3.12.1.2.3.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.3.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.4 | ZONE 04
16 | PROJECT.3.2.3.12.1.2.4.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.4.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.6 | ZONE 06
16 | PROJECT.3.2.3.12.1.2.6.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.6.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.7 | ZONE 07
16 | PROJECT.3.2.3.12.1.2.7.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.7.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.9 | ZONE 09
16 | PROJECT.3.2.3.12.1.2.9.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.9.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.11 | ZONE 11
16 | PROJECT.3.2.3.12.1.2.11.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.11.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.12 | ZONE 12
16 | PROJECT.3.2.3.12.1.2.12.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.12.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.13 | ZONE 13
16 | PROJECT.3.2.3.12.1.2.13.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.13.2 | REVIEW AND APPROVAL
14 | PROJECT.3.2.3.12.1.2.14 | ZONE 14
16 | PROJECT.3.2.3.12.1.2.14.1 | PREPARATION AND SUBMISSION
16 | PROJECT.3.2.3.12.1.2.14.2 | REVIEW AND APPROVAL
12 | PROJECT.3.2.3.12.1.3 | ENGINEERING OF ALUMINUM CLADDING
14 | PROJECT.3.2.3.12.1.3.1 | PREPARATION AND SUBMISSION
14 | PROJECT.3.2.3.12.1.3.2 | REVIEW AND APPROVAL
10 | PROJECT.3.2.3.12.2 | FABRICATION AND DELIVERY
12 | PROJECT.3.2.3.12.2.1 | STEEL PARAPETS
12 | PROJECT.3.2.3.12.2.2 | CEMENT BOARDS
12 | PROJECT.3.2.3.12.2.3 | LOUVERS
12 | PROJECT.3.2.3.12.2.4 | CURTAIN WALLS
12 | PROJECT.3.2.3.12.2.5 | STONE
12 | PROJECT.3.2.3.12.2.6 | CLADDING AND FALL ARREST SYSTEM & ABSEILING SYSTEM
14 | PROJECT.3.2.3.12.2.6.1 | FROM C08 TO A10 (NORTH WEST CORNER) Z01
14 | PROJECT.3.2.3.12.2.6.2 | FROM A18 to AB07 (NORTH CENTER WEST) Z04
14 | PROJECT.3.2.3.12.2.6.3 | FROM AB09 TO B06 (NORTH CENTER EAST) Z07
14 | PROJECT.3.2.3.12.2.6.5 | FROM A01 TO A10 (SOUTH WEST) Z03
10 | PROJECT.3.2.3.12.3 | INSTALLATION
12 | PROJECT.3.2.3.12.3.3 | WEST ELEVATION
14 | PROJECT.3.2.3.12.3.3.1 | WEST SOUTH (Grid C24-C42)
16 | PROJECT.3.2.3.12.3.3.1.1 | PART 1 (Non-Parapet Area)
16 | PROJECT.3.2.3.12.3.3.1.2 | PART 2 (Parapet Area)
18 | PROJECT.3.2.3.12.3.3.1.2.26 | FROM C42 TO C36 (WEST SOUTH) Zone 03
18 | PROJECT.3.2.3.12.3.3.1.2.27 | FROM C36 TO C27 (WEST SOUTH) Zone 03
18 | PROJECT.3.2.3.12.3.3.1.2.28 | FROM C27 TO C24 (WEST SOUTH) Zone 02
14 | PROJECT.3.2.3.12.3.3.3 | WEST NORTH (Grid C05-C22)
16 | PROJECT.3.2.3.12.3.3.3.1 | PART 3
16 | PROJECT.3.2.3.12.3.3.3.2 | PART 4
18 | PROJECT.3.2.3.12.3.3.3.2.29 | FROM C24 TO C23 (WEST NORTH) Zone 02
18 | PROJECT.3.2.3.12.3.3.3.2.30 | FROM C23 TO C19 (WEST NORTH) Zone 02
18 | PROJECT.3.2.3.12.3.3.3.2.31 | FROM C19 TO C8 (WEST NORTH) Zone 01
16 | PROJECT.3.2.3.12.3.3.3.3 | PART 5
18 | PROJECT.3.2.3.12.3.3.3.3.4 | FROM C08 TO C05 (WEST NORTH) Zone 01
12 | PROJECT.3.2.3.12.3.4 | EAST ELEVATION
14 | PROJECT.3.2.3.12.3.4.1 | EAST NORTH (Grid B20-B28, C04-C22)
16 | PROJECT.3.2.3.12.3.4.1.1 | PART 1
16 | PROJECT.3.2.3.12.3.4.1.2 | PART 2
18 | PROJECT.3.2.3.12.3.4.1.2.12 | FROM B19 TO C5 (EAST NORTH CORNER) Zone 12
18 | PROJECT.3.2.3.12.3.4.1.2.13 | FROM C05 TO C16 (EAST NORTH) Zone 12
18 | PROJECT.3.2.3.12.3.4.1.2.14 | FROM C16 TO C22 (EAST NORTH) Zone 13
16 | PROJECT.3.2.3.12.3.4.1.3 | FT-09 LOUVERS
14 | PROJECT.3.2.3.12.3.4.2 | EAST SOUTH (Grid C22-C40)
16 | PROJECT.3.2.3.12.3.4.2.1 | PART 1
16 | PROJECT.3.2.3.12.3.4.2.2 | PART 2
18 | PROJECT.3.2.3.12.3.4.2.2.17 | FROM C33 TO C40 (EAST SOUTH) Zone 14
18 | PROJECT.3.2.3.12.3.4.2.2.16 | FROM C28 TO C33 (EAST SOUTH) Zone 14
18 | PROJECT.3.2.3.12.3.4.2.2.15 | FROM C27 TO C28 (EAST SOUTH) Zone 14
18 | PROJECT.3.2.3.12.3.4.2.2.14 | FROM C22 TO C27 (EAST SOUTH) Zone 13
12 | PROJECT.3.2.3.12.3.5 | SOUTH ELEVATION
14 | PROJECT.3.2.3.12.3.5.1 | SOUTH EAST (Grid B05-B24)
16 | PROJECT.3.2.3.12.3.5.1.1 | PART 1
16 | PROJECT.3.2.3.12.3.5.1.2 | PART 2
18 | PROJECT.3.2.3.12.3.5.1.2.20 | FROM B10 TO B5 (SOUTH EAST) Zone 11
18 | PROJECT.3.2.3.12.3.5.1.2.19 | FROM B12 TO B10 (SOUTH EAST) Zone 11
18 | PROJECT.3.2.3.12.3.5.1.2.18 | FROM B22 TO B12 (SOUTH EAST) Zone 14
18 | PROJECT.3.2.3.12.3.5.1.2.17 | FROM B24 TO B22 (SOUTH EAST) Zone 14
14 | PROJECT.3.2.3.12.3.5.2 | SOUTH WEST (A01-A15)
16 | PROJECT.3.2.3.12.3.5.2.1 | PART 1
16 | PROJECT.3.2.3.12.3.5.2.2 | PART 2
18 | PROJECT.3.2.3.12.3.5.2.2.25 | FROM A7 TO A1 (SOUTH WEST) Zone 03
18 | PROJECT.3.2.3.12.3.5.2.2.24 | FROM A15 TO A7 (SOUTH WEST) Zone 03
18 | PROJECT.3.2.3.12.3.5.2.2.23 | FROM A19 TO A15 (SOUTH WEST) Zone 03 & 06
16 | PROJECT.3.2.3.12.3.5.2.3 | CLADDING WORKS (SOUTH WEST)
14 | PROJECT.3.2.3.12.3.5.3 | SOUTH CENTER (Grid (A15-B05)
16 | PROJECT.3.2.3.12.3.5.3.1 | PART 1
16 | PROJECT.3.2.3.12.3.5.3.2 | PART 2
18 | PROJECT.3.2.3.12.3.5.3.2.21 | FROM B5 TO B4 (SOUTH CENTER) Zone 11
18 | PROJECT.3.2.3.12.3.5.3.2.22 | FROM B4 TO A19 (SOUTH CENTER) Zone 06 & 11
12 | PROJECT.3.2.3.12.3.6 | NORTH ELEVATION
14 | PROJECT.3.2.3.12.3.6.2 | NORTH WEST (Grid A01-A19)
16 | PROJECT.3.2.3.12.3.6.2.1 | PART 1
16 | PROJECT.3.2.3.12.3.6.2.2 | PART 2
18 | PROJECT.3.2.3.12.3.6.2.2.7 | FROM A01 TO A10 (NORTH WEST) Zone 01
18 | PROJECT.3.2.3.12.3.6.2.2.1 | FROM A10 TO A19 (NORTH WEST) Zone 01 & 04
14 | PROJECT.3.2.3.12.3.6.3 | NORTH CENTER-8 (Grid A19-B06)
16 | PROJECT.3.2.3.12.3.6.3.1 | PART 1
16 | PROJECT.3.2.3.12.3.6.3.4 | PART 2
18 | PROJECT.3.2.3.12.3.6.3.4.4 | FROM A19 TO A20 (NORTH CENTER) Zone 04
18 | PROJECT.3.2.3.12.3.6.3.4.7 | FROM A20 TO AB05 (NORTH CENTER WEST) Zone 04
18 | PROJECT.3.2.3.12.3.6.3.4.1 | FROM AB05 TO AB14 (NORTH CENTER EAST) Zone 04 & 07
18 | PROJECT.3.2.3.12.3.6.3.4.2 | FROM AB14 TO B5 (NORTH CENTER EAST) Zone 07
18 | PROJECT.3.2.3.12.3.6.3.4.3 | CLADDING WORKS (NORTH CENTER WEST) Z04
18 | PROJECT.3.2.3.12.3.6.3.4.5 | CLADDING WORKS (NORTH CENTER EAST) Z07
14 | PROJECT.3.2.3.12.3.6.1 | NORTH EAST-9 (Grid B06-B20)
16 | PROJECT.3.2.3.12.3.6.1.1 | PART 1
16 | PROJECT.3.2.3.12.3.6.1.2 | PART 2
18 | PROJECT.3.2.3.12.3.6.1.2.4 | FROM B5 TO B8 (NORTH EAST) Zone 09
18 | PROJECT.3.2.3.12.3.6.1.2.8 | FROM B8 TO B12 (NORTH EAST) Zone 09
18 | PROJECT.3.2.3.12.3.6.1.2.9 | FROM B12 TO B15 (NORTH EAST) Zone 09
18 | PROJECT.3.2.3.12.3.6.1.2.10 | FROM B15 TO B18 (NORTH EAST) Zone 09
18 | PROJECT.3.2.3.12.3.6.1.2.11 | FROM B18 TO B19 (NORTH EAST) Zone 09 & 12
10 | PROJECT.3.2.3.12.4 | ROOF PLANT ROOMS (NON-FACADE EXTERNAL WALLS)
12 | PROJECT.3.2.3.12.4.1 | PP3 LEVEL
14 | PROJECT.3.2.3.12.4.1.1 | PP3-A9 : PR-118
14 | PROJECT.3.2.3.12.4.1.2 | PP3-A9 : PR-120
14 | PROJECT.3.2.3.12.4.1.3 | PP3-A17-A : PR-121
14 | PROJECT.3.2.3.12.4.1.4 | PP3-A17-B : PR-121
14 | PROJECT.3.2.3.12.4.1.5 | PP3-A6 : PR-136
14 | PROJECT.3.2.3.12.4.1.6 | PP3-A12 : PR-108&107
14 | PROJECT.3.2.3.12.4.1.7 | PP3-B01 : PR-109&106
14 | PROJECT.3.2.3.12.4.1.8 | PP3-B02 : PR-919
14 | PROJECT.3.2.3.12.4.1.9 | PP3-B20 : PR-124
14 | PROJECT.3.2.3.12.4.1.10 | PP3-B03 : PR-104
14 | PROJECT.3.2.3.12.4.1.11 | PP3-B03 : PR-102
14 | PROJECT.3.2.3.12.4.1.12 | PP3-B03 : PR-101
14 | PROJECT.3.2.3.12.4.1.13 | PP3-B11 : PR-134
14 | PROJECT.3.2.3.12.4.1.14 | PP3-B21 : PR-126
12 | PROJECT.3.2.3.12.4.2 | PP4 LEVEL
14 | PROJECT.3.2.3.12.4.2.1 | PP4-B5 : PR-992
14 | PROJECT.3.2.3.12.4.2.2 | PP4-B18 : PR-918
14 | PROJECT.3.2.3.12.4.2.3 | PP4-B23 : PR-952
14 | PROJECT.3.2.3.12.4.2.4 | PP4-B23 : PR-953
14 | PROJECT.3.2.3.12.4.2.5 | PP4-C2/C3 : PR-921
14 | PROJECT.3.2.3.12.4.2.6 | PP4-C4 : PR-919
14 | PROJECT.3.2.3.12.4.2.7 | PP4-C7 : PR-949,950,912
14 | PROJECT.3.2.3.12.4.2.8 | PP4-C9 : PR-908,951
14 | PROJECT.3.2.3.12.4.2.9 | PP4-C11 : PR-907
14 | PROJECT.3.2.3.12.4.2.10 | PP4-C6/C8 : PR-911
10 | PROJECT.3.2.3.12.5 | SNAGGING AND DESNAGGING
4 | PROJECT.3.3 | MEP
6 | PROJECT.3.3.1 | DESIGN APPROVAL FROM AUTHORITY/NOC
8 | PROJECT.3.3.1.1 | ADSSC-DRAINAGE
8 | PROJECT.3.3.1.2 | ABUDHABI DISTRIBUTION COMPANY-ADDC-Electrical (HV)
8 | PROJECT.3.3.1.3 | ABUDHABI DISTRIBUTION COMPANY-ADDC-Electrical (LV)
8 | PROJECT.3.3.1.4 | ABUDHABI DISTRIBUTION COMPANY-ADDC-Water Supply
8 | PROJECT.3.3.1.5 | ADNOC-GAS
8 | PROJECT.3.3.1.6 | ETISALAT/UTT
8 | PROJECT.3.3.1.7 | ABUDHABI CIVIL DEFENSE-ADCD
6 | PROJECT.3.3.2 | AUTHORITY INITIAL APPROVALS
8 | PROJECT.3.3.2.1 | ADSSC-DRAINAGE
8 | PROJECT.3.3.2.2 | ABUDHABI DISTRIBUTION COMPANY-ADDC-Electrical (HV)
8 | PROJECT.3.3.2.3 | ABUDHABI DISTRIBUTION COMPANY-ADDC-Electrical (LV)
8 | PROJECT.3.3.2.4 | ABUDHABI DISTRIBUTION COMPANY-ADDC-Water Supply
8 | PROJECT.3.3.2.5 | ABUDHABI CIVIL DEFENSE ADCD
8 | PROJECT.3.3.2.6 | ETISALAT/UTT
8 | PROJECT.3.3.2.7 | ADNOC-GAS
6 | PROJECT.3.3.3 | PROCUREMENT PHASE
8 | PROJECT.3.3.3.1 | SUBCONTRACTING
10 | PROJECT.3.3.3.1.1 | PREPARATION AND SUBMISSION
10 | PROJECT.3.3.3.1.2 | REVIEW AND APPROVAL
8 | PROJECT.3.3.3.2 | LONG LEAD MATERIALS
10 | PROJECT.3.3.3.2.1 | MATERIAL SUBMISSIONS
12 | PROJECT.3.3.3.2.1.1 | ELECTRICAL
12 | PROJECT.3.3.3.2.1.2 | MECHANICAL
10 | PROJECT.3.3.3.2.2 | MATERIAL APPROVAL
12 | PROJECT.3.3.3.2.2.1 | ELECTRICAL
12 | PROJECT.3.3.3.2.2.2 | MECHANICAL
10 | PROJECT.3.3.3.2.3 | ISSUE THE LPO/LC
12 | PROJECT.3.3.3.2.3.1 | ELECTRICAL
12 | PROJECT.3.3.3.2.3.2 | MECHANICAL
10 | PROJECT.3.3.3.2.4 | MATERIAL DELIVERY TO SITE
12 | PROJECT.3.3.3.2.4.1 | ELECTRICAL
12 | PROJECT.3.3.3.2.4.2 | MECHANICAL
8 | PROJECT.3.3.3.3 | OTHER MATERIALS
10 | PROJECT.3.3.3.3.1 | MATERIAL SUBMISSION
12 | PROJECT.3.3.3.3.1.1 | ELECTRICAL
12 | PROJECT.3.3.3.3.1.2 | MECHANICAL
10 | PROJECT.3.3.3.3.2 | MATERIAL APPROVAL
12 | PROJECT.3.3.3.3.2.1 | ELECTRICAL
12 | PROJECT.3.3.3.3.2.2 | MECHANICAL
10 | PROJECT.3.3.3.3.3 | ISSUE THE LPO/LC
12 | PROJECT.3.3.3.3.3.1 | ELECTRICAL
12 | PROJECT.3.3.3.3.3.2 | MECHANICAL
10 | PROJECT.3.3.3.3.4 | MATERIAL DELIVERY TO SITE
12 | PROJECT.3.3.3.3.4.1 | ELECTRICAL
12 | PROJECT.3.3.3.3.4.2 | MECHANICAL
8 | PROJECT.3.3.3.4 | FAT LIST
10 | PROJECT.3.3.3.4.1 | MECHANICAL
10 | PROJECT.3.3.3.4.2 | ELECTRICAL
6 | PROJECT.3.3.4 | ENGINEERING PHASE
8 | PROJECT.3.3.4.1 | IFC ENGINEERING DESIGN
8 | PROJECT.3.3.4.2 | SD CONTRACTORS DESIGN
10 | PROJECT.3.3.4.2.1 | SD PREPARATION AND SUBMISSION
12 | PROJECT.3.3.4.2.1.1 | RAFT-SD PREPARATION AND SUBMISSION
14 | PROJECT.3.3.4.2.1.1.1 | MECHANICAL
14 | PROJECT.3.3.4.2.1.1.2 | ELECTRICAL
12 | PROJECT.3.3.4.2.1.2 | ELECTRICAL SD
14 | PROJECT.3.3.4.2.1.2.1 | CONTAINMENT LAYOUT
16 | PROJECT.3.3.4.2.1.2.1.1 | SL
16 | PROJECT.3.3.4.2.1.2.1.2 | BP2
16 | PROJECT.3.3.4.2.1.2.1.3 | BP1
16 | PROJECT.3.3.4.2.1.2.1.4 | GL
16 | PROJECT.3.3.4.2.1.2.1.5 | L1
16 | PROJECT.3.3.4.2.1.2.1.6 | L2/PP1
16 | PROJECT.3.3.4.2.1.2.1.7 | L3/PP2
16 | PROJECT.3.3.4.2.1.2.1.8 | PP3
14 | PROJECT.3.3.4.2.1.2.2 | SCHEMATIC
14 | PROJECT.3.3.4.2.1.2.3 | POWER LAYOUT
14 | PROJECT.3.3.4.2.1.2.4 | LIGHTING LAYOUTS
14 | PROJECT.3.3.4.2.1.2.5 | EARTHING AND LIGHTNING PROTECTION
14 | PROJECT.3.3.4.2.1.2.6 | FIRE ALARM & EM. LIGHTING LAYOUT
14 | PROJECT.3.3.4.2.1.2.7 | EXTRA LOW VOLTAGE
12 | PROJECT.3.3.4.2.1.3 | MECHANICAL SD
14 | PROJECT.3.3.4.2.1.3.1 | DRAINAGE LAYOUT
14 | PROJECT.3.3.4.2.1.3.2 | WATER SERVICES LAYOUT
14 | PROJECT.3.3.4.2.1.3.3 | HVAC LAYOUT
14 | PROJECT.3.3.4.2.1.3.4 | VENTILATION LAYOUT
14 | PROJECT.3.3.4.2.1.3.5 | METERING STRATEGY
14 | PROJECT.3.3.4.2.1.3.6 | FIRE PROTECTION LAYOUT
14 | PROJECT.3.3.4.2.1.3.7 | GAS LAYOUT
10 | PROJECT.3.3.4.2.2 | SD REVIEW AND APPROVAL
12 | PROJECT.3.3.4.2.2.1 | RAFT-SD REVIEW AND APPROVAL
14 | PROJECT.3.3.4.2.2.1.1 | MECHANICAL
14 | PROJECT.3.3.4.2.2.1.2 | ELECTRICAL
12 | PROJECT.3.3.4.2.2.2 | ELECTRICAL SD
14 | PROJECT.3.3.4.2.2.2.1 | APPROVAL OF CONTAINMENT LAYOUT
16 | PROJECT.3.3.4.2.2.2.1.1 | SL
16 | PROJECT.3.3.4.2.2.2.1.2 | BP2
16 | PROJECT.3.3.4.2.2.2.1.3 | BP1
16 | PROJECT.3.3.4.2.2.2.1.4 | GL
16 | PROJECT.3.3.4.2.2.2.1.5 | L1
16 | PROJECT.3.3.4.2.2.2.1.6 | L2/PP1
16 | PROJECT.3.3.4.2.2.2.1.7 | L3/PP2
16 | PROJECT.3.3.4.2.2.2.1.8 | PP3
14 | PROJECT.3.3.4.2.2.2.2 | SCHEMATIC
14 | PROJECT.3.3.4.2.2.2.3 | POWER LAYOUT
14 | PROJECT.3.3.4.2.2.2.4 | LIGHTING LAYOUTS
14 | PROJECT.3.3.4.2.2.2.5 | EARTHING AND LIGHTNING PROTECTION
14 | PROJECT.3.3.4.2.2.2.6 | FIRE ALARM & EM. LIGHTING LAYOUT
14 | PROJECT.3.3.4.2.2.2.7 | EXTRA LOW VOLTAGE
12 | PROJECT.3.3.4.2.2.3 | MECHANICAL SD
14 | PROJECT.3.3.4.2.2.3.1 | DRAINAGE LAYOUT
14 | PROJECT.3.3.4.2.2.3.2 | WATER SERVICES LAYOUT
14 | PROJECT.3.3.4.2.2.3.3 | HVAC LAYOUT
14 | PROJECT.3.3.4.2.2.3.4 | VENTILATION LAYOUT
14 | PROJECT.3.3.4.2.2.3.5 | METERING STRATEGY
14 | PROJECT.3.3.4.2.2.3.6 | FIRE PROTECTION LAYOUT
14 | PROJECT.3.3.4.2.2.3.7 | GAS LAYOUT
8 | PROJECT.3.3.4.3 | COORDINATION WORKSHOPS & DRAWINGS
10 | PROJECT.3.3.4.3.1 | FULL RESOLUTION AND ENGINEER ANSWER TO RFIs
12 | PROJECT.3.3.4.3.1.1 | L1
12 | PROJECT.3.3.4.3.1.2 | L2/PP1
12 | PROJECT.3.3.4.3.1.3 | L3/PP2
12 | PROJECT.3.3.4.3.1.4 | PP3
12 | PROJECT.3.3.4.3.1.5 | PP4
10 | PROJECT.3.3.4.3.4 | FULL RESOLUTION MILESTONES
12 | PROJECT.3.3.4.3.4.1 | L1
12 | PROJECT.3.3.4.3.4.2 | L2/PP1
12 | PROJECT.3.3.4.3.4.3 | L3/PP2
12 | PROJECT.3.3.4.3.4.4 | PP3
12 | PROJECT.3.3.4.3.4.5 | PP4
10 | PROJECT.3.3.4.3.2 | PREPARATION AND SUBMISSION (INCLUDING WORKSHOPS & INHOUSE ACTIVITIES)
12 | PROJECT.3.3.4.3.2.1 | BP1
12 | PROJECT.3.3.4.3.2.2 | GL
12 | PROJECT.3.3.4.3.2.3 | L1
12 | PROJECT.3.3.4.3.2.4 | L2/PP1
12 | PROJECT.3.3.4.3.2.5 | L3/PP2
12 | PROJECT.3.3.4.3.2.6 | PP3
12 | PROJECT.3.3.4.3.2.7 | PP4
10 | PROJECT.3.3.4.3.3 | REVIEW AND APPROVALS
12 | PROJECT.3.3.4.3.3.0 | GL
12 | PROJECT.3.3.4.3.3.1 | L1
12 | PROJECT.3.3.4.3.3.2 | L2/PP1
12 | PROJECT.3.3.4.3.3.3 | L3/PP2
12 | PROJECT.3.3.4.3.3.4 | PP3
12 | PROJECT.3.3.4.3.3.5 | PP4
10 | PROJECT.3.3.4.3.5 | APPROVALS MILESTONES
12 | PROJECT.3.3.4.3.5.0 | GL
12 | PROJECT.3.3.4.3.5.1 | L1
12 | PROJECT.3.3.4.3.5.2 | L2/PP1
12 | PROJECT.3.3.4.3.5.3 | L3/PP2
12 | PROJECT.3.3.4.3.5.4 | PP3
12 | PROJECT.3.3.4.3.5.5 | PP4
6 | PROJECT.3.3.5 | CONSTRUCTION PHASE
8 | PROJECT.3.3.5.1 | BOH LEVEL
10 | PROJECT.3.3.5.1.1 | LB-05 A, LB-05B, LB-05C/ GARBAGE ROOM SL 203 (ZONE11)
12 | PROJECT.3.3.5.1.1.1 | GENERAL CIVIL ACCESS DATES-LB-05 A, LB-05B, LB-05C/ GARBAGE ROOM SL 203
12 | PROJECT.3.3.5.1.1.2 | MEP 1st Fix IN Wall-LB-05 A, LB-05B, LB-05C/ GARBAGE ROOM SL 203
12 | PROJECT.3.3.5.1.1.3 | MEP 2nd Fix-LB-05 A, LB-05B, LB-05C/ GARBAGE ROOM SL 203
14 | PROJECT.3.3.5.1.1.3.1 | HVAC WORKS
14 | PROJECT.3.3.5.1.1.3.2 | CHW PIPING WORKS
14 | PROJECT.3.3.5.1.1.3.3 | ELECTRICAL WORKS
14 | PROJECT.3.3.5.1.1.3.4 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.1.3.5 | PLUMBING AND DRAINAGE WORKS
12 | PROJECT.3.3.5.1.1.4 | MEP FINAL Fix-LB-05 A, LB-05B, LB-05C/ GARBAGE ROOM SL 203
14 | PROJECT.3.3.5.1.1.4.1 | HVAC WORKS
14 | PROJECT.3.3.5.1.1.4.2 | ELECTRICAL WORKS
14 | PROJECT.3.3.5.1.1.4.3 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.1.4.4 | PLUMBING AND DRAINAGE WORKS
10 | PROJECT.3.3.5.1.2 | STORE AREAS (ZONE 10,11,6)
12 | PROJECT.3.3.5.1.2.1 | MACHINE CHARGING YARD SL-410 & CLEANER OFFICE SL-409
14 | PROJECT.3.3.5.1.2.1.1 | GENERAL CIVIL ACCESS DATES-SL-410 & Cleaner Office SL-409
14 | PROJECT.3.3.5.1.2.1.2 | MEP 1st Fix IN WALLS-SL-410 & CLEANER OFFICE SL-409
14 | PROJECT.3.3.5.1.2.1.3 | MEP 2nd Fix-SL-410 & CLEANER OFFICE SL-409
16 | PROJECT.3.3.5.1.2.1.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.1.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.2.1.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.1.3.4 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.2.1.4 | MEP FINAL Fix-SL-410 & CLEANER OFFICE SL-409
16 | PROJECT.3.3.5.1.2.1.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.1.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.1.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.1.4.4 | PLUMBING AND DRAINAGE WORKS
12 | PROJECT.3.3.5.1.2.2 | BOH STORE SL-405/ARCH ROOM SL-406
14 | PROJECT.3.3.5.1.2.2.1 | GENERAL CIVIL ACCESS DATES-BOH Store SL-405/Arch Room SL-406
14 | PROJECT.3.3.5.1.2.2.2 | MEP 1st Fix IN WALL-BOH STORE SL-405/ARCH ROOM SL-406
14 | PROJECT.3.3.5.1.2.2.3 | MEP 2nd Fix-BOH STORE SL-405/ARCH ROOM SL-406
16 | PROJECT.3.3.5.1.2.2.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.2.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.2.2.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.2.3.4 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.2.2.4 | MEP FINAL Fix-BOH STORE SL-405/ARCH ROOM SL-406
16 | PROJECT.3.3.5.1.2.2.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.2.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.2.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.2.4.4 | PLUMBING AND DRAINAGE WORKS
12 | PROJECT.3.3.5.1.2.3 | ELECTRICAL STORE/CIVIL STORE/SUB CONTRACTOR STORE SL 449
14 | PROJECT.3.3.5.1.2.3.1 | GENERAL CIVIL ACCESS DATES-ELECTRICAL STORE/CIVIL STORE/SUB CONTRACTOR STORE SL 449
14 | PROJECT.3.3.5.1.2.3.2 | MEP 1st Fix IN WALL-ELECTRICAL STORE/CIVIL STORE/ SUB CONTRACTOR STORE SL 449
14 | PROJECT.3.3.5.1.2.3.3 | MEP 2nd Fix-ELECTRICAL STORE/CIVIL STORE/SUB CONTRACTOR STORE SL 449
16 | PROJECT.3.3.5.1.2.3.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.3.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.2.3.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.3.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.3.3.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.1.2.3.4 | MEP FINAL Fix-ELECTRICAL STORE/CIVIL STORE/SUB CONTRACTOR STORE SL 449
16 | PROJECT.3.3.5.1.2.3.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.3.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.3.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.3.4.4 | PLUMBING AND DRAINAGE WORKS
12 | PROJECT.3.3.5.1.2.4 | PAINT STORE/DISPOSAL STORE SL 452
14 | PROJECT.3.3.5.1.2.4.1 | GENERAL CIVIL ACCESS DATES-PAINT STORE/DISPOSAL STORE SL 452
14 | PROJECT.3.3.5.1.2.4.2 | MEP 1st Fix in Wall-PAINT STORE/DISPOSAL STORE SL 452
14 | PROJECT.3.3.5.1.2.4.3 | MEP 2nd Fix-PAINT STORE/DISPOSAL STORE SL 452
16 | PROJECT.3.3.5.1.2.4.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.4.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.2.4.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.4.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.4.3.6 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.1.2.4.4 | MEP FINAL Fix-PAINT STORE/DISPOSAL STORE SL 452
16 | PROJECT.3.3.5.1.2.4.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.4.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.4.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.4.4.4 | PLUMBING AND DRAINAGE WORKS
12 | PROJECT.3.3.5.1.2.5 | CHEMICAL STORE & CLEANING CONSUMABLE STORE SL-407
14 | PROJECT.3.3.5.1.2.5.1 | GENERAL CIVIL ACCESS DATES-CHEMICAL STORE & CLEANING CONSUMABLE STORE SL-407
14 | PROJECT.3.3.5.1.2.5.2 | MEP 1st Fix IN WALL-CHEMICAL STORE & CLEANING CONSUMABLE STORE SL-407
14 | PROJECT.3.3.5.1.2.5.3 | MEP 2nd Fix-CHEMICAL STORE & CLEANING CONSUMABLE STORE SL-407
16 | PROJECT.3.3.5.1.2.5.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.5.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.2.5.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.5.3.4 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.2.5.4 | MEP Final Fix-CHEMICAL STORE & CLEANING CONSUMABLE STORE SL-407
16 | PROJECT.3.3.5.1.2.5.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.5.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.5.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.5.4.4 | PLUMBING AND DRAINAGE WORKS
12 | PROJECT.3.3.5.1.2.6 | FILTER WASHING ROOM SL448/ FILTER STORE ROOM SL-447
14 | PROJECT.3.3.5.1.2.6.1 | GENERAL CIVIL ACCESS DATES-FILTER WASHING ROOM SL448/ FILTER STORE ROOM SL-447
14 | PROJECT.3.3.5.1.2.6.2 | MEP 1st Fix IN WALL-FILTER WASHING ROOM SL448/ FILTER STORE ROOM SL-447
14 | PROJECT.3.3.5.1.2.6.3 | MEP 2nd Fix-FILTER WASHING ROOM SL448/ FILTER STORE ROOM SL-447
16 | PROJECT.3.3.5.1.2.6.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.6.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.2.6.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.6.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.6.3.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.1.2.6.4 | MEP FINAL Fix-FILTER WASHING ROOM SL448/ FILTER STORE ROOM SL-447
16 | PROJECT.3.3.5.1.2.6.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.6.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.6.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.6.4.4 | PLUMBING AND DRAINAGE WORKS
12 | PROJECT.3.3.5.1.2.7 | DATA CENTER SL 446/TETRA ROOM SL-454
14 | PROJECT.3.3.5.1.2.7.1 | GENERAL CIVIL ACCESS DATES-DATA CENTER SL 446/TETRA ROOM SL-454
14 | PROJECT.3.3.5.1.2.7.2 | MEP 1st Fix IN WALL-DATA CENTER SL 446/TETRA ROOM SL-454
14 | PROJECT.3.3.5.1.2.7.3 | MEP 2nd Fix-DATA CENTER SL 446/TETRA ROOM SL-454
16 | PROJECT.3.3.5.1.2.7.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.7.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.2.7.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.7.3.4 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.2.7.4 | MEP FINAL Fix-DATA CENTER SL 446/TETRA ROOM SL-454
16 | PROJECT.3.3.5.1.2.7.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.2.7.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.2.7.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.2.7.4.4 | PLUMBING AND DRAINAGE WORKS
10 | PROJECT.3.3.5.1.3 | LB-04 A, LB-04B (ZONE 6)
12 | PROJECT.3.3.5.1.3.1 | GENERAL CIVIL ACCESS DATES-LB-04 A, LB-04B
12 | PROJECT.3.3.5.1.3.2 | MEP 1st Fix in Wall-LB-04 A, LB-04B
12 | PROJECT.3.3.5.1.3.3 | MEP 2nd Fix-LB-04 A, LB-04B
14 | PROJECT.3.3.5.1.3.3.1 | HVAC WORKS
14 | PROJECT.3.3.5.1.3.3.2 | CHW PIPING WORKS
14 | PROJECT.3.3.5.1.3.3.3 | ELECTRICAL WORKS
14 | PROJECT.3.3.5.1.3.3.4 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.3.3.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.1.3.4 | MEP Final Fix-LB-04 A, LB-04B
14 | PROJECT.3.3.5.1.3.4.1 | HVAC WORKS
14 | PROJECT.3.3.5.1.3.4.2 | ELECTRICAL WORKS
14 | PROJECT.3.3.5.1.3.4.3 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.3.4.4 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.1.4 | CORRIDORS (ZONE 5,6,8,10,11)
12 | PROJECT.3.3.5.1.4.1 | CORRIDOR SL-413
14 | PROJECT.3.3.5.1.4.1.1 | GENERAL CIVIL ACCESS DATES-CORRIDOR SL-413
14 | PROJECT.3.3.5.1.4.1.2 | MEP 1ST Fix IN WALL-CORRIDOR SL-413
14 | PROJECT.3.3.5.1.4.1.3 | MEP 2ND Fix-CORRIDOR SL-413
16 | PROJECT.3.3.5.1.4.1.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.4.1.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.4.1.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.4.1.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.4.1.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.1.4.1.4 | MEP FINAL Fix-CORRIDOR SL-413
16 | PROJECT.3.3.5.1.4.1.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.4.1.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.4.1.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.4.1.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.1.4.2 | CORRIDOR SL-402
14 | PROJECT.3.3.5.1.4.2.1 | GENERAL CIVIL ACCESS DATES-CORRIDOR SL-402
14 | PROJECT.3.3.5.1.4.2.2 | MEP 1ST Fix IN WALL-CORRIDOR SL-402
14 | PROJECT.3.3.5.1.4.2.3 | MEP 2ND Fix-CORRIDOR SL-402
16 | PROJECT.3.3.5.1.4.2.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.4.2.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.4.2.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.4.2.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.4.2.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.1.4.2.4 | MEP FINAL Fix-CORRIDOR SL-402
16 | PROJECT.3.3.5.1.4.2.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.4.2.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.4.2.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.4.2.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.1.4.3 | CORRIDOR SL-401
14 | PROJECT.3.3.5.1.4.3.1 | GENERAL CIVIL ACCESS DATES-CORRIDOR SL-401
14 | PROJECT.3.3.5.1.4.3.2 | MEP 1ST Fix IN WALL-CORRIDOR SL-401
14 | PROJECT.3.3.5.1.4.3.3 | MEP 2ND Fix-CORRIDOR SL-401
16 | PROJECT.3.3.5.1.4.3.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.4.3.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.4.3.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.4.3.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.4.3.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.1.4.3.4 | MEP FINAL Fix-CORRIDOR SL-401
16 | PROJECT.3.3.5.1.4.3.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.4.3.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.4.3.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.4.3.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.1.4.4 | CORRIDOR SL-456
14 | PROJECT.3.3.5.1.4.4.1 | GENERAL CIVIL ACCESS DATES-CORRIDOR SL-456
14 | PROJECT.3.3.5.1.4.4.2 | MEP 1ST Fix IN WALL-CORRIDOR SL-456
14 | PROJECT.3.3.5.1.4.4.3 | MEP 2ND Fix-CORRIDOR SL-456
16 | PROJECT.3.3.5.1.4.4.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.4.4.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.1.4.4.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.4.4.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.4.4.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.1.4.4.4 | MEP FINAL Fix-CORRIDOR SL-456
16 | PROJECT.3.3.5.1.4.4.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.1.4.4.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.1.4.4.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.1.4.4.4.4 | PLUMBING & DRAINAGE WORKS
10 | PROJECT.3.3.5.1.12 | Pour Area B8,B'8 (Zone 5&6)
12 | PROJECT.3.3.5.1.12.1 | Toilets-SL-431, SL-432, SL-229
14 | PROJECT.3.3.5.1.12.1.1 | General Civil Access Dates-Toilets-SL-431, SL-432, SL-229
14 | PROJECT.3.3.5.1.12.1.2 | MEP 1st Fix in Wall-Toilets-SL-431, SL-432, SL-229
14 | PROJECT.3.3.5.1.12.1.3 | MEP 2nd Fix-Toilets-SL-431, SL-432, SL-229
16 | PROJECT.3.3.5.1.12.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.1.12.1.3.2 | Electrical Works
16 | PROJECT.3.3.5.1.12.1.3.3 | Fire Fighting Works
16 | PROJECT.3.3.5.1.12.1.3.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.1.12.1.4 | MEP Final Fix-Toilets-SL-431, SL-432, SL-229
16 | PROJECT.3.3.5.1.12.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.1.12.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.1.12.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.1.12.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.1.12.2 | Kitchen & Ablution 429
14 | PROJECT.3.3.5.1.12.2.1 | General Civil Access Dates-Kitchen & Ablution
14 | PROJECT.3.3.5.1.12.2.2 | MEP 1st Fix in Wall-Kitchen & Ablution
14 | PROJECT.3.3.5.1.12.2.3 | MEP 2nd Fix-Kitchen & Ablution
16 | PROJECT.3.3.5.1.12.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.1.12.2.3.2 | Electrical Works
16 | PROJECT.3.3.5.1.12.2.3.3 | Fire Fighting Works
16 | PROJECT.3.3.5.1.12.2.3.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.1.12.2.4 | MEP Final Fix-Kitchen & Ablution
16 | PROJECT.3.3.5.1.12.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.1.12.2.4.2 | Electrical Works
16 | PROJECT.3.3.5.1.12.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.1.12.2.4.4 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.1.5 | TOILET-SL-241 (Zone 11)
12 | PROJECT.3.3.5.1.5.1 | GENERAL CIVIL ACCESS DATES-TOILETS-SL-241
12 | PROJECT.3.3.5.1.5.2 | MEP 1ST Fix IN WALL-TOILETS-SL-241
12 | PROJECT.3.3.5.1.5.3 | MEP 2ND Fix-TOILETS-SL-241
14 | PROJECT.3.3.5.1.5.3.1 | HVAC WORKS
14 | PROJECT.3.3.5.1.5.3.2 | ELECTRICAL WORKS
14 | PROJECT.3.3.5.1.5.3.3 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.5.3.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.1.5.4 | MEP FINAL Fix-TOILETS-SL-241
14 | PROJECT.3.3.5.1.5.4.1 | HVAC WORKS
14 | PROJECT.3.3.5.1.5.4.2 | ELECTRICAL WORKS
14 | PROJECT.3.3.5.1.5.4.3 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.5.4.4 | PLUMBING & DRAINAGE WORKS
10 | PROJECT.3.3.5.1.6 | SUBSTATION NO-6 (ZONE 6 &11)
12 | PROJECT.3.3.5.1.6.1 | GENERAL CIVIL ACCESS DATES-SS-06
12 | PROJECT.3.3.5.1.6.2 | MEP 1ST Fix IN WALL-SS-06
12 | PROJECT.3.3.5.1.6.3 | MEP 2ND Fix-SS-06
14 | PROJECT.3.3.5.1.6.3.1 | HVAC WORKS
14 | PROJECT.3.3.5.1.6.3.2 | CHW PIPING WORKS
14 | PROJECT.3.3.5.1.6.3.3 | ELECTRICAL WORKS
14 | PROJECT.3.3.5.1.6.3.4 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.6.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.1.6.3.6 | WATER SUPPLY WORKS
14 | PROJECT.3.3.5.1.6.3.7 | EQUIPMENT INSTALLATIONS
12 | PROJECT.3.3.5.1.6.4 | MEP FINAL Fix-SS-06
14 | PROJECT.3.3.5.1.6.4.1 | HVAC WORKS
14 | PROJECT.3.3.5.1.6.4.2 | ELECTRICAL WORKS
14 | PROJECT.3.3.5.1.6.4.3 | FIRE FIGHTING WORKS
14 | PROJECT.3.3.5.1.6.4.4 | PLUMBING & DRAINAGE WORKS
8 | PROJECT.3.3.5.2 | SERVICE LEVEL (SL)
10 | PROJECT.3.3.5.2.1 | SUB STATIONS
12 | PROJECT.3.3.5.2.1.1 | SUBSTATION NO-1 (ZONE 1)
14 | PROJECT.3.3.5.2.1.1.1 | GENERAL CIVIL ACCESS DATES-SS-01
14 | PROJECT.3.3.5.2.1.1.2 | MEP 1ST Fix IN WALL-SS-01
14 | PROJECT.3.3.5.2.1.1.3 | MEP 2ND Fix-SS-01
16 | PROJECT.3.3.5.2.1.1.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.1.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.1.1.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.1.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.1.3.5 | PLUMBING & DRAINAGE WORKS
16 | PROJECT.3.3.5.2.1.1.3.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.2.1.1.3.7 | EQUIPMENT INSTALLATIONS
14 | PROJECT.3.3.5.2.1.1.4 | MEP FINAL Fix-SS-01
16 | PROJECT.3.3.5.2.1.1.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.1.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.1.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.1.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.1.2 | SUBSTATION NO-4 (ZONE 12)
14 | PROJECT.3.3.5.2.1.2.1 | GENERAL CIVIL ACCESS DATES-SS-04
14 | PROJECT.3.3.5.2.1.2.2 | MEP 1ST Fix IN WALL-SS-04
14 | PROJECT.3.3.5.2.1.2.3 | MEP 2ND Fix-SS-04
16 | PROJECT.3.3.5.2.1.2.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.2.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.1.2.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.2.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.2.3.5 | PLUMBING & DRAINAGE WORKS
16 | PROJECT.3.3.5.2.1.2.3.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.2.1.2.3.7 | EQUIPMENT INSTALLATIONS
14 | PROJECT.3.3.5.2.1.2.4 | MEP FINAL Fix-SS-04
16 | PROJECT.3.3.5.2.1.2.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.2.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.2.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.2.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.1.3 | SUBSTATION NO-7 (ZONE 14)
14 | PROJECT.3.3.5.2.1.3.1 | GENERAL CIVIL ACCESS DATES-SS-07
14 | PROJECT.3.3.5.2.1.3.2 | MEP 1ST Fix IN WALL-SS-07
14 | PROJECT.3.3.5.2.1.3.3 | MEP 2ND Fix-SS-07
16 | PROJECT.3.3.5.2.1.3.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.3.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.1.3.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.3.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.3.3.5 | PLUMBING & DRAINAGE WORKS
16 | PROJECT.3.3.5.2.1.3.3.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.2.1.3.3.7 | EQUIPMENT INSTALLATIONS
14 | PROJECT.3.3.5.2.1.3.4 | MEP FINAL Fix-SS-07
16 | PROJECT.3.3.5.2.1.3.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.3.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.3.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.3.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.1.4 | SUBSTATION NO-5 (ZONE 2)
14 | PROJECT.3.3.5.2.1.4.1 | GENERAL CIVIL ACCESS DATES-SS-05
14 | PROJECT.3.3.5.2.1.4.2 | MEP 1ST Fix IN WALL-SS-05
14 | PROJECT.3.3.5.2.1.4.3 | MEP 2ND Fix-SS-05
16 | PROJECT.3.3.5.2.1.4.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.4.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.1.4.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.4.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.4.3.5 | PLUMBING & DRAINAGE WORKS
16 | PROJECT.3.3.5.2.1.4.3.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.2.1.4.3.7 | EQUIPMENT INSTALLATIONS
14 | PROJECT.3.3.5.2.1.4.4 | MEP FINAL Fix-SS-05
16 | PROJECT.3.3.5.2.1.4.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.4.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.4.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.4.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.1.5 | SUBSTATION NO-3 (ZONE 9)
14 | PROJECT.3.3.5.2.1.5.1 | GENERAL CIVIL ACCESS DATES-SS-03
14 | PROJECT.3.3.5.2.1.5.2 | MEP 1ST Fix IN WALL-SS-03
14 | PROJECT.3.3.5.2.1.5.3 | MEP 2ND Fix-SS-03
16 | PROJECT.3.3.5.2.1.5.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.5.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.1.5.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.5.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.5.3.5 | PLUMBING & DRAINAGE WORKS
16 | PROJECT.3.3.5.2.1.5.3.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.2.1.5.3.7 | EQUIPMENT INSTALLATIONS
14 | PROJECT.3.3.5.2.1.5.4 | MEP FINAL Fix-SS-03
16 | PROJECT.3.3.5.2.1.5.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.5.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.5.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.5.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.1.6 | SUBSTATION NO-2 (ZONE 4 & 7)
14 | PROJECT.3.3.5.2.1.6.1 | GENERAL CIVIL ACCESS DATES-SS-02
14 | PROJECT.3.3.5.2.1.6.2 | MEP 1ST Fix IN WALL-SS-02
14 | PROJECT.3.3.5.2.1.6.3 | MEP 2ND Fix-SS-02
16 | PROJECT.3.3.5.2.1.6.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.6.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.1.6.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.6.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.6.3.5 | PLUMBING & DRAINAGE WORKS
16 | PROJECT.3.3.5.2.1.6.3.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.2.1.6.3.7 | EQUIPMENT INSTALLATIONS
14 | PROJECT.3.3.5.2.1.6.4 | MEP FINAL Fix-SS-02
16 | PROJECT.3.3.5.2.1.6.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.1.6.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.1.6.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.1.6.4.4 | PLUMBING & DRAINAGE WORKS
10 | PROJECT.3.3.5.2.2 | ETS ROOMS
12 | PROJECT.3.3.5.2.2.1 | ETS ROOMS NO-01 (ZONE 14)
14 | PROJECT.3.3.5.2.2.1.1 | GENERAL CIVIL ACCESS DATES-ETS-01
14 | PROJECT.3.3.5.2.2.1.2 | MEP 1ST Fix IN WALL-ETS-01
14 | PROJECT.3.3.5.2.2.1.3 | MEP 2ND Fix-ETS-01
16 | PROJECT.3.3.5.2.2.1.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.2.1.3.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.2.2.1.3.2.1 | External CHW Piping works
16 | PROJECT.3.3.5.2.2.1.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.2.1.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.2.1.3.5 | PLUMBING & DRAINAGE WORKS
16 | PROJECT.3.3.5.2.2.1.3.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.2.2.1.3.7 | EQUIPMENT INSTALLATIONS
14 | PROJECT.3.3.5.2.2.1.4 | MEP FINAL Fix-ETS-01
16 | PROJECT.3.3.5.2.2.1.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.2.1.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.2.1.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.2.1.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.2.2 | ETS ROOMS NO-02 (ZONE 6 & 11)
14 | PROJECT.3.3.5.2.2.2.1 | GENERAL CIVIL ACCESS DATES-ETS-02
14 | PROJECT.3.3.5.2.2.2.2 | MEP 1ST Fix IN WALL-ETS-02
14 | PROJECT.3.3.5.2.2.2.3 | MEP 2ND Fix-ETS-02
16 | PROJECT.3.3.5.2.2.2.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.2.2.3.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.2.2.2.3.2.2 | External CHW Piping works
16 | PROJECT.3.3.5.2.2.2.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.2.2.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.2.2.3.5 | PLUMBING & DRAINAGE WORKS
16 | PROJECT.3.3.5.2.2.2.3.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.2.2.2.3.7 | EQUIPMENT INSTALLATIONS
14 | PROJECT.3.3.5.2.2.2.4 | MEP FINAL Fix-ETS-02
16 | PROJECT.3.3.5.2.2.2.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.2.2.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.2.2.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.2.2.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.2.3 | ETS ROOMS NO-03 (ZONE 3)
14 | PROJECT.3.3.5.2.2.3.1 | GENERAL CIVIL ACCESS DATES-ETS-03
14 | PROJECT.3.3.5.2.2.3.2 | MEP 1ST Fix IN WALL-ETS-03
14 | PROJECT.3.3.5.2.2.3.3 | MEP 2ND Fix-ETS-03
16 | PROJECT.3.3.5.2.2.3.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.2.3.3.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.2.2.3.3.2.1 | External CHW Piping works
16 | PROJECT.3.3.5.2.2.3.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.2.3.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.2.3.3.5 | PLUMBING & DRAINAGE WORKS
16 | PROJECT.3.3.5.2.2.3.3.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.2.2.3.3.7 | EQUIPMENT INSTALLATIONS
14 | PROJECT.3.3.5.2.2.3.4 | MEP FINAL Fix-ETS-03
16 | PROJECT.3.3.5.2.2.3.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.2.3.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.2.3.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.2.3.4.4 | PLUMBING & DRAINAGE WORKS
10 | PROJECT.3.3.5.2.3 | ELECTRICAL/ELV ROOMS
12 | PROJECT.3.3.5.2.3.1 | ELECTRICAL ROOM-SL 145/UTT RM/BMS RM/LED RM (ZONE 4)
14 | PROJECT.3.3.5.2.3.1.1 | GENERAL CIVIL ACCESS DATES-ELECTRICAL ROOM SL-145
14 | PROJECT.3.3.5.2.3.1.2 | MEP 1ST Fix IN WALL-ELECTRICAL ROOM SL-145
14 | PROJECT.3.3.5.2.3.1.3 | MEP 2ND Fix-ELECTRICAL ROOM SL-145
16 | PROJECT.3.3.5.2.3.1.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.1.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.3.1.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.1.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.1.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.2.3.1.4 | MEP FINAL Fix-ELECTRICAL ROOM SL-145
16 | PROJECT.3.3.5.2.3.1.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.1.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.1.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.1.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.3.2 | ELECTRICAL ROOM-SL 125/UTT RM/BMS RM/BATRM (ZONE 7)
14 | PROJECT.3.3.5.2.3.2.1 | GENERAL CIVIL ACCESS DATES-ELECTRICAL ROOM SL-125
14 | PROJECT.3.3.5.2.3.2.2 | MEP 1ST Fix IN WALL-ELECTRICAL ROOM SL-125
14 | PROJECT.3.3.5.2.3.2.3 | MEP 2ND Fix-ELECTRICAL ROOM SL-125
16 | PROJECT.3.3.5.2.3.2.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.2.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.3.2.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.2.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.2.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.2.3.2.4 | MEP FINAL Fix-ELECTRICAL ROOM SL-125
16 | PROJECT.3.3.5.2.3.2.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.2.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.2.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.2.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.3.3 | ELECTRICAL ROOM-SL 249/UTT RM/BMS RM/LED RM (ZONE 11)
14 | PROJECT.3.3.5.2.3.3.1 | GENERAL CIVIL ACCESS DATES-ELECTRICAL ROOM SL-249
14 | PROJECT.3.3.5.2.3.3.2 | MEP 1ST Fix IN WALL-ELECTRICAL ROOM SL-249
14 | PROJECT.3.3.5.2.3.3.3 | MEP 2ND Fix-ELECTRICAL ROOM SL-249
16 | PROJECT.3.3.5.2.3.3.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.3.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.3.3.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.3.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.3.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.2.3.3.4 | MEP FINAL Fix-ELECTRICAL ROOM SL-249
16 | PROJECT.3.3.5.2.3.3.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.3.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.3.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.3.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.3.4 | ELECTRICAL ROOM-SL 210/UTT RM/BMS RM/LED RM (ZONE 6)
14 | PROJECT.3.3.5.2.3.4.1 | GENERAL CIVIL ACCESS DATES-ELECTRICAL ROOM SL-210
14 | PROJECT.3.3.5.2.3.4.2 | MEP 1ST Fix IN WALL-ELECTRICAL ROOM SL-210
14 | PROJECT.3.3.5.2.3.4.3 | MEP 2ND Fix-ELECTRICAL ROOM SL-210
16 | PROJECT.3.3.5.2.3.4.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.4.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.3.4.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.4.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.4.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.2.3.4.5 | MEP FINAL Fix-ELECTRICAL ROOM SL-210
16 | PROJECT.3.3.5.2.3.4.5.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.4.5.2 | Electrical Works
16 | PROJECT.3.3.5.2.3.4.5.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.4.5.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.3.5 | ELECTRICAL ROOM-SL 421/UTT RM/BMS RM/LED RM (ZONE 5 & 6)
14 | PROJECT.3.3.5.2.3.5.1 | GENERAL CIVIL ACCESS DATES-ELECTRICAL ROOM SL-421
14 | PROJECT.3.3.5.2.3.5.2 | MEP 1ST Fix IN WALL-ELECTRICAL ROOM SL-421
14 | PROJECT.3.3.5.2.3.5.3 | MEP 2ND Fix-ELECTRICAL ROOM SL-421
16 | PROJECT.3.3.5.2.3.5.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.5.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.3.5.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.5.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.5.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.2.3.5.4 | MEP FINAL Fix-ELECTRICAL ROOM SL-421
16 | PROJECT.3.3.5.2.3.5.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.5.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.5.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.5.4.4 | PLUMBING & DRAINAGE WORKS
12 | PROJECT.3.3.5.2.3.6 | ELECTRICAL ROOM-SL 418/UTT RM/BMS RM/LED RM (ZONE 8,10,11)
14 | PROJECT.3.3.5.2.3.6.1 | GENERAL CIVIL ACCESS DATES-ELECTRICAL ROOM SL-418
14 | PROJECT.3.3.5.2.3.6.2 | MEP 1ST Fix IN WALL-ELECTRICAL ROOM SL-418
14 | PROJECT.3.3.5.2.3.6.3 | MEP 2ND Fix-ELECTRICAL ROOM SL-418
16 | PROJECT.3.3.5.2.3.6.3.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.6.3.2 | CHW PIPING WORKS
16 | PROJECT.3.3.5.2.3.6.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.6.3.4 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.6.3.5 | PLUMBING & DRAINAGE WORKS
14 | PROJECT.3.3.5.2.3.6.4 | MEP FINAL Fix-ELECTRICAL ROOM SL-418
16 | PROJECT.3.3.5.2.3.6.4.1 | HVAC WORKS
16 | PROJECT.3.3.5.2.3.6.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.3.6.4.3 | FIRE FIGHTING WORKS
16 | PROJECT.3.3.5.2.3.6.4.4 | PLUMBING & DRAINAGE WORKS
10 | PROJECT.3.3.5.2.4 | CPMF/CPEF ROOMS
12 | PROJECT.3.3.5.2.4.1 | CAR PARK MAKE-UP FAN ROOM SL-152 (ZONE 4)
14 | PROJECT.3.3.5.2.4.1.1 | GENERAL CIVIL ACCESS DATES-CPMF-152
14 | PROJECT.3.3.5.2.4.1.2 | MEP 1st Fix in Wall-CPMF-152
14 | PROJECT.3.3.5.2.4.1.3 | MEP 2nd Fix-CPMF-152
16 | PROJECT.3.3.5.2.4.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.4.1.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.4.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.1.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.4.1.3.6 | Water Supply Works
14 | PROJECT.3.3.5.2.4.1.4 | MEP Final Fix-CPMF-152
16 | PROJECT.3.3.5.2.4.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.1.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.4.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.4.2 | MAKE-UP FAN ROOM SL-118 (ZONE 9)
14 | PROJECT.3.3.5.2.4.2.1 | GENERAL CIVIL ACCESS DATES-MAKE-UP FAN ROOM SL-118 (ZONE 9)
14 | PROJECT.3.3.5.2.4.2.2 | MEP 1st Fix in Wall-CPMF-118
14 | PROJECT.3.3.5.2.4.2.3 | MEP 2nd Fix-CPMF-118
16 | PROJECT.3.3.5.2.4.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.2.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.4.2.3.3 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.4.2.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.2.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.4.2.3.6 | Water Supply Works
14 | PROJECT.3.3.5.2.4.2.4 | MEP Final Fix-CPMF-118
16 | PROJECT.3.3.5.2.4.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.2.4.2 | ELECTRICAL WORKS
16 | PROJECT.3.3.5.2.4.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.4.3 | CAR PARK EXTRACT FAN ROOM SL-266 (ZONE 14)
14 | PROJECT.3.3.5.2.4.3.1 | GENERAL CIVIL ACCESS DATES-CPMF-266
14 | PROJECT.3.3.5.2.4.3.2 | MEP 1st Fix in Wall-CPMF-266
14 | PROJECT.3.3.5.2.4.3.3 | MEP 2nd Fix-CPMF-266
16 | PROJECT.3.3.5.2.4.3.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.3.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.4.3.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.4.3.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.3.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.4.3.3.6 | Water Supply Works
14 | PROJECT.3.3.5.2.4.3.4 | MEP Final Fix-CPMF-266
16 | PROJECT.3.3.5.2.4.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.3.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.4.3.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.3.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.4.4 | CAR PARK EXTRACT FAN ROOM SL-243 (ZONE 6)
14 | PROJECT.3.3.5.2.4.4.1 | GENERAL CIVIL ACCESS DATES-CPMF-243
14 | PROJECT.3.3.5.2.4.4.2 | MEP 1st Fix in Wall-CPMF-243
14 | PROJECT.3.3.5.2.4.4.3 | MEP 2nd Fix-CPMF-243
16 | PROJECT.3.3.5.2.4.4.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.4.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.4.4.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.4.4.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.4.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.4.4.3.6 | Water Supply Works
14 | PROJECT.3.3.5.2.4.4.4 | MEP Final Fix-CPMF-243
16 | PROJECT.3.3.5.2.4.4.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.4.4.3 | Electrical Works
16 | PROJECT.3.3.5.2.4.4.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.4.4.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.4.5 | CAR PARK EXTRACT FAN ROOM SL-189 (ZONE 3)
14 | PROJECT.3.3.5.2.4.5.1 | GENERAL CIVIL ACCESS DATES-CPMF-189
14 | PROJECT.3.3.5.2.4.5.2 | MEP 1st Fix in Wall-CPMF-189
14 | PROJECT.3.3.5.2.4.5.3 | MEP 2nd Fix-CPMF-189
16 | PROJECT.3.3.5.2.4.5.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.5.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.4.5.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.4.5.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.5.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.4.5.3.6 | Water Supply Works
14 | PROJECT.3.3.5.2.4.5.4 | MEP Final Fix-CPMF-189
16 | PROJECT.3.3.5.2.4.5.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.5.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.4.5.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.5.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.4.6 | CAR PARK MAKE-UP FAN ROOM SL-187 (ZONE 3)
14 | PROJECT.3.3.5.2.4.6.1 | GENERAL CIVIL ACCESS DATES-CPMF-187
14 | PROJECT.3.3.5.2.4.6.2 | MEP 1st Fix in Wall-CPMF-187
14 | PROJECT.3.3.5.2.4.6.3 | MEP 2nd Fix-CPMF-187
16 | PROJECT.3.3.5.2.4.6.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.6.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.4.6.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.4.6.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.6.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.4.6.3.6 | Water Supply Works
14 | PROJECT.3.3.5.2.4.6.4 | MEP Final Fix-CPMF-187
16 | PROJECT.3.3.5.2.4.6.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.6.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.4.6.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.6.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.4.7 | MAKE-UP FAN ROOM SL-161 (ZONE 3)
14 | PROJECT.3.3.5.2.4.7.1 | GENERAL CIVIL ACCESS DATES-CPMF-161
14 | PROJECT.3.3.5.2.4.7.2 | MEP 1st Fix in Wall-CPMF-161
14 | PROJECT.3.3.5.2.4.7.3 | MEP 2nd Fix-CPMF-161
16 | PROJECT.3.3.5.2.4.7.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.7.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.4.7.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.4.7.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.7.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.4.7.3.6 | Water Supply Works
14 | PROJECT.3.3.5.2.4.7.4 | MEP Final Fix-CPMF-161
16 | PROJECT.3.3.5.2.4.7.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.7.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.4.7.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.7.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.4.8 | CPF ROOM SL-317/ SL-247 (ZONE 6 & 11)
14 | PROJECT.3.3.5.2.4.8.1 | GENERAL CIVIL ACCESS DATES-CPMF-317/247
14 | PROJECT.3.3.5.2.4.8.2 | MEP 1st Fix in Wall-CPMF-317/247
14 | PROJECT.3.3.5.2.4.8.3 | MEP 2nd Fix-CPMF-317/247
16 | PROJECT.3.3.5.2.4.8.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.8.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.4.8.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.4.8.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.8.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.4.8.3.6 | Water Supply Works
14 | PROJECT.3.3.5.2.4.8.4 | MEP Final Fix-CPMF-317/247
16 | PROJECT.3.3.5.2.4.8.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.4.8.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.4.8.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.4.8.4.4 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.2.5 | Loading Bay Areas/Garbage Room/Compactor Room
12 | PROJECT.3.3.5.2.5.1 | LB-02 A,LB-02 B,LB-02 C,LB-02 D/ Garbage Room SL 183/ Compactor Room SL 185 (Zone 3)
14 | PROJECT.3.3.5.2.5.1.1 | General Civil Access Dates-LB-02 A,LB-02 B,LB-02 C,LB-02 D/ SL 183/ SL 185
14 | PROJECT.3.3.5.2.5.1.2 | MEP 1st Fix in Wall-LB-02 A,LB-02 B,LB-02 C,LB-02 D/ SL 183/ SL 185
14 | PROJECT.3.3.5.2.5.1.3 | MEP 2nd Fix-LB-02 A,LB-02 B,LB-02 C,LB-02 D/ SL 183/ SL 185
16 | PROJECT.3.3.5.2.5.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.1.4 | MEP Final Fix-LB-02 A,LB-02 B,LB-02 C,LB-02 D/ SL 183/ SL 185
16 | PROJECT.3.3.5.2.5.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.5.2 | LB-04C, LB-04D, LB-04E, LB-04F/Garbage Room SL 227/ LB 03A,LB-03B (Zone 6)
14 | PROJECT.3.3.5.2.5.2.1 | General Civil Access Dates-LB-04C, LB-04D, LB-04E, LB-04F/Garbage Room SL 227/ LB 03A,LB-03B
14 | PROJECT.3.3.5.2.5.2.2 | MEP 1st Fix in Wall-LB-04C, LB-04D, LB-04E, LB-04F/Garbage Room SL 227/ LB 03A,LB-03B
14 | PROJECT.3.3.5.2.5.2.3 | MEP 2nd Fix-LB-04C, LB-04D, LB-04E, LB-04F/Garbage Room SL 227/ LB 03A,LB-03B
16 | PROJECT.3.3.5.2.5.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.2.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.2.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.2.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.2.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.2.4 | MEP Final Fix-LB-04C, LB-04D, LB-04E, LB-04F/Garbage Room SL 227/ LB 03A,LB-03B
16 | PROJECT.3.3.5.2.5.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.2.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.5.3 | LB-01 A, LB-01B (Zone 1)
14 | PROJECT.3.3.5.2.5.3.1 | General Civil Access Dates-LB-01 A, LB-01B
14 | PROJECT.3.3.5.2.5.3.2 | MEP 1st Fix in Wall-LB-01 A, LB-01B
14 | PROJECT.3.3.5.2.5.3.3 | MEP 2nd Fix-LB-01 A, LB-01B
16 | PROJECT.3.3.5.2.5.3.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.3.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.3.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.3.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.3.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.3.4 | MEP Final Fix-LB-01 A, LB-01B
16 | PROJECT.3.3.5.2.5.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.3.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.3.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.3.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.5.4 | LB-06 A, LB-06B/Garbage Room SL 119 (Zone 7& 9)
14 | PROJECT.3.3.5.2.5.4.1 | General Civil Access Dates-LB-06 A, LB-06B/Garbage Room SL 119
14 | PROJECT.3.3.5.2.5.4.2 | MEP 1st Fix in Wall-LB-06 A, LB-06B/Garbage Room SL 119
14 | PROJECT.3.3.5.2.5.4.3 | MEP 2nd Fix-LB-06 A, LB-06B/Garbage Room SL 119
16 | PROJECT.3.3.5.2.5.4.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.4.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.4.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.4.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.4.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.4.4 | MEP Final Fix-LB-06 A, LB-06B/Garbage Room SL 119
16 | PROJECT.3.3.5.2.5.4.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.4.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.4.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.4.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.5.5 | LB-05 D, LB-05E (Zone 6)
14 | PROJECT.3.3.5.2.5.5.1 | General Civil Access Dates-LB-05 D, LB-05E
14 | PROJECT.3.3.5.2.5.5.2 | MEP 1st Fix in Wall-LB-05 D, LB-05E
14 | PROJECT.3.3.5.2.5.5.3 | MEP 2nd Fix-LB-05 D, LB-05E
16 | PROJECT.3.3.5.2.5.5.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.5.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.5.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.5.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.5.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.5.4 | MEP Final Fix-LB-05 D, LB-05E
16 | PROJECT.3.3.5.2.5.5.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.5.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.5.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.5.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.5.6 | LB-07 A,LB-07 B,LB-07 C,LB-07 D/ Garbage Room SL 280/ Bulky waste RM SL-279 (Zone 13 &14)
14 | PROJECT.3.3.5.2.5.6.1 | General Civil Access Dates-LB-07 A,LB-07 B,LB-07 C,LB-07 D
14 | PROJECT.3.3.5.2.5.6.2 | MEP 1st Fix in Wall-LB-07 A,LB-07 B,LB-07 C,LB-07 D
14 | PROJECT.3.3.5.2.5.6.3 | MEP 2nd Fix-LB-07 A,LB-07 B,LB-07 C,LB-07 D
16 | PROJECT.3.3.5.2.5.6.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.6.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.6.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.6.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.6.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.6.4 | MEP Final Fix-LB-07 A,LB-07 B,LB-07 C,LB-07 D
16 | PROJECT.3.3.5.2.5.6.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.6.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.6.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.6.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.5.7 | LB-11A,11B,11C/Garbage Room SL 149/Compactor Room SL 148,150 (Zone 4 & 1)
14 | PROJECT.3.3.5.2.5.7.1 | General Civil Access Dates-LB-11A,11B,11C/Garbage Room SL 149/Compactor Room SL 148,150
14 | PROJECT.3.3.5.2.5.7.2 | MEP 1st Fix in Wall-LB-11A,11B,11C/Garbage Room SL 149/Compactor Room SL 148,150
14 | PROJECT.3.3.5.2.5.7.3 | MEP 2nd Fix-LB-11A,11B,11C/Garbage Room SL 149/Compactor Room SL 148,150
16 | PROJECT.3.3.5.2.5.7.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.7.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.7.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.7.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.7.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.7.4 | MEP Final Fix-LB-11A,11B,11C/Garbage Room SL 149/Compactor Room SL 148,150
16 | PROJECT.3.3.5.2.5.7.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.7.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.7.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.7.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.5.8 | LB-09 A,09 B,10C/Loading Deck/SLS S-002 & S-003 Room (Zone 12)
14 | PROJECT.3.3.5.2.5.8.1 | General Civil Access Dates-LB-09 A,09 B,10C/Loading Deck/SLS S-002 & S-003 Room
14 | PROJECT.3.3.5.2.5.8.2 | MEP 1st Fix in Wall-LB-09 A,09 B,10C/Loading Deck/SLS S-002 & S-003 Room
14 | PROJECT.3.3.5.2.5.8.3 | MEP 2nd Fix-LB-09 A,09 B,10C/Loading Deck/SLS S-002 & S-003 Room
16 | PROJECT.3.3.5.2.5.8.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.8.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.8.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.8.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.8.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.8.4 | MEP Final Fix-LB-09 A,09 B,10C/Loading Deck/SLS S-002 & S-003 Room
16 | PROJECT.3.3.5.2.5.8.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.8.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.8.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.8.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.5.9 | LB-10 A,10B,10C/Garbage Room SL 119 (Zone 7)
14 | PROJECT.3.3.5.2.5.9.1 | General Civil Access Dates-LB-10 A,10B,10C/Garbage Room SL 119
14 | PROJECT.3.3.5.2.5.9.2 | MEP 1st Fix in Wall-LB-10 A,10B,10C/Garbage Room SL 119
14 | PROJECT.3.3.5.2.5.9.3 | MEP 2nd Fix-LB-10 A,10B,10C/Garbage Room SL 119
16 | PROJECT.3.3.5.2.5.9.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.9.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.9.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.9.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.9.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.9.4 | MEP Final Fix-LB-10 A,10B,10C/Garbage Room SL 119
16 | PROJECT.3.3.5.2.5.9.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.9.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.9.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.9.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.5.10 | LB-08 A,LB-08 B,LB-08 C,LB-08 D,LB-08 E, LB-08 F/ Compactor Room SL 286 (Zone 12 &13)
14 | PROJECT.3.3.5.2.5.10.1 | General Civil Access Dates-LB-08 A,LB-08 B,LB-08 C,LB-08 D,LB-08 E, LB-08 F/ Compactor Room SL 286
14 | PROJECT.3.3.5.2.5.10.2 | MEP 1st Fix in Wall-LB-08 A,LB-08 B,LB-08 C,LB-08 D,LB-08 E, LB-08 F/ Compactor Room SL 286
14 | PROJECT.3.3.5.2.5.10.3 | MEP 2nd Fix-LB-08 A,LB-08 B,LB-08 C,LB-08 D,LB-08 E, LB-08 F/ Compactor Room SL 286
16 | PROJECT.3.3.5.2.5.10.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.10.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.5.10.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.5.10.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.10.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.5.10.4 | MEP Final Fix-LB-08 A,LB-08 B,LB-08 C,LB-08 D,LB-08 E, LB-08 F/ Compactor Room SL 286
16 | PROJECT.3.3.5.2.5.10.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.5.10.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.5.10.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.5.10.4.4 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.2.6 | Wet Areas
12 | PROJECT.3.3.5.2.6.1 | Pour Area A1 (Zone 1)
14 | PROJECT.3.3.5.2.6.1.1 | Toilets-SL-165
16 | PROJECT.3.3.5.2.6.1.1.1 | General Civil Access Dates-Toilets-SL-165
16 | PROJECT.3.3.5.2.6.1.1.2 | MEP 1st Fix in Wall-Toilets-SL-165
16 | PROJECT.3.3.5.2.6.1.1.3 | MEP 2nd Fix-Toilets-SL-165
18 | PROJECT.3.3.5.2.6.1.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.1.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.1.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.1.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.1.1.4 | MEP Final Fix-Toilets-SL-165
18 | PROJECT.3.3.5.2.6.1.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.1.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.1.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.1.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.2 | Pour Area A7 (Zone 3)
14 | PROJECT.3.3.5.2.6.2.1 | Combined Water Tank & Combined Pump Room SL-192
16 | PROJECT.3.3.5.2.6.2.1.1 | General Civil Access Dates-Pump Room SL-192
16 | PROJECT.3.3.5.2.6.2.1.2 | MEP 1st Fix in Wall-Pump Room SL-192
16 | PROJECT.3.3.5.2.6.2.1.3 | MEP 2nd Fix-Pump Room SL-192
18 | PROJECT.3.3.5.2.6.2.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.2.1.3.2 | CHW piping Works
18 | PROJECT.3.3.5.2.6.2.1.3.3 | Electrical Works
18 | PROJECT.3.3.5.2.6.2.1.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.2.1.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.2.1.4 | MEP Final Fix-Pump Room SL-192
18 | PROJECT.3.3.5.2.6.2.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.2.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.2.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.2.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.4 | Pour Area A8 (Zone 3)
14 | PROJECT.3.3.5.2.6.4.1 | Toilets-SL-199
16 | PROJECT.3.3.5.2.6.4.1.1 | General Civil Access Dates-Toilets-SL-199
16 | PROJECT.3.3.5.2.6.4.1.2 | MEP 1st Fix in Wall-Toilets-SL-199
16 | PROJECT.3.3.5.2.6.4.1.3 | MEP 2nd Fix-Toilets-SL-199
18 | PROJECT.3.3.5.2.6.4.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.4.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.4.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.4.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.4.1.4 | MEP Final Fix-Toilets-SL-199
18 | PROJECT.3.3.5.2.6.4.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.4.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.4.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.4.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.5 | Pour Area A5 (Zone 2 & 3)
14 | PROJECT.3.3.5.2.6.5.1 | Toilets-SL-179
16 | PROJECT.3.3.5.2.6.5.1.1 | General Civil Access Dates-Toilets-SL-179
16 | PROJECT.3.3.5.2.6.5.1.2 | MEP 1st Fix in Wall-Toilets-SL-179
16 | PROJECT.3.3.5.2.6.5.1.3 | MEP 2nd Fix-Toilets-SL-179
18 | PROJECT.3.3.5.2.6.5.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.5.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.5.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.5.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.5.1.4 | MEP Final Fix-Toilets-SL-179
18 | PROJECT.3.3.5.2.6.5.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.5.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.5.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.5.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.6 | Pour Area C7,C8 (Zone 13 &14)
14 | PROJECT.3.3.5.2.6.6.1 | Toilets-SL-285, SL-276
16 | PROJECT.3.3.5.2.6.6.1.1 | General Civil Access Dates-Toilets-SL-285, SL-276
16 | PROJECT.3.3.5.2.6.6.1.2 | MEP 1st Fix in Wall-Toilets-SL-285, SL-276
16 | PROJECT.3.3.5.2.6.6.1.3 | MEP 2nd Fix-Toilets-SL-285, SL-276
18 | PROJECT.3.3.5.2.6.6.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.6.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.6.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.6.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.6.1.4 | MEP Final Fix-Toilets-SL-285, SL-276
18 | PROJECT.3.3.5.2.6.6.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.6.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.6.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.6.1.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.6.6.2 | Storm Water Tank-02 & Pump Room SL-270
16 | PROJECT.3.3.5.2.6.6.2.1 | General Civil Access Dates-Pump Room SL-270
16 | PROJECT.3.3.5.2.6.6.2.2 | MEP 1st Fix in Wall-Pump Room SL-270
16 | PROJECT.3.3.5.2.6.6.2.3 | MEP 2nd Fix-Pump Room SL-270
18 | PROJECT.3.3.5.2.6.6.2.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.6.2.3.2 | CHW piping Works
18 | PROJECT.3.3.5.2.6.6.2.3.3 | Electrical Works
18 | PROJECT.3.3.5.2.6.6.2.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.6.2.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.6.2.4 | MEP Final Fix-Pump Room SL-270
18 | PROJECT.3.3.5.2.6.6.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.6.2.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.6.2.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.6.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.7 | Pour Area B12 (Zone 11)
14 | PROJECT.3.3.5.2.6.7.1 | Toilets-SL-229, SL-255
16 | PROJECT.3.3.5.2.6.7.1.1 | General Civil Access Dates-Toilets-SL-229, SL-255
16 | PROJECT.3.3.5.2.6.7.1.2 | MEP 1st Fix in Wall-Toilets-SL-229, SL-255
16 | PROJECT.3.3.5.2.6.7.1.3 | MEP 2nd Fix-Toilets-SL-229, SL-255
18 | PROJECT.3.3.5.2.6.7.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.7.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.7.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.7.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.7.1.4 | MEP Final Fix-Toilets-SL-229, SL-255
18 | PROJECT.3.3.5.2.6.7.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.7.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.7.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.7.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.8 | Pour Area B14 (Zone 6)
14 | PROJECT.3.3.5.2.6.8.1 | Gray Water Tank/ Gray Water Treatment Room/Irrigation tank & Pump Room SL-219
16 | PROJECT.3.3.5.2.6.8.1.1 | General Civil Access Dates-Pump Room SL-219
16 | PROJECT.3.3.5.2.6.8.1.2 | MEP 1st Fix in Wall-Pump Room SL-219
16 | PROJECT.3.3.5.2.6.8.1.3 | MEP 2nd Fix-Pump Room SL-219
18 | PROJECT.3.3.5.2.6.8.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.8.1.3.2 | CHW piping Works
18 | PROJECT.3.3.5.2.6.8.1.3.3 | Electrical Works
18 | PROJECT.3.3.5.2.6.8.1.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.8.1.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.8.1.4 | MEP Final Fix-Pump Room SL-219
18 | PROJECT.3.3.5.2.6.8.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.8.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.8.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.8.1.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.6.8.2 | Toilets-SL-214, SL-225
16 | PROJECT.3.3.5.2.6.8.2.1 | General Civil Access Dates-Toilets-SL-214, SL-225
16 | PROJECT.3.3.5.2.6.8.2.2 | MEP 1st Fix in Wall-Toilets-SL-214, SL-225
16 | PROJECT.3.3.5.2.6.8.2.3 | MEP 2nd Fix-Toilets-SL-214, SL-225
18 | PROJECT.3.3.5.2.6.8.2.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.8.2.3.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.8.2.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.8.2.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.8.2.4 | MEP Final Fix-Toilets-SL-214, SL-225
18 | PROJECT.3.3.5.2.6.8.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.8.2.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.8.2.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.8.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.9 | Pour Area B'14 (Zone 6)
14 | PROJECT.3.3.5.2.6.9.1 | Toilets-SL-223
16 | PROJECT.3.3.5.2.6.9.1.1 | General Civil Access Dates-Toilets-SL-223
16 | PROJECT.3.3.5.2.6.9.1.2 | MEP 1st Fix in Wall-Toilets-SL-223
16 | PROJECT.3.3.5.2.6.9.1.3 | MEP 2nd Fix-Toilets-SL-223
18 | PROJECT.3.3.5.2.6.9.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.9.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.9.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.9.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.9.1.4 | MEP Final Fix-Toilets-SL-223
18 | PROJECT.3.3.5.2.6.9.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.9.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.9.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.9.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.10 | Pour Area C1 (Zone 9)
14 | PROJECT.3.3.5.2.6.10.1 | Storm Water Tank-01 & Pump Room SL-105
16 | PROJECT.3.3.5.2.6.10.1.1 | General Civil Access Dates-Pump Room SL-105
16 | PROJECT.3.3.5.2.6.10.1.2 | MEP 1st Fix in Wall-Pump Room SL-105
16 | PROJECT.3.3.5.2.6.10.1.3 | MEP 2nd Fix-Pump Room SL-105
18 | PROJECT.3.3.5.2.6.10.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.10.1.3.2 | CHW piping Works
18 | PROJECT.3.3.5.2.6.10.1.3.3 | Electrical Works
18 | PROJECT.3.3.5.2.6.10.1.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.10.1.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.10.1.4 | MEP Final Fix-Pump Room SL-105
18 | PROJECT.3.3.5.2.6.10.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.10.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.10.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.10.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.11 | Pour Area C5 (Zone 12)
14 | PROJECT.3.3.5.2.6.11.1 | Toilets-SL-300
16 | PROJECT.3.3.5.2.6.11.1.1 | General Civil Access Dates-Toilets-SL-300
16 | PROJECT.3.3.5.2.6.11.1.2 | MEP 1st Fix in Wall-Toilets-SL-300
16 | PROJECT.3.3.5.2.6.11.1.3 | MEP 2nd Fix-Toilets-SL-300
18 | PROJECT.3.3.5.2.6.11.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.11.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.11.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.11.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.11.1.4 | MEP Final Fix-Toilets-SL-300
18 | PROJECT.3.3.5.2.6.11.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.11.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.11.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.11.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.12 | Pour Area B1 (Zone 4)
14 | PROJECT.3.3.5.2.6.12.1 | Toilets-SL-146
16 | PROJECT.3.3.5.2.6.12.1.1 | General Civil Access Dates-Toilets-SL-146
16 | PROJECT.3.3.5.2.6.12.1.2 | MEP 1st Fix in Wall-Toilets-SL-146
16 | PROJECT.3.3.5.2.6.12.1.3 | MEP 2nd Fix-Toilets-SL-146
18 | PROJECT.3.3.5.2.6.12.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.12.1.3.3 | Electrical Works
18 | PROJECT.3.3.5.2.6.12.1.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.12.1.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.12.1.4 | MEP Final Fix-Toilets-SL-146
18 | PROJECT.3.3.5.2.6.12.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.12.1.4.3 | Electrical Works
18 | PROJECT.3.3.5.2.6.12.1.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.12.1.4.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.2.6.13 | Pour Area B3 (Zone 7)
14 | PROJECT.3.3.5.2.6.13.1 | Toilets-SL-120
16 | PROJECT.3.3.5.2.6.13.1.1 | General Civil Access Dates-Toilets-SL-120
16 | PROJECT.3.3.5.2.6.13.1.2 | MEP 1st Fix in Wall-Toilets-SL-120
16 | PROJECT.3.3.5.2.6.13.1.3 | MEP 2nd Fix-Toilets-SL-120
18 | PROJECT.3.3.5.2.6.13.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.13.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.13.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.13.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.2.6.13.1.4 | MEP Final Fix-Toilets-SL-120
18 | PROJECT.3.3.5.2.6.13.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.2.6.13.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.2.6.13.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.2.6.13.1.4.4 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.2.7 | Drive Way SL-101/Lifts & Staircase Rooms/Lobby
12 | PROJECT.3.3.5.2.7.1 | Drive Way SL-101
14 | PROJECT.3.3.5.2.7.1.1 | General Civil Access Dates-Drive Way SL-101
14 | PROJECT.3.3.5.2.7.1.2 | MEP 1st Fix in Wall-Drive Way SL-101
14 | PROJECT.3.3.5.2.7.1.3 | MEP 2nd Fix-Drive Way SL-101
16 | PROJECT.3.3.5.2.7.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.2.7.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.2.7.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.2.7.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.2.7.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.2.7.1.4 | MEP Final Fix-Drive Way SL-101
16 | PROJECT.3.3.5.2.7.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.2.7.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.2.7.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.2.7.1.4.4 | Plumbing & Drainage Works
8 | PROJECT.3.3.5.3 | BASEMENT PARKING 2 (BP2)
10 | PROJECT.3.3.5.3.1 | SECTION-A
12 | PROJECT.3.3.5.3.1.1 | Car Parks
14 | PROJECT.3.3.5.3.1.1.1 | General Civil Access Dates-BP-2-Car Parks
14 | PROJECT.3.3.5.3.1.1.2 | MEP 1st Fix in Wall-BP-2-Car Parks
14 | PROJECT.3.3.5.3.1.1.3 | MEP 2nd Fix-BP-2-Car Parks
16 | PROJECT.3.3.5.3.1.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.3.1.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.3.1.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.3.1.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.3.1.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.3.1.1.4 | MEP Final Fix-BP-2-Car Parks
16 | PROJECT.3.3.5.3.1.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.3.1.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.3.1.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.3.1.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.3.1.2 | BP2-Lifts /Electrical Rooms/ FOH - LOBBY 06 - Zone 02
14 | PROJECT.3.3.5.3.1.2.1 | General Civil Access Dates-BP2-Lifts & Staircase Rooms/FOH - LOBBY 06 - Zone 02
14 | PROJECT.3.3.5.3.1.2.2 | MEP 1st Fix in Wall-BP2-Lifts & Staircase Rooms/FOH - LOBBY 06 - Zone 02
14 | PROJECT.3.3.5.3.1.2.3 | MEP 2nd Fix-BP2-Lifts Rooms/FOH - LOBBY 06 - Zone 02
16 | PROJECT.3.3.5.3.1.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.3.1.2.3.2 | CHW piping Works
16 | PROJECT.3.3.5.3.1.2.3.3 | Electrical Works
16 | PROJECT.3.3.5.3.1.2.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.3.1.2.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.3.1.2.4 | MEP Final Fix-BP2-Lifts & Staircase Rooms/FOH - LOBBY 06 - Zone 02
16 | PROJECT.3.3.5.3.1.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.3.1.2.4.2 | Electrical Works
16 | PROJECT.3.3.5.3.1.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.3.1.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.3.1.6 | STAIRCASES SL/BP2-BP1
14 | PROJECT.3.3.5.3.1.6.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.3.1.6.1 | ACCESS STAIRCASES ST11, ST12, ST48
10 | PROJECT.3.3.5.3.2 | SECTION-B
12 | PROJECT.3.3.5.3.2.1 | Car Parks
14 | PROJECT.3.3.5.3.2.1.1 | General Civil Access Dates-BP-2-Car Parks
14 | PROJECT.3.3.5.3.2.1.2 | MEP 1st Fix in Wall-BP-2-Car Parks
14 | PROJECT.3.3.5.3.2.1.3 | MEP 2nd Fix-BP-2-Car Parks
16 | PROJECT.3.3.5.3.2.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.3.2.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.3.2.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.3.2.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.3.2.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.3.2.1.4 | MEP Final Fix-BP-2-Car Parks
16 | PROJECT.3.3.5.3.2.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.3.2.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.3.2.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.3.2.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.3.2.6 | FOH LOBBIES
14 | PROJECT.3.3.5.3.2.6.3 | BP2-Lifts /Electrical Rooms/ LOBBY 02 Zone 07&09
16 | PROJECT.3.3.5.3.2.6.3.1 | General Civil Access Dates-BP2-Lifts /Electrical Rooms/ LOBBY 02 Zone 07&09
16 | PROJECT.3.3.5.3.2.6.3.2 | MEP 1st Fix in Wall-BP2-Lifts /Electrical Rooms/ LOBBY 02 Zone 07&09
16 | PROJECT.3.3.5.3.2.6.3.3 | MEP 2nd Fix-BP2-Lifts /Electrical Rooms/ LOBBY 02 Zone 07&09
18 | PROJECT.3.3.5.3.2.6.3.3.1 | HVAC Works
18 | PROJECT.3.3.5.3.2.6.3.3.2 | CHW piping Works
18 | PROJECT.3.3.5.3.2.6.3.3.3 | Electrical Works
18 | PROJECT.3.3.5.3.2.6.3.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.3.2.6.3.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.3.2.6.3.4 | MEP Final Fix-BP2-Lifts /Electrical Rooms/ LOBBY 02 Zone 07&09
18 | PROJECT.3.3.5.3.2.6.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.3.2.6.3.4.2 | Electrical Works
18 | PROJECT.3.3.5.3.2.6.3.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.3.2.6.3.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.3.2.6.2 | BP2-Lifts /Electrical Rooms/ LOBBY 01 Zone 04
16 | PROJECT.3.3.5.3.2.6.2.1 | General Civil Access Dates-BP2-Lifts /Electrical Rooms/ LOBBY 01 Zone 04
16 | PROJECT.3.3.5.3.2.6.2.2 | MEP 1st Fix in Wall-BP2-Lifts /Electrical Rooms/ LOBBY 01 Zone 04
16 | PROJECT.3.3.5.3.2.6.2.3 | MEP 2nd Fix-BP2-Lifts /Electrical Rooms/ LOBBY 01 Zone 04
18 | PROJECT.3.3.5.3.2.6.2.3.1 | HVAC Works
18 | PROJECT.3.3.5.3.2.6.2.3.2 | CHW piping Works
18 | PROJECT.3.3.5.3.2.6.2.3.3 | Electrical Works
18 | PROJECT.3.3.5.3.2.6.2.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.3.2.6.2.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.3.2.6.2.4 | MEP Final Fix-BP2-Lifts /Electrical Rooms/ LOBBY 01 Zone 04
18 | PROJECT.3.3.5.3.2.6.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.3.2.6.2.4.2 | Electrical Works
18 | PROJECT.3.3.5.3.2.6.2.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.3.2.6.2.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.3.2.6.4 | BP2-Lifts /Electrical Rooms/ LOBBY 04 Zone 11
16 | PROJECT.3.3.5.3.2.6.4.1 | General Civil Access Dates-BP2-Lifts /Electrical Rooms/ LOBBY 04 Zone 11
16 | PROJECT.3.3.5.3.2.6.4.2 | MEP 1st Fix in Wall-BP2-Lifts /Electrical Rooms/ LOBBY 04 Zone 11
16 | PROJECT.3.3.5.3.2.6.4.3 | MEP 2nd Fix-BP2-Lifts /Electrical Rooms/ LOBBY 04 Zone 11
18 | PROJECT.3.3.5.3.2.6.4.3.1 | HVAC Works
18 | PROJECT.3.3.5.3.2.6.4.3.2 | CHW piping Works
18 | PROJECT.3.3.5.3.2.6.4.3.3 | Electrical Works
18 | PROJECT.3.3.5.3.2.6.4.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.3.2.6.4.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.3.2.6.4.4 | MEP Final Fix-BP2-Lifts /Electrical Rooms/ LOBBY 04 Zone 11
18 | PROJECT.3.3.5.3.2.6.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.3.2.6.4.4.2 | Electrical Works
18 | PROJECT.3.3.5.3.2.6.4.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.3.2.6.4.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.3.2.6.5 | BP2-Lifts /Electrical Rooms/ LOBBY 05 Zone 06
16 | PROJECT.3.3.5.3.2.6.5.1 | General Civil Access Dates-BP2-Lifts /Electrical Rooms/ LOBBY 05 Zone 06
16 | PROJECT.3.3.5.3.2.6.5.2 | MEP 1st Fix in Wall-BP2-Lifts /Electrical Rooms/ LOBBY 05 Zone 06
16 | PROJECT.3.3.5.3.2.6.5.3 | MEP 2nd Fix-BP2-Lifts /Electrical Rooms/ LOBBY 05 Zone 06
18 | PROJECT.3.3.5.3.2.6.5.3.1 | HVAC Works
18 | PROJECT.3.3.5.3.2.6.5.3.2 | CHW piping Works
18 | PROJECT.3.3.5.3.2.6.5.3.3 | Electrical Works
18 | PROJECT.3.3.5.3.2.6.5.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.3.2.6.5.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.3.2.6.5.4 | MEP Final Fix-BP2-Lifts /Electrical Rooms/ LOBBY 05 Zone 06
18 | PROJECT.3.3.5.3.2.6.5.4.1 | HVAC Works
18 | PROJECT.3.3.5.3.2.6.5.4.2 | Electrical Works
18 | PROJECT.3.3.5.3.2.6.5.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.3.2.6.5.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.3.2.9 | STAIRCASES SL/BP2-BP1
14 | PROJECT.3.3.5.3.2.9.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.3.2.9.1 | ACCESS STAIRCASES ST16, ST18
10 | PROJECT.3.3.5.3.3 | SECTION-C
12 | PROJECT.3.3.5.3.3.1 | Car Parks
14 | PROJECT.3.3.5.3.3.1.1 | General Civil Access Dates-BP-2-Car Parks
14 | PROJECT.3.3.5.3.3.1.2 | MEP 1st Fix in Wall-BP-2-Car Parks
14 | PROJECT.3.3.5.3.3.1.3 | MEP 2nd Fix-BP-2-Car Parks
16 | PROJECT.3.3.5.3.3.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.3.3.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.3.3.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.3.3.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.3.3.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.3.3.1.4 | MEP Final Fix-BP-2-Car Parks
16 | PROJECT.3.3.5.3.3.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.3.3.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.3.3.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.3.3.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.3.3.2 | BP2-Lifts /Electrical Rooms/FOH LOBBY 03 Zone 10
14 | PROJECT.3.3.5.3.3.2.1 | General Civil Access Dates-BP2-Lifts /Electrical Rooms/FOH LOBBY 03 Zone 10
14 | PROJECT.3.3.5.3.3.2.2 | MEP 1st Fix in Wall-BP2-Lifts /Electrical Rooms/FOH LOBBY 03 Zone 10
14 | PROJECT.3.3.5.3.3.2.3 | MEP 2nd Fix-BP2-Lifts /Electrical Rooms/FOH LOBBY 03 Zone 10
16 | PROJECT.3.3.5.3.3.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.3.3.2.3.2 | CHW piping Works
16 | PROJECT.3.3.5.3.3.2.3.3 | Electrical Works
16 | PROJECT.3.3.5.3.3.2.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.3.3.2.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.3.3.2.4 | MEP Final Fix-BP2-Lifts /Electrical Rooms/FOH LOBBY 03 Zone 10
16 | PROJECT.3.3.5.3.3.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.3.3.2.4.2 | Electrical Works
16 | PROJECT.3.3.5.3.3.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.3.3.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.3.3.8 | STAIRCASES SL/BP2-BP1
14 | PROJECT.3.3.5.3.3.8.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.3.3.8.1 | ACCESS STAIRCASES ST23, ST26, ST35
8 | PROJECT.3.3.5.4 | BASEMENT PARKING 1 (BP1)
10 | PROJECT.3.3.5.4.3 | SECTION A
12 | PROJECT.3.3.5.4.3.1 | Car Parks (BP1)
14 | PROJECT.3.3.5.4.3.1.1 | General Civil Access Dates-Car Parks (BP1)
14 | PROJECT.3.3.5.4.3.1.2 | MEP 1st Fix in Wall-Car Parks (BP1)
14 | PROJECT.3.3.5.4.3.1.3 | MEP 2nd Fix-Car Parks (BP1)
16 | PROJECT.3.3.5.4.3.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.4.3.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.4.3.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.4.3.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.4.3.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.3.1.4 | MEP Final Fix-Car Parks (BP1)
16 | PROJECT.3.3.5.4.3.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.4.3.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.4.3.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.4.3.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.4.3.2 | BOH
14 | PROJECT.3.3.5.4.3.2.1 | CPF Rooms
16 | PROJECT.3.3.5.4.3.2.1.1 | BP1-CPF RM-114
18 | PROJECT.3.3.5.4.3.2.1.1.1 | General Civil Access Dates-BP1-CPF RM-114
18 | PROJECT.3.3.5.4.3.2.1.1.2 | MEP 1st Fix in Wall-BP1-CPF RM-114
18 | PROJECT.3.3.5.4.3.2.1.1.3 | MEP 2nd Fix-BP1-CPF RM-114
20 | PROJECT.3.3.5.4.3.2.1.1.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.1.1.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.3.2.1.1.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.1.1.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.1.1.3.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.4.3.2.1.1.4 | MEP Final Fix-BP1-CPF RM-114
20 | PROJECT.3.3.5.4.3.2.1.1.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.1.1.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.1.1.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.1.1.4.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.3.2.1.2 | BP1-CPF RM-111
18 | PROJECT.3.3.5.4.3.2.1.2.1 | General Civil Access Dates-BP1-CPF RM-111
18 | PROJECT.3.3.5.4.3.2.1.2.2 | MEP 1st Fix in Wall-BP1-CPF RM-111
18 | PROJECT.3.3.5.4.3.2.1.2.3 | MEP 2nd Fix-BP1-CPF RM-111
20 | PROJECT.3.3.5.4.3.2.1.2.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.1.2.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.3.2.1.2.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.1.2.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.1.2.3.5 | Plumbing & Drainage Works
20 | PROJECT.3.3.5.4.3.2.1.2.3.6 | Water Supply Works
18 | PROJECT.3.3.5.4.3.2.1.2.4 | MEP Final Fix-BP1-CPF RM-111
20 | PROJECT.3.3.5.4.3.2.1.2.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.1.2.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.1.2.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.1.2.4.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.3.2.1.3 | BP1-CPF RM-109
18 | PROJECT.3.3.5.4.3.2.1.3.1 | General Civil Access Dates-BP1-CPF RM-109
18 | PROJECT.3.3.5.4.3.2.1.3.2 | MEP 1st Fix in Wall-BP1-CPF RM-109
18 | PROJECT.3.3.5.4.3.2.1.3.3 | MEP 2nd Fix-BP1-CPF RM-109
20 | PROJECT.3.3.5.4.3.2.1.3.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.1.3.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.3.2.1.3.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.1.3.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.1.3.3.5 | Plumbing & Drainage Works
20 | PROJECT.3.3.5.4.3.2.1.3.3.6 | Water Supply Works
18 | PROJECT.3.3.5.4.3.2.1.3.4 | MEP Final Fix-BP1-CPF RM-109
20 | PROJECT.3.3.5.4.3.2.1.3.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.1.3.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.1.3.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.1.3.4.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.3.2.1.9 | BP1-CPF RM-126 & 123
18 | PROJECT.3.3.5.4.3.2.1.9.1 | General Civil Access Dates-CPF RM-126 & 123
18 | PROJECT.3.3.5.4.3.2.1.9.2 | MEP 1st Fix in Wall-CPF RM-126 & 123
18 | PROJECT.3.3.5.4.3.2.1.9.3 | MEP 2nd Fix-CPF RM-126 & 123
20 | PROJECT.3.3.5.4.3.2.1.9.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.1.9.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.3.2.1.9.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.1.9.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.1.9.3.5 | Plumbing & Drainage Works
20 | PROJECT.3.3.5.4.3.2.1.9.3.6 | Water Supply Works
18 | PROJECT.3.3.5.4.3.2.1.9.4 | MEP Final Fix-CPF RM-126 & 123
20 | PROJECT.3.3.5.4.3.2.1.9.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.1.9.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.1.9.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.1.9.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.3.2.2 | Electrical/ELV Rooms
16 | PROJECT.3.3.5.4.3.2.2.1 | BP1 206/UTT RM/BMS RM/LED RM/ Lift room BP1
18 | PROJECT.3.3.5.4.3.2.2.1.1 | General Civil Access Dates-Electrical Room SL-206
18 | PROJECT.3.3.5.4.3.2.2.1.2 | MEP 1st Fix in Wall-Electrical Room SL-206
18 | PROJECT.3.3.5.4.3.2.2.1.3 | MEP 2nd Fix-Electrical Room SL-206
20 | PROJECT.3.3.5.4.3.2.2.1.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.2.1.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.3.2.2.1.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.2.1.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.2.1.3.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.4.3.2.2.1.4 | MEP Final Fix-Electrical Room SL-206
20 | PROJECT.3.3.5.4.3.2.2.1.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.3.2.2.1.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.3.2.2.1.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.3.2.2.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.4.3.3 | FOH: LOBBIES
14 | PROJECT.3.3.5.4.3.3.7 | UTT RM BP 207/ BMS RM/LOBBY 6 - Zone 02
16 | PROJECT.3.3.5.4.3.3.7.1 | General Civil Access Dates-UTT RM BP 207/ BMS RM/LOBBY 6 - Zone 02
16 | PROJECT.3.3.5.4.3.3.7.2 | MEP 1st Fix in Wall-UTT RM BP 207/ BMS RM/LOBBY 6 - Zone 02
16 | PROJECT.3.3.5.4.3.3.7.3 | MEP 2nd Fix-UTT RM BP 207/ BMS RM/LOBBY 6 - Zone 02
18 | PROJECT.3.3.5.4.3.3.7.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.3.3.7.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.3.3.7.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.3.3.7.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.3.3.7.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.3.3.7.4 | MEP Final Fix-UTT RM BP 207/ BMS RM/LOBBY 6 - Zone 02
18 | PROJECT.3.3.5.4.3.3.7.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.3.3.7.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.3.3.7.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.3.3.7.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.3.3.4 | LOBBY 7 (Entrance West) Zone 01
16 | PROJECT.3.3.5.4.3.3.4.1 | General Civil Access Dates-LOBBY 7 (Entrance West) Zone 01
16 | PROJECT.3.3.5.4.3.3.4.2 | MEP 1st Fix in Wall-LOBBY 7 (Entrance West) Zone 01
16 | PROJECT.3.3.5.4.3.3.4.3 | MEP 2nd Fix-LOBBY 7 (Entrance West) Zone 01
18 | PROJECT.3.3.5.4.3.3.4.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.3.3.4.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.3.3.4.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.3.3.4.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.3.3.4.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.3.3.4.4 | MEP Final Fix-LOBBY 7 (Entrance West) Zone 01
18 | PROJECT.3.3.5.4.3.3.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.3.3.4.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.3.3.4.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.3.3.4.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.4.3.7 | STAIRCASES BP1-GF
14 | PROJECT.3.3.5.4.3.7.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.4.3.7.1 | ACCESS STAIRCASES ST11, ST12, ST48
10 | PROJECT.3.3.5.4.1 | SECTION B
12 | PROJECT.3.3.5.4.1.1 | Car Parks (BP1)
14 | PROJECT.3.3.5.4.1.1.1 | General Civil Access Dates-Car Parks (BP1)
14 | PROJECT.3.3.5.4.1.1.2 | MEP 1st Fix in Wall-Car Parks (BP1)
14 | PROJECT.3.3.5.4.1.1.3 | MEP 2nd Fix-Car Parks (BP1)
16 | PROJECT.3.3.5.4.1.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.4.1.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.4.1.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.4.1.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.4.1.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.1.1.4 | MEP Final Fix-Car Parks (BP1)
16 | PROJECT.3.3.5.4.1.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.4.1.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.4.1.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.4.1.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.4.1.3 | FOH: LOBBIES
14 | PROJECT.3.3.5.4.1.3.6 | UTT RM BP1- 221, 203/BMS RM/LOBBY 01 Zone 04
16 | PROJECT.3.3.5.4.1.3.6.1 | General Civil Access Dates-UTT RM BP1- 221, 203/BMS RM/LOBBY 01 Zone
16 | PROJECT.3.3.5.4.1.3.6.2 | MEP 1st Fix in Wall-UTT RM BP1- 221, 203/BMS RM/LOBBY 01 Zone
16 | PROJECT.3.3.5.4.1.3.6.3 | MEP 2nd Fix-UTT RM BP1- 221, 203/BMS RM/LOBBY 01 Zone
18 | PROJECT.3.3.5.4.1.3.6.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.6.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.1.3.6.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.6.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.6.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.3.6.4 | MEP Final Fix-UTT RM BP1- 221, 203/BMS RM/LOBBY 01 Zone
18 | PROJECT.3.3.5.4.1.3.6.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.6.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.6.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.6.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.1.3.5 | UTT RM BP1- 221, 203/BMS RM/LOBBY 02 Zone 09
16 | PROJECT.3.3.5.4.1.3.5.1 | General Civil Access Dates-UTT RM BP1- 221, 203/BMS RM/LOBBY 02 Zone
16 | PROJECT.3.3.5.4.1.3.5.2 | MEP 1st Fix in Wall-UTT RM BP1- 221, 203/BMS RM/LOBBY 02 Zone
16 | PROJECT.3.3.5.4.1.3.5.3 | MEP 2nd Fix-UTT RM BP1- 221, 203/BMS RM/LOBBY 02 Zone
18 | PROJECT.3.3.5.4.1.3.5.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.5.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.1.3.5.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.5.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.5.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.3.5.4 | MEP Final Fix-UTT RM BP1- 221, 203/BMS RM/LOBBY 02 Zone
18 | PROJECT.3.3.5.4.1.3.5.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.5.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.5.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.5.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.1.3.7 | UTT RM BP1- 221, 203/BMS RM/LOBBY 04 Zone 11
16 | PROJECT.3.3.5.4.1.3.7.1 | General Civil Access Dates-UTT RM BP1- 221, 203/BMS RM/LOBBY 04 Zone
16 | PROJECT.3.3.5.4.1.3.7.2 | MEP 1st Fix in Wall-UTT RM BP1- 221, 203/BMS RM/LOBBY 04 Zone
16 | PROJECT.3.3.5.4.1.3.7.3 | MEP 2nd Fix-UTT RM BP1- 221, 203/BMS RM/LOBBY 04 Zone
18 | PROJECT.3.3.5.4.1.3.7.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.7.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.1.3.7.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.7.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.7.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.3.7.4 | MEP Final Fix-UTT RM BP1- 221, 203/BMS RM/LOBBY 04 Zone
18 | PROJECT.3.3.5.4.1.3.7.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.7.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.7.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.7.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.1.3.8 | UTT RM BP1- 221, 203/BMS RM/LOBBY 05 Zone 06
16 | PROJECT.3.3.5.4.1.3.8.1 | General Civil Access Dates-UTT RM BP1- 221, 203/BMS RM/LOBBY 05 Zone
16 | PROJECT.3.3.5.4.1.3.8.2 | MEP 1st Fix in Wall-UTT RM BP1- 221, 203/BMS RM/LOBBY 05 Zone
16 | PROJECT.3.3.5.4.1.3.8.3 | MEP 2nd Fix-UTT RM BP1- 221, 203/BMS RM/LOBBY 05 Zone
18 | PROJECT.3.3.5.4.1.3.8.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.8.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.1.3.8.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.8.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.8.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.3.8.4 | MEP Final Fix-UTT RM BP1- 221, 203/BMS RM/LOBBY 05 Zone
18 | PROJECT.3.3.5.4.1.3.8.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.8.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.8.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.8.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.1.3.9 | LOBBY 08 (Mangrove North Entrance) Zone 07
16 | PROJECT.3.3.5.4.1.3.9.1 | General Civil Access Dates-LOBBY 08 (Mangrove North Entrance) Zone 07
16 | PROJECT.3.3.5.4.1.3.9.2 | MEP 1st Fix in Wall-LOBBY 08 (Mangrove North Entrance) Zone 07
16 | PROJECT.3.3.5.4.1.3.9.3 | MEP 2nd Fix-LOBBY 08 (Mangrove North Entrance) Zone 07
18 | PROJECT.3.3.5.4.1.3.9.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.9.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.1.3.9.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.9.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.9.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.3.9.4 | MEP Final Fix-LOBBY 08 (Mangrove North Entrance) Zone 07
18 | PROJECT.3.3.5.4.1.3.9.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.9.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.9.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.9.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.1.3.10 | LOBBY 09 (Main Entrance Mangrove South) Zone 06
16 | PROJECT.3.3.5.4.1.3.10.1 | General Civil Access Dates-LOBBY 09 (Main Entrance Mangrove South) Zone 06
16 | PROJECT.3.3.5.4.1.3.10.2 | MEP 1st Fix in Wall-LOBBY 09 (Main Entrance Mangrove South) Zone 06
16 | PROJECT.3.3.5.4.1.3.10.3 | MEP 2nd Fix-LOBBY 09 (Main Entrance Mangrove South) Zone 06
18 | PROJECT.3.3.5.4.1.3.10.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.10.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.1.3.10.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.10.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.10.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.3.10.4 | MEP Final Fix-LOBBY 09 (Main Entrance Mangrove South) Zone 06
18 | PROJECT.3.3.5.4.1.3.10.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.3.10.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.1.3.10.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.3.10.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.4.1.2 | BOH
14 | PROJECT.3.3.5.4.1.2.1 | CPF Rooms
16 | PROJECT.3.3.5.4.1.2.1.1 | BP1-CPF RM-101 & 102
18 | PROJECT.3.3.5.4.1.2.1.1.1 | General Civil Access Dates-BP1-CPF RM-101&102
18 | PROJECT.3.3.5.4.1.2.1.1.2 | MEP 1st Fix in Wall-BP1-CPF RM-101&102
18 | PROJECT.3.3.5.4.1.2.1.1.3 | MEP 2nd Fix-BP1-CPF RM-101&102
20 | PROJECT.3.3.5.4.1.2.1.1.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.1.1.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.1.1.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.1.1.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.1.1.3.5 | Plumbing & Drainage Works
20 | PROJECT.3.3.5.4.1.2.1.1.3.6 | Water Supply Works
18 | PROJECT.3.3.5.4.1.2.1.1.4 | MEP Final Fix-BP1-CPF RM-101&102
20 | PROJECT.3.3.5.4.1.2.1.1.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.1.1.4.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.1.1.4.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.1.1.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.1.2 | BP1-CPF RM-172 & 228
18 | PROJECT.3.3.5.4.1.2.1.2.1 | General Civil Access Dates-CPF RM-172 & 228
18 | PROJECT.3.3.5.4.1.2.1.2.2 | MEP 1st Fix in Wall-CPF RM-172 & 228
18 | PROJECT.3.3.5.4.1.2.1.2.3 | MEP 2nd Fix-CPF RM-172 & 228
20 | PROJECT.3.3.5.4.1.2.1.2.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.1.2.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.1.2.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.1.2.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.1.2.3.5 | Plumbing & Drainage Works
20 | PROJECT.3.3.5.4.1.2.1.2.3.6 | Water Supply Works
18 | PROJECT.3.3.5.4.1.2.1.2.4 | MEP Final Fix-CPF RM-172 & 228
20 | PROJECT.3.3.5.4.1.2.1.2.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.1.2.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.1.2.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.1.2.4.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.1.3 | BP1-CPF RM-170 & 169
18 | PROJECT.3.3.5.4.1.2.1.3.1 | General Civil Access Dates-CPF RM-170 & 169
18 | PROJECT.3.3.5.4.1.2.1.3.2 | MEP 1st Fix in Wall-CPF RM-170 & 169
18 | PROJECT.3.3.5.4.1.2.1.3.3 | MEP 2nd Fix-CPF RM-170 & 169
20 | PROJECT.3.3.5.4.1.2.1.3.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.1.3.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.1.3.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.1.3.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.1.3.3.5 | Plumbing & Drainage Works
20 | PROJECT.3.3.5.4.1.2.1.3.3.6 | Water Supply Works
18 | PROJECT.3.3.5.4.1.2.1.3.4 | MEP Final Fix-CPF RM-170 & 169
20 | PROJECT.3.3.5.4.1.2.1.3.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.1.3.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.1.3.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.1.3.4.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.1.4 | BP1-CPF RM-134,144 & 137
18 | PROJECT.3.3.5.4.1.2.1.4.1 | General Civil Access Dates-CPF RM-134,144 & 137
18 | PROJECT.3.3.5.4.1.2.1.4.2 | MEP 1st Fix in Wall-CPF RM-134,144 & 137
18 | PROJECT.3.3.5.4.1.2.1.4.3 | MEP 2nd Fix-CPF RM-134,144 & 137
20 | PROJECT.3.3.5.4.1.2.1.4.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.1.4.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.1.4.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.1.4.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.1.4.3.5 | Plumbing & Drainage Works
20 | PROJECT.3.3.5.4.1.2.1.4.3.6 | Water Supply Works
18 | PROJECT.3.3.5.4.1.2.1.4.4 | MEP Final Fix-CPF RM-134,144 & 137
20 | PROJECT.3.3.5.4.1.2.1.4.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.1.4.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.1.4.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.1.4.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.1.2.2 | Electrical/ELV Rooms
16 | PROJECT.3.3.5.4.1.2.2.1 | Electrical Room-BP1 106/UTT RM/BMS RM/LED RM/ Staircase/Lift room BP1
18 | PROJECT.3.3.5.4.1.2.2.1.1 | General Civil Access Dates-Electrical Room SL-106
18 | PROJECT.3.3.5.4.1.2.2.1.2 | MEP 1st Fix in Wall-Electrical Room SL-106
18 | PROJECT.3.3.5.4.1.2.2.1.3 | MEP 2nd Fix-Electrical Room SL-106
20 | PROJECT.3.3.5.4.1.2.2.1.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.1.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.2.1.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.1.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.1.3.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.4.1.2.2.1.4 | MEP Final Fix-Electrical Room SL-106
20 | PROJECT.3.3.5.4.1.2.2.1.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.1.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.1.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.1.4.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.2.2 | Electrical Room-BP1 174/UTT RM/BMS RM/BATRM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.4.1.2.2.2.1 | General Civil Access Dates-Electrical Room SL-174
18 | PROJECT.3.3.5.4.1.2.2.2.2 | MEP 1st Fix in Wall-Electrical Room SL-174
18 | PROJECT.3.3.5.4.1.2.2.2.3 | MEP 2nd Fix-Electrical Room SL-174
20 | PROJECT.3.3.5.4.1.2.2.2.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.2.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.2.2.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.2.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.2.3.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.4.1.2.2.2.4 | MEP Final Fix-Electrical Room SL-174
20 | PROJECT.3.3.5.4.1.2.2.2.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.2.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.2.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.2.4.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.2.4 | Electrical Room-BP1 141/UTT RM/BMS RM/BATRM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.4.1.2.2.4.1 | General Civil Access Dates-Electrical Room SL-141
18 | PROJECT.3.3.5.4.1.2.2.4.2 | MEP 1st Fix in Wall-Electrical Room SL-141
18 | PROJECT.3.3.5.4.1.2.2.4.3 | MEP 2nd Fix-Electrical Room SL-141
20 | PROJECT.3.3.5.4.1.2.2.4.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.4.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.2.4.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.4.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.4.3.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.4.1.2.2.4.4 | MEP Final Fix-Electrical Room SL-141
20 | PROJECT.3.3.5.4.1.2.2.4.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.4.4.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.4.4.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.4.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.2.5 | Electrical Room-BP1-131/UTT RM/BMS RM/BATRM/Lobby/Staircase/Lift room/Corridor
18 | PROJECT.3.3.5.4.1.2.2.5.1 | General Civil Access Dates-Electrical Room BP1-131
18 | PROJECT.3.3.5.4.1.2.2.5.2 | MEP 1st Fix in Wall-Electrical Room BP1-131
18 | PROJECT.3.3.5.4.1.2.2.5.3 | MEP 2nd Fix-Electrical Room BP1-131
20 | PROJECT.3.3.5.4.1.2.2.5.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.5.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.2.5.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.5.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.5.3.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.4.1.2.2.5.4 | MEP Final Fix-Electrical Room BP1-131
20 | PROJECT.3.3.5.4.1.2.2.5.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.5.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.5.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.5.4.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.2.6 | Electrical Room-BP1-213/UTT RM/BMS RM/BATRM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.4.1.2.2.6.1 | General Civil Access Dates-Electrical Room-BP1-213
18 | PROJECT.3.3.5.4.1.2.2.6.2 | MEP 1st Fix in Wall-Electrical Room-BP1-213
18 | PROJECT.3.3.5.4.1.2.2.6.3 | MEP 2nd Fix-Electrical Room-BP1-213
20 | PROJECT.3.3.5.4.1.2.2.6.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.6.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.2.6.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.6.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.6.3.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.4.1.2.2.6.4 | MEP Final Fix-Electrical Room-BP1-213
20 | PROJECT.3.3.5.4.1.2.2.6.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.6.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.6.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.6.4.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.2.7 | Electrical Room-BP1 216/UTT RM/BMS RM/BATRM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.4.1.2.2.7.1 | General Civil Access Dates-Electrical Room SL-216
18 | PROJECT.3.3.5.4.1.2.2.7.2 | MEP 1st Fix in Wall-Electrical Room SL-216
18 | PROJECT.3.3.5.4.1.2.2.7.3 | MEP 2nd Fix-Electrical Room SL-216
20 | PROJECT.3.3.5.4.1.2.2.7.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.7.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.1.2.2.7.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.7.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.7.3.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.4.1.2.2.7.4 | MEP Final Fix-Electrical Room SL-216
20 | PROJECT.3.3.5.4.1.2.2.7.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.1.2.2.7.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.1.2.2.7.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.1.2.2.7.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.1.2.3 | BP1-Water feature Pump Room-229
16 | PROJECT.3.3.5.4.1.2.3.1 | General Civil Access Dates-BP1-Water feature Pump Room-229
16 | PROJECT.3.3.5.4.1.2.3.2 | MEP 1st Fix in Wall-BP1-Water feature Pump Room-229
16 | PROJECT.3.3.5.4.1.2.3.3 | MEP 2nd Fix-BP1-Water feature Pump Room-229
18 | PROJECT.3.3.5.4.1.2.3.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.2.3.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.1.2.3.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.1.2.3.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.2.3.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.3.4 | MEP Final Fix-BP1-Water feature Pump Room-229
18 | PROJECT.3.3.5.4.1.2.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.2.3.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.1.2.3.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.2.3.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.1.2.4 | BP1-Water feature Pump Room-230
16 | PROJECT.3.3.5.4.1.2.4.1 | General Civil Access Dates-BP1-Water feature Pump Room-230
16 | PROJECT.3.3.5.4.1.2.4.2 | MEP 1st Fix in Wall-BP1-Water feature Pump Room-230
16 | PROJECT.3.3.5.4.1.2.4.3 | MEP 2nd Fix-BP1-Water feature Pump Room-230
18 | PROJECT.3.3.5.4.1.2.4.3.11 | HVAC Works
18 | PROJECT.3.3.5.4.1.2.4.3.22 | CHW piping Works
18 | PROJECT.3.3.5.4.1.2.4.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.1.2.4.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.2.4.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.1.2.4.4 | MEP Final Fix-BP1-Water feature Pump Room-230
18 | PROJECT.3.3.5.4.1.2.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.1.2.4.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.1.2.4.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.1.2.4.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.4.1.11 | STAIRCASES BP-GF
14 | PROJECT.3.3.5.4.1.11.1 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.4.1.11.4 | ACCESS STAIRCASES S16, ST18(36)
10 | PROJECT.3.3.5.4.2 | SECTION C
12 | PROJECT.3.3.5.4.2.1 | Car Parks (BP1)
14 | PROJECT.3.3.5.4.2.1.1 | General Civil Access Dates-Car Parks (BP1)
14 | PROJECT.3.3.5.4.2.1.2 | MEP 1st Fix in Wall-Car Parks (BP1)
14 | PROJECT.3.3.5.4.2.1.3 | MEP 2nd Fix-Car Parks (BP1)
16 | PROJECT.3.3.5.4.2.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.4.2.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.4.2.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.4.2.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.4.2.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.2.1.4 | MEP Final Fix-Car Parks (BP1)
16 | PROJECT.3.3.5.4.2.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.4.2.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.4.2.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.4.2.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.4.2.2 | BOH
14 | PROJECT.3.3.5.4.2.2.1 | CPF Rooms
16 | PROJECT.3.3.5.4.2.2.1.7 | BP1-CPF RM-152 & 146
18 | PROJECT.3.3.5.4.2.2.1.7.1 | General Civil Access Dates-CPF RM-152 & 146
18 | PROJECT.3.3.5.4.2.2.1.7.2 | MEP 1st Fix in Wall-CPF RM-152 & 146
18 | PROJECT.3.3.5.4.2.2.1.7.3 | MEP 2nd Fix-CPF RM-152 & 146
20 | PROJECT.3.3.5.4.2.2.1.7.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.2.2.1.7.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.2.2.1.7.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.2.2.1.7.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.2.2.1.7.3.5 | Plumbing & Drainage Works
20 | PROJECT.3.3.5.4.2.2.1.7.3.6 | Water Supply Works
18 | PROJECT.3.3.5.4.2.2.1.7.4 | MEP Final Fix-CPF RM-152 & 146
20 | PROJECT.3.3.5.4.2.2.1.7.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.2.2.1.7.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.2.2.1.7.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.2.2.1.7.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.2.2.2 | Electrical/ELV Rooms
16 | PROJECT.3.3.5.4.2.2.2.3 | Electrical Room-BP1 233/UTT RM/BMS RM/BATRM/Lobby/Staircase/Lift room BP1/Corridor-154
18 | PROJECT.3.3.5.4.2.2.2.3.1 | General Civil Access Dates-Electrical Room SL-233
18 | PROJECT.3.3.5.4.2.2.2.3.2 | MEP 1st Fix in Wall-Electrical Room SL-233
18 | PROJECT.3.3.5.4.2.2.2.3.3 | MEP 2nd Fix-Electrical Room SL-233
20 | PROJECT.3.3.5.4.2.2.2.3.3.1 | HVAC Works
20 | PROJECT.3.3.5.4.2.2.2.3.3.2 | CHW piping Works
20 | PROJECT.3.3.5.4.2.2.2.3.3.3 | Electrical Works
20 | PROJECT.3.3.5.4.2.2.2.3.3.4 | Fire Fighting Works
20 | PROJECT.3.3.5.4.2.2.2.3.3.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.4.2.2.2.3.4 | MEP Final Fix-Electrical Room SL-233
20 | PROJECT.3.3.5.4.2.2.2.3.4.1 | HVAC Works
20 | PROJECT.3.3.5.4.2.2.2.3.4.2 | Electrical Works
20 | PROJECT.3.3.5.4.2.2.2.3.4.3 | Fire Fighting Works
20 | PROJECT.3.3.5.4.2.2.2.3.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.2.2.5 | BP1-POP Room-163A
16 | PROJECT.3.3.5.4.2.2.5.1 | General Civil Access Dates-BP1-POP Room-163A
16 | PROJECT.3.3.5.4.2.2.5.2 | MEP 1st Fix in Wall-BP1-POP Room-163A
16 | PROJECT.3.3.5.4.2.2.5.3 | MEP 2nd Fix-BP1-POP Room-163A
18 | PROJECT.3.3.5.4.2.2.5.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.2.2.5.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.2.2.5.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.2.2.5.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.4.2.2.5.4 | MEP Final Fix-BP1-POP Room-163A
18 | PROJECT.3.3.5.4.2.2.5.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.2.2.5.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.2.2.5.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.2.2.5.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.2.2.6 | UTT RM BP1 - 233/BMS RM/LOBBY 03 Zone 09&13
16 | PROJECT.3.3.5.4.2.2.6.1 | General Civil Access Dates-UTT RM BP1 - 233/BMS RM/LOBBY 03 Zone 09&13
16 | PROJECT.3.3.5.4.2.2.6.2 | MEP 1st Fix in Wall-UTT RM BP1 - 233/BMS RM/LOBBY 03 Zone 09&13
16 | PROJECT.3.3.5.4.2.2.6.3 | MEP 2nd Fix-UTT RM BP1 - 233/BMS RM/LOBBY 03 Zone 09&13
18 | PROJECT.3.3.5.4.2.2.6.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.2.2.6.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.2.2.6.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.2.2.6.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.2.2.6.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.2.2.6.4 | MEP Final Fix-UTT RM BP1 - 233/BMS RM/LOBBY 03 Zone 09&13
18 | PROJECT.3.3.5.4.2.2.6.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.2.2.6.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.2.2.6.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.2.2.6.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.2.2.7 | BP1 - 164/ CONDENSER RM/COMP RM/Lift room
16 | PROJECT.3.3.5.4.2.2.7.1 | General Civil Access Dates-UTT RM BP1 - 164/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.4.2.2.7.2 | MEP 1st Fix in Wall-UTT RM BP1 - 164/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.4.2.2.7.3 | MEP 2nd Fix-UTT RM BP1 - 164/BMS RM/Lobby/Lift room
18 | PROJECT.3.3.5.4.2.2.7.3.1 | HVAC Works
18 | PROJECT.3.3.5.4.2.2.7.3.2 | CHW piping Works
18 | PROJECT.3.3.5.4.2.2.7.3.3 | Electrical Works
18 | PROJECT.3.3.5.4.2.2.7.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.4.2.2.7.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.4.2.2.7.4 | MEP Final Fix-UTT RM BP1 - 164/BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.4.2.2.7.4.1 | HVAC Works
18 | PROJECT.3.3.5.4.2.2.7.4.2 | Electrical Works
18 | PROJECT.3.3.5.4.2.2.7.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.4.2.2.7.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.4.2.6 | STAIRCASES BP1-GF
14 | PROJECT.3.3.5.4.2.6.1 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.4.2.6.4 | ACCESS STAIRCASES ST23, ST26, ST35
10 | PROJECT.3.3.5.4.5 | EGRESS CORRIDORS
12 | PROJECT.3.3.5.4.5.1 | ZONE 01 (CORRIDOR 115)
14 | PROJECT.3.3.5.4.5.1.1 | General Civil Access Dates-BP1-Egress Corridors/115
14 | PROJECT.3.3.5.4.5.1.2 | MEP 1st Fix in Wall-BP1-Egress Corridors/115
14 | PROJECT.3.3.5.4.5.1.3 | MEP 2nd Fix-BP1-Egress Corridors/115
16 | PROJECT.3.3.5.4.5.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.4.5.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.4.5.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.4.5.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.4.5.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.5.1.4 | MEP Final Fix-BP1-Egress Corridors/115
16 | PROJECT.3.3.5.4.5.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.4.5.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.4.5.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.4.5.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.4.5.2 | ZONE 03 (CORRIDOR 119)
14 | PROJECT.3.3.5.4.5.2.1 | General Civil Access Dates-BP1-Egress Corridors/119
14 | PROJECT.3.3.5.4.5.2.2 | MEP 1st Fix in Wall-BP1-Egress Corridors/119
14 | PROJECT.3.3.5.4.5.2.3 | MEP 2nd Fix-BP1-Egress Corridors/119
16 | PROJECT.3.3.5.4.5.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.4.5.2.3.2 | CHW piping Works
16 | PROJECT.3.3.5.4.5.2.3.3 | Electrical Works
16 | PROJECT.3.3.5.4.5.2.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.4.5.2.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.4.5.2.4 | MEP Final Fix-BP1-Egress Corridors/119
16 | PROJECT.3.3.5.4.5.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.4.5.2.4.2 | Electrical Works
16 | PROJECT.3.3.5.4.5.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.4.5.2.4.4 | Plumbing & Drainage Works
8 | PROJECT.3.3.5.5 | GROUND LEVEL (GL)
10 | PROJECT.3.3.5.5.2 | GL-West Side
12 | PROJECT.3.3.5.5.2.1 | GL-West Side-BOH
14 | PROJECT.3.3.5.5.2.1.1 | GL-Electrical Room-104/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.2.1.1.1 | General Civil Access Dates-GL-Electrical Room-104/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.2.1.1.2 | MEP 1st Fix in Wall-GL-Electrical Room-104/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.2.1.1.3 | MEP 2nd Fix-GL-Electrical Room-104/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.5.2.1.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.1.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.2.1.1.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.1.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.1.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.2.1.1.4 | MEP Final Fix-GL-Electrical Room-104/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.5.2.1.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.1.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.2.1.2 | GL-Electrical Room-206/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.2.1.2.1 | General Civil Access Dates-Electrical Room-206/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.2.1.2.2 | MEP 1st Fix in Wall-Electrical Room-206/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.2.1.2.3 | MEP 2nd Fix-Electrical Room-206/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.5.2.1.2.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.2.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.2.1.2.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.2.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.2.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.2.1.2.4 | MEP Final Fix-Electrical Room-206/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.5.2.1.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.2.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.2.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.2.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.2.1.3 | GL-Electrical Room-305/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.2.1.3.1 | General Civil Access Dates-Electrical Room SL-305
16 | PROJECT.3.3.5.5.2.1.3.2 | MEP 1st Fix in Wall-Electrical Room SL-305
16 | PROJECT.3.3.5.5.2.1.3.3 | MEP 2nd Fix-Electrical Room SL-305
18 | PROJECT.3.3.5.5.2.1.3.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.3.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.2.1.3.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.3.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.3.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.2.1.3.4 | MEP Final Fix-Electrical Room SL-305
18 | PROJECT.3.3.5.5.2.1.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.3.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.3.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.3.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.2.1.4 | GL-Electrical Room-711/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.2.1.4.1 | General Civil Access Dates-Electrical Room SL-711
16 | PROJECT.3.3.5.5.2.1.4.2 | MEP 1st Fix in Wall-Electrical Room SL-711
16 | PROJECT.3.3.5.5.2.1.4.3 | MEP 2nd Fix-Electrical Room SL-711
18 | PROJECT.3.3.5.5.2.1.4.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.4.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.2.1.4.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.4.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.4.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.2.1.4.4 | MEP Final Fix-Electrical Room SL-711
18 | PROJECT.3.3.5.5.2.1.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.4.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.4.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.4.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.2.1.5 | GL-UTT RM-706/BMS RM/Lobby/Lift room
16 | PROJECT.3.3.5.5.2.1.5.1 | General Civil Access Dates-UTT RM-706/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.5.2.1.5.2 | MEP 1st Fix in Wall-UTT RM-706/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.5.2.1.5.3 | MEP 2nd Fix-UTT RM-706/BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.5.2.1.5.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.5.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.2.1.5.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.5.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.5.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.2.1.5.4 | MEP Final Fix-UTT RM-706/BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.5.2.1.5.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.1.5.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.1.5.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.1.5.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.2.2 | GL-West Side-Shop Area
14 | PROJECT.3.3.5.5.2.2.1 | General Civil Access Dates-GL-West Side
14 | PROJECT.3.3.5.5.2.2.2 | MEP 1st Fix in Wall-GL-West Side
14 | PROJECT.3.3.5.5.2.2.3 | MEP 2nd Fix-GL-West Side
16 | PROJECT.3.3.5.5.2.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.2.2.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.2.2.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.2.2.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.2.2.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.2.2.4 | MEP Final Fix-GL-West Side
16 | PROJECT.3.3.5.5.2.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.2.2.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.2.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.2.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.2.3 | GL-West Side Wet Areas
14 | PROJECT.3.3.5.5.2.3.4 | GL-West Side-Toilets-T-Z01
16 | PROJECT.3.3.5.5.2.3.4.1 | General Civil Access Dates-GL-West Side-Toilets
16 | PROJECT.3.3.5.5.2.3.4.2 | MEP 1st Fix in Wall-GL-West Side-Toilets
16 | PROJECT.3.3.5.5.2.3.4.3 | MEP 2nd Fix-GL-West Side-Toilets
18 | PROJECT.3.3.5.5.2.3.4.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.3.4.3.5 | CHW piping Works
18 | PROJECT.3.3.5.5.2.3.4.3.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.3.4.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.3.4.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.2.3.4.4 | MEP Final Fix-GL-West Side-Toilets
18 | PROJECT.3.3.5.5.2.3.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.3.4.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.3.4.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.3.4.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.2.3.3 | GL-West Side-Toilets -T-Z03
16 | PROJECT.3.3.5.5.2.3.3.1 | General Civil Access Dates-GL-West Side-Toilets
16 | PROJECT.3.3.5.5.2.3.3.2 | MEP 1st Fix in Wall-GL-West Side-Toilets
16 | PROJECT.3.3.5.5.2.3.3.3 | MEP 2nd Fix-GL-West Side-Toilets
18 | PROJECT.3.3.5.5.2.3.3.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.3.3.3.5 | CHW piping Works
18 | PROJECT.3.3.5.5.2.3.3.3.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.3.3.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.3.3.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.2.3.3.4 | MEP Final Fix-GL-West Side-Toilets
18 | PROJECT.3.3.5.5.2.3.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.3.3.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.3.3.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.3.3.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.2.3.2 | GL-Dynamic Side-Toilets - T-ZO5-N
16 | PROJECT.3.3.5.5.2.3.2.1 | General Civil Access Dates-GL-Dynamic Side-Toilets
16 | PROJECT.3.3.5.5.2.3.2.2 | MEP 1st Fix in Wall-GL-Dynamic Side-Toilets
16 | PROJECT.3.3.5.5.2.3.2.3 | MEP 2nd Fix-GL-Dynamic Side-Toilets
18 | PROJECT.3.3.5.5.2.3.2.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.3.2.3.5 | CHW piping Works
18 | PROJECT.3.3.5.5.2.3.2.3.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.3.2.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.3.2.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.2.3.2.4 | MEP Final Fix-GL-Dynamic Side-Toilets
18 | PROJECT.3.3.5.5.2.3.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.3.2.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.3.2.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.3.2.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.2.3.1 | GL-Urban Side-Toilets -T-Z05-S
16 | PROJECT.3.3.5.5.2.3.1.1 | General Civil Access Dates-GL-Urban Side-Toilets
16 | PROJECT.3.3.5.5.2.3.1.2 | MEP 1st Fix in Wall-GL-Urban Side-Toilets
16 | PROJECT.3.3.5.5.2.3.1.3 | MEP 2nd Fix-GL-Urban Side-Toilets
18 | PROJECT.3.3.5.5.2.3.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.3.1.3.5 | CHW piping Works
18 | PROJECT.3.3.5.5.2.3.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.3.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.3.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.2.3.1.4 | MEP Final Fix-GL-Urban Side-Toilets
18 | PROJECT.3.3.5.5.2.3.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.2.3.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.2.3.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.2.3.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.2.6 | GL-West Side- STAIRCASES GF-L1 SECTION A
14 | PROJECT.3.3.5.5.2.6.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.5.2.6.2 | ACCESS STAIRCASES ST09, ST11, ST12
10 | PROJECT.3.3.5.5.1 | GL-East Side
12 | PROJECT.3.3.5.5.1.1 | GL-East Side-Shop Area
14 | PROJECT.3.3.5.5.1.1.1 | General Civil Access Dates-GL-East Side
14 | PROJECT.3.3.5.5.1.1.2 | MEP 1st Fix in Wall-GL-East Side
14 | PROJECT.3.3.5.5.1.1.3 | MEP 2nd Fix-GL-East Side
16 | PROJECT.3.3.5.5.1.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.1.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.1.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.1.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.1.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.1.1.4 | MEP Final Fix-GL-East Side
16 | PROJECT.3.3.5.5.1.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.1.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.1.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.1.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.1.3 | GL-East Side Wet Areas
14 | PROJECT.3.3.5.5.1.3.2 | GL-Dynamic Side-Toilets T-Z08-N
16 | PROJECT.3.3.5.5.1.3.2.1 | General Civil Access Dates-GL-Dynamic Side-Toilets
16 | PROJECT.3.3.5.5.1.3.2.2 | MEP 1st Fix in Wall-GL-Dynamic Side-Toilets
16 | PROJECT.3.3.5.5.1.3.2.3 | MEP 2nd Fix-GL-Dynamic Side-Toilets
18 | PROJECT.3.3.5.5.1.3.2.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.3.2.3.5 | CHW piping Works
18 | PROJECT.3.3.5.5.1.3.2.3.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.3.2.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.3.2.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.1.3.2.4 | MEP Final Fix-GL-Dynamic Side-Toilets
18 | PROJECT.3.3.5.5.1.3.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.3.2.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.3.2.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.3.2.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.1.3.1 | GL-Urban Side-Toilets T-Z08-S
16 | PROJECT.3.3.5.5.1.3.1.1 | General Civil Access Dates-GL-Urban Side-Toilets
16 | PROJECT.3.3.5.5.1.3.1.2 | MEP 1st Fix in Wall-GL-Urban Side-Toilets
16 | PROJECT.3.3.5.5.1.3.1.3 | MEP 2nd Fix-GL-Urban Side-Toilets
18 | PROJECT.3.3.5.5.1.3.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.3.1.3.5 | CHW piping Works
18 | PROJECT.3.3.5.5.1.3.1.3.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.3.1.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.3.1.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.1.3.1.4 | MEP Final Fix-GL-Urban Side-Toilets
18 | PROJECT.3.3.5.5.1.3.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.3.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.3.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.3.1.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.1.3.4 | GL-East Side-Toilets T-Z09
16 | PROJECT.3.3.5.5.1.3.4.1 | General Civil Access Dates-GL-East Side-Toilets
16 | PROJECT.3.3.5.5.1.3.4.2 | MEP 1st Fix in Wall-GL-East Side-Toilets
16 | PROJECT.3.3.5.5.1.3.4.3 | MEP 2nd Fix-GL-East Side-Toilets
18 | PROJECT.3.3.5.5.1.3.4.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.3.4.3.5 | CHW piping Works
18 | PROJECT.3.3.5.5.1.3.4.3.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.3.4.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.3.4.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.1.3.4.4 | MEP Final Fix-GL-East Side-Toilets
18 | PROJECT.3.3.5.5.1.3.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.3.4.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.3.4.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.3.4.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.1.3.3 | GL-East Side-Toilets T-Z14
16 | PROJECT.3.3.5.5.1.3.3.1 | General Civil Access Dates-GL-East Side-Toilets
16 | PROJECT.3.3.5.5.1.3.3.2 | MEP 1st Fix in Wall-GL-East Side-Toilets
16 | PROJECT.3.3.5.5.1.3.3.3 | MEP 2nd Fix-GL-East Side-Toilets
18 | PROJECT.3.3.5.5.1.3.3.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.3.3.3.5 | CHW piping Works
18 | PROJECT.3.3.5.5.1.3.3.3.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.3.3.3.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.3.3.3.4 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.1.3.3.4 | MEP Final Fix-GL-East Side-Toilets
18 | PROJECT.3.3.5.5.1.3.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.3.3.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.3.3.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.3.3.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.1.2 | GL-East Side-BOH
14 | PROJECT.3.3.5.5.1.2.1 | GL-Electrical Room-606/UTT RM/BMS RM/BATRM
16 | PROJECT.3.3.5.5.1.2.1.1 | General Civil Access Dates-Electrical Room SL-606
16 | PROJECT.3.3.5.5.1.2.1.2 | MEP 1st Fix in Wall-Electrical Room SL-606
16 | PROJECT.3.3.5.5.1.2.1.3 | MEP 2nd Fix-Electrical Room SL-606
18 | PROJECT.3.3.5.5.1.2.1.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.1.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.1.2.1.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.1.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.1.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.1.2.1.4 | MEP Final Fix-Electrical Room SL-606
18 | PROJECT.3.3.5.5.1.2.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.1.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.1.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.1.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.1.2.2 | GL-Electrical Room-504/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.1.2.2.1 | General Civil Access Dates-Electrical Room SL-504
16 | PROJECT.3.3.5.5.1.2.2.2 | MEP 1st Fix in Wall-Electrical Room SL-504
16 | PROJECT.3.3.5.5.1.2.2.3 | MEP 2nd Fix-Electrical Room SL-504
18 | PROJECT.3.3.5.5.1.2.2.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.2.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.1.2.2.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.2.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.2.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.1.2.2.4 | MEP Final Fix-Electrical Room SL-504
18 | PROJECT.3.3.5.5.1.2.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.2.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.2.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.2.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.1.2.3 | GL-Electrical Room-407/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.1.2.3.1 | General Civil Access Dates-Electrical Room SL-407
16 | PROJECT.3.3.5.5.1.2.3.2 | MEP 1st Fix in Wall-Electrical Room SL-407
16 | PROJECT.3.3.5.5.1.2.3.3 | MEP 2nd Fix-Electrical Room SL-407
18 | PROJECT.3.3.5.5.1.2.3.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.3.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.1.2.3.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.3.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.3.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.1.2.3.4 | MEP Final Fix-Electrical Room SL-407
18 | PROJECT.3.3.5.5.1.2.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.3.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.3.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.3.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.1.2.4 | GL-Electrical Room-804/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.5.1.2.4.1 | General Civil Access Dates-Electrical Room SL-804
16 | PROJECT.3.3.5.5.1.2.4.2 | MEP 1st Fix in Wall-Electrical Room SL-804
16 | PROJECT.3.3.5.5.1.2.4.3 | MEP 2nd Fix-Electrical Room SL-804
18 | PROJECT.3.3.5.5.1.2.4.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.4.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.1.2.4.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.4.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.4.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.1.2.4.4 | MEP Final Fix-Electrical Room SL-804
18 | PROJECT.3.3.5.5.1.2.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.4.4.2 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.4.4.3 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.4.4.4 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.1.2.5 | GL-UTT RM-814/BMS RM/Lobby/Lift room
16 | PROJECT.3.3.5.5.1.2.5.1 | General Civil Access Dates-UTT RM-814/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.5.1.2.5.2 | MEP 1st Fix in Wall-UTT RM-814/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.5.1.2.5.3 | MEP 2nd Fix UTT RM-814/BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.5.1.2.5.3.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.5.3.2 | CHW piping Works
18 | PROJECT.3.3.5.5.1.2.5.3.3 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.5.3.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.5.3.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.5.1.2.5.4 | MEP Final Fix-UTT RM-814/BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.5.1.2.5.4.1 | HVAC Works
18 | PROJECT.3.3.5.5.1.2.5.4.3 | Electrical Works
18 | PROJECT.3.3.5.5.1.2.5.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.5.1.2.5.4.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.1.4 | STAIRCASES GF-L1 SECTION B
14 | PROJECT.3.3.5.5.1.4.1 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.5.1.4.4 | ACCESS STAIRCASES ST16, ST18
12 | PROJECT.3.3.5.5.1.5 | STAIRCASES GF-L1 SECTION C
14 | PROJECT.3.3.5.5.1.5.1 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.5.1.5.4 | ACCESS STAIRCASES ST23, ST26, ST35
10 | PROJECT.3.3.5.5.3 | GL-The Mall Concourse
12 | PROJECT.3.3.5.5.3.1 | GL-West Mall
14 | PROJECT.3.3.5.5.3.1.1 | General Civil Access Dates-GL-West Side
14 | PROJECT.3.3.5.5.3.1.2 | MEP 1st Fix in Wall-GL-West Side
14 | PROJECT.3.3.5.5.3.1.3 | MEP 2nd Fix-GL-West Side
16 | PROJECT.3.3.5.5.3.1.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.1.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.3.1.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.1.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.1.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.3.1.4 | MEP Final Fix-GL-West Side
16 | PROJECT.3.3.5.5.3.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.1.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.3.1.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.1.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.3.2 | GL-Dynamic West
14 | PROJECT.3.3.5.5.3.2.1 | General Civil Access Dates-GL-Dynamic West
14 | PROJECT.3.3.5.5.3.2.2 | MEP 1st Fix in Wall-GL-Dynamic West
14 | PROJECT.3.3.5.5.3.2.3 | MEP 2nd Fix-GL-Dynamic West
16 | PROJECT.3.3.5.5.3.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.2.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.3.2.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.2.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.2.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.3.2.4 | MEP Final Fix-GL-Dynamic West
16 | PROJECT.3.3.5.5.3.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.2.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.3.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.3.3 | GL-East Mall
14 | PROJECT.3.3.5.5.3.3.3 | General Civil Access Dates-GL-East Mall
14 | PROJECT.3.3.5.5.3.3.2 | MEP 1st Fix in Wall-GL-East Mall
14 | PROJECT.3.3.5.5.3.3.4 | MEP 2nd Fix-GL-East Mall
16 | PROJECT.3.3.5.5.3.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.3.4.2 | CHW piping Works
16 | PROJECT.3.3.5.5.3.3.4.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.3.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.3.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.3.3.7 | MEP Final Fix-GL-East Mall
16 | PROJECT.3.3.5.5.3.3.7.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.3.7.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.3.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.3.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.3.4 | GL-Urban West
14 | PROJECT.3.3.5.5.3.4.3 | General Civil Access Dates-GL-Urban West
14 | PROJECT.3.3.5.5.3.4.2 | MEP 1st Fix in Wall-GL-Urban West
14 | PROJECT.3.3.5.5.3.4.4 | MEP 2nd Fix-GL-Urban West
16 | PROJECT.3.3.5.5.3.4.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.4.4.2 | CHW piping Works
16 | PROJECT.3.3.5.5.3.4.4.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.4.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.4.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.3.4.7 | MEP Final Fix-GL-Urban West
16 | PROJECT.3.3.5.5.3.4.7.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.4.7.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.4.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.4.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.3.5 | GL-Dynamic East
14 | PROJECT.3.3.5.5.3.5.3 | General Civil Access Dates-GL-Dynamic East
14 | PROJECT.3.3.5.5.3.5.2 | MEP 1st Fix in Wall-GL-Dynamic East
14 | PROJECT.3.3.5.5.3.5.4 | MEP 2nd Fix-GL-Dynamic East
16 | PROJECT.3.3.5.5.3.5.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.5.4.2 | CHW piping Works
16 | PROJECT.3.3.5.5.3.5.4.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.5.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.5.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.3.5.7 | MEP Final Fix-GL-Dynamic East
16 | PROJECT.3.3.5.5.3.5.7.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.5.7.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.5.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.5.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.3.6 | GL-Urban East
14 | PROJECT.3.3.5.5.3.6.3 | General Civil Access Dates-GL-Urban East
14 | PROJECT.3.3.5.5.3.6.2 | MEP 1st Fix in Wall-GL-Urban East
14 | PROJECT.3.3.5.5.3.6.4 | MEP 2nd Fix-GL-Urban East
16 | PROJECT.3.3.5.5.3.6.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.6.4.2 | CHW piping Works
16 | PROJECT.3.3.5.5.3.6.4.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.6.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.6.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.3.6.7 | MEP Final Fix-GL-Urban East
16 | PROJECT.3.3.5.5.3.6.7.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.6.7.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.6.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.6.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.3.7 | GL-Mangrove
14 | PROJECT.3.3.5.5.3.7.3 | General Civil Access Dates-GL-Mangrove
14 | PROJECT.3.3.5.5.3.7.2 | MEP 1st Fix in Wall-GL-Mangrove
14 | PROJECT.3.3.5.5.3.7.4 | MEP 2nd Fix-GL-Mangrove
16 | PROJECT.3.3.5.5.3.7.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.7.4.2 | CHW piping Works
16 | PROJECT.3.3.5.5.3.7.4.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.7.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.7.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.3.7.7 | MEP Final Fix-GL-Mangrove
16 | PROJECT.3.3.5.5.3.7.7.1 | HVAC Works
16 | PROJECT.3.3.5.5.3.7.7.3 | Electrical Works
16 | PROJECT.3.3.5.5.3.7.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.3.7.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.5.4 | EGRESS CORRIDORS
12 | PROJECT.3.3.5.5.4.2 | ZONE 02 (CORRIDOR 214)
14 | PROJECT.3.3.5.5.4.2.1 | General Civil Access Dates-GL-Egress Corridors/ 201/ 214
14 | PROJECT.3.3.5.5.4.2.2 | MEP 1st Fix in Wall-GL-Egress Corridors/ 201/ 214
14 | PROJECT.3.3.5.5.4.2.3 | MEP 2nd Fix-GL-Egress Corridors/ 201/ 214
16 | PROJECT.3.3.5.5.4.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.2.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.4.2.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.4.2.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.2.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.4.2.4 | MEP Final Fix-GL-Egress Corridors/ 201/ 214
16 | PROJECT.3.3.5.5.4.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.2.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.4.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.4.4 | ZONE 04 (CORRIDORS 101, 109)
14 | PROJECT.3.3.5.5.4.4.1 | General Civil Access Dates-GL-Egress Corridors/ 109, 101, 701
14 | PROJECT.3.3.5.5.4.4.2 | MEP 1st Fix in Wall-GL-Egress Corridors/109, 101, 701
14 | PROJECT.3.3.5.5.4.4.3 | MEP 2nd Fix-GL-Egress Corridors/ 109, 101, 701
16 | PROJECT.3.3.5.5.4.4.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.4.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.4.4.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.4.4.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.4.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.4.4.4 | MEP Final Fix-GL-Egress Corridors/ 109, 101, 701
16 | PROJECT.3.3.5.5.4.4.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.4.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.4.4.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.4.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.4.5 | ZONE 05 (CORRIDOR 708)
14 | PROJECT.3.3.5.5.4.5.1 | General Civil Access Dates-GL-Egress Corridors/ 708, 704
14 | PROJECT.3.3.5.5.4.5.2 | MEP 1st Fix in Wall-GL-Egress Corridors/ 708, 704
14 | PROJECT.3.3.5.5.4.5.3 | MEP 2nd Fix-GL-Egress Corridors/708, 704
16 | PROJECT.3.3.5.5.4.5.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.5.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.4.5.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.4.5.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.5.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.4.5.4 | MEP Final Fix-GL-Egress Corridors/708, 704
16 | PROJECT.3.3.5.5.4.5.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.5.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.4.5.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.5.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.4.6 | ZONE 06 (CORRIDORS 301, 303)
14 | PROJECT.3.3.5.5.4.6.1 | General Civil Access Dates-GL-Egress Corridors/ 301, 303
14 | PROJECT.3.3.5.5.4.6.2 | MEP 1st Fix in Wall-GL-Egress Corridors/301, 303
14 | PROJECT.3.3.5.5.4.6.3 | MEP 2nd Fix-GL-Egress Corridors/ 301, 303
16 | PROJECT.3.3.5.5.4.6.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.6.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.4.6.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.4.6.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.6.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.4.6.4 | MEP Final Fix-GL-Egress Corridors/ 301, 303
16 | PROJECT.3.3.5.5.4.6.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.6.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.4.6.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.6.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.4.7 | ZONE 07 (CORRIDORS 601, 602)
14 | PROJECT.3.3.5.5.4.7.1 | General Civil Access Dates-GL-Egress Corridors/ 602
14 | PROJECT.3.3.5.5.4.7.2 | MEP 1st Fix in Wall-GL-Egress Corridors/ 602
14 | PROJECT.3.3.5.5.4.7.3 | MEP 2nd Fix-GL-Egress Corridors/ 602
16 | PROJECT.3.3.5.5.4.7.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.7.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.4.7.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.4.7.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.7.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.4.7.4 | MEP Final Fix-GL-Egress Corridors/602
16 | PROJECT.3.3.5.5.4.7.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.7.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.4.7.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.7.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.4.8 | ZONE 08 (CORRIDORS 816, 817)
14 | PROJECT.3.3.5.5.4.8.1 | General Civil Access Dates-GL-Egress Corridors/ 816, 817
14 | PROJECT.3.3.5.5.4.8.2 | MEP 1st Fix in Wall-GL-Egress Corridors/ 816, 817
14 | PROJECT.3.3.5.5.4.8.3 | MEP 2nd Fix-GL-Egress Corridors/ 816, 817
16 | PROJECT.3.3.5.5.4.8.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.8.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.4.8.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.4.8.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.8.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.4.8.4 | MEP Final Fix-GL-Egress Corridors/816, 817
16 | PROJECT.3.3.5.5.4.8.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.8.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.4.8.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.8.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.4.10 | ZONE 10 (CORRIDOR 801)
14 | PROJECT.3.3.5.5.4.10.1 | General Civil Access Dates-GL-Egress Corridors/821, 812
14 | PROJECT.3.3.5.5.4.10.2 | MEP 1st Fix in Wall-GL-Egress Corridors/821, 812
14 | PROJECT.3.3.5.5.4.10.3 | MEP 2nd Fix-GL-Egress Corridors/821, 812
16 | PROJECT.3.3.5.5.4.10.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.10.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.4.10.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.4.10.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.10.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.4.10.4 | MEP Final Fix-GL-Egress Corridors/821, 812
16 | PROJECT.3.3.5.5.4.10.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.10.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.4.10.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.10.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.5.4.11 | ZONE 11 (CORRIDORS 401, 403)
14 | PROJECT.3.3.5.5.4.11.1 | General Civil Access Dates-GL-Egress Corridors/801, 403, 401
14 | PROJECT.3.3.5.5.4.11.2 | MEP 1st Fix in Wall-GL-Egress Corridors/ 801, 403, 401
14 | PROJECT.3.3.5.5.4.11.3 | MEP 2nd Fix-GL-Egress Corridors/801, 403, 401
16 | PROJECT.3.3.5.5.4.11.3.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.11.3.2 | CHW piping Works
16 | PROJECT.3.3.5.5.4.11.3.3 | Electrical Works
16 | PROJECT.3.3.5.5.4.11.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.11.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.5.4.11.4 | MEP Final Fix-GL-Egress Corridors/801, 403, 401
16 | PROJECT.3.3.5.5.4.11.4.1 | HVAC Works
16 | PROJECT.3.3.5.5.4.11.4.2 | Electrical Works
16 | PROJECT.3.3.5.5.4.11.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.5.4.11.4.4 | Plumbing & Drainage Works
8 | PROJECT.3.3.5.6 | LEVEL-01 (L1)
10 | PROJECT.3.3.5.6.6 | L1-West Side-Wet Areas
12 | PROJECT.3.3.5.6.6.2 | L1-Urban Side-Toilets TZ05S
14 | PROJECT.3.3.5.6.6.2.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.6.2.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.6.2.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.6.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.6.2.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.6.2.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.6.2.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.6.2.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.6.2.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.6.2.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.6.2.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.6.2.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.6.2.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.6.1 | L1-West Side T-Z03
14 | PROJECT.3.3.5.6.6.1.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.6.1.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.6.1.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.6.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.6.1.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.6.1.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.6.1.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.6.1.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.6.1.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.6.1.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.6.1.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.6.1.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.6.1.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.6.8 | L1-Dynamic Side-Toilets TZ05N
14 | PROJECT.3.3.5.6.6.8.3 | General Civil Access Dates-L1-Dynamic Side-Toilets
14 | PROJECT.3.3.5.6.6.8.2 | MEP 1st Fix in Wall-L1-Dynamic Side-Toilets
14 | PROJECT.3.3.5.6.6.8.4 | MEP 2nd Fix-L1-Dynamic Side-Toilets
16 | PROJECT.3.3.5.6.6.8.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.6.8.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.6.8.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.6.8.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.6.8.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.6.8.7 | MEP Final Fix-L1-Dynamic Side-Toilets
16 | PROJECT.3.3.5.6.6.8.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.6.8.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.6.8.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.6.8.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.6.9 | L1-West Side-Toilets T-Z01
14 | PROJECT.3.3.5.6.6.9.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.6.9.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.6.9.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.6.9.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.6.9.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.6.9.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.6.9.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.6.9.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.6.9.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.6.9.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.6.9.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.6.9.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.6.9.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.6.5 | STAIRCASES L1-L2 SECTION A
14 | PROJECT.3.3.5.6.6.5.4 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.6.6.5.2 | ACCESS STAIRCASES ST09, ST11, ST12
10 | PROJECT.3.3.5.6.7 | L1-East Side Wet Areas & Food Court
12 | PROJECT.3.3.5.6.7.1 | L1-East Side & Food Court T-Z14 (FOOD COURT)
14 | PROJECT.3.3.5.6.7.1.3 | General Civil Access Dates-L1-East Side
14 | PROJECT.3.3.5.6.7.1.2 | MEP 1st Fix in Wall-L1-East Side
14 | PROJECT.3.3.5.6.7.1.4 | MEP 2nd Fix-L1-East Side
16 | PROJECT.3.3.5.6.7.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.7.1.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.7.1.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.7.1.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.7.1.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.7.1.7 | MEP Final Fix-L1-East Side
16 | PROJECT.3.3.5.6.7.1.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.7.1.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.7.1.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.7.1.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.7.9 | L1-East Side-Toilets T-Z09
14 | PROJECT.3.3.5.6.7.9.3 | General Civil Access Dates-L1-East Side-Toilets
14 | PROJECT.3.3.5.6.7.9.2 | MEP 1st Fix in Wall-L1-East Side-Toilets
14 | PROJECT.3.3.5.6.7.9.4 | MEP 2nd Fix-L1-East Side-Toilets
16 | PROJECT.3.3.5.6.7.9.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.7.9.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.7.9.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.7.9.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.7.9.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.7.9.7 | MEP Final Fix-L1-East Side-Toilets
16 | PROJECT.3.3.5.6.7.9.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.7.9.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.7.9.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.7.9.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.7.2 | L1-Urban Side-Toilets T-Z08S
14 | PROJECT.3.3.5.6.7.2.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.7.2.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.7.2.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.7.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.7.2.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.7.2.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.7.2.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.7.2.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.7.2.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.7.2.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.7.2.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.7.2.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.7.2.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.7.8 | L1-Dynamic Side-Toilets T-Z08N
14 | PROJECT.3.3.5.6.7.8.3 | General Civil Access Dates-L1-Dynamic Side-Toilets
14 | PROJECT.3.3.5.6.7.8.2 | MEP 1st Fix in Wall-L1-Dynamic Side-Toilets
14 | PROJECT.3.3.5.6.7.8.4 | MEP 2nd Fix-L1-Dynamic Side-Toilets
16 | PROJECT.3.3.5.6.7.8.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.7.8.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.7.8.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.7.8.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.7.8.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.7.8.7 | MEP Final Fix-L1-Dynamic Side-Toilets
16 | PROJECT.3.3.5.6.7.8.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.7.8.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.7.8.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.7.8.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.7.5 | STAIRCASES L1-L2/PP1 SECTION B
14 | PROJECT.3.3.5.6.7.5.5 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.6.7.5.4 | ACCESS STAIRCASES ST16, ST18
12 | PROJECT.3.3.5.6.7.3 | STAIRCASES L1-L2/PP1 SECTION C
14 | PROJECT.3.3.5.6.7.3.5 | EARLY COMPLETION STAIRCASES
14 | PROJECT.3.3.5.6.7.3.4 | ACCESS STAIRCASES ST23, ST26, ST35
10 | PROJECT.3.3.5.6.1 | L1-The Mall Concourse
12 | PROJECT.3.3.5.6.1.7 | L1-West Mall
14 | PROJECT.3.3.5.6.1.7.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.1.7.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.1.7.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.1.7.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.7.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.1.7.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.7.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.7.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.1.7.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.1.7.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.7.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.7.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.7.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.1.5 | L1-Dynamic West
14 | PROJECT.3.3.5.6.1.5.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.1.5.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.1.5.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.1.5.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.5.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.1.5.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.5.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.5.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.1.5.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.1.5.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.5.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.5.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.5.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.1.1 | L1-East Mall
14 | PROJECT.3.3.5.6.1.1.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.1.1.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.1.1.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.1.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.1.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.1.1.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.1.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.1.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.1.1.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.1.1.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.1.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.1.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.1.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.1.6 | L1-Urban West
14 | PROJECT.3.3.5.6.1.6.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.1.6.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.1.6.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.1.6.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.6.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.1.6.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.6.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.6.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.1.6.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.1.6.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.6.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.6.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.6.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.1.2 | L1-Dynamic East
14 | PROJECT.3.3.5.6.1.2.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.1.2.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.1.2.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.1.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.2.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.1.2.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.2.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.2.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.1.2.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.1.2.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.2.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.2.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.2.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.1.3 | L1-Urban East
14 | PROJECT.3.3.5.6.1.3.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.1.3.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.1.3.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.1.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.3.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.1.3.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.3.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.3.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.1.3.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.1.3.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.3.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.3.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.3.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.1.4 | L1-Mangrove
14 | PROJECT.3.3.5.6.1.4.3 | General Civil Access Dates
14 | PROJECT.3.3.5.6.1.4.2 | MEP 1st Fix in Wall
14 | PROJECT.3.3.5.6.1.4.4 | MEP 2nd Fix
16 | PROJECT.3.3.5.6.1.4.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.4.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.1.4.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.4.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.4.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.1.4.7 | MEP Final Fix
16 | PROJECT.3.3.5.6.1.4.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.1.4.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.1.4.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.1.4.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.6.8 | L1-Electrical/ELV Rooms
12 | PROJECT.3.3.5.6.8.2 | L1-Electrical Room-604/UTT RM/BMS RM/BATRM
14 | PROJECT.3.3.5.6.8.2.3 | General Civil Access Dates-Electrical Room SL-L1 604
14 | PROJECT.3.3.5.6.8.2.2 | MEP 1st Fix in Wall-Electrical Room SL-L1 604
14 | PROJECT.3.3.5.6.8.2.4 | MEP 2nd Fix-Electrical Room SL-L1 604
16 | PROJECT.3.3.5.6.8.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.2.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.2.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.2.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.2.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.2.7 | MEP Final Fix-Electrical Room SL-L1 604
16 | PROJECT.3.3.5.6.8.2.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.2.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.2.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.2.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.8.1 | L1-Electrical Room-104/UTT RM/BMS RM/LED RM
14 | PROJECT.3.3.5.6.8.1.3 | General Civil Access Dates-Electrical Room SL-104
14 | PROJECT.3.3.5.6.8.1.2 | MEP 1st Fix in Wall-Electrical Room SL-104
14 | PROJECT.3.3.5.6.8.1.4 | MEP 2nd Fix-Electrical Room SL-104
16 | PROJECT.3.3.5.6.8.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.1.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.1.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.1.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.1.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.1.7 | MEP Final Fix-Electrical Room SL-104
16 | PROJECT.3.3.5.6.8.1.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.1.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.1.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.1.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.8.3 | L1-Electrical Room-205/UTT RM/BMS RM/LED RM
14 | PROJECT.3.3.5.6.8.3.3 | General Civil Access Dates-Electrical Room SL-205
14 | PROJECT.3.3.5.6.8.3.2 | MEP 1st Fix in Wall-Electrical Room SL-205
14 | PROJECT.3.3.5.6.8.3.4 | MEP 2nd Fix-Electrical Room SL-205
16 | PROJECT.3.3.5.6.8.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.3.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.3.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.3.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.3.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.3.7 | MEP Final Fix-Electrical Room SL-205
16 | PROJECT.3.3.5.6.8.3.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.3.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.3.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.3.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.8.4 | L1-Electrical Room-502/UTT RM/BMS RM/LED RM
14 | PROJECT.3.3.5.6.8.4.3 | General Civil Access Dates-Electrical Room SL-502
14 | PROJECT.3.3.5.6.8.4.2 | MEP 1st Fix in Wall-Electrical Room SL-502
14 | PROJECT.3.3.5.6.8.4.4 | MEP 2nd Fix-Electrical Room SL-502
16 | PROJECT.3.3.5.6.8.4.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.4.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.4.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.4.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.4.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.4.7 | MEP Final Fix-Electrical Room SL-502
16 | PROJECT.3.3.5.6.8.4.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.4.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.4.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.4.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.8.10 | L1-Electrical Room-305/UTT RM/BMS RM/LED RM
14 | PROJECT.3.3.5.6.8.10.3 | General Civil Access Dates-Electrical Room SL-305
14 | PROJECT.3.3.5.6.8.10.2 | MEP 1st Fix in Wall-Electrical Room SL-305
14 | PROJECT.3.3.5.6.8.10.4 | MEP 2nd Fix-Electrical Room SL-305
16 | PROJECT.3.3.5.6.8.10.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.10.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.10.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.10.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.10.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.10.7 | MEP Final Fix-Electrical Room SL-305
16 | PROJECT.3.3.5.6.8.10.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.10.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.10.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.10.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.8.5 | L1-Electrical Room-803/UTT RM/BMS RM/LED RM
14 | PROJECT.3.3.5.6.8.5.3 | General Civil Access Dates-Electrical Room SL-803
14 | PROJECT.3.3.5.6.8.5.2 | MEP 1st Fix in Wall-Electrical Room SL-803
14 | PROJECT.3.3.5.6.8.5.4 | MEP 2nd Fix-Electrical Room SL-803
16 | PROJECT.3.3.5.6.8.5.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.5.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.5.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.5.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.5.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.5.7 | MEP Final Fix-Electrical Room SL-803
16 | PROJECT.3.3.5.6.8.5.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.5.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.5.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.5.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.8.6 | L1-Electrical Room-405/UTT RM/BMS RM/LED RM
14 | PROJECT.3.3.5.6.8.6.3 | General Civil Access Dates-Electrical Room SL-405
14 | PROJECT.3.3.5.6.8.6.2 | MEP 1st Fix in Wall-Electrical Room SL-405
14 | PROJECT.3.3.5.6.8.6.4 | MEP 2nd Fix-Electrical Room SL-405
16 | PROJECT.3.3.5.6.8.6.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.6.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.6.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.6.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.6.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.6.7 | MEP Final Fix-Electrical Room SL-405
16 | PROJECT.3.3.5.6.8.6.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.6.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.6.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.6.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.8.7 | L1-Electrical Room-710/UTT RM/BMS RM/LED RM
14 | PROJECT.3.3.5.6.8.7.3 | General Civil Access Dates-Electrical Room SL-710
14 | PROJECT.3.3.5.6.8.7.2 | MEP 1st Fix in Wall-Electrical Room SL-710
14 | PROJECT.3.3.5.6.8.7.4 | MEP 2nd Fix-Electrical Room SL-710
16 | PROJECT.3.3.5.6.8.7.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.7.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.7.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.7.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.7.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.7.7 | MEP Final Fix-Electrical Room SL-710
16 | PROJECT.3.3.5.6.8.7.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.7.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.7.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.7.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.8.8 | L1-UTT RM-705/BMS RM/Lobby/Staircase/Lift room
14 | PROJECT.3.3.5.6.8.8.3 | General Civil Access Dates-UTT RM-705/BMS RM/Lobby/Staircase/Lift room
14 | PROJECT.3.3.5.6.8.8.2 | MEP 1st Fix in Wall-UTT RM-705/BMS RM/Lobby/Staircase/Lift room
14 | PROJECT.3.3.5.6.8.8.4 | MEP 2nd Fix-UTT RM-705/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.6.8.8.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.8.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.8.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.8.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.8.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.8.7 | MEP Final Fix-UTT RM-705/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.6.8.8.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.8.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.8.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.8.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.8.9 | L1-UTT RM-813/BMS RM/Lobby/Staircase/Lift room
14 | PROJECT.3.3.5.6.8.9.3 | General Civil Access Dates-UTT RM-813/BMS RM/Lobby/Staircase/Lift room
14 | PROJECT.3.3.5.6.8.9.2 | MEP 1st Fix in Wall-UTT RM-813/BMS RM/Lobby/Staircase/Lift room
14 | PROJECT.3.3.5.6.8.9.4 | MEP 2nd Fix-UTT RM-813/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.6.8.9.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.9.4.2 | CHW piping Works
16 | PROJECT.3.3.5.6.8.9.4.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.9.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.9.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.8.9.7 | MEP Final Fix-UTT RM-813/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.6.8.9.7.1 | HVAC Works
16 | PROJECT.3.3.5.6.8.9.7.3 | Electrical Works
16 | PROJECT.3.3.5.6.8.9.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.8.9.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.6.5 | EGRESS CORRIDORS
12 | PROJECT.3.3.5.6.5.2 | ZONE 02 (CORRIDOR 209)
14 | PROJECT.3.3.5.6.5.2.1 | General Civil Access Dates-L1-Egress Corridors/201, 209A
14 | PROJECT.3.3.5.6.5.2.2 | MEP 1st Fix in Wall-L1-Egress Corridors/ 201, 209A
14 | PROJECT.3.3.5.6.5.2.3 | MEP 2nd Fix-L1-Egress Corridors/ 201, 209A
16 | PROJECT.3.3.5.6.5.2.3.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.2.3.2 | CHW piping Works
16 | PROJECT.3.3.5.6.5.2.3.3 | Electrical Works
16 | PROJECT.3.3.5.6.5.2.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.2.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.5.2.4 | MEP Final Fix-L1-Egress Corridors/ 201, 209A
16 | PROJECT.3.3.5.6.5.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.2.4.2 | Electrical Works
16 | PROJECT.3.3.5.6.5.2.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.2.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.5.4 | ZONE 04 (CORRIDOR 101)
14 | PROJECT.3.3.5.6.5.4.1 | General Civil Access Dates-GL-Egress Corridors/ 101, 701
14 | PROJECT.3.3.5.6.5.4.2 | MEP 1st Fix in Wall-L1-Egress Corridors/101, 701
14 | PROJECT.3.3.5.6.5.4.3 | MEP 2nd Fix-L1-Egress Corridors/101, 701
16 | PROJECT.3.3.5.6.5.4.3.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.4.3.2 | CHW piping Works
16 | PROJECT.3.3.5.6.5.4.3.3 | Electrical Works
16 | PROJECT.3.3.5.6.5.4.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.4.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.5.4.4 | MEP Final Fix-L1-Egress Corridors/ 101, 701
16 | PROJECT.3.3.5.6.5.4.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.4.4.2 | Electrical Works
16 | PROJECT.3.3.5.6.5.4.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.4.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.5.5 | ZONE 05 (CORRIDORS 707, 708)
14 | PROJECT.3.3.5.6.5.5.1 | General Civil Access Dates-L1-Egress Corridors/703, 707, 708
14 | PROJECT.3.3.5.6.5.5.2 | MEP 1st Fix in Wall-L1-Egress Corridors/ 703, 707, 708
14 | PROJECT.3.3.5.6.5.5.3 | MEP 2nd Fix-L1-Egress Corridors/ 703, 707, 708
16 | PROJECT.3.3.5.6.5.5.3.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.5.3.2 | CHW piping Works
16 | PROJECT.3.3.5.6.5.5.3.3 | Electrical Works
16 | PROJECT.3.3.5.6.5.5.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.5.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.5.5.4 | MEP Final Fix-L1-Egress Corridors/ 703, 707, 708
16 | PROJECT.3.3.5.6.5.5.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.5.4.2 | Electrical Works
16 | PROJECT.3.3.5.6.5.5.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.5.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.5.6 | ZONE 06 (CORRIDORS 301, 303)
14 | PROJECT.3.3.5.6.5.6.1 | General Civil Access Dates-L1-Egress Corridors/ 303
14 | PROJECT.3.3.5.6.5.6.2 | MEP 1st Fix in Wall-L1-Egress Corridors/ 303
14 | PROJECT.3.3.5.6.5.6.3 | MEP 2nd Fix-L1-Egress Corridors/ 303
16 | PROJECT.3.3.5.6.5.6.3.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.6.3.2 | CHW piping Works
16 | PROJECT.3.3.5.6.5.6.3.3 | Electrical Works
16 | PROJECT.3.3.5.6.5.6.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.6.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.5.6.4 | MEP Final Fix-L1-Egress Corridors/ 303
16 | PROJECT.3.3.5.6.5.6.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.6.4.2 | Electrical Works
16 | PROJECT.3.3.5.6.5.6.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.6.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.5.7 | ZONE 07 (CORRIDORS 601, 602)
14 | PROJECT.3.3.5.6.5.7.1 | General Civil Access Dates-L1-Egress Corridors/ 602
14 | PROJECT.3.3.5.6.5.7.2 | MEP 1st Fix in Wall-L1-Egress Corridors/ 602
14 | PROJECT.3.3.5.6.5.7.3 | MEP 2nd Fix-L1-Egress Corridors/ 602
16 | PROJECT.3.3.5.6.5.7.3.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.7.3.2 | CHW piping Works
16 | PROJECT.3.3.5.6.5.7.3.3 | Electrical Works
16 | PROJECT.3.3.5.6.5.7.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.7.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.5.7.4 | MEP Final Fix-L1-Egress Corridors/ 602
16 | PROJECT.3.3.5.6.5.7.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.7.4.2 | Electrical Works
16 | PROJECT.3.3.5.6.5.7.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.7.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.5.8 | ZONE 08 (CORRIDORS 801, 807)
14 | PROJECT.3.3.5.6.5.8.1 | General Civil Access Dates-L1-Egress Corridors/807
14 | PROJECT.3.3.5.6.5.8.2 | MEP 1st Fix in Wall-L1-Egress Corridors/807
14 | PROJECT.3.3.5.6.5.8.3 | MEP 2nd Fix-L1-Egress Corridors/807
16 | PROJECT.3.3.5.6.5.8.3.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.8.3.2 | CHW piping Works
16 | PROJECT.3.3.5.6.5.8.3.3 | Electrical Works
16 | PROJECT.3.3.5.6.5.8.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.8.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.5.8.4 | MEP Final Fix-L1-Egress Corridors/807
16 | PROJECT.3.3.5.6.5.8.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.8.4.2 | Electrical Works
16 | PROJECT.3.3.5.6.5.8.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.8.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.5.11 | ZONE 11 (CORRIDORS 401, 402)
14 | PROJECT.3.3.5.6.5.11.1 | General Civil Access Dates-L1-Egress Corridors/401, 402
14 | PROJECT.3.3.5.6.5.11.2 | MEP 1st Fix in Wall-L1-Egress Corridors/401, 402
14 | PROJECT.3.3.5.6.5.11.3 | MEP 2nd Fix-L1-Egress Corridors/401, 402
16 | PROJECT.3.3.5.6.5.11.3.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.11.3.2 | CHW piping Works
16 | PROJECT.3.3.5.6.5.11.3.3 | Electrical Works
16 | PROJECT.3.3.5.6.5.11.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.11.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.5.11.4 | MEP Final Fix-L1-Egress Corridors/401, 402
16 | PROJECT.3.3.5.6.5.11.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.11.4.2 | Electrical Works
16 | PROJECT.3.3.5.6.5.11.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.11.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.6.5.14 | ZONE 14 (CORRIDOR 511)
14 | PROJECT.3.3.5.6.5.14.1 | General Civil Access Dates-L1-Egress Corridors/507
14 | PROJECT.3.3.5.6.5.14.2 | MEP 1st Fix in Wall-L1-Egress Corridors/507
14 | PROJECT.3.3.5.6.5.14.3 | MEP 2nd Fix-L1-Egress Corridors/507
16 | PROJECT.3.3.5.6.5.14.3.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.14.3.2 | CHW piping Works
16 | PROJECT.3.3.5.6.5.14.3.3 | Electrical Works
16 | PROJECT.3.3.5.6.5.14.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.14.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.6.5.14.4 | MEP Final Fix-L1-Egress Corridors/507
16 | PROJECT.3.3.5.6.5.14.4.1 | HVAC Works
16 | PROJECT.3.3.5.6.5.14.4.2 | Electrical Works
16 | PROJECT.3.3.5.6.5.14.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.6.5.14.4.4 | Plumbing & Drainage Works
8 | PROJECT.3.3.5.7 | LEVEL-02 PODIUM PARKING-01 (PP-01)
10 | PROJECT.3.3.5.7.9 | L2-PP-1-Wet Areas/ Female Prayer Room
12 | PROJECT.3.3.5.7.9.3 | General Civil Access Dates-L2-PP-1-Wet Areas/ Prayer Rooms
12 | PROJECT.3.3.5.7.9.2 | MEP 1st Fix in Wall-L2-PP-1-Wet Areas/ Prayer Rooms
12 | PROJECT.3.3.5.7.9.4 | MEP 2nd Fix-L2-PP-1-Wet Areas/ Prayer Rooms
14 | PROJECT.3.3.5.7.9.4.1 | HVAC Works
14 | PROJECT.3.3.5.7.9.4.2 | CHW piping Works
14 | PROJECT.3.3.5.7.9.4.3 | Electrical Works
14 | PROJECT.3.3.5.7.9.4.4 | Fire Fighting Works
14 | PROJECT.3.3.5.7.9.4.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.9.7 | MEP Final Fix-L2-PP-1-Wet Areas/ Prayer Rooms
14 | PROJECT.3.3.5.7.9.7.1 | HVAC Works
14 | PROJECT.3.3.5.7.9.7.3 | Electrical Works
14 | PROJECT.3.3.5.7.9.7.4 | Fire Fighting Works
14 | PROJECT.3.3.5.7.9.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.7.1 | L2-PP-1-Wet Areas in Section A (Excluding Food Court - T-Z03)
12 | PROJECT.3.3.5.7.1.1 | T-Z01
14 | PROJECT.3.3.5.7.1.1.3 | General Civil Access Dates-L2-PP-1-Wet Areas/ T-Z01
14 | PROJECT.3.3.5.7.1.1.2 | MEP 1st Fix in Wall-L2-PP-1-Wet Areas/T-Z01
14 | PROJECT.3.3.5.7.1.1.4 | MEP 2nd Fix-L2-PP-1-Wet Areas/T-Z01
16 | PROJECT.3.3.5.7.1.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.1.1.4.2 | CHW piping Works
16 | PROJECT.3.3.5.7.1.1.4.3 | Electrical Works
16 | PROJECT.3.3.5.7.1.1.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.1.1.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.1.1.7 | MEP Final Fix-L2-PP-1-Wet Areas/ T-Z01
16 | PROJECT.3.3.5.7.1.1.7.1 | HVAC Works
16 | PROJECT.3.3.5.7.1.1.7.3 | Electrical Works
16 | PROJECT.3.3.5.7.1.1.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.1.1.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.1.2 | T-08N
14 | PROJECT.3.3.5.7.1.2.3 | General Civil Access Dates-L2-PP-1-Wet Areas/ T-08N
14 | PROJECT.3.3.5.7.1.2.2 | MEP 1st Fix in Wall-L2-PP-1-Wet Areas/T-08N
14 | PROJECT.3.3.5.7.1.2.4 | MEP 2nd Fix-L2-PP-1-Wet Areas/T-08N
16 | PROJECT.3.3.5.7.1.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.1.2.4.2 | CHW piping Works
16 | PROJECT.3.3.5.7.1.2.4.3 | Electrical Works
16 | PROJECT.3.3.5.7.1.2.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.1.2.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.1.2.7 | MEP Final Fix-L2-PP-1-Wet Areas/T-08N
16 | PROJECT.3.3.5.7.1.2.7.1 | HVAC Works
16 | PROJECT.3.3.5.7.1.2.7.3 | Electrical Works
16 | PROJECT.3.3.5.7.1.2.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.1.2.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.1.3 | T-08S
14 | PROJECT.3.3.5.7.1.3.3 | General Civil Access Dates-L2-PP-1-Wet Areas/T-08S
14 | PROJECT.3.3.5.7.1.3.2 | MEP 1st Fix in Wall-L2-PP-1-Wet Areas/T-08S
14 | PROJECT.3.3.5.7.1.3.4 | MEP 2nd Fix-L2-PP-1-Wet Areas/T-08S
16 | PROJECT.3.3.5.7.1.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.1.3.4.2 | CHW piping Works
16 | PROJECT.3.3.5.7.1.3.4.3 | Electrical Works
16 | PROJECT.3.3.5.7.1.3.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.1.3.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.1.3.7 | MEP Final Fix-L2-PP-1-Wet Areas/T-08S
16 | PROJECT.3.3.5.7.1.3.7.1 | HVAC Works
16 | PROJECT.3.3.5.7.1.3.7.3 | Electrical Works
16 | PROJECT.3.3.5.7.1.3.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.1.3.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.7.4 | BOH
12 | PROJECT.3.3.5.7.4.2 | L2-PP-1-Offices
14 | PROJECT.3.3.5.7.4.2.3 | General Civil Access Dates-L2-PP-1-Offices
14 | PROJECT.3.3.5.7.4.2.2 | MEP 1st Fix in Wall-L2-PP-1-Offices
14 | PROJECT.3.3.5.7.4.2.4 | MEP 2nd Fix-L2-PP-1-Offices
16 | PROJECT.3.3.5.7.4.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.4.2.4.2 | CHW piping Works
16 | PROJECT.3.3.5.7.4.2.4.3 | Electrical Works
16 | PROJECT.3.3.5.7.4.2.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.4.2.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.4.2.7 | MEP Final Fix-L2-PP-1-Offices
16 | PROJECT.3.3.5.7.4.2.7.1 | HVAC Works
16 | PROJECT.3.3.5.7.4.2.7.3 | Electrical Works
16 | PROJECT.3.3.5.7.4.2.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.4.2.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.4.8 | L2-PP-1-Electrical/ELV Rooms
14 | PROJECT.3.3.5.7.4.8.2 | L2-PP-1-Electrical Room-604/UTT RM/BMS RM/BATRM
16 | PROJECT.3.3.5.7.4.8.2.3 | General Civil Access Dates-L2-PP-1-Electrical Room-604/UTT RM/BMS RM/BATRM
16 | PROJECT.3.3.5.7.4.8.2.2 | MEP 1st Fix in Wall-L2-PP-1-Electrical Room-604/UTT RM/BMS RM/BATRM
16 | PROJECT.3.3.5.7.4.8.2.4 | MEP 2nd Fix-L2-PP-1-Electrical Room-604/UTT RM/BMS RM/BATRM
18 | PROJECT.3.3.5.7.4.8.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.2.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.4.8.2.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.2.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.2.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.8.2.7 | MEP Final Fix-L2-PP-1-Electrical Room-604/UTT RM/BMS RM/BATRM
18 | PROJECT.3.3.5.7.4.8.2.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.2.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.2.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.2.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.4.8.1 | L2-PP-1-Electrical Room-104/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.1.3 | General Civil Access Dates-L2-PP-1-Electrical Room-104/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.1.2 | MEP 1st Fix in Wall-L2-PP-1-Electrical Room-104/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.1.4 | MEP 2nd Fix-L2-PP-1-Electrical Room-104/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.1.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.4.8.1.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.1.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.1.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.8.1.7 | MEP Final Fix-L2-PP-1-Electrical Room-104/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.1.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.1.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.1.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.1.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.4.8.3 | L2-PP-1-Electrical Room-205/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.3.3 | General Civil Access Dates-L2-PP-1-Electrical Room-205/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.3.2 | MEP 1st Fix in Wall-L2-PP-1-Electrical Room-205/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.3.4 | MEP 2nd Fix-L2-PP-1-Electrical Room-205/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.3.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.4.8.3.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.3.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.3.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.8.3.7 | MEP Final Fix-L2-PP-1-Electrical Room-205/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.3.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.3.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.3.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.3.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.4.8.4 | L2-PP-1-Electrical Room-917/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.4.3 | General Civil Access Dates-L2-PP-1-Electrical Room-917/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.4.2 | MEP 1st Fix in Wall-L2-PP-1-Electrical Room-917/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.4.4 | MEP 2nd Fix-L2-PP-1-Electrical Room-917/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.4.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.4.8.4.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.4.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.4.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.8.4.7 | MEP Final Fix-L2-PP-1-Electrical Room-917/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.4.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.4.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.4.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.4.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.4.8.5 | L2-PP-1-Electrical Room-305/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.5.3 | General Civil Access Dates-L2-PP-1-Electrical Room-305/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.5.2 | MEP 1st Fix in Wall-L2-PP-1-Electrical Room-305/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.5.4 | MEP 2nd Fix-L2-PP-1-Electrical Room-305/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.5.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.5.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.4.8.5.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.5.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.5.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.8.5.7 | MEP Final Fix-L2-PP-1-Electrical Room-305/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.5.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.5.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.5.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.5.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.4.8.6 | L2-PP-1-Electrical Room-712/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.6.3 | General Civil Access Dates-L2-PP-1-Electrical Room-712/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.6.2 | MEP 1st Fix in Wall-L2-PP-1-Electrical Room-712/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.6.4 | MEP 2nd Fix-L2-PP-1-Electrical Room-712/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.6.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.6.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.4.8.6.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.6.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.6.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.8.6.7 | MEP Final Fix-L2-PP-1-Electrical Room-712/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.6.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.6.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.6.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.6.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.4.8.7 | L2-PP-1-Electrical Room-904/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.7.3 | General Civil Access Dates-L2-PP-1-Electrical Room-904/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.7.2 | MEP 1st Fix in Wall-L2-PP-1-Electrical Room-904/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.7.4.8.7.4 | MEP 2nd Fix-L2-PP-1-Electrical Room-904/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.7.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.7.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.4.8.7.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.7.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.7.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.8.7.7 | MEP Final Fix-L2-PP-1-Electrical Room-904/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.7.4.8.7.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.7.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.7.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.7.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.4.8.8 | L2-PP-1-UTT RM 705/ BMS RM/Lobby/Staircase/Lift room-703
16 | PROJECT.3.3.5.7.4.8.8.3 | General Civil Access Dates-L2-PP-1-UTT RM 705/ BMS RM/Lobby/Staircase/Lift room-703
16 | PROJECT.3.3.5.7.4.8.8.2 | MEP 1st Fix in Wall-L2-PP-1-UTT RM 705/ BMS RM/Lobby/Staircase/Lift room-703
16 | PROJECT.3.3.5.7.4.8.8.4 | MEP 2nd Fix-L2-PP-1-UTT RM 705/BMS RM/Lobby/Staircase/Lift room-703
18 | PROJECT.3.3.5.7.4.8.8.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.8.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.4.8.8.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.8.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.8.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.8.8.7 | MEP Final Fix-L2-PP-1-UTT RM 705/ BMS RM/Lobby/Staircase/Lift room-703
18 | PROJECT.3.3.5.7.4.8.8.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.8.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.8.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.8.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.4.8.9 | L2-PP-1-UTT RM 816, Electrical Room-802/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.7.4.8.9.3 | General Civil Access Dates-L2-PP-1-UTT RM 816, Electrical Room-802/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.7.4.8.9.2 | MEP 1st Fix in Wall-L2-PP-1-UTT RM 816, Electrical Room-802/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.7.4.8.9.4 | MEP 2nd Fix-L2-PP-1-UTT RM 816, Electrical Room-802/BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.7.4.8.9.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.9.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.4.8.9.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.9.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.9.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.8.9.7 | MEP Final Fix-L2-PP-1-UTT RM 816, Electrical Room-802/BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.7.4.8.9.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.4.8.9.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.4.8.9.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.4.8.9.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.4.12 | L2-PP-1-Plant Rooms
14 | PROJECT.3.3.5.7.4.12.3 | General Civil Access Dates-PP-01-907,913 & 917
14 | PROJECT.3.3.5.7.4.12.2 | MEP 1st Fix in Wall-PP-01-907,913 & 917
14 | PROJECT.3.3.5.7.4.12.4 | MEP 2nd Fix-PP-01-907,913 & 917
16 | PROJECT.3.3.5.7.4.12.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.4.12.4.2 | CHW piping Works
16 | PROJECT.3.3.5.7.4.12.4.3 | Electrical Works
16 | PROJECT.3.3.5.7.4.12.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.4.12.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.4.12.4.6 | Water Supply Works
14 | PROJECT.3.3.5.7.4.12.7 | MEP Final Fix-PP-01-907,913 & 917
16 | PROJECT.3.3.5.7.4.12.7.1 | HVAC Works
16 | PROJECT.3.3.5.7.4.12.7.3 | Electrical Works
16 | PROJECT.3.3.5.7.4.12.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.4.12.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.7.5 | FOH
12 | PROJECT.3.3.5.7.5.8 | LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.7.5.8.3 | General Civil Access Dates-L2-PP-1-UTT RM 705/ BMS RM/Lobby/Staircase/Lift room-703
14 | PROJECT.3.3.5.7.5.8.2 | MEP 1st Fix in Wall-L2-PP-1-UTT RM 705/ BMS RM/Lobby/Staircase/Lift room-703
14 | PROJECT.3.3.5.7.5.8.4 | MEP 2nd Fix-L2-PP-1-UTT RM 705/BMS RM/Lobby/Staircase/Lift room-703
16 | PROJECT.3.3.5.7.5.8.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.5.8.4.2 | CHW piping Works
16 | PROJECT.3.3.5.7.5.8.4.3 | Electrical Works
16 | PROJECT.3.3.5.7.5.8.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.5.8.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.5.8.7 | MEP Final Fix-L2-PP-1-UTT RM 705/ BMS RM/Lobby/Staircase/Lift room-703
16 | PROJECT.3.3.5.7.5.8.7.1 | HVAC Works
16 | PROJECT.3.3.5.7.5.8.7.3 | Electrical Works
16 | PROJECT.3.3.5.7.5.8.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.5.8.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.5.3 | L2-PP-1-The Mall Concourse
14 | PROJECT.3.3.5.7.5.3.9 | L2-Dynamic West
16 | PROJECT.3.3.5.7.5.3.9.3 | General Civil Access Dates
16 | PROJECT.3.3.5.7.5.3.9.2 | MEP 1st Fix in Wall
16 | PROJECT.3.3.5.7.5.3.9.4 | MEP 2nd Fix
18 | PROJECT.3.3.5.7.5.3.9.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.5.3.9.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.5.3.9.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.5.3.9.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.5.3.9.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.5.3.9.7 | MEP Final Fix
18 | PROJECT.3.3.5.7.5.3.9.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.5.3.9.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.5.3.9.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.5.3.9.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.5.3.6 | L2-Urban West
16 | PROJECT.3.3.5.7.5.3.6.3 | General Civil Access Dates
16 | PROJECT.3.3.5.7.5.3.6.2 | MEP 1st Fix in Wall
16 | PROJECT.3.3.5.7.5.3.6.4 | MEP 2nd Fix
18 | PROJECT.3.3.5.7.5.3.6.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.5.3.6.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.5.3.6.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.5.3.6.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.5.3.6.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.5.3.6.7 | MEP Final Fix
18 | PROJECT.3.3.5.7.5.3.6.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.5.3.6.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.5.3.6.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.5.3.6.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.5.3.10 | L2-Mangrove
16 | PROJECT.3.3.5.7.5.3.10.3 | General Civil Access Dates
16 | PROJECT.3.3.5.7.5.3.10.2 | MEP 1st Fix in Wall
16 | PROJECT.3.3.5.7.5.3.10.4 | MEP 2nd Fix
18 | PROJECT.3.3.5.7.5.3.10.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.5.3.10.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.5.3.10.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.5.3.10.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.5.3.10.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.5.3.10.7 | MEP Final Fix
18 | PROJECT.3.3.5.7.5.3.10.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.5.3.10.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.5.3.10.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.5.3.10.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.5.3.8 | L2-West Mall
16 | PROJECT.3.3.5.7.5.3.8.3 | General Civil Access Dates
16 | PROJECT.3.3.5.7.5.3.8.2 | MEP 1st Fix in Wall
16 | PROJECT.3.3.5.7.5.3.8.4 | MEP 2nd Fix
18 | PROJECT.3.3.5.7.5.3.8.4.1 | HVAC Works
18 | PROJECT.3.3.5.7.5.3.8.4.2 | CHW piping Works
18 | PROJECT.3.3.5.7.5.3.8.4.3 | Electrical Works
18 | PROJECT.3.3.5.7.5.3.8.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.5.3.8.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.7.5.3.8.7 | MEP Final Fix
18 | PROJECT.3.3.5.7.5.3.8.7.1 | HVAC Works
18 | PROJECT.3.3.5.7.5.3.8.7.3 | Electrical Works
18 | PROJECT.3.3.5.7.5.3.8.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.7.5.3.8.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.5.6 | L2-PP-1-Food Court and Toilet T-Z03
14 | PROJECT.3.3.5.7.5.6.3 | General Civil Access Dates-L2-PP-1-Food Court and Toilet T-Z03
14 | PROJECT.3.3.5.7.5.6.2 | MEP 1st Fix in Wall-L2-PP-1-Food Court and Toilet T-Z03
14 | PROJECT.3.3.5.7.5.6.4 | MEP 2nd Fix-L2-PP-1-Food Court and Toilet T-Z03
16 | PROJECT.3.3.5.7.5.6.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.5.6.4.2 | CHW piping Works
16 | PROJECT.3.3.5.7.5.6.4.3 | Electrical Works
16 | PROJECT.3.3.5.7.5.6.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.5.6.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.5.6.7 | MEP Final Fix-L2-PP-1-Food Court and Toilet T-Z03
16 | PROJECT.3.3.5.7.5.6.7.1 | HVAC Works
16 | PROJECT.3.3.5.7.5.6.7.3 | Electrical Works
16 | PROJECT.3.3.5.7.5.6.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.5.6.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.7.2 | PP-02-Car Parks
12 | PROJECT.3.3.5.7.2.3 | General Civil Access Dates-PP-02-Car Parks
12 | PROJECT.3.3.5.7.2.2 | MEP 1st Fix in Wall-PP-02-Car Parks
12 | PROJECT.3.3.5.7.2.4 | MEP 2nd Fix-PP-02-Car Parks
14 | PROJECT.3.3.5.7.2.4.1 | HVAC Works
14 | PROJECT.3.3.5.7.2.4.2 | CHW piping Works
14 | PROJECT.3.3.5.7.2.4.3 | Electrical Works
14 | PROJECT.3.3.5.7.2.4.4 | Fire Fighting Works
14 | PROJECT.3.3.5.7.2.4.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.2.7 | MEP Final Fix-PP-02-Car Parks
14 | PROJECT.3.3.5.7.2.7.1 | HVAC Works
14 | PROJECT.3.3.5.7.2.7.3 | Electrical Works
14 | PROJECT.3.3.5.7.2.7.4 | Fire Fighting Works
14 | PROJECT.3.3.5.7.2.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.7.12 | STAIRCASES L2/PP1 TO L3/PP2 SECTION A
12 | PROJECT.3.3.5.7.12.9 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.3.5.7.12.4 | ACCESS STAIRCASES ST01
10 | PROJECT.3.3.5.7.3 | STAIRCASES L2/PP1 TO L3/PP2 SECTION B
12 | PROJECT.3.3.5.7.3.9 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.3.5.7.3.4 | ACCESS STAIRCASES ST16, ST18
10 | PROJECT.3.3.5.7.11 | STAIRCASES L2/PP1 TO L3/PP2 SECTION C
12 | PROJECT.3.3.5.7.11.9 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.3.5.7.11.4 | ACCESS STAIRCASES ST25, ST33
10 | PROJECT.3.3.5.7.6 | EGRESS CORRIDORS
12 | PROJECT.3.3.5.7.6.9 | ZONE 03 (CORRIDOR 822)
14 | PROJECT.3.3.5.7.6.9.1 | General Civil Access Dates-L2-Egress Corridors/822
14 | PROJECT.3.3.5.7.6.9.2 | MEP 1st Fix in Wall-L2-Egress Corridors/822
14 | PROJECT.3.3.5.7.6.9.3 | MEP 2nd Fix-L2-Egress Corridors/822
16 | PROJECT.3.3.5.7.6.9.3.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.9.3.2 | CHW piping Works
16 | PROJECT.3.3.5.7.6.9.3.3 | Electrical Works
16 | PROJECT.3.3.5.7.6.9.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.9.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.6.9.4 | MEP Final Fix-L2-Egress Corridors/822
16 | PROJECT.3.3.5.7.6.9.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.9.4.2 | Electrical Works
16 | PROJECT.3.3.5.7.6.9.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.9.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.6.4 | ZONE 04 (CORRIDORS 101, 701)
14 | PROJECT.3.3.5.7.6.4.1 | General Civil Access Dates-L2-Egress Corridors/101, 701, 710
14 | PROJECT.3.3.5.7.6.4.2 | MEP 1st Fix in Wall-L2-Egress Corridors/101, 701, 710
14 | PROJECT.3.3.5.7.6.4.3 | MEP 2nd Fix-L2-Egress Corridors/101, 701, 710
16 | PROJECT.3.3.5.7.6.4.3.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.4.3.2 | CHW piping Works
16 | PROJECT.3.3.5.7.6.4.3.3 | Electrical Works
16 | PROJECT.3.3.5.7.6.4.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.4.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.6.4.4 | MEP Final Fix-L2-Egress Corridors/101, 701, 710
16 | PROJECT.3.3.5.7.6.4.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.4.4.2 | Electrical Works
16 | PROJECT.3.3.5.7.6.4.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.4.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.6.8 | ZONE 04 (CORRIDOR 701)
14 | PROJECT.3.3.5.7.6.8.1 | General Civil Access Dates-L2-Egress Corridors/823, 901, 920
14 | PROJECT.3.3.5.7.6.8.2 | MEP 1st Fix in Wall-L2-Egress Corridors/823, 901, 920
14 | PROJECT.3.3.5.7.6.8.3 | MEP 2nd Fix-L2-Egress Corridors/823, 901, 920
16 | PROJECT.3.3.5.7.6.8.3.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.8.3.2 | CHW piping Works
16 | PROJECT.3.3.5.7.6.8.3.3 | Electrical Works
16 | PROJECT.3.3.5.7.6.8.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.8.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.6.8.4 | MEP Final Fix-L2-Egress Corridors/823, 901, 920
16 | PROJECT.3.3.5.7.6.8.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.8.4.2 | Electrical Works
16 | PROJECT.3.3.5.7.6.8.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.8.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.6.3 | ZONE 05 (CORRIDORS 707, 710)
14 | PROJECT.3.3.5.7.6.3.1 | General Civil Access Dates-L2-Egress Corridors/703, 716
14 | PROJECT.3.3.5.7.6.3.2 | MEP 1st Fix in Wall-L2-Egress Corridors/703, 716
14 | PROJECT.3.3.5.7.6.3.3 | MEP 2nd Fix-L2-Egress Corridors/703, 716
16 | PROJECT.3.3.5.7.6.3.3.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.3.3.2 | CHW piping Works
16 | PROJECT.3.3.5.7.6.3.3.3 | Electrical Works
16 | PROJECT.3.3.5.7.6.3.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.3.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.6.3.4 | MEP Final Fix-L2-Egress Corridors/703, 716
16 | PROJECT.3.3.5.7.6.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.3.4.2 | Electrical Works
16 | PROJECT.3.3.5.7.6.3.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.3.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.6.5 | ZONE 06 (CORRIDORS 301, 303)
14 | PROJECT.3.3.5.7.6.5.1 | General Civil Access Dates-L2-Egress Corridors/303, 308
14 | PROJECT.3.3.5.7.6.5.2 | MEP 1st Fix in Wall-L2-Egress Corridors/303, 308
14 | PROJECT.3.3.5.7.6.5.3 | MEP 2nd Fix-L2-Egress Corridors/303, 308
16 | PROJECT.3.3.5.7.6.5.3.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.5.3.2 | CHW piping Works
16 | PROJECT.3.3.5.7.6.5.3.3 | Electrical Works
16 | PROJECT.3.3.5.7.6.5.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.5.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.6.5.4 | MEP Final Fix-L2-Egress Corridors/303, 308
16 | PROJECT.3.3.5.7.6.5.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.5.4.2 | Electrical Works
16 | PROJECT.3.3.5.7.6.5.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.5.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.6.6 | ZONE 07 (CORRIDORS 602)
14 | PROJECT.3.3.5.7.6.6.1 | General Civil Access Dates-L2-Egress Corridors/ 602
14 | PROJECT.3.3.5.7.6.6.2 | MEP 1st Fix in Wall-L2-Egress Corridors/ 602
14 | PROJECT.3.3.5.7.6.6.3 | MEP 2nd Fix-L2-Egress Corridors/ 602
16 | PROJECT.3.3.5.7.6.6.3.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.6.3.2 | CHW piping Works
16 | PROJECT.3.3.5.7.6.6.3.3 | Electrical Works
16 | PROJECT.3.3.5.7.6.6.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.6.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.6.6.4 | MEP Final Fix-L2-Egress Corridors/ 602
16 | PROJECT.3.3.5.7.6.6.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.6.4.2 | Electrical Works
16 | PROJECT.3.3.5.7.6.6.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.6.4.4 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.7.6.7 | ZONE 08 (CORRIDORS 806, 807)
14 | PROJECT.3.3.5.7.6.7.1 | General Civil Access Dates-L2-Egress Corridors/806, 807, 814
14 | PROJECT.3.3.5.7.6.7.2 | MEP 1st Fix in Wall-L2-Egress Corridors/806, 807, 814
14 | PROJECT.3.3.5.7.6.7.3 | MEP 2nd Fix-L2-Egress Corridors/806, 807, 814
16 | PROJECT.3.3.5.7.6.7.3.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.7.3.2 | CHW piping Works
16 | PROJECT.3.3.5.7.6.7.3.3 | Electrical Works
16 | PROJECT.3.3.5.7.6.7.3.4 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.7.3.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.7.6.7.4 | MEP Final Fix-L2-Egress Corridors/806, 807, 814
16 | PROJECT.3.3.5.7.6.7.4.1 | HVAC Works
16 | PROJECT.3.3.5.7.6.7.4.2 | Electrical Works
16 | PROJECT.3.3.5.7.6.7.4.3 | Fire Fighting Works
16 | PROJECT.3.3.5.7.6.7.4.4 | Plumbing & Drainage Works
8 | PROJECT.3.3.5.8 | LEVEL-03 PODIUM PARKING-02 (PP-02)
10 | PROJECT.3.3.5.8.9 | L3-PP-02-Car Parks
12 | PROJECT.3.3.5.8.9.3 | General Civil Access Dates-PP-02-Car Parks
12 | PROJECT.3.3.5.8.9.2 | MEP 1st Fix in Wall-PP-02-Car Parks
12 | PROJECT.3.3.5.8.9.4 | MEP 2nd Fix-PP-02-Car Parks
14 | PROJECT.3.3.5.8.9.4.1 | HVAC Works
14 | PROJECT.3.3.5.8.9.4.2 | CHW piping Works
14 | PROJECT.3.3.5.8.9.4.3 | Electrical Works
14 | PROJECT.3.3.5.8.9.4.4 | Fire Fighting Works
14 | PROJECT.3.3.5.8.9.4.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.8.9.7 | MEP Final Fix-PP-02-Car Parks
14 | PROJECT.3.3.5.8.9.7.1 | HVAC Works
14 | PROJECT.3.3.5.8.9.7.3 | Electrical Works
14 | PROJECT.3.3.5.8.9.7.4 | Fire Fighting Works
14 | PROJECT.3.3.5.8.9.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.8.1 | BOH
12 | PROJECT.3.3.5.8.1.8 | L3-PP-02-Electrical/ELV Rooms
14 | PROJECT.3.3.5.8.1.8.6 | L3 PP-02-Electrical Room-904,913/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.8.1.8.6.3 | General Civil Access Dates-Electrical Room-PP2-904,913/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.8.1.8.6.2 | MEP 1st Fix in Wall-Electrical Room-PP2-904,913/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.8.1.8.6.4 | MEP 2nd Fix-Electrical Room-PP2-904,913/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.8.1.8.6.4.1 | HVAC Works
18 | PROJECT.3.3.5.8.1.8.6.4.2 | CHW piping Works
18 | PROJECT.3.3.5.8.1.8.6.4.3 | Electrical Works
18 | PROJECT.3.3.5.8.1.8.6.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.8.1.8.6.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.8.1.8.6.7 | MEP Final Fix-Electrical Room-PP2-904,913/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.8.1.8.6.7.1 | HVAC Works
18 | PROJECT.3.3.5.8.1.8.6.7.3 | Electrical Works
18 | PROJECT.3.3.5.8.1.8.6.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.8.1.8.6.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.8.1.8.7 | L3 PP-02-Electrical Room-802/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.8.1.8.7.3 | General Civil Access Dates-L3-802/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.8.1.8.7.2 | MEP 1st Fix in Wall-L3-802/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.8.1.8.7.4 | MEP 2nd Fix-L3-802/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.8.1.8.7.4.1 | HVAC Works
18 | PROJECT.3.3.5.8.1.8.7.4.2 | CHW piping Works
18 | PROJECT.3.3.5.8.1.8.7.4.3 | Electrical Works
18 | PROJECT.3.3.5.8.1.8.7.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.8.1.8.7.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.8.1.8.7.7 | MEP Final Fix-L3-802/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.8.1.8.7.7.1 | HVAC Works
18 | PROJECT.3.3.5.8.1.8.7.7.3 | Electrical Works
18 | PROJECT.3.3.5.8.1.8.7.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.8.1.8.7.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.8.1.12 | L3-PP-02-Plant Rooms-914 & 907
14 | PROJECT.3.3.5.8.1.12.3 | General Civil Access Dates-PP-04-914 & 907
14 | PROJECT.3.3.5.8.1.12.2 | MEP 1st Fix in Wall-PP-04-914 & 907
14 | PROJECT.3.3.5.8.1.12.4 | MEP 2nd Fix-PP-04-914 & 907
16 | PROJECT.3.3.5.8.1.12.4.1 | HVAC Works
16 | PROJECT.3.3.5.8.1.12.4.2 | CHW piping Works
16 | PROJECT.3.3.5.8.1.12.4.3 | Electrical Works
16 | PROJECT.3.3.5.8.1.12.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.8.1.12.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.8.1.12.4.6 | Water Supply Works
14 | PROJECT.3.3.5.8.1.12.7 | MEP Final Fix-PP-04-914 & 907
16 | PROJECT.3.3.5.8.1.12.7.1 | HVAC Works
16 | PROJECT.3.3.5.8.1.12.7.3 | Electrical Works
16 | PROJECT.3.3.5.8.1.12.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.8.1.12.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.8.1.6 | L3 PP-02-UTT Rooms
14 | PROJECT.3.3.5.8.1.6.1 | L3 PP-02-UTT RM-705/BMS RM/Lobby/Staircase/Lift room L3 706
16 | PROJECT.3.3.5.8.1.6.1.3 | General Civil Access Dates-UTT RM-705
16 | PROJECT.3.3.5.8.1.6.1.2 | MEP 1st Fix in Wall-UTT RM-705
16 | PROJECT.3.3.5.8.1.6.1.4 | MEP 2nd Fix-UTT RM-705
18 | PROJECT.3.3.5.8.1.6.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.8.1.6.1.4.2 | CHW piping Works
18 | PROJECT.3.3.5.8.1.6.1.4.3 | Electrical Works
18 | PROJECT.3.3.5.8.1.6.1.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.8.1.6.1.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.8.1.6.1.7 | MEP Final Fix-UTT RM-705
18 | PROJECT.3.3.5.8.1.6.1.7.1 | HVAC Works
18 | PROJECT.3.3.5.8.1.6.1.7.3 | Electrical Works
18 | PROJECT.3.3.5.8.1.6.1.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.8.1.6.1.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.8.1.6.3 | L3 PP-02-UTT RM-814/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.8.1.6.3.3 | General Civil Access Dates-UTT RM-814/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.8.1.6.3.2 | MEP 1st Fix in Wall-UTT RM-814/BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.8.1.6.3.4 | MEP 2nd Fix-UTT RM-814/BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.8.1.6.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.8.1.6.3.4.2 | CHW piping Works
18 | PROJECT.3.3.5.8.1.6.3.4.3 | Electrical Works
18 | PROJECT.3.3.5.8.1.6.3.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.8.1.6.3.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.8.1.6.3.7 | MEP Final Fix-UTT RM-814/BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.8.1.6.3.7.1 | HVAC Works
18 | PROJECT.3.3.5.8.1.6.3.7.3 | Electrical Works
18 | PROJECT.3.3.5.8.1.6.3.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.8.1.6.3.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.8.2 | L3-PP-2-Wet Areas/Male Prayer Room
12 | PROJECT.3.3.5.8.2.3 | General Civil Access Dates-L3-PP-2-Wet Areas/Male Prayer Room
12 | PROJECT.3.3.5.8.2.2 | MEP 1st Fix in Wall-L3-PP-2-Wet Areas/Male Prayer Room
12 | PROJECT.3.3.5.8.2.4 | MEP 2nd Fix-L3-PP-2-Wet Areas/Male Prayer Room
14 | PROJECT.3.3.5.8.2.4.1 | HVAC Works
14 | PROJECT.3.3.5.8.2.4.2 | CHW piping Works
14 | PROJECT.3.3.5.8.2.4.3 | Electrical Works
14 | PROJECT.3.3.5.8.2.4.4 | Fire Fighting Works
14 | PROJECT.3.3.5.8.2.4.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.8.2.7 | MEP Final Fix-L3-PP-2-Wet Areas/Male Prayer Room
14 | PROJECT.3.3.5.8.2.7.1 | HVAC Works
14 | PROJECT.3.3.5.8.2.7.3 | Electrical Works
14 | PROJECT.3.3.5.8.2.7.4 | Fire Fighting Works
14 | PROJECT.3.3.5.8.2.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.8.6 | FOH LOBBIES
12 | PROJECT.3.3.5.8.6.3 | LOBBY 02 Zone 07&09
14 | PROJECT.3.3.5.8.6.3.3 | General Civil Access Dates-LOBBY 02 Zone 07&09
14 | PROJECT.3.3.5.8.6.3.2 | MEP 1st Fix in Wall-LOBBY 02 Zone 07&09
14 | PROJECT.3.3.5.8.6.3.4 | MEP 2nd Fix-LOBBY 02 Zone 07&09
16 | PROJECT.3.3.5.8.6.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.8.6.3.4.2 | CHW piping Works
16 | PROJECT.3.3.5.8.6.3.4.3 | Electrical Works
16 | PROJECT.3.3.5.8.6.3.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.8.6.3.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.8.6.3.7 | MEP Final Fix-LOBBY 02 Zone 07&09
16 | PROJECT.3.3.5.8.6.3.7.1 | HVAC Works
16 | PROJECT.3.3.5.8.6.3.7.3 | Electrical Works
16 | PROJECT.3.3.5.8.6.3.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.8.6.3.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.8.6.4 | LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.8.6.4.3 | General Civil Access Dates-LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.8.6.4.2 | MEP 1st Fix in Wall-LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.8.6.4.4 | MEP 2nd Fix-LOBBY 03 Zone 10&13
16 | PROJECT.3.3.5.8.6.4.4.1 | HVAC Works
16 | PROJECT.3.3.5.8.6.4.4.2 | CHW piping Works
16 | PROJECT.3.3.5.8.6.4.4.3 | Electrical Works
16 | PROJECT.3.3.5.8.6.4.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.8.6.4.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.8.6.4.7 | MEP Final Fix-LOBBY 03 Zone 10&13
16 | PROJECT.3.3.5.8.6.4.7.1 | HVAC Works
16 | PROJECT.3.3.5.8.6.4.7.3 | Electrical Works
16 | PROJECT.3.3.5.8.6.4.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.8.6.4.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.8.6.5 | LOBBY 04 Zone 11
14 | PROJECT.3.3.5.8.6.5.3 | General Civil Access Dates-LOBBY 04 Zone 11
14 | PROJECT.3.3.5.8.6.5.2 | MEP 1st Fix in Wall-LOBBY 04 Zone 11
14 | PROJECT.3.3.5.8.6.5.4 | MEP 2nd Fix-LOBBY 04 Zone 11
16 | PROJECT.3.3.5.8.6.5.4.1 | HVAC Works
16 | PROJECT.3.3.5.8.6.5.4.2 | CHW piping Works
16 | PROJECT.3.3.5.8.6.5.4.3 | Electrical Works
16 | PROJECT.3.3.5.8.6.5.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.8.6.5.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.8.6.5.7 | MEP Final Fix-LOBBY 04 Zone 11
16 | PROJECT.3.3.5.8.6.5.7.1 | HVAC Works
16 | PROJECT.3.3.5.8.6.5.7.3 | Electrical Works
16 | PROJECT.3.3.5.8.6.5.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.8.6.5.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.8.3 | STAIRCASES PP3 TO PP4 SECTION A
12 | PROJECT.3.3.5.8.3.6 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.3.5.8.3.1 | ACCESS STAIRCASES ST18, ST25, ST33
10 | PROJECT.3.3.5.8.4 | STAIRCASES PP3 TO PP4 SECTION B
12 | PROJECT.3.3.5.8.4.6 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.3.5.8.4.1 | ACCESS STAIRCASES ST18, ST25, ST33
10 | PROJECT.3.3.5.8.5 | STAIRCASES PP3 TO PP4 SECTION C
12 | PROJECT.3.3.5.8.5.6 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.3.5.8.5.1 | ACCESS STAIRCASES ST18, ST25, ST33
8 | PROJECT.3.3.5.9 | PODIUM PARKING 3 (PP-03)
10 | PROJECT.3.3.5.9.1 | PP-03-Car Parks
12 | PROJECT.3.3.5.9.1.3 | General Civil Access Dates-PP-03-Car Parks
12 | PROJECT.3.3.5.9.1.2 | MEP 1st Fix in Wall-PP-03-Car Parks
12 | PROJECT.3.3.5.9.1.4 | MEP 2nd Fix-PP-03-Car Parks
14 | PROJECT.3.3.5.9.1.4.1 | HVAC Works
14 | PROJECT.3.3.5.9.1.4.2 | CHW piping Works
14 | PROJECT.3.3.5.9.1.4.3 | Electrical Works
14 | PROJECT.3.3.5.9.1.4.4 | Fire Fighting Works
14 | PROJECT.3.3.5.9.1.4.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.9.1.7 | MEP Final Fix-PP-03-Car Parks
14 | PROJECT.3.3.5.9.1.7.1 | HVAC Works
14 | PROJECT.3.3.5.9.1.7.3 | Electrical Works
14 | PROJECT.3.3.5.9.1.7.4 | Fire Fighting Works
14 | PROJECT.3.3.5.9.1.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.9.4 | BOH
12 | PROJECT.3.3.5.9.4.6 | PP-03-Plant Rooms/Lobby Room
14 | PROJECT.3.3.5.9.4.6.2 | PP-03-Plant Room-126 Zone 11
16 | PROJECT.3.3.5.9.4.6.2.3 | General Civil Access Dates-PP-03-126
16 | PROJECT.3.3.5.9.4.6.2.2 | MEP 1st Fix in Wall-PP-03-126
16 | PROJECT.3.3.5.9.4.6.2.4 | MEP 2nd Fix-PP-03-126
18 | PROJECT.3.3.5.9.4.6.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.2.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.2.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.2.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.2.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.2.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.2.7 | MEP Final Fix-PP-03 -126
18 | PROJECT.3.3.5.9.4.6.2.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.2.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.2.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.2.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.12 | PP-03-Plant Room-124 Zone 06
16 | PROJECT.3.3.5.9.4.6.12.3 | General Civil Access Dates-PP-03-124
16 | PROJECT.3.3.5.9.4.6.12.2 | MEP 1st Fix in Wall-PP-03-124
16 | PROJECT.3.3.5.9.4.6.12.4 | MEP 2nd Fix-PP-03-124
18 | PROJECT.3.3.5.9.4.6.12.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.12.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.12.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.12.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.12.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.12.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.12.7 | MEP Final Fix-PP-03-124
18 | PROJECT.3.3.5.9.4.6.12.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.12.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.12.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.12.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.8 | PP-03-Plant Room-121 Zone 06
16 | PROJECT.3.3.5.9.4.6.8.3 | General Civil Access Dates-Plant Room-PP-03-121
16 | PROJECT.3.3.5.9.4.6.8.2 | MEP 1st Fix in Wall-Plant Room-PP-03-121
16 | PROJECT.3.3.5.9.4.6.8.4 | MEP 2nd Fix-Plant Room-PP-03-121
18 | PROJECT.3.3.5.9.4.6.8.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.8.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.8.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.8.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.8.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.8.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.8.7 | MEP Final Fix-Plant Room-PP-03-121
18 | PROJECT.3.3.5.9.4.6.8.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.8.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.8.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.8.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.17 | PP-03-Plant Room-118 Zone 03
16 | PROJECT.3.3.5.9.4.6.17.3 | General Civil Access Dates-Plant Room-PP-03-118
16 | PROJECT.3.3.5.9.4.6.17.2 | MEP 1st Fix in Wall-Plant Room-PP-03-118
16 | PROJECT.3.3.5.9.4.6.17.4 | MEP 2nd Fix-Plant Room-PP-03-118
18 | PROJECT.3.3.5.9.4.6.17.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.17.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.17.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.17.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.17.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.17.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.17.7 | MEP Final Fix-Plant Room-PP-03-118
18 | PROJECT.3.3.5.9.4.6.17.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.17.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.17.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.17.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.20 | PP-03-Plant Room-137 Zone 02
16 | PROJECT.3.3.5.9.4.6.20.3 | General Civil Access Dates-Plant Room-PP-03-137
16 | PROJECT.3.3.5.9.4.6.20.2 | MEP 1st Fix in Wall-Plant Room-PP-03-137
16 | PROJECT.3.3.5.9.4.6.20.4 | MEP 2nd Fix-Plant Room-PP-03-137
18 | PROJECT.3.3.5.9.4.6.20.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.20.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.20.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.20.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.20.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.20.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.20.7 | MEP Final Fix-Plant Room-PP-03-137
18 | PROJECT.3.3.5.9.4.6.20.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.20.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.20.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.20.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.3 | PP-03-MCC ROOM- ATTACHED TO 121 (A17B) Zone 06
16 | PROJECT.3.3.5.9.4.6.3.3 | General Civil Access Dates-Plant Room-PP-03-121
16 | PROJECT.3.3.5.9.4.6.3.2 | MEP 1st Fix in Wall-Plant Room-PP-03-121
16 | PROJECT.3.3.5.9.4.6.3.4 | MEP 2nd Fix-Plant Room-PP-03-121
18 | PROJECT.3.3.5.9.4.6.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.3.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.3.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.3.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.3.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.3.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.3.7 | MEP Final Fix-Plant Room-PP-03-121
18 | PROJECT.3.3.5.9.4.6.3.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.3.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.3.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.3.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.21 | PP-03-Plant Room-140 Zone 06
16 | PROJECT.3.3.5.9.4.6.21.3 | General Civil Access Dates-Plant Room-PP-03-140
16 | PROJECT.3.3.5.9.4.6.21.2 | MEP 1st Fix in Wall-Plant Room-PP-03-140
16 | PROJECT.3.3.5.9.4.6.21.4 | MEP 2nd Fix-Plant Room-PP-03-140
18 | PROJECT.3.3.5.9.4.6.21.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.21.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.21.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.21.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.21.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.21.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.21.7 | MEP Final Fix-Plant Room-PP-03-140
18 | PROJECT.3.3.5.9.4.6.21.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.21.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.21.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.21.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.4 | PP-03-Plant Room-136 Zone 02
16 | PROJECT.3.3.5.9.4.6.4.3 | General Civil Access Dates-Plant Room-PP-03-136
16 | PROJECT.3.3.5.9.4.6.4.2 | MEP 1st Fix in Wall-Plant Room-PP-03-136
16 | PROJECT.3.3.5.9.4.6.4.4 | MEP 2nd Fix-Plant Room-PP-03-136
18 | PROJECT.3.3.5.9.4.6.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.4.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.4.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.4.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.4.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.4.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.4.7 | MEP Final Fix-Plant Room-PP-03-136
18 | PROJECT.3.3.5.9.4.6.4.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.4.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.4.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.4.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.5 | PP-03-Plant Room-142 Zone 06
16 | PROJECT.3.3.5.9.4.6.5.3 | General Civil Access Dates-Plant Room-PP-03-142
16 | PROJECT.3.3.5.9.4.6.5.2 | MEP 1st Fix in Wall-Plant Room-PP-03-142
16 | PROJECT.3.3.5.9.4.6.5.4 | MEP 2nd Fix-Plant Room-PP-03-142
18 | PROJECT.3.3.5.9.4.6.5.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.5.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.5.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.5.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.5.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.5.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.5.7 | MEP Final Fix-Plant Room-PP-03-142
18 | PROJECT.3.3.5.9.4.6.5.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.5.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.5.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.5.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.6 | PP-03-Plant Room-107 Zone 01 & 04
16 | PROJECT.3.3.5.9.4.6.6.3 | General Civil Access Dates-Plant Room-PP-03-107
16 | PROJECT.3.3.5.9.4.6.6.2 | MEP 1st Fix in Wall-Plant Room-PP-03-107
16 | PROJECT.3.3.5.9.4.6.6.4 | MEP 2nd Fix-Plant Room-PP-03-107
18 | PROJECT.3.3.5.9.4.6.6.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.6.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.6.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.6.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.6.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.6.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.6.7 | MEP Final Fix-Plant Room-PP-03-107
18 | PROJECT.3.3.5.9.4.6.6.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.6.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.6.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.6.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.28 | PP-03-MCC ROOM-ATTACHED TO 136 (A6) Zone 02
16 | PROJECT.3.3.5.9.4.6.28.3 | General Civil Access Dates-MCC Room-PP-03-ATT136
16 | PROJECT.3.3.5.9.4.6.28.2 | MEP 1st Fix in Wall-MCC Room-PP-03-ATT136
16 | PROJECT.3.3.5.9.4.6.28.4 | MEP 2nd Fix-MCC Room-PP-03-ATT136
18 | PROJECT.3.3.5.9.4.6.28.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.28.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.28.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.28.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.28.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.28.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.28.7 | MEP Final Fix-MCC Room-PP-03-ATT136
18 | PROJECT.3.3.5.9.4.6.28.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.28.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.28.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.28.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.29 | PP-03-MCC ROOM-ATTACHED TO 107 (A12) Zone 04
16 | PROJECT.3.3.5.9.4.6.29.3 | General Civil Access Dates-MCC Room-PP-03-ATT107
16 | PROJECT.3.3.5.9.4.6.29.2 | MEP 1st Fix in Wall-MCC Room-PP-03-ATT107
16 | PROJECT.3.3.5.9.4.6.29.4 | MEP 2nd Fix-MCC Room-PP-03-ATT107
18 | PROJECT.3.3.5.9.4.6.29.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.29.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.29.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.29.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.29.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.29.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.29.7 | MEP Final Fix-MCC Room-PP-03-ATT107
18 | PROJECT.3.3.5.9.4.6.29.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.29.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.29.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.29.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.13 | PP-03-Plant Room-108 Zone 01
16 | PROJECT.3.3.5.9.4.6.13.3 | General Civil Access Dates-Plant Room-PP-03-108
16 | PROJECT.3.3.5.9.4.6.13.2 | MEP 1st Fix in Wall-Plant Room-PP-03-108
16 | PROJECT.3.3.5.9.4.6.13.4 | MEP 2nd Fix-Plant Room-PP-03-108
18 | PROJECT.3.3.5.9.4.6.13.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.13.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.13.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.13.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.13.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.13.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.13.7 | MEP Final Fix-Plant Room-PP-03-108
18 | PROJECT.3.3.5.9.4.6.13.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.13.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.13.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.13.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.14 | PP-03-Plant Room-106 Zone 04
16 | PROJECT.3.3.5.9.4.6.14.3 | General Civil Access Dates-Plant Room-PP-03-106
16 | PROJECT.3.3.5.9.4.6.14.2 | MEP 1st Fix in Wall-Plant Room-PP-03-106
16 | PROJECT.3.3.5.9.4.6.14.4 | MEP 2nd Fix-Plant Room-PP-03-106
18 | PROJECT.3.3.5.9.4.6.14.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.14.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.14.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.14.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.14.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.14.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.14.7 | MEP Final Fix-Plant Room-PP-03-106
18 | PROJECT.3.3.5.9.4.6.14.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.14.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.14.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.14.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.9 | PP-03-Plant Room-109 Zone 04
16 | PROJECT.3.3.5.9.4.6.9.3 | General Civil Access Dates-Plant Room-PP-03-109
16 | PROJECT.3.3.5.9.4.6.9.2 | MEP 1st Fix in Wall-Plant Room-PP-03-109
16 | PROJECT.3.3.5.9.4.6.9.4 | MEP 2nd Fix-Plant Room-PP-03-109
18 | PROJECT.3.3.5.9.4.6.9.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.9.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.9.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.9.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.9.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.9.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.9.7 | MEP Final Fix-Plant Room-PP-03-109
18 | PROJECT.3.3.5.9.4.6.9.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.9.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.9.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.9.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.10 | PP-03-Plant Room-919 Zone 04
16 | PROJECT.3.3.5.9.4.6.10.3 | General Civil Access Dates-Plant Room-PP-03- 919
16 | PROJECT.3.3.5.9.4.6.10.2 | MEP 1st Fix in Wall-Plant Room-PP-03- 919
16 | PROJECT.3.3.5.9.4.6.10.4 | MEP 2nd Fix-Plant Room-PP-03- 919
18 | PROJECT.3.3.5.9.4.6.10.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.10.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.10.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.10.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.10.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.10.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.10.7 | MEP Final Fix-Plant Room-PP-03- 919
18 | PROJECT.3.3.5.9.4.6.10.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.10.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.10.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.10.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.15 | PP-03-Plant Room-101 Zone 07
16 | PROJECT.3.3.5.9.4.6.15.3 | General Civil Access Dates-PP-03-101
16 | PROJECT.3.3.5.9.4.6.15.2 | MEP 1st Fix in Wall-PP-03-101
16 | PROJECT.3.3.5.9.4.6.15.4 | MEP 2nd Fix-PP-03-101
18 | PROJECT.3.3.5.9.4.6.15.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.15.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.15.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.15.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.15.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.15.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.15.7 | MEP Final Fix-PP-03-101
18 | PROJECT.3.3.5.9.4.6.15.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.15.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.15.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.15.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.31 | PP-03-MCC ROOM-ATTACHED TO 101 (B3) Zone 07
16 | PROJECT.3.3.5.9.4.6.31.3 | General Civil Access Dates-MCC Room-PP-03-ATT101
16 | PROJECT.3.3.5.9.4.6.31.2 | MEP 1st Fix in Wall-MCC Room-PP-03-ATT101
16 | PROJECT.3.3.5.9.4.6.31.4 | MEP 2nd Fix-MCC Room-PP-03-ATT101
18 | PROJECT.3.3.5.9.4.6.31.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.31.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.31.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.31.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.31.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.31.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.31.7 | MEP Final Fix-MCC Room-PP-03-ATT101
18 | PROJECT.3.3.5.9.4.6.31.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.31.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.31.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.31.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.33 | PP-03-MCC ROOM-North east of 101 (B3) Zone 07
16 | PROJECT.3.3.5.9.4.6.33.3 | General Civil Access Dates-MCC Room-PP-03-NE101
16 | PROJECT.3.3.5.9.4.6.33.2 | MEP 1st Fix in Wall-MCC Room-PP-03-NE101
16 | PROJECT.3.3.5.9.4.6.33.4 | MEP 2nd Fix-MCC Room-PP-03-NE101
18 | PROJECT.3.3.5.9.4.6.33.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.33.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.33.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.33.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.33.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.33.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.33.7 | MEP Final Fix-MCC Room-PP-03-NE101
18 | PROJECT.3.3.5.9.4.6.33.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.33.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.33.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.33.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.11 | PP-03-Plant Room-102 Zone 07
16 | PROJECT.3.3.5.9.4.6.11.3 | General Civil Access Dates-PP-03-102
16 | PROJECT.3.3.5.9.4.6.11.2 | MEP 1st Fix in Wall-PP-03-102
16 | PROJECT.3.3.5.9.4.6.11.4 | MEP 2nd Fix-PP-03-102
18 | PROJECT.3.3.5.9.4.6.11.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.11.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.11.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.11.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.11.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.11.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.11.7 | MEP Final Fix-PP-03-102
18 | PROJECT.3.3.5.9.4.6.11.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.11.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.11.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.11.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.32 | PP-03-MCC ROOM-ATTACHED TO 102 (B3) Zone 07
16 | PROJECT.3.3.5.9.4.6.32.3 | General Civil Access Dates-MCC Room-PP-03-ATT102
16 | PROJECT.3.3.5.9.4.6.32.2 | MEP 1st Fix in Wall-MCC Room-PP-03-ATT102
16 | PROJECT.3.3.5.9.4.6.32.4 | MEP 2nd Fix-MCC Room-PP-03-ATT102
18 | PROJECT.3.3.5.9.4.6.32.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.32.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.32.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.32.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.32.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.32.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.32.7 | MEP Final Fix-MCC Room-PP-03-ATT102
18 | PROJECT.3.3.5.9.4.6.32.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.32.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.32.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.32.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.16 | PP-03-Plant Room-104 Zone 07
16 | PROJECT.3.3.5.9.4.6.16.3 | General Civil Access Dates-PP-03-104
16 | PROJECT.3.3.5.9.4.6.16.2 | MEP 1st Fix in Wall-PP-03-104
16 | PROJECT.3.3.5.9.4.6.16.4 | MEP 2nd Fix-PP-03-104
18 | PROJECT.3.3.5.9.4.6.16.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.16.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.16.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.16.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.16.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.16.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.16.7 | MEP Final Fix-PP-03-104
18 | PROJECT.3.3.5.9.4.6.16.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.16.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.16.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.16.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.18 | PP-03-Plant Room-139 Zone 06
16 | PROJECT.3.3.5.9.4.6.18.3 | General Civil Access Dates-Plant Room-PP-03-139
16 | PROJECT.3.3.5.9.4.6.18.2 | MEP 1st Fix in Wall-Plant Room-PP-03-139
16 | PROJECT.3.3.5.9.4.6.18.4 | MEP 2nd Fix-Plant Room-PP-03-139
18 | PROJECT.3.3.5.9.4.6.18.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.18.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.18.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.18.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.18.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.18.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.18.7 | MEP Final Fix-Plant Room-PP-03-139
18 | PROJECT.3.3.5.9.4.6.18.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.18.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.18.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.18.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.23 | PP-03-Plant Room-152 Zone 03 & 06
16 | PROJECT.3.3.5.9.4.6.23.3 | General Civil Access Dates-Plant Room-PP-03-152
16 | PROJECT.3.3.5.9.4.6.23.2 | MEP 1st Fix in Wall-Plant Room-PP-03-152
16 | PROJECT.3.3.5.9.4.6.23.4 | MEP 2nd Fix-Plant Room-PP-03-152
18 | PROJECT.3.3.5.9.4.6.23.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.23.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.23.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.23.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.23.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.23.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.23.7 | MEP Final Fix-Plant Room-PP-03-152
18 | PROJECT.3.3.5.9.4.6.23.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.23.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.23.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.23.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.22 | PP-03-Plant Room-119 Zone 03
16 | PROJECT.3.3.5.9.4.6.22.3 | General Civil Access Dates-Plant Room-PP-03-119
16 | PROJECT.3.3.5.9.4.6.22.2 | MEP 1st Fix in Wall-Plant Room-PP-03-119
16 | PROJECT.3.3.5.9.4.6.22.4 | MEP 2nd Fix-Plant Room-PP-03-119
18 | PROJECT.3.3.5.9.4.6.22.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.22.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.22.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.22.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.22.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.22.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.22.7 | MEP Final Fix-Plant Room-PP-03-119
18 | PROJECT.3.3.5.9.4.6.22.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.22.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.22.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.22.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.24 | PP-03-Plant Room-120 Zone 03
16 | PROJECT.3.3.5.9.4.6.24.3 | General Civil Access Dates-Plant Room-PP-03-120
16 | PROJECT.3.3.5.9.4.6.24.2 | MEP 1st Fix in Wall-Plant Room-PP-03-120
16 | PROJECT.3.3.5.9.4.6.24.4 | MEP 2nd Fix-Plant Room-PP-03-120
18 | PROJECT.3.3.5.9.4.6.24.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.24.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.24.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.24.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.24.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.24.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.24.7 | MEP Final Fix-Plant Room-PP-03-120
18 | PROJECT.3.3.5.9.4.6.24.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.24.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.24.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.24.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.30 | PP-03-MCC ROOM-ATTACHED TO 120 (A9) Zone 03
16 | PROJECT.3.3.5.9.4.6.30.3 | General Civil Access Dates-MCC Room-PP-03-ATT120
16 | PROJECT.3.3.5.9.4.6.30.2 | MEP 1st Fix in Wall-MCC Room-PP-03-ATT120
16 | PROJECT.3.3.5.9.4.6.30.4 | MEP 2nd Fix-MCC Room-PP-03-ATT120
18 | PROJECT.3.3.5.9.4.6.30.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.30.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.30.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.30.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.30.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.30.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.30.7 | MEP Final Fix-MCC Room-PP-03-ATT120
18 | PROJECT.3.3.5.9.4.6.30.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.30.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.30.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.30.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.19 | PP-03-Plant Room-131 UTT/BMS RM
16 | PROJECT.3.3.5.9.4.6.19.3 | General Civil Access Dates-Plant Room-PP-03-131
16 | PROJECT.3.3.5.9.4.6.19.2 | MEP 1st Fix in Wall-Plant Room-PP-03-131
16 | PROJECT.3.3.5.9.4.6.19.4 | MEP 2nd Fix-Plant Room-PP-03-131
18 | PROJECT.3.3.5.9.4.6.19.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.19.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.19.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.19.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.19.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.19.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.19.7 | MEP Final Fix-Plant Room-PP-03-131
18 | PROJECT.3.3.5.9.4.6.19.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.19.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.19.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.19.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.25 | PP-03-Plant Room-129 Zone 08
16 | PROJECT.3.3.5.9.4.6.25.3 | General Civil Access Dates-Plant Room-PP-03-129
16 | PROJECT.3.3.5.9.4.6.25.2 | MEP 1st Fix in Wall-Plant Room-PP-03-129
16 | PROJECT.3.3.5.9.4.6.25.4 | MEP 2nd Fix-Plant Room-PP-03-129
18 | PROJECT.3.3.5.9.4.6.25.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.25.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.25.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.25.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.25.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.25.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.25.7 | MEP Final Fix-Plant Room-PP-03-129
18 | PROJECT.3.3.5.9.4.6.25.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.25.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.25.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.25.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.27 | PP-03-Plant Room-134 Zone 08
16 | PROJECT.3.3.5.9.4.6.27.3 | General Civil Access Dates-Plant Room-PP-03-134
16 | PROJECT.3.3.5.9.4.6.27.2 | MEP 1st Fix in Wall-Plant Room-PP-03-134
16 | PROJECT.3.3.5.9.4.6.27.4 | MEP 2nd Fix-Plant Room-PP-03-134
18 | PROJECT.3.3.5.9.4.6.27.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.27.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.27.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.27.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.27.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.27.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.27.7 | MEP Final Fix-Plant Room-PP-03-134
18 | PROJECT.3.3.5.9.4.6.27.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.27.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.27.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.27.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.26 | PP-03-Plant Room-128 Zone 08 & 11
16 | PROJECT.3.3.5.9.4.6.26.3 | General Civil Access Dates-Plant Room-PP-03-128
16 | PROJECT.3.3.5.9.4.6.26.2 | MEP 1st Fix in Wall-Plant Room-PP-03-128
16 | PROJECT.3.3.5.9.4.6.26.4 | MEP 2nd Fix-Plant Room-PP-03-128
18 | PROJECT.3.3.5.9.4.6.26.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.26.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.26.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.26.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.26.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.9.4.6.26.4.6 | Water Supply Works
16 | PROJECT.3.3.5.9.4.6.26.7 | MEP Final Fix-Plant Room-PP-03-128
18 | PROJECT.3.3.5.9.4.6.26.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.26.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.26.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.26.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.7 | PP-03-Electrical Room-904/UTT RM/BMS RM/LED RM Zone 11
16 | PROJECT.3.3.5.9.4.6.7.3 | General Civil Access Dates-PP-03-Electrical Room-904/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.9.4.6.7.2 | MEP 1st Fix in Wall-PP-03-Electrical Room-904/UTT RM/BMS RM/LED RM
16 | PROJECT.3.3.5.9.4.6.7.4 | MEP 2nd Fix-PP-03-Electrical Room-904/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.9.4.6.7.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.7.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.7.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.7.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.7.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.9.4.6.7.7 | MEP Final Fix-PP-03-Electrical Room-904/UTT RM/BMS RM/LED RM
18 | PROJECT.3.3.5.9.4.6.7.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.7.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.7.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.7.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.6.1 | PP-03-UTT RM-914 & 925 UTT RM/ BMS RM/Lobby/Staircase/Lift room Zone 10 & 13
16 | PROJECT.3.3.5.9.4.6.1.3 | General Civil Access Dates-PP-03-UTT RM-914 & 925 UTT RM/ BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.9.4.6.1.2 | MEP 1st Fix in Wall-PP-03-UTT RM-914 & 925 UTT RM/ BMS RM/Lobby/Staircase/Lift room
16 | PROJECT.3.3.5.9.4.6.1.4 | MEP 2nd Fix-PP-03-UTT RM-914 & 925 UTT RM/ BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.9.4.6.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.1.4.2 | CHW piping Works
18 | PROJECT.3.3.5.9.4.6.1.4.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.1.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.1.4.5 | Plumbing & Drainage Works
16 | PROJECT.3.3.5.9.4.6.1.7 | MEP Final Fix-PP-03-UTT RM-914 & 925 UTT RM/ BMS RM/Lobby/Staircase/Lift room
18 | PROJECT.3.3.5.9.4.6.1.7.1 | HVAC Works
18 | PROJECT.3.3.5.9.4.6.1.7.3 | Electrical Works
18 | PROJECT.3.3.5.9.4.6.1.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.9.4.6.1.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.9.4.1 | PP-03- Pump Room 143 Zone 03
14 | PROJECT.3.3.5.9.4.1.3 | General Civil Access Dates-PP-03-Water Tank 143
14 | PROJECT.3.3.5.9.4.1.2 | MEP 1st Fix in Wall-PP-03-Water Tank 143
14 | PROJECT.3.3.5.9.4.1.4 | MEP 2nd Fix-PP-03-Water Tank 143
16 | PROJECT.3.3.5.9.4.1.4.6 | HVAC Works
16 | PROJECT.3.3.5.9.4.1.4.7 | CHW piping Works
16 | PROJECT.3.3.5.9.4.1.4.1 | Electrical Works
16 | PROJECT.3.3.5.9.4.1.4.2 | Fire Fighting Works
16 | PROJECT.3.3.5.9.4.1.4.8 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.1.7 | MEP Final Fix-PP-03-Water Tank 143
16 | PROJECT.3.3.5.9.4.1.7.1 | HVAC Works
16 | PROJECT.3.3.5.9.4.1.7.3 | Electrical Works
16 | PROJECT.3.3.5.9.4.1.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.9.4.1.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.9.4.3 | PP-03-Water Tank 144 Zone 03 , 145 Zone 06
14 | PROJECT.3.3.5.9.4.3.3 | General Civil Access Dates-PP-03-Water Tank 144
14 | PROJECT.3.3.5.9.4.3.2 | MEP 1st Fix in Wall-PP-03-Water Tank 144
14 | PROJECT.3.3.5.9.4.3.4 | MEP 2nd Fix-PP-03-Water Tank 144
16 | PROJECT.3.3.5.9.4.3.4.6 | HVAC Works
16 | PROJECT.3.3.5.9.4.3.4.7 | CHW piping Works
16 | PROJECT.3.3.5.9.4.3.4.1 | Electrical Works
16 | PROJECT.3.3.5.9.4.3.4.2 | Fire Fighting Works
16 | PROJECT.3.3.5.9.4.3.4.8 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.4.3.7 | MEP Final Fix-PP-03-Water Tank 144
16 | PROJECT.3.3.5.9.4.3.7.1 | HVAC Works
16 | PROJECT.3.3.5.9.4.3.7.3 | Electrical Works
16 | PROJECT.3.3.5.9.4.3.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.9.4.3.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.9.5 | FOH LOBBIES
12 | PROJECT.3.3.5.9.5.2 | LOBBY 02 Zone 07&09
14 | PROJECT.3.3.5.9.5.2.3 | General Civil Access Dates-LOBBY 02 Zone 07&09
14 | PROJECT.3.3.5.9.5.2.2 | MEP 1st Fix in Wall-LOBBY 02 Zone 07&09
14 | PROJECT.3.3.5.9.5.2.4 | MEP 2nd Fix-LOBBY 02 Zone 07&09
16 | PROJECT.3.3.5.9.5.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.9.5.2.4.2 | CHW piping Works
16 | PROJECT.3.3.5.9.5.2.4.3 | Electrical Works
16 | PROJECT.3.3.5.9.5.2.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.9.5.2.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.5.2.7 | MEP Final Fix-LOBBY 02 Zone 07&09
16 | PROJECT.3.3.5.9.5.2.7.1 | HVAC Works
16 | PROJECT.3.3.5.9.5.2.7.3 | Electrical Works
16 | PROJECT.3.3.5.9.5.2.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.9.5.2.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.9.5.1 | LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.9.5.1.3 | General Civil Access Dates-PP3-LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.9.5.1.2 | MEP 1st Fix in Wall-PP3-LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.9.5.1.4 | MEP 2nd Fix-PP3-LOBBY 03 Zone 10&13
16 | PROJECT.3.3.5.9.5.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.9.5.1.4.2 | CHW piping Works
16 | PROJECT.3.3.5.9.5.1.4.3 | Electrical Works
16 | PROJECT.3.3.5.9.5.1.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.9.5.1.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.5.1.7 | MEP Final Fix-PP3-LOBBY 03 Zone 10&13
16 | PROJECT.3.3.5.9.5.1.7.1 | HVAC Works
16 | PROJECT.3.3.5.9.5.1.7.3 | Electrical Works
16 | PROJECT.3.3.5.9.5.1.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.9.5.1.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.9.5.3 | LOBBY 04 Zone 11
14 | PROJECT.3.3.5.9.5.3.3 | General Civil Access Dates-PP3-LOBBY 04 Zone 11
14 | PROJECT.3.3.5.9.5.3.2 | MEP 1st Fix in Wall-PP3-LOBBY 04 Zone 11
14 | PROJECT.3.3.5.9.5.3.4 | MEP 2nd Fix-PP3-LOBBY 04 Zone 11
16 | PROJECT.3.3.5.9.5.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.9.5.3.4.2 | CHW piping Works
16 | PROJECT.3.3.5.9.5.3.4.3 | Electrical Works
16 | PROJECT.3.3.5.9.5.3.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.9.5.3.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.9.5.3.7 | MEP Final Fix-PP3-LOBBY 04 Zone 11
16 | PROJECT.3.3.5.9.5.3.7.1 | HVAC Works
16 | PROJECT.3.3.5.9.5.3.7.3 | Electrical Works
16 | PROJECT.3.3.5.9.5.3.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.9.5.3.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.9.2 | STAIRCASES PP3 TO PP4 SECTION B
12 | PROJECT.3.3.5.9.2.4 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.3.5.9.2.1 | ACCESS STAIRCASES ST18
10 | PROJECT.3.3.5.9.3 | STAIRCASES PP3 TO PP4 SECTION C
12 | PROJECT.3.3.5.9.3.4 | EARLY COMPLETION STAIRCASES
12 | PROJECT.3.3.5.9.3.1 | ACCESS STAIRCASES ST25, ST33
8 | PROJECT.3.3.5.10 | PODIUM PARKING 4 (PP-04)
10 | PROJECT.3.3.5.10.5 | FOH LOBBIES
12 | PROJECT.3.3.5.10.5.2 | LOBBY 02 Zone 07&09
14 | PROJECT.3.3.5.10.5.2.3 | General Civil Access Dates-PP4-LOBBY 02 Zone 07&09
14 | PROJECT.3.3.5.10.5.2.2 | MEP 1st Fix in Wall-PP4-LOBBY 02 Zone 07&09
14 | PROJECT.3.3.5.10.5.2.4 | MEP 2nd Fix-PP4-LOBBY 02 Zone 07&09
16 | PROJECT.3.3.5.10.5.2.4.1 | HVAC Works
16 | PROJECT.3.3.5.10.5.2.4.2 | CHW piping Works
16 | PROJECT.3.3.5.10.5.2.4.3 | Electrical Works
16 | PROJECT.3.3.5.10.5.2.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.10.5.2.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.5.2.7 | MEP Final Fix-PP4-LOBBY 02 Zone 07&09
16 | PROJECT.3.3.5.10.5.2.7.1 | HVAC Works
16 | PROJECT.3.3.5.10.5.2.7.3 | Electrical Works
16 | PROJECT.3.3.5.10.5.2.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.10.5.2.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.10.5.1 | LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.10.5.1.3 | General Civil Access Dates-PP4-LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.10.5.1.2 | MEP 1st Fix in Wall-PP4-LOBBY 03 Zone 10&13
14 | PROJECT.3.3.5.10.5.1.4 | MEP 2nd Fix-PP4-LOBBY 03 Zone 10&13
16 | PROJECT.3.3.5.10.5.1.4.1 | HVAC Works
16 | PROJECT.3.3.5.10.5.1.4.2 | CHW piping Works
16 | PROJECT.3.3.5.10.5.1.4.3 | Electrical Works
16 | PROJECT.3.3.5.10.5.1.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.10.5.1.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.5.1.7 | MEP Final Fix-PP4-LOBBY 03 Zone 10&13
16 | PROJECT.3.3.5.10.5.1.7.1 | HVAC Works
16 | PROJECT.3.3.5.10.5.1.7.3 | Electrical Works
16 | PROJECT.3.3.5.10.5.1.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.10.5.1.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.10.5.3 | LOBBY 04 Zone 11
14 | PROJECT.3.3.5.10.5.3.3 | General Civil Access Dates-PP4-LOBBY 04 Zone 11
14 | PROJECT.3.3.5.10.5.3.2 | MEP 1st Fix in Wall-PP4-LOBBY 04 Zone 11
14 | PROJECT.3.3.5.10.5.3.4 | MEP 2nd Fix-PP4-LOBBY 04 Zone 11
16 | PROJECT.3.3.5.10.5.3.4.1 | HVAC Works
16 | PROJECT.3.3.5.10.5.3.4.2 | CHW piping Works
16 | PROJECT.3.3.5.10.5.3.4.3 | Electrical Works
16 | PROJECT.3.3.5.10.5.3.4.4 | Fire Fighting Works
16 | PROJECT.3.3.5.10.5.3.4.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.5.3.7 | MEP Final Fix-PP4-LOBBY 04 Zone 11
16 | PROJECT.3.3.5.10.5.3.7.1 | HVAC Works
16 | PROJECT.3.3.5.10.5.3.7.3 | Electrical Works
16 | PROJECT.3.3.5.10.5.3.7.4 | Fire Fighting Works
16 | PROJECT.3.3.5.10.5.3.7.5 | Plumbing & Drainage Works
10 | PROJECT.3.3.5.10.11 | BOH
12 | PROJECT.3.3.5.10.11.4 | MEP 1st Fix in PP4
12 | PROJECT.3.3.5.10.11.1 | PLANT ROOMS-SECTION A
14 | PROJECT.3.3.5.10.11.1.1 | PP-04-PLANT ROOM- 934 ZONE 1
16 | PROJECT.3.3.5.10.11.1.1.3 | GENERAL CIVIL ACCESS DATES-PLANT ROOM-PP-04-934
16 | PROJECT.3.3.5.10.11.1.1.2 | MEP 1st Fix IN WALL-PLANT ROOM-PP-04-934
16 | PROJECT.3.3.5.10.11.1.1.4 | MEP 2nd Fix-PLANT ROOM-PP-04-934
18 | PROJECT.3.3.5.10.11.1.1.4.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.1.4.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.10.11.1.1.4.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.1.4.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.1.4.5 | PLUMBING AND DRAINAGE WORKS
18 | PROJECT.3.3.5.10.11.1.1.4.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.10.11.1.1.7 | MEP FINAL Fix-PLANT ROOM-PP-04-934
18 | PROJECT.3.3.5.10.11.1.1.7.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.1.7.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.1.7.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.1.7.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.10.11.1.2 | PP-04-PLANT ROOM-936 ZONE 1
16 | PROJECT.3.3.5.10.11.1.2.3 | GENERAL CIVIL ACCESS DATES-PP-04-936
16 | PROJECT.3.3.5.10.11.1.2.2 | MEP 1st Fix IN WALL-PP-04-936
16 | PROJECT.3.3.5.10.11.1.2.4 | MEP 2nd Fix-PP-04-936
18 | PROJECT.3.3.5.10.11.1.2.4.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.2.4.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.10.11.1.2.4.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.2.4.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.2.4.5 | PLUMBING AND DRAINAGE WORKS
18 | PROJECT.3.3.5.10.11.1.2.4.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.10.11.1.2.7 | MEP FINAL Fix-PP-04-936
18 | PROJECT.3.3.5.10.11.1.2.7.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.2.7.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.2.7.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.2.7.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.10.11.1.3 | PP-04-PLANT ROOM-937 ZONE 1
16 | PROJECT.3.3.5.10.11.1.3.3 | GENERAL CIVIL ACCESS DATES-PP-04-937
16 | PROJECT.3.3.5.10.11.1.3.2 | MEP 1st Fix IN WALL-PP-04-937
16 | PROJECT.3.3.5.10.11.1.3.4 | MEP 2nd Fix-PP-04-937
18 | PROJECT.3.3.5.10.11.1.3.4.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.3.4.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.10.11.1.3.4.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.3.4.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.3.4.5 | PLUMBING AND DRAINAGE WORKS
18 | PROJECT.3.3.5.10.11.1.3.4.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.10.11.1.3.7 | MEP FINAL Fix-PP-04-937
18 | PROJECT.3.3.5.10.11.1.3.7.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.3.7.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.3.7.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.3.7.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.10.11.1.9 | PP-04-PLANT ROOM-938 ZONE 1
16 | PROJECT.3.3.5.10.11.1.9.3 | GENERAL CIVIL ACCESS DATES-PP-04-938
16 | PROJECT.3.3.5.10.11.1.9.2 | MEP 1st Fix IN WALL-PP-04-938
16 | PROJECT.3.3.5.10.11.1.9.4 | MEP 2nd Fix-PP-04-938
18 | PROJECT.3.3.5.10.11.1.9.4.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.9.4.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.10.11.1.9.4.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.9.4.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.9.4.5 | PLUMBING AND DRAINAGE WORKS
18 | PROJECT.3.3.5.10.11.1.9.4.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.10.11.1.9.7 | MEP FINAL Fix-PP-04-938
18 | PROJECT.3.3.5.10.11.1.9.7.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.9.7.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.9.7.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.9.7.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.10.11.1.4 | PP-04-PLANT ROOM-947 ZONE 1
16 | PROJECT.3.3.5.10.11.1.4.3 | GENERAL CIVIL ACCESS DATES-PP-04-947
16 | PROJECT.3.3.5.10.11.1.4.2 | MEP 1st Fix IN WALL-PP-04-947
16 | PROJECT.3.3.5.10.11.1.4.4 | MEP 2nd Fix-PP-04-947
18 | PROJECT.3.3.5.10.11.1.4.4.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.4.4.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.10.11.1.4.4.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.4.4.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.4.4.5 | PLUMBING AND DRAINAGE WORKS
18 | PROJECT.3.3.5.10.11.1.4.4.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.10.11.1.4.7 | MEP FINAL Fix-PP-04-947
18 | PROJECT.3.3.5.10.11.1.4.7.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.4.7.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.4.7.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.4.7.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.10.11.1.5 | PP-04-PLANT ROOM-939 ZONE 1
16 | PROJECT.3.3.5.10.11.1.5.3 | GENERAL CIVIL ACCESS DATES-PP-04-939
16 | PROJECT.3.3.5.10.11.1.5.2 | MEP 1st Fix IN WALL-PP-04-939
16 | PROJECT.3.3.5.10.11.1.5.4 | MEP 2nd Fix-PP-04-939
18 | PROJECT.3.3.5.10.11.1.5.4.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.5.4.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.10.11.1.5.4.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.5.4.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.5.4.5 | PLUMBING AND DRAINAGE WORKS
18 | PROJECT.3.3.5.10.11.1.5.4.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.10.11.1.5.7 | MEP FINAL Fix-PP-04-939
18 | PROJECT.3.3.5.10.11.1.5.7.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.5.7.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.5.7.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.5.7.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.10.11.1.6 | PP-04-PLANT ROOM-940 ZONE 2
16 | PROJECT.3.3.5.10.11.1.6.3 | GENERAL CIVIL ACCESS DATES-PP-04-940
16 | PROJECT.3.3.5.10.11.1.6.2 | MEP 1st Fix IN WALL-PP-04-940
16 | PROJECT.3.3.5.10.11.1.6.4 | MEP 2nd Fix-PP-04-940
18 | PROJECT.3.3.5.10.11.1.6.4.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.6.4.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.10.11.1.6.4.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.6.4.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.6.4.5 | PLUMBING AND DRAINAGE WORKS
18 | PROJECT.3.3.5.10.11.1.6.4.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.10.11.1.6.7 | MEP FINAL Fix-PP-04-940
18 | PROJECT.3.3.5.10.11.1.6.7.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.6.7.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.6.7.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.6.7.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.10.11.1.7 | PP-04-PLANT ROOM-941 ZONE 2
16 | PROJECT.3.3.5.10.11.1.7.3 | GENERAL CIVIL ACCESS DATES-PP-04-941
16 | PROJECT.3.3.5.10.11.1.7.2 | MEP 1st Fix IN WALL-PP-04-941
16 | PROJECT.3.3.5.10.11.1.7.4 | MEP 2nd Fix-PP-04-941
18 | PROJECT.3.3.5.10.11.1.7.4.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.7.4.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.10.11.1.7.4.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.7.4.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.7.4.5 | PLUMBING AND DRAINAGE WORKS
18 | PROJECT.3.3.5.10.11.1.7.4.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.10.11.1.7.7 | MEP FINAL Fix-PP-04-941
18 | PROJECT.3.3.5.10.11.1.7.7.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.7.7.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.7.7.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.7.7.5 | PLUMBING AND DRAINAGE WORKS
14 | PROJECT.3.3.5.10.11.1.8 | PP-04-PLANT ROOM-942 ZONE 2
16 | PROJECT.3.3.5.10.11.1.8.3 | GENERAL CIVIL ACCESS DATES-PP-04-942
16 | PROJECT.3.3.5.10.11.1.8.2 | MEP 1st Fix IN WALL-PP-04-942
16 | PROJECT.3.3.5.10.11.1.8.4 | MEP 2nd Fix-PP-04-942
18 | PROJECT.3.3.5.10.11.1.8.4.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.8.4.2 | CHW PIPING WORKS
18 | PROJECT.3.3.5.10.11.1.8.4.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.8.4.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.8.4.5 | PLUMBING AND DRAINAGE WORKS
18 | PROJECT.3.3.5.10.11.1.8.4.6 | WATER SUPPLY WORKS
16 | PROJECT.3.3.5.10.11.1.8.7 | MEP FINAL Fix-PP-04-942
18 | PROJECT.3.3.5.10.11.1.8.7.1 | HVAC WORKS
18 | PROJECT.3.3.5.10.11.1.8.7.3 | ELECTRICAL WORKS
18 | PROJECT.3.3.5.10.11.1.8.7.4 | FIRE FIGHTING WORKS
18 | PROJECT.3.3.5.10.11.1.8.7.5 | PLUMBING AND DRAINAGE WORKS
12 | PROJECT.3.3.5.10.11.2 | PLANT ROOMS-SECTION B
14 | PROJECT.3.3.5.10.11.2.4 | PP-04-PLANT ROOM-932 ZONE 5
16 | PROJECT.3.3.5.10.11.2.4.3 | General Civil Access Dates-PP-04-932
16 | PROJECT.3.3.5.10.11.2.4.2 | MEP 1st Fix in Wall-PP-04-932
16 | PROJECT.3.3.5.10.11.2.4.4 | MEP 2nd Fix-PP-04-932
18 | PROJECT.3.3.5.10.11.2.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.2.4.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.2.4.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.2.4.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.2.4.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.2.4.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.2.4.7 | MEP Final Fix-PP-04-932
18 | PROJECT.3.3.5.10.11.2.4.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.2.4.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.2.4.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.2.4.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.2.2 | PP-04-PLANT ROOM-946 ZONE 5
16 | PROJECT.3.3.5.10.11.2.2.3 | General Civil Access Dates-PP-04-946
16 | PROJECT.3.3.5.10.11.2.2.2 | MEP 1st Fix in Wall-PP-04-946
16 | PROJECT.3.3.5.10.11.2.2.4 | MEP 2nd Fix-PP-04-946
18 | PROJECT.3.3.5.10.11.2.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.2.2.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.2.2.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.2.2.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.2.2.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.2.2.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.2.2.7 | MEP Final Fix-PP-04-946
18 | PROJECT.3.3.5.10.11.2.2.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.2.2.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.2.2.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.2.2.7.5 | Plumbing & Drainage Works
12 | PROJECT.3.3.5.10.11.3 | PLANT ROOMS-SECTION C
14 | PROJECT.3.3.5.10.11.3.15 | PP-04-PLANT ROOM-921 ZONE 9
16 | PROJECT.3.3.5.10.11.3.15.3 | General Civil Access Dates-Plant Room-PP-04-921
16 | PROJECT.3.3.5.10.11.3.15.2 | MEP 1st Fix in Wall-Plant Room-PP-04-921
16 | PROJECT.3.3.5.10.11.3.15.4 | MEP 2nd Fix-Plant Room-PP-04-921
18 | PROJECT.3.3.5.10.11.3.15.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.15.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.15.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.15.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.15.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.15.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.15.7 | MEP Final Fix-Plant Room-PP-04-921
18 | PROJECT.3.3.5.10.11.3.15.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.15.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.15.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.15.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.12 | PP-04-PLANT ROOM-908 ZONE 14
16 | PROJECT.3.3.5.10.11.3.12.3 | General Civil Access Dates-Plant Room-PP-04-908
16 | PROJECT.3.3.5.10.11.3.12.2 | MEP 1st Fix in Wall-Plant Room-PP-04-908
16 | PROJECT.3.3.5.10.11.3.12.4 | MEP 2nd Fix-Plant Room-PP-04-908
18 | PROJECT.3.3.5.10.11.3.12.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.12.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.12.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.12.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.12.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.12.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.12.7 | MEP Final Fix-Plant Room-PP-04-908
18 | PROJECT.3.3.5.10.11.3.12.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.12.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.12.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.12.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.11 | PP-04-PLANT ROOM-907 ZONE 14
16 | PROJECT.3.3.5.10.11.3.11.3 | General Civil Access Dates-Plant Room-PP-04-907
16 | PROJECT.3.3.5.10.11.3.11.2 | MEP 1st Fix in Wall-Plant Room-PP-04-907
16 | PROJECT.3.3.5.10.11.3.11.4 | MEP 2nd Fix-Plant Room-PP-04-907
18 | PROJECT.3.3.5.10.11.3.11.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.11.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.11.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.11.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.11.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.11.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.11.7 | MEP Final Fix-Plant Room-PP-04-907
18 | PROJECT.3.3.5.10.11.3.11.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.11.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.11.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.11.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.2 | PP-04-PLANT ROOM-918 ZONE 10
16 | PROJECT.3.3.5.10.11.3.2.3 | General Civil Access Dates-Plant Room-PP-04-918
16 | PROJECT.3.3.5.10.11.3.2.2 | MEP 1st Fix
16 | PROJECT.3.3.5.10.11.3.2.4 | MEP 2nd Fix-Plant Room-PP-04-918
18 | PROJECT.3.3.5.10.11.3.2.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.2.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.2.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.2.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.2.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.2.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.2.7 | MEP Final Fix-Plant Room-PP-04-918
18 | PROJECT.3.3.5.10.11.3.2.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.2.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.2.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.2.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.3 | PP-04-PLANT ROOM-922 ZONE 9
16 | PROJECT.3.3.5.10.11.3.3.3 | General Civil Access Dates-Plant Room-PP-04-922
16 | PROJECT.3.3.5.10.11.3.3.2 | MEP 1st Fix in Wall-Plant Room-PP-04-922
16 | PROJECT.3.3.5.10.11.3.3.4 | MEP 2nd Fix-Plant Room-PP-04-922
18 | PROJECT.3.3.5.10.11.3.3.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.3.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.3.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.3.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.3.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.3.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.3.7 | MEP Final Fix-Plant Room-PP-04-922
18 | PROJECT.3.3.5.10.11.3.3.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.3.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.3.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.3.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.4 | PP-04-PLANT ROOM-952 ZONE 11
16 | PROJECT.3.3.5.10.11.3.4.3 | General Civil Access Dates-Plant Room-PP-04-952
16 | PROJECT.3.3.5.10.11.3.4.2 | MEP 1st Fix in Wall-Plant Room-PP-04-952
16 | PROJECT.3.3.5.10.11.3.4.4 | MEP 2nd Fix-Plant Room-PP-04-952
18 | PROJECT.3.3.5.10.11.3.4.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.4.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.4.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.4.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.4.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.4.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.4.7 | MEP Final Fix-Plant Room-PP-04-952
18 | PROJECT.3.3.5.10.11.3.4.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.4.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.4.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.4.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.5 | PP-04-PLANT ROOM-912 ZONE 13
16 | PROJECT.3.3.5.10.11.3.5.3 | General Civil Access Dates-Plant Room-PP-04-912
16 | PROJECT.3.3.5.10.11.3.5.2 | MEP 1st Fix in Wall-Plant Room-PP-04-912
16 | PROJECT.3.3.5.10.11.3.5.4 | MEP 2nd Fix-Plant Room-PP-04-912
18 | PROJECT.3.3.5.10.11.3.5.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.5.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.5.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.5.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.5.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.5.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.5.7 | MEP Final Fix-Plant Room-PP-04-912
18 | PROJECT.3.3.5.10.11.3.5.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.5.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.5.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.5.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.6 | PP-04-PLANT ROOM-909 ZONE 11
16 | PROJECT.3.3.5.10.11.3.6.3 | General Civil Access Dates-Plant Room-PP-04-909
16 | PROJECT.3.3.5.10.11.3.6.2 | MEP 1st Fix in Wall-Plant Room-PP-04-909
16 | PROJECT.3.3.5.10.11.3.6.4 | MEP 2nd Fix-Plant Room-PP-04-909
18 | PROJECT.3.3.5.10.11.3.6.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.6.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.6.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.6.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.6.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.6.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.6.7 | MEP Final Fix-Plant Room-PP-04-909
18 | PROJECT.3.3.5.10.11.3.6.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.6.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.6.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.6.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.14 | PP-04-PLANT ROOM-953 ZONE 11
16 | PROJECT.3.3.5.10.11.3.14.3 | General Civil Access Dates-Plant Room-PP-04-953
16 | PROJECT.3.3.5.10.11.3.14.2 | MEP 1st Fix in Wall-Plant Room-PP-04-953
16 | PROJECT.3.3.5.10.11.3.14.4 | MEP 2nd Fix-Plant Room-PP-04-953
18 | PROJECT.3.3.5.10.11.3.14.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.14.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.14.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.14.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.14.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.14.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.14.7 | MEP Final Fix-Plant Room-PP-04-953
18 | PROJECT.3.3.5.10.11.3.14.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.14.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.14.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.14.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.7 | PP-04-PLANT ROOM-919 ZONE 9
16 | PROJECT.3.3.5.10.11.3.7.3 | General Civil Access Dates-Plant Room-PP-04-919
16 | PROJECT.3.3.5.10.11.3.7.2 | MEP 1st Fix in Wall-Plant Room-PP-04-919
16 | PROJECT.3.3.5.10.11.3.7.4 | MEP 2nd Fix-Plant Room-PP-04-919
18 | PROJECT.3.3.5.10.11.3.7.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.7.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.7.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.7.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.7.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.7.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.7.7 | MEP Final Fix-Plant Room-PP-04-919
18 | PROJECT.3.3.5.10.11.3.7.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.7.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.7.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.7.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.8 | PP-04-PLANT ROOM-911 ZONE 13
16 | PROJECT.3.3.5.10.11.3.8.3 | General Civil Access Dates-Plant Room-PP-04-911
16 | PROJECT.3.3.5.10.11.3.8.2 | MEP 1st Fix in Wall-Plant Room-PP-04-911
16 | PROJECT.3.3.5.10.11.3.8.4 | MEP 2nd Fix-Plant Room-PP-04-911
18 | PROJECT.3.3.5.10.11.3.8.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.8.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.8.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.8.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.8.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.8.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.8.7 | MEP Final Fix-Plant Room-PP-04-911
18 | PROJECT.3.3.5.10.11.3.8.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.8.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.8.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.8.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.9 | PP-04-PLANT ROOM- 949 ZONE 10
16 | PROJECT.3.3.5.10.11.3.9.3 | General Civil Access Dates-Plant Room-PP-04-949
16 | PROJECT.3.3.5.10.11.3.9.2 | MEP 1st Fix in Wall-Plant Room-PP-04-949
16 | PROJECT.3.3.5.10.11.3.9.4 | MEP 2nd Fix-Plant Room-PP-04-949
18 | PROJECT.3.3.5.10.11.3.9.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.9.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.9.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.9.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.9.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.9.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.9.7 | MEP Final Fix-Plant Room-PP-04-949
18 | PROJECT.3.3.5.10.11.3.9.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.9.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.9.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.9.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.1 | PP-04-PLANT ROOM-950 ZONE 10
16 | PROJECT.3.3.5.10.11.3.1.3 | General Civil Access Dates-Plant Room-PP-04-950
16 | PROJECT.3.3.5.10.11.3.1.2 | MEP 1st Fix in Wall-Plant Room-PP-04-950
16 | PROJECT.3.3.5.10.11.3.1.4 | MEP 2nd Fix-Plant Room-PP-04-950
18 | PROJECT.3.3.5.10.11.3.1.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.1.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.1.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.1.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.1.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.1.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.1.7 | MEP Final Fix-Plant Room-PP-04-950
18 | PROJECT.3.3.5.10.11.3.1.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.1.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.1.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.1.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.10 | PP-04-PLANT ROOM-948 ZONE 9
16 | PROJECT.3.3.5.10.11.3.10.3 | General Civil Access Dates-Plant Room-PP-04-948
16 | PROJECT.3.3.5.10.11.3.10.2 | MEP 1st Fix in Wall-Plant Room-PP-04-948
16 | PROJECT.3.3.5.10.11.3.10.4 | MEP 2nd Fix-Plant Room-PP-04-948
18 | PROJECT.3.3.5.10.11.3.10.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.10.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.10.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.10.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.10.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.10.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.10.7 | MEP Final Fix-Plant Room-PP-04-948
18 | PROJECT.3.3.5.10.11.3.10.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.10.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.10.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.10.7.5 | Plumbing & Drainage Works
14 | PROJECT.3.3.5.10.11.3.13 | PP-04-PLANT ROOM-951 ZONE 14
16 | PROJECT.3.3.5.10.11.3.13.3 | General Civil Access Dates-Plant Room-PP-04-951
16 | PROJECT.3.3.5.10.11.3.13.2 | MEP 1st Fix in Wall-Plant Room-PP-04-951
16 | PROJECT.3.3.5.10.11.3.13.4 | MEP 2nd Fix-Plant Room-PP-04-951
18 | PROJECT.3.3.5.10.11.3.13.4.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.13.4.2 | CHW piping Works
18 | PROJECT.3.3.5.10.11.3.13.4.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.13.4.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.13.4.5 | Plumbing & Drainage Works
18 | PROJECT.3.3.5.10.11.3.13.4.6 | Water Supply Works
16 | PROJECT.3.3.5.10.11.3.13.7 | MEP Final Fix-Plant Room-PP-04-951
18 | PROJECT.3.3.5.10.11.3.13.7.1 | HVAC Works
18 | PROJECT.3.3.5.10.11.3.13.7.3 | Electrical Works
18 | PROJECT.3.3.5.10.11.3.13.7.4 | Fire Fighting Works
18 | PROJECT.3.3.5.10.11.3.13.7.5 | Plumbing & Drainage Works
8 | PROJECT.3.3.5.11 | ROOF & FACADE WORKS
10 | PROJECT.3.3.5.11.2 | FACADE/ PARAPPET MEP Works
12 | PROJECT.3.3.5.11.2.4 | North Side
14 | PROJECT.3.3.5.11.2.4.3 | General Civil Access Dates- MEP Works
14 | PROJECT.3.3.5.11.2.4.1 | MEP Works
12 | PROJECT.3.3.5.11.2.2 | South Side
14 | PROJECT.3.3.5.11.2.2.3 | General Civil Access Dates- MEP Works
14 | PROJECT.3.3.5.11.2.2.1 | MEP Works
12 | PROJECT.3.3.5.11.2.1 | West Side
14 | PROJECT.3.3.5.11.2.1.3 | General Civil Access Dates- MEP Works
14 | PROJECT.3.3.5.11.2.1.1 | MEP Works
12 | PROJECT.3.3.5.11.2.3 | East Side
14 | PROJECT.3.3.5.11.2.3.3 | General Civil Access Dates- MEP Works
14 | PROJECT.3.3.5.11.2.3.1 | MEP Works
10 | PROJECT.3.3.5.11.1 | PRESSURIZATION FANS FOR STAIRCASES
12 | PROJECT.3.3.5.11.1.6 | Section A
14 | PROJECT.3.3.5.11.1.6.3 | General Civil Access Dates- MEP Works
14 | PROJECT.3.3.5.11.1.6.1 | MEP Works
12 | PROJECT.3.3.5.11.1.1 | Section B
14 | PROJECT.3.3.5.11.1.1.3 | General Civil Access Dates- MEP Works
14 | PROJECT.3.3.5.11.1.1.1 | MEP Works
12 | PROJECT.3.3.5.11.1.2 | Section C
14 | PROJECT.3.3.5.11.1.2.3 | General Civil Access Dates- MEP Works
14 | PROJECT.3.3.5.11.1.2.1 | MEP Works
8 | PROJECT.3.3.5.12 | MEP RISERS
10 | PROJECT.3.3.5.12.1 | ZONE 01
10 | PROJECT.3.3.5.12.2 | ZONE 02
10 | PROJECT.3.3.5.12.3 | ZONE 03
10 | PROJECT.3.3.5.12.4 | ZONE 04
10 | PROJECT.3.3.5.12.5 | ZONE 05
10 | PROJECT.3.3.5.12.6 | ZONE 06
10 | PROJECT.3.3.5.12.7 | ZONE 07
10 | PROJECT.3.3.5.12.8 | ZONE 08
10 | PROJECT.3.3.5.12.9 | ZONE 09
10 | PROJECT.3.3.5.12.10 | ZONE 10
10 | PROJECT.3.3.5.12.11 | ZONE 11
10 | PROJECT.3.3.5.12.12 | ZONE 12
10 | PROJECT.3.3.5.12.13 | ZONE 13
10 | PROJECT.3.3.5.12.14 | ZONE 14
6 | PROJECT.3.3.6 | TESTING & COMMISSIONING
8 | PROJECT.3.3.6.1 | TEMPORARY POWER & WATER
8 | PROJECT.3.3.6.2 | PRE TESTING & COMMISSIONING
10 | PROJECT.3.3.6.2.1 | ELECTRICAL WORKS
10 | PROJECT.3.3.6.2.5 | SPECIALIST SYSTEMS
10 | PROJECT.3.3.6.2.2 | PLUMBING WORKS
10 | PROJECT.3.3.6.2.4 | HVAC WORKS
10 | PROJECT.3.3.6.2.3 | FIRE FIGHTING WORKS
8 | PROJECT.3.3.6.3 | TESTING & COMMISSIONING
10 | PROJECT.3.3.6.3.1 | ELECTRICAL WORKS
10 | PROJECT.3.3.6.3.2 | PLUMBING WORKS
10 | PROJECT.3.3.6.3.5 | SPECIALIST SYSTEMS
10 | PROJECT.3.3.6.3.3 | HVAC WORKS
10 | PROJECT.3.3.6.3.4 | FIRE FIGHTING WORKS
4 | PROJECT.3.4 | VERTICAL TRANSPORTATION
6 | PROJECT.3.4.1 | SUBCONTRACTING
8 | PROJECT.3.4.1.1 | SUBCONTRACTING
10 | PROJECT.3.4.1.1.1 | PREPARATION AND SUBMISSION
10 | PROJECT.3.4.1.1.2 | REVIEW AND APPROVAL
6 | PROJECT.3.4.2 | ENGINEERING, MATERIAL SELECTION & PLACING ORDER
8 | PROJECT.3.4.2.6 | GENERAL
8 | PROJECT.3.4.2.1 | PASSENGER ELEVATORS
10 | PROJECT.3.4.2.1.1 | SUBMISSIONS
10 | PROJECT.3.4.2.1.2 | APPROVALS
10 | PROJECT.3.4.2.1.3 | PLACING ORDER
8 | PROJECT.3.4.2.2 | SERVICE ELEVATORS
10 | PROJECT.3.4.2.2.1 | SUBMISSIONS
10 | PROJECT.3.4.2.2.2 | APPROVALS
10 | PROJECT.3.4.2.2.3 | PLACING ORDER
8 | PROJECT.3.4.2.3 | ESCALATORS
10 | PROJECT.3.4.2.3.1 | SUBMISSIONS
10 | PROJECT.3.4.2.3.2 | APPROVALS
10 | PROJECT.3.4.2.3.3 | PLACING ORDER
8 | PROJECT.3.4.2.4 | TRAVELATORS
10 | PROJECT.3.4.2.4.1 | SUBMISSIONS
10 | PROJECT.3.4.2.4.2 | APPROVALS
10 | PROJECT.3.4.2.4.3 | PLACING ORDER
8 | PROJECT.3.4.2.5 | METHOD STATEMENTS/LOGISTICS STATEMENTS
10 | PROJECT.3.4.2.5.1 | ELEVATORS
10 | PROJECT.3.4.2.5.2 | ESCALATORS
10 | PROJECT.3.4.2.5.3 | TRAVELATORS
6 | PROJECT.3.4.4 | FABRICATION AND DELIVERY
8 | PROJECT.3.4.4.5 | FACTORY ACCEPTANCE TEST (FAT's)
8 | PROJECT.3.4.4.1 | PASSENGER ELEVATORS
8 | PROJECT.3.4.4.2 | SERVICE ELEVATORS
8 | PROJECT.3.4.4.3 | ESCALATORS
8 | PROJECT.3.4.4.4 | TRAVELATORS
6 | PROJECT.3.4.3 | CONSTRUCTION
8 | PROJECT.3.4.3.1 | INSTALLATION
10 | PROJECT.3.4.3.1.1 | PASSENGER ELEVATORS
12 | PROJECT.3.4.3.1.1.13 | PL13
12 | PROJECT.3.4.3.1.1.6 | PL6
12 | PROJECT.3.4.3.1.1.12 | PL12
12 | PROJECT.3.4.3.1.1.8 | PL8
12 | PROJECT.3.4.3.1.1.10 | PL10
12 | PROJECT.3.4.3.1.1.1 | PL1
12 | PROJECT.3.4.3.1.1.3 | PL3
12 | PROJECT.3.4.3.1.1.5 | PL5
12 | PROJECT.3.4.3.1.1.7 | PL7
12 | PROJECT.3.4.3.1.1.9 | PL9
12 | PROJECT.3.4.3.1.1.11 | PL11
12 | PROJECT.3.4.3.1.1.2 | PL2
12 | PROJECT.3.4.3.1.1.4 | PL4
12 | PROJECT.3.4.3.1.1.18 | PL18
12 | PROJECT.3.4.3.1.1.14 | PL14
12 | PROJECT.3.4.3.1.1.15 | PL15
12 | PROJECT.3.4.3.1.1.16 | PL16
12 | PROJECT.3.4.3.1.1.17 | PL17
10 | PROJECT.3.4.3.1.2 | SERVICE ELEVATORS
12 | PROJECT.3.4.3.1.2.1 | SL1
12 | PROJECT.3.4.3.1.2.2 | SL2
12 | PROJECT.3.4.3.1.2.3 | SL3
12 | PROJECT.3.4.3.1.2.5 | SL5
12 | PROJECT.3.4.3.1.2.30 | SL30
12 | PROJECT.3.4.3.1.2.29 | SL29
12 | PROJECT.3.4.3.1.2.31 | FL1
12 | PROJECT.3.4.3.1.2.25 | SL25
12 | PROJECT.3.4.3.1.2.7 | SL7
12 | PROJECT.3.4.3.1.2.11 | SL11
12 | PROJECT.3.4.3.1.2.20 | SL20
12 | PROJECT.3.4.3.1.2.17 | SL17
12 | PROJECT.3.4.3.1.2.26 | SL26
12 | PROJECT.3.4.3.1.2.15 | SL15
12 | PROJECT.3.4.3.1.2.24 | SL24
12 | PROJECT.3.4.3.1.2.8 | SL8
12 | PROJECT.3.4.3.1.2.22 | SL22
12 | PROJECT.3.4.3.1.2.4 | SL4
12 | PROJECT.3.4.3.1.2.18 | SL18
12 | PROJECT.3.4.3.1.2.27 | SL27
12 | PROJECT.3.4.3.1.2.23 | SL23
12 | PROJECT.3.4.3.1.2.6 | SL6
12 | PROJECT.3.4.3.1.2.9 | SL9
12 | PROJECT.3.4.3.1.2.19 | SL19
12 | PROJECT.3.4.3.1.2.32 | FL2
12 | PROJECT.3.4.3.1.2.28 | SL28
12 | PROJECT.3.4.3.1.2.12 | SL12
12 | PROJECT.3.4.3.1.2.21 | SL21
12 | PROJECT.3.4.3.1.2.16 | SL16
12 | PROJECT.3.4.3.1.2.10 | SL10
12 | PROJECT.3.4.3.1.2.13 | SL13
12 | PROJECT.3.4.3.1.2.14 | SL14
10 | PROJECT.3.4.3.1.3 | ESCALATORS
12 | PROJECT.3.4.3.1.3.1 | ESC 1-ESC 2 & ESC 9-ESC 10
12 | PROJECT.3.4.3.1.3.2 | ESC 3-ESC 4 & ESC 11-ESC 12
12 | PROJECT.3.4.3.1.3.3 | ESC 5-ESC 6 & ESC 13-ESC 14
12 | PROJECT.3.4.3.1.3.4 | ESC 17-ESC 18
12 | PROJECT.3.4.3.1.3.5 | ESC 19-ESC 20
12 | PROJECT.3.4.3.1.3.6 | ESC 25-ESC 26
12 | PROJECT.3.4.3.1.3.7 | ESC 31-ESC 32
12 | PROJECT.3.4.3.1.3.8 | ESC 37-ESC 38
12 | PROJECT.3.4.3.1.3.9 | ESC 21-ESC 22
12 | PROJECT.3.4.3.1.3.10 | ESC 27-ESC 28
12 | PROJECT.3.4.3.1.3.11 | ESC 29-ESC 30
12 | PROJECT.3.4.3.1.3.12 | ESC 33-ESC 34
12 | PROJECT.3.4.3.1.3.13 | ESC 41-ESC 42
12 | PROJECT.3.4.3.1.3.14 | ESC 35-ESC 36
12 | PROJECT.3.4.3.1.3.15 | ESC 49-ESC 50
12 | PROJECT.3.4.3.1.3.16 | ESC 55-ESC 56
12 | PROJECT.3.4.3.1.3.17 | ESC 43-ESC 44
12 | PROJECT.3.4.3.1.3.18 | ESC 45-ESC 46
12 | PROJECT.3.4.3.1.3.19 | ESC 47-ESC 48
12 | PROJECT.3.4.3.1.3.20 | ESC 51-ESC 52
12 | PROJECT.3.4.3.1.3.21 | ESC 53-ESC 54
12 | PROJECT.3.4.3.1.3.22 | ESC 57-ESC 58
12 | PROJECT.3.4.3.1.3.23 | ESC 61-ESC 62
12 | PROJECT.3.4.3.1.3.24 | ESC 59-ESC 60
12 | PROJECT.3.4.3.1.3.25 | ESC 63-ESC 64
12 | PROJECT.3.4.3.1.3.26 | ESC 67-ESC 68
12 | PROJECT.3.4.3.1.3.27 | ESC 65-ESC 66
10 | PROJECT.3.4.3.1.4 | TRAVELATORS
12 | PROJECT.3.4.3.1.4.1 | T3-T4
12 | PROJECT.3.4.3.1.4.2 | T7-T8
12 | PROJECT.3.4.3.1.4.3 | T1-T2
12 | PROJECT.3.4.3.1.4.4 | T5-T6
12 | PROJECT.3.4.3.1.4.5 | T9-T10
8 | PROJECT.3.4.3.2 | FINISHES
10 | PROJECT.3.4.3.2.1 | PASSENGER ELEVATORS
10 | PROJECT.3.4.3.2.2 | SERVICE ELEVATORS
10 | PROJECT.3.4.3.2.3 | ESCALATORS
10 | PROJECT.3.4.3.2.4 | TRAVELATORS
8 | PROJECT.3.4.3.5 | TESTING & COMMISSIONING
10 | PROJECT.3.4.3.5.1 | PASSENGER ELEVATORS
10 | PROJECT.3.4.3.5.2 | SERVICE ELEVATORS
10 | PROJECT.3.4.3.5.3 | ESCALATORS
10 | PROJECT.3.4.3.5.4 | TRAVELATORS
8 | PROJECT.3.4.3.3 | HANDING OVER
10 | PROJECT.3.4.3.3.1 | PASSENGER ELEVATORS
10 | PROJECT.3.4.3.3.2 | SERVICE ELEVATORS
10 | PROJECT.3.4.3.3.3 | ESCALATORS
10 | PROJECT.3.4.3.3.4 | TRAVELATORS
6 | PROJECT.3.4.5 | (New WBS)
4 | PROJECT.3.5 | SNOW PARK
6 | PROJECT.3.5.1 | PROCUREMENT
8 | PROJECT.3.5.1.1 | RECEIVING TENDER INFORMATION
8 | PROJECT.3.5.1.2 | SUBCONTRACT TENDER PACKAGES
10 | PROJECT.3.5.1.2.51 | REFERIGERATION AND SNOW MAKING SYSTEM
10 | PROJECT.3.5.1.2.52 | COLD INSULATION
10 | PROJECT.3.5.1.2.53 | EARLY THEMING
10 | PROJECT.3.5.1.2.54 | FINAL THEMING
10 | PROJECT.3.5.1.2.55 | RIDES (MT, TRAIN, CAROUSEL, BUMPER TUBES)
10 | PROJECT.3.5.1.2.56 | AERIAL RIDE
10 | PROJECT.3.5.1.2.57 | VERTICAL TRANSPORTATION (MAGIC CARPETS AND ZORB BALL RETURN SYSTEM)
10 | PROJECT.3.5.1.2.58 | FIT-OUT
10 | PROJECT.3.5.1.2.59 | FF&E
10 | PROJECT.3.5.1.2.60 | MEP
10 | PROJECT.3.5.1.2.61 | SHOW LIGHTING
10 | PROJECT.3.5.1.2.62 | AUDIO VIDEO
10 | PROJECT.3.5.1.2.63 | BMU AND CAT WALK SYSTEM
10 | PROJECT.3.5.1.2.64 | KITCHEN EQUIPMENT
10 | PROJECT.3.5.1.2.65 | TURNSTILE
10 | PROJECT.3.5.1.2.66 | ANTI-THEFT SYSTEM -TAGIT
10 | PROJECT.3.5.1.2.67 | LAUNDRY
10 | PROJECT.3.5.1.2.68 | SECONDARY STEEL WORKS
10 | PROJECT.3.5.1.2.69 | STEEL DOORS- PLANT ROOMS
10 | PROJECT.3.5.1.2.70 | GLAZING WORKS ( @MEZZANINE)
6 | PROJECT.3.5.2 | ENGINEERING AND MATERIAL SELECTION
8 | PROJECT.3.5.2.9 | SNOW MAKING AND REFERIGERATION
10 | PROJECT.3.5.2.9.3 | DESIGN DRAWINGS
10 | PROJECT.3.5.2.9.1 | SHOP DRAWINGS
10 | PROJECT.3.5.2.9.2 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.9.3.1 | MATERIAL PROCUREMENT AND DELIVERY
8 | PROJECT.3.5.2.10 | COLD INSULATION PACKAGE
10 | PROJECT.3.5.2.10.4 | DESIGN DRAWINGS
10 | PROJECT.3.5.2.10.1 | SHOP DRAWINGS
10 | PROJECT.3.5.2.10.2 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.10.3 | PROCUREMENT, FABRICATION AND DELIVERY
8 | PROJECT.3.5.2.6 | THEMING
10 | PROJECT.3.5.2.6.1 | ENCHANTING TREE
12 | PROJECT.3.5.2.6.1.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.6.1.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.6.1.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.6.2 | FLURRY TREE
12 | PROJECT.3.5.2.6.2.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.6.2.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.6.2.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.6.3 | LAUNCHING PLATFORM
12 | PROJECT.3.5.2.6.3.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.6.3.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.6.3.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.6.4 | LANDING PLATFORM
12 | PROJECT.3.5.2.6.4.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.6.4.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.6.4.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.6.5 | WARM SIDE THEMING
12 | PROJECT.3.5.2.6.5.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.6.5.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.6.5.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.6.6 | COLD SIDE THEMING
12 | PROJECT.3.5.2.6.6.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.6.6.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.6.6.4 | PROCUREMENT, FABRICATION AND DELIVERY
8 | PROJECT.3.5.2.4 | RIDES
10 | PROJECT.3.5.2.4.1 | MOUNTAIN THRILLER, TOBOGGAN RUN AND RETURN SYSTEM
12 | PROJECT.3.5.2.4.1.3 | DESIGN DRAWINGS
12 | PROJECT.3.5.2.4.1.1 | SHOP DRAWINGS
12 | PROJECT.3.5.2.4.1.2 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.4.1.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.4.2 | CRYSTAL CAROUSEL
12 | PROJECT.3.5.2.4.2.5 | DESIGN DRAWINGS
12 | PROJECT.3.5.2.4.2.6 | SHOP DRAWINGS
12 | PROJECT.3.5.2.4.2.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.4.2.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.4.3 | POLAR EXPRESS TRAIN
12 | PROJECT.3.5.2.4.3.1 | DESIGN DRAWINGS
12 | PROJECT.3.5.2.4.3.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.4.3.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.4.3.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.4.4 | BUMPER TUBES
12 | PROJECT.3.5.2.4.4.1 | DESIGN DRAWINGS
12 | PROJECT.3.5.2.4.4.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.4.4.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.4.4.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.4.5 | AERIAL RIDE
12 | PROJECT.3.5.2.4.5.1 | DESIGN DRAWINGS
12 | PROJECT.3.5.2.4.5.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.4.5.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.4.5.4 | PROCUREMENT, FABRICATION AND DELIVERY
8 | PROJECT.3.5.2.5 | VERTICAL TRANSPORTATION
10 | PROJECT.3.5.2.5.4 | MAGIC CARPET
12 | PROJECT.3.5.2.5.4.5 | DESIGN DRAWINGS
12 | PROJECT.3.5.2.5.4.6 | SHOP DRAWINGS
12 | PROJECT.3.5.2.5.4.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.5.4.4 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.5.2.5.1 | ZORB BALL RETURN SYSTEM
12 | PROJECT.3.5.2.5.1.1 | DESIGN DRAWINGS
12 | PROJECT.3.5.2.5.1.2 | SHOP DRAWINGS
12 | PROJECT.3.5.2.5.1.3 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.5.1.4 | PROCUREMENT, FABRICATION AND DELIVERY
8 | PROJECT.3.5.2.3 | FIT OUT AND FF&E
10 | PROJECT.3.5.2.3.4 | SHOP DRAWINGS
10 | PROJECT.3.5.2.3.1 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.3.3 | FABRICATION AND MATERIAL DELIVERY AT SITE
8 | PROJECT.3.5.2.1 | MEP
10 | PROJECT.3.5.2.1.1 | SHOP DRAWINGS
12 | PROJECT.3.5.2.1.1.2 | DRAINAGE/WATER/CONDENSATE PIPE
12 | PROJECT.3.5.2.1.1.1 | MECHANICAL
12 | PROJECT.3.5.2.1.1.3 | ELECTRICAL LOAD SCHEDULE
12 | PROJECT.3.5.2.1.1.4 | HVAC- CHW/AC/VENTILATION
12 | PROJECT.3.5.2.1.1.5 | FIRE PROTECTION/FIRE ALARM/EXIT EMERGENCY
12 | PROJECT.3.5.2.1.1.7 | ACCESS CONTROL SYSTEM
12 | PROJECT.3.5.2.1.1.8 | LIGHTING AND SMALL POWER/CONTAINMENT
12 | PROJECT.3.5.2.1.1.9 | BUILDERS WORK
12 | PROJECT.3.5.2.1.1.10 | CO-ORDINATON
12 | PROJECT.3.5.2.1.1.11 | PAVA/CCTV
10 | PROJECT.3.5.2.1.2 | MATERIAL SUBMITTALS
12 | PROJECT.3.5.2.1.2.1 | MECHANICAL
12 | PROJECT.3.5.2.1.2.2 | ELECTRICAL
12 | PROJECT.3.5.2.1.2.3 | PLUMBING/DRAINAGE
12 | PROJECT.3.5.2.1.2.4 | HVAC
12 | PROJECT.3.5.2.1.2.5 | FIRE ALARM/FIRE FIGHTING
10 | PROJECT.3.5.2.1.3 | MATERIAL PROCUREMENT AND DELIVERY
12 | PROJECT.3.5.2.1.3.1 | LONG LEAD ITEMS
14 | PROJECT.3.5.2.1.3.1.1 | ELECTRICAL
14 | PROJECT.3.5.2.1.3.1.2 | PLUMBING
14 | PROJECT.3.5.2.1.3.1.3 | HVAC
14 | PROJECT.3.5.2.1.3.1.4 | FIREFIGHTING
8 | PROJECT.3.5.2.8 | SHOW LIGHTING
10 | PROJECT.3.5.2.8.1 | SHOP DRAWING
10 | PROJECT.3.5.2.8.3 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.8.2 | PROCUREMENTAND DELIVERY AT SITE
8 | PROJECT.3.5.2.7 | AUDIO VIDEO
10 | PROJECT.3.5.2.7.1 | SHOP DRAWING
10 | PROJECT.3.5.2.7.2 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.7.3 | MATERIAL DELIVERY AT SITE
8 | PROJECT.3.5.2.14 | BMU
10 | PROJECT.3.5.2.14.4 | DESIGN DRAWINGS
10 | PROJECT.3.5.2.14.1 | SHOP DRAWINGS
10 | PROJECT.3.5.2.14.2 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.14.3 | PROCUREMENT, FABRICATION AND DELIVERY AT SITE
8 | PROJECT.3.5.2.18 | CAT WALK SYSTEM
10 | PROJECT.3.5.2.18.4 | DESIGN DRAWINGS
10 | PROJECT.3.5.2.18.1 | SHOP DRAWINGS
10 | PROJECT.3.5.2.18.2 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.18.3 | FABRICATION AND MATERIAL DELIVERY AT SITE
8 | PROJECT.3.5.2.11 | KITCHEN EQUIPMENT
10 | PROJECT.3.5.2.11.1 | SHOP DRAWINGS
10 | PROJECT.3.5.2.11.2 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.11.3 | PROCUREMENT, FABRICATION AND DELIVERY AT SITE
8 | PROJECT.3.5.2.16 | ANTI-THEFT SYSTEM -TAGIT
10 | PROJECT.3.5.2.16.1 | SHOP DRAWINGS
10 | PROJECT.3.5.2.16.2 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.16.3 | PROCUREMENT AND DELIVERY AT SITE
8 | PROJECT.3.5.2.13 | TURNSTILE
10 | PROJECT.3.5.2.13.1 | SHOP DRAWINGS
10 | PROJECT.3.5.2.13.15 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.13.2 | PROCUREMENT AND DELIVERY AT SITE
8 | PROJECT.3.5.2.12 | LAUNDRY
10 | PROJECT.3.5.2.12.14 | SHOP DRAWINGS
10 | PROJECT.3.5.2.12.1 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.12.2 | PROCUREMENT AND DELIVERY AT SITE
8 | PROJECT.3.5.2.2 | SECONDARY STEEL WORKS
10 | PROJECT.3.5.2.2.1 | SHOP DRAWINGS
12 | PROJECT.3.5.2.2.1.10 | FOR PLANT ROOM- LEVEL 3 ( MEP/REFERIGERATION, MELTPIT, MAINT PIT)
12 | PROJECT.3.5.2.2.1.11 | FOR PLANT ROOM- LEVEL 4 ( MEP/REFERIGERATION)
12 | PROJECT.3.5.2.2.1.1 | FOR INSULATION PACKAGE
12 | PROJECT.3.5.2.2.1.3 | FOR THEMING- ENCHANTING TREE, LAUNCHING & LANDING
12 | PROJECT.3.5.2.2.1.12 | FOR CEILING VOID SERVICES
12 | PROJECT.3.5.2.2.1.4 | FOR MOUNTAIN THRILLER
12 | PROJECT.3.5.2.2.1.7 | FOR BMU
12 | PROJECT.3.5.2.2.1.8 | FOR AERIAL RIDE
12 | PROJECT.3.5.2.2.1.9 | FOR CAT WALK
10 | PROJECT.3.5.2.2.2 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.2.3 | PROCUREMENT, FABRICATION AND DELIVERY AT SITE
8 | PROJECT.3.5.2.15 | GLAZING WORKS ( @MEZZANINE)
10 | PROJECT.3.5.2.15.1 | SHOP DRAWINGS
10 | PROJECT.3.5.2.15.2 | MATERIAL SUBMITTALS
10 | PROJECT.3.5.2.15.3 | PROCUREMENT, FABRICATION AND MATERIAL DELIVERY AT SITE
6 | PROJECT.3.5.3 | CONSTRUCTION
8 | PROJECT.3.5.3.4 | BASE BUILD
10 | PROJECT.3.5.3.4.4 | SECTION-A (GRID A17 TO A21)
10 | PROJECT.3.5.3.4.1 | SECTION-B (GRID A22 TO A25)
10 | PROJECT.3.5.3.4.2 | SECTION-C (GRID A26- End)
8 | PROJECT.3.5.3.10 | GENERAL MEP PROVISIONS- SNOWPARK
8 | PROJECT.3.5.3.7.1 | PLANT ROOM ( Grid A16-A17)
10 | PROJECT.3.5.3.7.1.3 | SERVICE LEVEL ( -0.975)- GLYCOL TANK ROOM AND STORAGE ROOM
10 | PROJECT.3.5.3.7.1.1 | LEVEL +29.375
12 | PROJECT.3.5.3.7.1.1.3 | CIVIL BUILDERS WORK
12 | PROJECT.3.5.3.7.1.1.1 | REFERIGERATION WORKS ( AMMONIA PR/LV ROOM)
12 | PROJECT.3.5.3.7.1.1.2 | MEP WORKS
12 | PROJECT.3.5.3.7.1.1.4 | FINAL FINISHES AND FIXTURES
10 | PROJECT.3.5.3.7.1.2 | LEVEL +34.60
12 | PROJECT.3.5.3.7.1.2.5 | ROOF INSTALLATIONS- MEP AND REFERIGERATION WORKS
8 | PROJECT.3.5.3.2 | WARM SIDE
10 | PROJECT.3.5.3.2.1 | SECTION-A (GRID A17 TO A21)
12 | PROJECT.3.5.3.2.1.4 | WARM SIDE- LEVEL 2, PP1(Laundry, Office Areas, ITRm, Cash offc, Equi Rental, Prayer Rm, Chng Rm,WCs)
14 | PROJECT.3.5.3.2.1.4.2 | WARM SIDE- LEVEL 2, PP1 (CIVIL & FINISHES)
14 | PROJECT.3.5.3.2.1.4.1 | WARM SIDE- LEVEL 2, PP1 (MEP)
16 | PROJECT.3.5.3.2.1.4.1.1 | ELECTRICAL
18 | PROJECT.3.5.3.2.1.4.1.1.1 | POWER & LIGHTING
20 | PROJECT.3.5.3.2.1.4.1.1.1.1 | FIRST FIX
20 | PROJECT.3.5.3.2.1.4.1.1.1.2 | SECOND FIX
20 | PROJECT.3.5.3.2.1.4.1.1.1.4 | THIRD FIX
20 | PROJECT.3.5.3.2.1.4.1.1.1.3 | FINAL FIX
18 | PROJECT.3.5.3.2.1.4.1.1.2 | LOW CURRENT
20 | PROJECT.3.5.3.2.1.4.1.1.2.2 | SECOND FIX
20 | PROJECT.3.5.3.2.1.4.1.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.2.1.4.1.2 | PLUMBING
18 | PROJECT.3.5.3.2.1.4.1.2.1 | FIRST FIX
18 | PROJECT.3.5.3.2.1.4.1.2.2 | SECOND FIX
18 | PROJECT.3.5.3.2.1.4.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.2.1.4.1.3 | HVAC
18 | PROJECT.3.5.3.2.1.4.1.3.1 | FIRST FIX
18 | PROJECT.3.5.3.2.1.4.1.3.2 | SECOND FIX
18 | PROJECT.3.5.3.2.1.4.1.3.3 | FINAL FIX
16 | PROJECT.3.5.3.2.1.4.1.4 | FIREFIGHTING
18 | PROJECT.3.5.3.2.1.4.1.4.1 | FIRST FIX
18 | PROJECT.3.5.3.2.1.4.1.4.2 | SECOND FIX
18 | PROJECT.3.5.3.2.1.4.1.4.3 | FINAL FIX
16 | PROJECT.3.5.3.2.1.4.1.5 | GAS SYSTEM
12 | PROJECT.3.5.3.2.1.7 | WARM SIDE- LEVEL 3, PP2 (UNIT-A4-RESTAURANT, PARTY ROOM, VIP SUITE, AIRL LOCK, WCs)
14 | PROJECT.3.5.3.2.1.7.4 | WARM SIDE- LEVEL 3, PP2 (CIVIL & FINISHES)
14 | PROJECT.3.5.3.2.1.7.3 | WARM SIDE- LEVEL 3, PP2 (MEP)
16 | PROJECT.3.5.3.2.1.7.3.1 | ELECTRICAL
18 | PROJECT.3.5.3.2.1.7.3.1.1 | POWER & LIGHTING
20 | PROJECT.3.5.3.2.1.7.3.1.1.1 | FIRST FIX
20 | PROJECT.3.5.3.2.1.7.3.1.1.2 | SECOND FIX
20 | PROJECT.3.5.3.2.1.7.3.1.1.4 | THIRD FIX
20 | PROJECT.3.5.3.2.1.7.3.1.1.3 | FINAL FIX
18 | PROJECT.3.5.3.2.1.7.3.1.2 | LOW CURRENT
20 | PROJECT.3.5.3.2.1.7.3.1.2.1 | FIRST FIX
20 | PROJECT.3.5.3.2.1.7.3.1.2.2 | SECOND FIX
20 | PROJECT.3.5.3.2.1.7.3.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.2.1.7.3.2 | PLUMBING
18 | PROJECT.3.5.3.2.1.7.3.2.1 | FIRST FIX
18 | PROJECT.3.5.3.2.1.7.3.2.2 | SECOND FIX
18 | PROJECT.3.5.3.2.1.7.3.2.3 | FINAL FIX
16 | PROJECT.3.5.3.2.1.7.3.3 | HVAC
18 | PROJECT.3.5.3.2.1.7.3.3.1 | FIRST FIX
18 | PROJECT.3.5.3.2.1.7.3.3.2 | SECOND FIX
18 | PROJECT.3.5.3.2.1.7.3.3.3 | FINAL FIX
16 | PROJECT.3.5.3.2.1.7.3.4 | FIREFIGHTING
18 | PROJECT.3.5.3.2.1.7.3.4.1 | FIRST FIX
18 | PROJECT.3.5.3.2.1.7.3.4.2 | SECOND FIX
18 | PROJECT.3.5.3.2.1.7.3.4.3 | FINAL FIX
16 | PROJECT.3.5.3.2.1.7.3.5 | FUEL OIL SYSTEM
16 | PROJECT.3.5.3.2.1.7.3.6 | ROOF EQUIPMENTS
10 | PROJECT.3.5.3.2.2 | SECTION-B (GRID A22 TO A25)
12 | PROJECT.3.5.3.2.2.3 | WARM SIDE- LEVEL 2, (Section- B; First Aid Rm, Canteen, Staff M/F Chng Rm, Animal hbtm)
14 | PROJECT.3.5.3.2.2.3.2 | WARM SIDE- LEVEL 2, (CIVIL & FINISHES)
14 | PROJECT.3.5.3.2.2.3.1 | WARM SIDE- LEVEL 2, (MEP)
16 | PROJECT.3.5.3.2.2.3.1.1 | ELECTRICAL
18 | PROJECT.3.5.3.2.2.3.1.1.1 | POWER & LIGHTING
20 | PROJECT.3.5.3.2.2.3.1.1.1.1 | FIRST FIX
20 | PROJECT.3.5.3.2.2.3.1.1.1.2 | SECOND FIX
20 | PROJECT.3.5.3.2.2.3.1.1.1.4 | THIRD FIX
20 | PROJECT.3.5.3.2.2.3.1.1.1.3 | FINAL FIX
18 | PROJECT.3.5.3.2.2.3.1.1.2 | LOW CURRENT
20 | PROJECT.3.5.3.2.2.3.1.1.2.2 | SECOND FIX
20 | PROJECT.3.5.3.2.2.3.1.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.2.2.3.1.2 | PLUMBING
18 | PROJECT.3.5.3.2.2.3.1.2.1 | FIRST FIX
18 | PROJECT.3.5.3.2.2.3.1.2.2 | SECOND FIX
18 | PROJECT.3.5.3.2.2.3.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.2.2.3.1.3 | HVAC
18 | PROJECT.3.5.3.2.2.3.1.3.1 | FIRST FIX
18 | PROJECT.3.5.3.2.2.3.1.3.2 | SECOND FIX
18 | PROJECT.3.5.3.2.2.3.1.3.3 | FINAL FIX
16 | PROJECT.3.5.3.2.2.3.1.4 | FIREFIGHTING
18 | PROJECT.3.5.3.2.2.3.1.4.1 | FIRST FIX
18 | PROJECT.3.5.3.2.2.3.1.4.2 | SECOND FIX
18 | PROJECT.3.5.3.2.2.3.1.4.3 | FINAL FIX
8 | PROJECT.3.5.3.3 | COLD BOX
10 | PROJECT.3.5.3.3.1 | AREA 1 ( A17-18 / C21-27)
12 | PROJECT.3.5.3.3.1.5 | ERECTION SCAFFOLDING ( A17-18 / C21-27)
12 | PROJECT.3.5.3.3.1.6 | CEILING VOID ( A17-18 / C21-27)
14 | PROJECT.3.5.3.3.1.6.1 | SECONDARY STEEL SUPPORT INSTALLATION
14 | PROJECT.3.5.3.3.1.6.2 | CEILING VOID INSTALLATION
14 | PROJECT.3.5.3.3.1.6.4 | CEILING VOID / MEP WORKS
16 | PROJECT.3.5.3.3.1.6.4.1 | ELECTRICAL
18 | PROJECT.3.5.3.3.1.6.4.1.1 | POWER & LIGHTING
20 | PROJECT.3.5.3.3.1.6.4.1.1.1 | FIRST FIX
20 | PROJECT.3.5.3.3.1.6.4.1.1.2 | SECOND FIX
20 | PROJECT.3.5.3.3.1.6.4.1.1.4 | THIRD FIX
20 | PROJECT.3.5.3.3.1.6.4.1.1.3 | FINAL FIX
18 | PROJECT.3.5.3.3.1.6.4.1.2 | LOW CURRENT
20 | PROJECT.3.5.3.3.1.6.4.1.2.1 | FIRST FIX
20 | PROJECT.3.5.3.3.1.6.4.1.2.2 | SECOND FIX
20 | PROJECT.3.5.3.3.1.6.4.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.3.1.6.4.3 | HVAC
18 | PROJECT.3.5.3.3.1.6.4.3.1 | FIRST FIX
18 | PROJECT.3.5.3.3.1.6.4.3.2 | SECOND FIX
18 | PROJECT.3.5.3.3.1.6.4.3.3 | FINAL FIX
16 | PROJECT.3.5.3.3.1.6.4.4 | FIREFIGHTING
18 | PROJECT.3.5.3.3.1.6.4.4.1 | FIRST FIX
18 | PROJECT.3.5.3.3.1.6.4.4.2 | SECOND FIX
18 | PROJECT.3.5.3.3.1.6.4.4.3 | FINAL FIX
14 | PROJECT.3.5.3.3.1.6.3 | BMU & AERIAL RIDE CANTILEVER
12 | PROJECT.3.5.3.3.1.4 | COLD SIDE ( A17-18 / C21-27)
14 | PROJECT.3.5.3.3.1.4.5 | CEILING/SOFFIT & WALLS INSULATION PANEL
14 | PROJECT.3.5.3.3.1.4.2 | REFERIGERATION /MEP WORKS
14 | PROJECT.3.5.3.3.1.4.1 | FLOOR AND RAMPS-SNOW MAKING WORKS
14 | PROJECT.3.5.3.3.1.4.3 | THEMING WORKS
14 | PROJECT.3.5.3.3.1.4.4 | RIDES
10 | PROJECT.3.5.3.3.9 | AREA 2 (A18-25 / C21-22)
12 | PROJECT.3.5.3.3.9.5 | ERECTION SCAFFOLDING (A18-25 / C21-22)
12 | PROJECT.3.5.3.3.9.6 | CEILING VOID (A18-25 / C21-22)
14 | PROJECT.3.5.3.3.9.6.1 | SECONDARY STEEL SUPPORT INSTALLATION
14 | PROJECT.3.5.3.3.9.6.2 | CEILING VOID INSTALLATION
14 | PROJECT.3.5.3.3.9.6.4 | CEILING VOID / MEP WORKS
16 | PROJECT.3.5.3.3.9.6.4.1 | ELECTRICAL
18 | PROJECT.3.5.3.3.9.6.4.1.1 | POWER & LIGHTING
20 | PROJECT.3.5.3.3.9.6.4.1.1.1 | FIRST FIX
20 | PROJECT.3.5.3.3.9.6.4.1.1.2 | SECOND FIX
20 | PROJECT.3.5.3.3.9.6.4.1.1.4 | THIRD FIX
20 | PROJECT.3.5.3.3.9.6.4.1.1.3 | FINAL FIX
18 | PROJECT.3.5.3.3.9.6.4.1.2 | LOW CURRENT
20 | PROJECT.3.5.3.3.9.6.4.1.2.1 | FIRST FIX
20 | PROJECT.3.5.3.3.9.6.4.1.2.2 | SECOND FIX
20 | PROJECT.3.5.3.3.9.6.4.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.3.9.6.4.3 | HVAC
18 | PROJECT.3.5.3.3.9.6.4.3.1 | FIRST FIX
18 | PROJECT.3.5.3.3.9.6.4.3.2 | SECOND FIX
18 | PROJECT.3.5.3.3.9.6.4.3.3 | FINAL FIX
16 | PROJECT.3.5.3.3.9.6.4.4 | FIREFIGHTING
18 | PROJECT.3.5.3.3.9.6.4.4.1 | FIRST FIX
18 | PROJECT.3.5.3.3.9.6.4.4.2 | SECOND FIX
18 | PROJECT.3.5.3.3.9.6.4.4.3 | FINAL FIX
14 | PROJECT.3.5.3.3.9.6.3 | AERIAL RIDE CANTILEVER
12 | PROJECT.3.5.3.3.9.4 | COLD SIDE (A18-25 / C21-22)
14 | PROJECT.3.5.3.3.9.4.5 | CEILING/SOFFIT & WALLS INSULATION PANEL
14 | PROJECT.3.5.3.3.9.4.2 | REFERIGERATION /MEP WORKS
14 | PROJECT.3.5.3.3.9.4.1 | FLOOR AND RAMPS-SNOW MAKING WORKS
14 | PROJECT.3.5.3.3.9.4.3 | THEMING WORKS
14 | PROJECT.3.5.3.3.9.4.4 | RIDES
14 | PROJECT.3.5.3.3.9.4.7 | GLAZING @ MEZANINE
14 | PROJECT.3.5.3.3.9.4.9 | STAIRCASES (BASE BUILD) ST-06
10 | PROJECT.3.5.3.3.2 | AREA 3 ( A18-AB03 / C26-27)
12 | PROJECT.3.5.3.3.2.5 | ERECTION SCAFFOLDING ( A18-AB03 / C26-27)
12 | PROJECT.3.5.3.3.2.6 | CEILING VOID ( A18-AB03 / C26-27)
14 | PROJECT.3.5.3.3.2.6.1 | SECONDARY STEEL SUPPORT INSTALLATION
14 | PROJECT.3.5.3.3.2.6.2 | CEILING VOID INSTALLATION
14 | PROJECT.3.5.3.3.2.6.4 | CEILING VOID / MEP WORKS
16 | PROJECT.3.5.3.3.2.6.4.1 | ELECTRICAL
18 | PROJECT.3.5.3.3.2.6.4.1.1 | POWER & LIGHTING
20 | PROJECT.3.5.3.3.2.6.4.1.1.1 | FIRST FIX
20 | PROJECT.3.5.3.3.2.6.4.1.1.2 | SECOND FIX
20 | PROJECT.3.5.3.3.2.6.4.1.1.4 | THIRD FIX
20 | PROJECT.3.5.3.3.2.6.4.1.1.3 | FINAL FIX
18 | PROJECT.3.5.3.3.2.6.4.1.2 | LOW CURRENT
20 | PROJECT.3.5.3.3.2.6.4.1.2.1 | FIRST FIX
20 | PROJECT.3.5.3.3.2.6.4.1.2.2 | SECOND FIX
20 | PROJECT.3.5.3.3.2.6.4.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.3.2.6.4.3 | HVAC
18 | PROJECT.3.5.3.3.2.6.4.3.1 | FIRST FIX
18 | PROJECT.3.5.3.3.2.6.4.3.2 | SECOND FIX
18 | PROJECT.3.5.3.3.2.6.4.3.3 | FINAL FIX
16 | PROJECT.3.5.3.3.2.6.4.4 | FIREFIGHTING
18 | PROJECT.3.5.3.3.2.6.4.4.1 | FIRST FIX
18 | PROJECT.3.5.3.3.2.6.4.4.2 | SECOND FIX
18 | PROJECT.3.5.3.3.2.6.4.4.3 | FINAL FIX
14 | PROJECT.3.5.3.3.2.6.3 | AERIAL RIDE CANTILEVER
12 | PROJECT.3.5.3.3.2.4 | COLD SIDE ( A18-AB03 / C26-27)
14 | PROJECT.3.5.3.3.2.4.5 | CEILING/SOFFIT & WALLS INSULATION PANEL
14 | PROJECT.3.5.3.3.2.4.2 | REFERIGERATION /MEP WORKS
14 | PROJECT.3.5.3.3.2.4.1 | FLOOR AND RAMPS-SNOW MAKING WORKS
14 | PROJECT.3.5.3.3.2.4.3 | THEMING WORKS
14 | PROJECT.3.5.3.3.2.4.4 | RIDES
14 | PROJECT.3.5.3.3.2.4.9 | STAIRCASES (BASE BUILD) ST-02
10 | PROJECT.3.5.3.3.8 | AREA 4 ( A18-AB03 / C22-26) - CENTRAL AREA
12 | PROJECT.3.5.3.3.8.5 | ERECT SCAFFOLDING ( A18-AB03 / C22-26) - CENTRAL AREA
14 | PROJECT.3.5.3.3.8.5.1 | ERECTION
14 | PROJECT.3.5.3.3.8.5.2 | DISMANTLING
12 | PROJECT.3.5.3.3.8.6 | CEILING VOID ( A18-AB03 / C22-26) - CENTRAL AREA
14 | PROJECT.3.5.3.3.8.6.1 | SECONDARY STEEL SUPPORT INSTALLATION
14 | PROJECT.3.5.3.3.8.6.2 | CEILING VOID INSTALLATION
14 | PROJECT.3.5.3.3.8.6.3 | CEILING VOID / MEP WORKS
16 | PROJECT.3.5.3.3.8.6.3.1 | ELECTRICAL
18 | PROJECT.3.5.3.3.8.6.3.1.1 | POWER & LIGHTING
20 | PROJECT.3.5.3.3.8.6.3.1.1.1 | FIRST FIX
20 | PROJECT.3.5.3.3.8.6.3.1.1.2 | SECOND FIX
20 | PROJECT.3.5.3.3.8.6.3.1.1.4 | THIRD FIX
20 | PROJECT.3.5.3.3.8.6.3.1.1.3 | FINAL FIX
18 | PROJECT.3.5.3.3.8.6.3.1.2 | LOW CURRENT
20 | PROJECT.3.5.3.3.8.6.3.1.2.1 | FIRST FIX
20 | PROJECT.3.5.3.3.8.6.3.1.2.2 | SECOND FIX
20 | PROJECT.3.5.3.3.8.6.3.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.3.8.6.3.3 | HVAC
18 | PROJECT.3.5.3.3.8.6.3.3.1 | FIRST FIX
18 | PROJECT.3.5.3.3.8.6.3.3.2 | SECOND FIX
18 | PROJECT.3.5.3.3.8.6.3.3.3 | FINAL FIX
16 | PROJECT.3.5.3.3.8.6.3.4 | FIREFIGHTING
18 | PROJECT.3.5.3.3.8.6.3.4.1 | FIRST FIX
18 | PROJECT.3.5.3.3.8.6.3.4.2 | SECOND FIX
18 | PROJECT.3.5.3.3.8.6.3.4.3 | FINAL FIX
12 | PROJECT.3.5.3.3.8.3 | COLD SIDE ( A18-AB03 / C22-26) - CENTRAL AREA
14 | PROJECT.3.5.3.3.8.3.5 | CEILING/SOFFIT & WALLS INSULATION PANEL
14 | PROJECT.3.5.3.3.8.3.1 | FLOOR AND RAMPS-SNOW MAKING WORKS
14 | PROJECT.3.5.3.3.8.3.3 | THEMING WORKS
16 | PROJECT.3.5.3.3.8.3.3.1 | PHASE-1- BASE SUPPORTS
16 | PROJECT.3.5.3.3.8.3.3.2 | PHASE-2 - FINAL INSTALLATIONS
14 | PROJECT.3.5.3.3.8.3.2 | REFERIGERATION
14 | PROJECT.3.5.3.3.8.3.6 | RIDES
14 | PROJECT.3.5.3.3.8.3.4 | STAIRCASES ( BASE BUILD) ST-03 / 04 / 05 / 07/ 08
16 | PROJECT.3.5.3.3.8.3.4.3 | STEEL STAIR NO- 3
16 | PROJECT.3.5.3.3.8.3.4.4 | STEEL STAIR NO- 4
16 | PROJECT.3.5.3.3.8.3.4.2 | STEEL STAIR NO- 5
16 | PROJECT.3.5.3.3.8.3.4.5 | STEEL STAIR NO- 7
16 | PROJECT.3.5.3.3.8.3.4.6 | STEEL STAIR NO- 8
12 | PROJECT.3.5.3.3.8.7 | BMU & AERIAL RIDE CANTILEVER ( A18-AB03 / C22-26) - CENTRAL AREA
10 | PROJECT.3.5.3.3.7 | AREA 5 (AB04-AB06 / C18-27) - CURVED AREA
12 | PROJECT.3.5.3.3.7.4 | INTERFACE WITH MALL/MANGROVE SIDE (AB03-AB06 / C18-27) - CURVED AREA
12 | PROJECT.3.5.3.3.7.5 | ERECTION SCAFFOLDING (AB03-AB06 / C18-27) - CURVED AREA
12 | PROJECT.3.5.3.3.7.6 | CEILING VOID (AB03-AB06 / C18-27) - CURVED AREA
14 | PROJECT.3.5.3.3.7.6.1 | SECONDARY STEEL SUPPORT INSTALLATION
14 | PROJECT.3.5.3.3.7.6.2 | CEILING VOID INSTALLATION
14 | PROJECT.3.5.3.3.7.6.5 | VOID - SECTION C (GRID A25 TO AB05) / MEP WORKS
16 | PROJECT.3.5.3.3.7.6.5.1 | ELECTRICAL
18 | PROJECT.3.5.3.3.7.6.5.1.1 | POWER & LIGHTING
20 | PROJECT.3.5.3.3.7.6.5.1.1.1 | FIRST FIX
20 | PROJECT.3.5.3.3.7.6.5.1.1.2 | SECOND FIX
20 | PROJECT.3.5.3.3.7.6.5.1.1.4 | THIRD FIX
20 | PROJECT.3.5.3.3.7.6.5.1.1.3 | FINAL FIX
18 | PROJECT.3.5.3.3.7.6.5.1.2 | LOW CURRENT
20 | PROJECT.3.5.3.3.7.6.5.1.2.2 | SECOND FIX
20 | PROJECT.3.5.3.3.7.6.5.1.2.3 | FINAL FIX
16 | PROJECT.3.5.3.3.7.6.5.3 | HVAC
18 | PROJECT.3.5.3.3.7.6.5.3.1 | FIRST FIX
18 | PROJECT.3.5.3.3.7.6.5.3.2 | SECOND FIX
18 | PROJECT.3.5.3.3.7.6.5.3.3 | FINAL FIX
16 | PROJECT.3.5.3.3.7.6.5.4 | FIREFIGHTING
18 | PROJECT.3.5.3.3.7.6.5.4.1 | FIRST FIX
18 | PROJECT.3.5.3.3.7.6.5.4.2 | SECOND FIX
18 | PROJECT.3.5.3.3.7.6.5.4.3 | FINAL FIX
12 | PROJECT.3.5.3.3.7.3 | COLD SIDE (AB03-AB06 / C18-27) - CURVED AREA
14 | PROJECT.3.5.3.3.7.3.5 | CEILING/SOFFIT & WALLS
14 | PROJECT.3.5.3.3.7.3.7 | INSULATION PANEL INSTALLATION- A25-END
14 | PROJECT.3.5.3.3.7.3.2 | REFERIGERATION /MEP WORKS
14 | PROJECT.3.5.3.3.7.3.1 | FLOOR AND RAMPS-SNOW MAKING WORKS
14 | PROJECT.3.5.3.3.7.3.3 | THEMING WORKS
14 | PROJECT.3.5.3.3.7.3.4 | RIDES
14 | PROJECT.3.5.3.3.7.3.6 | STAIRCASES (BASE BUILD) ST-01
8 | PROJECT.3.5.3.5 | NON-STRUCTURAL STEEL WORKS FOR THE RAMP
8 | PROJECT.3.5.3.1 | SPECIALTIES INSTALLATION
6 | PROJECT.3.5.6 | PRE- TESTING AND COMMISSIONING
8 | PROJECT.3.5.6.1 | Testing & Comissioning-mep
6 | PROJECT.3.5.7 | COMPLETION OF FIRST 500 mm OF SNOW
6 | PROJECT.3.5.4 | AUTHORITY APPROVALS
6 | PROJECT.3.5.5 | HANDING OVER
4 | PROJECT.3.6 | OTHER PROVISIONAL SUMS
6 | PROJECT.3.6.1 | CATEGORY A
8 | PROJECT.3.6.1.1 | PARKING GUIDANCE SYSTEM
10 | PROJECT.3.6.1.1.4 | SHOP DRAWINGS
10 | PROJECT.3.6.1.1.1 | MATERIAL SUBMITTAL
10 | PROJECT.3.6.1.1.2 | PROCUREMENT, FABRICATION AND DELIVERY
10 | PROJECT.3.6.1.1.3 | INSTALLATION
12 | PROJECT.3.6.1.1.3.1 | PGS Works - BP1
12 | PROJECT.3.6.1.1.3.2 | PGS Works - BP2
12 | PROJECT.3.6.1.1.3.3 | PGS Works - PP1
12 | PROJECT.3.6.1.1.3.4 | PGS Works - PP2
12 | PROJECT.3.6.1.1.3.5 | PGS Works - PP3
12 | PROJECT.3.6.1.1.3.6 | PSG Works - Server and Control Room, VMS Installation
12 | PROJECT.3.6.1.1.3.7 | Testing & Commissioning and Handover
8 | PROJECT.3.6.1.2 | DIGITAL SCREENS
8 | PROJECT.3.6.1.5 | PEDESTRIAN COUNTING SYSTEM
2 | PROJECT.4 | EXTERNAL WORKS
4 | PROJECT.4.3 | PROCUREMENT
6 | PROJECT.4.3.1 | SUBCONTRACTING
8 | PROJECT.4.3.1.PR | PREPARATION AND SUBMISSION
8 | PROJECT.4.3.1.APP | REVIEW AND APPROVALS
6 | PROJECT.4.3.2 | MATERIAL SUBMITTALS
8 | PROJECT.4.3.2.PREP | PREPARE AND SUBMIT
8 | PROJECT.4.3.2.Approv | REVIEW AND APPROVAL
6 | PROJECT.4.3.3 | ORDER, FABRICATION AND DELIVERY TO SITE
4 | PROJECT.4.2 | ENGINEERING
6 | PROJECT.4.2.1 | SHOP DRAWINGS
8 | PROJECT.4.2.1.1 | SUBMITTAL
8 | PROJECT.4.2.1.2 | APPROVAL
4 | PROJECT.4.1 | CONSTRUCTION
6 | PROJECT.4.1.7 | WEST ELEVATION- CAR PARK AREA AT GRADE
6 | PROJECT.4.1.4 | SOUTH ELEVATION
8 | PROJECT.4.1.4.4 | COMPLETION OF EXTERNAL STEPS/RAMPS/PRs/and ASSOCIATED STONE&BALUSTRADE WORKS
8 | PROJECT.4.1.4.1 | SOUTH WEST ( A01-A15)
8 | PROJECT.4.1.4.2 | SOUTH CENTRE ( A15-B05)
8 | PROJECT.4.1.4.3 | SOUTH EAST (B05- B24)
6 | PROJECT.4.1.1 | EAST ELEVATION
6 | PROJECT.4.1.2 | NORTH ELEVATION
8 | PROJECT.4.1.2.1 | NORTH WEST (A01-A19)
8 | PROJECT.4.1.2.2 | NORTH CENTRE ( A19-B06)
8 | PROJECT.4.1.2.3 | NORTH EAST ( B06- B28)
4 | PROJECT.4.4 | FINAL HAND OVER
2 | PROJECT.5 | INFRA-STRUCTURE
4 | PROJECT.5.1 | PROCUREMENT
6 | PROJECT.5.1.1 | SUBCONTRACTING
8 | PROJECT.5.1.1.PR | PREPARATION AND SUBMISSION
8 | PROJECT.5.1.1.APP | REVIEW AND APPROVALS
6 | PROJECT.5.1.2 | MATERIAL SELECTION ( ONLY FROM DAE)
8 | PROJECT.5.1.2.PREP | PREPARE AND SUBMIT
8 | PROJECT.5.1.2.Approv | REVIEW AND APPROVALS( DAE)
6 | PROJECT.5.1.4 | MATERIAL TO BE APPROVED FROM ENGINEER/ADM
8 | PROJECT.5.1.4.1 | SUBMISSION TO ENGINEER/ADM
8 | PROJECT.5.1.4.2 | APPROVAL FROM ENGINEER/ADM
6 | PROJECT.5.1.3 | ORDER, FABRICATION AND DELIVERY TO SITE
4 | PROJECT.5.2 | ENGINEERING AND NOCs
6 | PROJECT.5.2.1 | TRAFFIC MANAGEMENT PLAN AND NOCS
8 | PROJECT.5.2.1.SPI | FOR SHEET PILING INSTALLATION
10 | PROJECT.5.2.1.SPI.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.SPI.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.GI1 | FOR GEOTECHNICAL INVESTIGATION
10 | PROJECT.5.2.1.GI1.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.GI1.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.TRD | FOR TRUCK ROAD CLOSURE
10 | PROJECT.5.2.1.TRD.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.TRD.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.TR | FOR ELECTRICAL UTILITIES IN THE TEMPORARY ROAD
10 | PROJECT.5.2.1.TR.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.TR.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.TR2 | FOR OTHER UTILITIES (TELECOM, WATER, GAS AND IRRIGATION)
10 | PROJECT.5.2.1.TR2.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.TR2.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.TR21 | FOR OTHER UTILITIES (CCTV, SEWER, STORMWATER AND DISTRICT COOLING)
10 | PROJECT.5.2.1.TR21.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.TR21.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.PHBZ | CLOSURE OF LANE IN HAZA BIN ZAYED FOR PILING WORKS
10 | PROJECT.5.2.1.PHBZ.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.PHBZ.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.GANT | NARROWING OF HAZA BIN ZAYED TO INSTALL GANTRY
10 | PROJECT.5.2.1.GANT.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.GANT.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.RE | FOR ELECTRICAL UTILITIES ON ABDULLAH OMRAM TARYAM (ROAD E)
10 | PROJECT.5.2.1.RE.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.RE.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.RB | NOCS FOR ROADS AND BRIDGES
10 | PROJECT.5.2.1.RB.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.RB.2 | REVIEW AND APPROVALS
8 | PROJECT.5.2.1.216 | ITS DESIGN AND DESIGN OF INTERSECTIONS 212 AND 216, 235, 246
10 | PROJECT.5.2.1.216.1 | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.1.216.2 | REVIEW AND APPROVALS
6 | PROJECT.5.2.2 | PILE WORKS
8 | PROJECT.5.2.2.1 | PREPARATION AND SUBMISSION
8 | PROJECT.5.2.2.2 | REVIEW AND APPROVALS
6 | PROJECT.5.2.3 | GANTRY DESIGN
8 | PROJECT.5.2.3.SaA | PREPARATION AND SUBMISSION
8 | PROJECT.5.2.3.APP | REVIEW AND APPROVALS
6 | PROJECT.5.2.6 | RETAINING WALL
8 | PROJECT.5.2.6.1 | SHOP DRAWING SUBMISSION
10 | PROJECT.5.2.6.1.1 | SHOP DRAWING APPROVAL
6 | PROJECT.5.2.4 | BRIDGE STRUCTURAL DRAWINGS
8 | PROJECT.5.2.4.BRA1 | BRIDGE A1
10 | PROJECT.5.2.4.BRA1.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRA1.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRA2 | BRIDGE A2
10 | PROJECT.5.2.4.BRA2.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRA2.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRA3 | BRIDGE A3
10 | PROJECT.5.2.4.BRA3.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRA3.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRA4 | BRIDGE A4
10 | PROJECT.5.2.4.BRA4.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRA4.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRA5 | BRIDGE A5
10 | PROJECT.5.2.4.BRA5.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRA5.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRA6 | BRIDGE A6
10 | PROJECT.5.2.4.BRA6.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRA6.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRA7 | BRIDGE A7
10 | PROJECT.5.2.4.BRA7.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRA7.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRB1 | BRIDGE B1
10 | PROJECT.5.2.4.BRB1.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRB1.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRB2 | BRIDGE B2
10 | PROJECT.5.2.4.BRB2.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRB2.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRD1 | BRIDGE D1
10 | PROJECT.5.2.4.BRD1.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRD1.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRE1 | BRIDGE E1
10 | PROJECT.5.2.4.BRE1.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRE1.App | REVIEW AND APPROVALS
8 | PROJECT.5.2.4.BRF1 | BRIDGE F1
10 | PROJECT.5.2.4.BRF1.PaS | PREPARATION AND SUBMISSION
10 | PROJECT.5.2.4.BRF1.App | REVIEW AND APPROVALS
4 | PROJECT.5.3 | CONSTRUCTION
6 | PROJECT.5.3.1 | GI
6 | PROJECT.5.3.2 | TRUCK ROAD CLOSURE
6 | PROJECT.5.3.3 | SERVICE DIVERSION/PROTECTION
8 | PROJECT.5.3.3.1 | 11 kV Cable Rerouting
8 | PROJECT.5.3.3.2 | 22 kV Cable Rerouting/ Protection
8 | PROJECT.5.3.3.3 | 132 kV Cable Protection
10 | PROJECT.5.3.3.3.1 | Area 1 ( Bridge A6 P17 to P19) 65m
10 | PROJECT.5.3.3.3.2 | Area 2 ( Close to MSE- H) 70m
10 | PROJECT.5.3.3.3.3 | Area 3 ( Road H) 20 m
10 | PROJECT.5.3.3.3.4 | Area 4 ( Close to Road 5) 12 m
8 | PROJECT.5.3.3.OTHU | OTHER UTILITIES
8 | PROJECT.5.3.3.POWER1 | FINAL REROUTING FOR 22KV
6 | PROJECT.5.3.7 | TUNNEL B
6 | PROJECT.5.3.4 | TUNNEL C
6 | PROJECT.5.3.15 | BRIDGES
8 | PROJECT.5.3.15.1 | Bridge B1
10 | PROJECT.5.3.15.1.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.1.2 | Abutment & Piers
10 | PROJECT.5.3.15.1.3 | Deck Slab
10 | PROJECT.5.3.15.1.4 | Approaches
10 | PROJECT.5.3.15.1.5 | Deck Finishes
8 | PROJECT.5.3.15.5 | Bridge B2
10 | PROJECT.5.3.15.5.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.5.2 | Abutment & Piers
10 | PROJECT.5.3.15.5.3 | Deck Slab
10 | PROJECT.5.3.15.5.4 | Deck Finishes
8 | PROJECT.5.3.15.2 | Bridge A1
10 | PROJECT.5.3.15.2.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.2.2 | Abutment & Piers
10 | PROJECT.5.3.15.2.3 | Deck Slab
10 | PROJECT.5.3.15.2.4 | Approaches
10 | PROJECT.5.3.15.2.5 | Deck Finishes
8 | PROJECT.5.3.15.3 | Bridge A2
10 | PROJECT.5.3.15.3.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.3.2 | Piers
10 | PROJECT.5.3.15.3.3 | Deck Slab
10 | PROJECT.5.3.15.3.4 | Deck Finishes
8 | PROJECT.5.3.15.4 | Bridge D1
10 | PROJECT.5.3.15.4.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.4.2 | Abutment
10 | PROJECT.5.3.15.4.3 | Deck Slab
10 | PROJECT.5.3.15.4.4 | Deck Finishes
8 | PROJECT.5.3.15.6 | Bridge A3
10 | PROJECT.5.3.15.6.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.6.2 | Pier
10 | PROJECT.5.3.15.6.3 | Deck Slab
10 | PROJECT.5.3.15.6.4 | Deck Finishes
8 | PROJECT.5.3.15.7 | Bridge E1
10 | PROJECT.5.3.15.7.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.7.2 | Abutment
10 | PROJECT.5.3.15.7.3 | Deck Slab
10 | PROJECT.5.3.15.7.4 | Approaches
10 | PROJECT.5.3.15.7.5 | Deck Finishes
8 | PROJECT.5.3.15.8 | Bridge A4
10 | PROJECT.5.3.15.8.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.8.2 | Pier
10 | PROJECT.5.3.15.8.3 | Deck Slab
10 | PROJECT.5.3.15.8.4 | Deck Finishes
8 | PROJECT.5.3.15.9 | Bridge A5
10 | PROJECT.5.3.15.9.1 | Bridge A
12 | PROJECT.5.3.15.9.1.1 | Piling and Pile Cap
12 | PROJECT.5.3.15.9.1.2 | Pier
12 | PROJECT.5.3.15.9.1.3 | Deck Slab
10 | PROJECT.5.3.15.9.4 | Bridge B
12 | PROJECT.5.3.15.9.4.1 | Pile Cap
12 | PROJECT.5.3.15.9.4.2 | Pier
12 | PROJECT.5.3.15.9.4.3 | Deck Slab
10 | PROJECT.5.3.15.9.2 | Deck Finishes
8 | PROJECT.5.3.15.10 | Bridge A6
10 | PROJECT.5.3.15.10.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.10.2 | Abutment & Piers
10 | PROJECT.5.3.15.10.3 | Deck Slab
10 | PROJECT.5.3.15.10.4 | Approaches
10 | PROJECT.5.3.15.10.5 | Deck Finishes
8 | PROJECT.5.3.15.11 | Bridge F1
10 | PROJECT.5.3.15.11.1 | Piling and Pile Cap
10 | PROJECT.5.3.15.11.2 | Abutment
10 | PROJECT.5.3.15.11.3 | Deck Slab
10 | PROJECT.5.3.15.11.4 | Approaches
10 | PROJECT.5.3.15.11.5 | Deck Finishes
8 | PROJECT.5.3.15.12 | Bridge A7
10 | PROJECT.5.3.15.12.2 | Piling and Pile Cap
10 | PROJECT.5.3.15.12.3 | Piers
10 | PROJECT.5.3.15.12.1 | Deck Slab
10 | PROJECT.5.3.15.12.4 | Deck Finishes
6 | PROJECT.5.3.14 | RETAINING WALL
8 | PROJECT.5.3.14.2 | GENERAL - RETAINING WALL
8 | PROJECT.5.3.14.1 | Retaining Wall Parapets
6 | PROJECT.5.3.13 | MSE WALL & COPING BEAM
8 | PROJECT.5.3.13.1 | MSE-A1/A2
8 | PROJECT.5.3.13.2 | MSE-D1/D2
8 | PROJECT.5.3.13.3 | MSE-H1/H2
8 | PROJECT.5.3.13.4 | MSE-E1/B3
8 | PROJECT.5.3.13.5 | MSE-F1/F2
6 | PROJECT.5.3.8 | ROAD WORK
8 | PROJECT.5.3.8.4 | Other Utilities
8 | PROJECT.5.3.8.1 | ELEVATED ROAD
10 | PROJECT.5.3.8.1.1 | Road D Upto High road
10 | PROJECT.5.3.8.1.2 | Road- B -Exit Bridge- Up from Basement 2
10 | PROJECT.5.3.8.1.3 | Road E- Down from High Road to Basement 1
10 | PROJECT.5.3.8.1.4 | Road F
8 | PROJECT.5.3.8.2 | At Grade Road
10 | PROJECT.5.3.8.2.1 | Road C Works and Protection along NW side
10 | PROJECT.5.3.8.2.3 | Road E works and Protection A6,A7,A8, Mall to Juntion 235
10 | PROJECT.5.3.8.2.2 | Intersection
10 | PROJECT.5.3.8.2.6 | Traffic Signals
10 | PROJECT.5.3.8.2.4 | Road K ( SL Entrance- East) and Road L ( B1- Entrance South East) and Taxi Drop off - Bus Lay by
10 | PROJECT.5.3.8.2.5 | Road M ( B1-Exit South) and Road N (B1 Entrance- South West)
6 | PROJECT.5.3.9 | STORM WATER ( including Testing and Commissioning by IGJV)
6 | PROJECT.5.3.5 | INTERFACE/CONNECTION TO MALL
6 | PROJECT.5.3.10 | ACCESS TO NEARBY PLOTS
6 | PROJECT.5.3.6 | TESTING AND COMMISSIONING
4 | PROJECT.5.5 | FINAL HANDOVER OF INFRASTRUCTURE WORKS
6 | PROJECT.5.5.5 | AUTHORITY INSPECTION/APPROVAL-INFRA WORKS
6 | PROJECT.5.5.2 | FINAL SNAGGING-INFRA WORKS
6 | PROJECT.5.5.4 | AUTHORITY APPROVALS- INFRA ONLY
6 | PROJECT.5.5.1 | HANDOVER
2 | PROJECT.7 | MODIFICATION IN SMOKE MANAGEMENT SYSTEM
4 | PROJECT.7.1 | Preliminaries
4 | PROJECT.7.EI 171 | Smoke Extract for BOH Corridor- EI 171
6 | PROJECT.7.EI 171.ENG | Engineering & Procurement
8 | PROJECT.7.EI 171.ENG.6 | MEP services & equipments
10 | PROJECT.7.EI 171.ENG.6.4 | Engineering
10 | PROJECT.7.EI 171.ENG.6.5 | Procurement
12 | PROJECT.7.EI 171.ENG.6.5.1 | Ductwork Fabrication
8 | PROJECT.7.EI 171.ENG.3 | Structural Stability of Slab for Coring (Additonal Ventilation Shafts)
10 | PROJECT.7.EI 171.ENG.3.3 | Engineeing
12 | PROJECT.7.EI 171.ENG.3.3.1 | Preparation of Shop Drawings & Connection Design
12 | PROJECT.7.EI 171.ENG.3.3.2 | Phase 1
12 | PROJECT.7.EI 171.ENG.3.3.3 | Phase 2
10 | PROJECT.7.EI 171.ENG.3.1 | Procurement of Subcontractor
10 | PROJECT.7.EI 171.ENG.3.2 | Fabrication
12 | PROJECT.7.EI 171.ENG.3.2.1 | Phase 1
12 | PROJECT.7.EI 171.ENG.3.2.2 | Phase 2
6 | PROJECT.7.EI 171.CON | Construction
8 | PROJECT.7.EI 171.CON.GF | Ground Floor
10 | PROJECT.7.EI 171.CON.GF.1 | Zone 1
12 | PROJECT.7.EI 171.CON.GF.1.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.1.2 | Coring & Strengthening Works (L1- Correspond to GL)
12 | PROJECT.7.EI 171.CON.GF.1.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.1.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.2 | Zone 2
12 | PROJECT.7.EI 171.CON.GF.2.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.2.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.2.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.2.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.3 | Zone 3
12 | PROJECT.7.EI 171.CON.GF.3.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.3.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.3.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.3.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.4 | Zone 4
12 | PROJECT.7.EI 171.CON.GF.4.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.4.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.4.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.4.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.5 | Zone 5
12 | PROJECT.7.EI 171.CON.GF.5.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.5.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.5.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.5.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.6 | Zone 6
12 | PROJECT.7.EI 171.CON.GF.6.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.6.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.6.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.6.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.7 | Zone 7
12 | PROJECT.7.EI 171.CON.GF.7.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.7.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.7.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.7.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.8 | Zone 8
12 | PROJECT.7.EI 171.CON.GF.8.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.8.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.8.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.8.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.9 | Zone 9
12 | PROJECT.7.EI 171.CON.GF.9.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.9.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.9.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.9.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.10 | Zone 10
12 | PROJECT.7.EI 171.CON.GF.10.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.10.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.10.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.10.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.11 | Zone 11
12 | PROJECT.7.EI 171.CON.GF.11.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.11.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.11.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.11.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.12 | Zone 12
12 | PROJECT.7.EI 171.CON.GF.12.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.12.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.12.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.12.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.13 | Zone 13
12 | PROJECT.7.EI 171.CON.GF.13.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.13.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.13.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.13.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.14 | Zone 14
12 | PROJECT.7.EI 171.CON.GF.14.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.GF.14.2 | Coring & Strengthening Works (L1)
12 | PROJECT.7.EI 171.CON.GF.14.3 | Builders Works
12 | PROJECT.7.EI 171.CON.GF.14.4 | MEP
12 | PROJECT.7.EI 171.CON.GF.14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.GF.Gen | General
8 | PROJECT.7.EI 171.CON.L1 | Level- 01
10 | PROJECT.7.EI 171.CON.L1.Z1 | Zone 1
12 | PROJECT.7.EI 171.CON.L1.Z1.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z1.2 | Coring & Strengthening Works (L2- Correspond to L1)
12 | PROJECT.7.EI 171.CON.L1.Z1.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z1.4 | MEP Works
12 | PROJECT.7.EI 171.CON.L1.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z2 | Zone 2
12 | PROJECT.7.EI 171.CON.L1.Z2.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z2.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z2.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z2.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z3 | Zone 3
12 | PROJECT.7.EI 171.CON.L1.Z3.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z3.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z3.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z3.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z4 | Zone 4
12 | PROJECT.7.EI 171.CON.L1.Z4.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z4.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z4.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z4.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z5 | Zone 5
12 | PROJECT.7.EI 171.CON.L1.Z5.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z5.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z5.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z5.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z6 | Zone 6
12 | PROJECT.7.EI 171.CON.L1.Z6.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z6.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z6.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z6.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z7 | Zone 7
12 | PROJECT.7.EI 171.CON.L1.Z7.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z7.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z7.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z7.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z8 | Zone 8
12 | PROJECT.7.EI 171.CON.L1.Z8.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z8.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z8.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z8.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z9 | Zone 9
12 | PROJECT.7.EI 171.CON.L1.Z9.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z9.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z9.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z9.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z10 | Zone 10
12 | PROJECT.7.EI 171.CON.L1.Z10.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z10.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z10.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z10.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z11 | Zone 11
12 | PROJECT.7.EI 171.CON.L1.Z11.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z11.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z11.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z11.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z12 | Zone 12
12 | PROJECT.7.EI 171.CON.L1.Z12.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z12.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z12.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z12.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z13 | Zone 13
12 | PROJECT.7.EI 171.CON.L1.Z13.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z13.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z13.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z13.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Z14 | Zone 14
12 | PROJECT.7.EI 171.CON.L1.Z14.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L1.Z14.2 | Coring & Strengthening Works (L2)
12 | PROJECT.7.EI 171.CON.L1.Z14.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L1.Z14.4 | MEP
12 | PROJECT.7.EI 171.CON.L1.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L1.Gen | General
8 | PROJECT.7.EI 171.CON.L2 | Level- 02
10 | PROJECT.7.EI 171.CON.L2.Z1 | Zone 1
12 | PROJECT.7.EI 171.CON.L2.Z1.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z1.2 | Coring & Strengthening Works (L3- Correspond to L2)
12 | PROJECT.7.EI 171.CON.L2.Z1.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z1.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z2 | Zone 2
12 | PROJECT.7.EI 171.CON.L2.Z2.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z2.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z2.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z2.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z3 | Zone 3
12 | PROJECT.7.EI 171.CON.L2.Z3.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z3.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z3.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z3.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z4 | Zone 4
12 | PROJECT.7.EI 171.CON.L2.Z4.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z4.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z4.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z4.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z5 | Zone 5
12 | PROJECT.7.EI 171.CON.L2.Z5.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z5.2 | Coring & Strengthening Works (L3- Correspond to L2)
12 | PROJECT.7.EI 171.CON.L2.Z5.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z5.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z6 | Zone 6
12 | PROJECT.7.EI 171.CON.L2.Z6.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z6.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z6.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z6.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z7 | Zone 7
12 | PROJECT.7.EI 171.CON.L2.Z7.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z7.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z7.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z7.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z8 | Zone 8
12 | PROJECT.7.EI 171.CON.L2.Z8.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z8.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z8.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z8.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z9 | Zone 9
12 | PROJECT.7.EI 171.CON.L2.Z9.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z9.2 | Coring & Strengthening Works (L3- Correspond to L2/PP1)
12 | PROJECT.7.EI 171.CON.L2.Z9.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z9.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z10 | Zone 10
12 | PROJECT.7.EI 171.CON.L2.Z10.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z10.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z10.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z10.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z11 | Zone 11
12 | PROJECT.7.EI 171.CON.L2.Z11.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z11.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z11.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z11.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z12 | Zone 12
12 | PROJECT.7.EI 171.CON.L2.Z12.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z12.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z12.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z12.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z13 | Zone 13
12 | PROJECT.7.EI 171.CON.L2.Z13.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z13.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z13.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z13.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Z14 | Zone 14
12 | PROJECT.7.EI 171.CON.L2.Z14.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L2.Z14.2 | Coring & Strengthening Works (L3)
12 | PROJECT.7.EI 171.CON.L2.Z14.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L2.Z14.4 | MEP
12 | PROJECT.7.EI 171.CON.L2.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L2.Gen | General
8 | PROJECT.7.EI 171.CON.L3 | Level- 03
10 | PROJECT.7.EI 171.CON.L3.Z1 | Zone 1
12 | PROJECT.7.EI 171.CON.L3.Z1.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z1.2 | Coring & Strengthening Works (L4- Correspond to L3/PP2)
12 | PROJECT.7.EI 171.CON.L3.Z1.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z1.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z2 | Zone 2
12 | PROJECT.7.EI 171.CON.L3.Z2.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z2.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z2.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z2.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z3 | Zone 3
12 | PROJECT.7.EI 171.CON.L3.Z3.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z3.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z3.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z3.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z4 | Zone 4
12 | PROJECT.7.EI 171.CON.L3.Z4.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z4.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z4.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z4.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z5 | Zone 5
12 | PROJECT.7.EI 171.CON.L3.Z5.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z5.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z5.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z5.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z6 | Zone 6
12 | PROJECT.7.EI 171.CON.L3.Z6.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z6.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z6.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z6.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z7 | Zone 7
12 | PROJECT.7.EI 171.CON.L3.Z7.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z7.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z7.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z7.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z8 | Zone 8
12 | PROJECT.7.EI 171.CON.L3.Z8.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z8.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z8.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z8.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z9 | Zone 9
12 | PROJECT.7.EI 171.CON.L3.Z9.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z9.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z9.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z9.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z10 | Zone 10
12 | PROJECT.7.EI 171.CON.L3.Z10.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z10.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z10.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z10.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z11 | Zone 11
12 | PROJECT.7.EI 171.CON.L3.Z11.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z11.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z11.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z11.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z12 | Zone 12
12 | PROJECT.7.EI 171.CON.L3.Z12.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z12.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z12.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z12.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z13 | Zone 13
12 | PROJECT.7.EI 171.CON.L3.Z13.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z13.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z13.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z13.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Z14 | Zone 14
12 | PROJECT.7.EI 171.CON.L3.Z14.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L3.Z14.2 | Coring & Strengthening Works (L4)
12 | PROJECT.7.EI 171.CON.L3.Z14.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L3.Z14.4 | MEP
12 | PROJECT.7.EI 171.CON.L3.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L3.Gen | General
8 | PROJECT.7.EI 171.CON.L4 | Level- 04 / PP3
10 | PROJECT.7.EI 171.CON.L4.Z1 | Zone 1
12 | PROJECT.7.EI 171.CON.L4.Z1.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z1.2 | Coring & Strengthening Works (L5- Correspond to L4/PP3)
12 | PROJECT.7.EI 171.CON.L4.Z1.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z1.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z2 | Zone 2
12 | PROJECT.7.EI 171.CON.L4.Z2.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z2.2 | Coring & Strengthening Works (L5- Correspond to L4/PP3)
12 | PROJECT.7.EI 171.CON.L4.Z2.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z2.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z3 | Zone 3
12 | PROJECT.7.EI 171.CON.L4.Z3.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z3.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z3.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z3.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z4 | Zone 4
12 | PROJECT.7.EI 171.CON.L4.Z4.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z4.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z4.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z4.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z5 | Zone 5
12 | PROJECT.7.EI 171.CON.L4.Z5.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z5.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z5.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z5.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z6 | Zone 6
12 | PROJECT.7.EI 171.CON.L4.Z6.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z6.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z6.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z6.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z7 | Zone 7
12 | PROJECT.7.EI 171.CON.L4.Z7.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z7.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z7.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z7.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z8 | Zone 8
12 | PROJECT.7.EI 171.CON.L4.Z8.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z8.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z8.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z8.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z9 | Zone 9
12 | PROJECT.7.EI 171.CON.L4.Z9.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z9.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z9.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z9.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z10 | Zone 10
12 | PROJECT.7.EI 171.CON.L4.Z10.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z10.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z10.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z10.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z11 | Zone 11
12 | PROJECT.7.EI 171.CON.L4.Z11.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z11.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z11.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z11.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z12 | Zone 12
12 | PROJECT.7.EI 171.CON.L4.Z12.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z12.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z12.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z12.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z13 | Zone 13
12 | PROJECT.7.EI 171.CON.L4.Z13.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z13.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z13.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z13.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Z14 | Zone 14
12 | PROJECT.7.EI 171.CON.L4.Z14.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L4.Z14.2 | Coring & Strengthening Works (L5)
12 | PROJECT.7.EI 171.CON.L4.Z14.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L4.Z14.4 | MEP
12 | PROJECT.7.EI 171.CON.L4.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L4.Gen | General
8 | PROJECT.7.EI 171.CON.L5 | Level- 05 / PP4
10 | PROJECT.7.EI 171.CON.L5.Z1 | Zone 1
12 | PROJECT.7.EI 171.CON.L5.Z1.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z1.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z1.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z2 | Zone 2
12 | PROJECT.7.EI 171.CON.L5.Z2.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z2.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z2.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z3 | Zone 3
12 | PROJECT.7.EI 171.CON.L5.Z3.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z3.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z3.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z4 | Zone 4
12 | PROJECT.7.EI 171.CON.L5.Z4.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z4.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z4.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z5 | Zone 5
12 | PROJECT.7.EI 171.CON.L5.Z5.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z5.2 | Coring & Strengthening Works (RL- Correspond to L5/PP4)
12 | PROJECT.7.EI 171.CON.L5.Z5.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z5.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z6 | Zone 6
12 | PROJECT.7.EI 171.CON.L5.Z6.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z6.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z6.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z7 | Zone 7
12 | PROJECT.7.EI 171.CON.L5.Z7.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z7.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z7.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z8 | Zone 8
12 | PROJECT.7.EI 171.CON.L5.Z8.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z8.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z8.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z9 | Zone 9
12 | PROJECT.7.EI 171.CON.L5.Z9.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z9.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z9.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z10 | Zone 10
12 | PROJECT.7.EI 171.CON.L5.Z10.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z10.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z10.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z11 | Zone 11
12 | PROJECT.7.EI 171.CON.L5.Z11.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z11.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z11.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z12 | Zone 12
12 | PROJECT.7.EI 171.CON.L5.Z12.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z12.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z12.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z13 | Zone 13
12 | PROJECT.7.EI 171.CON.L5.Z13.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z13.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z13.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Z14 | Zone 14
12 | PROJECT.7.EI 171.CON.L5.Z14.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.L5.Z14.3 | Builders Works
12 | PROJECT.7.EI 171.CON.L5.Z14.4 | MEP
12 | PROJECT.7.EI 171.CON.L5.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.L5.Gen | General
8 | PROJECT.7.EI 171.CON.RL | Roof level
10 | PROJECT.7.EI 171.CON.RL.Z5 | Zone 5
12 | PROJECT.7.EI 171.CON.RL.Z5.1 | Abortive Works
12 | PROJECT.7.EI 171.CON.RL.Z5.3 | Builders Works
12 | PROJECT.7.EI 171.CON.RL.Z5.4 | MEP
12 | PROJECT.7.EI 171.CON.RL.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 171.CON.RL.Z8 | Zone 8
10 | PROJECT.7.EI 171.CON.RL.Z11 | Zone 11
12 | PROJECT.7.EI 171.CON.RL.Z11.3 | Builders Works
10 | PROJECT.7.EI 171.CON.RL.Gen | General
6 | PROJECT.7.EI 171.T&C | Testing & Commissioning
8 | PROJECT.7.EI 171.T&C.1 | Pre-commissioning
8 | PROJECT.7.EI 171.T&C.2 | Final testing & commissioning
4 | PROJECT.7.EI 178 | Lifts Pressurization Fans - EI 178
6 | PROJECT.7.EI 178.ENG | Engineering & Procurement
8 | PROJECT.7.EI 178.ENG.6 | MEP services & equipments
10 | PROJECT.7.EI 178.ENG.6.4 | Engineering
10 | PROJECT.7.EI 178.ENG.6.5 | Procurement
8 | PROJECT.7.EI 178.ENG.3 | Structural Stability of Slab for Coring (Additonal Ventilation Shafts)
10 | PROJECT.7.EI 178.ENG.3.3 | Engineeing
12 | PROJECT.7.EI 178.ENG.3.3.1 | Preparation of Shop Drawings & Connection Design
10 | PROJECT.7.EI 178.ENG.3.1 | Procurement of Subcontractor
10 | PROJECT.7.EI 178.ENG.3.2 | Fabrication
6 | PROJECT.7.EI 178.CON | Construction
8 | PROJECT.7.EI 178.CON.1 | Basement-02
10 | PROJECT.7.EI 178.CON.1.Z1 | Zone 1
12 | PROJECT.7.EI 178.CON.1.Z1.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z1.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z1.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z1.4 | MEP Works
12 | PROJECT.7.EI 178.CON.1.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z2 | Zone 2
12 | PROJECT.7.EI 178.CON.1.Z2.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z2.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z2.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z2.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z3 | Zone 3
12 | PROJECT.7.EI 178.CON.1.Z3.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z3.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z3.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z3.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z4 | Zone 4
12 | PROJECT.7.EI 178.CON.1.Z4.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z4.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z4.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z4.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z5 | Zone 5
12 | PROJECT.7.EI 178.CON.1.Z5.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z5.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z5.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z5.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z6 | Zone 6
12 | PROJECT.7.EI 178.CON.1.Z6.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z6.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z6.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z6.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z7 | Zone 7
12 | PROJECT.7.EI 178.CON.1.Z7.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z7.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z7.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z7.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z8 | Zone 8
12 | PROJECT.7.EI 178.CON.1.Z8.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z8.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z8.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z8.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z9 | Zone 9
12 | PROJECT.7.EI 178.CON.1.Z9.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z9.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z9.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z9.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z10 | Zone 10
12 | PROJECT.7.EI 178.CON.1.Z10.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z10.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z10.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z10.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z11 | Zone 11
12 | PROJECT.7.EI 178.CON.1.Z11.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z11.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z11.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z11.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z12 | Zone 12
12 | PROJECT.7.EI 178.CON.1.Z12.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z12.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z12.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z12.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z13 | Zone 13
12 | PROJECT.7.EI 178.CON.1.Z13.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z13.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z13.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z13.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.Z14 | Zone 14
12 | PROJECT.7.EI 178.CON.1.Z14.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.1.Z14.2 | Coring Works
12 | PROJECT.7.EI 178.CON.1.Z14.3 | Builders Works
12 | PROJECT.7.EI 178.CON.1.Z14.4 | MEP
12 | PROJECT.7.EI 178.CON.1.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.1.6 | General
8 | PROJECT.7.EI 178.CON.2 | Basement-01
10 | PROJECT.7.EI 178.CON.2.Z1 | Zone 1
12 | PROJECT.7.EI 178.CON.2.Z1.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z1.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z1.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z1.4 | MEP Works
12 | PROJECT.7.EI 178.CON.2.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z2 | Zone 2
12 | PROJECT.7.EI 178.CON.2.Z2.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z2.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z2.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z2.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z3 | Zone 3
12 | PROJECT.7.EI 178.CON.2.Z3.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z3.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z3.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z3.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z4 | Zone 4
12 | PROJECT.7.EI 178.CON.2.Z4.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z4.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z4.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z4.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z5 | Zone 5
12 | PROJECT.7.EI 178.CON.2.Z5.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z5.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z5.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z5.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z6 | Zone 6
12 | PROJECT.7.EI 178.CON.2.Z6.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z6.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z6.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z6.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z7 | Zone 7
12 | PROJECT.7.EI 178.CON.2.Z7.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z7.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z7.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z7.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z8 | Zone 8
12 | PROJECT.7.EI 178.CON.2.Z8.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z8.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z8.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z8.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z9 | Zone 9
12 | PROJECT.7.EI 178.CON.2.Z9.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z9.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z9.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z9.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z10 | Zone 10
12 | PROJECT.7.EI 178.CON.2.Z10.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z10.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z10.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z10.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z11 | Zone 11
12 | PROJECT.7.EI 178.CON.2.Z11.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z11.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z11.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z11.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z12 | Zone 12
12 | PROJECT.7.EI 178.CON.2.Z12.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z12.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z12.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z12.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z13 | Zone 13
12 | PROJECT.7.EI 178.CON.2.Z13.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z13.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z13.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z13.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.Z14 | Zone 14
12 | PROJECT.7.EI 178.CON.2.Z14.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.2.Z14.2 | Coring Works
12 | PROJECT.7.EI 178.CON.2.Z14.3 | Builders Works
12 | PROJECT.7.EI 178.CON.2.Z14.4 | MEP
12 | PROJECT.7.EI 178.CON.2.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.2.6 | General
8 | PROJECT.7.EI 178.CON.3 | Ground Floor
10 | PROJECT.7.EI 178.CON.3.Z1 | Zone 1
12 | PROJECT.7.EI 178.CON.3.Z1.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z1.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z1.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z1.4 | MEP Works
12 | PROJECT.7.EI 178.CON.3.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z2 | Zone 2
12 | PROJECT.7.EI 178.CON.3.Z2.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z2.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z2.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z2.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z3 | Zone 3
12 | PROJECT.7.EI 178.CON.3.Z3.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z3.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z3.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z3.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z4 | Zone 4
12 | PROJECT.7.EI 178.CON.3.Z4.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z4.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z4.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z4.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z5 | Zone 5
12 | PROJECT.7.EI 178.CON.3.Z5.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z5.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z5.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z5.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z6 | Zone 6
12 | PROJECT.7.EI 178.CON.3.Z6.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z6.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z6.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z6.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z7 | Zone 7
12 | PROJECT.7.EI 178.CON.3.Z7.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z7.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z7.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z7.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z8 | Zone 8
12 | PROJECT.7.EI 178.CON.3.Z8.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z8.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z8.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z8.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z9 | Zone 9
12 | PROJECT.7.EI 178.CON.3.Z9.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z9.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z9.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z9.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z10 | Zone 10
12 | PROJECT.7.EI 178.CON.3.Z10.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z10.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z10.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z10.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z11 | Zone 11
12 | PROJECT.7.EI 178.CON.3.Z11.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z11.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z11.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z11.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z12 | Zone 12
12 | PROJECT.7.EI 178.CON.3.Z12.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z12.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z12.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z12.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z13 | Zone 13
12 | PROJECT.7.EI 178.CON.3.Z13.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z13.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z13.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z13.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.Z14 | Zone 14
12 | PROJECT.7.EI 178.CON.3.Z14.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.3.Z14.2 | Coring Works
12 | PROJECT.7.EI 178.CON.3.Z14.3 | Builders Works
12 | PROJECT.7.EI 178.CON.3.Z14.4 | MEP
12 | PROJECT.7.EI 178.CON.3.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.3.6 | General
8 | PROJECT.7.EI 178.CON.4 | Level- 01
10 | PROJECT.7.EI 178.CON.4.Z1 | Zone 1
12 | PROJECT.7.EI 178.CON.4.Z1.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z1.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z1.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z1.4 | MEP Works
12 | PROJECT.7.EI 178.CON.4.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z2 | Zone 2
12 | PROJECT.7.EI 178.CON.4.Z2.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z2.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z2.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z2.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z3 | Zone 3
12 | PROJECT.7.EI 178.CON.4.Z3.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z3.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z3.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z3.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z4 | Zone 4
12 | PROJECT.7.EI 178.CON.4.Z4.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z4.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z4.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z4.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z5 | Zone 5
12 | PROJECT.7.EI 178.CON.4.Z5.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z5.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z5.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z5.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z6 | Zone 6
12 | PROJECT.7.EI 178.CON.4.Z6.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z6.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z6.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z6.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z7 | Zone 7
12 | PROJECT.7.EI 178.CON.4.Z7.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z7.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z7.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z7.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z8 | Zone 8
12 | PROJECT.7.EI 178.CON.4.Z8.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z8.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z8.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z8.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z9 | Zone 9
12 | PROJECT.7.EI 178.CON.4.Z9.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z9.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z9.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z9.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z10 | Zone 10
12 | PROJECT.7.EI 178.CON.4.Z10.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z10.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z10.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z10.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z11 | Zone 11
12 | PROJECT.7.EI 178.CON.4.Z11.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z11.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z11.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z11.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z12 | Zone 12
12 | PROJECT.7.EI 178.CON.4.Z12.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z12.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z12.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z12.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z13 | Zone 13
12 | PROJECT.7.EI 178.CON.4.Z13.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z13.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z13.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z13.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.Z14 | Zone 14
12 | PROJECT.7.EI 178.CON.4.Z14.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.4.Z14.2 | Coring Works
12 | PROJECT.7.EI 178.CON.4.Z14.3 | Builders Works
12 | PROJECT.7.EI 178.CON.4.Z14.4 | MEP
12 | PROJECT.7.EI 178.CON.4.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.4.6 | General
8 | PROJECT.7.EI 178.CON.5 | Level- 02
10 | PROJECT.7.EI 178.CON.5.Z1 | Zone 1
12 | PROJECT.7.EI 178.CON.5.Z1.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z1.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z1.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z1.4 | MEP Works
12 | PROJECT.7.EI 178.CON.5.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z2 | Zone 2
12 | PROJECT.7.EI 178.CON.5.Z2.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z2.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z2.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z2.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z3 | Zone 3
12 | PROJECT.7.EI 178.CON.5.Z3.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z3.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z3.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z3.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z4 | Zone 4
12 | PROJECT.7.EI 178.CON.5.Z4.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z4.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z4.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z4.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z5 | Zone 5
12 | PROJECT.7.EI 178.CON.5.Z5.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z5.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z5.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z5.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z6 | Zone 6
12 | PROJECT.7.EI 178.CON.5.Z6.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z6.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z6.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z6.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z7 | Zone 7
12 | PROJECT.7.EI 178.CON.5.Z7.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z7.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z7.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z7.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z8 | Zone 8
12 | PROJECT.7.EI 178.CON.5.Z8.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z8.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z8.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z8.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z9 | Zone 9
12 | PROJECT.7.EI 178.CON.5.Z9.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z9.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z9.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z9.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z10 | Zone 10
12 | PROJECT.7.EI 178.CON.5.Z10.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z10.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z10.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z10.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z11 | Zone 11
12 | PROJECT.7.EI 178.CON.5.Z11.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z11.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z11.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z11.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z12 | Zone 12
12 | PROJECT.7.EI 178.CON.5.Z12.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z12.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z12.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z12.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z13 | Zone 13
12 | PROJECT.7.EI 178.CON.5.Z13.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z13.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z13.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z13.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.Z14 | Zone 14
12 | PROJECT.7.EI 178.CON.5.Z14.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.5.Z14.2 | Coring Works
12 | PROJECT.7.EI 178.CON.5.Z14.3 | Builders Works
12 | PROJECT.7.EI 178.CON.5.Z14.4 | MEP
12 | PROJECT.7.EI 178.CON.5.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.5.6 | General
8 | PROJECT.7.EI 178.CON.6 | Level- 03
10 | PROJECT.7.EI 178.CON.6.Z1 | Zone 1
12 | PROJECT.7.EI 178.CON.6.Z1.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z1.2 | Coring Works
12 | PROJECT.7.EI 178.CON.6.Z1.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z1.4 | MEP Works
12 | PROJECT.7.EI 178.CON.6.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z2 | Zone 2
12 | PROJECT.7.EI 178.CON.6.Z2.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z2.2 | Coring Works (L4 slab openings - Correspond to L3 )
12 | PROJECT.7.EI 178.CON.6.Z2.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z2.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z3 | Zone 3
12 | PROJECT.7.EI 178.CON.6.Z3.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z3.2 | Coring Works
12 | PROJECT.7.EI 178.CON.6.Z3.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z3.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z4 | Zone 4
12 | PROJECT.7.EI 178.CON.6.Z4.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z4.2 | Coring Works (L4 slab openings - Correspond to L3 )
12 | PROJECT.7.EI 178.CON.6.Z4.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z4.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z5 | Zone 5
12 | PROJECT.7.EI 178.CON.6.Z5.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z5.2 | Coring Works
12 | PROJECT.7.EI 178.CON.6.Z5.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z5.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z6 | Zone 6
12 | PROJECT.7.EI 178.CON.6.Z6.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z6.2 | Coring Works (L4 slab openings - Correspond to L3 )
12 | PROJECT.7.EI 178.CON.6.Z6.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z6.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z7 | Zone 7
12 | PROJECT.7.EI 178.CON.6.Z7.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z7.2 | Coring Works (L4 slab openings - Correspond to L3 )
12 | PROJECT.7.EI 178.CON.6.Z7.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z7.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z8 | Zone 8
12 | PROJECT.7.EI 178.CON.6.Z8.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z8.2 | Coring Works (L4 slab openings - Correspond to L3 )
12 | PROJECT.7.EI 178.CON.6.Z8.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z8.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z9 | Zone 9
12 | PROJECT.7.EI 178.CON.6.Z9.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z9.2 | Coring Works
12 | PROJECT.7.EI 178.CON.6.Z9.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z9.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z10 | Zone 10
12 | PROJECT.7.EI 178.CON.6.Z10.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z10.2 | Coring Works
12 | PROJECT.7.EI 178.CON.6.Z10.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z10.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z11 | Zone 11
12 | PROJECT.7.EI 178.CON.6.Z11.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z11.2 | Coring Works
12 | PROJECT.7.EI 178.CON.6.Z11.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z11.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z12 | Zone 12
12 | PROJECT.7.EI 178.CON.6.Z12.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z12.2 | Coring Works
12 | PROJECT.7.EI 178.CON.6.Z12.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z12.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z13 | Zone 13
12 | PROJECT.7.EI 178.CON.6.Z13.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z13.2 | Coring Works
12 | PROJECT.7.EI 178.CON.6.Z13.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z13.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.Z14 | Zone 14
12 | PROJECT.7.EI 178.CON.6.Z14.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.6.Z14.2 | Coring Works
12 | PROJECT.7.EI 178.CON.6.Z14.3 | Builders Works
12 | PROJECT.7.EI 178.CON.6.Z14.4 | MEP
12 | PROJECT.7.EI 178.CON.6.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.6.6 | General
8 | PROJECT.7.EI 178.CON.7 | Level- 04 / PP3
10 | PROJECT.7.EI 178.CON.7.Z1 | Zone 1
12 | PROJECT.7.EI 178.CON.7.Z1.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z1.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z1.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z1.4 | MEP Works
12 | PROJECT.7.EI 178.CON.7.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z2 | Zone 2
12 | PROJECT.7.EI 178.CON.7.Z2.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z2.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z2.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z2.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z3 | Zone 3
12 | PROJECT.7.EI 178.CON.7.Z3.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z3.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z3.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z3.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z4 | Zone 4
12 | PROJECT.7.EI 178.CON.7.Z4.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z4.2 | Coring Works (L5 slab openings - Correspond to L4 )
12 | PROJECT.7.EI 178.CON.7.Z4.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z4.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z5 | Zone 5
12 | PROJECT.7.EI 178.CON.7.Z5.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z5.2 | Coring Works (L5 slab openings - Correspond to L4 )
12 | PROJECT.7.EI 178.CON.7.Z5.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z5.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z6 | Zone 6
12 | PROJECT.7.EI 178.CON.7.Z6.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z6.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z6.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z6.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z7 | Zone 7
12 | PROJECT.7.EI 178.CON.7.Z7.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z7.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z7.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z7.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z8 | Zone 8
12 | PROJECT.7.EI 178.CON.7.Z8.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z8.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z8.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z8.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z9 | Zone 9
12 | PROJECT.7.EI 178.CON.7.Z9.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z9.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z9.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z9.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z10 | Zone 10
12 | PROJECT.7.EI 178.CON.7.Z10.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z10.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z10.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z10.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z11 | Zone 11
12 | PROJECT.7.EI 178.CON.7.Z11.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z11.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z11.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z11.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z12 | Zone 12
12 | PROJECT.7.EI 178.CON.7.Z12.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z12.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z12.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z12.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z13 | Zone 13
12 | PROJECT.7.EI 178.CON.7.Z13.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z13.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z13.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z13.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.Z14 | Zone 14
12 | PROJECT.7.EI 178.CON.7.Z14.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.7.Z14.2 | Coring Works
12 | PROJECT.7.EI 178.CON.7.Z14.3 | Builders Works
12 | PROJECT.7.EI 178.CON.7.Z14.4 | MEP
12 | PROJECT.7.EI 178.CON.7.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.7.6 | General
8 | PROJECT.7.EI 178.CON.8 | Level- 05 / PP4
10 | PROJECT.7.EI 178.CON.8.Z1 | Zone 1
12 | PROJECT.7.EI 178.CON.8.Z1.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z1.2 | Coring Works (RL slab openings - Correspond to L5 )
12 | PROJECT.7.EI 178.CON.8.Z1.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z1.4 | MEP Works
12 | PROJECT.7.EI 178.CON.8.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z2 | Zone 2
12 | PROJECT.7.EI 178.CON.8.Z2.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z2.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z2.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z2.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z3 | Zone 3
12 | PROJECT.7.EI 178.CON.8.Z3.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z3.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z3.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z3.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z4 | Zone 4
12 | PROJECT.7.EI 178.CON.8.Z4.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z4.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z4.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z4.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z5 | Zone 5
12 | PROJECT.7.EI 178.CON.8.Z5.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z5.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z5.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z5.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z6 | Zone 6
12 | PROJECT.7.EI 178.CON.8.Z6.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z6.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z6.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z6.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z7 | Zone 7
12 | PROJECT.7.EI 178.CON.8.Z7.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z7.2 | Coring Works (RL slab openings - Correspond to L5 )
12 | PROJECT.7.EI 178.CON.8.Z7.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z7.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z8 | Zone 8
12 | PROJECT.7.EI 178.CON.8.Z8.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z8.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z8.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z8.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z9 | Zone 9
12 | PROJECT.7.EI 178.CON.8.Z9.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z9.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z9.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z9.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z10 | Zone 10
12 | PROJECT.7.EI 178.CON.8.Z10.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z10.2 | Coring Works (RL slab openings - Correspond to L5 )
12 | PROJECT.7.EI 178.CON.8.Z10.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z10.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z11 | Zone 11
12 | PROJECT.7.EI 178.CON.8.Z11.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z11.2 | Coring Works (RL slab openings - Correspond to L5 )
12 | PROJECT.7.EI 178.CON.8.Z11.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z11.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z12 | Zone 12
12 | PROJECT.7.EI 178.CON.8.Z12.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z12.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z12.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z12.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z13 | Zone 13
12 | PROJECT.7.EI 178.CON.8.Z13.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z13.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z13.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z13.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.Z14 | Zone 14
12 | PROJECT.7.EI 178.CON.8.Z14.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.8.Z14.2 | Coring Works
12 | PROJECT.7.EI 178.CON.8.Z14.3 | Builders Works
12 | PROJECT.7.EI 178.CON.8.Z14.4 | MEP
12 | PROJECT.7.EI 178.CON.8.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.8.6 | General
8 | PROJECT.7.EI 178.CON.9 | Roof level
10 | PROJECT.7.EI 178.CON.9.Z1 | Zone 1
12 | PROJECT.7.EI 178.CON.9.Z1.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z1.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z1.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z1.4 | MEP Works
12 | PROJECT.7.EI 178.CON.9.Z1.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z2 | Zone 2
12 | PROJECT.7.EI 178.CON.9.Z2.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z2.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z2.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z2.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z2.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z3 | Zone 3
12 | PROJECT.7.EI 178.CON.9.Z3.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z3.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z3.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z3.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z3.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z4 | Zone 4
12 | PROJECT.7.EI 178.CON.9.Z4.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z4.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z4.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z4.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z4.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z5 | Zone 5
12 | PROJECT.7.EI 178.CON.9.Z5.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z5.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z5.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z5.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z5.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z6 | Zone 6
12 | PROJECT.7.EI 178.CON.9.Z6.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z6.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z6.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z6.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z6.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z7 | Zone 7
12 | PROJECT.7.EI 178.CON.9.Z7.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z7.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z7.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z7.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z7.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z8 | Zone 8
12 | PROJECT.7.EI 178.CON.9.Z8.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z8.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z8.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z8.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z8.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z9 | Zone 9
12 | PROJECT.7.EI 178.CON.9.Z9.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z9.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z9.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z9.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z9.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z10 | Zone 10
12 | PROJECT.7.EI 178.CON.9.Z10.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z10.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z10.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z10.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z10.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z11 | Zone 11
12 | PROJECT.7.EI 178.CON.9.Z11.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z11.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z11.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z11.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z11.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z12 | Zone 12
12 | PROJECT.7.EI 178.CON.9.Z12.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z12.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z12.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z12.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z12.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z13 | Zone 13
12 | PROJECT.7.EI 178.CON.9.Z13.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z13.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z13.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z13.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z13.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.Z14 | Zone 14
12 | PROJECT.7.EI 178.CON.9.Z14.1 | Abortive Works
12 | PROJECT.7.EI 178.CON.9.Z14.2 | Coring Works
12 | PROJECT.7.EI 178.CON.9.Z14.3 | Builders Works
12 | PROJECT.7.EI 178.CON.9.Z14.4 | MEP
12 | PROJECT.7.EI 178.CON.9.Z14.5 | Reinstatement Works- After coring
10 | PROJECT.7.EI 178.CON.9.6 | General
6 | PROJECT.7.EI 178.1 | Testing & Commissioning
8 | PROJECT.7.EI 178.1.1 | Precommissioning
8 | PROJECT.7.EI 178.1.2 | Final Testing & Commissioning
2 | PROJECT.6 | FINAL WORKS
4 | PROJECT.6.1 | FINAL SNAGGING AND CLEANING-MALL WORKS
4 | PROJECT.6.3 | CONNECTION TO MAIN
6 | PROJECT.6.3.1 | STATUTORY AUTHORITY APPROVAL FEES
6 | PROJECT.6.3.2 | CONNECTION TO MAIN
4 | PROJECT.6.4 | BCC AND POWER ON-MALL
6 | PROJECT.6.4.1 | MALL
6 | PROJECT.6.4.2 | SNOW PARK
4 | PROJECT.6.6 | HANDING OVER DOCUMENTATION