## Data
Factory | Cluster | Project name | Project Code | Status | Category 1 | Category 2 | Project Lead | OAS | OAS Expected raise date | Planned Date | LV Date | Depreciation Years | Project Budget | Spent End PY | Part Capitalized PY | Comments | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Current AIC | Current Delayed | Delay month | Delay months bucket
Chartres | Health Relief | Ana Sui - new transparent formula for Veet CWS | CHA-PL20-001 | Submitted | Capability(NPD/EPD) |  | Antoine BAUDICHON | 57867 | 2019-07-08 | 2019-12-31 | 2020-02-29 | 0 | 30 | 10 | 5 | document received on 05/03/20. Capex will be closed in March vs February | 2 | 4 | 6 | [9 empty] | 17 | Yes | 2 | 0 to 2 Months delayed
Chartres | Health Relief | Warehouse management system to improve warehouse efficiency in Chartres (Cost avoidance project with new internal audit requirements) | CHA-PL20-002 | In Progress | Infrastructure | IS/IT | Anabel CRUCES | 60814 | 2019-07-26 | 2020-03-30 | 2020-09-30 | 0 | 44 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Chartres | Health Relief | Zadie 50ml | CHA-PL20-003 | Commissioned | Efficiency | Cost Saving-Project Good(X-Trim/Squeeze) | Antoine BAUDICHON | 18918 |  | 2019-06-30 | 2019-11-30 | 0 | 12 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Chartres | Health Relief | Quality Capex 2019 | CHA-PL20-004 | In Progress | Quality | Compliance | Antoine BAUDICHON | 48745 | 2019-04-18 | 2019-11-30 | 2020-06-30 | 0 | 67 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | Yes | 3 | 3 to 6 months delayed
Chartres | Health Relief | HSE 2019 | CHA-PL20-005 | Submitted | Employee Safety | People | Marion INGRAO | 45238 | 2019-03-08 | 2019-12-31 | 2020-03-31 | 0 | 88 | 10 | 5 | last action need better weather conditions to be implemented | 2 | 4 | 6 | [9 empty] | 17 | Yes | 2 | 0 to 2 Months delayed
Chartres | Health Relief | Veet Obsolescence Capex | CHA-PL20-006 | Closed | Obsolescence | Productivity | Abde SIOUD | 52860 | 2019-04-30 | 2019-12-31 | 2019-12-15 | 0 | 45 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Chartres | Health Relief | Obsolescence Skin Care Area | CHA-PL20-007 | Commissioned | Obsolescence | Productivity | Martin | 46060 | 2019-03-21 | 2019-12-31 | 2020-04-30 | 0 | 33 | 10 | 5 | No line stop until W10 for PW loop cleaning | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Chartres | Health Relief | Inga 75 ml | CHA-PL20-008 | In Progress | Capability(NPD/EPD) | Cost Saving-Project Good(X-Trim/Squeeze) | Martin | 59397 | 2019-06-27 | 2020-03-30 | 2020-06-30 | 0 | 23 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Chartres | Health Relief | Compliance Capex | CHA-PL20-009 | In Progress | Infrastructure | Compliance | Martin | 85285 | 2019-10-18 | 2020-03-30 | 2020-09-30 | 0 | 45 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Chartres | Health Relief | Hull Labeller | CHA-PL20-010 | In Progress | Efficiency | Productivity | Martin | 70960 | 2019-10-04 | 2020-03-30 | 2020-04-30 | 0 | 5 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Chartres | Health Relief | Water Rejects recover on Purified Water installation | CHA-PL20-011 | Submitted | Infrastructure | Environment | Martin | 56222 | 2019-05-20 | 2019-11-30 | 2020-05-31 | 0 | 12 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | Yes | 3 | 3 to 6 months delayed
Chartres | Health Relief | Energy Savings - LED light changes + Doors to creating heat buffering zones | CHA-PL20-012 | Commissioned | Infrastructure | Environment | Martin | 52858 | 2019-04-18 | 2019-11-30 | 2020-03-31 | 0 | 22 | 10 | 5 | Last modification done | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Chartres | Health Relief | Steam Circuits Rewamping on COS2 process + safety amendments on Veet 2 | CHA-PL20-013 | Closed | Obsolescence | Maintenance | Martin | 48741 | 2019-04-04 | 2019-10-30 | 2020-09-30 | 0 | 333 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Chartres | Health Relief | Factory Social Infrastructure Renovation | CHA-PL20-014 | Closed | Infrastructure | Environment | Martin | 59465 | 2019-06-28 | 2019-12-31 | 2020-05-30 | 0 | 654 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Chartres | Health Relief | Phoenix phase 2 | CHA-PL20-015 | Closed | Infrastructure | IS/IT | Martin | 76929 | 2019-11-20 | 2019-12-31 | 2019-11-30 | 0 | 24 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Qingdao | Wellness&Personal | (In 2020PLan) - NPD - Ghost 2 for 5m Grs capacity | QIN-PL20-001 | Approved | Capability(NPD/EPD) | Productivity | Martin | S92520 | 2019-12-01 | 2021-03-01 | 2021-03-01 | 8 | 99 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Qingdao | Wellness&Personal | (In 2020PLan) - EPD - Condom orientation roll-out Phase2 (29 sets) | QIN-PL20-002 | Not Submitted | Capability(NPD/EPD) | Productivity | Martin | N202003 | 2020-01-01 | 2021-06-01 | 2021-06-01 | 8 | 886 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Qingdao | Wellness&Personal | (In 2019 plan) - NPD - Project Ghost - Condom Transparency | QIN-PL20-003 | Commissioned | Capability(NPD/EPD) | Productivity | Martin | S35112 | 2018-12-02 | 2020-10-01 | 2020-10-01 | 10.1 | 33 | 10 | 5 | Due to finish in Oct 20. | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Qingdao | Wellness&Personal | (In 2020PLan) - EFF - ET Autoloader Roll Out | QIN-PL20-004 | Submitted | Efficiency | Cost Saving-Project Good(X-Trim/Squeeze) | Martin | N202010 | 2019-12-01 | 2020-11-01 | 2020-11-01 | 8 | 67 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Manila | IFCN | PRODUCTION: Project Lightyear | PHI-PL20-001 | Not Submitted | Efficiency |  | Martin |  | 2020-02-29 | 2020-12-31 | 2021-05-31 | 8 | 88 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Manila | IFCN | MFG: ACF and Tamper Evidence | PHI-PL20-002 | In Progress | Capability(NPD/EPD) |  | Martin | C3PHS19008 |  | 2020-12-31 | 2021-01-31 | 5 | 45 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Manila | IFCN | Compressor for Process Line | PHI-PL20-003 | In Progress |  | Maintenance | Martin | C3PHS19006 |  | 2020-05-31 | 2020-05-31 | 10 | 33 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Manila | IFCN | QMP: HPR Phase 2 (Locker Separation) | PHI-PL20-004 | Commissioned | Quality |  | Martin | C3PHS19022 |  | 2020-02-29 | 2020-02-29 | 10 | 23 | 10 | 5 | Retention Fee to be capitalized in Feb | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Manila | IFCN | EHS: In-line case weigher for BIB4 (July SPIN CAPA capex) | PHI-PL20-005 | In Progress | Employee Safety |  | Martin | C3PHS19017 |  | 2020-03-31 | 2020-03-31 | 5 | 45 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Evansville | IFCN | QP - RO Water Upgrade | EVV-FC220-001 | In Progress | Quality | Compliance | Martin | 27061 |  | 2020-07-01 | 2020-07-01 | 8 | 5 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | No | 0 | -
Evansville | IFCN | QP 2019 Liquids Floor & Drain Replacement | EVV-FC220-002 | Closed | Quality | Compliance | Martin | 39303 |  | 2020-01-01 | 2020-03-01 | 20 | 12 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 0 | No | 0 | -
Evansville | IFCN | V211 Remediation | EVV-FC220-003 | In Progress | Quality | Compliance | Martin | 50578 |  | 2019-12-01 | 2020-04-01 | 8 | 22 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | Yes | 3 | 3 to 6 months delayed
Evansville | IFCN | Liquids Freight Elevator Upgrades | EVV-FC220-004 | In Progress | Infrastructure | Maintenance | Martin | 16614 |  | 2020-02-01 | 2020-04-01 | 20 | 4 | 10 | 5 |  | 2 | 4 | 6 | [9 empty] | 17 | Yes | 1 | 0 to 2 Months delayed

## Mapping for calculation
2020-03-01
Summary
0 to 2 Months delayed
3 to 6 months delayed
7 to 9 months delayed
10 to 12 months delayed
Over 1 year

## Sheet1 (hidden)
NMG-PL18-051 | Nijmegen CIP Kitchen Improvements | #N/A | #N/A
NMG-PL20-003 | Replacement of cos phi installation | #N/A | #N/A
NMG-PL20-004 | Revision Ammonia Compressor Chilled Water | #N/A | #N/A
NMG-PL20-005 | Plastic pallets (FM-approved) voor alle stelling locaties | #N/A | #N/A
NMG-PL20-006 | C1NSC16065 Upgrade SDB-2 | #N/A | #N/A
NMG-PL20-007 | Restoration work sewarage (proceswater, vwa, hwa) | #N/A | #N/A
NMG-PL20-008 | Upgrade waste water installation | #N/A | #N/A
NMG-PL20-009 | Laboratory Equipment | #N/A | #N/A
NMG-PL20-010 | Phasing out of low caloric gas to high caloric gas | #N/A | #N/A
NMG-PL20-011 | Sewer | #N/A | #N/A
NMG-PL20-012 | Replace guard house | #N/A | #N/A
NMG-PL20-014 | Replace HOVAP valves | #N/A | #N/A
NMG-PL20-015 | Sewer | #N/A | #N/A
NMG-PL20-016 | Replace Kemutec sifter | #N/A | #N/A
NMG-PL20-017 | Reservation Improvement CAPEX | #N/A | #N/A
NMG-PL20-021 | Manifold upgrades ( MSS 210 en MSS218,213,214,223 en MSS 204S en MSS203 ) | #N/A | #N/A
NMG-PL20-022 | Automatic seam monitoring | #N/A | #N/A
NMG-PL20-023 | Canteen 2.0 | #N/A | #N/A
NMG-PL19-001 | C1NSC19001 SAMR Upgrade HVAC NMDB | #N/A | #N/A
NMG-PL20-025 | Risk Assessement points 2017 | #N/A | #N/A
NMG-PL20-026 | Upgrade oil/glucose reception | #N/A | #N/A
NMG-PL20-027 | C1NSC19021 QP Compliancy Zoning BIB | #N/A | #N/A
NMG-PL20-028 | Rovema Clampshell system | #N/A | #N/A
NMG-PL20-029 | C1NSC17007 Process Water Supply Network | #N/A | #N/A
NMG-PL20-030 | Waste management (inside and out) | #N/A | #N/A
NMG-PL20-031 | Upgrade of Security Management Platform | #N/A | #N/A
NMG-PL20-032 | Follow-up of rejection points from various input points (Scios and NEN) | #N/A | #N/A
NMG-PL20-033 | Uniformity emergency stop buttons | #N/A | #N/A
NMG-PL20-034 | Uniformity status signals (lightbeacon) | #N/A | #N/A
NMG-PL20-035 | Inspection system laserprint | #N/A | #N/A
NMG-PL20-036 | Stairs to access patio area's (roofaccess) | #N/A | #N/A
NMG-PL20-500 | Reservation Improvement CAPEX | #N/A | #N/A
NMG-PL16-165 | C1NSC16165 QMP Tower Roof Fouling SDB | #N/A | #N/A
NMG-PL19-061 | New spray drying capability | #N/A | #N/A
NMG-PL19-017 | Laboratory Equipment | #N/A | #N/A
NMG-PL15-018 | C1NSC15018 Spray Dryer Projects | #N/A | #N/A
NMG-PL19-058 | C1NSC17005 400g Can Capability Canning Line 2 | #N/A | #N/A
NMG-PL17-007 | C1NSC17007 Process Water Supply Network | #N/A | #N/A
NMG-PL17-092 | Spring Flip Top capability CL3 | #N/A | #N/A
NMG-PL18-001 | SCIOS - NEN 3140 Remediation | #N/A | #N/A
NMG-PL18-002 | CFDA Upgrade Premix | #N/A | #N/A
NMG-PL18-033 | Roof support frame LBK | #N/A | #N/A
NMG-PL18-049 | Optimize Scholastic supply Filler CL2-3 | #N/A | #N/A
NMG-PL18-052 | SiSi | #N/A | #N/A
NMG-PL18-063 | CCTV System | #N/A | #N/A
NMG-PL19-005 | IT Compliance Internal Audit eWeighing | #N/A | #N/A
NMG-PL19-007 | CIP Valves Glucose Tank | #N/A | #N/A
NMG-PL19-042 | Replace Alpine Sieve | #N/A | #N/A
NMG-PL19-044 | Premix sprinkler above ceiling | #N/A | #N/A
NMG-PL19-047 | Pest Control | #N/A | #N/A
NMG-PL19-049 | CFDA Zoning CL1 | #N/A | #N/A
NMG-PL19-050 | CFDA Zoning BBFA | #N/A | #N/A
NMG-PL19-051 | CFDA Zoning DB3CL2 | #N/A | #N/A
NMG-PL19-052 | CFDA Zoning DB4CL3 | #N/A | #N/A
NMG-PL19-053 | CFDA Zoning DB1 | #N/A | #N/A
NMG-PL19-055 | Phoenix - FOM | #N/A | #N/A
NMG-PL19-057 | CIP Valves Mix Tanks | #N/A | #N/A
NMG-PL19-900 | Inprocess control DB4CL3 | #N/A | #N/A
NMG-PL19-902 | Mini Sifters | #N/A | #N/A
NMG-PL19-907 | Replacement Hoists | #N/A | #N/A
NMG-PL19-908 | Safe Walkway Warehouse Phase 1 | #N/A | #N/A
NMG-PL19-997 | LV Fliptop 3th mold | #N/A | #N/A
NMG-PL20-002 | Barcode Inspection - BIB Carton | #N/A | #N/A
NMG-PL20-111 | Other Projects | #N/A | #N/A
NMG-PL15-043 | Upgrade SD 2 (PLC-SCADA-Batch) | #N/A | #N/A
NMG-PL16-040 | Replace CO detection SDA | #N/A | #N/A
NMG-PL16-045 | Inline Printing | #N/A | #N/A
NMG-PL16-095 | Flip Top capping upgrade | #N/A | #N/A
NMG-PL16-195 | CL2 Spring to Launch | #N/A | #N/A
NMG-PL17-018 | QMP Artwork CCP | #N/A | #N/A
NMG-PL19-001 | CFDA Upgrade HVAC NMDB | #N/A | #N/A
NMG-PL19-021 | QP Compliancy Zoning BIB | #N/A | #N/A
NMG-PL20-XXX | PUMP | #N/A | #N/A
NMG-PL20-XXX | Shaped Can CL3 | #N/A | #N/A

## 2021-2022 (hidden)
| LV FY NY | LV FY NY +1 | Factory | Currency | Project code
Baddi (BADDI-HE) | 1210000 | 725000
Mysore (MYSORE) | 2268593.4771 | 1740000
AMESA (HR) | 3478593.4771 | 2465000
Chartres (CHARTRES) | 5371000.3507 | 5633000
Hull (HULL) | 23917000 | 18525000
Nottingham (NOTTINGH) | 15071000 | 10375000
Weinheim (WEINHEIM) | 1334157.461 | 1793942.6751
Europe (HR) | 45693157.8117 | 36326942.6751
Tlalpan (TLALPAN-HR) | 7119303.2058 | 4202680.1788
LATAM (HR) | 7119303.2058 | 4202680.1788
Salt Lake City (SALT_LAK) | 9536000.1566 | 9665000
North America (HR) | 9536000.1566 | 9665000
Health Relief | 65827054.6512 | 52659622.854
Bahrain (BAHRAIN) | 0 | 0
Bangladesh (BANGLADE) | 0 | 0
Irungattukottai - Footcare (IRUNGATT) | 0 | 0
Karachi (KARACHI) | 284999.7019 | 1023998.929
Nigeria (NIGERIA) | 0 | 0
South Africa (SOUTH_AF) | 0 | 0
Uttaranchal (UTTARANC) | 9200020.4718 | 2000004.4504
West/Central Budget | 27000060.0802 | 0
AMESA (WPH) | 36485080.2539 | 3024003.3794
Cileungsi (CILEUNGS) | 6728918.3003 | 11868092.1581
Bangkapong (BANGKAPO) | 10633187.7234 | 5120090.3925
Bangplee (BANGPLEE) | 7130125.8786 | 3600063.5572
ASEAN (WPH) | 24492231.9023 | 20588246.1079
Qingdao (QINGDAO) | 9402238.6282 | 0
Shashi (SHASHI) | 0 | 0
Guilong (GUILONG) | 0 | 0
Taicang (TAICANG) | 24005715.6466 | 15003572.2791
GREATER CHINA (WPH) | 33407954.2748 | 15003572.2791
Wellness&amp;Personal Hygiene | 94385266.431 | 38615821.7664
Chonburi (CHONBURI) | 9000158.8931 | 0
Manila (MANILA) | 0 | 0
Tuas (TUAS) | 0 | 0
ASEAN (IFCN) | 9000158.8931 | 0
Derrimut (DERRIMUT) | 0 | 0
Guangzhou (GUANGZHO) | 0 | 0
Nijmegen (NIJMEGEN) | 76368805.8916 | 90952130.4577
Tatura (TATURA) | 0 | 0
IFCN GREATER CHINA (IFCN) | 76368805.8916 | 90952130.4577
Delicias (DELICIAS) | 0 | 0
Sao Paulo (SAO_PAUL) | 0 | 0
LATAM (IFCN) | 0 | 0
Evansville (EVANSVIL) | 15037593.985 | 42105263.1579
Zeeland (ZEELAND) | 59749373.4336 | 21453634.0852
US HQ | 0 | 0
North America (IFCN) | 74786967.4185 | 63558897.2431
IFCN central budget | 0 | 0
IFCN Central Budget | 0 | 0
IFCN | 160155932.2033 | 154511027.7008
X-Seed Quality | 4000000 | 0
X-Seed OPS Model | 2000000 | 0
X-Seed IS | 3700000 | 2700000
X-Seed MFG Productivity | 9000000 | 4000000
X-Seed Supply Services | 2000000 | 1000000
X-Seed | 20700000 | 7700000
X-Seed | 20700000 | 7700000
Health BU | 341068253.2855 | 253486472.3211